## Summary
SUBWAY Final Bill NT
Sr No. | Final | PO Amount without GST | Certified Amount without GST | Remarks
PO Amount
1 | Final Bill | 324420 | 324420
| Total | 324420 | 324420
| 18% | 58395.6 | 58395.6
| Total With GST | 382815.6 | 382815.6

## Abstract
PRICE COMPARATIVE Final
PROJECT: SUBWAY, LUCKNOW AIRPORT - TERMINAL-T3 |  |  |  |  | Qty. |  |  | Remarks
SR. NO. | ITEM DESCRIPTION | UOM | QTY. | UNIT RATE | Previous bill | This bill | Up To Date | Remarks
| SUPPLY OF BTU METER MAKE - BELIMO | Nos | 1 | 50500 |  | 50500 | 50500
| ITC - CHILLED WATER UNIT 2.0 TR | Nos | 1 | 5000 |  | 5000 | 5000
| SITC - MOTORISED VALVE WITH THERMOSTATE, fitted in return chw line to control room temperature and chw water. | Nos | 1 | 13600 |  | 13600 | 13600
| SITC - CHILLED WATER PIPE WITH TUBE INSULATION WITH ALL | MTR | 11.6 | 1450 |  | 16820 | 16820
| SITC - CPVC PIPE WITH 6 MM THICK TUBE INST | MTR | 2.5 | 300 |  | 750 | 750
| SITC - 2 PRESSURE GAUGE, 2 THERMOMETER, 2 BALL VALVE, AIR VENT AND Y STRAINER WITH ALL MS FITTING | SET | 1 | 12250 |  | 12250 | 12250
| SITC - CANVAS CONNECTION OF AHU | Nos | 1 | 1900 |  | 1900 | 1900
| SITC - GSS DUCT / INSULATION / GRILL Gss Duct - galvanized sheet steel and Aluminum ac Grill | SET | 1 | 16500 |  | 16500 | 16500
| ITC - BTU METER INSTALLATION | SET | 1 | 5500 |  | 5500 | 5500
| SITC - THRMOWELL & FITTINGS FOR BTU METER, Thermowall is connected to the main chw line in which the temperature meter of Btu meter is installed. | SET | 1 | 7500 |  | 7500 | 7500
| ITC - ADITIONAL WATER LINE TESTING | Nos | 1 | 5000 |  | 5000 | 5000
| MACHINE TRANSPORTATION from chennai | Nos | 1 | 3500 |  | 3500 | 3500
| Fire rated CEILLING - 15 mm thick Gypsteel ULTRA stud CEILLING which includes ONE layers of tapered edge 15 mm thk Gypboard Fireline (Conforming to IS 26095 Part 1:2011) fixed to either side of 50 mm Gypsteel ULTRA C Stud AND Ceiling Channel are anchored to the f6loor and ceiling using suitable anchor fasteners at 600 c/c in zigzag manner. 15 mm thk Gyproc Fireline board strip of 45 mm width is placed between ceiling channel and ceiling slab to improve fire performance of the system. PATTI and channel are crimped together using crimpi6ng tool. A Gypsteel ULTRA Noggin channel of 45 mm width (0.5 mm thk having two flanges of 40 mm each) has to be provided at the horizontal joints of the two boards screw fixed to the studs using Gyproc metal to metal flat head screws. The boards are to be fixed to the framework with joints staggered to avoid leakage through joints with Gyproc CEILLING screws of 25mm and 35mm at 600 mm C/C at the center and 300 mm C/C at periphery of board. Finally square and tapered edges of the boards are to be joined and finished so as to have a flush look which includes filling and finishing with Gyproc Jointing Compound, Gyproc Joint Paper tape (as per recommended practices of Saint- Gobain Gyproc India). The Junction of theCEILLING with masonry and all penetration through the CEILLING has to be treated with a fire GYPROCK FILLING | SFT | 310 | 160 |  | 49600 | 49600
| ELECTRIC METER | NOS | 1 | 8500 |  | 8500 | 8500
| TESTING OF FS AND HVAC | Nos | 1 | 15000 |  | 15000 | 15000
| Providing and fixing of hollow metal fire rated doors SIZE 2000 X 2400 as per IS 3614 part-1 & part-2 for stability and integrity. Pressed Galvanized steel confirming to IS 277 with the following specification. Recommended fire door shall have doors tested at CBRI or ARAI for maximum rating of 2hrs. Test certificates should be available for vision lites /panels as part of the fire door assembly. Door frame shall be double rebate profile of size 143 x 57 mm made out of 1.60mm (16 gauge) minimum thick galvanized steel sheet. Frames shall be Mitered and field assembled with self tabs. All provision should be mortised, drilled and tapped for receiving appropriate hardware. Rubber door silencers should be provided on the striking jamb. Frames should be provided with back plate bracket and anchor fasteners for installation on a finished plastered masonry wall opening. Once frame installed should be grouted with cement & sand slurry necessary for fire doors on the clear masonry opening. Door leaf shall be 46mm thick fully flush double skin door with or without vision lite. Door leaf shall be manufactured from 1.2mm (18guage) minimum thick galvanised steel sheet. The internal construction of the door should be rigid reinforcement pads for receiving appropriate hardware. The infill material shall be resin bonded honeycomb core. All doors shall be factory prepped for receiving appropriate hardware and provided with necessary reinforcement for hinges, locks, and door closers. The edges should be interlocked with a bending radius of 1.4mm. For pair of doors astragals has to be provided on the meeting stile for both active and inactive leaf. Vision lite wherever applicable should be provided as per manufacturers recommendation with a beeding and screws from inside. All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. With Iron Pull Handle and Double lock provision. | Nos | 1 | 49000 |  | 49000 | 49000
| P/F OF MOTOR PIPE VALUVE ETC INCLUDING ALL FITTING | NOS | 1 | 63500 |  | 63500 | 63500
| GRAND TOTAL |  |  |  |  | 324420 | 324420

## MB Sheet
VARIATION STATEMENT
SR NO | SERVICE NO | ITEM DESCRIPTION | UNIT | RATE | QTY | AMOUNT
CIVIL AND INTERIOR
Boq Item no-
| 1 | SUPPLY OF BTU METER MAKE - BELIMO | Nos | 50500 | 1 | 50500
| 2 | ITC - CHILLED WATER UNIT 2.0 TR | Nos | 5000 | 1 | 5000
| 3 | SITC - MOTORISED VALVE WITH THERMOSTATE, fitted in return chw line to control room temperature and chw water. | Nos | 13600 | 1 | 13600
| 4 | SITC - CHILLED WATER PIPE WITH TUBE INSULATION WITH ALL | MTR | 1450 | 11.6 | 16820
| 5 | SITC - CPVC PIPE WITH 6 MM THICK TUBE INST | MTR | 300 | 2.5 | 750
| 6 | SITC - 2 PRESSURE GAUGE, 2 THERMOMETER, 2 BALL VALVE, AIR VENT AND Y STRAINER WITH ALL MS FITTING | SET | 12250 | 1 | 12250
| 7 | SITC - CANVAS CONNECTION OF AHU | Nos | 1900 | 1 | 1900
| 8 | SITC - GSS DUCT / INSULATION / GRILL Gss Duct - galvanized sheet steel and Aluminum ac Grill | SET | 16500 | 1 | 16500
| 9 | ITC - BTU METER INSTALLATION | SET | 5500 | 1 | 5500
| 10 | SITC - THRMOWELL & FITTINGS FOR BTU METER, Thermowall is connected to the main chw line in which the temperature meter of Btu meter is installed. | SET | 7500 | 1 | 7500
| 11 | ITC - ADITIONAL WATER LINE TESTING | Nos | 5000 | 1 | 5000
| 12 | MACHINE TRANSPORTATION from chennai | Nos | 3500 | 1 | 3500
| 13 | Fire rated CEILLING - 15 mm thick Gypsteel ULTRA stud CEILLING which includes ONE layers of tapered edge 15 mm thk Gypboard Fireline (Conforming to IS 26095 Part 1:2011) fixed to either side of 50 mm Gypsteel ULTRA C Stud AND Ceiling Channel are anchored to the f6loor and ceiling using suitable anchor fasteners at 600 c/c in zigzag manner. 15 mm thk Gyproc Fireline board strip of 45 mm width is placed between ceiling channel and ceiling slab to improve fire performance of the system. PATTI and channel are crimped together using crimpi6ng tool. A Gypsteel ULTRA Noggin channel of 45 mm width (0.5 mm thk having two flanges of 40 mm each) has to be provided at the horizontal joints of the two boards screw fixed to the studs using Gyproc metal to metal flat head screws. The boards are to be fixed to the framework with joints staggered to avoid leakage through joints with Gyproc CEILLING screws of 25mm and 35mm at 600 mm C/C at the center and 300 mm C/C at periphery of board. Finally square and tapered edges of the boards are to be joined and finished so as to have a flush look which includes filling and finishing with Gyproc Jointing Compound, Gyproc Joint Paper tape (as per recommended practices of Saint- Gobain Gyproc India). The Junction of theCEILLING with masonry and all penetration through the CEILLING has to be treated with a fire GYPROCK FILLING | SFT | 160 | 310 | 49600
| 14 | ELECTRIC METER | NOS | 8500 | 1 | 8500
| 15 | TESTING OF FS AND HVAC | Nos | 15000 | 1 | 15000
| 16 | Providing and fixing of hollow metal fire rated doors SIZE 2000 X 2400 as per IS 3614 part-1 & part-2 for stability and integrity. Pressed Galvanized steel confirming to IS 277 with the following specification. Recommended fire door shall have doors tested at CBRI or ARAI for maximum rating of 2hrs. Test certificates should be available for vision lites /panels as part of the fire door assembly. Door frame shall be double rebate profile of size 143 x 57 mm made out of 1.60mm (16 gauge) minimum thick galvanized steel sheet. Frames shall be Mitered and field assembled with self tabs. All provision should be mortised, drilled and tapped for receiving appropriate hardware. Rubber door silencers should be provided on the striking jamb. Frames should be provided with back plate bracket and anchor fasteners for installation on a finished plastered masonry wall opening. Once frame installed should be grouted with cement & sand slurry necessary for fire doors on the clear masonry opening. Door leaf shall be 46mm thick fully flush double skin door with or without vision lite. Door leaf shall be manufactured from 1.2mm (18guage) minimum thick galvanised steel sheet. The internal construction of the door should be rigid reinforcement pads for receiving appropriate hardware. The infill material shall be resin bonded honeycomb core. All doors shall be factory prepped for receiving appropriate hardware and provided with necessary reinforcement for hinges, locks, and door closers. The edges should be interlocked with a bending radius of 1.4mm. For pair of doors astragals has to be provided on the meeting stile for both active and inactive leaf. Vision lite wherever applicable should be provided as per manufacturers recommendation with a beeding and screws from inside. All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. With Iron Pull Handle and Double lock provision. | Nos | 49000 | 1 | 49000
|  | P/F OF MOTOR PIPE VALUVE ETC INCLUDING ALL FITTING | NOS | 63500 | 1 | 63500
0
|  | TOTAL AMOUNT |  |  |  | 324420