## Summary Sheet
AHM_Domino's _NT Items_Final Bill_28.11.2024
S.N | Item Description | PO Amount | Billed Amount
PO | Semolina/PO/24-25/001402
1 | NT ITEMS
a | Fabrication | 113850 | 113850
b | Electrical | 331231 | 331231
c | Plumbing | 129214 | 129214
d | Finishes | 122028.3 | 122028.3
e | Fire Sprinkler | 76500 | 76500
f | Façade | 59256.5 | 59256.5
g | Mis | 127670 | 127670
h | HVAC | 363534 | 363534
2 | TOTAL | 1323283.8 | 1323283.8
3 | GST 18 % | 238191.084 | 238191.084
4 | G. TOTAL | 1561474.884 | 1561474.884

## Abstarct
AHM_DOMINO'S _NT ITEMS |  | PO - Semolina/PO/24-25/001402 |  |  |  | FINAL BILL
Sr No. | Item Description | UOM | Qty | Unit Price | Amount | Qty | Amount
A | Fabrication |  |  |  | 113850 |  | 113850
1 | MS Stand for cold room and AC outdoor unit size 4x6x2 Ft | Nos | 4 | 12750 | 51000 | 4 | 51000
2 | Manager Room M. S frame lifting station with ply and cladded with SS 304 - 2.5x1.6x2 Ft | Nos | 1 | 17750 | 17750 | 1 | 17750
3 | Entry lifting station with ply and SS palte - 0.5x0.75x0.6m | Nos | 1 | 13750 | 13750 | 1 | 13750
4 | S.S Pole hanging from Ceiling | RFT | 9 | 2150 | 19350 | 9 | 19350
5 | Front Counter M.S Frame Work - 6X1.5M | SQM | 9 | 850 | 7650 | 9 | 7650
6 | Microwave Oven Self with MS Stand - 2X1.5fT | SQF | 3 | 1450 | 4350 | 3 | 4350
B | Electrical |  |  |  | 331231 |  | 331231
7 | 2 Pole MCB 32A With Box | Nos | 4 | 3600 | 14400 | 4 | 14400
8 | 63A RCBO 4 Pole | Nos | 1 | 6250 | 6250 | 1 | 6250
9 | 16 A Switch Board 3 module | Nos | 1 | 1150 | 1150 | 1 | 1150
10 | Gang Box 16 A Switch Board 6 module | Nos | 3 | 2275 | 6825 | 3 | 6825
11 | Rubber Mat 1.1 KV ( Supply plus Installation ) - 2x1 Mtr | Nos | 1 | 3850 | 3850 | 1 | 3850
12 | Main LT Panel ( As per Site Requirement plus SLD) ) | Nos | 1 | 298756 | 298756 | 1 | 298756
C | Plumbing |  |  |  | 129214 |  | 129214
13 | MOP sink tap and RO Tap ( Supply plus Installation ) | Nos | 1 | 7890 | 7890 | 1 | 7890
14 | Mop sink connection complete ( Supply plus Installation ) | Nos | 1 | 1975 | 1975 | 1 | 1975
15 | Chamber ( Supply plus Installation ) - 300x300mm | Nos | 1 | 5578 | 5578 | 1 | 5578
16 | S. S Grating ( Supply plus Installation ) - 300x300mm | Set | 2 | 2598 | 5196 | 2 | 5196
17 | R.O Stand above ceiling with ms pipe with Ply base ( Supply plus Installation ) - 4x4 ft | Set | 1 | 15000 | 15000 | 1 | 15000
18 | 100 LPH RO Plant (Supply & Installation) | Set | 1 | 93575 | 93575 | 1 | 93575
D | Finishes |  |  |  | 122028.3 |  | 122028.3
19 | S.S Profile near counter entrance | RFT | 7 | 450 | 3150 | 7 | 3150
20 | TV Stand With MS Framing plus Ply - 1.25x8.5 ft | SQF | 11 | 1450 | 15950 | 11 | 15950
21 | L- Shape gypsum Ceiling with Ply base support | SQF | 120 | 510 | 61200 | 120 | 61200
22 | Supply and installation kota stone floor cold room - 2.6x1.9 Mtr | SQF | 53.15 | 450 | 23917.5 | 53.15 | 23917.5
23 | Supply and installation kota stone skirting 100mm H cold room | Mtr | 8.4 | 225 | 1890 | 8.4 | 1890
24 | Supply and installation ACP sheet packing for above hood 100mm H | RFT | 22 | 410 | 9020 | 22 | 9020
25 | Ply panelling side counter - 1.25x1.35 Mtr | SQF | 18.16 | 380 | 6900.8 | 18.16 | 6900.8
E | Fire Sprinkler |  |  |  | 76500 |  | 76500
26 | Supply and installation sprinkler with accessories and re-work of existing sprinkler | Nos | 6 | 8500 | 51000 | 6 | 51000
27 | Supply and installation Site of sprinkler rossettle plate | Nos | 6 | 950 | 5700 | 6 | 5700
28 | Supply and installation Site of UL listed approved corrugeted sheet SS 304 | Nos | 6 | 3300 | 19800 | 6 | 19800
F | Façade |  |  |  | 59256.5 |  | 59256.5
29 | Supply and installation corian for counter façade drop | Rmt | 8 | 4200 | 33600 | 8 | 33600
30 | 12 mm toughned Glass | SQF | 22.31 | 1150 | 25656.5 | 22.31 | 25656.5
G | Mis |  |  |  | 127670 |  | 127670
31 | Ply with laminate panelling over DB panel | SQF | 11.3 | 650 | 7345 | 11.3 | 7345
32 | Hood MS structure/ pipe support for hanging | Nos | 1 | 7500 | 7500 | 1 | 7500
33 | Mop Hanger | Nos | 1 | 950 | 950 | 1 | 950
34 | Supply and installation anti scratch tap | Nos | 1 | 1250 | 1250 | 1 | 1250
35 | Supply and installation wall boxing for ac | Nos | 4 | 2700 | 10800 | 4 | 10800
36 | Supply and installation chain 1.5 mtr | Nos | 2 | 1250 | 2500 | 2 | 2500
37 | Supply and installation panelling above cold room - 7'x1'-6" | SQF | 10.5 | 450 | 4725 | 10.5 | 4725
38 | Supply and installation corian above counter - 2x5 | SQF | 10 | 2150 | 21500 | 10 | 21500
39 | Supply and installation MS support for Gas meter | Nos | 1 | 3600 | 3600 | 1 | 3600
40 | Supply of pvc strip curtain for Conveyor oven- size 20x7 FT ht | SQF | 140 | 275 | 38500 | 140 | 38500
41 | Equipment installation | Nos | 1 | 20000 | 20000 | 1 | 20000
42 | Supply and installation soap dispenser _ Uronics | Nos | 1 | 7500 | 7500 | 1 | 7500
43 | Supply of Tissue paper holder | Nos | 1 | 1500 | 1500 | 1 | 1500
H | HVAC |  |  |  | 363534 |  | 363534
44 | Supply Installation, Testing and Commissioning of Split AC 1.8 TR - Daikin | Nos | 3 | 55789 | 167367 | 3 | 167367
45 | Supply Installation, Testing and Commissioning of Split AC 1.5 TR - Daikin | Nos | 1 | 43587 | 43587 | 1 | 43587
46 | 6.4 mm OD Soft Copper ( Insulation-9 mm ) | RM | 14 | 625 | 8750 | 14 | 8750
47 | 9.5 mm OD Soft Copper ( Insulation-9 mm ) | RM | 52 | 785 | 40820 | 52 | 40820
48 | 12.7 mm OD Soft Copper ( Insulation-9 mm | RM | 14 | 985 | 13790 | 14 | 13790
49 | 15.9 mm OD Soft Copper ( Insulation- 9 mm ) | RM | 52 | 1185 | 61620 | 52 | 61620
50 | Cable 4 Core 2.5 Sqmm | RM | 80 | 345 | 27600 | 80 | 27600

## JMR
AHM_DOMINO'S _NT ITEMS |  | Semolina/PO/24-25/001402 |  | JMR
Sr No. | Item Description | UOM | Qty | Qty
A | Fabrication
1 | MS Stand for cold room and AC outdoor unit size 4x6x2 Ft | Nos | 4 | 4
2 | Manager Room M. S frame lifting station with ply and cladded with SS 304 - 2.5x1.6x2 Ft | Nos | 1 | 1
3 | Entry lifting station with ply and SS palte - 0.5x0.75x0.6m | Nos | 1 | 1
4 | S.S Pole hanging from Ceiling | RFT | 9 | 9
5 | Front Counter M.S Frame Work - 6X1.5M | SQM | 9 | 9
6 | Microwave Oven Self with MS Stand - 2X1.5fT | SQF | 3 | 3
B | Electrical
7 | 2 Pole MCB 32A With Box | Nos | 4 | 4
8 | 63A RCBO 4 Pole | Nos | 1 | 1
9 | 16 A Switch Board 3 module | Nos | 1 | 1
10 | Gang Box 16 A Switch Board 6 module | Nos | 3 | 3
11 | Rubber Mat 1.1 KV ( Supply plus Installation ) - 2x1 Mtr | Nos | 1 | 1
12 | Main LT Panel ( As per Site Requirement plus SLD) ) | Nos | 1 | 1
C | Plumbing
13 | MOP sink tap and RO Tap ( Supply plus Installation ) | Nos | 1 | 1
14 | Mop sink connection complete ( Supply plus Installation ) | Nos | 1 | 1
15 | Chamber ( Supply plus Installation ) - 300x300mm | Nos | 1 | 1
16 | S. S Grating ( Supply plus Installation ) - 300x300mm | Set | 2 | 2
17 | R.O Stand above ceiling with ms pipe with Ply base ( Supply plus Installation ) - 4x4 ft | Set | 1 | 1
18 | 100 LPH RO Plant (Supply & Installation) | Set | 1 | 1
D | Finishes
19 | S.S Profile near counter entrance | RFT | 7 | 7
20 | TV Stand With MS Framing plus Ply - 1.25x8.5 ft | SQF | 11 | 11
21 | L- Shape gypsum Ceiling with Ply base support | SQF | 120 | 120
22 | Supply and installation kota stone floor cold room - 2.6x1.9 Mtr | SQF | 53.15 | 53.15
23 | Supply and installation kota stone skirting 100mm H cold room | Mtr | 8.4 | 8.4
24 | Supply and installation ACP sheet packing for above hood 100mm H | RFT | 22 | 22
25 | Ply panelling side counter - 1.25x1.35 Mtr | SQF | 18.16 | 18.16
E | Fire Sprinkler
26 | Supply and installation sprinkler with accessories and re-work of existing sprinkler | Nos | 6 | 6
27 | Supply and installation Site of sprinkler rossettle plate | Nos | 6 | 6
28 | Supply and installation Site of UL listed approved corrugeted sheet SS 304 | Nos | 6 | 6
F | Façade
29 | Supply and installation corian for counter façade drop | Rmt | 8 | 8
30 | 12 mm toughned Glass | SQF | 22.31 | 22.31
G | Mis
31 | Ply with laminate panelling over DB panel | SQF | 11.3 | 11.3
32 | Hood MS structure/ pipe support for hanging | Nos | 1 | 1
33 | Mop Hanger | Nos | 1 | 1
34 | Supply and installation anti scratch tap | Nos | 1 | 1
35 | Supply and installation wall boxing for ac | Nos | 4 | 4
36 | Supply and installation chain 1.5 mtr | Nos | 2 | 2
37 | Supply and installation panelling above cold room - 7'x1'-6" | SQF | 10.5 | 10.5
38 | Supply and installation corian above counter - 2x5 | SQF | 10 | 10
39 | Supply and installation MS support for Gas meter | Nos | 1 | 1
40 | Supply of pvc strip curtain for Conveyor oven- size 20x7 FT ht | SQF | 140 | 140
41 | Equipment installation | Nos | 1 | 1
42 | Supply and installation soap dispenser _ Uronics | Nos | 1 | 1
43 | Supply of Tissue paper holder | Nos | 1 | 1
H | HVAC
44 | Supply Installation, Testing and Commissioning of Split AC 1.8 TR - Daikin | Nos | 3 | 3
45 | Supply Installation, Testing and Commissioning of Split AC 1.5 TR - Daikin | Nos | 1 | 1
46 | 6.4 mm OD Soft Copper ( Insulation-9 mm ) | RM | 14 | 14
47 | 9.5 mm OD Soft Copper ( Insulation-9 mm ) | RM | 52 | 52
48 | 12.7 mm OD Soft Copper ( Insulation-9 mm | RM | 14 | 14
49 | 15.9 mm OD Soft Copper ( Insulation- 9 mm ) | RM | 52 | 52
50 | Cable 4 Core 2.5 Sqmm | RM | 80 | 80