## Summary
Semolina Kitchens Pvt.Ltd.
Project : AJ Kitchen
PO NO : | PO/SKPL/23-24/1487
Venodr Name : Pioneer Infra
SR NO | DISCRIPTION | PO VALUE | PREVIOUS BILL AMT | PRESENT BILL AMT (RA_04) | CUMULATIVE AMT | VARIANCE AMT
1 | CVCP WORKS | 1147017.11 | 1116232.1055 | 131591.97 | 1247824.0755 | -100806.9655
2 | FURNITURE | 974100 | 360800 | 469100 | 829900 | 144200
3 | SIGNAGE | 186000 | 0 | 0 | 0 | 0
| NET TOTAL | 2307117.11 | 1477032.1055 | 600691.97 | 2077724.0755 | 43393.0345
| GST 18% | 415281.0798 | 265865.779 | 108124.5546 | 373990.3336 | 7810.7462
| TOTAL | 2722398.1898 | 1742897.8845 | 708816.5246 | 2451714.4091 | 51203.7807

## CVCP
BILL OF QUANTITY
SECTION 02 - FINISHES (WALL, FLOOR, CEILING & DOORS) |  |  | PO Amount |  |  | Previous Bill Amount(INR) |  | Present Bill Amount (INR) |  | Cumulative Amount (INR)
NO. | ITEM DESCRIPTION | UNIT | QTY | UNIT RATE | AMOUNT | Qty | Amt | Qty | Amt | Qty | Amt
INR
SECTION 02 - FINISHES (WALL, FLOOR, CEILING & DOORS)
NOTE | The Contractor is referred to the Specifications and Drawings for all details related to this Section of the works and he is to include for complying with all the requirement contained therein, whether or not they are specifically mentioned within the items description.
1 | Partition walls
1.01 | Supply and installation of fire rated calcium silicate board Partition Wall with the necessory supports, fittings and fixtures (excluding final finishes). Purposed height is 4500mm, it may be change as per site conditions GI framing shall be considered | SQM | 48.598 | 1870 | 90878.26 | 30.2384 | 56545.808 | 15.5 | 28985 | 45.7384 | 85530.808
1.02 | Supply and installation of fire rated calcium silicate board cladding on the existing walls in the Kitchen & pot wash area to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures (excluding final finishes). Purposed height is 3000mm, it may be change as per site conditions GI framing shall be considered | SQM | 35.78 | 1870 | 66908.6 | 19.373 | 36227.51 | 12.481 | 23339.47 | 31.854 | 59566.98
| Supply and installation of Gypsum board cladding on the existing walls to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures in the FOH & dining area walls, Front elevations & columns. (excluding final finishes). Purposed height is 3000mm, it may be change as per site conditions GI framing shall be considered | SQM | 80.924 | 1150 | 93062.6 | 52.018 | 59820.7 | 6.25 | 7187.5 | 58.268 | 67008.2
| TOTAL OF PARTITION |  |  |  | 250849.46 | 0 | 152594.018 |  | 59511.97 |  | 212105.988
2 | FLOOR FINISHES |  |  |  |  | 0
| Floor / tiles finishes including grouting, pointing, polishing, backing and etc. as required to complete all in accordance with drawings and specifications & as per client approval. |  |  |  |  | 0
2.01 | 150mm thick concrete floor screeding/AAC blocks to raise the floor to accomodate the drainage pipes and floor gratings & to receive floor finish in the Kitchen & pot wash areas; all in accordance with drawings & site conditions. Note: Total height of floor to be raised including floor finishes is 200mm in the kitchen & pot wash area only | SQM | 13.6 | 820 |  | 0
2.02 | Supply & installation of water proofing with all necessary items; all in accordance with drawings and below mentioned specification. Detailed specifications of the materials to be submitted to client |  |  |  |  | 0
2.02a | Dry Area: 1 Layer of 4mm thick SBS Bituminous membrane with 24-hour water ponding test (inspected and approved from airports team). | SQM | 86.02 | 950 |  | 0
2.02b | Wet Areas: 2 Layers of 4mm thick SBS Bituminous membrane with 24-hour water ponding test including the sealing of Cores in the slab/walls (inspected and approved from airports team). | SQM | 17 | 1800 |  | 0
2.03 | Supply and installation of self levelling with all necessary items; all in accordance with drawings. | SQM | 88.4 | 400 |  | 0
2.04 | Supply and installation of anti-skid 600 x 600 mm white floor tile in the kitchen & Pot wash area as per the drawings and renders. Note: Material to be approved by Clients team. Tile Base Rate = Rs. 60 per sft. | SQM | 13.6 | 1450 | 19720 | 0 | 0 | 0 | 0 | 0 | 0
2.05 | Supply and installation of Stone Plastic Composite (SPC) flooring in the FOH dining area area; colour & design as per drawings & render. Note: material to be approved by Clients Team Tile Base Rate = Rs. 100 per sft. | SQM | 57.75 | 2000 | 115500 | 53.99 | 107980 | 0 | 0 | 53.99 | 107980
2.06 | Supply and installation of Matt finish designer tiles in the FOH area; colour & design as per drawings & render. Note: material to be approved by Clients Team Tile Base Rate = Rs. 60 per sft. | SQM | 20.75 | 1450 | 30087.5 | 22.41 | 32494.5 | 0 | 0 | 22.41 | 32494.5
| TOTAL OF FLOOR FINISHES |  |  |  | 165307.5 | 0 | 140474.5 |  | 0 |  | 140474.5
3 | SKIRTING |  |  |  |  | 0
3.01 | supply & installation of 150mm HIGH Marble textured Corian material skirting - FOH area, matching with FOH Counter top corian as per the renders & drawings. Note: material to be approved by Clients Team | SQM | 10 | 8000 | 80000 | 10.741 | 85928 | 0 | 0 | 10.741 | 85928
| TOTAL OF SKIRTING |  |  |  | 80000 | 0 | 85928 |  | 0 |  | 85928
4 | WALL FINISHES |  |  |  |  | 0
A | Kitchen & Pot Wash areas |  |  |  |  | 0
4.01 | Supply & installation of 300x300 mm White wall tile in the kitchen & Pot wash area as per drawings and renders. Note: material to be approved by Clients Team Tile Base Rate = Rs. 30 per sft. | SQM | 57.946 | 1250 | 72432.5 | 54.365 | 67956.25 | 0 | 0 | 54.365 | 67956.25
4.02 | Supply and Installation of SS corner beeding on the corners of kitchen wall tiles. Size 50 mm | Rmt. | 10 | 1200 | 12000 | 11.2 | 13440 | 0 | 0 | 11.2 | 13440
B | FOH Dining areas |  |  |  |  | 0 |  |  |  |  | 0
4.03 | Supply & Painiting of matt finish paint RAL : 9012 on the walls of dining & FOH area as per the drawings & renders Note: Material to be approved by clients Team | SQM | 86.229 | 350 | 30180.15 | 113.385 | 39684.75 | 0.00425 |  | 113.3893 | 39686.2375
4.04 | Supply & installation of Wooden moulding cladding with paint finish on the walls of Dining & FOH area as per drawings and renders. Note: Material to be approved by clients Team 25mm size half round moulding | Rmt. | 100 | 650 | 65000 | 142.94 | 92911 | 0 | 0 | 142.94 | 92911
4.05 | Supply & installation of Matt finish Oak wood veneer on the walls of FOH area as per drawings and renders. Size: 850 mm Length wall only Note: Material to be approved by clients Team | SQM | 1.105 | 7500 | 8287.5 | 12.069 | 90517.3125 | 0 | 0 | 12.069 | 90517.3125
C | Front Elevation area. |  |  |  |  | 0 |  |  |  |  | 0
4.06 | Supply & installation of Wooden moulding cladding with paint finish on the front elevation, columns as per drawings and renders. Note: Material to be approved by clients Team 25mm size half round moulding | Rmt. | 30 | 650 | 19500 | 12 | 7800 | 14 | 9100 | 26 | 16900
4.07 | Supply & installation of Marble textured Corian material cladding on the columns, walls as per drawings and renders. Note: Material to be approved by clients Team | SQM | 10 | 8000 | 80000 | 13.0261 | 104208.8 | 0 | 0 | 13.0261 | 104208.8
| TOTAL OF WALL FINISHES |  |  |  | 287400.15 | 0 | 416518.1125 |  | 9100 |  | 425619.6
5 | GYPSUM WORKS |  |  |  |  | 0
5.01 | Supply & installation of bulkhead gypsum above the hood in white paint matt finish. Paint shall be included, as per the below hood sizes. Considered Ceiling height in kitchen is 2800mm |  |  |  |  | 0
5.01A | Hood 1 - Hot Cooking line : 2600 L x 1000 W x 400 H mm | Nos | 1 | 45000 | 45000 | 0 | 0 | 1 | 45000 | 1 | 45000
| TOTAL OF GYPSUM WORKS |  |  |  | 45000 | 0 | 0 |  | 45000 |  | 45000
0
6 | CEILING WORKS |  |  |  |  | 0
6.01 | Supply & Installation of 600x600 mm metal tile ceiling in the Kitchen & Pot wash area with necessary support, fixtures & accessories as per drawings & renders Note: Material to be approved by Clients Team. Tile Base Rate = Rs. 60 per sft. | SQM | 13.6 | 1850 | 25160 | 13.52 | 25012 |  | 0 | 13.52 | 25012
6.02 | Supply and Installation of Metal grid ceiling with hanging flowers in the FOH & Dining areas including the final finishes with necessary support, fixtures & accessories as per drawings & renders. Note: Material to be approved by Clients Team. | SQM | 58 | 3100 | 179800 | 49.9045 | 154703.95 | 5.8 | 17980 | 55.7045 | 172683.95
6.03 | Supply and Installation of Gypsum false ceiling at the sides of walls with the cove lights provision in the the FOH & dining area with paint in White color finishes with necessary support, fixtures & accessories as per drawings & renders. Including access panel as per the MEP services and Cutting & finishing for the AC grill/diffuser and lights. Note: Material to be approved by Clients Team. GI frame shall be considered | SQM | 50 | 1150 | 57500 | 55.4645 | 63784.175 |  | 0 | 55.4645 | 63784.175
6.04 | Supply and painting with matt finish paint on the slab & walls of void ceiling area of FOH & dinning, including paints on all MEP services & metal ceiling parts. Note: color to be selected/approved by Clients Team. | SQM | 70 | 350 | 24500 | 130.621 | 45717.35 |  | 0 | 130.621 | 45717.35
| TOTAL OF CEILING WORKS |  |  |  | 286960 | 0 | 289217.475 |  | 17980 |  | 307197.475
7 | DOORS & WINDOWS |  |  |  |  | 0
7.01 | Supply and installation of heavy duty single leaf both side swing wooden door with the door frame for kitchen, including all the fittings & accessories, with vision glass as per the drawings and showing in the renders. This door to be decorative and designed type matching with the FOH design. Dim: 2200H x 900W mm x 45T mm | Nos | 1 | 31500 | 31500 | 1 | 31500 |  | 0 | 1 | 31500
| TOTAL OF DOORS & WINDOWS |  |  |  | 31500 | 0 | 31500 |  | 0 |  | 31500
Sub-total |  |  |  |  | 1147017.11 | 0 | 1116232.1055 |  | 131591.97 |  | 1247825.563 | 1247824.0755 | 1.4875

## FURNITURE
BILL OF QUANTITY
SECTION 03 - JOINERY, PLANTER BOX WITH PLANTS & LOOSE FURNITURES
|  |  | AS PER PO |  |  |  | Previous Bill Amount(INR) |  | Present Bill Amount (INR) |  | Cumulative Amount (INR)
NO. | Pictures | ITEM DESCRIPTION | UNIT | QTY | UNIT RATE | AMOUNT | Qty | AMOUNT |  |  | Qty | AMOUNT
SECTION 03 - JOINERY, PLANTER BOX WITH PLANTS & LOOSE FURNITURES
| NOTE | The Contractor is referred to the Specifications and Drawings for all details related to this Section of the works and he is to include for complying with all the requirement contained therein, whether or not they are specifically mentioned within the items description.
A |  | Furniture specs, details & samples to be submitted to Client for review and approvals
B |  | All shop drawings of Joinery counters to be co-ordinated and approved with the kitchen equipment team.
C |  | Ensure all table and seating components are of the commercial quality or specification. Metal in table base may need to be treated for opportunities of oxidation where rust may occur for example, the material of the base need to be specified in drawings. All tables and seating are to be anti-rust, anti-fade and washable.
1 |  | CHAIRS & BANQUETTE SEATING
1.01 |  | Customer Dining Chair : Supply of Chair made up of Fabric and foam with golden powder coated Metal base. Dimensions, color & design as per the drawings and renders. Note: Samples to be submitted by contractor | PCS | 31 | 9800 | 303800 | 13.5 | 132300 | 13.5 | 132300 | 27 | 264600
1.02 |  | Banquett Seating: Supply and installation of Seating made up of Fabric and foam with Wooden base in the polish finish as per the drawings & renders. Size: L 6500 mm Note: Samples to be submitted by contractor. | PCS | 1 | 65000 | 65000 | 0.5 | 32500 | 0.5 | 32500 | 1 | 65000
2 |  | TABLE
2.01 |  | Customer Dining Table: Supply and Installation of Table made up of Marble textured Corian material top with Metal base in the powder coated finish, Golden strip on the sides of tables as per the drawings and renders. Note: Samples to be submitted by contractor
|  | 650L x 650W x 750H mm (750+ thickness table top material) | PCS | 19 | 16500 | 313500 | 8.5 | 140250 | 8.5 | 140250 | 17 | 280500
3 |  | JOINERY
3.01 |  | Supply & installation of FOH counter made up of 18mm thick MR-MDF structured with Marble textured Corian material finish and front facia cladding with 6mm-thk Charcoal panel & Matt finish Oak wood veneer, LED Cove lighting, PU paint finish inner side portions, glass display with shelves to be made in the counter, soft closing drawers, storage & handleless cabinets, fillers, panels, skirting and all necessary support, fittings, accessories and profiles as per approved drawings and renders. Space/provisions to be provided to accomodate the equipment inside the counter as showing in the drawings & renders. Note: Actual countertop material sample shall be submitted by contractor and, required provision for electrical socket as per power layout. Contractor shall refer to the counter details for complete detailings, dimensions & materials etc. | Nos | 1 | 75800 | 75800 | 0 | 0 | 1 | 75800 | 1 | 75800
3.02 |  | Supply & installation of Service counter with 18mm thick MR MDF with Marble textured Corian material finish, Matt finish Oak wood veneer adjustable shelves, drawers, doors, handleless cabinets, fillers, panels, skirting and all necessary support, fittings, accessories and profiles as per drawings and renders. Note: Actual countertop material sample shall be submitted by contractor, and required provision for electrical socket as per power layout. Contractor should refer to the counter details for dimensions, drawer & shelves location, and Materials etc. | Nos | 1 | 65000 | 65000 | 0 | 0 | 1 | 65000 | 1 | 65000
4 |  | PLANTER BOXES & ARTIFICIAL PLANTS
4.01 |  | Supply & installation of planter box with plants with the paint finish, wooden moulding & Corian cladding at front entrance areas as per drawings and renders. Size: 600 x 250 mm Note: Samples shall be submitted by contractor. | Nos | 3 | 15500 | 46500 | 1.5 | 23250 | 1.5 | 23250 | 3 | 46500
4.02 |  | Supply & installation of round shape planter box with plants with the paint/powder coated finishes as per drawings and renders. Size of planter box: dia. 300mm Note: Samples shall be submitted by contractor. | Nos | 4 | 18000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0
4.04 |  | Supply and Installation of big plant to be inserted in the FOH counter and planter box (decorative type) on the counter top as per the drawings and renders. To be coordinate with FOH counter drawings. Note: Samples shall be submitted by contractor. | Nos | 1 | 32500 | 32500 | 1 | 32500 | 0 | 0 | 1 | 32500
|  | Total |  |  |  | 974100 |  | 360800 |  | 469100 |  | 829900
|  | GST 18% |  |  |  | 175338 |  | 64944 |  | 84438 |  | 149382
Sub-total | [5 empty] | 1149438 |  | 425744 |  | 553538 |  | 979282

## SIGNAGE
BILL OF QUANTITY
SECTION 04 - SIGNAGES & LOGOS WORK
|  |  | As Per PO |  |  |  | As Per Site
NO. | Pictures | ITEM DESCRIPTION | UNIT | QTY | UNIT RATE | AMOUNT | Qty | Amt
SECTION 04 - SIGNAGES & LOGOS WORK
| NOTE | The Contractor is referred to the Specifications and Drawings for all details related to this Section of the works and he is to include for complying with all the requirement contained therein, whether or not they are specifically mentioned within the items description.
1 |  | SIGNAGES
Install Signages with necessary wiring, conduits in accordance with the drawings and specification & Airport Regulations. All signages sample to be provided for review and approval.
1.01 |  | AJ1881 LOGO AT FRONT ELEVATION: Supply & Installation of AJ1881 front lit aluminium 3D logo, letter made of aluminium channellume 3D letters with font face acrylic illuminated LED with transformer. Including the base structure on which logo to be installed, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 | 50000 | 50000 | 0 | 0
1.02 |  | AJ1881 LOGO IN THE DINING AREA WALL: Supply & Installation of AJ1881 front lit aluminium 3D logo, letter made of aluminium channellume 3D letters with front face acrylic illuminated LED with transformer, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 | 50000 | 50000 | 0 | 0
1.03 |  | HEART SHAPE LOGO IN THE DINING AREA WALL: Supply & Installation of front lit 3D Logo- Heart Shape, letter made of aluminium channellume 3D letters with front face acrylic illuminated LED with transformer, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 | 44000 | 44000 | 0 | 0
1.04 |  | "FLY ON THE GO" SIGNAGE: Supply & Installation of back lit aluminium 3D logo, letter made of aluminium channellume 3D letters with power coating and LED backlit with transformer, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 | 42000 | 42000 | 0 | 0
Sub-total | [5 empty] | 186000 |  | 0
270