## Additional work
Additional work Nourish HEALTHY EATS
Sl/no | Item | Description |  |  | Additional Qty | Unit | Rate | Amount | Remark
CIVIL WORKS
A
1 | Brick work | Providing and constructing 150mm thk Siphorex block in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. in substructure and superstructure to its true line & level in cement mortar proportion as specified in all shapes, size, at all heights, depths, leads & locations etc. complete. The rate shall also include for cleaning of surface, hacking of RCC surface in contact with brickwork, racking of joints, providing, erecting, & dismantling steel scaffolding , curing for 10 days, including 75 mm thk. R.C.C. stiffener at approximately every 1000 mm ht. with required M.S. reinforcement bars and Lintels for Doors and wall openings etc. compete as per the drgs., details & specifications. |  |  | 13.63 | Sq.M | 2100 | 28623 | Non tendor iteam
|  | Front wall - | 3.92 | 2.93 | 11.4856
|  | Inner wall- | 0.88 | 2.44 | 2.1472
2 | Plaster work | P&A of single coat backing plaster of 15-18 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction. |  |  | 27.27 | Sq.M | 1500 | 40905 | Non tendor iteam
|  |  | 3.92 | 2.93 | 11.4856
|  |  | 3.92 | 2.93 | 11.4856
|  |  | 0.88 | 2.44 | 2.1472
|  |  | 0.88 | 2.44 | 2.1472
3 | Cinder filling | CINDER BLOCK COBA of Avg. thickness mentioned below; After laying of soil pipes, floor traps is completed the floor of the sunken portion shall be covered with cinder coba embedded manually with 15-20 mm wide joints in 20 mm thk. Waterproofing mortar 1:4 ( 1 cement : 4 coarse sand )in layers upto the full ht. of sunken portion, having top layer of 50 mm thk waterproof mortar 1:4 ( 1 cement : 4 coarse sand ) using specialized W.P. chemical, finished smooth / rough with floating coat of neat cement all complete and as per specification up to 300mm . |  |  | 20.89 | Sq.M | 2200 | 45958 | Non tendor iteam
|  |  | 3.92 | 2.72 | 10.6624
|  |  | 3.92 | 2.61 | 10.2312
4 | PCC | Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, filling joints, or as directed, finishing smooth with cement Mortar 1:1 of sufficient minimum thickness to give a smooth & even surface and curing etc. complete as per architects instructions. |  |  | 20.89 | Sq.M | 1450 | 30290.5 | Non tendor iteam
|  |  | 3.92 | 2.72 | 10.6624
|  |  | 3.92 | 2.61 | 10.2312
5 | Trolly defender | Providing and fixing of trolly defender made out of 50 mm 304 SS pipe |  |  | 2.77 | RM | 5900 | 16343 | Non tendor iteam
6 | Side counter | Providing and fixing of side counter made out of ply finished with laminate with granite top |  |  | 1 | NO. | 12000 | 12000 | Non tendor iteam
7 | Hood fixing | Fixing of hood from ceiling frame with support of MS pipe frame. |  |  | 1 | NO. | 10000 | 10000 | Non tendor iteam
8 | Ele. DB box | Providing and fixing of electrical DB box made out of plywood finished with laminate and MS louvers fixed on shutters. |  |  | 1.97 | Sq.M | 17259 | 34000.23 | Non tendor iteam
9 | SS corner guard | Providing and fixing of 25 mm X 25 mm SS corner guard for wall corner. |  |  | 9 | RM | 800 | 7200 | Non tendor iteam
10 | Gas meter stand | Providing and fixing of gas meter stand made out of SS pipe. |  |  | 1 | NO. | 2000 | 2000
11 | Green Ceramic tile cladding (Over Servery rear wall) | Providing & Fixing of Green Ceramic tile (100 x 100mm Base price rs.100/sft)cladding with cement mortar over Servery rear wall as per design ,details &finishes specified. |  |  | 1 | Sq.M | 3200 | 3200 | Semolina/PO/24-25/000080
12 | MOH WALL | P/fixing glazed ceramic (Kajaria) Veda Bianaca Décor (450x450nn) Wall tiles,in MOH back bison board partition in per approved pattern, setting the tiles in appropriate adhesive as per manufacturer's specifications, joints filled and finished neat with epoxy grout as/spec |  |  | 7 | Sq.M | 1820 | 12740 | Semolina/PO/24-25/000080
13 | Debris removal | Removing of debris from duming area to out side of airport premisses |  |  | 10 | NO. | 2800 | 28000 | Semolina/PO/23-24/000806
14 | Trap door | Provision of trap door in gypsum ceiling |  |  | 2 | NO. | 2500 | 5000 | Non tender item
15 | Equipment shifting | Lording and unloading of outlet equipment and shifting from out side of airport premisses and arrange and fixing in side the outlet as per instructions |  |  | 1 | NO | 45000 | 45000 | Non tender item
321259.73