## ELECTRICAL
Nourish at Food Court_Ahemdabad Airport.
Additional of Quantities- Electrical Works
S. No. | Description |  | Unit | Additional | Rate | Amount | Remark
Qty
1 | 2 x 6 sq.mm + 1 No. 4 Sq. mm in 25 mm dia MS Conduit |  | Mtrs | 5 | 475 | 2375 | Semolina/PO/24-25/000080
2 | 2 x 4 sq.mm + 1 No. 2.5 Sq. mm in 25 mm dia MS Conduit |  | Mtrs | 310.2 | 150 | 46530 | Semolina/PO/24-25/000080
| DB to Induction plate kitchen | 10
| DB to Utility Socket kitchen | 9.8
| DB to Geyser point | 6.2
| DB to Near Geyser Extra Point | 6.2
| DB to Drain Pump Extra Point | 6.8
| DB to Insect killer | 4.9
| DB to Exhaust Hood | 7.9
| DB to Utility Socket | 9.7
| DB to Merry Chef | 10.2
| DB to Yogurt | 10.2
| DB to Tea coffee | 9.1
| DB to Extra Point Loop | 8.1
| DB to Extra point Industrial box | 10.4
| DB to Ice Cube | 10.3
| DB to Blender | 10.4
| DB to Juicer | 12.4
| DB to Sandwich griller | 23.2
| DB to Sandwich griller 2 | 13.4
| DB to Exhaust chimney | 12.7
| DB to Induction | 16.1
| DB to Utility Socket - 1 | 17.6
| DB to Utility Socket - 2 | 18.1
| DB to Utility Socket - 3 | 18.7
| DB to Cold Display | 18.7
| DB to Insect killer | 11.1
| DB to Utility Socket - 1 | 8.9
| DB to Utility Socket - 2 | 9.1
3 | 2.5sqmm X 2 +2.5sqmm |  |  | 92.2 | 125 | 11525 | Non tender item
| DB to TV Point 1 | 8.7
| DB to TV Point 2 | 8.7
| DB to POS | 16
| DB to Signage Point | 7.3
| DB to Emergency light point P1 | 7.8
| Loop P1 to P2 | 4.2
| Loop P2 to P3 | 5.9
| DB to Raw Light point P1 | 7.8
| Loop P1 to P2 | 3.6
| Loop P2 to P3 | 4.2
| Loop P3 to P4 | 3
| Loop P4 to P5 | 3.1
| DB to Emergency light point kitchen P1 | 4.8
| DB to Raw light point kitchen P1 | 7.1
4 | Wiring for MCB controlled normal primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). |  | Pt | 6 | 1500 | 9000 | Semolina/PO/24-25/000080
5 | Wiring for secondary MCB controlled normal light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. |  | Pt | 6 | 850 | 5100 | Semolina/PO/24-25/000080
6 | Wiring for MCB controlled Emergency primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). |  | Pt | 4 | 2200 | 8800 | Semolina/PO/24-25/000080
7 | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. |  | Pt | 1 | 1200 | 1200 | Semolina/PO/24-25/000080
8 | Wiring for a 5 pin 240 volt 6 amp single phase and neutral switch socket outlet with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / ceiling including cost of providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade wires and including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and providing and fixing of a combined 5 pin 240 volt 6 amp socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires complete as requied( Switch and socket shall be as approved by the architect / Client) |  | Pt.
9 | Wiring same as in Item 12 above looped from an adjacent 6 amp switch socket outlet as required and providing and fixing of a modular type 5 pin 240 Volt 6 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole switch in a recessed GI boxes with internal wiring and moulded front plates complete as required. ( Switch and socket shall be as approved by the architect / Client) |  | Pt.
10 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) |  | Pt.
11 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 4.0 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) |  | Pt. | 26 | 3050 | 79300 | Semolina/PO/24-25/000080
12 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (2 outlets wired on 1 circuit) with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 4.0 sq mm upto the first outlet and 2.5 sq mm from first to the second outlet in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing of two sets of 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switches with moulded cover plate in a recessed GI box including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) |  | Pt. | 2 | 3800 | 7600 | Semolina/PO/24-25/000080
13 | Wiring for primary switch board consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A switch with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 2.5 sq FRLS copper wire mm in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing prewired switch board each consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A modular switch , safety shutters in a recessed/surface GI box including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) Note- Conduits shall be 16 SWG MS on surface and FRLS PVC for wall concealed |  | Pt. | 3 | 4000 | 12000 | Semolina/PO/24-25/000080
14 | Supply installation testing and fixing 3 pin 20A , 240V , single Phase metal Clad industrial socket outlet with 20A DP MCB and complete in all respects( Wiring Excluded from scope of this item) |  | Nos.
15 | Supply installation testing and fixing 3 pin 25A/32A , 240V , single Phase metal Clad industrial socket outlet with 25A/32A DP MCB and complete in all respects( Wiring Excluded from scope of this item) |  | Nos. | 5 | 3200 | 16000 | Semolina/PO/24-25/000080
16 | Supply , fixing & Laying 2.0mm Thick FRLS PVC conduits on surface or concealed complete with PVC junction boxes, cover plates, PVC bends, PVC saddles, base and other accessories all made in PVC with GI screws as required to complete the job. .
17 | 20 mm dia FRLS metal conduit |  | Mtrs | 115 | 210 | 24150 | Non tender item
18 | Supply and installation of flush mounted (Enhanced Category 6T 568 A or B) outlets with 2 mm thick GI box complete including cutting, chases, fixing of GI boxes and making good. The plastic shall be high impact, flame-retardant, UL rate thermoplastic. Dust cover / blank shall be provided to protect unused faceplate openings. Termination caps and plastic cover shall be provided to protect jack wiring.
19 | LED Strip Light |  | Mtrs | 15 | 550 | 8250 | Non tender item
20 | 15 W panel light |  | Nos. | 4 | 1000 | 4000 | Non tender item
TOTAL | [5 empty] | 235830