## SUMMARY
Semolina Kitchens Pvt.Ltd.
Project : Dhaba
PO NO : | Semolina/PO/24-25/000078
Venodr Name : INVENTECH SOLUTIONS
SR NO | DISCRIPTION | PO VALUE | PREVIOUS BILL AMT(RA-1) | THIS BILL AMT (Final Bill) | CUMULATIVE AMT (Previous + This Invoice) | VARIANCE AMT
1 | ELECTRICAL | 218800 | 209860 | 1240 | 211100 | -7700
2 | PLUMBING | 186750 | 14040 | 26655 | 40695 | -146055
3 | CIVIL & INTERIOR | 1136514.43 | 963116.25 | 140380 | 1103496.25 | -33018.18
| NET TOTAL | 1542064.43 | 1187016.25 | 168275 | 1355291.25 | -186773.18
| GST 18% | 277571.5974 | 213662.925 | 30289.5 | 243952.425 | -33619.1724
| TOTAL | 1819636.0274 | 1400679.175 | 198564.5 | 1599243.675 | -220392.3524
1400679
-0.175

## CIVIL & INTERIOR
Nourish-AHM-PHE BOQ |  |  |  |  | Rev: | R0
[5 empty] | Date: | 09.10.2023 | Present Bill Amount (INR) |  | Previous Bill Amount(INR) |  | Cumulative Amount (INR)
Item No. | Item | Description | PO Qty | UOM | Rate | PO Amount | Qty | Amount | Qty | Amount | Qty | Amount | Make
PRELIMINARY WORKS (WATER PROOFING & RAISED FLOOR WORKS)
1 | Waterproofing of BOH area | Providing,laying and testing of chemical waterproofing at BOH area . Specifications and Method to be followed as specified by airport (Refer Annexture-01) | 25.34 | Sq.Mt | 402 | 10186.68 |  | 0
2 | 150mm thick x 300mm high masonry wall with Siporex block along periphery of water-proofing area | Providing,laying 150mm thick x 300mm high masonry wall with Siporex block with Cement mortar along periphery of water-proofing area | 4.821 | R.Mt | 1500 | 7231.5 |  | 0
3 | 100mm thick x 300mm high masonry wall with Siporex block for Trenches | Providing,laying 100mm thick x 300mm high masonry wall with Siporex block with Cement mortar for Trenches (Length considered = Length of Drain pipe x 2 sides) | 2.4 | R.Mt | 1500 | 3600 |  | 0
4 | Inspection Chamber - 600 x600 x350(external dimensions) | Providing Inspection chamber with 100 mm thk Siporex walls Plasterd with cement mortar & waterproof chemical .with necessary PCC bedding to required slope. | 2 | nos | 4500 | 9000 | 2 | 9000
5 | Inspection Chamber cover - (Perforated S.S) 600 x600mm | Providing and fixing of S.S. perforated Inspection chamber cover with necessary fittings | 2 | nos | 9500 | 19000 |  | 0 | 2 | 19000
6 | Floor filling + Screed (raised floor) (+350mm to the top of the Floor finish) | Cinder Filling over finish level of waterproofing layers to achieve a finihsed floor level of +350mm . Screed as per mandatory floor PCC norms from airport | 25.34 | Sq.Mt | 1200 | 30408 | 25.34 | 30408
8 | ENDURA GREY TILE BOH | Providing & laying of 600x600 mm ENDURA GREY tiles (anti slip finish ), Fixed with Cement mortar. Surface to have anti-slip grooves , including edge polish and finish | 25.34 | Sq.Mt | 2830 | 71712.2 | 25.34 | 71712.2
0
METAL WORKS | [7 empty] | 0
A | M.S. FRAMING | [6 empty] | 0
1 | Decorative metal work at Front counter (Truck design element) | Providing and fixing of (decorative) metal tubes of 18SWG (as per design) ,made factory conditions . To receive finishes as per schedule | 33 | R.Mt | 1260 | 41580 |  | 0 | 33 | 41580
[6 empty] | 0 |  | 0
CARPENTRY WORKS | [5 empty] | 0 |  | 0
B | PARTITIONS/ BOXING |  |  |  |  | 0 |  | 0
1 | SINGLE SIDE PARTITION | P/F Full Ht Single Side Partition, in front of existing airport walls, with Framework of MS Box section 40x40mm, 18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame, fixed to the floor and soffit of slab/beam with MS cleats bolted as required, with rust-free treatment & enamel paint of colour as specified ready to recieve 12mm th. Bison board as base(upto 75 mm above BOFC as per site). Rate to include making provsion for electrical wiring, necessary hardware, wastage, scafollding at all levels etc complete. Measurement as per elevation | 46.74 | Sq.Mt | 4795 | 224118.3 | 46.74 | 224118.3
2 | Front counter Carcass -100mm thk (Carcass Only) | Providing and fixing 100 mm THK. carcass at front counter with 18mm ply on both sides of SW/Alu framing , to take finishes as per design and details | 3.595 | Sq.Mt | 10150 | 36489.25 | 3.595 | 36489.25
3 | Front counter Facade Truck design carpentry | Grill pattern with fret cut 18mm thk. HDHMR board ,as per design & details , to receive finishes as per schedule | 5.06 | Sq.Mt | 11075 | 56039.5 | 5.06 | 56039.5
|  | Reflector & Nameplate ledge boxing with 18mm thk. HDHMR board , as per design & details , to receive finishes as per schedule | 0.1 | Sq.Mt |  | 0 | 0.1 | 0
|  | Providing and fixing of Tyre on Ply base | 2 | nos | 9450 | 18900 | 2 | 18900
|  | Number plate (5mm thk HDHMR) | 0.1 | Sq.Mt | 35000 | 3500 | 0.1 | 3500
|  | Wheel flap sticker base (5mm thk HDHMR) | 0.85 | Sq.Mt | 26500 | 22525 | 0.85 | 22525
4 | Designer Side wall paneling over Wall at Servery area (both sides) | Providing and fixing side wall paneling with 18mm thk HDHMR board over side walls in servery area (Design element). as per design & details , to receive finishes as per schedule | 13.8 | Sq.Mt | 5870 | 81006 | 13.8 | 81006
5 | Back wall Truck design carpentry (Carpentry only) | Providing and fixing truck design elements at back wall with HDHMR board (Varying thickness),as per design & details to receive finishes as per schedule | 8.12 | Sq.Mt | 7850 | 63742 | 8.12 | 63742
|  | Foods carrier' boxing with Band (18mm thk. HDHMR) | [5 empty] | 0
|  | Blue border around opening (25mm thk HDHMR) | [5 empty] | 0
|  | Yellow border around opening (12mm thk HDHMR) | [5 empty] | 0
|  | paneling with groves on Boxing-04 (18mm thk. HDHMR) | [5 empty] | 0
|  | Rhombus shaped elements at Front counter , Back wall ,sides | [5 empty] | 0
|  | 'Horn Not OK Please ' , board (18mm thk HDHMR)' | [5 empty] | 0
[6 empty] | 0 |  | 0
C | DOORS / FIXED GLASS |  |  |  |  | 0 |  | 0
[6 empty] | 0 |  | 0
1 | Door- D1 (1000W x 2100 H | Providing & fixing of Flush code door with - 50x100 Wood Frame - 35mm thk flush core shutter , edge to be sealed with teak wood lipping - 8mm thk. toughened glass vision panel secured with aluminium holder - S.S. handles on both sides - All to be painted to approved specs - with necessary fittings & iron mongery to receive finishes as per schedule all as per design | 1 | Nos | 28700 | 28700 | 1 | 28700
[6 empty] | 0 |  | 0
D | STORAGE UNITS/ SHELVES |  |  |  |  | 0 |  | 0
1 | Front counter (Storage unit + Box unit) (3.98L x 0.70D x 0.98 H) Finished height after fixing Engg stone shoud be 1M.To be co-ordinated with selected Engg stone thickness | Providing and fabrication of Front Counter Storage unit & Box unit with - 18mm thk FR+WP Ply carcass as per design & specified finishes - 18mm thk FR+WP Ply Shutters & Shelvesand shelves as per design & specified finishes - Edges to be finished with 2mm plastic edge binding -Cabinet counter-top prepped to receive Engineered stone as per details and design. | 1 | Nos | 81950 | 81950 | 1 | 81950
2 | Rear counter (3.95L x 0.80D x 0.93 H) Finished height after fixing Engg stone shoud be 0.95M. To be co-ordinated with selected Engg stone thickness | Providing and fabrication of Rear counter with - 18mm thk FR+WP Ply framing as per design & specified finishes - 18mm thk FR+WP Ply Shutters & Shelvesand shelves as per design & specified finishes - Edges to be finished with 2mm plastic edge binding -Cabinet counter-top prepped to receive Engineered stone as per details and design. | 1 | Nos | 74150 | 74150 | 1 | 74150
[6 empty] | 0 |  | 0
FALSE CEILING | [5 empty] | 0 |  | 0
E | FLOORING & WALL CLADDING |  |  |  |  | 0 |  | 0
1 | Gypsum ceiling | Providing & fixing of false ceiling with fire rated Gyprock Gypsum board , incl of all cuts & grooves required for services & lights ,Hvac etc not to be paid separate , to receive finishes as per specifications | 19.44 | Sq.Mt | 1600 | 31104 |  | 0 | 19.44 | 31104
Note: Engineered Stone cost to be priced separately and has been included in the Finishes schedule | [5 empty] | 0 |  | 0
FINISHES | [5 empty] | 0 |  | 0
F | FLOORING & WALL CLADDING |  |  |  |  | 0 |  | 0
1 | BOH & MOH | Providing & Laying of 600x600 mm Vitrified tiles flooring (Base price Rs.60/sqft) with Cement mortar, as per finishes schedule | 24.01 | Sq.Mt | 2200 | 52822 | 24.01 | 52822
3 | Ceramic tile dado on BOH & Dishwash walls | Providing & Fixing of Ceramic tile (200 x 300mm - Kajaria-Oxford Blanco)cladding over BOH & Dishwashing walls with cement mortar ,as per design ,details &finishes specified. | 46.98 | Sq.Mt | 2300 | 108054 | 46.98 | 108054
4 | 15/18 mm THK. engineered stone as countertop (Front counter & Rear counter) | Providing and installing 15/18mm thick engineered stone (base cost of stone Rs.400 per Sft) counter-top fixed to Ply carcass/ base ,Polished and edge finished as per design & detail | 3.2 | Sq.Mt | 9800 | 31360 |  | 0 | 3.2 | 31360
G | PAINTING |  |  |  |  | 0 |  | 0
1 | Paint Finish (A) (Training room & BOH walls above tiles + Gyp Ceiling) | Primer + Emulsion Paint over Training room walls & Area above tiles in BOH & Dishwash area & Gypsum ceiling | 19.44 | Sq.Mt | 450 | 8748 |  | 0 | 19.44 | 8748
2 | Paint Finish (B) - Various Colors- Enamel paint | Primer + Enamel Paint over over Front & Sides & Boxings at Servery area ( colors consistent to design & details) | 22 | Sq.Mt | 350 | 7700 |  | 0 | 22 | 7700
MISCELLANEOUS | [5 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
M.1 | Truck mirror sign board | Custom made Truck mirror sign board , with metal frame and acrylic sign board | 2 | Nos | 4500 | 9000 |  | 0
M.3 | Triangle reflector (Truck detail) | Providing & Fixing reflector (triangle shape , as per details) on HDHMR board | 2 | Nos | 1500 | 3000 |  | 0
M.3 | M.S hooks Truck detail) | Providing & Fixing reflector (M.S. Hooks , as per details) | 2 | Nos | 444 | 888 |  | 0 | 2 | 888
[6 empty] | 1136514.43 |  | 963116.25 |  | 140380

## ELECTRICAL
Dhaba @ AHM
ELECTRICAL BOQ
DATE :
|  | AS per the PO |  |  |  | Previous Bill Amount(INR) | Previous Bill Amount(INR) |  | This Bill Amount(INR)
SR. No | DESCRIPTION | PO QTY | UNIT | UNIT RATE | PO AMOUNT
[7 empty] | QTY | AMOUNT | QTY | AMOUNT
S. No. | Description | QTY | UOM | Rate | Amount
|  |  |  | (Rs.) | (Rs.)
1 | DISTRIBUTION BOARDS
Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof double door type distribution boards constructed from 16 SWG sheet steel IP 42 construction, finished with rust proof duly powder coated in approved shade with hinged gasketed door and housing the following complete with P.V.C. insulated copper busbars rated 200 amp with interconnections, neutral and earth bar assembly per phase, earthing terminals complete as approved by Architects.
Note : All MCBs in distribuition board for power circuits shall be of C curve
1.1 | Type A
| 1-63amp FP MCB with 3 single phase banks each comprising of 63A DP RCCB(100 mA) and 10 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 25650 | 25650 |  | 1 | 25650
0
1.2 | Type B | [6 empty] | 0
0
| 1-20 amp DP MCB + DP RCCB ( 100mA) and 4 nos. 6/16/20/25 amps SP 10 kA MCB(Type D) with thermal magnetic protective releases out goings. | 1 | Set | 6500 | 6500 |  | 1 | 6500
0
2 | Supply installation testing and commisioning 1.2 kVA online ( 1ph input and 1ph output) UPS with 15 Min power back up complete with in buit Static by pass switch , Mannual external maintenance by pass switch , Rectifiers , Sealed MF batteries etc as required | 1 | No. | 12000 | 12000 |  | 1 | 12000
0
3 | Supply, laying, testing & commissioning of following sizes of Cu. conductor 1.1 kV grade, armoured, XLPE insulated FRLS LT Cables/ Control Cables including necessary cleats, clamps etc. (Cables shall be partly laid in Pipes, O/H cable tray, on wall as required ) | [6 empty] | 0
0
3.1 | 4C – 16.0 (Cu.) FRLS Armoured XLPE Cable * | 30 | Mtrs | 850 | 25500 |  | 30 | 25500
3.2 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 10 | Mtrs | 270 | 2700 |  | 10 | 2700
0
| * Approximate and shall be as per point of supply from Airport Panel/ Isolator | [6 empty] | 0
0
4 | Supply, erection, testing & commissioning of following sizes of cable end terminations with Single compression gland for 1.1 kV grade, XLPE insulated, Cu Conductor cable | [6 empty] | 0
0
4.1 | 4C – 16.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 750 | 1500 |  | 2 | 1500
4.2 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 500 | 1000 |  | 2 | 1000
0
5 | Wiring for DB Submains with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in surface/concealed MS surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and making suitable end termination with copper lugs complete as required and as below | [6 empty] | 0
0
5.1 | 2 x 6 sq.mm + 1 No. 4 Sq. mm in 25 mm dia MS Conduit | 15 | Mtrs | 475 | 7125 |  | 15 | 7125
5.2 | 2 x 4 sq.mm + 1 No. 2.5 Sq. mm in 25 mm dia MS Conduit | 65 | Mtrs | 350 | 22750 |  | 65 | 22750
0
6 | Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required | [6 empty] | 0
0
6.1 | 25X3 mm GI Strip | RO | Mtrs | 200 |  |  | RO
6.2 | 8 SWG Copper Wire | 20 | Mtrs | 90 | 1800 |  | 20 | 1800
6.3 | 8 SWG GI Wire | 50 | Mtrs | 25 | 1250 |  | 50 | 1250
6.4 | 1 Core 4.0 Sq. Mm FRLS Green Wire | 25 | Mtrs | 45 | 1125 |  | 25 | 1125
0
7 | Supply, erection, testing & commissioning of prefabricated GI Perforated type cable trays including Tees / Bends / Crossing / Reducers / Couping to be laid in cable trench, overhead on wall or hanged from ceiling complete with all accessories as required including support at every 1500mm as required | [6 empty] | 0
0
7.1 | 150 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | RO | Mtrs | 700 |  |  | RO
0
8 | Wiring for MCB controlled normal primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 3 | Pt | 1800 | 5400 |  | 3 | 5400
0
9 | Wiring for secondary MCB controlled normal light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 3 | Pt | 850 | 2550 |  | 3 | 2550
0
10 | Wiring for MCB controlled Emergency primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 1 | Pt | 2200 | 2200 |  | 1 | 2200
0
11 | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 1 | Pt | 1200 | 1200 |  | 1 | 1200
0
12 | Wiring for a 5 pin 240 volt 6 amp single phase and neutral switch socket outlet with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / ceiling including cost of providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade wires and including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and providing and fixing of a combined 5 pin 240 volt 6 amp socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires complete as requied( Switch and socket shall be as approved by the architect / Client) | 2 | Pt. | 2000 | 4000 |  | 2 | 4000
0
13 | Wiring same as in Item 12 above looped from an adjacent 6 amp switch socket outlet as required and providing and fixing of a modular type 5 pin 240 Volt 6 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole switch in a recessed GI boxes with internal wiring and moulded front plates complete as required. ( Switch and socket shall be as approved by the architect / Client) | 2 | Pt. | 1200 | 2400 |  | 2 | 2400
0
14 | Same as above but switch and socket provided at separate location including wiring berween switch and socket and complete as required | RO | Pt. |  |  |  | RO
0
15 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 3 | Pt. | 2500 | 7500 |  | 3 | 7500
0
16 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 4.0 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 10 | Pt. | 3050 | 30500 |  | 10 | 30500
0
17 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (2 outlets wired on 1 circuit) with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 4.0 sq mm upto the first outlet and 2.5 sq mm from first to the second outlet in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing of two sets of 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switches with moulded cover plate in a recessed GI box including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) | 4 | Pt. | 4500 | 18000 |  | 4 | 18000
0
18 | Wiring for primary switch board consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A switch with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 2.5 sq FRLS copper wire mm in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing prewired switch board each consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A modular switch , safety shutters in a recessed/surface GI box including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) Note- Conduits shall be 16 SWG MS on surface and FRLS PVC for wall concealed | 1 | Pt. | 3800 | 3800 |  | 1 | 3800
0
19 | Supply installation testing and fixing 3 pin 20A , 240V , single Phase metal Clad industrial socket outlet with 20A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 2 | Nos. | 3200 | 6400 |  | 2 | 6400
0
20 | Supply installation testing and fixing 3 pin 25A/32A , 240V , single Phase metal Clad industrial socket outlet with 25A/32A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 4 | Nos. | 2500 | 10000 |  | 4 | 10000
0
21 | Supply installation testing and fixing 5 pin 25A/20A , 415V , single Phase metal Clad industrial socket outlet with 25A/20A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | RO | Nos. | 5500 |  |  | RO
0
22 | Supply , fixing & Laying 2.0mm Thick FRLS PVC conduits on surface or concealed complete with PVC junction boxes, cover plates, PVC bends, PVC saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . | [6 empty] | 0
0
i | 25 mm dia FRLS PVC conduit | 35 | Mtrs | 85 | 2975 |  |  | 0
ii | 20 mm dia FRLS PVC conduit | 25 | Mtrs | 65 | 1625 |  |  | 0
0
23 | Supply , fixing & Laying 16 SWG MS conduits on surface or concealed complete with PVC junction boxes, cover plates, bends, saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . | [6 empty] | 0
0
i | 25 mm dia 16 SWG MS conduit | RO | Mtrs | 180 |  |  |  | 0
ii | 20 mm dia 16 SWG MS conduit | RO | Mtrs | 160 |  |  |  | 0
0
24 | Supply and installation of flush mounted (Enhanced Category 6T 568 A or B) outlets with 2 mm thick GI box complete including cutting, chases, fixing of GI boxes and making good. The plastic shall be high impact, flame-retardant, UL rate thermoplastic. Dust cover / blank shall be provided to protect unused faceplate openings. Termination caps and plastic cover shall be provided to protect jack wiring. | [6 empty] | 0
i | Single outlet face plate with RJ-45 Jack with information outlet | 3 | Nos. | 800 | 2400 |  | 3 | 2400
ii | Duplex outlet face plate with RJ-45 Jack with information outlet | 1 | Nos. | 1500 | 1500 |  | 1 | 1500
0
25 | Supply,installtion testing and commisioning of Cat-6A UTP cables in existing Conduit complete as required for Telephone and Data System | 60 | Mtrs | 55 | 3300 |  | 52 | 2860 | 8 | 440
0
26 | Supplying,installation and commisioning of CAT-6A patch cords 2 mtrs. | 5 | Nos | 250 | 1250 |  |  | 0
0
27 | Supplying,installation and commisioning of CAT-6A patch cords 1 mtr. | 5 | Nos | 325 | 1625 |  |  | 0
0
28 | Installation of following light fixtures including connections and complete in all respects | [6 empty] | 0
0
i | Recessed Downlighter | 6 | No. | 100 | 600 |  |  | 0 | 8 | 800
0
iii | 2x28W LED Tube | 2 | No. | 150 | 300 |  |  | 0
iv | LED Strip Light ( Per Meter) | 5 | Mtrs | 25 | 125 |  |  | 0
iv | Signage | 1 | No. | 250 | 250 |  | 1 | 250 |  | 0
Total For Electrical Works - INR |  |  |  |  | 218800 |  |  | 209860 |  | 1240

## Dhaba-Plumbing
DHABA @ DIAL |  |  |  |  | DATE
MUFFIN DESIGN SOLUTIONS |  |  |  |  | REV
PLUMBING WORKS-WATER SUPPLY AND DRAINAGE WORKS |  |  |  |  | STATUS |  | Present Bill Amount (INR) |  | Final Bill (INR)
S.NO | DESCRIPTION | UNIT | QTY | RATE |  |  | Qty | Amount | Qty | Amount | Make
|  |  |  | SUPPLY + Insta | INSTALLATION | Total
I | INTERNAL WATER SYSTEM
(A) | WATER DISTRIBUTION FOR ALL THE AREAS
1 | Supplying, installing, fixing, jointing, testing and commissioning of approved make Chlorinated Polyvinyl Chloride pipes (CPVC) up to 50mm dia SDR.11, ASTM CTS, and above 50mm dia CPVC schedule 40 ASTM IPS. Fittings up to 50mm dia SDR.11, The fittings and specials such as tees, elbows, couplers, bends, enlargers etc, with CPVC brass threaded combination / transition specials such as male adapters brass threaded female adapters, brass FPT Tee, Brass FPT elbow, clamps, supports etc., where connection with metal is to be made including necessary drilling holes, chasing walls and the same original condition neately as directed by the Engineer in-charge. Joints to be made with CPVC solvent cement up to 50mm dia as per ASTM D-2846 and above 50mm dia primer P-70, and solvent confirming to ASTM F-4931 / 724. (DWS AND HWS)
1.1 | 20 mm dia (DWS & HWS) | Rmt | 10 | 225 |  | 2250 | 4 | 900
1.2 | 25 mm dia -287 rate | Rmt | 80 | 315 |  | 25200 | 20 | 6300
1.3 | 32 mm dia | Rmt | 50 | 405 |  | 20250 |  | 0
0
2 | Supplying, installing and testing, 32 mm dia (Screwed ends), approved make GM ball valves PN10 conforming to IS 1703 with unions etc., complete. | Nos | 1 | 1800 |  | 1800 |  | 0
0
3 | Supplying, installing and testing, Digital Water Flow meter for measuring water consumption for the unit with all the mounting accessories with 32mm dia inlet and outlet size. Endress Hauser Flow Meters. | Nos | 1 | 7500 |  | 7500 |  | 0
0
(A) | SUB-TOTAL FOR WATER DISTRIBUTION FOR ALL THE AREAS | [6 empty] | 0
0
(B) | INTERNAL SEWERAGE WATER SYSTEM + BOH/BAR AREA | [6 empty] | 0
1 | Supplying, fixing, testing and commissioning PVC, waste pipes (SWR) confirming to IS13592 :1992, type B with rubber ring (confirming IS:5382) joint inclusive of all necessary specials like bends, tees, offsets, door ends, junctions, cowls, etc., laid under floor/fixed on walls and in pipe shafts etc., complete.The quoted rate should include necessary earthwork,chasing in walls, making bores in walls, foundations and slabs and making good the chased surfaces, Anchor fasteners, supports like hanger supports, MS brackets with GI clamps, grip bolts, etc., complete. (Note:GI brackets/Supports shall be provided at every 1.5m c/c) | [6 empty] | 0
| INTERNAL DIA | [6 empty] | 0
1.1 | 50 mm dia | Rmt | 15 | 405 |  | 6075 |  | 0
1.2 | 75 mm dia | Rmt | 15 | 540 |  | 8100 |  | 0 | 9 | 4860
1.3 | 100 mm dia | Rmt | 20 | 765 |  | 15300 | 7 | 5355
0
2 | Supplying, fixing and testing PVC pressure pipes (6Kg/sqcm) confirming to IS 4985 for waste connection from wash basin to 'P' trap and sink outlet pipe with solvent joints, including all the fittings, laid above false ceiling concealed in wall etc, complete. The quoted rate should include necessary chasing in walls making good the same in C.M 1:4, necessary fittings viz., supports like Hi-tech supports, grip bolts elbows, tees etc., with G.I clamps and Brackets, Anchor fasteners, Grip bolts, nuts and bolts, etc, complete. | [6 empty] | 0
2.1 | 40mm dia | Rmt | 10 | 495 |  | 4950 | 3 | 1485 | 5 | 2475
0
3 | 40mm dia Flexible pipe for the drawing from the sink to the grease trap + from the sink to the outlet pipe | Rmt | 5 | 585 |  | 2925 |  | 0
0
4 | Sink Tap Goft Swivel Spout Chrome Plated Foam Flow 15mm, Sink Cock complete with all accessories to function | Nos. | 16 | 2250 |  | 36000 |  | 0
0
5 | Supply, Fixing, Installation & Commissioning of Bib Cock with nozzle of Jaquar make model no CON-049KN with wall flange and necessary fittings etc complete., | Each | 16 | 1845 |  | 29520 |  | 0
0
6 | Supply & Fixing of Floor drain with anticockroached trap Chilly make model number CCT-SG-129 Square Gypsy 129*129 mm & 31mm hole for waste pipe with necessary fittings etc., complete. | Each | 11 | 1080 |  | 11880 |  | 0 | 4 | 4320
0
7 | Supply & Fixing of Water heater of 15lts of Jaquar Make Model No. ELM-WHT-V025, Angular stop cock with wall flange of Jaquar Make Model No CON-CHR-059KN, 2nos 450mm long SS brided hose with M10x1nipple,15mm nut,O-ring & rubber wahser with necessary fittings etc., complete. Water heater to be rated for 7 Kg/cm2 inlet pressure. | Each | 1 | 15000 |  | 15000 |  | 0 | 1 | 15000
0
(B) | SUB -TOTAL FOR INTERNAL SEWERAGE WATER SYSTEM ALL AREAS |  |  |  |  | 186750 |  | 14040 |  | 26655
GRAND TOTAL FOR PHE WATER SUPPLY SYSTEM
EXCLUSIONS
1 | Sink is excluded from BOQ/ To be supplied by TFS
2 | Grease trap is excluded. Grease traps will be supplied by TFS/ Client
GENERAL NOTES :
1 | Necessary consumables like brass screws of approved make, dia and length, wooden plugs, white cement, sealants etc., required if any, shall be arranged by the contractor.
2 | All works to be carried out to relevant specifications as enumerated elsewhere in the Tender and as per the latest IS specifications.
3 | All chasing in wall for CPVC pipes shall be carried out by electric chasing machine.
4 | Any bore to be done in RCC wall, slab and beams shall be done by core cutting machine In consultation with structural consultants.

## PLUMBING (hidden)
Nourish-AHM-PHE BOQ |  |  |  | Rev: | R0
|  |  |  | Date: | 09.10.2023 | Previous Bill Amount(INR) |  | Present Bill Amount (INR) |  | Cumulative Amount (INR)
Item No. | Description | Unit | PO Qty | Rate | PO Amount | Qty | Amount | Qty | Amount | Qty | Amount | Make
S.NO | DESCRIPTION
I | INTERNAL WATER SYSTEM
(A) | WATER DISTRIBUTION FOR ALL THE AREAS
1 | Supplying, installing, fixing, jointing, testing and commissioning of approved make Chlorinated Polyvinyl Chloride pipes (CPVC) up to 50mm dia SDR.11, ASTM CTS, and above 50mm dia CPVC schedule 40 ASTM IPS. Fittings up to 50mm dia SDR.11, The fittings and specials such as tees, elbows, couplers, bends, enlargers etc, with CPVC brass threaded combination / transition specials such as male adapters brass threaded female adapters, brass FPT Tee, Brass FPT elbow, clamps, supports etc., where connection with metal is to be made including necessary drilling holes, chasing walls and the same original condition neately as directed by the Engineer in-charge. Joints to be made with CPVC solvent cement up to 50mm dia as per ASTM D-2846 and above 50mm dia primer P-70, and solvent confirming to ASTM F-4931 / 724. (DWS AND HWS)
1.1 | 20 mm dia (DWS & HWS) | Rmt | 4 | 612 | 2448 |  |  | 4 | 2448
1.2 | 25 mm dia -287 rate |  | 20 | 710 | 14200 |  |  | 20 | 14200
[5 empty] | 0 |  |  |  | 0
2 | Supplying, installing and testing, 32 mm dia (Screwed ends), approved make GM ball valves PN10 conforming to IS 1703 with unions etc., complete. | Nos | 1 | 1950 | 1950 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
3 | Supplying, installing and testing, Digital Water Flow meter for measuring water consumption for the unit with all the mounting accessories with 32mm dia inlet and outlet size. Endress Hauser Flow Meters. | Nos | 1 | 7500 | 7500 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
(A) | SUB-TOTAL FOR WATER DISTRIBUTION FOR ALL THE AREAS |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
(B) | INTERNAL SEWERAGE WATER SYSTEM + BOH/BAR AREA |  |  |  | 0 |  |  |  | 0
1 | Supplying, fixing, testing and commissioning PVC, waste pipes (SWR) confirming to IS13592 :1992, type B with rubber ring (confirming IS:5382) joint inclusive of all necessary specials like bends, tees, offsets, door ends, junctions, cowls, etc., laid under floor/fixed on walls and in pipe shafts etc., complete.The quoted rate should include necessary earthwork,chasing in walls, making bores in walls, foundations and slabs and making good the chased surfaces, Anchor fasteners, supports like hanger supports, MS brackets with GI clamps, grip bolts, etc., complete. (Note:GI brackets/Supports shall be provided at every 1.5m c/c) |  |  |  | 0 |  |  |  | 0
| INTERNAL DIA |  |  |  | 0 |  |  |  | 0
1.3 | 100 mm dia |  | 7 | 750 | 5250 |  |  | 7 | 5250
[5 empty] | 0 |  |  |  | 0
2 | Supplying, fixing and testing PVC pressure pipes (6Kg/sqcm) confirming to IS 4985 for waste connection from wash basin to 'P' trap and sink outlet pipe with solvent joints, including all the fittings, laid above false ceiling concealed in wall etc, complete. The quoted rate should include necessary chasing in walls making good the same in C.M 1:4, necessary fittings viz., supports like Hi-tech supports, grip bolts elbows, tees etc., with G.I clamps and Brackets, Anchor fasteners, Grip bolts, nuts and bolts, etc, complete. |  |  |  | 0 |  |  |  | 0
2.1 | 40mm dia | Rmt | 3 | 2100 | 6300 |  |  | 3 | 6300
[5 empty] | 0 |  |  |  | 0
3 | 40mm dia Flexible pipe for the drawing from the sink to the grease trap + from the sink to the outlet pipe |  | 2 | 650 | 1300 |  |  |  | 0
|  | Rmt |  |  | 0 |  |  |  | 0
4 | Mixer Tap |  | 1 | 3448 | 3448 |  |  |  | 0
|  | Rmt |  |  | 0 |  |  |  | 0
5 | Supply, Fixing, Installation & Commissioning of Bib Cock with nozzle of Jaquar make model no CON-049KN with wall flange and necessary fittings etc complete., |  | 4 | 2050 | 8200 |  |  |  | 0
|  | Nos. |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
(B) | SUB -TOTAL FOR INTERNAL SEWERAGE WATER SYSTEM ALL AREAS | Each |  |  | 0 |  |  |  | 0
GRAND TOTAL FOR PHE WATER SUPPLY SYSTEM
| GRAND TOTAL FOR PHE WATER SUPPLY SYSTEM |  |  |  | 50596 |  |  |  | 28198