## SUMMARY
Semolina Kitchens Pvt.Ltd.
Project : IDLI.COM
PO NO : | Semolina/PO/24-25/000082
Venodr Name : INVENTECH SOLUTIONS
SR NO | DISCRIPTION | PO VALUE | PREVIOUS BILL AMT (RA-1) | THIS BILL AMT (Final Bill) | CUMULATIVE AMT (previous + This Bill) | VARIANCE AMT
1 | CIVIL & INTERIOR | 849585 | 553503 | 159726 | 713229 | -136356
3 | PLUMBING | 84446 | 60723 | 0 | 60723 | -23723
2 | ELECTRICAL | 237575 | 233655 | 3800 | 237455 | -120
| NET TOTAL | 1171606 | 847881 | 163526 | 1011407 | -160199
| GST 18% | 210889.08 | 152618.58 | 29434.68 | 182053.26 | -28835.82
| TOTAL | 1382495.08 | 1000499.58 | 192960.68 | 1193460.26 | -189034.82

## CIVIL & INTERIOR
Nourish-AHM-PHE BOQ |  |  | Rev: | R0
|  |  | Date: | 09.10.2023 | Previous Bill Amount(INR) |  | Previous Bill Amount (INR) |  | Final Bill (INR)
Item No. | Description | PO Qty | Qty | Unit | Rate | Amount | Qty | Amount | Qty | Amount | Make
A | CIVIL
1 | NITCO GREY (BAYCLIFF FOLSSIL) TILE |  | 27 | Sq.m. | 2000 | 54000 | 27 | 54000
| Providing and Fixing appvd 2'X2' vitrified tile flooring with cement-sand mortar bedding of appd proportions as per the design & specifications. Joints to be filled properly with pigmented cement / epoxy grouts matching the tile. Flooring should be fixed in proper plumb line. Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing and grouting. | [6 empty] | 0
2 | SS Skirting - 3" height |  | 105 | R.ft. | 400 | 42000 |  | 0
Providing and Fixing appvd ss skirting fixed on plywood base as per the design & specifications. Joints to be filled properly with pigmented cement / epoxy grouts matching the tile. Skirting should be fixed in proper plumb line. Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing and grouting.
3 | Provided Vitrified Tiles |  | 505 | Sq.ft. | 200 | 101000 | 505 | 101000
| Providing and Fixing of 8"X12" PROVIDED VITRIFIED TILE on wall as appvd with cement-sand mortar bedding of appd proportions as per the design & specifications. Joints to be filled properly with pigmented cement / epoxy grouts matching the tile/stone. Flooring should be fixed in proper plumb line . Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing and grouting. | [6 empty] | 0
4 | Idli.com Front Counter in appvd solid surface |  | 16.2 | Sq.ft. | 1200 | 19440 | 16 | 19200
| Providing and Fixing of Pantry counter in appvd Acrylic solid surface with as per the design & specifications with plywood base & M.S. support. Counter should be fixed in proper plumb line Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing, grouting, sink/hob template cutouts, groove making, edge moulding and polishing. | [6 empty] | 0
5 | Wooden Veneer for Side Wall |  | 300 | Sq.ft. | 350 | 105000 | 153 | 53550
| Providing and Fixing of tiles with 2mm grooves & matte finish on wall as per approved the design & specifications. . Job to include cost of labour, material, cartage, loading, unloading, cutting, fixing and grouting. | [6 empty] | 0
0
TOTAL PART A : | [5 empty] | 321440 |  | 0
0
B | GYPSUM AND DESIGNER CEILING | [6 empty] | 0
1 | Gyprock Ceiling Ceiling |  | 209 | Sq. Ft | 150 | 31350 | 209 | 31350
| Providing and applying average 12 mm thk. Gyprock Ceiling Ceiling scraping and cleaning wherever required, to proper angle, line, level and plumb, ready to receive paint. Including protective, external corners of 20/25 SWG GI [India Gypsum or equivalent make], making all grooves, required scaffolding and protecting the surrounding areas and cleaning finished complete. | [7 empty] | 21 | 3150
3 | Cutouts in False ceiling for lights / Speakers etc. |  | 8 | Nos. | 200 | 1600 | 8 | 1600
| Making cutouts in the False ceiling for spot lights, speakers etc. | [6 empty] | 0 |  | 0
| RECESSED DOWN LIGHT WHITE POWDER COATED. LAMP :COB LED 12W, 4000K | [6 empty] | 0
4 | Miscellaneous Points, if any please specify | [6 empty] | 0
0
TOTAL PART B : | [5 empty] | 32950 |  | 0
0
C | PAINTING AND POLISHING | [6 empty] | 0
1 | Asian Royale Paint : Morning Glory |  | 209 | Sq.ft | 30 | 6270 |  | 0
| Sand papering the finished POP surface, filling in the cracks on the surface if any, Apply a coat of cement primer on the surface, Applying enamel putty making the surface smooth, applying one more coat of cement primer on the surface & applying two or more coats of approved Black Royale paint in approved hue to achieve uniform shade. | [6 empty] | 0 | 209 | 6270
2 | Zinc Yellow Duco paint and Glossy PU Finish for idli.com Laser Cut Screen on Counter Front |  | 374.5 | Sq.ft | 492 | 184254 | 69 | 33948
| Sand papering the finished MDF surface, filling in the cracks on the surface if any, Apply a coat of cement primer on the surface, Applying enamel putty making the surface smooth, applying one more coat of cement primer on the surface & applying two or more coats of approved Terracotta shade finish Duco paint in approved hue to achieve uniform shade. | [6 empty] | 0 | 305.5 | 150306
3 | EMBOSSED MDF SHEET FINISHED Pearl GREEN DUCO PAINT AND GLOSSY PU FOR FORNT COUNTER BACK PANEL |  | 46.5 | Sq.ft | 492 | 22878 | 46.5 | 22878
| Sand papering the finished MDF surface, filling in the cracks on the surface if any, Apply a coat of cement primer on the surface, Applying enamel putty making the surface smooth, applying one more coat of cement primer on the surface & applying two or more coats of approved Terracotta shade finish Duco paint in approved hue to achieve uniform shade. | [6 empty] | 0 |  | 0
4 | Miscellaneous Points, if any please specify |  |  |  |  | 0 |  | 0
0
TOTAL PART C : | [5 empty] | 213402 |  | 0
0
D | CARPENTERY | [6 empty] | 0
1 | IDLI.COM FRONT COUNTER |  | 53.34 | Sq.ft. | 2400 | 128016 | 53 | 127200
| Providing and Fixing Low Height storage of 20" height Glass finished with embossed MDF sheet finished green duco paint and glossy PU for IDLI.COM as approved using 19mm marine plywood / blockboard for shutters, shelves & divider panel & 8mm marine plywood for back ply & finished with appvd tile/ laminate as per the design complete with 6 inch toughened glass band with hardware, locks etc. Job to include cost of labour, material, cartage, loading,unloading, glazing, hardware, adhesives/resins, edgeband, etc. | [6 empty] | 0
| Insulsive of the cost of Clear toughened glass/Embossed mdf sheet | [6 empty] | 0
2 | IDLI.COM SIGNAGE BOARD |  | 1 | Nos | 42000 | 42000 |  | 0
| Providing and Fixing 1' high Green ACP base with 6" thick verticals of approved make and shade alongwith Logo in Front Lit Acrylic Signage of approved wattage and electrical points . Job to include cost of labour, material, cartage, loading,unloading, glazing, hardware, adhesives/resins, edgeband, etc. | [6 empty] | 0
3 | IDLI.COM DIGITAL MENU BOARD |  | 2 | Nos | 7500 | 15000 | 2 | 15000
| Providing and Fixing Digital Menu Board | [6 empty] | 0
4 | IDLI.COM FRONT, SIDE AND BACK UNDER COUNTER STORAGE |  | 30 | Sq.ft. | 2400 | 72000 | 30 | 72000
| Providing & fixing of Curry Kitchen Counter using 19mm comm/marine ply complete with drawers & pedestal storage units duly finished in appvd laminate as per the dwg. Counter to be finished in DominoTerazzo Corian of approved make and shade. Job to include cost of labour, material, cartage, loading,unloading, hardware, adhesives/resins, edgeband and appvd coatings/ polishing. | [6 empty] | 0
5 | FLUSH DOOR | [6 empty] | 0
| Flush Door: Providing and fixing single leaf solid core flush door 35mm thick factory made–., finished on both sides with 1.0mm thick laminate of approved shade as indicated in drawing. Shutter to be lipped on all sides with 6mm thick teak wood beading. Rate inclusive of PU polish, making visiion panels with 8mm th. glass, to size as per door details. Applicable hardwares to be considered for following doors according to requirement as per detailed drawings including below mentioned hardware-Door closer,SS Ball bearing Hinges ,SS foot operated Door stopper,SS Mortise Latch Lock / concealed dead lock,SS Mortise Handle.900x211 |  | 1 | Nos | 21777 | 21777 | 1 | 21777
6 | HOOD PANELING | [6 empty] | 0
| Providing & fixing partition made 18mm thk. HDHMR ply covering all sides of the visble faces of the hood, hung from the ceiling with threaded rods and cleats. All internal faces to be pasted with 1mm th. black laminate and outer visible faces to be PU painted as per approved shade, as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures. Measurement as per visble elevation |  | 2 | Nos | 1500 | 3000 |  | 0
TOTAL PART D : | [5 empty] | 281793
SUM TOTAL | [5 empty] | 849585 |  | 553503 |  | 159726
ADD SERVICE TAX
ADD GST | [5 empty] | 152925.3
GRAND TOTAL | [5 empty] | 1002510.3

## PLUMBING
Nourish-AHM-PHE BOQ |  |  |  | Rev: | R0
|  |  |  | Date: | 09.10.2023 | Previous Bill Amount(INR) |  | Present Bill Amount (INR) |  | Cumulative Amount (INR)
Item No. | Description | Unit | PO Qty | Rate | PO Amount | Qty | Amount | Qty | Amount | Qty | Amount | Make
S.NO | DESCRIPTION
I | INTERNAL WATER SYSTEM
(A) | WATER DISTRIBUTION FOR ALL THE AREAS
1 | Supplying, installing, fixing, jointing, testing and commissioning of approved make Chlorinated Polyvinyl Chloride pipes (CPVC) up to 50mm dia SDR.11, ASTM CTS, and above 50mm dia CPVC schedule 40 ASTM IPS. Fittings up to 50mm dia SDR.11, The fittings and specials such as tees, elbows, couplers, bends, enlargers etc, with CPVC brass threaded combination / transition specials such as male adapters brass threaded female adapters, brass FPT Tee, Brass FPT elbow, clamps, supports etc., where connection with metal is to be made including necessary drilling holes, chasing walls and the same original condition neately as directed by the Engineer in-charge. Joints to be made with CPVC solvent cement up to 50mm dia as per ASTM D-2846 and above 50mm dia primer P-70, and solvent confirming to ASTM F-4931 / 724. (DWS AND HWS)
1.1 | 20 mm dia (DWS & HWS) | Rmt | 4 | 612 | 2448 |  |  |  | 0
1.2 | 25 mm dia -287 rate |  | 18 | 710 | 12780 |  |  | 18 | 12780
[5 empty] | 0 |  |  |  | 0
2 | Supplying, installing and testing, 32 mm dia (Screwed ends), approved make GM ball valves PN10 conforming to IS 1703 with unions etc., complete. | Nos | 1 | 1950 | 1950 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
3 | Supplying, installing and testing, Digital Water Flow meter for measuring water consumption for the unit with all the mounting accessories with 32mm dia inlet and outlet size. Endress Hauser Flow Meters. | Nos | 1 | 15500 | 15500 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
(A) | SUB-TOTAL FOR WATER DISTRIBUTION FOR ALL THE AREAS |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
(B) | INTERNAL SEWERAGE WATER SYSTEM + BOH/BAR AREA |  |  |  | 0 |  |  |  | 0
1 | Supplying, fixing, testing and commissioning PVC, waste pipes (SWR) confirming to IS13592 :1992, type B with rubber ring (confirming IS:5382) joint inclusive of all necessary specials like bends, tees, offsets, door ends, junctions, cowls, etc., laid under floor/fixed on walls and in pipe shafts etc., complete.The quoted rate should include necessary earthwork,chasing in walls, making bores in walls, foundations and slabs and making good the chased surfaces, Anchor fasteners, supports like hanger supports, MS brackets with GI clamps, grip bolts, etc., complete. (Note:GI brackets/Supports shall be provided at every 1.5m c/c) |  |  |  | 0 |  |  |  | 0
| INTERNAL DIA |  |  |  | 0 |  |  |  | 0
1.3 | 100 mm dia |  | 6 | 1670 | 10020 |  |  | 6 | 10020
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
3 | 40mm dia Flexible pipe for the drawing from the sink to the grease trap + from the sink to the outlet pipe | Rmt | 5 | 650 | 3250 |  |  | 4.5 | 2925
[5 empty] | 0 |  |  |  | 0
4 | Mixer Tap |  | 1 | 6500 | 6500 |  |  | 1 | 6500
|  | Rmt |  |  | 0 |  |  |  | 0
5 | Supply, Fixing, Installation & Commissioning of Bib Cock with nozzle of Jaquar make model no CON-049KN with wall flange and necessary fittings etc complete., |  | 4 | 2050 | 8200 |  |  | 4 | 8200
|  | Rmt |  |  | 0 |  |  |  | 0
6 | Supply & Fixing of Floor drain with anticockroached trap Chilly make model number CCT-SG-129 Square Gypsy 129*129 mm & 31mm hole for waste pipe with necessary fittings etc., complete. |  | 11 | 350 | 3850 |  |  | 1 | 350
|  | Nos. |  |  | 0 |  |  |  | 0
7 | Supply & Fixing of Water heater of 15lts of Jaquar Make Model No. ELM-WHT-V025, Angular stop cock with wall flange of Jaquar Make Model No CON-CHR-059KN, 2nos 450mm long SS brided hose with M10x1nipple,15mm nut,O-ring & rubber wahser with necessary fittings etc., complete. Water heater to be rated for 7 Kg/cm2 inlet pressure. |  | 1 | 19948 | 19948 |  |  | 1 | 19948
|  | Each |  |  | 0 |  |  |  | 0
0
(B) | SUB -TOTAL FOR INTERNAL SEWERAGE WATER SYSTEM ALL AREAS | [7 empty] | 0
| GRAND TOTAL FOR PHE WATER SUPPLY SYSTEM |  |  |  | 84446 |  |  |  | 60723

## ELECTRICAL
IDLI.COM @ AHM
ELECTRICAL BOQ
DATE :
|  | AS per the PO |  |  |  | Previous Amount(INR) |  | Final Bill Amount(INR)
SR. No | DESCRIPTION | PO QTY. | UNIT | UNIT RATE | PO AMOUNT
S. No. | Description | Unit | Qty. | Rate | Amount
|  |  |  | (Rs.) | (Rs.)
1 | DISTRIBUTION BOARDS
Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof double door type distribution boards constructed from 16 SWG sheet steel IP 42 construction, finished with rust proof duly powder coated in approved shade with hinged gasketed door and housing the following complete with P.V.C. insulated copper busbars rated 200 amp with interconnections, neutral and earth bar assembly per phase, earthing terminals complete as approved by Architects.
Note : All MCBs in distribuition board for power circuits shall be of C curve
1.1 | Type A
| 1-63amp FP MCB with 3 single phase banks each comprising of 63A DP RCCB(100 mA) and 10 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 28000 | 28000 | 1 | 28000
0
1.2 | Type B | [5 empty] | 0
0
| 1-20 amp DP MCB + DP RCCB ( 100mA) and 4 nos. 6/16/20/25 amps SP 10 kA MCB(Type D) with thermal magnetic protective releases out goings. | 1 | Set | 7500 | 7500 | 1 | 7500
0
2 | Supply installation testing and commisioning 1.2 kVA online ( 1ph input and 1ph output) UPS with 15 Min power back up complete with in buit Static by pass switch , Mannual external maintenance by pass switch , Rectifiers , Sealed MF batteries etc as required | 1 | No. | 12000 | 12000 | 1 | 12000
0
3 | Supply, laying, testing & commissioning of following sizes of Cu. conductor 1.1 kV grade, armoured, XLPE insulated FRLS LT Cables/ Control Cables including necessary cleats, clamps etc. (Cables shall be partly laid in Pipes, O/H cable tray, on wall as required ) | [5 empty] | 0
0
3.1 | 4C – 16.0 (Cu.) FRLS Armoured XLPE Cable * | 30 | Mtrs | 1050 | 31500 | 30 | 31500
3.2 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 10 | Mtrs | 270 | 2700 | 10 | 2700
0
| * Approximate and shall be as per point of supply from Airport Panel/ Isolator | [5 empty] | 0
0
4 | Supply, erection, testing & commissioning of following sizes of cable end terminations with Single compression gland for 1.1 kV grade, XLPE insulated, Cu Conductor cable | [5 empty] | 0
0
4.1 | 4C – 16.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 750 | 1500 | 2 | 1500
4.2 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 500 | 1000 | 2 | 1000
0
5 | Wiring for DB Submains with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in surface/concealed MS surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and making suitable end termination with copper lugs complete as required and as below | [5 empty] | 0
0
5.1 | 2 x 6 sq.mm + 1 No. 4 Sq. mm in 25 mm dia MS Conduit | 15 | Mtrs | 475 | 7125 | 15 | 7125
5.2 | 2 x 4 sq.mm + 1 No. 2.5 Sq. mm in 25 mm dia MS Conduit | 90 | Mtrs | 350 | 31500 | 90 | 31500
0
6 | Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required | [5 empty] | 0
0
6.1 | 25X3 mm GI Strip | RO | Mtrs | 200 |  | RO
6.2 | 8 SWG Copper Wire | 20 | Mtrs | 90 | 1800 |  | 0
6.3 | 8 SWG GI Wire | 50 | Mtrs | 25 | 1250 | 5 | 125
6.4 | 1 Core 4.0 Sq. Mm FRLS Green Wire | 25 | Mtrs | 45 | 1125 | 15 | 675
0
7 | Supply, erection, testing & commissioning of prefabricated GI Perforated type cable trays including Tees / Bends / Crossing / Reducers / Couping to be laid in cable trench, overhead on wall or hanged from ceiling complete with all accessories as required including support at every 1500mm as required | [5 empty] | 0
0
7.1 | 150 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | RO | Mtrs | 700 |  | RO
0
8 | Wiring for MCB controlled normal primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 3 | Pt | 1800 | 5400 | 3 | 5400
0
9 | Wiring for secondary MCB controlled normal light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 3 | Pt | 850 | 2550 | 3 | 2550
0
10 | Wiring for MCB controlled Emergency primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 1 | Pt | 2200 | 2200 | 1 | 2200
0
11 | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 1 | Pt | 1200 | 1200 | 1 | 1200
0
12 | Wiring for a 5 pin 240 volt 6 amp single phase and neutral switch socket outlet with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / ceiling including cost of providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade wires and including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and providing and fixing of a combined 5 pin 240 volt 6 amp socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires complete as requied( Switch and socket shall be as approved by the architect / Client) | 2 | Pt. | 2000 | 4000 | 2 | 4000 |  |  | 6
0
13 | Wiring same as in Item 12 above looped from an adjacent 6 amp switch socket outlet as required and providing and fixing of a modular type 5 pin 240 Volt 6 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole switch in a recessed GI boxes with internal wiring and moulded front plates complete as required. ( Switch and socket shall be as approved by the architect / Client) | 2 | Pt. | 1200 | 2400 |  | 0
0
14 | Same as above but switch and socket provided at separate location including wiring berween switch and socket and complete as required | RO | Pt. |  |  | RO
0
15 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 3 | Pt. | 2800 | 8400 | 3 | 8400 |  |  | 19
0
16 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 4.0 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 9 | Pt. | 3250 | 29250 | 9 | 29250
0
17 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (2 outlets wired on 1 circuit) with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 4.0 sq mm upto the first outlet and 2.5 sq mm from first to the second outlet in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing of two sets of 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switches with moulded cover plate in a recessed GI box including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) | 3 | Pt. | 4200 | 12600 | 3 | 12600
0
18 | Wiring for primary switch board consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A switch with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 2.5 sq FRLS copper wire mm in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing prewired switch board each consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A modular switch , safety shutters in a recessed/surface GI box including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) Note- Conduits shall be 16 SWG MS on surface and FRLS PVC for wall concealed | 1 | Pt. | 4500 | 4500 |  | 0
0
19 | Supply installation testing and fixing 3 pin 20A , 240V , single Phase metal Clad industrial socket outlet with 20A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 4 | Nos. | 3200 | 12800 | 3 | 9600
0
20 | Supply installation testing and fixing 3 pin 25A/32A , 240V , single Phase metal Clad industrial socket outlet with 25A/32A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 4 | Nos. | 3500 | 14000 | 2 | 7000
0
21 | Supply installation testing and fixing 5 pin 25A/20A , 415V , single Phase metal Clad industrial socket outlet with 25A/20A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | RO | Nos. | 5500 |  | RO
0
22 | Supply , fixing & Laying 2.0mm Thick FRLS PVC conduits on surface or concealed complete with PVC junction boxes, cover plates, PVC bends, PVC saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . | [5 empty] | 0
0
i | 25 mm dia FRLS PVC conduit | 35 | Mtrs |  | 0 |  | 0
ii | 20 mm dia FRLS PVC conduit | 25 | Mtrs |  | 0 |  | 0
0
23 | Supply , fixing & Laying 16 SWG MS conduits on surface or concealed complete with PVC junction boxes, cover plates, bends, saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . | [5 empty] | 0
0
i | 25 mm dia 16 SWG MS conduit | RO | Mtrs | 180 |  |  | 0
ii | 20 mm dia 16 SWG MS conduit | RO | Mtrs | 160 |  | 148 | 23680
0
24 | Supply and installation of flush mounted (Enhanced Category 6T 568 A or B) outlets with 2 mm thick GI box complete including cutting, chases, fixing of GI boxes and making good. The plastic shall be high impact, flame-retardant, UL rate thermoplastic. Dust cover / blank shall be provided to protect unused faceplate openings. Termination caps and plastic cover shall be provided to protect jack wiring. | [5 empty] | 0
i | Single outlet face plate with RJ-45 Jack with information outlet | 3 | Nos. | 800 | 2400 | 3 | 2400
ii | Duplex outlet face plate with RJ-45 Jack with information outlet | 1 | Nos. | 1500 | 1500 | 1 | 1500
0
25 | Supply,installtion testing and commisioning of Cat-6A UTP cables in existing Conduit complete as required for Telephone and Data System | 60 | Mtrs | 55 | 3300 |  | 0 | 60 | 3300
0
26 | Supplying,installation and commisioning of CAT-6A patch cords 2 mtrs. | 5 | Nos | 250 | 1250 |  | 0
0
27 | Supplying,installation and commisioning of CAT-6A patch cords 1 mtr. | 5 | Nos | 325 | 1625 |  | 0
0
28 | Installation of following light fixtures including connections and complete in all respects | [5 empty] | 0
0
i | Recessed Downlighter | 5 | No. | 100 | 500 |  | 0 | 5 | 500
0
iii | 2x28W LED Tube | 2 | No. | 150 | 300 |  | 0
iv | LED Strip Light ( Per Meter) | 6 | Mtrs | 25 | 150 |  | 0
iv | Signage | 1 | No. | 250 | 250 | 1 | 250 |  | 0
Total For Electrical Works - INR |  |  |  |  | 237575 |  | 233655 |  | 3800