## SUMMARY
Semolina Kitchens Pvt.Ltd.
Project : Nourish
PO NO : | Semolina/PO/24-25/000080
Venodr Name : INVENTECH SOLUTIONS
SR NO | DISCRIPTION | PO VALUE | PREVIOUS BILL AMT (RA-1) | THIS BILL AMT (Final Bill) | CUMULATIVE AMT (Previous + This Bill) | VARIANCE AMT
1 | Civil & Interior | 691668.82 | 609713.796 | 52948.6 | 662662.396 | -29006.424
2 | PLUMBING | 41950 | 33125 | 0 | 33125 | -8825
3 | ELECTRICAL | 209930 | 169010 | 945 | 169955 | -39975
| NET TOTAL | 943548.82 | 811848.796 | 53893.6 | 865742.396 | -29006.424
| GST 18% | 169838.7876 | 146132.7833 | 9700.848 | 155833.6313 | -5221.1563
| TOTAL | 1113387.6076 | 957981.5793 | 63594.448 | 1021576.0273 | -34227.5803

## Civil & Interior1
Nourish | [6 empty] | Previous Bill Amount (INR) |  | Final Bill Amount (INR)
All componets of carpentry (Plywood / WPC boards / Gypsum boards) to be of 1Hr Fire rating | [6 empty] | Qty | Amount | Qty | Amount
SIMNA
Sl/no | Item | Description | Qty | Unit | Rate | Amount
CIVIL WORKS
A | M.S. FRAMING
1 | Inspection Chamber - 600 x600 x350(external dimensions) | Providing Inspection chamber with 100 mm thk Siporex walls Plasterd with cement mortar & waterproof chemical .with necessary PCC bedding to required slope. | 2 | nos | 6000 | 12000 | 2 | 12000
2 | Inspection Chamber cover - (Perforated S.S) 600 x600mm | Providing and fixing of S.S. perforated Inspection chamber cover with necessary fittings | 2 | nos | 9000 | 18000 | 2 | 18000
0
0
[6 empty] | 0 |  | 0
CARPENTRY WORKS | [5 empty] | 0 |  | 0
C | PARTITIONS/ BOXING |  |  |  |  | 0 |  | 0
1 | SINGLE SIDE PARTITION | P/F Full Ht Single Side Partition, in front of existing airport walls, with Framework of MS Box section 40x40mm, 18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame, fixed to the floor and soffit of slab/beam with MS cleats bolted as required, with rust-free treatment & enamel paint of colour as specified ready to recieve 12mm th. Bison board as base(upto 75 mm above BOFC as per site). Rate to include making provsion for electrical wiring, necessary hardware, wastage, scafollding at all levels etc complete. Measurement as per elevation | 43.6 | Sq.Mt | 2520 | 109872 | 37.3448 | 94108.896
3 | Overhead Storage | Providing and fixing of Overhead storage with - 18mm FR+WP Ply carcass - 18mm FR+WP Ply shutters -Inside finished with laminate (as per finishes schedule) - edges finished with plastic edge beading ,To take finished as per design & details | 2.458 | Sq.Mt | 25840 | 63514.72 | 2.46 | 63566.4
4 | WPC fret cut panel over Front facade | Providing and fixing of 25mm THK WPC fret cut panel over front counter facade , as per design and details , to take finish coat as per finish schedule | 2.34 | Sq.Mt | 12450 | 29133 | 3.24 | 40338
[6 empty] | 0 |  | 0
D | DOORS / FIXED GLASS |  |  |  |  | 0 |  | 0
[6 empty] | 0 |  | 0
1 | Door- D1 (900W x 2100 H | Providing & fixing of Flush code door with - 50x100 Wood Frame - 35mm thk flush core shutter , edge to be sealed with teak wood lipping - S.S. handles with Lock - All to be painted to approved specs - with necessary fittings & iron mongery all as per design , to receive finishes as per schedule | 1 | Nos | 25000 | 25000 | 1 | 25000
[6 empty] | 0 |  | 0
E | STORAGE UNITS/ SHELVES |  |  |  |  | 0 |  | 0
1 | Front counter 3.73L x 0.75D x 0.90 H | Providing and fabrication of Front Counter unit with - 18mm thk HDHMR carcass as per design - 18mm thk HDHMR Shutters and shelves -Inside finished with laminate (as per finishes schedule) - Outside finished with Teakwood - Edges to be finished with 2mm plastic edge binding -Cabinet counter-top prepped to receiveSolid surface as per details and design. | 1 | Nos | 113029 | 113029 | 1 | 113029
[6 empty] | 0 |  | 0
FALSE CEILING | [5 empty] | 0 |  | 0
F | FLOORING & WALL CLADDING |  |  |  |  | 0 |  | 0
1 | Gypsum ceiling | Providing & fixing of false ceiling with fire rated Gypsum board , incl of all cuts & grooves required for services & lights ,Hvac etc not to be paid separate , to receive finishes as per specifications | 16.78 | Sq.Mt | 1200 | 20136 |  | 0 | 16.78 | 20136
Note: Engineered Stone cost to be priced separately and has been included in the Finishes schedule | [5 empty] | 0 |  | 0
FINISHES | [5 empty] | 0 |  | 0
G | FLOORING & WALL CLADDING |  |  |  |  | 0 |  | 0
1 | Servery & BOH flooring | Providing & Laying of 600x600 mm Vitrified tiles flooring (Base price -Rs.60/Sft)with Cement mortar, as per finishes schedule | 18.5 | Sq.Mt | 1990 | 36815 | 18.5 | 36815
2 | Servery & BOH flooring Skirting | Providing & Laying of 100 high skirting with same 600x600 mm Vitrified tiles used for flooring, with cement mortar, as per finishes schedule | 27.8 | R.Mt | 250 | 6950 |  | 0
3 | Front counter skirting-12mm thk. WPC | Providing & Laying of 100 high with 12mm THK WPC board skirting , to take finishes as per schedule | 3.73 | R.Mt | 2550 | 9511.5 | 3.73 | 9511.5
4 | Ceramic tile cladding | Providing & Fixing of Ceramic tile (600 x 300mm - Kajaria-Oxford Blanco)cladding with cement mortar. over BOH & Dishwashing walls ,as per design ,details &finishes specified. | 44.5 | Sq.Mt | 2100 | 93450 | 44.5 | 93450
5 | Green Ceramic tile cladding (Over Servery rear wall) | Providing & Fixing of Green Ceramic tile (100 x 100mm , Base price rs.100/sft)cladding with cement mortar over Servery rear wall as per design ,details &finishes specified. | 2.05 | Sq.Mt | 3200 | 6560 | 2.05 | 6560
6 | 15/18 mm THK. engineered stone on rear countertop | Providing and installing 15/18mm thick engineered stone counter-top fixed to Ply carcass/ base as per design & detail | 1.89 | Sq.Mt | 25500 | 48195 | 1.89 | 48195
7 | Veneer Cladding finished with Stainer + polish (Impulse unit, Bulkhead & Overhead storage & Side walls) | Providing and installing Pinewood Veneer over surfaces ,finished with necessary coats of Polish as per design & detail | 2.34 | Sq.Mt | 7500 | 17550 |  | 0
8 | Wallpaper for side wall (Slender branched leaves) | Providing and installing Custom made wallpaper as per design & detail | 6.94 | Sq.Mt | 3640 | 25261.6 |  | 0 | 6.94 | 25261.6
9 | MOH WALL | P/fixing glazed ceramic (Kajaria) Veda Bianaca Décor (450x450nn) Wall tiles,in MOH back bison board partition in per approved pattern, setting the tiles in appropriate adhesive as per manufacturer's specifications, joints filled and finished neat with epoxy grout as/spec | 7 | Sq.Mt | 1820 | 12740 | 7 | 12740
10 | MOH WALL | Trophical Wallpaper fixed on shera board paneling | 7 | Sq.Mt | 5200 | 36400 | 7 | 36400
H | PAINTING |  |  |  |  | 0 |  | 0
1 | Paint Finish (A) (Locker rooms + Gyp Ceiling) | Primer + Emulsion Paint over Training room walls & Area above tiles in BOH & Dishwash area & Gypsum ceiling | 16.78 | Sq.Mt | 450 | 7551 |  | 0 | 16.78 | 7551
IMP NOTE: The description of works provided above along with the drawings are meant only to describe the intent for the design. The vendor/ contractor is expected to develop his/her details/shop drawings as required to fulfil the design intent whilst ensuring functional compliance and structural stability. These details are to be reviewed with the architect/ project manager prior to commencement of work at site. If there are any discrepancies between the drawing and the BOQ provided, please consult/ clarify with the designer. | [5 empty] | 691668.82 |  | 609713.796 |  | 52948.6
No wastage % considered for Interior works

## Plumbing
Nourish-AHM-PHE BOQ |  |  |  | Rev: | R0
|  |  |  | Date: | 09.10.2023 | Previous Bill Amount(INR) |  | Previous Bill Amount (INR) |  | Final bill Amount (INR)
Item No. | Description | Unit | PO Qty | Rate | PO Amount | Qty | Amount | Qty | Amount | Qty | Amount | Make
S.NO | DESCRIPTION
I | INTERNAL WATER SYSTEM
A | WATER DISTRIBUTION FOR ALL THE AREAS
1 | Supplying, installing, fixing, jointing, testing and commissioning of approved make Chlorinated Polyvinyl Chloride pipes (CPVC) up to 50mm dia SDR.11, ASTM CTS, and above 50mm dia CPVC schedule 40 ASTM IPS. Fittings up to 50mm dia SDR.11, The fittings and specials such as tees, elbows, couplers, bends, enlargers etc, with CPVC brass threaded combination / transition specials such as male adapters brass threaded female adapters, brass FPT Tee, Brass FPT elbow, clamps, supports etc., where connection with metal is to be made including necessary drilling holes, chasing walls and the same original condition neately as directed by the Engineer in-charge. Joints to be made with CPVC solvent cement up to 50mm dia as per ASTM D-2846 and above 50mm dia primer P-70, and solvent confirming to ASTM F-4931 / 724. (DWS AND HWS)
1.1 | 25 mm dia | Rmt | 20 | 710 | 14200 |  |  | 20 | 14200 |  | 0
[5 empty] | 0 |  |  |  | 0
2 | Supplying, installing and testing approved make GM ball valves PN10 conforming to IS 1703 with unions etc., complete. |  |  |  | 0 |  |  |  | 0
i | 25 mm dia (Screwed ends) | Nos | 1 | 1950 | 1950 |  |  | 1 | 1950
[5 empty] | 0 |  |  |  | 0
3 | Digital Water Flow meter for measuring water consumption for the unit with all the mounting accessories with 25mm dia inlet and outlet size. Endress Hauser Flow Meters. | Nos | 1 | 8200 | 8200 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
A) | SUB-TOTAL FOR WATER DISTRIBUTION FOR ALL THE AREAS |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
II | INTERNAL DRAINAGE SYSTEM |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
B | INTERNAL SEWERAGE WATER SYSTEM + BOH/BAR AREA |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
1 | Supplying, fixing, testing and commissioning PVC, waste pipes (SWR) confirming to IS13592 :1992, type B with rubber ring (confirming IS:5382) joint inclusive of all necessary specials like bends, tees, offsets, door ends, junctions, cowls, etc., laid under floor/fixed on walls and in pipe shafts etc., complete.The quoted rate should include necessary earthwork,chasing in walls, making bores in walls, foundations and slabs and making good the chased surfaces, Anchor fasteners, supports like hanger supports, MS brackets with GI clamps, grip bolts, etc., complete. (Note:GI brackets/Supports shall be provided at every 1.5m c/c) |  |  |  | 0 |  |  |  | 0
| I) INTERNAL AREA |  |  |  | 0 |  |  |  | 0
ii | 100 mm dia | Rmt | 7 | 1250 | 8750 |  |  | 6.5 | 8125
[5 empty] | 0 |  |  |  | 0
2 | Supplying, fixing and testing PVC pressure pipes (6Kg/sqcm) confirming to IS 4985 for waste connection from wash basin to 'P' trap and sink outlet pipe with solvent joints, including all the fittings, laid above false ceiling concealed in wall etc, complete. The quoted rate should include necessary chasing in walls making good the same in C.M 1:4, necessary fittings viz., supports like Hi-tech supports, grip bolts elbows, tees etc., with G.I clamps and Brackets, Anchor fasteners, Grip bolts, nuts and bolts, etc, complete. |  |  |  | 0 |  |  |  | 0
2.1 | 40mm dia | Rmt | 3 | 550 | 1650 |  |  | 3 | 1650
[5 empty] | 0 |  |  |  | 0
3 | 40mm dia Flexible pipe for the drawing from the sink to the grease trap + from the sink to the outlet pipe | Rmt | 1 | 650 | 650 |  |  | 1 | 650
[5 empty] | 0 |  |  |  | 0
4 | Sink Tap Goft Swivel Spout Chrome Plated Foam Flow 15mm, Sink Cock complete with all accessories to function | Nos. | 1 | 4500 | 4500 |  |  | 1 | 4500
[5 empty] | 0 |  |  |  | 0
5 | Supply, Fixing, Installation & Commissioning of Bib Cock with nozzle of Jaquar make model no CON-049KN with wall flange and necessary fittings etc complete., | Each | 1 | 2050 | 2050 |  |  | 1 | 2050
(B) | SUB -TOTAL FOR INTERNAL SEWERAGE WATER SYSTEM ALL AREAS
| GRAND TOTAL FOR PHE WATER SUPPLY SYSTEM |  |  |  | 41950 |  |  |  | 33125 |  | 0

## ELECTRICAL
Nourish @ AHM
ELECTRICAL BOQ
DATE :
|  | AS per the PO |  |  |  | Previous Bill Amount(INR) | Previous Bill Amount(INR) |  | Final bill Amount(INR)
SR. No | DESCRIPTION | PO QTY. | UNIT | UNIT RATE | PO AMOUNT
S. No. | Description | Unit | Qty. | Rate | Amount
|  |  |  | (Rs.) | (Rs.)
1 | DISTRIBUTION BOARDS
Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof double door type distribution boards constructed from 16 SWG sheet steel IP 42 construction, finished with rust proof duly powder coated in approved shade with hinged gasketed door and housing the following complete with P.V.C. insulated copper busbars rated 200 amp with interconnections, neutral and earth bar assembly per phase, earthing terminals complete as approved by Architects.
Note : All MCBs in distribuition board for power circuits shall be of C curve
1.1 | Type A
| 1-63amp FP MCB with 3 single phase banks each comprising of 63A DP RCCB(100 mA) and 8 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 25830 | 25830 |  | 1 | 25830
[5 empty] | 0 |  |  | 0
1.2 | Type B |  |  |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
| 1-20 amp DP MCB + DP RCCB ( 100mA) and 4 nos. 6/16/20/25 amps SP 10 kA MCB(Type D) with thermal magnetic protective releases out goings. | 1 | Set | 6500 | 6500 |  | 1 | 6500
[5 empty] | 0 |  |  | 0
2 | Supply installation testing and commisioning 1.2 kVA online ( 1ph input and 1ph output) UPS with 15 Min power back up complete with in buit Static by pass switch , Mannual external maintenance by pass switch , Rectifiers , Sealed MF batteries etc as required | 1 | No. | 12000 | 12000 |  | 1 | 12000
[5 empty] | 0 |  |  | 0
3 | Supply, laying, testing & commissioning of following sizes of Cu. conductor 1.1 kV grade, armoured, XLPE insulated FRLS LT Cables/ Control Cables including necessary cleats, clamps etc. (Cables shall be partly laid in Pipes, O/H cable tray, on wall as required ) |  |  |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
3.1 | 4C – 16.0 (Cu.) FRLS Armoured XLPE Cable * | 30 | Mtrs | 850 | 25500 |  | 30 | 25500
3.2 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 10 | Mtrs | 270 | 2700 |  | 10 | 2700
[5 empty] | 0 |  |  | 0
| * Approximate and shall be as per point of supply from Airport Panel/ Isolator |  |  |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
4 | Supply, erection, testing & commissioning of following sizes of cable end terminations with Single compression gland for 1.1 kV grade, XLPE insulated, Cu Conductor cable |  |  |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
4.1 | 4C – 16.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 750 | 1500 |  | 2 | 1500
4.2 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 500 | 1000 |  | 2 | 1000
[5 empty] | 0 |  |  | 0
5 | Wiring for DB Submains with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in surface/concealed MS surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and making suitable end termination with copper lugs complete as required and as below |  |  |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
5.1 | 2 x 6 sq.mm + 1 No. 4 Sq. mm in 25 mm dia MS Conduit | 15 | Mtrs | 475 | 7125 |  | 15 | 7125
5.2 | 2 x 4 sq.mm + 1 No. 2.5 Sq. mm in 25 mm dia MS Conduit | 70 | Mtrs | 150 | 10500 |  | 70 | 10500
[5 empty] | 0 |  |  | 0
6 | Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required |  |  |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
6.2 | 8 SWG Copper Wire | 20 | Mtrs | 200 | 4000 |  | 20 | 4000
6.3 | 8 SWG GI Wire | 50 | Mtrs | 90 | 4500 |  | 30 | 2700
6.4 | 1 Core 4.0 Sq. Mm FRLS Green Wire | 25 | Mtrs | 25 | 625 |  | 25 | 625
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
8 | Wiring for MCB controlled normal primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 3 | Pt | 1500 | 4500 |  | 3 | 4500
[5 empty] | 0 |  |  | 0
9 | Wiring for secondary MCB controlled normal light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 3 | Pt | 850 | 2550 |  | 3 | 2550
[5 empty] | 0 |  |  | 0
10 | Wiring for MCB controlled Emergency primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 1 | Pt | 2200 | 2200 |  | 1 | 2200
[5 empty] | 0 |  |  | 0
11 | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 1 | Pt | 1200 | 1200 |  | 1 | 1200
[5 empty] | 0 |  |  | 0
12 | Wiring for a 5 pin 240 volt 6 amp single phase and neutral switch socket outlet with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / ceiling including cost of providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade wires and including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and providing and fixing of a combined 5 pin 240 volt 6 amp socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires complete as requied( Switch and socket shall be as approved by the architect / Client) | 2 | Pt. | 2000 | 4000 |  | 2 | 4000
[5 empty] | 0 |  |  | 0
13 | Wiring same as in Item 12 above looped from an adjacent 6 amp switch socket outlet as required and providing and fixing of a modular type 5 pin 240 Volt 6 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole switch in a recessed GI boxes with internal wiring and moulded front plates complete as required. ( Switch and socket shall be as approved by the architect / Client) | 2 | Pt. | 1200 | 2400 |  | 2 | 2400
[5 empty] | 0 |  |  | 0
15 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 3 | Pt. | 2500 | 7500 |  |  | 0
[5 empty] | 0 |  |  | 0
16 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 4.0 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 11 | Pt. | 3050 | 33550 |  | 11 | 33550
[5 empty] | 0 |  |  | 0
17 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (2 outlets wired on 1 circuit) with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 4.0 sq mm upto the first outlet and 2.5 sq mm from first to the second outlet in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing of two sets of 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switches with moulded cover plate in a recessed GI box including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) | 3 | Pt. | 3800 | 11400 |  |  | 0
[5 empty] | 0 |  |  | 0
18 | Wiring for primary switch board consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A switch with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 2.5 sq FRLS copper wire mm in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing prewired switch board each consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A modular switch , safety shutters in a recessed/surface GI box including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) Note- Conduits shall be 16 SWG MS on surface and FRLS PVC for wall concealed | 1 | Pt. | 4000 | 4000 |  | 1 | 4000
[5 empty] | 0 |  |  | 0
19 | Supply installation testing and fixing 3 pin 20A , 240V , single Phase metal Clad industrial socket outlet with 20A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 2 | Nos. | 3200 | 6400 |  | 2 | 6400
[5 empty] | 0 |  |  | 0
20 | Supply installation testing and fixing 3 pin 25A/32A , 240V , single Phase metal Clad industrial socket outlet with 25A/32A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 5 | Nos. | 2500 | 12500 |  | 1 | 2500
[5 empty] | 0 |  |  | 0
22 | Supply , fixing & Laying 2.0mm Thick FRLS PVC conduits on surface or concealed complete with PVC junction boxes, cover plates, PVC bends, PVC saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . |  |  |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
i | 25 mm dia FRLS PVC conduit | 35 | Mtrs | 85 | 2975 |  |  | 0
ii | 20 mm dia FRLS PVC conduit | 25 | Mtrs | 65 | 1625 |  |  | 0
[5 empty] | 0 |  |  | 0
24 | Supply and installation of flush mounted (Enhanced Category 6T 568 A or B) outlets with 2 mm thick GI box complete including cutting, chases, fixing of GI boxes and making good. The plastic shall be high impact, flame-retardant, UL rate thermoplastic. Dust cover / blank shall be provided to protect unused faceplate openings. Termination caps and plastic cover shall be provided to protect jack wiring. |  |  |  | 0 |  |  | 0
i | Single outlet face plate with RJ-45 Jack with information outlet | 3 | Nos. | 800 | 2400 |  | 3 | 2400
ii | Duplex outlet face plate with RJ-45 Jack with information outlet | 1 | Nos. | 1500 | 1500 |  |  | 0
[5 empty] | 0 |  |  | 0
25 | Supply,installtion testing and commisioning of Cat-6A UTP cables in existing Conduit complete as required for Telephone and Data System | 60 | Mtrs | 55 | 3300 |  | 56 | 3080 | 4 | 220
[5 empty] | 0 |  |  | 0
26 | Supplying,installation and commisioning of CAT-6A patch cords 2 mtrs. | 5 | Nos | 250 | 1250 |  |  | 0
[5 empty] | 0 |  |  | 0
27 | Supplying,installation and commisioning of CAT-6A patch cords 1 mtr. | 5 | Nos | 325 | 1625 |  |  | 0
[5 empty] | 0 |  |  | 0
28 | Installation of following light fixtures including connections and complete in all respects |  |  |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
i | Recessed Downlighter | 6 | No. | 100 | 600 |  |  | 0 | 6 | 600
[5 empty] | 0 |  |  | 0
iii | 2x28W LED Tube | 2 | No. | 150 | 300 |  |  | 0
iv | LED Strip Light ( Per Meter) | 5 | Mtrs | 25 | 125 |  |  | 0 | 5 | 125
iv | Signage | 1 | No. | 250 | 250 |  | 1 | 250 |  | 0
Total For Electrical Works - INR |  |  |  |  | 209930 |  |  | 169010 |  | 945