## SUMMARY
Billing Summary - A-09 Flying Bites , T-3 Lucknow
S.NO. | ITEM | PO Amount | RA-01 | RA-02 | RA-03 | Cummulative | Variation
|  |  | Amount | Amount | Amount | Amount |  | RA 3 % of billing
1 | C&I | 2345270 | 1000188.07 | 661934.3191 | 499556.1304 | 2161678.5194 | -183591.4806 | 21.3006
2 | Plumbing | 72250 | 25552 | 34056.5869 | 25702.2128 | 85310.7997 | 13060.7997 | 35.574
3 | Electrical | 592375 | 0 | 263511.6418 | 198869.9669 | 462381.6087 | -129993.3913 | 33.5716
4 | HVAC | 240750 | 194350 | 31658.2357 | 23892.1979 | 249900.4335 | 9150.4335 | 9.9241
5 | Lighting | 201800 | 0 | 96485.6683 | 72816.903 | 169302.5713 | -32497.4287 | 36.0837
6 | CCTV | 63900 | 0 | 30650.9282 | 23127.5991 | 53778.5273 | -10121.4727 | 36.1934
| TOTAL AMOUNT | 3516345 | 1220090.07 | 1118297.38 | 843965.01 | 3182352.46 | -333992.54
Po Required
| Additional Item | Qty | Rate | Amount
| Sink | 1 | 6500 | 6500
| Electrical Meter | 1 | 22500 | 22500
| GRID CEILING | 67.29 | 2400 | 161496
| Total |  |  | 190496
[5 empty] | Credit note |  |  | 190496
[5 empty] | Po to Come | 190496

## C&I
RAB-02 -Civil & Interior Work - Flying Bytes ( A-09) | [6 empty] | QTY |  |  |  |  | AMOUNT
SN. | AREA | ITEM | UNIT | QTY. | RATE | AMOUNT | RA-01 | RA-02 | RA 3 | Cummulative | Variation | RA-01 | RA-02 | RA-03 | Cummulative | Variation
1 |  | ANTI TERMITE TREATMENT
1.1 | ALL MOH & FOH | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | Sq.m. | 160 | 135 | 21600 |  | 69.1589 | 52.1936 | 121.3524 | -38.6476 |  | 9336.4454 | 7046.135 | 16382.5804 | -5217.4196
0
|  | SUB TOTAL OF ANTI TERMITE TREATMENT |  |  |  | 21600 |  |  | 0 |  |  | 0 | 9336.4454 | 7046.135 | 16382.5804 | -5217.4196
0
2 |  | CIVIL WORK | [6 empty] | 0
0
2.1 |  | WATERPROOFING | [6 empty] | 0
|  | Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC sunken slabs comprising of the following operations. | Sq.m. | 25 | 1200 | 30000 |  | 0 | 0 | 0 | -25 |  |  | 0 | 0 | -30000
|  | 1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush & Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions & on all 4 Sides Walls till 350m.m Height . If the Floor has to be raised 250m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface & Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope & main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
2.2 |  | CINDER/ LIGHT WT. SIPORAX BLOCK BATS FILLING | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
a | MOH RAISED AREA (up to 150 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m. | 22 | 1500 | 33000 | 16.1288 | 0 | 0 | 16.1288 | -5.8712 | 24193.125 |  | 0 | 24193.125 | -8806.875
2.3 |  | PCC LAYER | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Providing & Laying P.C.C 1:3:6 of average thickness 75mm of M 10 grade of concrete ( 1 cement :3 coarse sand:6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 160 | 850 | 136000 |  | 0 | 0 | 0 | -160 |  |  | 0 | 0 | -136000
2.4 |  | Block WORK | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
| 100 MM THICK BLOCK MASONARY | Providing & Laying of block masonry of thickness 100mm in bund wall, in raised MOH counter area using in cement mortar 1:4 (1 cement :4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. | Sq.m. | 2 | 1650 | 3300 |  | 0 | 0 | 0 | -2 |  |  | 0 | 0 | -3300
2.5 |  | PLASTER | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
|  | P/L12-15mm thick plaster in cement mortar 1:4 (1 cement : 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 2 | 850 | 1700 |  | 0 | 0 | 0 | -2 |  |  | 0 | 0 | -1700
2.6 |  | CIVIL WORK FOR AC | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Making cut out in wall for A.C. duct pass trhru & finish with plaster etc, approx sixe upto 3' x 3' and cost includes closing of the hole after ducting, and cleaning the debris as per disposing in the municipal ground ,completed as per the details are provided in drawings or as directed by Architect. | Nos | 2 | 3500 | 7000 |  | 0 | 0 | 0 | -2 |  |  | 0 | 0 | -7000
0
|  | SUB TOTAL OF CIVIL WORK |  |  |  | 211000 |  |  | 0 |  |  | 24193.125 | 0 | 0 | 24193.125 | -186806.875
0
3 |  | FLOORING | [6 empty] | 0
0
3.2 | FOH BOH AREA TILES | Providing, fixing & laying in position Approved Tile Flooring of approved make, color, size and shade, Standard thickness in approved pattern to true line and level on average 50mm thk bedding of 1:4 mix cement sand mortar floated with neat cement, filling the joint with matching color Timex /or filling Joint with approved latecrete including cleaning, watering, curing, Gala Cutting for floor Spring & other etc. complete as per detail drawing, as specified and as directed by Architect & Site Incharge. Rate inclusive of all wastage etc complete. | [5 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
| A_(TL-01) | Floor Tile Type 1 ( Size :- 600mm x 1200mm) Flooring (Basic Rate of tile Rs. 80/- per sq.ft.) | Sq.m. | 65 | 1900 | 123500 |  |  | 0 | 0 | -65 |  |  |  | 0 | -123500
| B_(TL-02) | Floor Tile Type 2 ( Size :- 600mm x 1200mm) Flooring (Basic Rate of tile Rs.80/- per sq.ft.) | Sq.m. | 10 | 1900 | 19000 |  |  | 0 | 0 | -10 |  |  |  | 0 | -19000
| C_(TL-03) | Floor Tile Type 3 ( Size :- 600mm x 600mm) Flooring (Basic Rate of tile Rs.60/- per sq.ft.) | Sq.m. | 100 | 1700 | 170000 | 83.0865 | 7.9242 | 5.9803 | 96.9909 | -3.0091 | 141247.05 | 13471.059 | 10166.4922 | 164884.6011 | -5115.3989
| D | Providing & fixing of 100 mm high Tile Skirting (TL-02) over a bed of 20 mm thk. Cement mortar ( 1:4 ) jointed with cement slurry mixed with pigment to match the colour of tile including necessary wastage ,cutting ,grinding & polishing complete. (Base Rate of Tile is Rs. 80/- sq.ft.) | R.m | 30 | 1100 | 33000 |  | 24.0315 | 18.1364 | 42.1678 | 12.1678 | 0 | 26434.6268 | 19949.9852 | 46384.612 | 0
3.3 | 2mm spacer with Laticrete epoxy | Cleaning and filling up to 4 to 5mm deep and 2mm wide epoxy / laticrate( color and make has to approve by Architect & projects Head ) in gaps, consider total floor area includes kitchen. | Sq.m. | 165 | 250 | 41250 |  | 81.4956 | 61.504 | 142.9996 | -22.0004 | 0 | 20373.8914 | 15376.0004 | 35749.8918 | 0
0
|  | SUB TOTAL OF FLOORING WORK |  |  |  | 386750 |  |  | 0 |  |  | 141247.05 | 60279.5772 | 45492.4778 | 247019.105 | -147615.3989
0
4 |  | WALL TILING | [6 empty] | 0
0
4.1 | MOH WALLS | P/fixing glazed ceramic (Modernity Make) Mustard (300x75mm) Wall tiles,in MOH back bison board partition in per approved pattern, setting the tiles in appropriate adhesive as per manufacturer's specifications, joints filled and finished neat with epoxy grout as/spec.(Basic cost of tile Rs. 80/- per sft.) | Sq.m. | 10 | 1900 | 19000 |  | 4.9573 | 3.7413 | 8.6986 | -1.3014 | 0 | 9418.9535 | 7108.4031 | 16527.3566 | 0
[8 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
4.2 | SS Sheet Cladding MT-01 (directly over existing panelling) | Providing & fixing of 1mm thk. SS sheet (Grade 304), fixed over existing wall/panelling surfaces with approved adhesive behind rear counter as shown in drawing, all to be made & fixed with necessary arrangements & hardware- screw, adhesive, etc., as per approved sample. Rate is inclusive of all wastage, all incidentals, cutting, fixing, lead, lift, scaffolding, staging, provision for opening if any required for MEP services, as shown in drawing, complete in all respect as per drawing, designs and directions by Architect/Project-In-charge. | Sq.m. | 5 | 5450 | 27250 |  | 0 | 0 | 0 | -5 |  | 0 | 0 | 0 | -27250
[9 empty] | 0 |  |  |  |  | 0
|  | SUB TOTAL OF WALL TILING |  |  |  | 46250 |  |  | 0 |  |  | 0 | 9418.9535 | 7108.4031 | 16527.3566 | -27250
0
5 |  | WOODWORK | [6 empty] | 0
5.01 | PANEL DOOR | Flush door (38 mm thk ply) finished with approved laminate (LT-01) on both faces, All necessary hardware (SS Mortice handle and lock, SS heavy duty hinges, door closer, stopper, PVC Buffer) etc . to be provided. All to be completed as per the details are provided in drawings or as directed by Architect/Engineer. | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0
a | D1 | Door Size 1200x2100 | NO | 1 | 22400 | 22400 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 10744.6133 | 8108.8672 | 18853.4805 | -3546.5195
5.02 | WOODEN DOOR FRAME | Providing & fixing SAL wood door frame having a size of 75x63mm, formed as per details, to be finished in melamine polish as directed & instructed. Rate inclusive of all necessary hardware, wastage etc complete. | R.M | 5.4 | 1700 | 9180 |  | 2.5327 | 1.9114 | 4.444 | -0.95597 | 0 | 4305.5201 | 3249.3389 | 7554.859 | -1625.141
5.03 | OVERHEAD STORAGE CABINET | Providing and fixing in position 500mm deep Overhead Storage with a horizontal shelf in the center and openable shutters at front. Complete unit & shelf to be made of FR Ply of 19mm thk. finished with laminate LM-01 from all sides. Provision for 25x12mm aluminum strip light to be made under the unit as shown in detail drawing. Menu screens to be fixed over the openable shutters with clip-on system and the shutters behind these to be made upward openable with uplift shockers. Rate shall include all wastage, necessary hardware, fixtures. All complete as per the details, drawings or as directed by Architect/Engineer. Front Elevation Area to be Measured. | Sq.m. | 4 | 14900 | 59600 |  | 1.9187 | 1.448 | 3.3667 | -0.63331 | 0 | 28588.3462 | 21575.3787 | 50163.7248 | -9436.2752
5.04 | BACK COUNTER | Providing & Fixing total 750mm deep, 900mm High complete back counter made of 19mm thk. FR Ply. including shelves & shutters finished with lamiate LM-01 from all visible surfaces. Provision of open space to be left at some area as shown in elevation/detail drawing to accomodate under counter equipments. Providing & fixing concealed SS sink & counter mount mixer is included in the job. Top of counter and front nosing to be finished with Corian CR-01. Provision for sink, mixer, plumbing and electrical points etc to completed as per details & design provided or as directed by Architect. Cost includes completing the job including all finishes with all necessary hard ware complete as mentioned in detail drawings. Elevation area shall be measured. | Sq.m. | 5 | 22400 | 112000 |  | 2.3984 | 1.81 | 4.2084 | -0.79163 | 0 | 53723.0666 | 40544.3358 | 94267.4024 | -17732.5976
5.05 | FRONT COUNTER | Low Height Partition (in front of chilled food display) made of 19 mm thk. FR Ply from inside and 12mm thk. HDMR on outer side and top closed with same ply. Finishing of top & front of partition is as explained below and rear finished with Laminate LM-01 as shown in detail drawing. Providing & Fixing total 950mm deep complete POS counter. Complete box to be made up of 19mm thick FR Ply including shelves, shutters, drawers etc. and front made of 12mm thk. HDMR board. Top and front nosing of partition & complete counter TOP to be finished with Corian CR-01. At front of counter, 19mm thk. Fluted design panel 500mm high made out of HDMR board with rounded edges and 16x8mm grove at 16mm interval fixed on fire rated ply base, finished with PU paint PT-01. Under this, 12mm thk. Fluted design panel 400mm high made out of HDMR board with 16x8mm grove at 16mm interval fixed on fire rated ply base, finished with PU paint as per approved shades. Rear surfaces of partition & counter and all internal visible surfaces & drawers, shutters of counter to be finished with Laminate LM-01. Rate inclusive of Flap Door made of 19mm thk. FR Ply to receive similar finish as above on outer surface & laminate on inner surface as mentioned in detail drawing. Top of the flap door to be finished with Corian CR-01 as per details. Item to be completed in all respect including necessary hardware. Provision of POS machine and cash till/drawer to be made in the counter. Provision for wire manager, electrical etc to completed as per details & design provided or as directed by Architect. Cost includes completing the job including all finishes with all necessary hard ware complete as mentioned in detail drawings. Elevation area shall be measured. | Sq.m. | 8 | 28000 | 224000 |  | 3.8374 | 2.896 | 6.7334 | -1.2666 | 0 | 107446.1333 | 81088.6715 | 188534.8048 | -35465.1952
5.06 | BULKHEAD ABOVE COUNTER | Providing & fixing 600mm high, 12mm th. HDHMR ply bulkhead, verticall supported by the Gyproc GI framework, further clad with 12mm thk. Fluted design panel made out of HDMR board with 16x8mm grove at 16mm interval, finished with PU paint as per approved shades. Rate inclusive of all wastage, hardware, pu PAINT making provision for electrical points, fixing signage, scafollding at all levels, etc complete in all respects. Measurement as per elevation. | Sq.m. | 10 | 4950 | 49500 |  | 7.9242 | 5.9803 | 13.9044 | 3.9044 | 0 | 39224.554 | 29602.4331 | 68826.9872 | -49500
5.07 | SINGLE SIDE PARTITION | P/F Full Ht Single Side Partition, in front of existing airport walls, with Framework of MS Box section 40x40mm, 18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame, fixed to the floor and soffit of slab/beam with MS cleats bolted as required, with rust-free treatment & enamel paint of colour as specified ready to recieve 12mm th. Bison board as base(upto 75 mm above BOFC as per site). Rate to include making provsion for electrical wiring, necessary hardware, wastage, scafollding at all levels etc complete. Measurement as per elevation | Sq.m. | 110 | 3100 | 341000 | 101.664 | 48.7652 | 36.8027 | 187.2319 | 77.2319 | 315158.4 | 151172.1047 | 114088.2856 | 580418.7903 | -25841.6
5.08 | DOUBLE SIDE PARTITION | P/F Full Ht Double side Partition, clad on all visible faces in 12mm thk Bison board (upto 75 mm above BOFC as per site) with Framework of MS Box section 40x40mm ,18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame of approved sections fixed to floor/soffit with rust-free treatment & enamel paint of colour as specified. Rate inclusive of all necessary hardware, wastage, making provision for electrical points, door opening with grooves, provision for fixing furniture, edge finishing as per detailed drawing. Measurement as per elevation. | Sq.m. | 75 | 4000 | 300000 | 42.516 | 20.3937 | 15.3909 | 78.3006 | 3.3006 | 170064 | 81574.6393 | 61563.6778 | 313202.3171 | -129936
5.09 | WALL CLADDING | Providing and fixing 8mm thk. HDMR ply 200mm wid planks fixed on 12mm bison board partition finished with paint PT-01, with 8x8mm grooves after each plank. Rate inclusive of all necessary hardware, wastage, making provision for electrical points, scafollding at all levels etc complete in all repects. Measurement as per elevation. | Sq.m. | 30 | 1600 | 48000 |  | 13.3065 | 10.0423 | 23.3489 | -6.6511 | 0 | 21290.4513 | 16067.7203 | 37358.1716 | -10641.8284
5.1 | GYPSUM BOARD CLADDING | Providing & fixing 12mm th. Gyproc make gypsum board cladding over existing airport bulkhead and columns on all visible inner faces as shown in detail drawing. Rate is inclusive of all necessary hardware & wastage etc complete. | Sq.m. | 27 | 850 | 22950 |  | 8.6648 | 6.5393 | 15.2041 | -11.7959 | 0 | 7365.0895 | 5558.3696 | 12923.4591 | -10026.5409
5.11 | TRAP DOORS | Providing and making Trap door made of 19 mm marine ply finished with WHITE laminate. With all necessary frame work in Sal wood complete as per the detailed drawing & instruction provided by architect. Rate is inclusive of all necessary hardware, completed as per the details are provided in drawings or as directed by Architect/Engineer. Basic cost of 0.8mm White Laminate 700/- sheet | Sq.m. | 2.5 | 4950 | 12375 |  |  | 0 | 0 | -2.5 |  | 0 | 0 | 0 | -12375
5.12 | ELECTRICAL PANEL CABINET | Providing and making 1500X550x2100mm Panel cabinet made up of 19mm thick FR ply finished with Laminate from all sides, front shutters made up of 19mm thk Laminated FR ply slit cut as per drawings, with all necessary hardware, and accesories including handle, lock etc complete as per detail & design given in approved drawing or as directed by Architect/Engineer. Front Elevation Area to be measured. Refer to detail drawing. Basic cost of (Laminate: Rs. 1400 /sheet.) | Sq.m. | 3.5 | 10000 | 35000 |  |  | 0 | 0 | -3.5 |  | 0 | 0 | 0 | -35000
0
|  | SUB TOTAL OF WOODWORK |  |  |  | 1236005 |  |  | 0 |  |  | 485222.4 | 505434.5183 | 381447.0784 | 1372103.9966 | -341126.6979
0
6 |  | PAINTING/POLISHING | [6 empty] | 0
[9 empty] | 0 |  |  |  |  | 0
6.01 | PLASTIC PAINT ON CEILING | Providing & applying two or more coats of Plastic paint of approved quality & shade on prepared surface by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer & applying two final roller coats of plastic emulsion paint on internal walls /ceilings /masonry /concrete surfaces incl. scaffolding etc.. | Sq.m. | 85 | 400 | 34000 |  |  | 0 | 0 | -85 |  |  | 0 | 0 | -34000
6.02 | LUXURY EMULSION PAINT IN ROLLER FINISH ON WALLS | Providing & applying two or more coats of Luxury Emulsion Paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of lustre paint, touching up with putty & applying two final roller coats of luxury emulsion paint, to existing surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. to completed as per details & design given in drawing/Architect instruction. | Sq.m. | 57 | 500 | 28500 |  |  | 0 | 0 | -57 |  |  | 0 | 0 | -28500
0
|  | SUB TOTAL OF PAINTING/POLISHING |  |  |  | 62500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | -62500
0
7 |  | FALSE CEILING WORK | [6 empty] | 0
0
7.01 | GYPSUM FALSE CEILING | Providing & fixing of seamless GYPSUM BOARD 12.5mm thk fixed to the under side of the suspended grid formed of GI perimeter channel of size 20x27x30mm fixed along the wall by using wood screws & metal expansion rawl plugs. The GI intermediate channel of size 45x15x0.90mm shall be fixed to the suspended strap hanger /GI ceiling angle at intervals No.t more than 1220mm.The suspended GI ceiling angle/strap hanger is to be connected with GI soffit cleat of size 37x27x25, 1.6mm & it should be fixed on the roof slab/ beam by using metal expansion fasteners of 12.5mm dia. to the length of 35mm with screw at top ends, including all drops, coves, offsets in design etc and taping & finishing. Rate to be inclusive cutting for lights, grills/ ducts etc. As per the Details.(Make : India Gyproc), completed as per the details are provided in drawings or as directed by Architect/Engineer. | Sq.m. | 85 | 1250 | 106250 |  |  | 0 | 0 | -85 |  |  | 0 | 0 | -106250
7.02 | SUSPENDED WOODEN ELEMENT | Providing and suspending from ceiling, Rubber wood 50x50mm members, forming cuboids, interlocked, approximate size of each as 600x1100x600mm finished with natrual melamine polish. Rate inclusive of polish, all necessary hardware, wastage, additional supports to hang these from ceiling/slab etc. Completed as per detail drawing, instructions of architect and site in-charge. | Sq.m. | 16 | 7800 | 124800 |  |  | 0 | 0 | -16 |  |  | 0 | 0 | -124800
7.03 | SUSPENDED HDHMR CEILING | Prroviding & fixing 12mm thk. HDHMR Ply offset, hung from Gyproc frame, creating a 100x50mm chanel for fixing track lights as per detail drawing, instructions of architect and site in-charge. Rate also inclusive of all accessories. | Sq.m. | 4 | 2200 | 8800 |  |  | 0 | 0 | -4 |  |  | 0 | 0 | -8800
[8 empty] | 0 | 0 | 0 |  |  |  | 0
7.04 | GRID CEILING | Add new Item as per site requirement | Sq.m. | 0 | 2400 | 0 |  | 32.277 | 24.3592 | 56.6362 | 56.6362 |  | 77464.8247 | 58462.0361 | 135926.8609 | 135926.8609
0
|  | SUB TOTAL OF FALSE CEILING |  |  |  | 239850 |  |  | 0 |  |  | 0 | 77464.8247 | 58462.0361 | 135926.8609 | -103923.1391
0
8 |  | SIGNAGES | [6 empty] | 0
[9 empty] | 0 |  |  |  |  | 0
8.01 | DOODLE GRAPHIC | Hand painted doodle graphic on wall as per design and color | Sq.m. | 14 | 1400 | 19600 |  | 0 | 0 | 0 | -14 |  |  | 0 | 0 | -19600
8.02 | SIGNAGES | Flying bite siganges in side lit acrylic, 3mm th. Black acrylic router cut to shape of branding as per sizes | [5 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
| a | 850x250mm | No. | 1 | 14965 | 14965 |  | 0 | 0 | 0 | -1 |  |  | 0 | 0 | -14965
| b | 1200x400 | No. | 4 | 20000 | 80000 |  | 0 | 0 | 0 | -4 |  |  | 0 | 0 | -80000
8.03 | PRINTED VINYL GRAPHIC | Laminated printed vinyl graphic, pasted on existing glazing, approx. size: 5600x2500mm | Sq.m. | 14 | 1500 | 21000 |  | 0 | 0 | 0 | -14 |  |  | 0 | 0 | -21000
8.04 | FROSTED FILM ON GLASS | 3M Frosted film as per design ref detail F-101 pasted on existing glazing | Sq.m. | 5 | 1150 | 5750 |  | 0 | 0 | 0 | -5 |  |  | 0 | 0 | -5750
0
|  | SUB TOTAL OF SIGNAGES |  |  |  | 141315 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | -141315
|  | GRAND TOTAL |  |  |  | 2345270 | [5 empty] | 650662.575 | 661934.3191 | 499556.1304 | 1812153.0244 | -533116.9756

## PLUMBING
RAB-02 - PLUMBING WORK | [6 empty] | QTY |  |  |  |  | AMOUNT
SR. NO. | MATERIAL | DESCRIPTION | UNIT | QTY. | RATE | AMOUNT | RA-01 | RA-02 | RA-03 | Cumm. | Variation | RA-01 | RA-02 | RA-03 | Cumm. | Variation
1 |  | WATER SUPPLY PIPES | [6 empty] | 0
| CPVC Pipes | Supply, laying, testing & commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia. (Make – SUPREME / KASTA) including all necessary fitting as per site. | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0
1.01 |  | 15mm dia | R.M. |  | 75 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
1.02 |  | 20mm dia | R.M. | 15 | 90 | 1350 | 4.8 | 0 | 0 | 4.8 | -10.2 | 432 | 0 | 0 | 432 | -918
1.03 |  | 25mm dia | R.M. |  | 125 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  |  |  |  | 1350 |  |  | 0 |  |  | 432 | 0 | 0 | 432 | -918
2 |  | WATER DRAIN PIPES | [6 empty] | 0
| UPVC WASTE PIPE | UPVC Pipe for Drainage (Make – SUPREME / KASTA) including all necessary fitting as per site. | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0
2.01 |  | 150mm dia | R.M. |  | 950 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
2.02 |  | 100mm dia | R.M. |  | 450 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
2.03 |  | 75mm dia | R.M. |  | 250 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
2.04 |  | 50mm dia | R.M. | 7 | 200 | 1400 | 0.6 | 0 | 0 | 0.6 | -6.4 | 120 | 0 | 0 | 120 | -1280
| TOTAL |  |  |  |  | 1400 |  |  | 0 |  |  | 120 | 0 | 0 | 120 | -1280
3 |  | CHAMBER & GRATING | [6 empty] | 0
3.01 | INSPECTION CHAMBER | Supply, Laying, Testing & Commissioning of Approved SS Inspection Chamber along of Size- 300mmx300mm with SS Cover & SS Grating over it. Make Jaquar / Ozone. Including trenching and finishing with ceramic tiles as per dwg and details. | Nos. | 0 | 5000 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0
3.02 | OPEN GRATING | Providing & Fixing 20mm heavy quality SS triple layer Grating along with Perforated Mesh & Angle Frame of width 200mm, complete as per detail Drawings. Rate inclusive of chamber construction | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Size - 560mm x 200mm | R.M. |  | 4500 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Size - 1000mm x 200mm | R.M. |  | 6000 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
| TOTAL |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
4 |  | FLOOR TRAP | [6 empty] | 0
4.01 | FLOOR TRAP | Supply, Laying, Testing & Commissioning of 100x100mm Floor Trap with Approved Make heavy duty round or Square. | Nos. | 1 | 10000 | 10000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 4796.7024 | 3620.03 | 8416.7324 | -1583.2676
| TOTAL |  |  |  |  | 10000 |  |  | 0 |  |  | 0 | 4796.7024 | 3620.03 | 8416.7324 | -1583.2676
5 |  | VALVE AND TAP | [6 empty] | 0
5.01 | ANGLE VALVE | Providing & Fixing Angle Valve with connector pipe. | Nos. | 7 | 2500 | 17500 |  | 3.3577 | 2.534 | 5.8917 | -1.1083 | 0 | 8394.2292 | 6335.0525 | 14729.2816 | -2770.7184
5.02 | LONG BODY TAP | Providing & Fixing Sink Cock. with foot operated | Nos. | 0 | 4500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.03 | Table Mixer | Providing & Fixing Sink Cock. | Nos. | 1 | 3000 | 3000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 1439.0107 | 1086.009 | 2525.0197 | -474.9803
5.04 | Gate Valves | Providing & Fixing PPR Ball Valve ISI mark. (For Inlet) | Nos. | 1 | 2500 | 2500 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 1199.1756 | 905.0075 | 2104.1831 | -395.8169
| TOTAL |  |  |  |  | 23000 |  |  | 0 |  |  | 0 | 11032.4155 | 8326.0689 | 19358.4844 | -3641.5156
6 |  | ACCESSORIES | [6 empty] | 0
6.01 | Grease Trap | Providing & Fixing of portable grease trap NGT-14 from Nugreen | Nos. |  | 35000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.02 | Grease Trap | Providing & Fixing of portable grease trap NGT-50 from Nugreen | Nos. |  | 35000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.03 | Bottle Trap | Providing & fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR / OZONE) | Nos. |  | 1500 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04 | Water Meter | 25mm Dia Water meter | Nos. | 1 | 5000 | 5000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 2398.3512 | 1810.015 | 4208.3662 | -791.6338
6.05 | GEYSER | 6 LITER GEYSER | Nos. | 1 | 6500 | 6500 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 3117.8565 | 2353.0195 | 5470.876 | -1029.124
6.06 | GEYSER | 35 LITER GEYSER | Nos. |  | 15000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.07 | Waste Coupling | Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. | Nos. |  | 850 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.08 | Water supply connection | water supply connection taken from existing point complete with all necessary fittings. | Nos. | 1 | 10000 | 10000 | 1 | 0 | 0 | 1 | 0 | 10000 | 0 | 0 | 10000 | 0
6.09 | Drainage connection | Drainage connection connect to existing drain point complete with all necessary fittings including cleanout plug | Nos. | 1 | 15000 | 15000 | 1 | 0 | 0 | 1 | 0 | 15000 | 0 | 0 | 15000 | 0
6.1 | Pressure Pump | Pressure Pump | Nos. |  | 5000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.11 | RO Plant | Providing and fixing of RO Plant on MS platform with all necessary valves and fiting required. | Nos. |  | 45000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.12 | Domestic RO | Providing and fixing of Domestic RO with water storage with all necessary valves and fiting required. | Nos. | 0 | 20000 | 0 |  | 0.47967 | 0.362 | 0.84167 | 0.84167 | 0 | 9593.4048 | 7240.06 | 16833.4647 | 16833.4647
6.13 | Water Tank | Providing and fixing of 200 Ltr. Storage Loft Tank on MS Platform with all necessary valves and fiting required. | Nos. |  | 3000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.14 | Trench (125 mm wide) | Making 125 mm wide 300 mm deep trench with 4" thk. Block wall on both side of trench. Floor & inner surfaces of walls to be finished with plaster followed with 12mm ceramic tiles. Top of the trench to be covered with floor tile fixed inside L-angle frame placed over another L-angle which is fixed on trench top, complete as per dwg/details. Rate inclusive of making trench, providing finish tiles & top tiles in frame. | RMT |  | 2500 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Additional Item | [6 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
7.01 | Sink |  |  |  | 6500 |  |  | 0.47967 | 0.362 | 0.84167 | 0.84167 | 0 | 3117.8565 | 2353.0195 | 5470.876 | 5470.876
| TOTAL |  |  |  |  | 36500 | [5 empty] | 25000 | 18227.469 | 13756.1139 | 56983.583 | 20483.583
| GRAND TOTAL |  |  |  |  | 72250 | [5 empty] | 25552 | 34056.5869 | 25702.2128 | 85310.7997 | 13060.7997

## ELECTRICAL
RAB-02 , Electrical Work - A-09 Flying Bites , Lucknow | [5 empty] | QTY |  |  |  |  | AMOUNT
S. No. | Description | Qty | UOM | RATE | AMOUNT | RA-01 | RA-02 | RA-03 | Cumm. | Variation | RA-01 | RA-02 | RA-03 | Cumm. | Variation
0
1 | DISTRIBUTION BOARDS | [6 empty] | 0
0
| Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof double door type distribution boards constructed from 16 SWG sheet steel IP 42 construction, finished with rust proof duly powder coated in approved shade with hinged gasketed door and housing the following complete with P.V.C. insulated copper busbars rated 200 amp with interconnections, neutral and earth bar assembly per phase, earthing terminals complete as approved by Architects. | [6 empty] | 0
| Note : All MCBs in distribuition board for power circuits shall be of C curve | [6 empty] | 0
0
1.1 | Type A | [6 empty] | 0
0
| 1-63amp FP MCB with 3 single phase banks each comprising of 63A DP RCCB(100 mA) and 8 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 21500 | 21500 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 10312.9101 | 7783.0645 | 18095.9746 | -3404.0254
0
1.2 | Type B | [6 empty] | 0
0
| 1-32 amp DP MCB + DP RCCB ( 100mA) and 14 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 20000 | 20000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 9593.4048 | 7240.06 | 16833.4647 | -3166.5353
0
1.3 | Type C | [6 empty] | 0
0
| 1-20 amp DP MCB + DP RCCB ( 100mA) and 4 nos. 6/16/20/25 amps SP 10 kA MCB(Type D) with thermal magnetic protective releases out goings. | 1 | Set | 15000 | 15000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 7195.0536 | 5430.045 | 12625.0985 | -2374.9015
0
2 | Supply installation testing and commisioning 1.2 kVA online ( 1ph input and 1ph output) UPS with 15 Min power back up complete with in buit Static by pass switch , Mannual external maintenance by pass switch , Rectifiers , Sealed MF batteries etc as required | 1 | No. | 70000 | 70000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 33576.9166 | 25340.2098 | 58917.1265 | -11082.8735
0
3 | Supply, laying, testing & commissioning of following sizes of Cu. conductor 1.1 kV grade, armoured, XLPE insulated FRLS LT Cables/ Control Cables including necessary cleats, clamps etc. (Cables shall be partly laid in Pipes, O/H cable tray, on wall as required ) | [6 empty] | 0
0
3.1 | 4C – 16.0 (Cu.) FRLS Armoured XLPE Cable * | 25 | Mtrs | 1050 | 26250 |  | 3.8374 | 2.896 | 6.7334 | -18.2666 | 0 | 4029.23 | 3040.8252 | 7070.0552 | -19179.9448
3.2 | 4C – 25.0 (Al.) FRLS Armoured XLPE Cable * | RO | Mtrs |  |  |  |  | 0
3.3 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 20 | Mtrs | 400 | 8000 |  | 0 | 0 | 0 | -20 | 0 | 0 |  | 0 | -8000
0
| * Approximate and shall be as per point of supply from Airport Panel/ Isolator | [6 empty] | 0
0
4 | Supply, erection, testing & commissioning of following sizes of cable end terminations with Single compression gland for 1.1 kV grade, XLPE insulated, Cu Conductor cable | [6 empty] | 0
0
4.1 | 4C – 16.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 450 | 900 |  | 0.95934 | 0.72401 | 0.95934 | -1.0407 | 0 | 431.7032 | 325.8027 | 757.5059 | -142.4941
4.2 | 4C – 25.0 (Al.) FRLS Armoured XLPE Cable | RO | Nos. |  |  |  |  | 0
4.3 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 450 | 900 |  |  | 0
0
5 | Wiring for DB Submains with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in surface/concealed MS surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and making suitable end termination with copper lugs complete as required and as below | [6 empty] | 0
0
5.1 | 4 x 4 sq.mm + 2 No. 2.5 Sq. mm in 32 mm dia MS Conduit | RO | Mtrs | 750 |  |  |  | 0
5.2 | 2 x 6 sq.mm + 1 No. 4 Sq. mm in 25 mm dia MS Conduit | 30 | Mtrs | 300 | 9000 |  | 13.4308 | 10.1361 | 23.5669 | -6.4331 | 0 | 4029.23 | 3040.8252 | 7070.0552 | -1929.9448
5.3 | 2 x 4 sq.mm + 1 No. 2.5 Sq. mm in 25 mm dia MS Conduit | 200 | Mtrs | 300 | 60000 |  | 93.056 | 70.2286 | 163.2846 | -36.7154 | 0 | 27916.8078 | 21068.5745 | 48985.3823 | -11014.6177
0
6 | Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required | [6 empty] | 0
0
6.1 | 25X3 mm GI Strip | 20 | Mtrs | 125 | 2500 |  |  | 0
6.2 | 8 SWG Copper Wire | 30 | Mtrs | 180 | 5400 |  |  | 0
6.3 | 8 SWG GI Wire | 50 | Mtrs | 75 | 3750 |  | 13.9104 | 10.4981 | 24.4085 | -25.5915 | 0 | 1043.2828 | 787.3565 | 1830.6393 | -1919.3607
6.4 | 1 Core 4.0 Sq. Mm FRLS Green Wire | 25 | Mtrs | 65 | 1625 |  | 2.3984 | 1.81 | 4.2084 | -20.7916 | 0 | 155.8928 | 117.651 | 273.5438 | -1351.4562
0
7 | Supply, erection, testing & commissioning of prefabricated GI Perforated type cable trays including Tees / Bends / Crossing / Reducers / Couping to be laid in cable trench, overhead on wall or hanged from ceiling complete with all accessories as required including support at every 1500mm as required | [6 empty] | 0
0
7.1 | 150 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 15 | Mtrs | 450 | 6750 |  |  | 0
0
8 | Wiring for MCB controlled normal primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 12 | Pt | 1250 | 15000 |  | 5.756 | 4.344 | 10.1001 | -1.8999 | 0 | 7195.0536 | 5430.045 | 12625.0985 | -2374.9015
0
9 | Wiring for secondary MCB controlled normal light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 60 | Pt | 950 | 57000 |  | 27.8209 | 20.9962 | 48.817 | -11.183 | 0 | 26429.8301 | 19946.3652 | 46376.1953 | -10623.8047
0
10 | Wiring for MCB controlled Emergency primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 1 | Pt | 2000 | 2000 |  |  | 0
0
11 | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 7 | Pt | 2000 | 14000 |  | 3.3577 | 2.534 | 5.8917 | -1.1083 | 0 | 6715.3833 | 5068.042 | 11783.4253 | -2216.5747
0
12 | Wiring for a 5 pin 240 volt 6 amp single phase and neutral switch socket outlet with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / ceiling including cost of providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade wires and including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and providing and fixing of a combined 5 pin 240 volt 6 amp socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires complete as requied( Switch and socket shall be as approved by the architect / Client) | 2 | Pt. | 950 | 1900 |  | 0.95934 | 0.72401 | 1.6833 | -0.31665 | 0 | 911.3735 | 687.8057 | 1599.1791 | -300.8209
0
13 | Wiring same as in Item 12 above looped from an adjacent 6 amp switch socket outlet as required and providing and fixing of a modular type 5 pin 240 Volt 6 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole switch in a recessed GI boxes with internal wiring and moulded front plates complete as required. ( Switch and socket shall be as approved by the architect / Client) | 6 | Pt. | 850 | 5100 |  | 2.878 | 2.172 | 5.05 | -0.94996 | 0 | 2446.3182 | 1846.2153 | 4292.5335 | -807.4665
0
14 | Same as above but switch and socket provided at separate location including wiring berween switch and socket and complete as required | RO | Pt. | 1500 |  |  |  | 0
0
15 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 2 | Pt. | 1250 | 2500 |  | 0.95934 | 0.72401 | 1.6833 | -0.31665 | 0 | 1199.1756 | 905.0075 | 2104.1831 | -395.8169
0
16 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 4.0 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 4 | Pt. | 1500 | 6000 |  |  | 0
0
17 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (2 outlets wired on 1 circuit) with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 4.0 sq mm upto the first outlet and 2.5 sq mm from first to the second outlet in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing of two sets of 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switches with moulded cover plate in a recessed GI box including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) | 1 | Pt. | 1500 | 1500 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 719.5054 | 543.0045 | 1262.5099 | -237.4901
0
18 | Wiring for primary switch board consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A switch with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 2.5 sq FRLS copper wire mm in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing prewired switch board each consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A modular switch , safety shutters in a recessed/surface GI box including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) Note- Conduits shall be 16 SWG MS on surface and FRLS PVC for wall concealed | 1 | Pt. | 1500 | 1500 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 719.5054 | 543.0045 | 1262.5099 | -237.4901
0
19 | Supply installation testing and fixing 3 pin 20A , 240V , single Phase metal Clad industrial socket outlet with 20A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 6 | Nos. | 4000 | 24000 |  | 2.878 | 2.172 | 5.05 | -0.94996 | 0 | 11512.0857 | 8688.0719 | 20200.1577 | -3799.8423
0
20 | Supply installation testing and fixing 3 pin 25A/32A , 240V , single Phase metal Clad industrial socket outlet with 25A/32A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 5 | Nos. | 4000 | 20000 |  | 2.3984 | 1.81 | 4.2084 | -0.79163 | 0 | 9593.4048 | 7240.06 | 16833.4647 | -3166.5353
0
21 | Supply installation testing and fixing 5 pin 25A/20A , 415V , single Phase metal Clad industrial socket outlet with 25A/20A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | RO | Nos. | 1500 |  |  |  | 0
0
22 | Supply , fixing & Laying 2.0mm Thick FRLS PVC conduits on surface or concealed complete with PVC junction boxes, cover plates, PVC bends, PVC saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . | [6 empty] | 0
0
i | 25 mm dia FRLS PVC conduit | 35 | Mtrs | 250 | 8750 |  | 15.3494 | 11.5841 | 26.9335 | -8.0665 | 0 | 3837.3619 | 2896.024 | 6733.3859 | -2016.6141
ii | 20 mm dia FRLS PVC conduit | 50 | Mtrs | 180 | 9000 |  | 22.5445 | 17.0141 | 39.5586 | -10.4414 | 0 | 4058.0102 | 3062.5454 | 7120.5556 | -1879.4444
0
23 | Supply , fixing & Laying 16 SWG MS conduits on surface or concealed complete with PVC junction boxes, cover plates, bends, saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . | [6 empty] | 0
0
i | 25 mm dia 16 SWG MS conduit | RO | Mtrs | 110 |  |  |  | 0
ii | 20 mm dia 16 SWG MS conduit | RO | Mtrs | 90 |  |  |  | 0
0
24 | Supply and installation of flush mounted (Enhanced Category 6T 568 A or B) outlets with 2 mm thick GI box complete including cutting, chases, fixing of GI boxes and making good. The plastic shall be high impact, flame-retardant, UL rate thermoplastic. Dust cover / blank shall be provided to protect unused faceplate openings. Termination caps and plastic cover shall be provided to protect jack wiring. | [6 empty] | 0
i | Single outlet face plate with RJ-45 Jack with information outlet | 2 | Nos. | 850 | 1700 |  | 0.95934 | 0.72401 | 1.6833 | -0.31665 | 0 | 815.4394 | 615.4051 | 1430.8445 | -269.1555
ii | Duplex outlet face plate with RJ-45 Jack with information outlet | 1 | Nos. | 850 | 850 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 407.7197 | 307.7025 | 715.4223 | -134.5777
0
25 | Supply,installtion testing and commisioning of Cat-6A UTP cables in existing Conduit complete as required for Telephone and Data System | 75 | Mtrs | 50 | 3750 |  | 34.5363 | 26.0642 | 60.6005 | -14.3995 | 0 | 1726.8129 | 1303.2108 | 3030.0236 | -719.9764
[7 empty] | 0 | 0
26 | Supplying,installation and commisioning of CAT-6A patch cords 2 mtrs. | 4 | Nos | 1000 | 4000 |  | 1.9187 | 1.448 | 3.3667 | -0.63331 | 0 | 1918.681 | 1448.012 | 3366.6929 | -633.3071
0
27 | Supplying,installation and commisioning of CAT-6A patch cords 1 mtr. | 4 | Nos | 750 | 3000 |  | 1.9187 | 1.448 | 3.3667 | -0.63331 | 0 | 1439.0107 | 1086.009 | 2525.0197 | -474.9803
0
28 | Installation of following light fixtures including connections and complete in all respects | [6 empty] | 0
0
i | Track Light including track | 13 | No. | 2500 | 32500 |  | 6.2357 | 4.706 | 10.9418 | -2.0582 | 0 | 15589.2827 | 11765.0974 | 27354.3802 | -5145.6198
ii | 600mm X 600mm Light Panel | 20 | No. | 2200 | 44000 |  | 9.5934 | 7.2401 | 16.8335 | -3.1665 | 0 | 21105.4905 | 15928.1319 | 37033.6224 | -6966.3776
0
iii | 5W Light | 5 | No. | 650 | 3250 |  | 2.3984 | 1.81 | 4.2084 | -0.79163 | 0 | 1558.9283 | 1176.5097 | 2735.438 | -514.562
iv | 3W COB Light | 5 | No. | 750 | 3750 |  | 2.3984 | 1.81 | 4.2084 | -0.79163 | 0 | 1798.7634 | 1357.5112 | 3156.2746 | -593.7254
0
v | Pandent/ Hanfing Light | 24 | No. | 2500 | 60000 |  | 10.0731 | 7.6021 | 17.6751 | -6.3249 | 0 | 25182.6875 | 19005.1574 | 44187.8449 | -15812.1551
vi | LED Strip Light ( Per Meter) | 5 | Mtrs | 650 | 3250 |  | 2.3984 | 1.81 | 4.2084 | -0.79163 | 0 | 1558.9283 | 1176.5097 | 2735.438 | -514.562
vii | Signage | 5 | No. | 2500 | 12500 |  | 2.3984 | 1.81 | 4.2084 | -0.79163 | 0 | 5995.878 | 4525.0375 | 10520.9154 | -1979.0846
29 | Additional item | [6 empty] | 0
i | Electrical meter (Liberty 370 Three-phase prepayment electricity meter) |  | No. | 22500 |  |  | 0.47967 | 0.362 | 0.84167 | 0.84167 |  | 10792.5804 | 8145.0675 | 18937.6478 | 18937.6478
Total For Electrical Works - INR |  |  |  |  | 592375 | [5 empty] | 0 | 263511.6418 | 198869.9669 | 462381.6087 | -106443.3913

## HVAC
RAB-02 - HVAC - A-09 FLYING BITES AT LUCKNOW AIRPORT | [5 empty] | QTY |  |  |  |  | AMOUNT
S.No. | Description | Unit | Qty. | RATE | AMOUNT | RA-01 | RA-02 | RA-03 | Cumm. | Variation | RA-01 | RA-02 | RA-03 | Cumm. | Variation
Part A | Low Side Works | [6 empty] | 0
0
1 | DUCTING | [6 empty] | 0
1.1 | G.I. Sheet Metal Ducting - Site Fabricated | [6 empty] | 0
| Supply , Installation, Testing and Commissioning of site fabricated GSS sheet metal rectangular ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required. | [6 empty] | 0
1.1.1 | 0.63 MM (24 Gauge) | Sqm. | 80 | 1200 | 96000 | 80 |  | 0 | 80 | 0 | 96000 | 0 |  | 96000 | 0
1.1.2 | 0.80 MM (22 Gauge) | Sqm. | 5 | 1300 | 6500 | 5 |  | 0 | 5 | 0 | 6500 | 0 |  | 6500 | 0
|  |  |  | 0 |  |  |  | 0
2 | INSULATION |  |  | 0 |  |  |  | 0
2.1 | Nitrile Rubber Insulation- Class 'O' |  |  | 0 |  |  |  | 0
| Supplying and fixing of closed cell elastomeric insulation of following thickness of density 55 kg/cu.m.and K valueof not less than 0.037W/mk at 20 deg C as per specifications and drawings (For indoor applications) with factory Laminated 7 mill woven glass cloth |  |  | 0 |  |  |  | 0
2.1.1 | 19 mm thick | Sqm. | 85 | 850 | 72250 | 85 |  | 0 | 85 | 0 | 72250 | 0 |  | 72250 | 0
|  |  |  | 0 |  |  |  | 0
3 | DUCT ACCESSORIES |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
3.1 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded Aluminium Continuous Grille as per specifications |  |  | 0 |  |  |  | 0
3.1.1 | Continuos Grille 150MM Wide | RM | 20 | 2500 | 50000 |  | 9.5934 | 7.2401 | 16.8335 | -3.1665 | 0 | 23983.5119 | 18100.1499 | 42083.6618 | -7916.3382
|  |  |  | 0 |  |  |  | 0
3.2 | Supply, Installation, Testing and Commissioning of multiblade Al volume control Collar / Grille / exhaust Air Opening damper complete with suitable links, lever and quadrants for manual control of airflow and with suitable links , lever and quadrants for manual control of airflow and neoprene rubber gaskets, nuts, bolts, screws, flanges etc., as per specifications. | Sqm | 1 | 8000 | 8000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 3837.3619 | 2896.024 | 6733.3859 | -1266.6141
|  |  |  | 0 |  |  |  | 0
3.3 | Supply, Installation, Testing and Commissioning of GI multiblade volume control duct damper complete with neoprene rubber gaskets, nuts, bolts, screws linkages, flanges etc., as per specifications. | Sqm | 1 | 8000 | 8000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 3837.3619 | 2896.024 | 6733.3859 | -1266.6141
0
Total |  |  |  |  | 240750 | [5 empty] | 174750 | 31658.2357 | 23892.1979 | 230300.4335 | -10449.5665

## Lighting
RAB-02 - Lighting - A09 Flying Bites_T3_Lucknow Airport | [5 empty] | QTY | [5 empty] | AMOUNT
S.NO. | DISCRIPTION | UNIT | QTY. | RATE | AMOUNT | RA-01 | RA-02 | RA-03 | 100% | Cumm. | Variation | RA-01 | RA-02 | RA-03 | Cumm. | Variation
1.01 | 2M TRACK, BLACK FINISH | NOS | 10 | 1800 | 18000 |  | 4.7967 | 3.62 | 10 | 8.4167 | -1.5833 | 0 | 8634.0643 | 6516.054 | 15150.1182 | -2849.8818
1.02 | SPOT LIGHT, 9W LED, 36°, 6000K, IP 20, BLACK FINISH Make- G-Home LED, Item Code- G28-9W-4K-14-T | NOS | 13 | 2000 | 26000 |  | 6.2357 | 4.706 | 13 | 10.9418 | -2.0582 | 0 | 12471.4262 | 9412.0779 | 21883.5041 | -4116.4959
1.03 | GLASS BALL SHAPED PENDANT LIGHT 300MM DIA GLASS BALL SHAPED PENDANT LIGHT LAMP - 3W LED, 6000K HEIGHT-2500 BOTTOM | NOS | 21 | 3500 | 73500 |  | 10.0731 | 7.6021 | 21 | 17.6751 | -3.3249 | 0 | 35255.7625 | 26607.2203 | 61862.9828 | -11637.0172
1.04 | GLASS BALL SHAPED PENDANT LIGHT 150MM DIA GLASS BALL SHAPED PENDANT LIGHT LAMP - 3W LED, 6000K HEIGHT-2100 BOTTOM | NOS | 4 | 2500 | 10000 |  | 1.9187 | 1.448 | 4 | 3.3667 | -0.63331 | 0 | 4796.7024 | 3620.03 | 8416.7324 | -1583.2676
1.05 | 5 WATT LINEAR LIGHT 4000K Make- G-Home LED, Item Code- GP 10015 | NOS | 5 | 2500 | 12500 |  | 2.3984 | 1.81 | 5 | 4.2084 | -0.79163 | 0 | 5995.878 | 4525.0375 | 10520.9154 | -1979.0846
1.06 | 600MM X 600MM LIGHT PANEL 27 WATT, 6000K | NOS | 21 | 2400 | 50400 |  | 10.0731 | 7.6021 | 21 | 17.6751 | -3.3249 | 0 | 24175.38 | 18244.9511 | 42420.3311 | -7979.6689
1.07 | 3WATT 4000K COB SPOT LIGHT Make- G-Home LED, Item Code- GM 0831 | NOS | 5 | 1500 | 7500 |  | 2.3984 | 1.81 | 5 | 4.2084 | -0.79163 | 0 | 3597.5268 | 2715.0225 | 6312.5493 | -1187.4507
1.08 | LED STRIP LIGHTS WITH ALUMINUM CHANNEL 5V PER METER, 4000K Make- G-Home LED, | R.MT | 6 | 650 | 3900 |  | 2.3984 | 1.81 | 5 | 4.2084 | -1.7916 | 0 | 1558.9283 | 1176.5097 | 2735.438 | -1164.562
| TOTAL |  |  |  | 201800 | [6 empty] | 0 | 96485.6683 | 72816.903 | 169302.5713 | -32497.4287

## CCTV
RAB-02 - CCTV Work - A-09 Flying Bites Lucknow_T3_Lucknow Airport | [7 empty] | QTY |  |  |  |  | AMOUNT
S.No | Items | Specification | Model | Make | Qty | RATE | AMOUNT | RA-01 | RA-02 | RA-03 | Cumm. | Variation | RA-01 | RA-02 | RA-03 | Cumm. | Variation
1 | Dome Cameras | Full HD 720p Video Output, Adopt HDTVI Technology, Trud Day & Night, Lens 3.6mm, 12LED, Upto 20M IR Distance | DS-2CE5ZCOT-IRP | Hikvision | 8 | 2500 | 20000 |  | 3.8374 | 2.896 | 6.7334 | -1.2666 | 0 | 9593.4048 | 7235.6675 | 16829.0722 | -3170.9278
2 | Bullet Camera | 1080P Outdoor 2 MP bullet camera fixed lens | DS-2CE1ADOT-IT1F | Hikvision | 0 | 4500 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
3 | Digital Video Recorder | 4 Channel DVR, Supported 1mp, H.264 /H.264 & Dual stream video compression, Support HD-TVI/Analoge and AHD Cameras with adaptive access. HDMI and VGA output to 1920x1080P resolution, Supported 1 Hard disk upto 4TB | DS-7A04HGHI-F1/N | Hikvision | 0 | 12500 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
4 | Digital Video Recorder | 8 Channel DVR, Supported 1mp, H.264 /H.264 & Dual stream video compression, Support HD-TVI/Analoge and AHD Cameras with adaptive access. HDMI and VGA output to 1920x1080P resolution, Supported 1 Hard disk upto 6TB | DS-7A08HGHI-F1/N | Hikvision | 1 | 7000 | 7000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 3357.6917 | 2534.021 | 5891.7126 | -1108.2874
5 | Digital Video Recorder | 16 Channel DVR, Supported 1mp, H.264 /H.264 & Dual stream video compression, Support HD-TVI/Analoge and AHD Cameras with adaptive access. HDMI and VGA output to 1920x1080P resolution, Supported 1 Hard disk upto 6TB | DS-7A16HGHI-F1/N | Hikvision | 0 | 25000 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
6 | Digital Video Recorder | 16 Channel DVR, Supported 1mp, H.264 /H.264 & Dual stream video compression, Support HD-TVI/Analoge and AHD Cameras with adaptive access. HDMI and VGA output to 1920x1080P resolution, Supported 2 Hard disk upto 8TB | DS-7016/7216 HQHI/K1 | Hikvision | 0 | 30000 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
7 | CEILING SUSPENDED CAMERA PIPE | MS power coated white/black color 3.5'-5.5' tele4scopic mount with provision to make mount in straight line and box to install power supply inside for dome camera installation. | No |  | 0 | 1000 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
8 | Hard Disk - SURVEILLANCE | 2TB | WD/ Purple | Seagate / Toshiba | 0 | 5000 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
9 | Hard Disk - SURVEILLANCE | 4TB | WD/ Purple | Seagate / Toshiba | 1 | 7500 | 7500 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 3597.5268 | 2715.0225 | 6312.5493 | -1187.4507
10 | Screen | 18-19" | with HDMI | Acer/LG/Dell | 1 | 14700 | 14700 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 7051.1525 | 5321.4441 | 12372.5966 | -2327.4034
11 | BNC Connectors | [7 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
12 | DC Connectors | [7 empty] | 0 | 0 | 0 |  |  |  | 0 | 0
13 | Power Supply | 8 Cameras - 10 amps X 2 |  | CP-PLUS / ZEBRONICS | 1 | 2000 | 2000 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 959.3405 | 724.006 | 1683.3465 | -316.6535
14 | Power Supply | 16 Cameras - 20 amps X 2 |  | CP-PLUS / ZEBRONICS | 0 | 3000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | HDMI Cable | 5 Mtrs |  | MX | 1 | 2200 | 2200 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 1055.2745 | 796.4066 | 1851.6811 | -348.3189
16 | Cameras Installation | All Over India |  | Hikvision | 1 | 10500 | 10500 |  | 0.47967 | 0.362 | 0.84167 | -0.15833 | 0 | 5036.5375 | 3801.0315 | 8837.569 | -1662.431
17 | Music System | 10 Watt to 60Watt JBL | CSS1/ST | JBL | 0 | 32000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Music System | Amplifier | Libra 250 | JBL | 0 | 28000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Music System | Amplifier | Libra 500 | JBL | 0 | 32000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Music Installation | All Over India |  | JBL | 0 | 50000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Amount | [6 empty] | 63900 | [5 empty] | 0 | 30650.9282 | 23127.5991 | 53778.5273 | -10121.4727