## Idli.com
ADDITIONAL WORK IDLI.COM
S. NO. | DESCRIPTION | UNIT |  |  | ADDITIONAL QTY. | RATE | AMOUNT | REMARK
A | CIVIL
1 | Brick work
| Providing and constructing 150mm thk Siphorex block in cement mortar 1:4 of approved make like Aerocon/Siporex etc. Job to include raking out joints, scaffolding, making openings walls, curing etc. in substructure and superstructure to its true line & level in cement mortar proportion as specified in all shapes, size, at all heights, depths, leads & locations etc. complete. The rate shall also include for cleaning of surface, hacking of RCC surface in contact with brickwork, racking of joints, providing, erecting, & dismantling steel scaffolding , curing for 10 days, including 75 mm thk. R.C.C. stiffener at approximately every 1000 mm ht. with required M.S. reinforcement bars and Lintels for Doors and wall openings etc. compete as per the drgs., details & specifications. | Sq.M |  |  | 16.2872 | 2100 | 34209 | Non tender item
|  |  | 5.02 | 2.93 | 14.14
|  |  | 0.88 | 2.44 | 2.1472
2 | Plaster work
| P&A of single coat backing plaster of 15-18 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction | Sq.M |  |  | 32.87 | 1500 | 49305 | Non tender item
|  |  | 5.02 | 2.93 | 14.14
|  |  | 5.02 | 2.93 | 14.14
|  |  | 0.88 | 2.44 | 2.1472
|  |  | 1 | 2.44 | 2.44
3 | Cinder filling
| CINDER BLOCK COBA of Avg. thickness mentioned below; After laying of soil pipes, floor traps is completed the floor of the sunken portion shall be covered with cinder coba embedded manually with 15-20 mm wide joints in 20 mm thk. Waterproofing mortar 1:4 ( 1 cement : 4 coarse sand )in layers upto the full ht. of sunken portion, having top layer of 50 mm thk waterproof mortar 1:4 ( 1 cement : 4 coarse sand ) using specialized W.P. chemical, finished smooth / rough with floating coat of neat cement all complete and as per specification up to 300mm . | Sq.m |  |  | 26.76 | 2200 | 58872 | Non tender item
|  |  | 5.02 | 2.7 | 13.554
|  |  | 5.02 | 2.63 | 13.2026
4 | PCC
| Providing and laying up to 50-75 mm thick cement concrete flooring with 1:2:4 cement concrete laid to proper level and slope in alternate bays including compactions, filling joints, or as directed, finishing smooth with cement Mortar 1:1 of sufficient minimum thickness to give a smooth & even surface and curing etc. complete as per architects instructions. | Sq.m |  |  | 26.76 | 1450 | 38802 | Non tender item
|  |  | 5.02 | 2.7 | 13.554
|  |  | 5.02 | 2.63 | 13.2026
5 | Inspection Chamber
| 300 x 300 inspection chamber in brick work with water proofing finished with tiles inside. | No. |  |  | 1 | 4500 | 4500 | Semolina/PO/24-25/000078
6 | Inspection Chamber cover
| Providing and fixing of S.S. perforated Inspection chamber cover with necessary fittings. | No. |  |  | 1 | 9500 | 9500 | Semolina/PO/24-25/000078
7 | Guard Rail
| Providing and fixing of trolly defender made out of 50 mm 304 SS pipe with 50mm pipe vertical support fixed on floor with fasteners | RM | 4.26 | 1 | 4.26 | 5904 | 25151.04 | Non tender item
8 | Hood fixing
| Fixing of hood from ceiling frame with support of MS pipe frame. | No. |  |  | 3 | 10000 | 30000 | Non tender item
9 | Ele. DB box
| Providing and fixing of electrical DB box made out of plywood finished with laminate and MS louvers fixed on shutters. | Sq.m | 2.3454 | 0.88 | 2.06 | 17259 | 35553.54 | Non tender item
10 | SS corner guard
| Providing and fixing of 25 mm X 25 mm SS corner guard for wall corner. | RM |  |  | 9.2 | 800 | 7360 | Non tender item
11 | Gas meter stand
| Providing and fixing of gas meter stand made out of SS pipe. | No. |  |  | 1 | 2000 | 2000 | Non tender item
12 | DNB stand
| Providing and fixing DNB stand made out of MS frame with 18mm plywood finished with black paint | No. |  |  | 1 | 10000 | 10000 | Non tender item
13 | Microvan shelf
| Providing and fixing granite shelf with SS angle frame. | No. |  |  | 1 | 4500 | 4500 | Non tender item
14 | Trap door
| Provision of trap door in gypsum ceiling | No. |  |  | 2 | 2500 | 5000 | Non tender item
15 | Sneeze guard
| Providing and fixing sneeze guard made out of 12 mm toughened glass fixed on bracket fitting. | Sq.m |  |  | 3.69 | 9500 | 35055 | Non tender item
16 | Equipment shifting
| Lording and unloading of outlet equipment and shifting from out side of airport premisses and arrange and fixing in side the outlet as per instructions | [6 empty] | Non tender item
| Unloading from container transport at outside of Airport premises and shifting in located area. Again shifting from outside to second floor food court area in side the airport. Arranging of equipment as per layout in the outlet. Hood-1nos. , SS sink- 2Nos. , SS work work table-1Nos. ,SS rack-1Nos. ,SS storage unit-1Nos. ,4Gas burner-1Nos., Under counter chiller-2Nos. , Cold display unit-1Nos. ,Merryshef-1Nos. and other small items. | No. | 8 | 1 | 8 | 3600 | 28800
| Day one manpower | No. | 8 |  |  | 1200 | 9600
| DayTwo manpower | No. | 8 |  |  | 1200 | 9600
| Day Three manpower | No. | 8 |  |  | 1200 | 9600
B | PLUMBING WORK
1 | Angle cock
| Providing and fixing of angle cock for inlet and outlet pipe connections | No. |  |  | 9 | 1350 | 12150 | Non tender item
2 | Sink cock
| Providing and fixing of single sink cock for sink counter with all fittings | No. |  |  | 3 | 3800 | 11400 | Semolina/PO/24-25/000080
3 | SS Sink
| Providing and fixing of SS sink ( Nirali make) in granite counter with cutting and polishing work. | No. |  |  | 1 | 8500 | 8500 | Non tender item
4 | Grease trap
| Fixing of grease trap with pipe connection including all fittings. | No. |  |  | 2 | 7000 | 14000 | Non tender item
Grease trap size - 500 x 400 x 350
40 mm CPVC pipe with elbow, bend, stop cock and required hardware.
| Number of plumber day one | No. | 2 |  | 2200 | 4400 | 4400
| Number of plumber day Two | No. | 2 |  | 2200 | 4400 | 4400
5 | Water heater
| Supply & Fixing of Water heater of 15lts with necessary fittings | No. |  |  | 1 | 12500 | 12500 | Semolina/PO/24-25/000082
6 | Sink mixer cock
| Providing and fixing of sink mixer cock for ss counter sink with all fittings | No. |  |  | 1 | 5200 | 5200 | Semolina/PO/24-25/000082
| TOTAL A & B | [5 empty] | 451157.58