## Total
DISTINCT INDIA ENTERPRISES LLP
Total Extra Work Value
# | Description | Pre GST Value | GST | Grand Total
A | PO no 048 | 44455.396 | 8001.9713 | 52457.3673
B | PO no 059 | 7482 | 1346.76 | 8828.76
C | PO no 060 | 6207 | 1117.26 | 7324.26
D | Extra work beyond PO Scope | 122584 | 22065.12 | 144649.12
(A + B + C + D)
|  | Total Pre GST Value |  |  | = | 180728.396
|  | Total GST |  |  | = | 32531.1113
|  | Final total value for all extra work executed |  |  | = | 213259.5073

## PO no 048 (A)
DISTINCT INDIA ENTERPRISES LLP
WO # TFSL/23-24/000048
S/NO | Description | UNIT | RATE | PO Qty | PO Value | Actual Qty | Actual Value | Diff in Qty | Diff in Value
1 A | Providing & Fixing full Height Partation | SQFT | 345 | 416 | 143520 | 677.75 | 233823.75 | 261.75 | 90303.75
2 B | MS FRAME WORK FLORING EQUPMENT | SQFT | 670 | 123 | 82410 | 7.5 | 5025 | -115.5 | -77385
3C | MS FRAME WORK FOR CEELING | SQFT | 345 | 123 | 42435 | 144 | 49680 | 21 | 7245
4 D | GYPSUM FALSCEELING WORK | SQFT | 160 | 123 | 19680 | 144 | 23040 | 21 | 3360
5 E | PREMIUM EMULSON PAINT WATER BASE | SQFT | 80 | 424 | 33920 | 730 | 58400 | 306 | 24480
6 F | Vinyl Flooring | SQFT | 270 | 123 | 33210 |  | 0 | -123 | -33210
7 G | PVC Trap | NOS | 375 | 2 | 750 |  | 0 | -2 | -750
8 H | LAMINETED SKIRTING | RFT | 145 | 34 | 4930 | 53.99 | 7828.55 | 19.99 | 2898.55
9 I | DOOR | NOS | 42000 | 2 | 84000 | 2 | 84000 | 0 | 0
10 J | 300X300 MM DADO TILES | SQFT | 215 | 300 | 64500 | 314.58 | 67634.7 | 14.58 | 3134.7
11 K | PUTTY | SQFT | 50 | 387 | 19350 | 870.966 | 43548.3 | 483.966 | 24198.3
12 L | OBD INSIODE | SQFT | 80 | 87 | 6960 | 89.2512 | 7140.096 | 2.2512 | 180.096
13 M | STOREGE CVABNITE | NOS | 8500 | 4 | 34000 | 4 | 34000 | 0 | 0
14N | SHELIVING | NOS | 6500 | 1 | 6500 | 1 | 6500 | 0 | 0
| TOTAL |  |  |  | 576165 |  | 620620.396 |  | 44455.396
| GST18% |  |  |  | 103709.7 |  | 111711.6713 |  | 8001.9713
| GRAND TOTAL |  |  |  | 679874.7 |  | 732332.0673 |  | 52457.3673

## PO no 059 (B)
DISTINCT INDIA ENTERPRISES LLP
WO # TFSPL/PO/23-24/000059
S/NO | Description | UNIT | RATE | PO Qty | PO Value | Actual Qty | Actual Value | Diff in Qty | Diff in Value
6 | 32 amp ray rolle soket | NOS | 5500 | 2 | 11000 | 1 | 5500 | -1 | -5500
7 | 16 amp ray rolle soket | NOS | 4500 | 3 | 13500 | 2 | 9000 | -1 | -4500
9 | 6Way Eipn DB lighting &power | NOS | 14000 | 1 | 14000 | 1 | 14000 | 0 | 0
57a | Primairy light point | NOS | 1250 | 4 | 5000 | 4 | 5000 | 0 | 0
58b | secondry light point | NOS | 1020 | 5 | 5100 | 5 | 5100 | 0 | 0
61 a | primery point | NOS | 1250 | 1 | 1250 | 1 | 1250 | 0 | 0
64a | raw primairy point | NOS | 1250 | 1 | 1250 | 5 | 6250 | 4 | 5000
68a | 2Rx2.5 +1rx2.5 wire | MTR | 187 | 35 | 6545 | 35 | 6545 | 0 | 0
69b | 2Rx4+1R2.5 sqmm wire | MTR | 321 | 15 | 4815 | 15 | 4815 | 0 | 0
73a | GI conduit | MTR | 210 | 25 | 5250 | 25 | 5250 | 0 | 0
74b | flexibale conduits | MTR | 116 | 2 | 232 | 2 | 232 | 0 | 0
83b | 6A5PIN outlet soket | NOS | 450 | 1 | 450 | 1 | 450 | 0 | 0
84c | 16A 5 pin outlet soket | NOS | 1165 | 6 | 6990 | 6 | 6990 | 0 | 0
85d | 6/13switch soket outlet | NOS | 1450 | 1 | 1450 | 1 | 1450 | 0 | 0
86e | 6/13a switch soket outlet | NOS | 2250 | 2 | 4500 | 2 | 4500 | 0 | 0
94 | led dowen lighter | NOS | 850 | 6 | 5100 | 6 | 5100 | 0 | 0
96 | led light | NOS | 525 | 2 | 1050 | 2 | 1050 | 0 | 0
| TOTAL |  |  |  | 75000 |  | 82482 |  | 7482
| GST 18% |  |  |  | 13500 |  | 14846.76 |  | 1346.76
| GRAND TOTAL |  |  |  | 88500 |  | 97328.76 |  | 8828.76

## PO no 060 (C)
DISTINCT INDIA ENTERPRISES LLP
WO: TFSL/PO/23-24/000060
S/NO | Description | UNIT | RATE | PO Qty | PO Value | Actual Qty | Actual Value | Diff in Qty | Diff in Value
1 | PREP KITCHIN DISMENTLING AREA | SQFT | 15 | 1000 | 15000 | 1413.8 | 21207 | 413.8 | 6207
2 | PAINT WORK PREP KITCHIN | SQFT | 25 | 250 | 6250 | 250 | 6250 | 0 | 0
| TOTAL |  |  |  | 21250 |  | 27457 |  | 6207
| GST 18% |  |  |  | 3825 |  | 4942.26 |  | 1117.26
| GRAND TOTAL |  |  |  | 25075 |  | 32399.26 |  | 7324.26

## Extra work (D)
DISTINCT INDIA ENTERPRISES LLP
MB SHEET - EXTRA WORK CIVIL PLUMBING ELECTRICAL BEYOND PO SCOPE
S/NO | Description | UNIT | QTY | RATE | TOTAL
PLUMBING EXTRA WORK
1 | Plumbing work with demolation & drain line & water supply line & demolation tile laying new fixing with trap | L/S | 1 | 70000 | 70000
ELECTRICAL EXTRA WORK
1 | 100 AMP BUSBAR | NO | 1 | 9500 | 9500
2 | ALU 4X16 SQMM ARMOUND XLPE | MTR | 26 | 425 | 11050
CIVIL WORK
1 | SS PARTATION WORK SUPPLY & FIXING | L/S | 12 | 2669.5 | 32034
| TOTAL |  |  |  | 122584
| GST18% |  |  |  | 22065.12
| GRAND TOTAL |  |  |  | 144649.12