## Bill of Summary
Semolina Projects
Project : Budweiser
Details : Project Invoicing
PO No.: PO/23-24/000698
BUDWEISER - BILL SUMMARY
S. No. | Items | PO Value | Previous Bills | This Bill | Cumulative | Varition (In Amount)
1 | Wet Work of Water proofing and Wall | 330195 | 0 | 197822.4036 | 197822.4036 | 0
| Subtotal | 330195 |  | 197822.4036 | 197822.4036
| GST @ 18% | 59435.1 |  | 35608.0326 | 35608.0326
| Grand Total | 389630.1 |  | 233430.4362 | 233430.4362

## C&I abstract
BOQ-CIVIL & INTERIOR WORKS RA SHEET
SN. | AREA | ITEM | UNIT | QTY. | Rate | Quantity |  |  | Amount
[6 empty] | Previous Bill | This Bill | Upto Date | Previous Bill | This Bill | Upto Date
1 |  | ANTI TERMITE TREATMENT
1.1 | ALL MOH & FOH | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | Sq.m. | 325 | 71 |  | 36.0074 | 36.0074 |  | 2556.5247 | 2556.5247
SUB TOTAL OF ANTI TERMITE TREATMENT
2
2.1 |  | WATERPROOFING
|  | Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. | Sq.m. | 80 | 500 |  | 36.0074 | 36.0074 |  | 18003.695 | 18003.695
1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush & Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions & on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface & Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope & main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring
2.2 |  | CINDER/ LIGHT WT. SIPORAX BLOCK BATS FILLING
a | MOH RAISED AREA (up to 75 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m. | 54.25 | 330 |  | 36.0074 | 36.0074 |  | 11882.4387 | 11882.4387
b | MOH RAISED AREA (up to 600 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m.
2.3 |  | PCC LAYER
|  | Providing & Laying P.C.C 1:3:6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement :3 coarse sand:6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 54.25 | 500 |  | 36.0074 | 36.0074 |  | 18003.695 | 18003.695
2.4 |  | Block WORK
| 150 MM THICK BLOCK MASONARY | Providing & Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1:4 (1 cement :4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. | Sq.m. | 110 | 1070 |  | 62.2493 | 62.2493 |  | 66606.6975 | 66606.6975
2.5 |  | PLASTER
|  | P/L12-15mm thick plaster in cement mortar 1:4 (1 cement : 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 220 | 430 |  | 164.5799 | 164.5799 |  | 70769.3527 | 70769.3527
2.6 | RCC LINTEL BEAM | P/L in place (cast in situ) RCC lintel beams in 150mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1:4:8) 100mm high with 4 no.'s 8mm th. Steel bars as per general specifications, complete in all respects | Rmt | 20 | 500 |  | 20 | 20 |  | 10000 | 10000
|  | SUB TOTAL OF CIVIL WORK | [6 empty] | TOTAL | 197822.4036 | 197822.4036

## C&I MB
BOQ-CIVIL & INTERIOR WORKS RA SHEET
SN. | AREA | ITEM | UNIT | QTY. | LOCATION | L | B | H |  | RA QTY | RATE | AMOUNT
1 |  | ANTI TERMITE TREATMENT
1.1 | ALL MOH & FOH | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | Sq.m. | 325
[5 empty] | PART-A | 2.24 | 2.88 |  |  | 6.4512
[5 empty] | PART-B | 2.554 | 8.665 |  |  | 22.1304
[5 empty] | PART-C | 1.83 | 3.56 |  |  | 6.5148
[5 empty] | PART-D | 0.63 | 1.446 |  |  | 0.91098
[6 empty] | TOTAL |  |  |  | 36.0074 | 71 | 2556.5247
SUB TOTAL OF ANTI TERMITE TREATMENT
2
2.1 |  | WATERPROOFING
|  | Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. | Sq.m. | 80
1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush & Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions & on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface & Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope & main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring
[5 empty] | PART-A | 2.24 | 2.88 |  |  | 6.4512
[5 empty] | PART-B | 2.554 | 8.665 |  |  | 22.1304
[5 empty] | PART-C | 1.83 | 3.56 |  |  | 6.5148
[5 empty] | PART-D | 0.63 | 1.446 |  |  | 0.91098
[6 empty] | TOTAL |  |  |  | 36.0074 | 500 | 18003.695
2.2 |  | CINDER/ LIGHT WT. SIPORAX BLOCK BATS FILLING
a | MOH RAISED AREA (up to 75 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m. | 54.25
[5 empty] | PART-A | 2.24 | 2.88 |  |  | 6.4512
[5 empty] | PART-B | 2.554 | 8.665 |  |  | 22.1304
[5 empty] | PART-C | 1.83 | 3.56 |  |  | 6.5148
[5 empty] | PART-D | 0.63 | 1.446 |  |  | 0.91098
|  |  |  | TOTAL | [5 empty] | 36.0074 | 330 | 11882.4387
b | MOH RAISED AREA (up to 600 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m.
2.3 |  | PCC LAYER
|  | Providing & Laying P.C.C 1:3:6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement :3 coarse sand:6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 54.25
[5 empty] | PART-A | 2.24 | 2.88 |  |  | 6.4512
[5 empty] | PART-B | 2.554 | 8.665 |  |  | 22.1304
[5 empty] | PART-C | 1.83 | 3.56 |  |  | 6.5148
[5 empty] | PART-D | 0.63 | 1.446 |  |  | 0.91098
|  |  |  | TOTAL | [5 empty] | 36.0074 | 500 | 18003.695
2.4 |  | Block WORK
| 150 MM THICK BLOCK MASONARY | Providing & Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1:4 (1 cement :4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. | Sq.m. | 110
[6 empty] | 3.04 |  | 3.15 |  | 9.576
[6 empty] | 1.195 |  | 3.15 |  | 3.7643
[6 empty] | 7.63 |  | 3.15 |  | 24.0345
|  |  |  | DEDUCT | DOOR1 | -0.9 |  | 2.1 |  | -1.89
[6 empty] | 2.58 |  | 3.15 |  | 8.127
|  |  |  | DEDUCT | DOOR2 | -1.04 |  | 2.1 |  | -2.184
[6 empty] | 0.88 |  | 3.15 |  | 2.772
[6 empty] | 5.1 |  | 3.15 |  | 16.065
[6 empty] | 0.63 |  | 3.15 |  | 1.9845
2.5 |  | PLASTER |  |  |  | TOTAL |  |  |  | 62.2493 | 1070 | 66606.6975
|  | P/L12-15mm thick plaster in cement mortar 1:4 (1 cement : 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 220
[6 empty] | 3.04 |  | 3.15 | 2 | 19.152
[6 empty] | 1.195 |  | 3.15 | 2 | 7.5285
[6 empty] | 7.63 |  | 3.15 | 2 | 48.069
|  |  |  | DEDUCT | DOOR1 | -0.9 |  | 2.1 |  | -1.89
[6 empty] | 2.58 |  | 3.15 | 2 | 16.254
|  |  |  | DEDUCT | DOOR2 | -1.04 |  | 2.1 |  | -2.184
[6 empty] | 0.88 |  | 3.15 | 2 | 5.544
[6 empty] | 5.1 |  | 3.15 | 2 | 32.13
[6 empty] | 0.63 |  | 3.15 | 2 | 3.969
[5 empty] | FLOOR | QTY. AS IN ITEM NO. 1.1 |  |  |  | 36.0074
[7 empty] | TOTAL |  |  | 164.5799 | 430 | 70769.3527
2.6 | RCC LINTEL BEAM | P/L in place (cast in situ) RCC lintel beams in 150mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1:4:8) 100mm high with 4 no.'s 8mm th. Steel bars as per general specifications, complete in all respects | Rmt | 20 |  | 19.315 |  |  | 2 | 38.63
[8 empty] | BOQ QTY |  | 20 | 500 | 10000
[8 empty] | EXTRA QTY |  | 18.63 | 500 | 9315
|  | SUB TOTAL OF CIVIL WORK | [9 empty] | 207137.4036
Floor Plaster and rcc column we have to discussed with irfan sir

## Extra Qauntity
Extra Qauntity
S.No. | Area | Item | Unit | BOQ Qty | Rate |  |  |  | Amount
2.6 | RCC LINTEL BEAM | P/L in place (cast in situ) RCC lintel beams in 150mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1:4:8) 100mm high with 4 no.'s 8mm th. Steel bars as per general specifications, complete in all respects | Rmt | 20 | 500
[6 empty] | Total Qty |  | 38.63
[6 empty] | BOQ QTY |  | 20
[6 empty] | EXTRA QTY |  | 18.63 | 9315
2.7 | RCC COLUMN | 150 MM Thick column with shuttring, bolt fastner 4 no's 8 mm th Steel bars as general specification, complete in all respects | Rmt | 0 | 2500 | 3.15 | 8 | 25.2
[6 empty] | Total Extra Qty |  | 25.2 | 63000
[6 empty] | TOTAL |  |  | 72315