## Summary
Semolina Projects
Project : LKN Budweiser bar
Details : Project Invoicing
PO No.: Semolina/PO/24-25/000806
Vendor Name : VSAS GROUP
LKN Budweiser Bar - BILL SUMMARY
S. No. | Items | PO Value | Previous Bill | This Bill | Cumulative | Varition (In Amount)
1 | NT items of wet work | 63000 | 0 | 63000 | 63000
| Subtotal | 63000 |  | 63000 | 63000
| GST @ 18% | 11340 |  | 11340 | 11340
| Grand Total | 74340 |  | 74340 | 74340

## Budweiser Non PO Abstract
BUDWEISER NON PO ITEMS ABSTRACT
|  |  | AS PER PO |  |  | RA QUANTITY |  |  | Amount
S.No. | Area | Item | Unit | BOQ Qty | Rate | Previous Bill | This Bill | Up to Date | Previous Bill | This Bill | Up to Date | Varition
2.7 | RCC COLUMN | 150 MM Thick column with shuttring, bolt fastner 4 no's 8 mm th Steel bars as general specification, complete in all respects | Rmt | 25.2 | 2500 | 0 | 25.2 | 25.2 | 0 | 63000 | 63000
[6 empty] | TOTAL |  |  |  | 63000 | 63000

## Budweiser Non PO MB Sheet
BUDWEISER NON PO ITEMS MB
S.No. | Area | Item | Unit | BOQ Qty |  |  | QTY
2.7 | RCC COLUMN | 150 MM Thick column with shuttring, bolt fastner 4 no's 8 mm th Steel bars as general specification, complete in all respects | Rmt |  | 3.15 | 8 | 25.2
[5 empty] | TOTAL |  | 25.2