## Summary RAB-02
SUMMARY FOR CIVIL, INTERIOR & STRUCTURAL STEEL WORK FOR PROPOSED IN LOUNGE AT JAIPUR AIRPORT
S.No | ITEM DESCRIPTION | PO Amount | Previous Bill Amount | This Bill Amount (RA-01 Checked) | Cummulative | Variance
CARPET AREA in SQM
A | CIVIL WORK
I | DISMANTLING WORK | 33004.7222 |  |  |  | 33004.7222
II | CIVIL WORK | 302311.3852 | 0 | 251264.8229 | 251264.8229 | 51046.5623
B | INTERIOR WORK
I | FLOORING & WALL TILES / STONE WORK | 1201287.163 | 0 | 960925.0123 | 960925.0123 | 240362.1508
II | DOOR WINDOW WORK | 746279.9004 | 0 | 423490.781 | 423490.781 | 322789.1194
III | OTHER WOOD WORK FOR WALL PANELLING, PARTITIONS & STORAGES | 2189172.5913 | 0 | 1672030.4212 | 1672030.4212 | 517142.1702
IV | FALSE CEILING WORK | 412731.9 | 0 | 397800.081 | 397800.081 | 14931.819
V | FINISHING WORK | 451039.442 | 0 | 383362.6759 | 383362.6759 | 67676.7661
VI | MISC. WORK | 525793.4774 | 0 | 422287.3998 | 422287.3998 | 103506.0776
| TOTAL OF CIVIL & INTERIOR WORK | 5861620.5817 | 0 | 4511161.194 | 4511161.194 | 1350459.3876
D | SANITARY PLUMBING FIXTURES WORK | 121010.4 | 0 | 13925.8 | 13925.8 | 107084.6
E | STRUCTURAL STEEL WORK | 470596 | 0 | 147878.7809 | 147878.7809 | 322717.2191
F | EXTRA ITEMS CIVIL WORKS
| TOTAL OF CIVIL & INTERIOR & STRUCTURE WORK RAB-01 | 6453226.9817 | 0 | 4672965.7749 | 4672965.7749 | 1780261.2067
MEP
1 | ELECTRICAL WORK | 1911748.23 | 0 | 967506.96 | 967506.96 | 944241.27
2 | ELECTRICAL WORK NON TENDER ITEM |  |  |  |  | 0
3 | HVAC WORK | 1619968.2 | 0 | 625390.871 | 625390.871 | 994577.329
4 | FIRE FIGHTING AND PHE WORK | 466082.12 | 0 | 97288.52 | 97288.52 | 368793.6
5 | FIRE FIGHTING AND PHE WORK NON TENDER ITEM |  |  |  |  | 0
6 | LIGHT FITTINGS | 656289.34 | 0 | 616672.84 | 616672.84 | 39616.5
7 | LIGHT FITTINGS NON TENDER ITEM
8 | SANITARY PLUMBING WORK
9 | FURNITURE WORK | 3479529.2 | 0 | 3178443.8 | 3178443.8 | 301085.4
10 | EXTRA NEW ITEM IN FURNITURE
FROM ADANI WORK ORDER
11 | EXTRA ITEM HVAC 2ND FLOORING DUCTING AS PER SKETCH RECEIVED
12 | EXTRA ITEM C& S |  |  |  |  | 0
| SUB TOTAL RAB -02 | 8133617.09 | 0 | 5485302.991 | 5485302.991 | 2648314.099
| GRAND TOTAL RAB-02 | 14586844.0717 | 0 | 10158268.7659 | 10158268.7659 | 4428575.3057

## WORK ODER ISSUED
S.No | DESCRIPTION | ISSUED BY | DATE | ODER NO |  | TENDER AMOUNT BASIC RATES
1 | WO FOR DISMANTLING | ADANI | 10.08.23 | 5700329979 |  | 431356.4
2 | WO FOR FITOUT WORK | SEMOLINA KITCHENS PVT LTD | 08.08.23 | PO/SKPL/23-24/001035 |  | 14586825
| GRAND TOTAL |  |  |  |  | 15018181.4
EOT Explanation
Sr. No | Description | client | Reference | Planned start date | Planned Finish | Actual Start Date | Actual Finish Date | constraints/ remarks
1 | Work order Awarded | SEMOLINA KITCHENS PVT LTD | PO/SKPL/23-24/001035 | 08.08.23 | 27.09.23 | 20.08.23 | 27.08.23 | We have asked the management that we need 10 days for mobilization and all barication flex design received on 18.08.23
2 | Dismantling work | C&S |  | 08.08.23 | 18.08.23 | 27.08.23 | 15.10.23 | Due to many challenges at site like CISF IT main rack Shifting , ACP along all sides dismantling , All existing live services of client site reallocation , Live Active main duct of floor uplifting took time to close as , all agencies from client sides and airport authorities are involved in it , afterwards based on the space constrains at site we have received the final revised GFC to work
3 | Revised Drawings after dismantling | C&S |  | 10.09.23 | 20.09.23 | 10.09.23 | 15.10.23
4 | Fit out work |  |  | 20.09.23 | 20.12.23 | 15.10.23 | 15.01.24 | Due to many changes at site as mentioned in various MOM and mails the overall schedule deferred to the mentioned dates
5 | Final documentation and billing certification |  |  | 20.12.23 | 05.01.23 | 15.01.24 | 25.01.24

## C&I BOQ
CIVIL & INTERIOR WORK BOQ FOR PROPOSED LOUNGE AT JAIPUR AIRPORT
S.NO | DESCRIPTION OF ITEMS | UNIT | QTY | BOQ RATE | BOQ AMOUNT | RAB -02 SUBMITTED QTY | RAB-02 SUB AMT | RA-1 CHECK TENDER QTY | RA-1 AMOUNT | RAB-02 CHECKED AMD QTY | RAB-02 CHECKED AMD AMT | Remarks
I | DIAMANTLING WORK
I | Dismantling of existing aluminium Door, window frames including glazing, repairing the cavity in teh wall with epoxy mortar and finished smooth as per adjacent finish, colour, texture including removing teh glazings and stacking the serviceable material at teh designated place and disposal of the unserviceable materials at teh designated place for further disposal to teh dumping yard.
|  | SQM | 9.808 | 672.28 | 6593.7222 | 9.808 | 6593.7222 | 0 | 0
0
2 | Dismantling of existing false ceiling work including frame etc and stacking teh serviceable materials at a designated place including disposing/ shifting teh unserviceable material at the designated place for further disposal as per instructions of Project In Charge complete | Job | LS | 4802 | 4802 |  | 0
0
3 | Dismantling of Airconditionning ducts including shifting teh serviceable & non serviceable material at teh designated place as per directions of Project In Charge complete. | Job | LS | 4802 | 4802 |  | 0
0
4 | Dismantling of electrical conduits, wiring, DBS, switches, switch boards, sockets etc as per directions of Project In Charge and shifting teh serviceable & unserviceable materials at teh respective designated places for final disposal | Job | LS | 4802 | 4802 |  | 0
0
5 | Removing teh existing carpet along with base materials if any any disposal of serviceable & un serviceable materials at teh respective designated place for final disposal as per directions of Project In Charge complete. | Job | LS | 2401 | 2401 |  | 0
0
6 | Dismantling of existing stone flooring and disposal of Malwa at teh designated place for final disposal as per directions of Project-in-Charge complete including cleaning teh RCC slab top with wire brushes after shifting of all teh materials as per above items. | Job | LS | 9604 | 9604 |  | 0
0
| TOTAL |  |  |  | 33004.7222 |  | 6593.7222 |  | 0
0
II | CIVIL WORK | [5 empty] | 0
0
7 | Providing and laying 150mm / 200mm / 250mm thick ACC block wall with grade -1 AAC Blocks of density 551.to 650kg / cum conforming to IS : 2185 ( Part -3) in superstructure above plinth level with R.C.C. bend at cill & Lintel level, RCC, Steel reinforcement & CSS of Lintels, Bands etc shall be paid separately under relevant items, with approved block laying polymer modified adhesive mortar all complete as per direction of Engineer-in-Charge. (The payment of RCC band and reinforcement shall be made for separately). size of block (2'-0" x 0'-8" and width 0'-4" ). including the cost of scaffolding, curing etc. complete as specified. | Cum | Rate Only | 7203 |  |  | 0
0
8 | Providing and laying 100mm thick ACC block wall with grade -1 AAC Blocks of density 551.to 650kg / cum conforming to IS : 2185 ( Part -3) in superstructure above plinth level with R.C.C. bend at cill & Lintel level with approved block laying polymer modified adhesive mortar all complete as per direction of Engineer-in-Charge. (The payment of RCC band and reinforcement shall be made for separately). size of block (2'-0" x 0'-8" and width 0'-4" ). the rate is inclusive of scaffolding, tools & tackles, all leads & heights etc. complete. | Sqm | 55.6712 | 1728.72 | 96239.9169 | 76.0473 | 131464.4885 | 55.67 | 96237.8424 | 21.77 | 37634.2344
0
9 | R.C.C- ( 1 : 1.5 : 3 ) ( 1 cement : 1.5 coarse send : 3 graded stone aggregate 20mm nominal size ) for lintels, Lintel in arch etc. or where ever required I/c reinforcement for lintel 4no 12mm dia bars with 8mm dia rings @ 150c/c & centering shuttering for all levels and height.( Door Lintel length as per drawing 100mm wide x 100mm height ) The rate includes RCC, steel, shuttering & de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge. | Rmt | 1.4 | 720.3 | 1008.42 | 2.5 | 1800.75 | 1.4 | 1008.42 | 1.1 | 792.33
0
10 | R.C.C- ( 1 : 1.5 : 3 ) ( 1 cement : 1.5 coarse send : 3 graded stone aggregate 20mm nominal size ) for Band where ever required I/c reinforcement 2Nos 8mm dia bar with 8mm dia links @ 150mm c/c including centering shuttering for all levels and height,( bend cross section size 100mm wide x 75mm thick ) etc. complete. The rate includes RCC ( Cement Concrete + Reinforcemnet steel), Shuttering, de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge. | Rmt | 42.824 | 672.28 | 28789.7187 | 38.14 | 25640.7592 | 41.68 | 28020.6304 | 0 | 0
0
11 | R.C.C in ( 1: 1.5 : 3 ) for counters, slabs ( 75mm thick) I/c reinforcement 10mm dia bar @ 150mm c/c both ways & centering shuttering for all levels and height. The rate includes de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge. | Sqm | 5.2066 | 1152.48 | 6000.5024 |  | 0
0
12 | Providing & laying 50mm thick ( average thickness ) screeding with 1:2:4 cement conc. (1 cement :2 coarse sand :4 graded stone agg 10mm nominal size ) in line and level including required shuttering, curing etc. complete in all respect | CUM | 7.8668 | 7683.2 | 60441.9212 | 8.928 | 68595.567 | 5.42 | 41642.6367 | 0 | 0
0
13 | Extra for above Item No-7 for floating quote of neat cement punning over screeding including curing etc. | Sqm | 157.3353 | 288.12 | 45331.4409 | 154.7271 | 44579.9689 | 68.91 | 19854.3492 | 0
0
14 | Providing and applying 15 mm thick cement plaster of mix in 1:4 (1 cement : 4 coarse sand) at all levels & heights including scaffolding, curing etc. complete as specified. | Sqm | 122.1072 | 528.22 | 64499.4652 | 199.9121 | 105597.5959 | 122.11 | 64500.9442 | 57.709 | 30483.048 | Same as AAC wall
0
| Total of block & R.C.C. & M.S. work |  |  |  | 302311.3852 |  | 377679.1294 |  | 251264.8229 |  | 68909.6124
0
III | INTERIOR WORK | [5 empty] | 0
0
I | FLOORING & WALL TILES / STONE WORK | [5 empty] | 0
0
A | TILE FLOORING | [5 empty] | 0
0
15 | Providing and laying Vitrified tiles in floor in different sizes (thickness to be specified by the manufacturer) with water absorption less than 0.08% and conforming to IS:15622, of approved brand & manufacturer, in all colours and shade, laid on 20 mm thick cement mortar 1:4 (1 cement: 4 coarse sand) jointing with grey cement slurry @3.3 kg/sqm including grouting the joints with white cement and matching pigments etc. The tiles must be cut with the zero chipping diamond cutter only . Laying of tiles will be done with the notch trowel, plier, wedge, clips of required thickness, leveling system and rubber mallet for placing the tiles gently etc complete | Sqm | 28.4657 | 1920.8 | 54676.9166 | 32.7278 | 62863.5582 | 27.8282 | 53452.4066 |  | 0 | 320
| Glazed Vitrified Tiles Matt/Anti skid finish of 600x600mm size with basic cost as Rs.560 per sqm | [5 empty] | 0
0
16 | Deduct for not using 20 mm thick Cement Mortar 1:4 ( 1 Cement: 4 coarse sand) bedding in laying of floor tiles and jointing with grey cement slurry @ 3.3 kg/ sqm. | Sqm | R.O. |  |  |  | 0
0
17 | Fixing glazed/ Ceramic/ Vitrified floor tiles with cement based high polymer modified quick-set tile adhesive (Water based) conforming to IS: 15477,in average 3mm thickness. | Sqm | R.O |  |  |  | 0
0
18 | Providing and laying rectified Glazed Ceramic floor tiles of size 300x300 mm or more (thickness to be specified by the manufacturer), of 1st quality conforming to IS : 15622, of approved make, in colours White, Ivory, Grey, Fume Red Brown, laid on 20 mm thick cement mortar 1:4 (1 Cement: 4 Coarse sand), jointing with grey cement slurry @ 3.3 kg/ sqm including grouting the joints with white cement and matching pigment etc complete.( Basic cost of tile@ Rs.340/- per Sqm ( Under Servery counter area floor Tiles ) | Sqm | 5.2481 | 1440.6 | 7560.4129 | 5.07 | 7303.842 | 3.96 | 5704.776 |  | 0
0
0
B | DADO TILES | [5 empty] | 0
0
0
19 | Providing and fixing 1st quality ceramic glazed wall tiles , 600 x 600mm Glazed/Matt/Anti skid finish etc (thickness to be specified by the manufacturer), of approved make, in all colours, shades as approved by Engineer-in-Charge, for dados, over 12 mm thick bed of cement mortar 1:3 (1 cement : 3 coarse sand) and jointing with grey cement slurry @ 3.3kg per sqm, including pointing in white cement mixed with pigment of matching shade complete. ( Basic cost of tiles @ Rs.480/- Sqm ) | Sqm | 88.3112 | 1776.74 | 156906.0415 | 89.3932 | 158828.4742 | 73.344 | 130313.2186 |  | 0 | 1312
0
20 | Providing and fixing 1st quality ceramic glazed wall tiles , 600 x 600mm Glazed/Matt/Anti skid finish etc (thickness to be specified by the manufacturer), of approved make, in all colours, shades as approved by Engineer-in-Charge, for dados, with cement based high polymer modified quick set adhesive ( water based) conforming to IS :15477, in average 6mm thickness and jointing with grey cement slurry @ 3.3kg per sqm, including pointing in white cement mixed with pigment of matching shade complete. ( Basic cost of tiles @ Rs.480/- Sqm ) | SQM | 11.251 | 1776.74 | 19990.1017 |  | 0
0
21 | Providing & fixing hand made mosaic tiles as per mood board design & drawings with approved quality adhesive on the servery area walls complete as per directions of Project In Charge | SQM | 7.6019 | 3841.6 | 29203.459 | 10.2948 | 39548.4653 | 7.6 | 29196.16 | 1.6817 | 6460.4187 | basic rate assumed 200/sqft
0
22 | Providing and laying Vitrified tiles in different sizes (thickness to be specified by the manufacturer), with water absorption less than 0.08% and conforming to IS: 15622, of approved brand & manufacturer, in all colours and shade, in skirting, riser of steps, laid with cement based high polymer modified quick set tile adhesive (water based) conforming to IS: 15477, in average 6 mm thickness, including grouting of joints (Payment for grouting of joints to be made separately). | [5 empty] | 0 |  |  |  |  | basic rate assumed 65/sqft
| Size of Tile 600x600 mm | SQM | 0.862 | 2112.88 | 1821.3026 |  | 0
0
C | Stone Work | [5 empty] | 0
0
23 | Providing and fixing 18mm thick Granite Stone for window cill, Jams, counter, staircase steps & riser etc. laid over 20 mm. thick cement mortar 1:4 (1 cement :4 coarse sand) and jointed with cement slurry complete as per pattern and design .including moulding ( half / full ), polishing as required complete in all respect. ( Basic cost of Granite stone @ Rs. 200/- Sqft ) | Sqm | 1.8845 | 4321.8 | 8144.4321 |  | 0
0
0
24 | Providing and fixing 16 to 18mm thick Italian Stone for Counter laid over 20 mm. thick cement mortar 1:4 (1 cement :4 coarse sand) and jointed with cement slurry complete as per pattern and design .including full round moulding, rubbing, polishing & curing as required complete in all respect. ( Basic cost of Italian stone @ Rs. 4845/- Sqm )( Actual size of stone to be measured & paid ). | Sqm | 36.5505 | 8163.4 | 298376.3517 | 15.7632 | 128680.9803 | 16.1532 | 131864.7063
0
0
25 | Providing and fixing 16 to 18mm thick Italian Stone for wall fixed with adhesive of approved make over existing partition and jointed with adhesive mixed with pigment to match the shade of stone including necessary grooves & polishing, edge chamfering, buffing, polishing, complete in all respect. ( Basic cost of Italian stone @ Rs. 4845/- Sqm )( Actual size of stone to be measured & paid ). Servery counter area wall & counter facade finishing stone ). | Sqm | 1.1 | 9604 | 10564.4 | 1.425 | 13685.7 | 1.1232 | 10787.2128
0
D | Wooden Flooring | [5 empty] | 0
0
26 | Providing & fixing 15mm thick Engineered wooden flooring of approved make & shade in chevron pattern with 2mm thick base foam including all fixing arrangement & required profile & skirting complete in all respect. (Basic cost of Engineered Wooden flooring@ Rs. 4035/- Sqm) (Actual carpet area at site to be measured & paid ). ( Business Dropdown, Bar Lounge Area, Reception, Servery area, Business centre area & Toilet Vestibule ). | Sqm | 90.93 | 5762.4 | 523975.032 | 103.2078 | 594724.4953 | 90.93 | 523975.032 | 1.53 | 8816.472
0
E | CARPET FLOORING | [5 empty] | 0
0
27 | Providing, laying & fixing carpet flooring of approved brand & manufacture: HAND TUFTED 4.50 LBS. 12- 14MM THK. CUSTOMIZED NYLON HANDTUFTED BROADLOOM CARPET 100% NYLON (NF) | [5 empty] | 0
| SIZE & specifications as per mood board : AS PER DWG. RUBBER UNDERLAY 8 MM. etc complete as per Directions of Project In- Charge complete. | Sqm | 35 | 2160.9 | 75631.5 | 40.5054 | 87528.067 | 35 | 75631.5 | 2.084 | 4503.3156 | basic rate assumed 150/sqft
0
28 | Providing & fixing floor anodised aluminium ( Rose Gold Finish ) transition profile as per approved sample including all fixing arrangement between junction of two type flooring i.e. wooden & carpet & tile / stone junction complete in all respect.( Basic cost for aluminium Transition profile @ Rs. 230/- Rmtr) | Rmt | 30.065 | 480.2 | 14437.213 | 23.774 | 11416.2748 | 0 | 0
0
| Total of Flooring Work |  |  |  | 1201287.163 |  | 1104579.8572 |  | 960925.0123 |  | 19780.2063
0
II | DOOR WINDOW WORK | [5 empty] | 0
0
29 | Providing and fixing door and window frames made out of White ASH Wood with necessary groove ( 6mm x 6 mm ) & single rebate including necessary M.S. hold-fasts/ fastners , minimum four on each side of teh frame, in cement concrete blocks 1: 2: 4 / fasteners ( expendable 10mm dia ) on either side fixed in line and level, finishing with matching finish of teh wall etc. The frame to be treated with necessary anti-termite chemical and fire retardant paint on partition side & finally finished with PU polish complete in all respect. | Cum | 0.042705 | 216090 | 9228.1234 | 0.16426 | 35494.8173 | 0.0095 | 2052.855
0
30 | Providing and fixing 38 mm. thick flush door shutters with vision slit ( 250mm x 900mm apro. as per drawing ) core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both sides of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size SS 304v grade PVD Coated with approved shade, colour & texture butt hinges per leaf with necessary screws and S.S.304 grade PVD Coated handles of long length minimum 60 CMs of height, of approved shape, profile, grip similar finish in tower bolts minimum 300mm long, similar finishes as that of handles door stopper, rubber buffer, vision slit as per design with 6mm thick glass with wooden beading on back side fixed into a special rebate created in block board core of doors ( white ash wood ), handles,motrise dead lock with one side key knob cylinder finished as per handles in, with horizontal & vertical PVD Coated SS 304 grade I or T channel of width 12 mmx6mmx6mm for verticals & 6mmx6mm for horizontal and thickness not less than 6mm for T section etc. complete in all respect. .( Basic cost of laminate @ Rs. 970/-Sqm ) ( Actual size of shutter to be measured & paid ). ( Kitchen Back & Lounge side entry door ) | Sqm | 4.56 | 12005 | 54742.8 | 2.88 | 34574.4 | 2.4824 | 29801.212
0
31 | Providing and fixing 38 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both faces of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, etc. complete in all respect.( Basic cost of laminate @ Rs. 970/-Sqm) ( Actual size of shutter to be measured & paid ). | Sqm | 5.76 | 12005 | 69148.8 | 6.408 | 76928.04 | 3.9108 | 46949.154
0
32 | Extra for cutting rebate in flush door shutter to fix sliding mechanism as per manufacturer of sliding arrangement specifications etc complete as per Directions of Project In Charge complete including finishing the cut area of shutters with ash wood margin of required width & thickness, polished as per edges complete. No deduction of lipping etc cut shall be made from teh measurements. | RMT | 1 | 480.2 | 480.2 |  | 0 |  | 0
0
33 | Extra for providing & Fixing sliding arrangement, mechanism, rollers on bottom , corresponding embedded chanel fixtures of approved brand & manufacture complete with all accessories, screws, fixing, alignment, hanging, finishing, grittiest, fastners, nails, screws etc in all respects of Hafele or equivalent make mechanism of Model SLIDO CLASSIC 80M OR equivalent as per directions of Project In Charge complete. | Each | 1 | 9604 | 9604 |  | 0
0
34A | Supply and installation of dormakaba ALTERRA Single glazed fixed glass partition using 10mm Toughened glass in proprietary natural anodised aluminium sections ALT 50 of size 50mm x 30mm with Concealed sealing (No visible Gaskets/Seals) with acoustic. The profile will have Carpert Groove at the Bottom on both sides for accommodating max. 8mm carpets. Glass to be fixed with help of Proprietary Stability GRIPPER Clamp to have a stable system. It should consists of intermediate slim junction profiles for Glass to Glass vertical joints, 90 Degree L Junction and T Junction profiles suitably to be used as per room configuration designs. No VISIBLE Clip Lines to provide clutter free view at both side of section. The Glass to be Offset mounted towards outer edge leading to minimum aluminium frame on one side. Optional Profile Bottom Seal pair for additional acoustic if required. | [5 empty] | 0
| All Profiles are min 1.5mm thickness excluding 20 microns of Anodizing, Standards applicable | [5 empty] | 0
| • Structural stability test accordance to BS 5234: Part2:1992 & EN 1991-1-1:2002 | [5 empty] | 0
| • Acoustic test for sound insulation in accordance to DIN EN ISO 10140-2 ASTME-E 90 | [5 empty] | 0
| • ALT profile sections are manufactured and tested in accordance to EN573-3, EN755-2, DIN EN 12020 T2 , non_x0002_dimensions manufacturing tolerance deviation DIN ISO 2768- 1 class C = coarse | SQM | 30.005 | 8163.4 | 244942.817 |  | 0 |  | 0
34B | Providing & Fixing in position (in front of the Fixed Glass Glazing) SS 304 grade PVD Coated having outer frame of SS Box Section/ Flat & intermediate SS Square Bar etc. as/drawing fixed to top & bottom with the help of SS PVD Coated Screws matching with the Grill PVD shade etc. complete as per the direction in-charge. | SQM | 21.56 | 14406 | 310593.36 | 36.2243 | 521847.2658 | 21.56 | 310593.36 | 14.6643 | 211253.9058
0
35 | Providing & fixing concealed Hydraulic door closer of approved make Hafele or equivalent, Model No. DCL 71, EN 2-5, DOOR WEIGHT 120 KG including all fixing arrangement complete in all respect. | No | 3 | 3841.6 | 11524.8 | 3 | 11524.8 | 3 | 11524.8
0
36 | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in rose gold SS ) of approved make including all fixing arrangement complete in all respect. DORSET MODEL NO. | No | 3 | 4321.8 | 12965.4 | 3 | 12965.4 | 3 | 12965.4
0
37 | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in SS ) of approved make including all fixing arrangement complete in all respect. | No | 2 | 4321.8 | 8643.6 |  | 0 |  | 0
0
38 | PROVIDING & FIXING 600mm long 'H' type pull handle, hand grip height of 400mm, 36mm dia, made of SS, finished in Rose Gold colour of Dorset or equivalent make as per directions of Project In Charge complete | Set | 3 | 4802 | 14406 | 2 | 9604 | 2 | 9604
0
| Total of Door Window Work |  |  |  | 746279.9004 |  | 702938.7231 |  | 423490.781 |  | 211253.9058
0
III | OTHER WOOD WORK FOR WALL PANELLING, PARTITIONS & STORAGES | [5 empty] | 0
39 | Providing and fixing frame work for partitions/ wall lining etc. made of 50x50x1.6 mm hollow MS tube, placed along the walls, ceiling and floor in a grid pattern with spacing @ 60 cm centre to centre both ways (vertically & horizontally) or at required spacing near opening, with necessary welding at junctions and fixing the frame to wall/ ceiling/floors with steel dash fasteners of 8 mm dia, 75 mm long bolt, including making provision for opening for doors,windows, electrical conduits,switch boards etc., including providing with two coats of approved steel primer etc. complete, all as per direction of Engineer-in-charge. | KG | 1351.44 | 192.08 | 259584.5952 | 2189.2506 | 420511.2552 | 1351.44 | 259584.5952 | 798.576 | 153390.4781
0
40 | Providing and fixing 12mm thick HDHMR ply of approved make & manufacture in two layers, first layer on to existing wall.MS Frame, Wooden Frame with nails, screws, grittiest, cleats, clips as required and second layer with approved adhesive including all fixing arrangement complete in all respect . | Sqm | 178.6872 | 2641.1 | 471930.7639 | 217.55 | 574571.305 | 148.593 | 392448.9723
0
41 | Providing and fixing 12mm thick flexible MR grade ply in two layers, of approved brand & manufacture on existing M.S. frame work, 1st layer with screws, nails, cleats , clips as required and second layer with approved adhesive including all fixing arrangement complete in all respect . | Sqm | 21.4824 | 3361.4 | 72210.9394 | 16.075 | 54034.5218 | 21.48 | 72202.872 | 13.9105 | 46758.7547
0
42 | Providing & fixing first layer of 12mm thick waterproof MR grade flexible ply of approved brand & manufacture in panelling on wall/existing M.S. / termite treated wooden frame with screw then fixing/ pasting with approved adhesive second layer of 12mm thick flexible ply of approved make complete in all respect.( ) | Sqm | Rate only | 3601.5 |  |  | 0
0
43 | Providing and fixing 1mm thick laminate panelling over existing partition as per approved sample including all fixing arrangement complete in all respect. Only finished area to be measured & paid.( Basic cost of Laminate@ Rs.970/-Sqm ). | Sqm | 90.533 | 1440.6 | 130421.8398 | 173.7959 | 250370.3303 | 90.53 | 130417.518 | 13.5945 | 19584.1647
0
44 | Providing & fixing 12mm thick HDHMR ply panelling on wall with required termite treated wooden frame work with the help of gutties & screw , nails complete in all respect. The base frame shall be made from approved quality Kali wood , kiln seasoned, termite treated etc of size 50x25mm( minimum) @600mm c/c with additional members on the ends etc as per Directions of Project In Charge, premium lounge wall and executive lunge wall of block work. | Sqm | 22.423 | 1920.8 | 43070.0984 | 63.6543 | 122267.1218 | 22.42 | 43064.336 | 25.5999 | 49172.2975
0
45 | Providing & fixing 1.2mm thick aluminium. Skirting PVDF coated 100mm height rose gold finish or as per approved sample over existing partition including all fixing arrangement complete in all respect. ( Basic cost Aluminium Skirting @ Rs. 450/-Rmtr) | Rmt | 67.021 | 624.26 | 41838.5295 | 82.771 | 51670.6245 | 67.02 | 41837.9052 | 16.69 | 10418.8994
[7 empty] | 0 |  | 0
46 | Providing and fixing over head storage with necessary shelves as per design made out of 19mm thick HDHMR board fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with 1mm thick laminate including required shelves, shutters and required hardware like handle, knobs, magnetic catcher, hinges, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 270/-Sqm & external surface laminate@ Rs.970/-Sqm) | [5 empty] | 0
0
a | 450mm | Sqm | 13.2683 | 15366.4 | 203885.2368 | 2.1222 | 32610.5741 | 2.358 | 36233.9712
0
47 | Providing and fixing under counter storage with necessary drawers & Shelves as per design made out of 19mm thick HDHMR board fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with 1mm thick laminate including required drawer unit, required shelves , shutters and required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, shutter lock, drawer channel etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 270/-Sqm & external surface laminate@ Rs.970/-Sqm) | [5 empty] | 0
0
a | 600mm deep | Sqm | 13.0212 | 16807 | 218847.3084 |  | 0 |  | 0
0
48 | Providing and fixing partly open partly closed Servery counter storage as per drawing made out of 19mm thick HDHMR board fixed with the help of all necessary hardware like nail and fasteners and all internal area of storage ( Excluding open shelves inner surface ) to be finished with 0.8mm thick laminate and open shelves inner surface to be finished with rose gold finish 1mm thick SS sheet & external facade surface & top surface of survery storage to be finished with Italian stone fixed with adhesive & 100mm high rose gold finish Aluminium skirting at floor level, including required drawer unit, required open shelves, Louver shutters and required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, drawer channel, shutter lock etc. all are superior quality of approved make, complete in all respect. ( Rose Gold finish SS sheet paid separately in rose gold finish SS sheet item & Italian Stone paid separately in Italian stone Item). ( Basic cost of internal laminate @ Rs.270/-Sqm & external surface laminate@ Rs.970/-Sqm.) | [5 empty] | 0
0
a | 1000 mm | Sqm | 8.16 | 19208 | 156737.28 | 8.614 | 165457.712 | 6.2474 | 120000.2513
0
49 | Providing and fixing Reception Table ( 450mm to 600mm Deep ) (2.1mtr. long x 1.2mtr ht. ) made out of 19mm thick HDHMR ply for required partition, front & sides including necessary shelves with shutter & drawers, Key board tray, all necessary hardware of superior quality like nail, self closing type hinges, S.S. handles, knobs, locks, key board tray , etc. And front facade, sides & top finish with Italian marble stone of approved make, shade & texture including all fixing arrangement ,grinding polishing, edge chamfering & polishing & all internal surface to be finished with 0.8mm thick laminate & external exposed drawer / wooden surface to be finished with 1mm thick laminate of approved make & shade & reception table facade surface at floor level 100mm high skirting & top & sides edging finished with PVD coated rose gold finish in aluminium . complete in all respect. ( Basic cost of internal laminate @ Rs.270/- Sqm & external laminate @ Rs970/-Sqm & Italian marble stone @ Rs. 4845/- Sqmt ) & PVD coated rose gold finish 1mm thick SS sheet @ Rs.4420Sqm) | No | 1 | 144060 | 144060 | 1 | 144060 | 1 | 144060
0
50 | Providing making & fixing in position 19mm thick India Map ( 1.58mtr x 1.87mtr) made of 18mm thick MDF Board of approved make finished with 1mm thick PVD coated Rose Gold finish SS sheet with provision for LED light glowing arrangement at location of Lucknow including all fixing arrangement complete in all respect.( Basic cost of PVD coated SS sheet @ Rs.4420/- Sqm ) | No | 1 | 72030 | 72030 | 1 | 72030 | 1 | 72030
0
51 | Providing Making & fixing/pasting with approved adhesive in position 1mm thick SS Sheet of grade 304 PVD coated with approved colour, shade, texture & finish over 12mm thick flexi fire retardant ply of approved brand & manufacture in circular portion of the display at top and on 12mmm thick MDF Board on horizontal/vertical surfaces. the fins of teh display shall be made 50mm thick, with projection of 300mm in straight portion UPTO height of about 2.40meters and thereafter it shall further add 200mm projection to 300mm projection making overall projected length at top most pont( at Ceiling) of 500mm. The top shall have another recessed semicircular ( 50mm inside from 500 mm overall projection at top) of R230mm etc as per drawings. The top surface and all inside surfaces and out side surfaces of fins forming display shall be wrapped with 1mm thick PVD coated SS304 grade sheet with coating of approved colour, shade and texture. The PVD sheet shall be wrapped with approved adhesive etc.. In addition to it a box shall be created at height from 450mm to 1100 mm i.e. 650mm front with wooden Hollock wood battens of appropriate size over it HDHMR board of 19mmm thickness shall be fixed and on this board 19mm thick Italian stone shall be fixed. The HDHMR Board shall be semi circular at teh bottom so shall be Italian stone as per drawing. The top shall also have Italian stoneof size 300x500x19mm with bird beak corner grove joint with teh vertical stone surface, polished complete over HDHMR Board of 19mm thick of approved shade, colour, design, pattern & profile as per drawing complete. The front area in between teh fins shall have 1mm thick laminate on the existing HDHMR partition. there shall be a 10mm thick glass of 500mm height placed above Italian stone with suitable opening & locking arrangement, the glass box shall have top also of 10mmm thick toughened glass fixed to back with tubular section of SS304 grade as frame on corner for fixing glass to glass and glass to side fins and glass to back wall of size 25x10mm, with locking arrangement complete. | [5 empty] | 0
| Rate is inclusive of frame of MS tubular section minimum thickness of 1.6mm and or of wooden chemically treated Hollock wood frame, HDHMR Boards19mm thick for base to Italian stone, Italian stone 19mm thick of required shade, colour, design & pattern, 12mmm MDF sheet & 12mmm thick flexi ply for base to PVD coated SS304 grade sheet, PVD coated 304 SS sheet 1mm thick, frame of MS tubular section of minimum thickness of 1.6mm, laminate 1mm thick of approved design, manufacture & brand, shade colour, design, 100mm thick toughenned glass, PVD coated ss304 grade 1mm thick tubelar section of 25x10mm (minimum) for fixing at corners of glass box, appropriate PVD coated hinges/brackets for making the front glass portion openable or the top glare p[ortion opennable, locking arrangement to glass openable piece, adhesives of approved quality, nails, screws, grittiest of approved brand & manufacture and type matching with teh finish on to which these are used. Etc complete with temporary arrangement for fixing, and fixing to teh back wall secureley. The rate is for one set of overall height 3000mmx 600mm. | [5 empty] | 0
0
b | The rate is also inclusive of fixing 19mmx19mm edge Italian stone at the bottom semi circular portion with adhesive and in pieces in true semi circular profile of teh front Italian stone ( making visible thickness of stone at bottom as 19+19mm=38mm, polishes complete | Set | 3 | 120050 | 360150 | 3 | 360150 | 3 | 360150
0
52 | Providing , making & fixing projected surface with frame of wooden/MS as described in above item having front face 12mm thick MDF Board of approved brand & manufacture fixed with nails, screws, adhesive and then finally fixing Vinyle paper of approved brand, manufacture, colour, shade, pattern & design in between the display sets , the width shall be variable startling with 200mm at base and increasing as per teh profile ( semi circular of display panels) complete with basic cost of Vinyle as 3230/sqm | SQM | 1.5 | 9604 | 14406 |  | 0
0
| Total of other wood work for wall Cladding & Display Rack |  |  |  | 2189172.5913 |  | 2247733.4447 |  | 1672030.4212 |  | 279324.5944
0
IV | False ceiling Work | [5 empty] | 0
0
53 | Providing and fixing split level gypsum board false ceiling including providing and fixing GI grade 175 (120 gm/m2) perimeter, channels (20 x 30 x 27 x 0.50mm thick) fixed to brick masonry / partition / hanging with existing ceiling / existing M.S. frame work and suspended GI intermediate channel. Rate to include making necessary cut out/opening for light fitting A C diffuser etc. The cut out to have perimeter channel of size 20x27x30x.5mm all round and supported suitably and finally finished with gypsum board and finally finished with two or more coat of plastic emulsion paint of approved make & shade with required tapping the joints, base primer, putty complete in all respect. (Actual plan area to be measured & paid.). Rate quoted should be included for all design work, providing false ceiling in circular profile in horizontal as well as vertical edges to teh horizontal circular profiles including straight profiles as per drawing, levels Nothing to be paid extra for design work. PREMIUM LOUNGE AREA | Sqm | 34 | 1920.8 | 65307.2 | 19.8029 | 38037.4103 | 18.291 | 35133.3528
54 | Providing and fixing gypsum board false ceiling with coves on sides along the walls to receive light fixtures, AC diffusers etc including providing and fixing GI grade 175 (120 gm/m2) perimeter, channels (20 x 30 x 27 x 0.50mm thick) fixed to brick masonry / partition / hanging with existing ceiling / existing M.S. frame work and suspended GI intermediate channel. Rate to include making necessary cut out/opening for light fitting A C diffuser etc. The cut out to have perimeter channel of size 20x27x30x.5mm all round and supported suitably and finally finished with gypsum board and finally finished with two or more coat of plastic emulsion paint of approved make & shade with required tapping the joints, base primer, putty complete in all respect. (Actual plan area to be measured & paid.). Rate quoted should be included for all design work, providing false ceiling in circular profile in horizontal as well as vertical edges to teh horizontal circular profiles including straight profiles as per drawing, levels Nothing to be paid extra for design work. EXECUTIVE LOUNGE, RECEPTION, ADMN ROOM etc | SQM | 140 | 2112.88 | 295803.2 | 161.7384 | 341733.8116 | 140 | 295803.2 | 19.95 | 42151.956
0
55 | Providing and fixing Gl Clip in Metal Ceiling System of 600x600 mm module which includes providing and fixing 'C' wall angle of size 20x30x20 mm made of 0.5 mm thick pre painted steel along the perimeter of the room with help of nylon sleeves and wooden screws at 300 mm center to centre, suspending the main C carrier of size 10x38x10 mm made of G.I steel 0.7 mm thick from the soffit with the help of soffit cleat 37x27x25x1.6 mm, rawl plugs of size 38x12 mm and C carrier suspension clip and main carrier bracket at 1000 mm c/c. Inverted triangle shaped Spring Tee having height of 24 mm and width of 34 mm made of Gl steel 0.45 mm thick is then fixed to the main C carrier and in direction perpendicular to it at 600 mm centers with help of suspension brackets. Wherever the main C carrier and spring T have to join, C carrier and spring T connectors have to be used. All sections to be galvanized @ 120 gms/sqm (both side inclusive), fixing with clip in tiles into spring T with : | [5 empty] | 0
| GI Metal Ceiling Clip in plain Bevelled edge global white colour plain tiles of size 600x600 and 0.5 mm thick with 25 mm height, made of G I sheet having galvanizing of 100 gms/ sqm (both sides inclusive) and electro statically polyester powder coated of thickness 60 microns (minimum), including factory painted after bending. ( Kitchen & Kitchen Store false ceiling ) | Sqm | 21.5 | 2401 | 51621.5 | 24.955 | 59917.027 | 27.8482 | 66863.5282
0
| Total of False ceiling Work |  |  |  | 412731.9 |  | 439688.2489 |  | 397800.081 |  | 42151.956
0
V | Finishing Work | [5 empty] | 0
0
56 | Providing & applying P.O.P. punning on walls with an average thickness of 2mm including finishing the surface smooth in line & level complete in all respect. | Sqm | R.O. | 336.14 |  | 47.177 | 15858.0667 |  | 0 | 40.5115 | 13617.5356
0
57 | Providing three or more coats of Plastic Emulsion paint of approved make & shade including preparation of base by cement based putty & primer complete in all respect. ( Admin area inside wall paint ) | Sqm | 50.5802 | 336.14 | 17002.0284 | 225.4765 | 75791.6845 | 0 | 0
0
58 | Providing & fixing Fabric backed Vinyl Wall covering(10.05mtr. X .52mtr ) ( 300gsm Type-II) fire Retardant as per approved sample including all fixing arrangement complete in all respect.( Basic cost of Fabric backed Vinyl Wall covering @ Rs. 3230/- Sqm ) | Sqm | 90.3868 | 4802 | 434037.4136 | 78.5245 | 377074.7931 | 79.834 | 383362.6759
0
| Total of finishing work |  |  |  | 451039.442 |  | 468724.5442 |  | 383362.6759 |  | 13617.5356
0
VI | Misc. Work | [5 empty] | 0
0
59 | Providing & filling 50mm thick Fibre Glass wool ( 64kg density ) in M. S. frame work for partition wall for making sound proof | Sqm | 130.4691 | 720.3 | 93976.8927 | 112.9656 | 81369.1217 | 0 | 0
0
60 | Providing & fixing aluminium. T profile ( 19mm x 19mm x 6mm thick ) PVDF coated ( Rose gold finish ) as per approved sample including all fixing arrangement complete in all respect. ( Basic cost of T Profile @ Rs. 250/- Rmtr. ) | Rmt | 30.065 | 480.2 | 14437.213 | 10.726 | 5150.6252 | 13.7 | 6578.74
0
61 | Providing & fixing Rose Gold finish L- angle aluminium profile ( 12mm x 12mm x 1.5mm thick ) as per approved sample fixed with adhesive of approved make including all fixing arrangement complete in all respect. ( Basic cost of Angle @ Rs. 330 Rmtr. ) | Rmtr | 24.6 | 480.2 | 11812.92 | 61.019 | 29301.3238 | 24.6 | 11812.92 | 38.519 | 18496.8238
0
62 | P/F 1mm thick PVD coated SS sheet fixing on existing wall panelling as per approved sample including all fixing arrangement complete in all respect.( Basic cost of PVD coated SS sheet @ Rs.4420/- Sqm ) | Sqm | 12.645 | 12005 | 151803.225 | 16.1162 | 193475.2811 | 12.5064 | 150138.8518
0
63 | Providing & doing water proofing of sunken areas of Toilets, balconies etc, of following operations: i) Cleaning the sunken area surface using wire brush and then broom making teh surface dust free. Ii) Repairing the holes, depressions or taking out loose materials of brick work/cement plater/concrete and grouting the same with cement concrete (1:11/2:3) or cement plater (1:3) as teh case may be and only if required. Iii) Applying two coats of base primer of URP301 of Dr Fixit or equivalent as per manufacturers specifications. Iv) (laying of pipes, PCC on pipes ) and applying URP301 two coats on teh PCC surfaces and the other ares which got damaged due to laying of pipes and subsequenty made good( grouted). V) Laying of water proof coat of 2K of Dr Fixit or equivalent as per manufacturer's specifications. Vi) Allowing it dry then checking teh sunken areas by water ponding for two days and if leakage is observed then redoing the 2K coats all over again. VII) Laying water proof plaster in slope 1:100 towards spout fixed for drainage in cement mortar 1:3 mixed with water proofing compound with cement @2% by weight of cement , finished neat or as may be specified by teh manufacturer, curing for minimum seven days. | [5 empty] | 0
| Kitchen Area ( raised or sunken) | SQM | 19.6633 | 1920.8 | 37769.2666 | 42.0176 | 80707.4061 | 19.66 | 37762.928 | 18.4092 | 35360.3914
0
64 | Providing & filling Khanger in the sunken areas as per Directions of Project-in-Charge | CUM | 1 | 6242.6 | 6242.6 | 5.7199 | 35706.8729 | 1 | 6242.6 | 4.9506 | 30904.8653
0
65 | Providing and doing 12mm thick solid surface ( corian) of approved, shade, texture, make & manufacture over base of 12mm water proof ply with all adhesives, including all processes & making the curves smooth and joints seamless as per profile, drawings and instructions of Engineer incharge complete | SQM | 13.65 | 15366.4 | 209751.36 | 29.2898 | 450078.7827 | 13.65 | 209751.36 | 5.7092 | 87729.0826 | basic rate of corion assumed as 800/sqft
0
0
0
| Total of Misc. Work |  |  |  | 525793.4774 |  | 875789.4136 |  | 422287.3998 |  | 172491.163
0
D | SANITARY FIXTURES FITTINGS WORK | [5 empty] | 0
0
66 | P / F CP Brass 15mm Diameter Angle Valve of KOHLER make Model-PARALLEL or as approved by the Project-in-Charge. | No | 4 | 1920.8 | 7683.2 | 8 | 15366.4 | 4 | 7683.2 | 5 | 9604
0
0
67 | Providing & fixing ROB HOOK of EURONICS make Model No. EC02 or equivalent as approved by the Project-in-Charge. | No | 8 | 2881.2 | 23049.6 | 8 | 23049.6 | 0 | 0
0
68 | P / F S.S. Liquid Soap dispenser of aEURONICS make Model No. ES80A or equivalent. | No | 4 | 7203 | 28812 | 4 | 28812 | 0 | 0
0
69 | Providing SS 304 grade Dust Bin in W.C. area of approved make and size of 6 L Capacity of KOHLER Make reference Model No. K-17531T-ST or equivalent( approximately 300mm dia and 45 cms high) etc as per directions of Project -in-Charge | No | 8 | 3841.6 | 30732.8 | 8 | 30732.8 | 0 | 0
0
0
70 | Providing & fixing Sink mixture of CERA make Model No. F 2002511 or equivalent as approved by the Project -in-Charge. | No | 1 | 6242.6 | 6242.6 | 2 | 12485.2 | 1 | 6242.6 | 1 | 6242.6
0
71 | Providing & fixing single bowl single draining board , stain less steel grade 304 kitchen sink, with coating for sound absorption, CP waste, CP Brass bottle trap of 32mm dia of NIRALI make of size 1000x510x250mm or equivalent as approved by the Project-in-Charge. | No | 1 | 8163.4 | 8163.4 | 2 | 16326.8 |  | 0
0
72 | Providing & fixing Bar Sink in SS ( 304 grade ) of KAFF Make reference Model No. KS 22 SB (R10) of size 220x440x200mm Bowl size of 180x400x200mm, 1 mm thick SS Sheet, with sound reduction pad all around & bottom, anti condensation coating etc with all fixtures, firings, brackets , screws, fasteners for fixing to wall and or counter as per drawing or equivalent Make as approved by the Project-in-Charge complete as per drawings & instructions of Project-in-Charge. | No | 1 | 9604 | 9604 | 2 | 19208 | 0 | 0
0
73 | Providing & fixing dual level spout of CP Brass of KOHLER Make reference Model No.CUFF K-37316IN-4-CP OR OF EQUIVALENT MAKE AS as approved by Project-in-Charge for bar sink etc complete. | No | 1 | 6722.8 | 6722.8 | 2 | 13445.6 | 0 | 0
0
0
74 | Providing and fixing 12mm thick flexible ply (curved area) of approved make over existing partition for wall paper & Laminate panelling base including all fixing arrangement complete in all respect . | Sqm | Rate only | 1920.8 |  |  | 0
0
75 | Providing & fixing 12mm thick gypsum board over existing partition for paint base including all fixing arrangement complete in all respect. | Sqm | Rate only | 768.32 |  | 70 | 53782.4 |  | 0 | 25.5531 | 19632.9578
0
76 | Providing and fixing 12mm thick HDHMR ply of approved make on existing wall & counter with the help of wooden gutties / PVC sleeves & Screw including drilling etc. for solid surface ( Corian ) base including all fixing arrangement complete in all respect . | Sqm | Rate only | 1200.5 |  |  | 0
0
| TOTAL |  |  |  | 121010.4 |  | 213208.8 |  | 13925.8 |  | 35479.5578
0
0
| Extra Non Tender Items |  |  | NT RATES
1 | Providing and fixing 12 mm thick CNC cut HDHMR jaali as per approved design and drawings finished with Duco Paint of approved shade to be cladded on HHDMR wall from adhasive complete with all accessories . | Sqm |  | 8850 | 0 | 11.0016 | 97364.16 |  | 0 | 10.44 | 92394
2 | Providing and installation of coloured film as per aprooved design on front glass. | Sqm |  | 4350 | 0 | 22 | 95700 |  | 0
3 | Provding and fixing MOULDING over Exp joint FINISH WITH pu PAINT on floor as per required by EIC | RMT |  | 3150 | 0 | 8 | 25200 |  | 0
4 | Providing and fixing wooden Rafter 80mm x 40 mm made out of soild wood as per approved design finished with 1 mm laminate of approved make complete in all respect. | RMT |  | 2150 |  | 67.6 | 145340 |  | 0 | 67.6 | 145340
4 | Providing and fixing Foot rail at reception counter made of 50 mm hollow pipe cladded with PVD coated ss sheet in rose gold finish as per approved design | RMT |  | 4350 |  | 20.877 | 90814.95 | 0 | 0
| Total Non Tender Items | [5 empty] | 454419.11 |  |  |  | 237734

## MB (hidden)
S.NO | DESCRIPTION OF ITEMS | No | L | B | H | Total
| Carpet Area in Sqm | 1 |  |  |  | 0
Say Area in Sqm
I | DIAMANTLING WORK
I | Dismantling of existing aluminium Door, window frames including glazing, repairing the cavity in the wall with epoxy mortar and finished smooth as per adjacent finish, colour, texture including removing teh glazings and stacking the serviceable material at teh designated place and disposal of the unserviceable materials at teh designated place for further disposal to teh dumping yard. | 1 | 3.065 |  | 3.2 | 9.808
[5 empty] | SQM | 9.808
2 | Dismantling of existing false ceiling work including frame etc and stacking teh serviceable materials at a designated place including disposing/ shifting teh unserviceable material at the designated place for further disposal as per instructions of Project In Charge complete | Job | LS
3 | Dismantling of Airconditionning ducts including shifting teh serviceable & non serviceable material at teh designated place as per directions of Project In Charge complete. | Job | LS
4 | Dismantling of electrical conduits, wiring, DBS, switches, switch boards, sockets etc as per directions of Project In Charge and shifting teh serviceable & unserviceable materials at teh respective designated places for final disposal | Job | LS
5 | Removing the existing carpet along with base materials if any and disposal of serviceable & un serviceable materials at the respective designated place for final disposal as per directions of Project In Charge complete. | Job | LS
6 | Dismantling of existing stone flooring and disposal of Malwa at the designated place for final disposal as per directions of Project-in-Charge complete including cleaning teh RCC slab top with wire brushes after shifting of all the materials as per above items. | Job | LS
II | CIVIL WORK
7 | Providing and laying 150mm / 200mm / 250mm thick ACC block wall with grade -1 AAC Blocks of density 551.to 650kg / cum conforming to IS : 2185 ( Part -3) in superstructure above plinth level with R.C.C. bend at cill & Lintel level, RCC, Steel reinforcement & CSS of Lintels, Bands etc shall be paid separately under relevant items, with approved block laying polymer modified adhesive mortar all complete as per direction of Engineer-in-Charge. (The payment of RCC band and reinforcement shall be made for separately). size of block (2'-0" x 0'-8" and width 0'-4" ). including the cost of scaffolding, curing etc. complete as specified. | Cum | Rate Only
8 | Making ACC block wall in cement mortar 1:4 ( 1 cement : 4 c/sand) of 4" thick block size (2'-0"x8" and width 4")) | Sqft
| Executive Lounge End Wall 9 in place of glass) | 1 | 3.065 |  | 3.4 | 10.421
| Store End Wall( abutting Coloumn) | 1 | 1.95 |  | 3.4 | 6.63
| Wall of Store/ Premium Lounge | 1 | 2.435 |  | 4.2 | 10.227
| Wall kitchen/servery & Lounge | 1 | 2.06 |  | 4.2 | 8.652
|  | 1 | 2.878 |  | 4.2 | 12.0876
| Wall store/kitchen | 1 | 2.42 |  | 4.2 | 10.164
| Less door | -1 | 0.8 |  | 2.4 | -1.92
| Less beam projection | -1 | 0.25 |  | 0.8 | -0.2
| End wall | 1 | 0.96 |  | 4.2 | 4.032
| Less door lintel | -1 | 1.4 |  | 0.1 | -0.14
| Kitchen/surgery wall | -3 | 7.373 |  | 0.1 | -2.2119
| Store end wall | -3 | 1.95 |  | 0.1 | -0.585
| Store/kit wall | -3 | 2.42 |  | 0.1 | -0.726
| Less door | 2 | 0.8 |  | 0.1 | 0.16
| Executive lounge end wall | -3 | 3.065 |  | 0.1 | -0.9195
55.6712
9 | R.C.C- M-20 in lintels, beams, soffits, shelves counters, slabs, staircase, Lintel in arch etc or where ever required I/c required reinforcement as per design & centring shuttering for all levels and height. |  |  |  |  | 0
100mm wide and 100mm high lintels
| Store room enterance door lintel(800mm opening) | 1 | 1.4 |  |  | 1.4
1.4
10 | RCC Band @1.00m c/c in 100 mm thick AAC block walls
| Kitchen/surgery wall | 3 | 7.373 |  |  | 22.119
| Store end wall | 3 | 1.95 |  |  | 5.85
| Store/kit wall | 3 | 2.42 |  |  | 7.26
| Less door | -2 | 0.8 |  |  | -1.6
| Executive lounge end wall | 3 | 3.065 |  |  | 9.195
11 | R.C.C in ( 1: 1.5 : 3 ) for counters, slabs ( 75mm thick) I/c reinforcement 10mm dia bar @ 150mm c/c both ways & centering shuttering for all levels and height. The rate includes de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge. |  |  |  |  | 42.824
Counter slab
| Kitchen | 1 | 5.138 |  | 0.7 | 3.5966
| Kitchen sink side | 1 | 2.3 |  | 0.7 | 1.61
5.2066
12 | Providing & laying cement conc. (1: 2 : 4) cement : 2 coarse sand :4 graded stone agg 10 mm nominal size ) |  |  |  |  | 0
| Store ( tentative) | 1 | 2.42 | 2.335 | 0.05 | 0.28253
| Kitchen( | 1 | 2.42 | 2.06 | 0.05 | 0.24926
|  | 1 | 2.878 | 2.71 | 0.05 | 0.38997
| Wooden flooring Area | 1 | 95 |  | 0.05 | 4.75
| Carpet Flooring Area | 1 | 35 |  | 0.05 | 1.75
| Italian Flooring Area | 1 | 8.9 |  | 0.05 | 0.445
7.8668
13 | Neat cement punning over screeding
Wooden flooring area
| Store ( tentative) | 1 | 2.42 | 2.335 |  | 5.6507
| Kitchen( | 1 | 2.42 | 2.06 |  | 4.9852
|  | 1 | 2.878 | 2.71 |  | 7.7994
| Wooden flooring Area | 1 | 95 | 1 |  | 95
| Carpet Flooring Area | 1 | 35 | 1 |  | 35
| Italian Flooring Area | 1 | 8.9 | 1 |  | 8.9
157.3353
157.3353
14 | Providing and applying 15 mm thick cement plaster of mix in 1:4 (1 cement : 4 course sand) at all levels & heights including scaffolding, curing etc. complete as specified. |  |  |  |  | 0
| Executive Lounge End Wall ( in place of glass) | 2 | 3.065 |  | 3.4 | 20.842
| Store End Wall( abutting Coloumn) | 2 | 1.95 |  | 3.4 | 13.26
| Wall of Store/ Premium Lounge | 2 | 2.435 |  | 4.2 | 20.454
| Wall kitchen/servery & Lounge | 2 | 2.06 |  | 4.2 | 17.304
|  | 2 | 2.878 |  | 4.2 | 24.1752
| Wall store/kitchen | 2 | 2.42 |  | 4.2 | 20.328
| Less door | -1 | 0.8 |  | 2.4 | -1.92
| Less beam projection | -2 | 0.25 |  | 0.8 | -0.4
| End wall | 2 | 0.96 |  | 4.2 | 8.064
122.1072
15 | P/F Vitrified tiles of approved shade and size for flooring , skirting fixed with cement mortar 12mm thick in 1:4 ratio including filling the joints with grout to match the shade of the tiles to give a smooth surface. |  | Grey Color
| Kitchen flooring as per polyline area | 1 | 4.938 | 2.5 |  | 12.345
| Store room floor | 1 | 2.335 | 2.42 |  | 5.6507
| Admin floor tiles P line basis | 1 | 7.95 |  |  | 7.95
| Additional store Room | 1 | 2.1 | 1.2 |  | 2.52
| Total |  |  |  |  | 28.4657
16 | Deduct for not using 20 mm thick Cement Mortar 1:4 ( 1 Cement: 4 coarse sand) bedding in laying of floor tiles and jointing with grey cement slurry @ 3.3 kg/ sqm. | Sqm | R.O.
17 | Fixing glazed/ Ceramic/ Vitrified floor tiles with cement based high polymer modified quick-set tile adhesive (Water based) conforming to IS: 15477,in average 3mm thickness. | Sqm | R.O
18 | Providing and laying rectified Glazed Ceramic floor tiles of size 300x300 mm or more (thickness to be specified by the manufacturer), of 1st quality conforming to IS : 15622, of approved make, in colours White, Ivory, Grey, Fume Red Brown, laid on 20 mm thick cement mortar 1:4 (1 Cement: 4 Coarse sand), jointing with grey cement slurry @ 3.3 kg/ sqm including grouting the joints with white cement and matching pigment etc complete.( Basic cost of tile@ Rs.340/- per Sqm ( Under Servery counter area floor Tiles )
Tile -3
Under Servery Counter area floor tiles
Servery Counter area floor tiles ( Veg )
|  | 1 | 3.874 | 0.65 |  | 2.5181
| Servery Counter area floor tiles (Non Veg. ) | 1 | 4.2 | 0.65 |  | 2.73
[5 empty] | SQM | 5.2481
19 | P/F 6mm thick ceramic tiles of approved shade and size for kitchen walls fixed with cement mortar 12mm thick in 1:4 ratio including filling the joints mixed with pigment to match the shade of the tiles to give a smooth surface
| Store wall end & door side wall | 2 | 2.42 |  | 3.1 | 15.004
| Store side walls | 2 | 2.335 |  | 3.1 | 14.477
| Less store entry door | -1 | 0.8 |  | 2.4 | -1.92
| Kitchen wall store side with door | 1 | 2.42 |  | 3.1 | 7.502
| Less door DS1A | -2 | 0.8 |  | 2.4 | -3.84
| Servery side wall of kitched | 1 | 2.06 |  | 3.1 | 6.386
|  | 1 | 2.878 |  | 3.1 | 8.9218
| Less Live Counter Window | -1 | 1.99 |  | 1.99 | -3.9601
| Other side wall of kitchen ( sink side) | 1 | 2.06 |  | 3.1 | 6.386
|  | 1 | 2.6 |  | 3.1 | 8.06
| Sides of coloumns | 1 | 1.8 |  | 3.1 | 5.58
| Set back | 1 | 0.635 |  | 3.1 | 1.9685
| Opening jamb | 1 | 0.1 |  | 3.1 | 0.31
|  | 1 | 0.96 |  | 3.1 | 2.976
| Store Wall Additional | 2 | 2.1 |  | 3.1 | 13.02
|  | 2 | 1.2 |  | 3.1 | 7.44
88.3112
20 | Providing and fixing 1st quality ceramic glazed wall tiles , 600 x 600mm Glazed/Matt/Anti skid finish etc (thickness to be specified by the manufacturer), of approved make, in all colours, shades as approved by Engineer-in-Charge, for dados, with cement based high polymer modified quick set adhesive ( water based) conforming to IS :15477, in average 6mm thickness and jointing with grey cement slurry @ 3.3kg per sqm, including pointing in white cement mixed with pigment of matching shade complete. ( Basic cost of tiles @ Rs.480/- Sqm )
| Lounge wall kit side with adhesive | 1 | 3.01 |  | 3.1 | 9.331
| Less DS1A | -1 | 0.8 |  | 2.4 | 1.92
11.251
21 | Providing & fixing hand made mosaic tiles as per mood board design & drawings with approved quality adhesive on the servery area walls complete as per directions of Project In Charge
Cladding on wallls
| Counter back wall above counter ( veg ) | 1 | 3.87 |  | 0.6 | 2.322
|  | 1 | 2.87 |  | 2.2 | 6.314
| Counter façade area | 1 | 1.33 |  | 2.2 | 2.926
| Less Live Counter Window Kitchen side | -1 | 1.99 |  | 1.99 | -3.9601
7.6019
22 | Providing and laying Vitrified tiles in different sizes (thickness to be specified by the manufacturer), with water absorption less than 0.08% and conforming to IS: 15622, of approved brand & manufacturer, in all colours and shade, in skirting, riser of steps, laid with cement based high polymer modified quick set tile adhesive (water based) conforming to IS: 15477, in average 6 mm thickness, including grouting of joints (Payment for grouting of joints to be made separately).
Size of Tile 600x600 mm
| ADMN ROOM | 1 | 1.03 |  | 0.1 | 0.103
|  | 1 | 2.2 |  | 0.1 | 0.22
|  | 1 | 0.275 |  | 0.1 | 0.0275
|  | 1 | 0.815 |  | 0.1 | 0.0815
|  | 1 | 1.88 |  | 0.1 | 0.188
|  | 1 | 2.42 |  | 0.1 | 0.242
0.862
23 | Providing and fixing 18mm thick Granite Stone for window cill, Jams, counter, staircase steps & riser etc. laid over 20 mm. thick cement mortar 1:4 (1 cement :4 coarse sand) and jointed with cement slurry complete as per pattern and design .including moulding ( half / full ), polishing as required complete in all respect. ( Basic cost of Granite stone @ Rs. 200/- Sqft ) | Sqft
| Kitchen counter stone | 1 | 2.06 |  | 0.6 | 1.236
|  | 1 | 2.878 |  | 0.6 | 1.7268
|  | 1 | 2.6 |  | 0.6 | 1.56
4.5228
| Latak stone front of counter | 1 | 2.06 |  | 0.15 | 0.309
|  | 1 | 2.878 |  | 0.15 | 0.4317
|  | 1 | 2.6 |  | 0.15 | 0.39
| Counter back wall | 1 | 2.06 |  | 0.1 | 0.206
|  | 1 | 2.878 |  | 0.1 | 0.2878
|  | 1 | 2.6 |  | 0.1 | 0.26
1.8845
24 | Providing and fixing 16 to 18mm thick Italian Stone for Counter laid over 20 mm. thick cement mortar 1:4 (1 cement :4 coarse sand) and jointed with cement slurry complete as per pattern and design .including full round moulding, rubbing, polishing & curing as required complete in all respect. ( Basic cost of Italian stone @ Rs. 4845/- Sqm )( Actual size of stone to be measured & paid ).
PEDESTAL FOR PLANTER
| SIDE WALLS | 2 | 12.01 |  | 0.35 | 8.407
| TOP | 1 | 12.01 | 0.35 |  | 4.2035
| SERVERY COUNTER | 1 | 3.6 | 0.8 |  | 2.88
|  | 1 | 4.2 | 0.8 |  | 3.36
| REception Table top | 1 | 2 | 1 |  | 4
|  | 1 | 4 |  | 1.05 | 4.2
|  | 1 | 4 |  | 0.15 | 0.6
| RECEPTION AREA FLOOR | 1 |  |  |  | 8.9
36.5505
25 | Providing and fixing 16 to 18mm thick Italian Stone for wall fixed with adhesive of approved make over existing partition and jointed with adhesive mixed with pigment to match the shade of stone including necessary grooves & polishing, edge chamfering, buffing, polishing, complete in all respect. ( Basic cost of Italian stone @ Rs. 4845/- Sqm )( Actual size of stone to be measured & paid ). Servery counter area wall & counter facade finishing stone ).
| Counter latak | 1 | 3.6 |  | 0.1 | 0.36
| Both side | 1 | 4.2 |  | 0.1 | 0.42
| SIDES | 2 | 0.8 |  | 0.1 | 0.16
|  | 2 | 0.8 |  | 0.1 | 0.16
1.1
26 | Providing & fixing 15mm thick Engineered wooden flooring of approved make & shade in chevron pattern with 2mm thick base foam including all fixing arrangement & required profile & skirting complete in all respect. (Basic cost of Engineered Wooden flooring@ Rs. 4035/- Sqm) (Actual carpet area at site to be measured & paid ). ( Business Dropdown, Bar Lounge Area, Reception, Servery area, Business centre area & Toilet Vestibule ).
Wooden Flooring Area
As per polyline
| Servery Area, Executive LOUNGE, merchandise display area, Digital Display area, | 1 | 93.45 |  |  | 93.45
| Less Additional Store Room created | -1 | 2.1 | 1.2 |  | -2.52
90.93
90.93
CARPET FLOORING
27 | Providing, laying & fixing carpet flooring of approved brand & manufacture: HAND TUFTED 4.50 LBS. 12- 14MM THK. CUSTOMIZED NYLON HANDTUFTED BROADLOOM CARPET 100% NYLON (NF)
SIZE & specifications as per mood board : AS PER DWG. RUBBER UNDERLAY 8 MM. etc complete as per Directions of Project In- Charge complete.
Carpet flooring ( 01 )
| Premium lounge as per polyline | 1 | 34.37 |  |  | 34.37
0
34.37
35
28 | Providing & fixing aluminium. T profile ( 19mm x 19mm x 6mm thick ) PVDF coated ( Rose gold finish ) as per approved sample including all fixing arrangement complete in all respect. ( Basic cost of T Profile @ Rs. 250/- Rmtr. )
Aliminium T profile
| Executive Lounge wall on the side of servery & Kitchen foyer-Horizontal | 1 | 6.415 |  |  | 6.415
| Executive Lounge wall on the side of servery & Kitchen foyer- vertical | 1 | 4.97 |  |  | 4.97
| Executive Lounge wall ( block work) | 1 | 7.01 |  |  | 7.01
| Executive Lounge wall ( block work)- vertical | 1 | 2.67 |  |  | 2.67
| Misc | LS | 9 |  |  | 9
30.065
WOOD WORK
Providing and fixing door and window frames made out of White ASH Wood with necessary groove ( 6mm x 6 mm ) & single rebate including necessary M.S. hold-fasts/ fastners , minimum four on each side of teh frame, in cement concrete blocks 1: 2: 4 / fasteners ( expendable 10mm dia ) on either side fixed in line and level, finishing with matching finish of teh wall etc. The frame to be treated with necessary anti-termite chemical and fire retardant paint on partition side & finally finished with PU polish complete in all respect.
Door Frame
| Store Door Frame DS1A | 2 | 0.8 | 0.01 | 0.065 | 0.00104
|  | 4 | 0.01 | 0.065 | 2.4 | 0.00624
| Door frame Kit passage entry/servery | 1 | 0.9 | 0.01 | 0.065 | 0.000585
|  | 2 | 0.1 | 0.065 | 2.4 | 0.0312
| Admin Office/ Passage | 1 | 0.8 | 0.01 | 0.065 | 0.00052
|  | 2 | 0.01 | 0.065 | 2.4 | 0.00312
0.042705
Providing and fixing 38 mm. thick flush door shutters with vision slit ( 250mm x 900mm apro. as per drawing ) core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both sides of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size SS 304v grade PVD Coated with approved shade, colour & texture butt hinges per leaf with necessary screws and S.S.304 grade PVD Coated handles of long length minimum 60 CMs of height, of approved shape, profile, grip similar finish in tower bolts minimum 300mm long, similar finishes as that of handles door stopper, rubber buffer, vision slit as per design with 6mm thick glass with wooden beading on back side fixed into a special rebate created in block board core of doors ( white ash wood ), handles,motrise dead lock with one side key knob cylinder finished as per handles in, with horizontal & vertical PVD Coated SS 304 grade I or T channel of width 12 mmx6mmx6mm for verticals & 6mmx6mm for horizontal and thickness not less than 6mm for T section etc. complete in all respect. .( Basic cost of laminate @ Rs. 970/-Sqm ) ( Actual size of shutter to be measured & paid ). ( Kitchen Back & Lounge side entry door )
| Vision Slit Door shutter Kitchen passage/ servery area DVP1 | 1 | 0.9 |  | 2.4 | 2.16
| Servery / premium Lounge entry Sliding shutter SD1 | 1 | 1 |  | 2.4 | 2.4
4.56
Providing and fixing 38 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both faces of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, etc. complete in all respect.( Basic cost of laminate @ Rs. 970/-Sqm) ( Actual size of shutter to be measured & paid ).
Flush door shutters
| Admin entry door shutter. DS1 | 1 | 0.8 |  | 2.4 | 1.92
| Store Room Door Shutters DS1A | 2 | 0.8 |  | 2.4 | 3.84
5.76
32 | Extra for cutting rebate in flush door shutter to fix sliding mechanism as per manufacturer of sliding arrangement specifications etc complete as per Directions of Project In Charge complete including finishing the cut area of shutters with ash wood margin of required width & thickness, polished as per edges complete. No deduction of lipping etc cut shall be made from teh measurements. | RMT | 1 |  | 1 | 1
1
33 | Extra for providing & Fixing sliding arrangement, mechanism, rollers on bottom , corresponding embedded chanel fixtures of approved brand & manufacture complete with all accessories, screws, fixing, alignment, hanging, finishing, grittiest, fastners, nails, screws etc in all respects of Hafele or equivalent make mechanism of Model SLIDO CLASSIC 80M OR equivalent as per directions of Project In Charge complete. | Each | 1 |  |  | 1
1
Providing & fixing floor anodised aluminium ( Rose Gold Finish ) transition profile as per approved sample including all fixing arrangement between junction of two type flooring i.e. wooden & carpet & tile / stone junction complete in all respect.( Basic cost for aluminium Transition profile @ Rs. 230/- Rmtr)
Transition profile
| Premium Lounge/ Digital Display Area | 1 | 1.945 |  |  | 1.945
|  | 1 | 0.905 |  |  | 0.905
| Reception/display , lounge entry point | 1 | 1.8 |  |  | 1.8
| DVP1 | 3 | 0.9 |  |  | 0.9
| SD1 | 1 | 1.1 |  |  | 1.1
6.65
34 | Supply and installation of dormakaba ALTERRA Single glazed fixed glass partition using 10mm Toughened glass in proprietary natural anodised aluminium sections ALT 50 of size 50mm x 30mm with Concealed sealing (No visible Gaskets/Seals) with acoustic. The profile will have Carpert Groove at the Bottom on both sides for accommodating max. 8mm carpets. Glass to be fixed with help of Proprietary Stability GRIPPER Clamp to have a stable system. It should consists of intermediate slim junction profiles for Glass to Glass vertical joints, 90 Degree L Junction and T Junction profiles suitably to be used as per room configuration designs. No VISIBLE Clip Lines to provide clutter free view at both side of section. The Glass to be Offset mounted towards outer edge leading to minimum aluminium frame on one side. Optional Profile Bottom Seal pair for additional acoustic if required.
All Profiles are min 1.5mm thickness excluding 20 microns of Anodizing, Standards applicable
• Structural stability test accordance to BS 5234: Part2:1992 & EN 1991-1-1:2002
• Acoustic test for sound insulation in accordance to DIN EN ISO 10140-2 ASTME-E 90
• ALT profile sections are manufactured and tested in accordance to EN573-3, EN755-2, DIN EN 12020 T2 , nondimensions manufacturing tolerance deviation DIN ISO 2768- 1 class C = coarse
| Executive Lounge side wall | 1 | 8.825 |  | 3.4 | 30.005
30.005
35 | Providing & fixing concealed Hydraulic door closer of approved make including all fixing arrangement complete in all respect.
Door Closer
| Kitchen Store Entry door | 1 |  |  |  | 1
| Admin entry door shutter | 1 |  |  |  | 1
| Kitchen entry servery side | 1 |  |  |  | 1
3
36 | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in rose gold SS ) of approved make including all fixing arrangement complete in all respect.
Door Lock
| Admin entry door shutter | 1 |  |  |  | 1
| Kitchen entry servery side | 1 |  |  |  | 1
| DS1A | 1 |  |  |  | 1
3
37 | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in SS ) of approved make including all fixing arrangement complete in all respect.
| Kitchen Store Entry door | 2 |  |  |  | 2
2
38 | PROVIDING & FIXING 600mm long 'H' type pull handle, hand grip height of 400mm, 36mm dia, made of SS, finished in Rose Gold colour of Dorset or equivalent make as per directions of Project In Charge complete | Set | 3 |  |  | 3
3
39 | Providing and fixing frame work for partitions/ wall lining etc. made of 50x50x1.6 mm hollow MS tube, placed along the walls, ceiling and floor in a grid pattern with spacing @ 60 cm centre to centre both ways (vertically & horizontally) or at required spacing near opening, with necessary welding at junctions and fixing the frame to wall/ ceiling/floors with steel dash fasteners of 8 mm dia, 75 mm long bolt, including making provision for opening for doors,windows, electrical conduits,switch boards etc., including providing with two coats of approved steel primer etc. complete, all as per direction of Engineer-in-charge.
M.S. Work
| Partition wall servery/executive lounge | 1 | 3.01 |  |  | 3.01
| Door | 1 | 0.1 |  |  | 0.1
|  | 1 | 3.46 |  |  | 3.46
| Servery/executive lounge semi circular wall | 1 | 1.2452 |  |  | 1.2452
| Veg side semi circular wall | 1 | 1.331 |  |  | 1.331
| Servery/premium lounge wall | 1 | 1.1 |  |  | 1.1
| SD1( sliding door) | 1 | 1 |  |  | 1
| Other side of SD1 | 1 | 1.83 |  |  | 1.83
| Business Drop down/ premium lounge wall | 1 | 1.735 |  |  | 1.735
| Merchandise display wall | 1 | 7.04 |  |  | 7.04
| Admn Room walls passage side straight | 1 | 2.035 |  |  | 2.035
| Door DS1 | 1 | 0.8 |  |  | 0.8
| Off set | 1 | 0.2 |  |  | 0.2
| Admn room/executive lounge wall staraight | 1 | 1.06 |  |  | 1.06
| Offset | 1 | 0.2 |  |  | 0.2
|  | 1 | 0.347 |  |  | 0.347
| Semi circular wall( digital display ) | 1 | 4.069 |  |  | 4.069
| Side of digital wall | 1 | 0.347 |  |  | 0.347
| Semi circular reception side | 1 | 0.913 |  |  | 0.913
|  | 1 | 2.681 |  |  | 2.681
| Dummy staraight | 1 | 1.03 |  |  | 1.03
| Semi circular behind digital wall | 1 | 2.201 |  |  | 2.201
| Dead off set | 1 | 0.275 |  |  | 0.275
| Door jamb wall of DVP1 | 1 | 0.1 |  |  | 0.1
| Store ( additional) | 1 | 1.3 |  |  | 1.3
|  | 1 | 1.2 |  |  | 1.2
40.6092
| Total vertical members @600mm c/c | 67.682
| Add 10% extra fro additional members at small places and at ends for estimation | 6.7682
| Total | 74.4502 | Nos
| Height ( assuming 4.2 meters up to soffit of slab as availability) | 312.6909 | Rmt | Deduction for door not done |  | 750.4583
| Horizontal members assuming height of 4.2 meters | 7
| Add 10 % extra for end and Small places | 0.7
| Total | 7.7
| Total length = 7.7x 43.24 | 312.6909 | Rmt |  |  | 750.4583
50x50x1.6mm thick tubal section weight
| 12mm thick plates for floors | 81 | 0.3 | 0.3 | 94.2 | 686.718
| 6mm thick plate for top position at ceiling level if required | 81 | 0.3 | 0.3 | 47.1 | 343.359
| fastners 8mm dia 75mm long | 648 | 0.075 | 0.62 |  | 30.132
Say vertical members
PLANTER PEDESTAL 12.01 METERS LONG
| VERTICAL PIECES OF 50X50X1.6MM | 3 | 20.0167 | 0.35 | 2.4 | 50.442
| HORIZONTAL | 4 | 12.01 |  | 2.4 | 115.296
| PLATES | 67 | 0.3 | 0.3 | 47.1 | 284.013
| FASTNERS | 268 | 0.075 | 0.62 |  | 12.462
| VERTICAL PIECES OF 50x50x3mm | 26 | 3.4 | 4.71 |  | 416.364
| Vertical pieces over feature wall (200mm high) | 19 | 0.2 | 2.4 |  | 9.12
| Horizontal | 2 | 10.96 | 2.4 |  | 52.608
[5 empty] | KG | 3501.4306
OTHER WOOD WORK FOR WALL PANELLING, DISPLAY, RAFTERS & PARTITION
40 | Providing and fixing 12mm thick HDHMR ply of approved make & manufacture in two layers, first layer on to existing wall.MS Frame, Wooden Frame with nails, screws, grittiest, cleats, clips as required and second layer with approved adhesive including all fixing arrangement complete in all respect .
Both side HDHMR PLY in two layers on each side
| Partition wall servery/executive lounge | 2 | 3.01 |  | 3.3 | 19.866
| Door | 2 | 0.1 |  | 3.3 | 0.66
|  | 2 | 3.46 |  | 3.3 | 22.836
| Servery/premium lounge wall | 1 | 1.1 |  | 3.3 | 3.63
| SD1( sliding door) | 1 | 1 |  | 3.3 | 3.3
| Other side of SD1 | 1 | 1.83 |  | 3.3 | 6.039
| Servery/premium lounge wall | 1 | 0.895 |  | 3.3 | 2.9535
| SD1( sliding door) | 1 | 1 |  | 3.3 | 3.3
| Other side of SD1 | 1 | 0.865 |  | 3.3 | 2.8545
| 1.83-0.865-0.1 | 1 | 0.865 |  | 3.3 | 2.8545
| Door jambs | 2 | 0.1 |  | 2.4 | 0.48
| Less Door SD1 | -2 | 1 |  | 2.4 | -4.8
| Business Drop down/ premium lounge wall | 2 | 1.735 |  | 3.3 | 11.451
|  | 1 | 0.1 |  | 3.3 | 0.33
| Merchandise display wall on either side of Merchandise Display | 2 | 3.645 |  | 3.3 | 24.057
|  | 2 | 1.085 |  | 3.3 | 7.161
|  | 2 | 2.2 |  | 3.3 | 14.52
| Admn Room walls passage side straight | 1 | 2.035 |  | 3.3 | 6.7155
|  | 1 | 1.88 |  | 3.3 | 6.204
| Door DS1 | 1 | 0.8 |  | 3.3 | 2.64
| Door jambs | 2 | 0.1 |  | 2.4 | 0.48
| Store Room Addl | 1 | 2.1 |  | 3.3 | 6.93
|  | 1 | 1.2 |  | 3.3 | 3.96
| Less door | -3 | 0.8 |  | 2.4 | -5.76
| Off set | 1 | 0.2 |  | 3.3 | 0.66
|  | 1 | 0.1 |  | 3.3 | 0.33
| Admn room/executive lounge wall staraight | 1 | 1.06 |  | 3.3 | 3.498
|  | 1 | 0.815 |  | 3.3 | 2.6895
| Offset | 1 | 0.2 |  | 3.3 | 0.66
|  | 1 | 0.347 |  | 3.3 | 1.1451
| Side of digital wall | 1 | 0.347 |  | 3.3 | 1.1451
| Dummy staraight Admn room | 1 | 1.03 |  | 3.3 | 3.399
| Dead off set | 1 | 0.275 |  | 3.3 | 0.9075
| Door jamb wall of DVP1 | 2 | 0.1 |  | 3.3 | 0.66
|  | 1 | 0.1 |  | 2.4 | 0.24
| Semi circular behind digital wall | 1 | 2.201 |  | 3.3 | 7.2633
| Semi circular wall( digital display ) | 1 | 4.069 |  | 3.3 | 13.4277
178.6872
41 | Providing and fixing 12mm thick flexible MR grade ply in two layers, of approved brand & manufacture on existing M.S. frame work, 1st layer with screws, nails, cleats , clips as required and second layer with approved adhesive including all fixing arrangement complete in all respect .
| Semi circular reception side | 1 | 0.913 |  | 3.3 | 3.0129
|  | 1 | 2.681 |  | 3.3 | 8.8473
| Servery/executive lounge semi circular wall | 1 | 3.874 |  | 1.35 | 5.2299
| Veg side semi circular wall | 1 | 1.331 |  | 3.3 | 4.3923
21.4824
42 | Providing & fixing first layer of 12mm thick waterproof MR grade flexible ply of approved brand & manufacture in panelling on wall/existing M.S. / termite treated wooden frame with screw then fixing/ pasting with approved adhesive second layer of 12mm thick flexible ply of approved make complete in all respect.( )
43 | Providing and fixing 1mm thick laminate panelling over existing partition as per approved sample including all fixing arrangement complete in all respect. Only finished area to be measured & paid.( Basic cost of Laminate@ Rs.970/-Sqm ).
Laminate panelling over exiting partition wall upto 3mtr height
| Premium Lounge wall store side | 1 | 2.85 |  | 1 | 2.85
| Partition wall servery/executive lounge | 1 | 6.57 |  | 1 | 6.57
| Other side | 1 | 3.46 |  | 3.1 | 10.726
| Servery/premium lounge wall | 1 | 1.1 |  | 3.1 | 3.41
| SD1( sliding door) | 1 | 1 |  | 3.1 | 3.1
| Other side of SD1 | 1 | 1.83 |  | 3.1 | 5.673
| Servery/premium lounge wall | 1 | 0.895 |  | 3.1 | 2.7745
| SD1( sliding door) | 1 | 1 |  | 3.1 | 3.1
| Other side of SD1 | 1 | 0.865 |  | 3.1 | 2.6815
| 1.83-0.865-0.1 | 1 | 0.865 |  | 3.1 | 2.6815
| Less Door SD1 | -2 | 1 |  | 2.4 | -4.8
| Business Drop down/ premium lounge wall | 2 | 1.735 |  | 3.1 | 10.757
|  | 1 | 0.1 |  | 3.1 | 0.31
| Merchandise display wall on either side of Merchandise Display | 3 | 0.6 |  | 3.1 | 5.58
| Admn room/executive lounge wall staraight | 1 | 1.06 |  | 3.5 | 3.71
| Offset | 1 | 0.2 |  | 3.5 | 0.7
|  | 1 | 0.347 |  | 3.5 | 1.2145
| Side of digital wall | 1 | 0.347 |  | 3.5 | 1.2145
| Semi circular wall( digital display ) | 1 | 4.069 |  | 3.5 | 14.2415
| Servery/executive lounge semi circular wall | 1 | 3.874 |  | 1 | 3.874
| Executive lounge wall | 1 | 3.745 |  | 1 | 3.745
| Band over PVD( no deduction for vertical members) | 1 | 10.96 |  | 0.5 | 5.48
| DVP1 wall | 1 | 1 |  | 3.1 | 3.1
| Less door | -1 | 0.9 |  | 2.4 | -2.16
90.533
Providing & fixing Fabric backed Vinyl Wall covering(10.05mtr. X .52mtr ) ( 300gsm Type-II) fire Retardant as per approved sample including all fixing arrangement complete in all respect.( Basic cost of Fabric backed Vinyl Wall covering @ Rs. 3230/- Sqm )
| Partition wall servery/executive lounge | 1 | 6.57 |  | 2.1 | 13.797
| Servery/executive lounge semi circular wall | 1 | 3.874 |  | 1.35 | 5.2299
| Executive lounge wall | 1 | 3.745 |  | 2.1 | 7.8645
| Premium Lounge wall store side | 1 | 2.85 |  | 2.1 | 5.985
| Semi circular reception side | 1 | 0.913 |  | 3.1 | 2.8303
|  | 1 | 2.681 |  | 3.1 | 8.3111
| Admn Room walls passage side straight | 1 | 2.035 |  | 3.1 | 6.3085
| Door DS1 | 1 | 0.8 |  | 3.1 | 2.48
| Less door | -2 | 0.8 |  | 2.4 | -3.84
| Off set | 1 | 0.2 |  | 3.1 | 0.62
| Merchandise display wall on either side of Merchandise Display | 1 | 3.645 |  | 3.1 | 11.2995
|  | 1 | 1.085 |  | 3.1 | 3.3635
|  | 1 | 7.04 |  | 3.3 | 23.232
87.4813
44 | Providing & fixing 12mm thick HDHMR ply panelling on wall with required termite treated wooden frame work with the help of gutties & screw , nails complete in all respect. The base frame shall be made from approved quality Kali wood , kiln seasoned, termite treated etc of size 50x25mm( minimum) @600mm c/c with additional members on the ends etc as per Directions of Project In Charge, premium lounge wall and executive lunge wall of block work.
| Executive lounge wall | 1 | 3.745 |  | 3.4 | 12.733
| Premium Lounge wall store side | 1 | 2.85 |  | 3.4 | 9.69
22.423
45 | Providing & fixing 1.2mm thick aluminium. Skirting PVDF coated 100mm height rose gold finish or as per approved sample over existing partition including all fixing arrangement complete in all respect. ( Basic cost Aluminium Skirting @ Rs. 450/-Rmtr)
Aluminium Skirting
| Partition wall servery/executive lounge | 2 | 3.01 |  |  | 6.02
|  | 2 | 3.46 |  |  | 6.92
| Servery/premium lounge wall | 1 | 1.1 |  |  | 1.1
| SD1( sliding door) | 2 | 0.1 |  |  | 0.2
| Other side of SD1 | 1 | 1.83 |  |  | 1.83
| Servery/premium lounge wall | 1 | 0.895 |  |  | 0.895
| Other side of SD1 | 1 | 0.865 |  |  | 0.865
| 1.83-0.865-0.1 | 1 | 0.865 |  |  | 0.865
| Door jambs | 2 | 0.1 |  |  | 0.2
| Business Drop down/ premium lounge wall | 2 | 1.735 |  |  | 3.47
|  | 1 | 0.1 |  |  | 0.1
| Merchandise display wall on either side of Merchandise Display | 2 | 3.645 |  |  | 7.29
|  | 2 | 1.085 |  |  | 2.17
|  | 2 | 2.2 |  |  | 4.4
| Admn Room walls passage side straight | 1 | 2.035 |  |  | 2.035
| Door jambs | 2 | 0.1 |  |  | 0.2
| Off set | 1 | 0.2 |  |  | 0.2
| Admn room/executive lounge wall staraight | 1 | 1.06 |  |  | 1.06
| Offset | 1 | 0.2 |  |  | 0.2
|  | 1 | 0.347 |  |  | 0.347
| Side of digital wall | 1 | 0.347 |  |  | 0.347
| Door jamb wall of DVP1 | 1 | 0.1 |  |  | 0.1
| Semi circular reception side | 1 | 0.913 |  |  | 0.913
|  | 1 | 2.681 |  |  | 2.681
| Semi circular wall( digital display ) | 1 | 4.069 |  |  | 4.069
| Servery/executive lounge semi circular wall | 2 | 3.874 |  |  | 7.748
| Veg side semi circular wall | 1 | 1.331 |  |  | 1.331
|  | 1 | 2.87 |  |  | 2.87
|  | 1 | 3.745 |  |  | 3.745
|  | 1 | 2.85 |  |  | 2.85
67.021
46 | Providing and fixing over head storage with necessary shelves as per design made out of 19mm thick HDHMR board fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with 1mm thick laminate including required shelves, shutters and required hardware like handle, knobs, magnetic catcher, hinges, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 270/-Sqm & external surface laminate@ Rs.970/-Sqm)
450mm
Storages
300 to 450mm deep
| Admin area over head storages | 1 | 4.28 |  | 0.75 | 3.21
| Kitchen over head | 1 | 3.211 |  | 0.75 | 2.4082
|  | 1 | 2.75 |  | 0.75 | 2.0625
|  | 1 | 4.41 |  | 0.75 | 3.3075
| Misc | 1 | 3.04 |  | 0.75 | 2.28
13.2683
47 | Providing and fixing under counter storage with necessary drawers & Shelves as per design made out of 19mm thick HDHMR board fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with 1mm thick laminate including required drawer unit, required shelves , shutters and required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, shutter lock, drawer channel etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 270/-Sqm & external surface laminate@ Rs.970/-Sqm)
Vending area 450mm to 600mm deep
|  | 1 | 3.05 |  | 0.9 | 2.745
| Kitchen under counter Storage | 1 | 2.878 |  | 0.9 | 2.5902
|  | 1 | 2.06 |  | 0.9 | 1.854
|  | 1 | 2.3 |  | 0.9 | 2.07
| Store (if Required) | 1 | 2.33 |  | 0.9 | 2.097
|  | 1 | 1.85 |  | 0.9 | 1.665
13.0212
48 | Providing and fixing partly open partly closed Servery counter storage as per drawing made out of 19mm thick HDHMR board fixed with the help of all necessary hardware like nail and fasteners and all internal area of storage ( Excluding open shelves inner surface ) to be finished with 0.8mm thick laminate and open shelves inner surface to be finished with rose gold finish 1mm thick SS sheet & external facade surface & top surface of survery storage to be finished with Italian stone fixed with adhesive & 100mm high rose gold finish Aluminium skirting at floor level, including required drawer unit, required open shelves, Louver shutters and required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, drawer channel, shutter lock etc. all are superior quality of approved make, complete in all respect. ( Rose Gold finish SS sheet paid separately in rose gold finish SS sheet item & Italian Stone paid separately in Italian stone Item). ( Basic cost of internal laminate @ Rs.270/-Sqm & external surface laminate@ Rs.970/-Sqm.)
650mm
Servery counter
|  | 1 | 4.75 |  | 0.85 | 4.0375
|  | 1 | 4.85 |  | 0.85 | 4.1225
8.16
49 | Providing and fixing Reception Table ( 450mm to 600mm Deep ) (2.1mtr. long x 1.2mtr ht. ) made out of 19mm thick HDHMR ply for required partition, front & sides including necessary shelves with shutter & drawers, Key board tray, all necessary hardware of superior quality like nail, self closing type hinges, S.S. handles, knobs, locks, key board tray , etc. And front facade, sides & top finish with Italian marble stone of approved make, shade & texture including all fixing arrangement ,grinding polishing, edge chamfering & polishing & all internal surface to be finished with 0.8mm thick laminate & external exposed drawer / wooden surface to be finished with 1mm thick laminate of approved make & shade & reception table facade surface at floor level 100mm high skirting & top & sides edging finished with PVD coated rose gold finish in aluminium . complete in all respect. ( Basic cost of internal laminate @ Rs.270/- Sqm & external laminate @ Rs970/-Sqm & Italian marble stone @ Rs. 4845/- Sqmt ) & PVD coated rose gold finish 1mm thick SS sheet @ Rs.4420Sqm) | 1 |  |  |  | 1
1
50 | Providing making & fixing in position 19mm thick India Map ( 1.58mtr x 1.87mtr) made of 18mm thick MDF Board of approved make finished with 1mm thick PVD coated Rose Gold finish SS sheet with provision for LED light glowing arrangement at location of Lucknow including all fixing arrangement complete in all respect.( Basic cost of PVD coated SS sheet @ Rs.4420/- Sqm ) | 1 |  |  |  | 1
1
51 | Providing Making & fixing/pasting with approved adhesive in position 1mm thick SS Sheet of grade 304 PVD coated with approved colour, shade, texture & finish over 12mm thick flexi fire retardant ply of approved brand & manufacture in circular portion of the display at top and on 12mmm thick MDF Board on horizontal/vertical surfaces. the fins of teh display shall be made 50mm thick, with projection of 300mm in straight portion UPTO height of about 2.40meters and thereafter it shall further add 200mm projection to 300mm projection making overall projected length at top most pont( at Ceiling) of 500mm. The top shall have another recessed semicircular ( 50mm inside from 500 mm overall projection at top) of R230mm etc as per drawings. The top surface and all inside surfaces and out side surfaces of fins forming display shall be wrapped with 1mm thick PVD coated SS304 grade sheet with coating of approved colour, shade and texture. The PVD sheet shall be wrapped with approved adhesive etc.. In addition to it a box shall be created at height from 450mm to 1100 mm i.e. 650mm front with wooden Hollock wood battens of appropriate size over it HDHMR board of 19mmm thickness shall be fixed and on this board 19mm thick Italian stone shall be fixed. The HDHMR Board shall be semi circular at teh bottom so shall be Italian stone as per drawing. The top shall also have Italian stoneof size 300x500x19mm with bird beak corner grove joint with teh vertical stone surface, polished complete over HDHMR Board of 19mm thick of approved shade, colour, design, pattern & profile as per drawing complete. The front area in between teh fins shall have 1mm thick laminate on the existing HDHMR partition. there shall be a 10mm thick glass of 500mm height placed above Italian stone with suitable opening & locking arrangement, the glass box shall have top also of 10mmm thick toughened glass fixed to back with tubular section of SS304 grade as frame on corner for fixing glass to glass and glass to side fins and glass to back wall of size 25x10mm, with locking arrangement complete.
Rate is inclusive of frame of MS tubular section minimum thickness of 1.6mm. HDHMR Boards19mm thick for base to Italian stone, Italian stone 19mm thick of required shade, colour, design & pattern, 12mmm MDF sheet & 12mmm thick flexi ply for base to PVD coated SS304 grade sheet, PVD coated 304 SS sheet 1mm thick, frame of MS tubular section of minimum thickness of 1.6mm, laminate 1mm thick of approved design, manufacture & brand, shade colour, design, 100mm thick toughenned glass, PVD coated ss304 grade 1mm thick tubelar section of 25x10mm (minimum) for fixing at corners of glass box, appropriate PVD coated hinges/brackets for making the front glass portion openable or the top glare p[ortion opennable, locking arrangement to glass openable piece, adhesives of approved quality, nails, screws, grittiest of approved brand & manufacture and type matching with teh finish on to which these are used. Etc complete with temporary arrangement for fixing, and fixing to teh back wall secureley. The rate is for one set of overall height 3000mmx 600mm.
| The rate is also inclusive of fixing 19mmx19mm edge Italian stone at the bottom semi circular portion with adhesive and in pieces in true semi circular profile of teh front Italian stone ( making visible thickness of stone at bottom as 19+19mm=38mm, polishes complete | 3 |  |  |  | 3
3
52 | Providing , making & fixing projected surface with frame of wooden/MS as described in above item having front face 12mm thick MDF Baird of approved brand & manufacture fixed with nails, screws, adhesive and then finally fixing Vinyle paper of approved brand, manufacture, colour, shade, pattern & design in between the display sets , the width shall be variable startling with 200mm at base and increasing as per teh profile ( semi circular of display panels) complete with basic cost of Vinyle as 3230/sqm
|  | 2 | 3 | 0.2 |  | 1.2
| Additional |  |  |  |  | 0.3
1.5
53 | Providing and fixing split level gypsum board false ceiling including providing and fixing GI grade 175 (120 gm/m2) perimeter, channels (20 x 30 x 27 x 0.50mm thick) fixed to brick masonry / partition / hanging with existing ceiling / existing M.S. frame work and suspended GI intermediate channel. Rate to include making necessary cut out/opening for light fitting A C diffuser etc. The cut out to have perimeter channel of size 20x27x30x.5mm all round and supported suitably and finally finished with gypsum board and finally finished with two or more coat of plastic emulsion paint of approved make & shade with required tapping the joints, base primer, putty complete in all respect. (Actual plan area to be measured & paid.). Rate quoted should be included for all design work, providing false ceiling in circular profile in horizontal as well as vertical edges to teh horizontal circular profiles including straight profiles as per drawing, levels Nothing to be paid extra for design work. PREMIUM LOUNGE AREA |  |  |  |  | 34
34
54 | Providing and fixing gypsum board false ceiling with coves on sides along the walls to receive light fixtures, AC diffusers etc including providing and fixing GI grade 175 (120 gm/m2) perimeter, channels (20 x 30 x 27 x 0.50mm thick) fixed to brick masonry / partition / hanging with existing ceiling / existing M.S. frame work and suspended GI intermediate channel. Rate to include making necessary cut out/opening for light fitting A C diffuser etc. The cut out to have perimeter channel of size 20x27x30x.5mm all round and supported suitably and finally finished with gypsum board and finally finished with two or more coat of plastic emulsion paint of approved make & shade with required tapping the joints, base primer, putty complete in all respect. (Actual plan area to be measured & paid.). Rate quoted should be included for all design work, providing false ceiling in circular profile in horizontal as well as vertical edges to teh horizontal circular profiles including straight profiles as per drawing, levels Nothing to be paid extra for design work. EXECUTIVE LOUNGE, RECEPTION, ADMN ROOM etc | Sqm |  |  | 140 | 140
140
55 | Providing and fixing Gl Clip in Metal Ceiling System of 600x600 mm module which includes providing and fixing 'C' wall angle of size 20x30x20 mm made of 0.5 mm thick pre painted steel along the perimeter of the room with help of nylon sleeves and wooden screws at 300 mm center to centre, suspending the main C carrier of size 10x38x10 mm made of G.I steel 0.7 mm thick from the soffit with the help of soffit cleat 37x27x25x1.6 mm, rawl plugs of size 38x12 mm and C carrier suspension clip and main carrier bracket at 1000 mm c/c. Inverted triangle shaped Spring Tee having height of 24 mm and width of 34 mm made of Gl steel 0.45 mm thick is then fixed to the main C carrier and in direction perpendicular to it at 600 mm centers with help of suspension brackets. Wherever the main C carrier and spring T have to join, C carrier and spring T connectors have to be used. All sections to be galvanized @ 120 gms/sqm (both side inclusive), fixing with clip in tiles into spring T with :
GI Metal Ceiling Clip in plain Bevelled edge global white colour plain tiles of size 600x600 and 0.5 mm thick with 25 mm height, made of G I sheet having galvanizing of 100 gms/ sqm (both sides inclusive) and electro statically polyester powder coated of thickness 60 microns (minimum), including factory painted after bending. ( Kitchen & Kitchen Store false ceiling )
Grid Ceiling
| Kitchen & store As per polyline | 1 | 21.5 |  |  | 21.5
21.5
56 | Providing & applying P.O.P. punning on walls with an average thickness of 2mm including finishing the surface smooth in line & level complete in all respect. | Ratebonly
57 | Providing three or more coats of Plastic Emulsion paint of approved make & shade including preparation of base by cement based putty & primer complete in all respect. ( Admin area inside wall paint )
Plastic emulsion Paint
| Admn Room walls passage side straight | 1 | 1.88 |  | 3.1 | 5.828
| Door DS1 | 1 | 0.8 |  | 3.1 | 2.48
| Less door | -2 | 0.8 |  | 2.3 | -3.68
| Off set | 1 | 0.1 |  | 3.1 | 0.31
| Admn room/executive lounge wall staraight | 1 | 0.815 |  | 3.1 | 2.5265
| Dummy staraight Admn room | 1 | 1.03 |  | 3.1 | 3.193
| Dead off set | 1 | 0.275 |  | 3.1 | 0.8525
| Semi circular behind digital wall | 1 | 2.201 |  | 3.1 | 6.8231
| Semi circular reception side | 1 | 2.681 |  | 3.1 | 8.3111
| Merchandise wall out side | 1 | 7.04 |  | 3.4 | 23.936
50.5802
58 | Providing & fixing Fabric backed Vinyl Wall covering(10.05mtr. X .52mtr ) ( 300gsm Type-II) fire Retardant as per approved sample including all fixing arrangement complete in all respect.( Basic cost of Fabric backed Vinyl Wall covering @ Rs. 3230/- Sqm )
Providing & fixing Fabric backed Vinyl Wall covering(10.05mtr. X .52mtr ) ( 300gsm Type-II) fire Retardant as per approved sample including all fixing arrangement complete in all respect.( Basic cost of Fabric backed Vinyl Wall covering @ Rs. 3230/- Sqm )
| Partition wall servery/executive lounge | 1 | 6.57 |  | 2.1 | 13.797
| Servery/executive lounge semi circular wall | 1 | 3.874 |  | 2.1 | 8.1354
| Executive lounge wall | 1 | 3.745 |  | 2.1 | 7.8645
| Premium Lounge wall store side | 1 | 2.85 |  | 2.1 | 5.985
| Semi circular reception side | 1 | 0.913 |  | 3.1 | 2.8303
|  | 1 | 2.681 |  | 3.1 | 8.3111
| Admn Room walls passage side straight | 1 | 2.035 |  | 3.1 | 6.3085
| Door DS1 | 1 | 0.8 |  | 3.1 | 2.48
| Less door | -2 | 0.8 |  | 2.4 | -3.84
| Off set | 1 | 0.2 |  | 3.1 | 0.62
| Merchandise display wall on either side of Merchandise Display | 1 | 3.645 |  | 3.1 | 11.2995
|  | 1 | 1.085 |  | 3.1 | 3.3635
|  | 1 | 7.04 |  | 3.3 | 23.232
90.3868
59 | Providing & filling 50mm thick Fibre Glass wool ( 64kg density ) in M. S. frame work for partition wall for making sound proof
ROCK WOOL
Both side HDHMR PLY
| Partition wall servery/executive lounge | 1 | 3.01 |  | 3.3 | 9.933
|  | 1 | 3.46 |  | 3.3 | 11.418
| Servery/premium lounge wall | 1 | 1.1 |  | 3.3 | 3.63
| SD1( sliding door) | 1 | 1 |  | 3.3 | 3.3
| Other side of SD1 | 1 | 1.83 |  | 3.3 | 6.039
| Less Door SD1 | 1 | 1 |  | 2.4 | 2.4
| Business Drop down/ premium lounge wall | 1 | 1.735 |  | 3.3 | 5.7255
| Merchandise display wall on either side of Merchandise Display | 1 | 3.645 |  | 3.3 | 12.0285
|  | 1 | 1.085 |  | 3.3 | 3.5805
|  | 1 | 2.2 |  | 3.3 | 7.26
| Admn Room walls passage side straight | 1 | 2.035 |  | 3.3 | 6.7155
| Door DS1 | 1 | 0.8 |  | 3.3 | 2.64
| Less door | 1 | 0.8 |  | 2.4 | 1.92
| Off set | 1 | 0.2 |  | 3.3 | 0.66
| Admn room/executive lounge wall staraight | 1 | 1.06 |  | 3.3 | 3.498
| Offset | 1 | 0.2 |  | 3.3 | 0.66
|  | 1 | 0.347 |  | 3.3 | 1.1451
| Side of digital wall | 1 | 0.347 |  | 3.3 | 1.1451
| Dummy staraight Admn room | 1 | 1.03 |  | 3.3 | 3.399
| Dead off set | 1 | 0.275 |  | 3.3 | 0.9075
| Semi circular reception side | 1 | 0.913 |  | 3.3 | 3.0129
|  | 1 | 2.681 |  | 3.3 | 8.8473
| Semi circular wall( digital display ) | 1 | 4.069 |  | 3.3 | 13.4277
| Servery/executive lounge semi circular wall | 1 | 3.874 |  | 3.3 | 12.7842
| Veg side semi circular wall | 1 | 1.331 |  | 3.3 | 4.3923
130.4691
60 | Providing & fixing aluminium. T profile ( 19mm x 19mm x 6mm thick ) PVDF coated ( Rose gold finish ) as per approved sample including all fixing arrangement complete in all respect. ( Basic cost of T Profile @ Rs. 250/- Rmtr. )
Aliminium T profile
| Executive Lounge wall on the side of servery & Kitchen foyer-Horizontal | 1 | 6.415 |  |  | 6.415
| Executive Lounge wall on the side of servery & Kitchen foyer- vertical | 1 | 4.97 |  |  | 4.97
| Executive Lounge wall ( block work) | 1 | 7.01 |  |  | 7.01
| Executive Lounge wall ( block work)- vertical | 1 | 2.67 |  |  | 2.67
| Misc | LS | 9 |  |  | 9
30.065
61 | Providing & fixing Rose Gold finish L- angle aluminium profile ( 12mm x 12mm x 1.5mm thick ) as per approved sample fixed with adhesive of approved make including all fixing arrangement complete in all respect. ( Basic cost of Angle @ Rs. 330 Rmtr. )
L Angle profile 12 mm x 12mm
| Corners of reception wall | 3 | 3.2 |  |  | 9.6
| Column on left of enterance near merchandise display | 2 | 3 |  |  | 6
| MISC | 3 | 3 |  |  | 9
24.6
62 | P/F 1mm thick PVD coated SS sheet fixing on existing wall panelling as per approved sample including all fixing arrangement complete in all respect.( Basic cost of PVD coated SS sheet @ Rs.4420/- Sqm )
P/F SS Sheet Fixing
| Jambs of SLD1 | 2 | 0.1 |  | 2.4 | 0.48
| Free edges of 100mm thick partition walls | 3 | 0.125 |  | 3 | 1.125
| Sheet fixing in Servery counter back inside finish | 4 | 2 |  | 0.3 | 2.4
| Servery counter both sides | 8 | 0.6 |  | 0.3 | 1.44
| Servery Counter top & Bottom | 8 | 1.5 |  | 0.6 | 7.2
0
| Total |  |  |  |  | 12.645
63 | Providing & doing water proofing of sunken areas of Toilets, balconies etc, of following operations: i) Cleaning the sunken area surface using wire brush and then broom making teh surface dust free. Ii) Repairing the holes, depressions or taking out loose materials of brick work/cement plater/concrete and grouting the same with cement concrete (1:11/2:3) or cement plater (1:3) as teh case may be and only if required. Iii) Applying two coats of base primer of URP301 of Dr Fixit or equivalent as per manufacturers specifications. Iv) (laying of pipes, PCC on pipes ) and applying URP301 two coats on teh PCC surfaces and the other ares which got damaged due to laying of pipes and subsequenty made good( grouted). V) Laying of water proof coat of 2K of Dr Fixit or equivalent as per manufacturer's specifications. Vi) Allowing it dry then checking teh sunken areas by water ponding for two days and if leakage is observed then redoing the 2K coats all over again. VII) Laying water proof plaster in slope 1:100 towards spout fixed for drainage in cement mortar 1:3 mixed with water proofing compound with cement @2% by weight of cement , finished neat or as may be specified by teh manufacturer, curing for minimum seven days.
Waterproofing Work
| Kitchen area | 1 | 4.93 |  | 2.71 | 13.3603
| On walls | 2 | 4.93 |  | 0.6 | 5.916
|  | 1 | 2.42 |  | 0.1 | 0.242
|  | 1 | 1.45 |  | 0.1 | 0.145
19.6633
64 | Providing & filling Khanger in the sunken areas as per Directions of Project-in-Charge | CUM | 1 |  |  | 1
1
65 | Providing and doing 12mm thick solid surface ( corian) of approved, shade, texture, make & manufacture over base of existing 12mm water proof ply with all adhesives, including all processes & making the curves smooth and joints seamless as per profile, drawings and instructions of Engineer incharge complete
| SERVERY COUNTER | 1 | 3.6 | 0.8 |  | 2.88 | The
|  | 1 | 4.2 | 0.8 |  | 3.36
| Servery counter facias | 1 | 3.87 |  | 0.9 | 3.483
|  | 1 | 2.87 |  | 0.9 | 2.583
|  | 1 | 1.33 |  | 0.9 | 1.197
| Less opening in servery area for open shelves | -2 | 2.85 |  | 0.6 | -3.42
| Above counter of servery 150mm high | 1 | 3.6 |  | 0.15 | 0.54
|  | 1 | 4.2 |  | 0.15 | 0.63
| Kitchen wall live counter opening | 4 | 1.275 | 0.3 |  | 1.53
|  | 4 | 1.275 | 0.17 |  | 0.867
13.65

## C&I M.B Sheet
Jaipur Airport Site Lounge
(M.B SHEET)
S.No. | Description | Nos | L | W | H | Qty
I | DISMANTLING WORK
I | Dismantling of existing aluminium Door, window frames including glazing, repairing the cavity in teh wall with epoxy mortar and finished smooth as per adjacent finish, colour, texture including removing teh glazings and stacking the serviceable material at teh designated place and disposal of the unserviceable materials at teh designated place for further disposal to teh dumping yard.
| Same as BOQ | 1 |  |  |  | 0
| Sub Total |  |  |  |  | 0
II | CIVIL WORK
8 | Providing and laying 100mm thick ACC block wall with grade -1 AAC Blocks of density 551.to 650kg / cum conforming to IS : 2185 ( Part -3) in superstructure above plinth level with R.C.C. bend at cill & Lintel level with approved block laying polymer modified adhesive mortar all complete as per direction of Engineer-in-Charge. (The payment of RCC band and reinforcement shall be made for separately). size of block (2'-0" x 0'-8" and width 0'-4" ). the rate is inclusive of scaffolding, tools & tackles, all leads & heights etc. complete.
RAB-02
8.01 | Kitchen ramp right side wall | 1 | 1.9 | 3.35 |  | 6.365
8.02 | Kitchen ramp left side wall | 1 | 1.1 | 3.35 |  | 3.685
8.03 | Kichen mozzaic highlighter wall | 1 | 4.5 | 4.15 |  | 18.675
8.04 | Along premium lounge wall with kitchen door wall L-shape wall | 1 | 5.31 | 4.15 |  | 22.0365
8.05 | Primium lounge LCD wall | 1 | 2.5 | 4.15 |  | 10.375
8.07 | Store entrance door wall | 1 | 2.5 | 2.8 |  | 7
8.08 | Store inside DB wall | 1 | 1.88 | 2.8 |  | 5.264
8.09 | Inside of store lounge area side wall | 1 | 2.2 | 4.15 |  | 9.13
FINAL RAB -03
Less (-)
| Kitchen door | -1 | 0.92 | 2.4 |  | -2.208
| Store door | -1 | 1.2 | 2.4 |  | -2.88
| Sub Total |  |  |  |  | 77.4425
| TENDER QTY |  |  |  |  | 55.67
| AMENDED QTY |  |  |  |  | 21.77
| TOTAL |  |  |  |  | 77.44
9 | R.C.C- ( 1 : 1.5 : 3 ) ( 1 cement : 1.5 coarse send : 3 graded stone aggregate 20mm nominal size ) for lintels, Lintel in arch etc. or where ever required I/c reinforcement for lintel 4no 12mm dia bars with 8mm dia rings @ 150c/c & centering shuttering for all levels and height.( Door Lintel length as per drawing 100mm wide x 100mm height ) The rate includes RCC, steel, shuttering & de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge.
9.01 | Kitchen entrance door Lintel | 1 | 1.1 |  |  | 1.1
9.02 | Store door lintel | 1 | 1.4 |  |  | 1.4
| Sub Total |  |  |  |  | 2.5
| TENDER QTY CHECKED |  |  |  |  | 1.4
| AMENDED QTY CHECKED |  |  |  |  | 1.1
| TOTAL |  |  |  |  | 2.5
10 | R.C.C- ( 1 : 1.5 : 3 ) ( 1 cement : 1.5 coarse send : 3 graded stone aggregate 20mm nominal size ) for Band where ever required I/c reinforcement 2Nos 8mm dia bar with 8mm dia links @ 150mm c/c including centering shuttering for all levels and height,( bend cross section size 100mm wide x 75mm thick ) etc. complete. The rate includes RCC ( Cement Concrete + Reinforcemnet steel), Shuttering, de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge.
10.01 | Kitchen ramp right side wall | 2 | 1.9 | 1 |  | 3.8
10.02 | Kitchen ramp left side wall | 2 | 1.1 | 1 |  | 2.2
10.03 | Kichen mozzaic highlighter wall | 2 | 4.5 | 1 |  | 9
10.04 | Kitchen Oven partition wall | 2 | 5.31 | 1 |  | 10.62
10.05 | Along premium lounge wall with kitchen door wall | 2 | 2.5 | 1 |  | 5
10.06 | Primium lounge right side wall | 2 | 2.5 | 1 |  | 5
10.07 | Store entrance door wall | 2 | 1.88 | 1 |  | 3.76
10.08 | Inside of store lounge area side wall | 2 | 2.2 | 1 |  | 4.4
| Less (-) |  |  |  |  | 0
| Kitchen door | -1 | 0.9 | 1 |  | -0.9
| Store door | -1 | 1.2 | 1 |  | -1.2
| Sub Total |  |  |  |  | 41.68
| TENDER QTY CHECKED |  |  |  |  | 41.68
AMENDED QTY CHECKED
| TOTAL |  |  |  |  | 41.68
12 | Providing & laying 50mm thick ( average thickness ) screeding with 1:2:4 cement conc. (1 cement :2 coarse sand :4 graded stone agg 10mm nominal size ) in line and level including required shuttering, curing etc. complete in all respect
12.01 | Section -1 Bathroom side premium lounge | 1 | 12.4 | 3.44 | 0.05 | 2.1328
12.02 | Section - 4 Executive lounge area | 1 | 11.91 | 5.52 | 0.05 | 3.2872
12.03 | Section -5 Air side premium lounge area | 1 | 11.91 | 3.19 | 0.05 | 1.8996
| Sub Total |  |  |  |  | 5.42
13 | Extra for above Item No-7 for floating quote of neat cement punning over screeding including curing etc.
13.01 | Section -1 Bathroom side premium lounge ( Area considered from P-Line ) | 1 | 31.91 | 1 |  | 31.91
13.02 | Section - 4 Executive lounge area ( Area considered from P-Line ) | 1 | 15 | 1 |  | 15
13.03 | Section -5 Air side premium lounge area( Area considered from P-Line ) | 1 | 22 | 1 |  | 22
| Sub Total |  |  |  |  | 68.91
14 | Providing and applying 15 mm thick cement plaster of mix in 1:4 (1 cement : 4 coarse sand) at all levels & heights including scaffolding, curing etc. complete as specified.
14.01 | Kitchen ramp right side wall | 2 | 1.9 | 3.35 |  | 12.73
14.02 | Kitchen ramp left side wall | 2 | 1.16 | 3.35 |  | 7.772
14.03 | Kichen mozzaic highlighter wall | 2 | 4.5 | 4.15 |  | 37.35
14.04 | Kitchen Oven partition wall | 1 | 9.695 | 2 |  | 19.39
14.05 | Along premium lounge wall with kitchen door wall | 2 | 5.31 | 4.15 |  | 44.073
14.06 | Primium lounge LCD wall | 2 | 2.5 | 4.15 |  | 20.75
14.07 | Store entrance door wall | 2 | 2.5 | 2.8 |  | 14
14.08 | Store inside electrical panel wall | 1 | 2.8 | 2 |  | 5.6
14.09 | Store inside DB wall | 1 | 1.88 | 2.65 |  | 4.982
14.08 | Inside of store lounge area side wall | 2 | 2.2 | 4.15 |  | 18.26
Less (-)
| Kitchen door | -1 | 0.92 | 2.4 |  | -2.208
| Store door | -1 | 1.2 | 2.4 |  | -2.88
| Sub Total |  |  |  |  | 179.819
| TENDER QTY CHECKED |  |  |  |  | 122.11
| AMENDED QTY CHECKED |  |  |  |  | 57.709
| TOTAL |  |  |  |  | 179.819
15 | Providing and laying Vitrified tiles in floor in different sizes (thickness to be specified by the manufacturer) with water absorption less than 0.08% and conforming to IS:15622, of approved brand & manufacturer, in all colours and shade, laid on 20 mm thick cement mortar 1:4 (1 cement: 4 coarse sand) jointing with grey cement slurry @3.3 kg/sqm including grouting the joints with white cement and matching pigments etc. The tiles must be cut with the zero chipping diamond cutter only . Laying of tiles will be done with the notch trowel, plier, wedge, clips of required thickness, leveling system and rubber mallet for placing the tiles gently etc complete.
15.01 | Kitchen all area including store | 1 | 9.5 | 2.48 |  | 23.56
15.02 | Admin cabin as per P-Line | 1 | 5.32 | 1 |  | 5.32
Less (-)
| Front equipment wall Oven side pillar | -1 | 0.95 | 0.15 |  | -0.1425
| Front equipment wall Oven side pillar | -1 | 0.3 | 0.8 |  | -0.24
| Store room right side wall | -1 | 0.9 | 0.15 |  | -0.135
| Store room left side wall | -1 | 0.73 | 0.15 |  | -0.1095
| Stone room LT panel wall corner | -1 | 0.59 | 0.72 |  | -0.4248
| Sub Total |  |  |  |  | 27.8282
18 | Providing and laying rectified Glazed Ceramic floor tiles of size 300x300 mm or more (thickness to be specified by the manufacturer), of 1st quality conforming to IS : 15622, of approved make, in colours White, Ivory, Grey, Fume Red Brown, laid on 20 mm thick cement mortar 1:4 (1 Cement: 4 Coarse sand), jointing with grey cement slurry @ 3.3 kg/ sqm including grouting the joints with white cement and matching pigment etc complete.( Basic cost of tile@ Rs.340/- per Sqm ( Under Servery counter area floor Tiles )
18.01 | Buffet counter front side | 1 | 2.8 | 0.6 |  | 1.68
18.02 | Buffet counter Bcak side | 1 | 3.8 | 0.6 |  | 2.28
| Sub Total |  |  |  |  | 3.96
19 | Providing and fixing 1st quality ceramic glazed wall tiles , 600 x 600mm Glazed/Matt/Anti skid finish etc (thickness to be specified by the manufacturer), of approved make, in all colours, shades as approved by Engineer-in-Charge, for dados, over 12 mm thick bed of cement mortar 1:3 (1 cement : 3 coarse sand) and jointing with grey cement slurry @ 3.3kg per sqm, including pointing in white cement mixed with pigment of matching shade complete. ( Basic cost of tiles @ Rs.480/- Sqm )
19.01 | Kitchen entrance door L- shape wall along primium lounge | 1 | 4.7 | 2.4 |  | 11.28
19.02 | Kitchen entrance door front wall | 1 | 5.07 | 2.4 |  | 12.168
19.03 | Oven partition wall | 1 | 2.06 | 2.4 |  | 4.944
19.04 | Oven partition wall to store room door wall | 1 | 2.68 | 2.4 |  | 6.432
19.05 | Store entrance door wall both side | 2 | 2.45 | 2.4 |  | 11.76
19.06 | Store inside electrical panel wall | 1 | 2.84 | 2.4 |  | 6.816
19.07 | Store inside DB wall | 1 | 1.88 | 2.4 |  | 4.512
19.08 | Store inside lounge side wall | 2 | 2.46 | 2.4 |  | 11.808
19.09 | Kitchen inside highighter wall | 1 | 4.51 | 2.4 |  | 10.824
19.1 | Kitchen entrance left wall | 1 | 1.284 | 2.4
19.11 | Kitchen entrance right wall | 1 | 1.284 | 2.4
| Less (-) |  |  |  |  | 0
| Kitchen door | -1 | 1.2 | 2.4 |  | -2.88
| Store door both side | -2 | 0.9 | 2.4 |  | -4.32
| Sub Total |  |  |  |  | 73.344
21 | Providing & fixing hand made mosaic tiles as per mood board design & drawings with approved quality adhesive on the servery area walls complete as per directions of Project In Charge
21.01 | Buffet counter front side above counter highlighter | 1 | 2.9 | 0.36 |  | 1.044
21.02 | Buffet counter front side floor to highlighter height | 1 | 1.365 | 0.86 |  | 1.1739
21.03 | Buffet counter Back side | 1 | 3.86 | 1.83 |  | 7.0638
21.04 | 10% material for edge cutting
| Sub Total |  |  |  |  | 9.2817
| TENDER QTY CHECKED |  |  |  |  | 7.6
| AMENDED QTY CHECKED |  |  |  |  | 1.6817
| TOTAL |  |  |  |  | 9.2817
25 | Providing and fixing 16 to 18mm thick Italian Stone for wall fixed with adhesive of approved make over existing partition and jointed with adhesive mixed with pigment to match the shade of stone including necessary grooves & polishing, edge chamfering, buffing, polishing, complete in all respect. ( Basic cost of Italian stone @ Rs. 4845/- Sqm )( Actual size of stone to be measured & paid ). Servery counter area wall & counter facade finishing stone ).
24.01 | Merchantise unit front | 3 | 0.5 | 0.48 |  | 0.72
24.02 | Merchantise unit top | 3 | 0.48 | 0.28 |  | 0.4032
| Sub Total |  |  |  |  | 1.1232
C | Stone Work
24 | Providing and fixing 16 to 18mm thick Italian Stone for Counter laid over 20 mm. thick cement mortar 1:4 (1 cement :4 coarse sand) and jointed with cement slurry complete as per pattern and design .including full round moulding, rubbing, polishing & curing as required complete in all respect. ( Basic cost of Italian stone @ Rs. 4845/- Sqm )( Actual size of stone to be measured & paid ).
25.01 | Reception area ( section 2 ) P line considered | 1 | 9.95 | 1 |  | 9.95
25.02 | Kichen ramp | 1 | 1.42 | 1.098 |  | 1.5592
25.03 | Reception counter
a | Counter top | 1 | 0.45 | 1.6 |  | 0.72
b | Front | 1 | 2.94 | 1 |  | 2.94
e | Inside ledge cladding on top including handrest top | 1 | 0.4 | 2.46 |  | 0.984
| Sub Total |  |  |  |  | 16.1532
26 | Providing & fixing 15mm thick Engineered wooden flooring of approved make & shade in chevron pattern with 2mm thick base foam including all fixing arrangement & required profile & skirting complete in all respect. (Basic cost of Engineered Wooden flooring@ Rs. 4035/- Sqm) (Actual carpet area at site to be measured & paid ). ( Business Dropdown, Bar Lounge Area, Reception, Servery area, Business centre area & Toilet Vestibule ).
26.01 | Wooden flooring as per drawing( Area considered from P-Line) WF-01 ,WF-02 | 1 | 92.46 | 1 |  | 92.46
| Sub Total |  |  |  |  | 92.46
| TENDER QTY CHECKED |  |  |  |  | 90.93
| AMENDED QTY CHECKED |  |  |  |  | 1.53
| TOTAL |  |  |  |  | 92.46
E | CARPET FLOORING
27 | Providing, laying & fixing carpet flooring of approved brand & manufacture: HAND TUFTED 4.50 LBS. 12- 14MM THK. CUSTOMIZED NYLON HANDTUFTED BROADLOOM CARPET 100% NYLON (NF)
27.01 | Lounge carpet area ( CR -01 ) | 1 | 3.15 | 12.048 |  | 37.9512
Less (-)
| Admin area | -1 | 0.84 | 0.58 |  | -0.4872
| Reception area | -1 | 1.9 | 0.2 |  | -0.38
| Sub Total |  |  |  |  | 37.084
| TENDER QTY CHECKED |  |  |  |  | 35
| AMENDED QTY CHECKED |  |  |  |  | 2.084
| TOTAL |  |  |  |  | 37.084
28 | Providing & fixing floor anodised aluminium ( Rose Gold Finish ) transition profile as per approved sample including all fixing arrangement between junction of two type flooring i.e. wooden & carpet & tile / stone junction complete in all respect.( Basic cost for aluminium Transition profile @ Rs. 230/- Rmtr)
| Kitchen entrance door both side | 2 | 5.79 |  |  | 11.58
| Store room both side | 2 | 6.097 |  |  | 12.194
Sub Total
29 | Providing and fixing door and window frames made out of White ASH Wood with necessary groove ( 6mm x 6 mm ) & single rebate including necessary M.S. hold-fasts/ fastners , minimum four on each side of teh frame, in cement concrete blocks 1: 2: 4 / fasteners ( expendable 10mm dia ) on either side fixed in line and level, finishing with matching finish of teh wall etc. The frame to be treated with necessary anti-termite chemical and fire retardant paint on partition side & finally finished with PU polish complete in all respect.
29.01 | Kitchen main entrance door | 1 | 20 | 1 |  | 20
29.02 | Store room door | 1 | 19 | 1 |  | 19
| Sub Total (RFT) |  |  |  |  | 39
| Sub Total (CUM) |  |  |  |  | 0.0095
30 | Providing and fixing 38 mm. thick flush door shutters with vision slit ( 250mm x 900mm apro. as per drawing ) core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both sides of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size SS 304v grade PVD Coated with approved shade, colour & texture butt hinges per leaf with necessary screws and S.S.304 grade PVD Coated handles of long length minimum 60 CMs of height, of approved shape, profile, grip similar finish in tower bolts minimum 300mm long, similar finishes as that of handles door stopper, rubber buffer, vision slit as per design with 6mm thick glass with wooden beading on back side fixed into a special rebate created in block board core of doors ( white ash wood ), handles,motrise dead lock with one side key knob cylinder finished as per handles in, with horizontal & vertical PVD Coated SS 304 grade I or T channel of width 12 mmx6mmx6mm for verticals & 6mmx6mm for horizontal and thickness not less than 6mm for T section etc. complete in all respect. .( Basic cost of laminate @ Rs. 970/-Sqm ) ( Actual size of shutter to be measured & paid ). ( Kitchen Back & Lounge side entry door )
30.01 | Kitchen main entrance door | 1 | 1.07 | 2.32 |  | 2.4824
| Sub Total |  |  |  |  | 2.4824
31 | Providing and fixing 38 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both faces of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, etc. complete in all respect.( Basic cost of laminate @ Rs. 970/-Sqm) ( Actual size of shutter to be measured & paid ).
31.01 | Store room door | 1 | 0.8 | 2.33 |  | 1.864
31.02 | Admin cabin door | 1 | 0.86 | 2.38 |  | 2.0468
| Sub Total |  |  |  |  | 3.9108
34B | Providing & Fixing in position (in front of the Fixed Glass Glazing) SS 304 grade PVD Coated having outer frame of SS Box Section/ Flat & intermediate SS Square Bar etc. as/drawing fixed to top & bottom with the help of SS PVD Coated Screws matching with the Grill PVD shade etc. complete as per the direction in-charge.
34.01 | Front side premium lounge partition | 1 | 9.18 | 2.425 |  | 22.2615
34.02 | Premium longe side partition | 1 | 5.36 | 2.605 |  | 13.9628
| Sub Total |  |  |  |  | 36.2243
| TENDER QTY CHECKED |  |  |  |  | 21.56
| AMENDED QTY CHECKED |  |  |  |  | 14.6643
| TOTAL |  |  |  |  | 36.2243
35 | Providing & fixing concealed Hydraulic door closer of approved make Hafele or equivalent, Model No. DCL 71, EN 2-5, DOOR WEIGHT 120 KG including all fixing arrangement complete in all respect.
35.01 | Kitchen | 1 | 1 |  |  | 1
35.02 | Store | 1 | 1 |  |  | 1
35.03 | Admin | 1 | 1 |  |  | 1
| Sub Total |  |  |  |  | 3
36 | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in rose gold SS ) of approved make including all fixing arrangement complete in all respect. DORSET MODEL NO.
36.01 | Kitchen | 1 | 1 |  |  | 1
36.02 | Store | 1 | 1 |  |  | 1
36.03 | Admin | 1 | 1 |  |  | 1
| Sub Total |  |  |  |  | 3
38 | PROVIDING & FIXING 600mm long 'H' type pull handle, hand grip height of 400mm, 36mm dia, made of SS, finished in Rose Gold colour of Dorset or equivalent make as per directions of Project In Charge complete
| Kitchen | 1 | 1 |  |  | 1
| Store | 1 | 1 |  |  | 1
| Sub Total |  |  |  |  | 2
III | OTHER WOOD WORK FOR WALL PANELLING, PARTITIONS & STORAGES
39 | Providing and fixing frame work for partitions/ wall lining etc. made of 50x50x1.6 mm hollow MS tube, placed along the walls, ceiling and floor in a grid pattern with spacing @ 60 cm centre to centre both ways (vertically & horizontally) or at required spacing near opening, with necessary welding at junctions and fixing the frame to wall/ ceiling/floors with steel dash fasteners of 8 mm dia, 75 mm long bolt, including making provision for opening for doors,windows, electrical conduits,switch boards etc., including providing with two coats of approved steel primer etc. complete, all as per direction of Engineer-in-charge.
39.01 | Admin cabin entrance wall - V (Z-46) (3.14X4.20) | 6 |  | 4 |  | 24
39.02 | Admin cabin entrance wall - H (Z-46) (4.26x3.14) | 8 |  | 3.14 |  | 25.12
39.03 | Reception area back wall - V (Z-53) (3.445x4.26) | 7 |  | 4 |  | 28
39.04 | Admin outer area corner wall - H (Z-54) (4.26X.35) | 8 |  | 0.35 |  | 2.8
39.05 | Admin area outer wall -V (Z-55) (4.2x4.26) | 8 |  | 4 |  | 32
39.06 | Admin area outer wall -H(Z-55) (4.26X4.20) | 8 |  | 4 |  | 32
39.07 | Admin area outer wall -V (Z-56) (1.17x4.20) | 2 |  | 4 |  | 8
39.08 | Admin area outer wall - H (Z-56) (4.2x1.17) | 8 |  | 1.17 |  | 9.36
39.09 | Bathroom side premium lounge partition above glass framing V (Z-57) (9.17 X 0.80)) | 6 |  | 0.8 |  | 4.8
39.1 | Bathroom side premium lounge partition above glass framing - H (Z-57) (1.8x9.17) | 3 |  | 9.17 |  | 27.51
39.11 | Bathroom side premium lounge partition above glass framing - (Z-57) (1x9.17) | 1 |  | 9.17 |  | 9.17
39.12 | Front buffet counter V (Z-30) (3.775x1.30) | 7 |  | 1.3 |  | 9.1
39.13 | Front buffet counter H (Z-30) (1.3x3.78) | 3 |  | 3.78 |  | 11.34
39.14 | Premium lounge air side partition wall V (Z-38) (2.035x4.20) | 4 |  | 4 |  | 16
39.15 | Premium lounge air side partition wall H (Z-38) (4.2 x 2.035) | 8 |  | 2.035 |  | 16.28
39.16 | Air side premium lounge buffet counter partition - V (Z-35) (3.93x4.20) | 8 |  | 4 |  | 32
39.17 | Air side premium lounge buffet counter partition - H (Z-35) (4.20x3.93) | 8 |  | 3.93 |  | 31.44
39.18 | Exicutive lounge above glass partition - V (Z-31) (5.345x1.73) | 4 |  | 1.73 |  | 6.92
39.19 | Exicutive lounge above glass partition - H (Z-31) (1.73x4.345) | 8 |  | 4 |  | 32
39.2 | Exicutive lounge above rafters partition - V (Z-34) (5.25x1.73) | 4 |  | 1.73 |  | 6.92
39.21 | Exicutive lounge above rasters partition - H (Z-34) (1.73x5.25) | 8 |  | 5.25 |  | 42
39.22 | Premium lounge bathroom side oposite of glazing -V (Z-4,Z-5,Z-6, and Z-7) (7.05x4.20) | 12 |  | 4 |  | 48
39.23 | Premium lounge partition along executive Kitchen entrance - H (Z-4,Z-5,Z-6, and Z-7) (4.20X1) | 8 |  | 6.9 |  | 55.2
Less (-)
| Buffet passage runway side(V) (1.47x2.40) | -2 | 1.465 | 2.4 |  | -4.8
| Buffet passage runway side(H) (2.40x1.47) | -4 | 2.4 | 1.465 |  | -5.86
| Admin door (V) (1.47x2.40) | -2 | 1.465 | 2.4 |  | -4.8
| Admin door (H) (2.40x1.47) | -4 | 2.4 | 1.465 |  | -5.86
| Sub Total |  |  |  |  | 488.64
| weight considered for the material section used 40mmx40mmx 3.5mm (thickness) as per airport norms/Meter/ KG |  |  |  |  | 4.4
| Total Kg |  |  |  |  | 2150.016
| TENDER QTY CHECKED |  |  |  |  | 1351.44
| AMENDED QTY CHECKED |  |  |  |  | 798.576
| TOTAL |  |  |  |  | 2150.016
40 | Providing and fixing 12mm thick HDHMR ply of approved make & manufacture in two layers, first layer on to existing wall.MS Frame, Wooden Frame with nails, screws, grittiest, cleats, clips as required and second layer with approved adhesive including all fixing arrangement complete in all respect .
40.01 | Premium lounge bathroom side oposite of glazing (Z-4,Z-5,Z-6, and Z-7) | 1 | 6.88 | 2.9 |  | 19.952
40.02 | Deck chiller to ramp wall (Z-8, Z-9, Z-10 and Z-11) | 1 | 6.85 | 2.82 |  | 19.317
40.1 | Kitchen entrance left wall (Z-25) | 1 | 1.1 | 2.9 |  | 3.19
40.1 | Kitchen entrance left wall (Z-26) | 1 | 0.585 | 2.9 |  | 1.6965
40.03 | Buffet counter passage area inside (Z-28) | 1 | 3.55 | 2.82 |  | 10.011
40.04 | Buffet counter passage area outer side (Z-35) | 1 | 3.835 | 2.82 |  | 10.8147
40.05 | Exicutive lounge above glass partition (Z-31) | 1 | 5.345 | 0.3 |  | 1.6035
40.06 | Exicutive lounge above glass partition (Z-34) | 1 | 5.345 | 0.3 |  | 1.6035
40.07 | Exicutive lounge above rafters partition (Z-32) | 1 | 5.2 | 0.3 |  | 1.56
40.08 | Exicutive lounge above rafters partition (Z-33) | 1 | 5 | 0.3 |  | 1.5
40.09 | Premium lounge air side partition wall (Z-38) | 1 | 1.95 | 2.82 |  | 5.499
40.1 | Premium lounge air side partition wall (Z-39) | 1 | 1.95 | 2.82 |  | 5.499
40.11 | Runway side CNC partition floor to 900mm height (Z-37) | 1 | 11.95 | 0.9 |  | 10.755
40.12 | Runway side CNC partition floor to 900mm height (Z-37A) | 1 | 11.95 | 0.9 |  | 10.755
40.13 | Premium lounge bathroom side partition above glass framing above glass (Z-57) | 1 | 9.17 | 0.5 |  | 4.585
40.14 | Premium lounge bathroom side partition above glass framing above glass (Z-47) | 1 | 9.17 | 0.5 |  | 4.585
40.15 | Front side premium lounge partition Bottom ledge wall (Z-57) | 1 | 9.17 | 1 |  | 9.17
40.16 | Front side premium lounge partition Bottom ledge wall (Z-47) | 1 | 9.17 | 1 |  | 9.17
40.17 | Coloumns verticals patta at both ends Air side b/w CNC jaali to glass partition | 6 | 1.8 | 0.6 |  | 6.48
40.18 | Marchantise wall I.T rack (3-no. hdhmr board) Z 43 Z 42 Z41 | 1 | 3.9 | 2.6 |  | 10.14
40.19 | I.T raack right side wall upper door shutter area (Z-41) | 1 | 0.8 | 0.27 |  | 0.216
40.2 | Admin cabin entrance wall (Z-46) | 1 | 3.14 | 2.82 |  | 8.8548
40.21 | Machandise unit shelves | 4 | 0.6 | 0.91 |  | 2.184
Less (-)
| Buffet passage runway side | -3 | 1.465 | 2.4 |  | -10.548
| Sub Total |  |  |  |  | 148.593
41 | Providing and fixing 12mm thick flexible MR grade ply in two layers, of approved brand & manufacture on existing M.S. frame work, 1st layer with screws, nails, cleats , clips as required and second layer with approved adhesive including all fixing arrangement complete in all respect .
41.01 | Reception area back wall ( Z 53) | 1 | 3.72 | 2.8 |  | 10.416
41.02 | Admin cabin reception Side back wall(Z 49 ) | 1 | 2.66 | 2.8 |  | 7.448
41.03 | Front buffet counter outer side area ( Z 30) | 1 | 3.775 | 1.35 |  | 5.0963
41.03 | Front buffet counter outer inside area (Z 29) | 1 | 3.775 | 1.35 |  | 5.0963
41.04 | Back buffet counter (Z 27) | 1 | 3.86 | 1.9 |  | 7.334
| Sub Total |  |  |  |  | 35.3905
| TENDER QTY CHECKED |  |  |  |  | 21.48
| AMENDED QTY CHECKED |  |  |  |  | 13.9105
| TOTAL |  |  |  |  | 35.3905
43 | Providing and fixing 1mm thick laminate panelling over existing partition as per approved sample including all fixing arrangement complete in all respect. Only finished area to be measured & paid.( Basic cost of Laminate@ Rs.970/-Sqm ).
43.01 | Premium lounge bathroom side kitchen side wall (Z-1) | 1 | 2.536 | 0.9 |  | 2.2824
43.02 | Premium lounge bathroom side kitchen side wall (Z-2) | 1 | 2.19 | 0.9 |  | 1.971
43.03 | Premium lounge bathroom side kitchen side wall (Z-3) | 1 | 0.985 | 0.9 |  | 0.8865
43.04 | Premium lounge bathroom buffet counter back side wall (Z-4) | 1 | 3.88 | 0.9 |  | 3.492
43.05 | Premium lounge bathroom side deck chiller wall (Z-5) | 1 | 0.72 | 0.9 |  | 0.648
43.06 | Premium lounge deck chiller back wall (Z-6) | 1 | 1.4 | 0.9 |  | 1.26
43.07 | Premium lounge deck chiller back wall (Z-7) | 1 | 0.873 | 0.9 |  | 0.7857
43.08 | Deck chiller right wall(Z-8) | 1 | 0.77 | 2.82 |  | 2.1714
43.09 | Deck chiller front wall (Z-9) | 1 | 1.325 | 2.82 |  | 3.7365
43.1 | Deck chiller left wall (Z-10) | 1 | 0.77 | 2.82 |  | 2.1714
43.11 | Kitchen passage left wall (Z-11) | 1 | 3.98 | 2.82 |  | 11.2236
43.12 | Kitchen door wall (Z-12) | 1 | 1.45 | 2.82 |  | 4.089
43.13 | Kitchen ramp left side wall (Z-25 and Z-26) | 1 | 1.685 | 2.82 |  | 4.7517
43.14 | Buffet counter passage area inside (Z-28) | 1 | 3.55 | 2.82 |  | 10.011
43.15 | Buffet counter passage area outer side (Z-35) | 1 | 3.835 | 2.82 |  | 10.8147
43.16 | Buffet counter front side (Z-30) | 1 | 3.775 | 1.35 |  | 5.0963
43.17 | Exicutive lounge above glass partition (Z-31 and Z-34) | 2 | 5.345 | 0.3 |  | 3.207
43.18 | Exicutive lounge above rafters partition (Z-32 and Z-33) | 2 | 5.25 | 0.3 |  | 3.15
43.19 | Premium lounge air side partition wall (Z-38 and Z-39) | 2 | 1.95 | 2.82 |  | 10.998
43.2 | I.T raack right side wall (Z-41) |  |  |  |  | 0
43.21 | I.T raack right side wall upper door shutter area (Z-41) |  |  |  |  | 0
43.22 | Runway (Airbay Side ) premium lounge CNC wall inside deep L-type (Z-37A) | 1 | 14.1 | 1.19 |  | 16.779
43.23 | Admin cabin entrance wall (Z-46) | 1 | 3.14 | 2.82 |  | 8.8548
43.24 | Bathroom side premium lounge partition above glass framing V (Z-57) | 1 | 9.17 | 0.3 |  | 0.3
43.25 | Bathroom side premium lounge partition above glass framing V (Z-47) | 1 | 9.17 | 0.6 |  | 0.6
43.26 | Coloumns verticals patta at both ends Air side b/w CNC jaali to glass partition | 6 | 1.835 | 0.65 |  | 7.1565
Less (-)
| Buffet passage runway side | -2 | 1.465 | 2.4 |  | -7.032
| Admin door | -2 | 1.1 | 2.4 |  | -5.28
| Sub Total |  |  |  |  | 104.1244
| TENDER QTY CHECKED |  |  |  |  | 90.53
| AMENDED QTY CHECKED |  |  |  |  | 13.5945
| TOTAL |  |  |  |  | 104.1244
44 | Providing & fixing 12mm thick HDHMR ply panelling on wall with required termite treated wooden frame work with the help of gutties & screw , nails complete in all respect. The base frame shall be made from approved quality Kali wood , kiln seasoned, termite treated etc of size 50x25mm( minimum) @600mm c/c with additional members on the ends etc as per Directions of Project In Charge, premium lounge wall and executive lunge wall of block work.
44.01 | Buffet area ceiling, board fixing on ceiling for light hanging | 1 | 3.335 | 1.421 |  | 4.739
44.02 | Marchantise unit area CNC partition side corner Z 40A | 1 | 1.48 | 2.82 |  | 4.1736
44.03 | Runway (Airbay Side ) premium lounge CNC wall inside deep L-type Z 37A | 1 | 15.233 | 1.19 |  | 18.1273
44.04 | Air side CNC wall Z 37 | 1 | 11.95 | 0.9 |  | 10.755
44.05 | premium lounge kitchen passage back wall (Z-1, Z-2, Z-3, Z-4, Z-5, Z-6 and Z-7) | 1 | 10.225 | 0.9 |  | 10.225
| Sub Total |  |  |  |  | 48.0199
| TENDER QTY CHECKED |  |  |  |  | 22.42
| AMENDED QTY CHECKED |  |  |  |  | 25.5999
| TOTAL |  |  |  |  | 48.0199
45 | Providing & fixing 1.2mm thick aluminium. Skirting PVDF coated 100mm height rose gold finish or as per approved sample over existing partition including all fixing arrangement complete in all respect. ( Basic cost Aluminium Skirting @ Rs. 450/-Rmtr)
RAB-01
1 | Reception counter back wall (Z-53) | 1 | 3.445 |  |  | 3.445
2 | Admin outer wall recpection corner (Z-54) | 1 | 0.35 |  |  | 0.35
3 | Admin outer wall (Z-55 and Z-56) | 1 | 4.8 |  |  | 4.8
4 | glass partition area (Z-57) | 1 | 9.17 |  |  | 9.17
5 | Premium lounge front wall (Z-1) | 1 | 2.5 |  |  | 2.5
6 | premium lounge kitchen passage back wall (Z-2, Z-3, Z-4, Z-5, Z-6 and Z-7) | 1 | 9.6 |  |  | 9.6
7 | kitchen passage area till ramp (Z-8 a , Z-9, Z-10, and Z-11 | 1 | 7.84 |  |  | 7.84
9 | Kitchen ramp left side wall (Z-25) | 1 | 1.1 |  |  | 1.1
9 | Back buffet counter (Z-27) | 1 | 4.33 |  |  | 4.33
10 | Front buffet counter inside (Z-29) | 1 | 3.95 |  |  | 3.95
11 | Front buffet counter outer side (Z-30) | 1 | 3.775 |  |  | 3.775
12 | Buffet counter Passage door frame along PVD frame side (Z-28 and Z-29) | 1 | 1 |  |  | 1
13 | Buffet counter passage door along kitchen (Z-35) | 1 | 2.33 |  |  | 2.33
14 | Runway side (Airbay side) premium lounge fids wall (Z-36) | 1 | 3.1 |  |  | 3.1
15 | Runway side CNC wall (Z-37) | 1 | 11.95 |  |  | 11.95
16 | Runway side premiunm lounge partition (Z-38 and Z-39) | 2 | 1.95 |  |  | 3.9
17 | Marchantise wall till reception entrance (Z-40) | 1 | 6.8 |  |  | 6.8
18 | I.T rack (Z-41,Z-42 and Z-43) | 1 | 3.77 |  |  | 3.77
RAB -02
| Sub Total |  |  |  |  | 83.71
| TENDER QTY CHECKED |  |  |  |  | 67.02
| AMENDED QTY CHECKED |  |  |  |  | 16.69
| TOTAL |  |  |  |  | 83.71
46 | Providing and fixing over head storage with necessary shelves as per design made out of 19mm thick HDHMR board fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with 1mm thick laminate including required shelves, shutters and required hardware like handle, knobs, magnetic catcher, hinges, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 270/-Sqm & external surface laminate@ Rs.970/-Sqm)
46.01 | Admin cabin (Z-49) | 1 | 2.62 | 0.9 |  | 2.358
| Sub Total |  |  |  |  | 2.358
48 | Providing and fixing partly open partly closed Servery counter storage as per drawing made out of 19mm thick HDHMR board fixed with the help of all necessary hardware like nail and fasteners and all internal area of storage ( Excluding open shelves inner surface ) to be finished with 0.8mm thick laminate and open shelves inner surface to be finished with rose gold finish 1mm thick SS sheet & external facade surface & top surface of survery storage to be finished with Italian stone fixed with adhesive & 100mm high rose gold finish Aluminium skirting at floor level, including required drawer unit, required open shelves, Louver shutters and required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, drawer channel, shutter lock etc. all are superior quality of approved make, complete in all respect. ( Rose Gold finish SS sheet paid separately in rose gold finish SS sheet item & Italian Stone paid separately in Italian stone Item). ( Basic cost of internal laminate @ Rs.270/-Sqm & external surface laminate@ Rs.970/-Sqm.)
48.01 | Front buffet counter (Z-29) | 1 | 2.65 | 0.83 |  | 2.1995
48.02 | Back buffet counter (Z-27) | 1 | 4.877 | 0.83 |  | 4.0479
| Sub Total |  |  |  |  | 6.2474
49 | Providing and fixing Reception Table ( 450mm to 600mm Deep ) (2.1mtr. long x 1.2mtr ht. ) made out of 19mm thick HDHMR ply for required partition, front & sides including necessary shelves with shutter & drawers, Key board tray, all necessary hardware of superior quality like nail, self closing type hinges, S.S. handles, knobs, locks, key board tray , etc. And front facade, sides & top finish with Italian marble stone of approved make, shade & texture including all fixing arrangement ,grinding polishing, edge chamfering & polishing & all internal surface to be finished with 0.8mm thick laminate & external exposed drawer / wooden surface to be finished with 1mm thick laminate of approved make & shade & reception table facade surface at floor level 100mm high skirting & top & sides edging finished with PVD coated rose gold finish in aluminium . complete in all respect. ( Basic cost of internal laminate @ Rs.270/- Sqm & external laminate @ Rs970/-Sqm & Italian marble stone @ Rs. 4845/- Sqmt ) & PVD coated rose gold finish 1mm thick SS sheet @ Rs.4420Sqm)
49.01 | Reception counter | nos |  |  |  | 1
| Sub Total |  |  |  |  | 1
50 | Providing making & fixing in position 19mm thick India Map ( 1.58mtr x 1.87mtr) made of 18mm thick MDF Board of approved make finished with 1mm thick PVD coated Rose Gold finish SS sheet with provision for LED light glowing arrangement at location of Lucknow including all fixing arrangement complete in all respect.( Basic cost of PVD coated SS sheet @ Rs.4420/- Sqm )
50.01 | Reception counter back wall (Z-53) | nos |  |  |  | 1
| Sub Total |  |  |  |  | 1
51 | Providing Making & fixing/pasting with approved adhesive in position 1mm thick SS Sheet of grade 304 PVD coated with approved colour, shade, texture & finish over 12mm thick flexi fire retardant ply of approved brand & manufacture in circular portion of the display at top and on 12mmm thick MDF Board on horizontal/vertical surfaces. the fins of teh display shall be made 50mm thick, with projection of 300mm in straight portion UPTO height of about 2.40meters and thereafter it shall further add 200mm projection to 300mm projection making overall projected length at top most pont( at Ceiling) of 500mm. The top shall have another recessed semicircular ( 50mm inside from 500 mm overall projection at top) of R230mm etc as per drawings. The top surface and all inside surfaces and out side surfaces of fins forming display shall be wrapped with 1mm thick PVD coated SS304 grade sheet with coating of approved colour, shade and texture. The PVD sheet shall be wrapped with approved adhesive etc.. In addition to it a box shall be created at height from 450mm to 1100 mm i.e. 650mm front with wooden Hollock wood battens of appropriate size over it HDHMR board of 19mmm thickness shall be fixed and on this board 19mm thick Italian stone shall be fixed. The HDHMR Board shall be semi circular at teh bottom so shall be Italian stone as per drawing. The top shall also have Italian stoneof size 300x500x19mm with bird beak corner grove joint with teh vertical stone surface, polished complete over HDHMR Board of 19mm thick of approved shade, colour, design, pattern & profile as per drawing complete. The front area in between teh fins shall have 1mm thick laminate on the existing HDHMR partition. there shall be a 10mm thick glass of 500mm height placed above Italian stone with suitable opening & locking arrangement, the glass box shall have top also of 10mmm thick toughened glass fixed to back with tubular section of SS304 grade as frame on corner for fixing glass to glass and glass to side fins and glass to back wall of size 25x10mm, with locking arrangement complete.
51.01 | The rate is also inclusive of fixing 19mmx19mm edge Italian stone at the bottom semi circular portion with adhesive and in pieces in true semi circular profile of teh front Italian stone ( making visible thickness of stone at bottom as 19+19mm=38mm, polishes complete | 1 | 3 |  |  | 3
| Sub Total |  |  |  |  | 3
IV | False ceiling Work
53 | Providing and fixing split level gypsum board false ceiling including providing and fixing GI grade 175 (120 gm/m2) perimeter, channels (20 x 30 x 27 x 0.50mm thick) fixed to brick masonry / partition / hanging with existing ceiling / existing M.S. frame work and suspended GI intermediate channel. Rate to include making necessary cut out/opening for light fitting A C diffuser etc. The cut out to have perimeter channel of size 20x27x30x.5mm all round and supported suitably and finally finished with gypsum board and finally finished with two or more coat of plastic emulsion paint of approved make & shade with required tapping the joints, base primer, putty complete in all respect. (Actual plan area to be measured & paid.). Rate quoted should be included for all design work, providing false ceiling in circular profile in horizontal as well as vertical edges to teh horizontal circular profiles including straight profiles as per drawing, levels Nothing to be paid extra for design work. PREMIUM LOUNGE AREA
53.01 | Runway (airbay Side ) boxing from gypsum to make ceiling patta (Z-37) | 1 | 14.07 | 1.3 |  | 18.291
| Sub Total |  |  |  |  | 18.291
54 | Providing and fixing gypsum board false ceiling with coves on sides along the walls to receive light fixtures, AC diffusers etc including providing and fixing GI grade 175 (120 gm/m2) perimeter, channels (20 x 30 x 27 x 0.50mm thick) fixed to brick masonry / partition / hanging with existing ceiling / existing M.S. frame work and suspended GI intermediate channel. Rate to include making necessary cut out/opening for light fitting A C diffuser etc. The cut out to have perimeter channel of size 20x27x30x.5mm all round and supported suitably and finally finished with gypsum board and finally finished with two or more coat of plastic emulsion paint of approved make & shade with required tapping the joints, base primer, putty complete in all respect. (Actual plan area to be measured & paid.). Rate quoted should be included for all design work, providing false ceiling in circular profile in horizontal as well as vertical edges to teh horizontal circular profiles including straight profiles as per drawing, levels Nothing to be paid extra for design work. EXECUTIVE LOUNGE, RECEPTION, ADMN ROOM etc | [5 empty] | Drawing required
54.01 | Section -1 Bathroom side premium lounge Considered from P-Line | 1 | 31.91 | 1 |  | 31.91
54.02 | Section -2 Reception area Considered from P-Line | 1 | 9.95 | 1 |  | 9.95
54.03 | Section 3 Admin Room Considered from P-Line | 1 | 5.32 | 1 |  | 5.32
54.04 | Section - 4 Executive lounge area Considered from P-Line | 1 | 68 | 1 |  | 68
54.05 | Section -5 Air side premium lounge area Considered from P-Line | 1 | 44.77 | 1 |  | 44.77
| Sub Total |  |  |  |  | 159.95
| TENDER QTY CHECKED |  |  |  |  | 140
| AMENDED QTY CHECKED |  |  |  |  | 19.95
| TOTAL |  |  |  |  | 159.95
55 | Providing and fixing Gl Clip in Metal Ceiling System of 600x600 mm module which includes providing and fixing 'C' wall angle of size 20x30x20 mm made of 0.5 mm thick pre painted steel along the perimeter of the room with help of nylon sleeves and wooden screws at 300 mm center to centre, suspending the main C carrier of size 10x38x10 mm made of G.I steel 0.7 mm thick from the soffit with the help of soffit cleat 37x27x25x1.6 mm, rawl plugs of size 38x12 mm and C carrier suspension clip and main carrier bracket at 1000 mm c/c. Inverted triangle shaped Spring Tee having height of 24 mm and width of 34 mm made of Gl steel 0.45 mm thick is then fixed to the main C carrier and in direction perpendicular to it at 600 mm centers with help of suspension brackets. Wherever the main C carrier and spring T have to join, C carrier and spring T connectors have to be used. All sections to be galvanized @ 120 gms/sqm (both side inclusive), fixing with clip in tiles into spring T with :
55.01 | Kitchen all area including store | 1 | 9.5 | 2.48 |  | 23.56
55.02 | Admin cabin | 1 | 3 | 1.78 |  | 5.34
55.03 | Kitchen entrance ramp
Less (-)
| Front equipment wall Oven side pillar | -1 | 0.95 | 0.15 |  | -0.1425
| Front equipment wall Oven side pillar | -1 | 0.3 | 0.8 |  | -0.24
| Store room right side wall | -1 | 0.9 | 0.15 |  | -0.135
| Store room left side wall | -1 | 0.73 | 0.15 |  | -0.1095
| Stone room LT panel wall corner | -1 | 0.59 | 0.72 |  | -0.4248
| Sub Total |  |  |  |  | 27.8482
| TENDER QTY CHECKED |  |  |  |  | 21.5
| AMENDED QTY CHECKED |  |  |  |  | 6.3482
| TOTAL |  |  |  |  | 27.8482
56 | Providing & applying P.O.P. punning on walls with an average thickness of 2mm including finishing the surface smooth in line & level complete in all respect.
56.01 | Bathroom side premium lounge area along kitchen wall (Z-1, Z-2, Z-3 ) | 1 | 2.21 | 5.75 |  | 12.7075
56.03 | Merchandise unit side wall with column (Z-40) | 1 | 6.76 | 2.8 |  | 18.928
56.04 | Runway side (Airbay side) premium lounge fids wall (Z-36) | 1 | 3.17 | 2.8 |  | 8.876
| Sub Total |  |  |  |  | 40.5115
57 | Providing three or more coats of Plastic Emulsion paint of approved make & shade including preparation of base by cement based putty & primer complete in all respect. ( Admin area inside wall paint )
Ceiling
57.01 | Section -1 Bathroom side premium lounge area as per P-Line | 1 | 31.91 | 1 |  | 31.91
57.02 | Section -2 Reception area | 1 | 9.95 | 1 |  | 9.95
57.03 | Section 3 Admin Room | 1 | 5.32 | 1 |  | 5.32
57.04 | Section - 5 Executive lounge area | 1 | 68 | 1 |  | 68
57.05 | Section -5 Air side premium lounge area | 1 | 44.77 | 1 |  | 44.77
57.06 | Premium lounge bathroom side kitchen side wall (Z-1) | 1 | 2.536 | 1.9 |  | 4.8184
57.07 | Premium lounge bathroom side kitchen side wall (Z-2) | 1 | 2.19 | 1.9 |  | 4.161
57.08 | Premium lounge bathroom side kitchen side wall (Z-3) | 1 | 0.985 | 1.9 |  | 1.8715
57.09 | Premium lounge bathroom buffet counter back side wall (Z-4) | 1 | 3.88 | 1.9 |  | 7.372
57.1 | Premium lounge bathroom side deck chiller wall (Z-5) | 1 | 0.771 | 1.9 |  | 1.4649
57.11 | Premium lounge deck chiller back wall (Z-6) | 1 | 1.525 | 1.9 |  | 2.8975
57.12 | Premium lounge deck chiller back wall (Z-7) | 1 | 0.873 | 1.9 |  | 1.6587
57.13 | Admin ouetr PL side wall along glass side(Z-56) | 1 | 1.145 | 2.91 |  | 3.3319
57.14 | Admin outer PL side wall (Z-55) | 1 | 4.2 | 2.91 |  | 12.222
57.15 | Admin outer corner (Z-54) | 1 | 0.49 | 2.91 |  | 1.4259
57.16 | Reception back wall(Z-53) | 1 | 3.58 | 2.91 |  | 10.4178
57.17 | Marchantise unit wall(Z-40) | 1 | 7.106 | 2.91 |  | 20.6785
57.18 | Premium lounge Air side FIDS wall (Z-36) | 1 | 3.711 | 2.91 |  | 10.799
57.19 | Admin cabin wall (Z-48) | 1 | 2.875 | 2.82 |  | 8.1075
57.2 | Admin cabin wall (Z-50) | 1 | 0.63 | 2.82 |  | 1.7766
57.21 | Admin cabin wall (Z-51) | 1 | 2.4 | 2.82 |  | 6.768
57.22 | Admin cabin wall (Z-52) | 1 | 1.6 | 2.82 |  | 4.512
57.23 | 2600mm Ceiling (200 patta ) | 4 | 8.835 | 0.3 |  | 10.602
57.24 | Buffet counter ceiling | 1 | 8.648 | 0.3 |  | 2.5944
57.25 | All cove | 1 | 67.538 | 0.3 |  | 20.2614
Sub Total
58 | Providing & fixing Fabric backed Vinyl Wall covering(10.05mtr. X .52mtr ) ( 300gsm Type-II) fire Retardant as per approved sample including all fixing arrangement complete in all respect.( Basic cost of Fabric backed Vinyl Wall covering @ Rs. 3230/- Sqm )
58.01 | Premium lounge bathroom side kitchen side wall (Z-1) | 1 | 2.5 | 1.94 |  | 4.85
58.02 | Premium lounge bathroom side kitchen side wall (Z-2) | 1 | 2.2 | 1.94 |  | 4.268
58.03 | Premium lounge bathroom side kitchen side wall (Z-3) | 1 | 0.985 | 1.94 |  | 1.9109
58.04 | Premium lounge bathroom buffet counter back side wall (Z-4) | 1 | 3.88 | 1.94 |  | 7.5272
58.05 | Premium lounge bathroom side deck chiller wall (Z-5) | 1 | 0.771 | 1.94 |  | 1.4957
58.06 | Premium lounge deck chiller back wall (Z-6) | 1 | 1.42 | 1.94 |  | 2.7548
58.07 | Premium lounge deck chiller back wall (Z-7) | 1 | 0.873 | 1.94 |  | 1.6936
58.08 | Admin ouetr PL side wall along glass side(Z-56) | 1 | 1.145 | 2.7 |  | 3.0915
58.09 | Admin outer PL side wall (Z-55) | 1 | 3.5 | 2.7 |  | 9.45
58.1 | Admin outer corner (Z-54) | 1 | 0.039 | 2.3 |  | 0.0897
58.11 | Reception back wall(Z-53) | 1 | 3.5 | 2.5 |  | 8.75
58.12 | Marchantise unit side I.T rack wall(Z-43, Z-42 and Z-41) | 1 | 2.575 | 2.7 |  | 6.9525
58.13 | Marchantise unit wall(Z-40) | 1 | 6.8 | 2.7 |  | 18.36
58.14 | Premium lounge Air side FIDS wall (Z-36) | 1 | 3.2 | 2.7 |  | 8.64
58.15 | Coloumns verticals patta at both ends Air side b/w CNC jaali to glass partition | 2 | 1.835 | 1.6 |  | 5.872
Less (-)
| Air side pillar tuk | -2 | 0.3 | 0.45 |  | -0.27
| Sub Total |  |  |  |  | 79.834
VI | Misc. Work
59 | Providing & filling 50mm thick Fibre Glass wool ( 64kg density ) in M. S. frame work for partition wall for making sound proof
59.01 | Admin cabin entrance wall - V (Z-46) | 1 | 3.14 | 4.26 |  | 13.3764
59.02 | Reception area back wall - V (Z-53) | 1 | 3.445 | 4.26 |  | 14.6757
59.03 | Admin outer area corner wall - H (Z-54) | 1 | 0.35 | 4.26 |  | 1.491
59.04 | Admin area outer wall -V (Z-55) | 1 | 4.2 | 4.26 |  | 17.892
59.05 | Admin area outer wall -V (Z-56) | 1 | 1.17 | 4.2 |  | 4.914
59.06 | Bathroom side premium lounge partition above glass framing V (Z-57) | 1 | 9.17 | 1.8 |  | 16.506
59.07 | Air side premium lounge buffet counter partition - V (Z-35) | 1 | 3.93 | 4.2 |  | 16.506
59.08 | Exicutive lounge above glass partition - V (Z-31) | 1 | 5.345 | 1.73 |  | 9.2469
59.09 | Exicutive lounge above rafters partition - V (Z-34) | 1 | 5.25 | 1.73 |  | 9.0825
59.1 | Premium lounge bathroom side oposite of glazing -V (Z-4,Z-5,Z-6, and Z-7) | 1 | 7.05 | 4.2 |  | 29.61
Less (-)
| Buffet passage runway side(V) | -1 | 1.465 | 2.4 |  | -3.516
| Admin door (V) | -1 | 1.465 | 2.4 |  | -3.516
Sub Total
60 | Providing & fixing aluminium. T profile ( 19mm x 19mm x 6mm thick ) PVDF coated ( Rose gold finish ) as per approved sample including all fixing arrangement complete in all respect. ( Basic cost of T Profile @ Rs. 250/- Rmtr. )
60.01 | Glass partition Exicutive lounge area top,bottom and sides (Z-34) | 1 | 13.7 |  |  | 13.7
Sub Total
61 | Providing & fixing Rose Gold finish L- angle aluminium profile ( 12mm x 12mm x 1.5mm thick ) as per approved sample fixed with adhesive of approved make including all fixing arrangement complete in all respect. ( Basic cost of Angle @ Rs. 330 Rmtr. )
61.01 | Reception area including admin wall (Corner guard) Z 56 TO Z 46 | 4 | 2.5 |  |  | 10
61.02 | Bathroom side premium lounge wall along kitchen and international airport side area (Corner guard) Z 2 TO Z 11 | 7 | 2.7 |  |  | 18.9
61.03 | Kitchen entrance left side wall (Corner guard) Z 25 26 | 2 | 2.7 |  |  | 5.4
61.04 | Air side premiun lounge partition and column (Corner guard) Z 38, 39,40 | 3 | 2.5 |  |  | 7.5
61.05 | Marchandise wall I.t area (Corner guard) Z 42,43 | 2 | 2.5 |  |  | 5
61.06 | JUNCTION Bathroom side premium lounge area wall joint b/w laminate and wallpaper (Z-1 To Z-7) | 1 | 10.119 |  |  | 10.119
60.01 | Reception area (Z-54 side) JUCTION Profile italian and wooden flooring | 1 | 2.011 |  |  | 2.011
60.02 | Merchantise area side exicutive lounge to premium lounge (Z-40 Side) JUNCTION CARPET AND WOODEN FLOORING | 1 | 2.667 |  |  | 2.667
60.03 | Air side Premium lounge to buffet counter passage (Z-28) JUNCTION CARPET AND WOODEN FLOORING | 1 | 1.522 |  |  | 1.522
60.04 | Kitchen entrance ramp (Z-12) JUNCTION
| Sub Total |  |  |  |  | 63.119
| TENDER QTY CHECKED |  |  |  |  | 24.6
| AMENDED QTY CHECKED |  |  |  |  | 38.519
| TOTAL |  |  |  |  | 63.119
0
62 | P/F 1mm thick PVD coated SS sheet fixing on existing wall panelling as per approved sample including all fixing arrangement complete in all respect.( Basic cost of PVD coated SS sheet @ Rs.4420/- Sqm )
62.01 | Buffet counter Passage door frame along PVD frame side (Z-28) | 1 | 6.3 | 0.13 |  | 0.819
62.02 | Buffet front counter top and side (Z-29) | 1 | 5.102 | 0.13 |  | 0.66326
62.03 | Marchandise unit top outer courve area | 3 | 1.5 | 0.5 |  | 2.25
6.04 | Marchandise unit top inner courve area | 3 | 0.86 | 0.345 |  | 0.8901
62.05 | Marchandise unit front top edges | 6 | 1.58 | 0.05 |  | 0.474
62.06 | Marchandise uint u-shape side and front covering | 6 | 0.65 | 1.9 |  | 7.41
| Sub Total |  |  |  |  | 12.5064
63 | Providing & doing water proofing of sunken areas of Toilets, balconies etc, of following operations: i) Cleaning the sunken area surface using wire brush and then broom making teh surface dust free. Ii) Repairing the holes, depressions or taking out loose materials of brick work/cement plater/concrete and grouting the same with cement concrete (1:11/2:3) or cement plater (1:3) as teh case may be and only if required. Iii) Applying two coats of base primer of URP301 of Dr Fixit or equivalent as per manufacturers specifications. Iv) (laying of pipes, PCC on pipes ) and applying URP301 two coats on teh PCC surfaces and the other ares which got damaged due to laying of pipes and subsequenty made good( grouted). V) Laying of water proof coat of 2K of Dr Fixit or equivalent as per manufacturer's specifications. Vi) Allowing it dry then checking teh sunken areas by water ponding for two days and if leakage is observed then redoing the 2K coats all over again. VII) Laying water proof plaster in slope 1:100 towards spout fixed for drainage in cement mortar 1:3 mixed with water proofing compound with cement @2% by weight of cement , finished neat or as may be specified by teh manufacturer, curing for minimum seven days.
63.01 | Kitchen all area including store floor | 1 | 9.5 | 2.48 |  | 23.56
63.02 | Admin cabin floor | 1 | 3.45 | 2.1 |  | 7.245
Less (-)
| Front equipment wall Oven side pillar | -1 | 0.95 | 0.15 |  | -0.1425
| Front equipment wall Oven side pillar | -1 | 0.3 | 0.8 |  | -0.24
| Store room right side wall | -1 | 0.9 | 0.15 |  | -0.135
| Store room left side wall | -1 | 0.73 | 0.15 |  | -0.1095
| Stone room LT panel wall corner | -1 | 0.59 | 0.72 |  | -0.4248
63.02 | Kitchen walls
a | Kitchen entrance door L- shape wall along primium lounge | 1 | 4.51 | 0.3 |  | 1.353
b | Kitchen entrance door front wall | 1 | 5.07 | 0.3 |  | 1.521
c | Oven partition wall | 1 | 2.06 | 0.3 |  | 0.618
d | Oven partition wall to store room door wall | 1 | 2.66 | 0.3 |  | 0.798
e | Store entrance door wall both side | 2 | 2.45 | 0.3 |  | 1.47
f | Store inside electrical panel wall | 1 | 2.84 | 0.3 |  | 0.852
g | Store inside DB wall | 1 | 1.88 | 0.3 |  | 0.564
h | Store inside lounge side wall | 1 | 2.29 | 0.3 |  | 0.687
i | Kitchen inside highighter wall | 1 | 4.51 | 0.3 |  | 1.353
| Less (-) |  |  |  |  | 0
| Kitchen door | -1 | 1.2 | 0.3 |  | -0.36
| Store door both side | -2 | 0.9 | 0.3 |  | -0.54
| Sub Total |  |  |  |  | 38.0692
| TENDER QTY CHECKED |  |  |  |  | 19.66
| AMENDED QTY CHECKED |  |  |  |  | 18.4092
| TOTAL |  |  |  |  | 38.0692
64 | Providing & filling Khanger in the sunken areas as per Directions of Project-in-Charge
63.01 | Kitchen all area including store floor | 1 | 9.5 | 2.48 | 0.2 | 23.56
63.02 | Admin cabin floor | 1 | 3.45 | 2.1 | 0.2 | 7.245
Less (-)
| Front equipment wall Oven side pillar | -1 | 0.95 | 0.15 | 0.2 | -0.1425
| Front equipment wall Oven side pillar | -1 | 0.3 | 0.8 | 0.2 | -0.24
| Store room right side wall | -1 | 0.9 | 0.15 | 0.2 | -0.135
| Store room left side wall | -1 | 0.73 | 0.15 | 0.2 | -0.1095
| Stone room LT panel wall corner | -1 | 0.59 | 0.72 | 0.2 | -0.4248
| Total Sqmtr. |  |  |  |  | 29.7532
| Sub Total (CUM) |  |  |  |  | 5.9506
| TENDER QTY CHECKED |  |  |  |  | 1
| AMENDED QTY CHECKED |  |  |  |  | 4.9506
| TOTAL |  |  |  |  | 5.9506
65 | Providing and doing 12mm thick solid surface ( corian) of approved, shade, texture, make & manufacture over base of 12mm water proof ply with all adhesives, including all processes & making the curves smooth and joints seamless as per profile, drawings and instructions of Engineer incharge complete
1 | Front buffet counter
1.01 | Counter top | 1 | 2.88 | 0.69 |  | 1.9872
1.02 | Fornt area | 1 | 3.64 | 0.73 |  | 2.6572
1.03 | Counter top skirting | 1 | 2.88 | 0.15 |  | 0.432
1.04 | Inside of open shelves sides | 12 | 0.54 | 0.25 |  | 1.62
1.05 | Inside open shelves top and bottom | 4 | 0.54 | 0.565 |  | 1.2204
1.06 | Inside horizontal shelves | 2 | 0.76 | 0.49 |  | 0.7448
2 | Back buffet counter
2.01 | Counter top | 1 | 3.86 | 0.73 |  | 2.8178
2.02 | Fornt area | 1 | 4.945 | 0.73 |  | 3.6098
2.03 | Counter top skirting | 1 | 3.86 | 0.155 |  | 0.5983
2.04 | Inside of open shelves sides | 12 | 0.55 | 0.25 |  | 1.65
2.05 | Inside open shelves top and bottom | 4 | 0.57 | 0.55 |  | 1.254
2.06 | Inside horizontal shelves | 2 | 0.76 | 0.505 |  | 0.7676
| Sub Total |  |  |  |  | 19.3591
| TENDER QTY CHECKED |  |  |  |  | 13.65
| AMENDED QTY CHECKED |  |  |  |  | 5.7092
| TOTAL |  |  |  |  | 19.3591
D | SANITARY FIXTURES FITTINGS WORK
66 | P / F CP Brass 15mm Diameter Angle Valve of KOHLER make Model-PARALLEL or as approved by the Project-in-Charge. | 4 |  |  |  | 9
| Sub Total |  |  |  |  | 9
| TENDER QTY CHECKED |  |  |  |  | 4
| AMENDED QTY CHECKED |  |  |  |  | 5
| TOTAL |  |  |  |  | 9
67 | Providing & fixing ROB HOOK of EURONICS make Model No. EC02 or equivalent as approved by the Project-in-Charge. | 8
Sub Total
68 | P / F S.S. Liquid Soap dispenser of aEURONICS make Model No. ES80A or equivalent. | 4
Sub Total
69 | Providing SS 304 grade Dust Bin in W.C. area of approved make and size of 6 L Capacity of KOHLER Make reference Model No. K-17531T-ST or equivalent( approximately 300mm dia and 45 cms high) etc as per directions of Project -in-Charge | 8
Sub Total
70 | Providing & fixing Sink mixture of CERA make Model No. F 2002511 or equivalent as approved by the Project -in-Charge. | 1 |  |  |  | 2
| Sub Total |  |  |  |  | 2
| TENDER QTY CHECKED |  |  |  |  | 1
| AMENDED QTY CHECKED |  |  |  |  | 1
| TOTAL |  |  |  |  | 2
71 | Providing & fixing single bowl single draining board , stain less steel grade 304 kitchen sink, with coating for sound absorption, CP waste, CP Brass bottle trap of 32mm dia of NIRALI make of size 1000x510x250mm or equivalent as approved by the Project-in-Charge. | 1
Sub Total
72 | Providing & fixing Bar Sink in SS ( 304 grade ) of KAFF Make reference Model No. KS 22 SB (R10) of size 220x440x200mm Bowl size of 180x400x200mm, 1 mm thick SS Sheet, with sound reduction pad all around & bottom, anti condensation coating etc with all fixtures, firings, brackets , screws, fasteners for fixing to wall and or counter as per drawing or equivalent Make as approved by the Project-in-Charge complete as per drawings & instructions of Project-in-Charge. | 1
D
73 | Providing & fixing dual level spout of CP Brass of KOHLER Make reference Model No.CUFF K-37316IN-4-CP OR OF EQUIVALENT MAKE AS as approved by Project-in-Charge for bar sink etc complete. | 1
Sub Total
75 | Providing & fixing 12mm thick gypsum board over existing partition for paint base including all fixing arrangement complete in all respect.
75.01 | Bathroom side premium lounge partition along Kitchen entrance above 900mm height from floor (Z-4,Z-5,Z-6, and Z-7) | 1 | 7.17 | 0.9 |  | 6.453
75.02 | Admin cabin wall (Z-48) | 1 | 2.875 | 2.82 |  | 8.1075
75.03 | Admin cabin wall (Z-50) | 1 | 0.63 | 2.82 |  | 1.7766
75.04 | Admin cabin wall (Z-51) | 1 | 2.4 | 2.82 |  | 6.768
75.05 | Admin cabin wall (Z-52) | 1 | 1.6 | 2.82 |  | 4.512
Less (-)
| Admin cabin door | -1 | 0.86 | 2.4 |  | -2.064
0
| Sub Total |  |  |  |  | 25.5531
PHASE-I (EXTRA ITEMS)
1 | Providing and fixing 12 mm thick CNC cut HDHMR jaali as per approved design and drawings finished with Duco Paint of approved shade to be cladded on HHDMR wall from adhasive complete with all accessories . | 1 | 11.6 | 0.9 |  | 10.44
| Sub Total |  |  |  |  | 10.44
2 | Providing and installation of coloured film as per aprooved design on bathroom side premium lounge area glass. | 1 | 9.18 | 2.425 |  | 22.2615
Sub Total
3 | Provding and fixing ss expansion joint cover over Exp joint on floor and wall as per required by EIC
| Sub Total |  |  |  |  | 0
4 | Providing and fixing wooden Rafter 80mm x 40 mm Size | 26 | 2.6 |  |  | 67.6
| Sub Total |  |  |  |  | 67.6
5 | Providing and fixing Foot rail at reception counter made of 50mm hollow pipe PVD coated rose gold finish as per approved design
5.01 | Reception Counter | 1 | 2.6 |  |  | 2.6
5.02 | Exicutive lounge glass partition | 1 | 5.727 |  |  | 5.727
5.03 | Air side CNC wall | 1 | 12.55 |  |  | 12.55
Sub Total
| Sub Total |  |  |  |  | 36.2243

## Structural Steel Work BOQ
STRUCTURAL STEEL WORK BOQ FOR LOUNGE ( T2 ) AT JAIPUR AIRPORT
SL | DESCRIPTION | UOM | BOQ QTY | RATE | AMOUNT | RAB-02 SUBMITTED QTY | RAB -02 SUBMITTED AMOUNT | RA-1 CHECKED QTY. | RA-1 CHECKED AMOUNT
GENERALLY
PREAMBLE NOTES
a | Not with standing Preamble Notes of the Standard Method of Measurement of Building Works, the Contractor shall refer to the Specification and Drawings for full particulars and descriptions of materials and workmanship and shall include for the full intent and meaning the thereof in the prices of the items. | Note
DRAWINGS AND OTHER DOCUMENTS
b | The scope of works includes Civil & Structure for Proposed IXE,LKO & AMD AIRPORTS(DOMESTIC CIP LOUNGE) | Note
c | The Contractor shall inspect the Technical Specifications and Drawings, visit the site and fully ascertain the nature and extent of the Works, and limitations and restrictions as to means of access, working and storage space and any other relevant factors prior to tendering as no claim of any kind shall be entertained for want of knowledge or ignorance of the conditions under which the Works will be executed. | Note
d | The Contractor shall visit the site and site inspection has been made all the cost towards access are included in the rate | Note
PRICES
e | The cost of Preliminaries is to be covered in this Contract. | Note
f | Clause headings only are given for these items and the Contractors should refer to the relevant Contract Document or Specification clause to ascertain the liability for the duration of the Contract. | Note
SPECIFIC OBLIGATIONS
g | Compliance with all statutory regulations with respect to Civil & Strucutre Contract and employment of labour including but not limited to Labour License, Workmen Compensation, ESI, Transit & storage insurance etc. | Note
h | Submission of specified sets ( hard and electronic copies ) of fabrication / construction drawings, as built drawings, operating and maintenance manuals, test certificates, spare parts lists, replacement cycle information , etc. to the Engineer's satisfaction prior to the issue of taking over certificate. | Note
i | Provision of all materials required for site safety without limiting any requirement to safety items for the Labour, Contractor, Employees. | Note
j | The Contractor shall provide adequate and competent site supervisory and administrative staffs for the proper execution of the works | Note
k | Provision, maintenance and removal of temporary office accommodation for staff, sanitation and other facilities for the workmen and staff. The facilities shall be maintained in a clean and orderly condition. | Note
l | Provision, maintenance and removal of equipment, plant and tools required for the execution of works | Note
m | The Contractor shall provide all necessary labour, plant and tools for the proper and efficient execution of the Works. | Note
n | The Client shall provide land and Contractor shall construct temporary accommodation, all transport for labour and for the movement of plant and equipment to and from site, erection, dismantling, moving about site as necessary | Note
o | Provision, maintenance and removal of temporary stores. | Note
p | Provision of suitable first-aid equipment and all medical aids. | Note
q | All the temporary buildings and other temporary facilities as provided shall be dismantled & removed and the site shall be made good within 1 week of receipt of the Engineer's instruction to remove such buildings. | Note
r | Provision, maintenance and removal of testing facilities, testing equipment and carrying out the required tests in accordance with the contract. | Note
s | Provide all consumables for the equipment till handing over including buffers as specified in the Contract / Specifications. | Note
t | Provide product guarantee / warranty as specified in the Contract / Specifications. | Note
u | Allow for all costs in connection with transport of the plant, equipment and materials to site including all transit insurances | Note
v | Allow for any costs to comply with any other specific obligation in accordance with the contract conditions. | Note
w | Mobilization, demobilization and hire of one no tower crane for nine months and four numbers of spider boom placer for nine months | Item
1 | STRUCTURAL STEEL
a | Cost of all materials, labour, equipment / tools & plants required, conveyance, infrastructure facilities required etc. at all heights and levels.
b | Work at any depth below ground level or any height above ground level and at all levels, heights & elevation and location.
c | Weight of steel will be the measured on weight basis in accordance with IS 1200, but no wastage will be considered.
d | Fabrication of the structural steel items shall be completed in all respects including all associated costs up to delivery at site.
e | Erection of fabricated items shall be carried out including lifting, placing in position, jointing and painting as specified in the Bill of Quantities. No extra cost shall be paid for temporary bracings wherever required.
f | All welding with electrodes shall be in accordance with IS specification and as approved.
g | All structural steel columns shall be shot blasted as per SSPC -SP10( Sa-2-1/2). Rate shall include the same to respective elements.
h | The rate to include the cost of all materials, labour, tools, tackles, devices and plants, wastage etc., as per specification and drawings complete
i | Rate to include shims and packing pieces. No extra on this account will be paid for and rate to include preparation of fabrication drawings for Employer / OE & PMCs approval.
j | The structural steel work shall include built up sections and girders, with gusset plates, base plates, cleats, installing inserts etc., as per drawings. Cost to include fabricating necessary Gusset Plates, Cleats, seating angles, etc., to the required size, shape, alignment etc., as per the drawings
k | 1 Coat (50 micron) of Zinc phosphate primer shall be applied at the welded joints/welded surfaces for Columns
l | Primer to be applied over all exposed surfaces of the CFT columns.
m | Quantities verified by structural consultant/Client In-charge shall be payable only.
n | Contractor to share TEKLA (or equivalent) model for review based on which quantities are estimated.
1.1 | Providing, fabricating and erecting structural steel beams, columns, shear walls, canopy, MEP services, ramps, insert plates, embedded plates, shear angles, base plates, fasteners, stud connectors etc., of readymade / built-up / rolled sections of grade upto Fy 250-450 in position at all levels and at all heights as specified in the drawings conforming to IS 226/800; The rate shall include blasting to SA 2.5 and applying one coat of primer to the CFT columns/walls & beams; main steel, fasteners and miscellaneous items; The rate shall also include the provision of tower cranes for erection as required and described elsewhere; rate is deemed to include all wastages; steel procurement price shall be considered as basic rate provided and any variation between the actual procurement price and this rate shall be paid extra; if steel is provided as free issue, the cost of such steel computed at the basic rate shall be deducted from the overall price after adjustment of rolling margins only; no adjustments shall be permitted for wastages and same shall be considered as included in the rate.
a | Fy-250 Grade MS TUBE (Rolled) | MT | 2.15 | 177674 | 381999.1 | 1.55 | 275394.7 | 0.8323 | 147878.7809
b | MS PLATE | MT | 0.09 | 216090 | 19448.1
2 | Anchoring Work
Providing, scanning, drilling and driving of various Dia and Shape Anchor rods / Anchor fastener of HILTI (Chemical anchors - RE500) including all other consumables like chemicals, foils, Grouting materials, using HILTI / Bosch make machinery, tools & plants, all accessories etc. complete at all levels as directed by the Engineer-in-charge.
a | RE 500-Hilti Anchor-10mm dia (150mm anchoring) | Nos | 96 | 720.3 | 69148.8 | 96 | 69148.8 |  | 0
b | RE 500-Hilti Anchor-16mm dia (150mm anchoring) | Nos |  | 750 | 0
| TOTAL |  |  |  | 470596 |  | 344543.5 |  | 147878.7809

## Structural Steel Work M.B
S.No. | Description | Nos | Nos | L | W | H | Qty
1 | Airside premium lounge CNC wall L-type (V) Z-37 | 21 | 21 |  | 1.19 |  | 24.99
2 | Airside premium lounge CNC wall L-type (H) Z-37 | 3 | 3 |  | 14 |  | 42
3 | Airside premium lounge Ceiling patta frame (V) Z-37A | 21 | 21 |  | 1.1 |  | 23.1
5 | Air Side Deep inside base framing (V)L-shape Z-37A |  | 13 |  | 1.1 |  | 14.3
5 | I.T Unit V(Z41, Z-42 and Z-43) | 7 | 6 |  | 4 |  | 24
6 | I.T Unit H(Z41, Z-42 and Z-43) | 8 | 8 |  | 3.67 |  | 29.36
| Sub Total | [5 empty] | 157.75
| @ Per meter kg weight | [5 empty] | 4.4
| Total Kg | [5 empty] | 694.1
7 | Second floor ducting support size 40mmx80mm |  |  | 6 |  |  | 0
8 | Front side premium lounge partition above glass framing above glass (40mmx80mmx3.2) Z-44, 45 ,46 and 47. | 1 | 1 | 18 |  |  | 102.78
9 | Runway side outer area ducting support |  | 4 | 1.8 |  |  | 35.424
| Sub Total (KG) | [5 empty] | 832.304
| Total (MT) | [5 empty] | 0.8323

## MEP SUMMARY
Project :JAI_T2_INTERNATIONAL CIP LOUNGE (SUMMARY OF COST)
Sub Head | Description |  | BOQ Amount (Rs.) | RA-1 checked Tender Amt | RA-2 checked Amended amt Amt | Total checked Amt
Part I | Electrical
A | TOTAL SUB-HEAD I carried over to Summary | Rs. | 628725.86 | 192080 | 54646.76 | 246726.76
B | TOTAL SUB-HEAD II carried over to Summary | Rs. | 232680.91 | 0
C | TOTAL SUB-HEAD III carried over to Summary | Rs. | 520056.6 | 480200 | 0 | 480200
D | TOTAL SUB-HEAD IV carried over to Summary | Rs. | 467858.86 | 266414.96 | 16518.88 | 282933.84
E | TOTAL SUB-HEAD V carried over to Summary | Rs. | 62426 | 28812 | 28812 | 57624
| TOTAL - Part I |  | 1911748.23 | 967506.96 | 99977.64 | 1067484.6
Part II | HVAC
A | TOTAL "SECTION-A" | Rs. | 813712.4 | 159596.871 | 38896.2 | 198493.071
B | TOTAL "SECTION-B" | Rs. | 806255.8 | 465794 | 86436 | 552230
| TOTAL -Part II | Rs. | 1619968.2 | 625390.871 | 125332.2 | 750723.071
Part III | PL & FF
A | WATER SUPPLY | Rs. | 60745.3 | 0 | 0 | 0
B | DRAINAGE | Rs. | 67996.32 | 33421.92 | 9604 | 43025.92
C | FIRE FIGHTING | Rs. | 337340.5 | 63866.6 | 12005 | 75871.6
| TOTAL - Part III | Rs. | 466082.12 | 97288.52 | 21609 | 118897.52
| SUB TOTAL - MEP | Rs. | 3997798.55 | 1690186.351 | 246918.84 | 1937105.191
EXTRA ITEM ELECTRICAL
EXTRA WORK HVAC WORKS
EXTRA ITEM FOR PHE
| TOTAL FOR EXTRA ITEM |  | 0
| GRAND TOTAL - MEP |  | 3997798.55 | 1690186.351 | 246918.84
Note | 1. Kitchen ventilation system does not include hood and associated arrangement. 2. Kitchen Sanitary Fixtures does not included in BOQ.

## ELECTRICAL
INTERNATIONAL CIP LOUNGE_JAI T1_ELECTRICAL
Sl No. | Description | Unit | BOQ Qty. | BOQ Rate | BOQ Amount | RAB -02 Submitted Qty | Submitted Amt | RAB -01 TENDER QTY | CHECKED RA-1 AMOUNT | RAB -02 AMD QTY | CHECKED RA-2 AMD AMOUNT
Part I | ELECTRICAL
A | SUB HEAD I - WIRING
1.1 | Wiring for primary light points for Switch controlled points with 2.5 sq. mm LSZH PVC insulated stranded /multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia FRLSH PVC surface /concealed conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting, and including the cost of Supply and fixing a 6 amp 240 Volt grid plate mounted switch with moulded cover plate in zinc chromate passivated GI box and including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. | nos | 12 | 1920.8 | 23049.6 | 10 | 19208 | 10 | 19208
1.2 | Wiring for primary light points for DB / Dimmer/ Sensor/ Automation controlled points with 2.5 sq. mm LSZH PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia FRLSH PVC surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item)(Normal) | nos | 2 | 2401 | 4802 | 2 | 4802 | 2 | 4802
1.3 | Wiring for primary light points for DB/ Dimmer/ Sensor/ Automation controlled points with 2.5 sq. mm LSZH PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia FRLSH PVC surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item). (Emergency) | nos | 2 | 2401 | 4802 | 3 | 7203 | 2 | 4802 | 1 | 2401
1.4 | Wiring for secondary light points with 2.5 sq. mm LSZH PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia FRLSH PVC conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Normal) | nos | 34 | 960.4 | 32653.6 | 42 | 40336.8 | 34 | 32653.6 | 8 | 7683.2
1.5 | Wiring for secondary light points with 2.5 sq. mm LSZH PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia FRLSH PVC conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Emergency) | nos | 12 | 960.4 | 11524.8 | 12 | 11524.8 | 12 | 11524.8
1.6 | Wiring for 240 volt 6 amp Multistandard single phase and neutral switch socket outlet with 4.0 sq. mm LSZH PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia FRLSH PVC surface/concealed conduit including cost of providing circuit wiring with 4.0 sq mm LSZH PVC insulated stranded/ multistranded copper conductor 1100 volt grade wires and including the cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and Supply and fixing of a 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 4.0 sq. mm LSZH PVC insulated copper earth wire conductor wires complete as directions of Engineer-in-charge and as required. | nos | 7 | 2881.2 | 20168.4 | 7 | 20168.4 | 7 | 20168.4
1.7 | Wiring as in Item 1.6 above looped from an adjacent switch socket outlet as required and Supply and fixing of a combined 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 4.0 sq. mm LSZH PVC insulated copper earth wire conductor wires complete as directions of Engineer-in-charge and as required. | nos | R/o | 1920.8 |  | 11 | 21128.8 | 0 | 0
1.8 | Wiring for a multi-pin 240 volt 6-13 amp single phase and neutral universal switch socket outlet with 4.0 sq. mm LSZH PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia LSZH PVC surface/concealed conduit including the cost of providing circuit wiring with 4.0 sq mm LSZH PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a combined multi-pin 240 volt 6-13 amp universal socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed galvanized box and including earthing of the 3rd pin with 4.0 sq mm 1100 volt grade LSZH PVC insulated stranded copper conductor wires complete as directions of Engineer-in-charge and as required. | nos | 18 | 2881.2 | 51861.6 | 10 | 28812 | 10 | 28812
1.9 | Wiring as in Item 1.8 above looped from an adjacent switch socket outlet as per specifications and directions of Engineer-in-charge and providing and fixing of a modular type multi-pin 240 Volt 6-13 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole rocker type switch in a recessed galvanized boxes with internal wiring and moulded front plates complete as directions of Engineer-in-charge and as required. | nos | 2 | 1920.8 | 3841.6 | 12 | 23049.6 | 2 | 3841.6 | 10 | 19208
1.1 | Supply , Installation, Testing and comissioning of IP 66 EGA Boxes with all standard accessories consisting of following: a) 3nos 6-13 amp socket with single Switch b) 2nos Data outlets with includes of Data wiring and terminations. Wiring for socket outlet with 4.0 sq. mm LSZH PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia LSZH PVC surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 4.0 sq mm LSZH PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a EGA Box complete as directions of Engineer-in-charge and as required. | nos | 13 | 7683.2 | 99881.6 | - |  | -
1.11 | Wiring for 6 pin 240 volt 16 amp single phase and neutral Universal switch socket outlets with 4.0 sq. mm LSZH PVC insulated stranded/multi stranded copper conductor 1100 volt grade wires in IS embossed 25mm dia FRLSH PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including Supply and fixing of a 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switch with moulded cover plate in a recessed zinc chromate passivated GI box including earthing of the 3rd pin with 4.0 sq. mm 1100 volt grade LSZH PVC insulated stranded copper earth wire complete as directions of Engineer-in-charge and as required. | Nos. | 2 | 2881.2 | 5762.4 | 2 | 5762.4 | 2 | 5762.4
1.12 | Wiring for 25 amp SPN isolator for Geyser with 4.0 sq. mm LSZH PVC insulated standed/multi stranded copper conductor 1100 volt grade wires in PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including providing and fixing of a 25 amp terminal block in recessed GI box with conduit Bend out for connection to equipment including earthing with 2 nos 4.0 sq mm 1100 volt grade PVC insulated FRLS multistranded copper conductor wire complete as directions of Engineer-in-charge and as required. | Nos. | 1 | 4802 | 4802 | 1 | 4802 | 0 | 0
1.13 | Wiring for 25 amp TPN isolator for HVAC Fan & Scrubber with 4.0 sq. mm LSZH PVC insulated standed/multi stranded copper conductor 1100 volt grade wires in PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including providing and fixing of a 25 amp terminal block in recessed GI box with conduit Bend out for connection to equipment including earthing with 2 nos 4.0 sq mm 1100 volt grade PVC insulated FRLS multistranded copper conductor wire complete as directions of Engineer-in-charge and as required. | Nos. | 2 | 6242.6 | 12485.2 | 2 | 12485.2 | 0 | 0
1.14 | Wiring for a multi-pin 240 volt 5/15 amp single phase and neutral universal switch socket outlet with 4.0 sq. mm LSZH PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia LSZH PVC surface/concealed conduit including the cost of providing circuit wiring with 4.0 sq mm LSZH PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a combined multi-pin 240 volt 5/15 amp universal socket outlet with safety shutters and 15 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed galvanized box and including earthing of the 3rd pin with 4.0 sq mm 1100 volt grade LSZH PVC insulated stranded copper conductor wires complete as directions of Engineer-in-charge and as required. | Nos. | 15 | 3169.32 | 47539.8 | 23 | 72894.36 | 15 | 47539.8 | 8 | 25354.56
1.15 | Wiring for 32 amp SPN isolator for Kitchen Equipments with 4.0 sq. mm LSZH PVC insulated standed/multi stranded copper conductor 1100 volt grade wires in PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including providing and fixing of a 32 amp terminal block in recessed GI box with conduit Bend out for connection to equipment including earthing with 2 nos 4.0 sq mm 1100 volt grade PVC insulated FRLS multistranded copper conductor wire complete as directions of Engineer-in-charge and as required. | Nos. | 3 | 4321.8 | 12965.4 | 3 | 12965.4 | 3 | 12965.4
1.16 | Wiring for 32 amp Three phase 5Pole industrial socket outlets with 6.0 sq mm FRLS PVC insulated 1100 volt grade stranded copper conductor wires in 25 mm dia FRLS PVC surface/concealed conduit including cost of providing brackets, saddles etc as per specifications and directions of Engineer-in-charge for surface conduiting and/or cost of cutting and filling chases and including the cost of supplying and fixing 32 amp 10 kA TPN MCB, industrial type socket outlet in galvanized box, industrial plug top and including the cost of loop earthing with 6.0 sq mm FRLS PVC insulated copper conductor wires complete as per specifications and directions of Engineer-in-charge.(MCB shall be 'B' Curve) | Nos. | 1 | 5282.2 | 5282.2 | 1 | 5282.2 | 0 | 0
1.17 | Wiring for 32 amp TPN isolator for Kitchen with 6.0 sq. mm LSZH PVC insulated standed/multi stranded copper conductor 1100 volt grade wires in PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including providing and fixing of a 32 amp terminal block in recessed GI box with conduit Bend out for connection to equipment including earthing with 2 nos 4.0 sq mm 1100 volt grade PVC insulated FRLS multistranded copper conductor wire complete as directions of Engineer-in-charge and as required. | Nos. | 4 | 7683.2 | 30732.8 | 4 | 30732.8 | 0 | 0
|  |  |  | 0 |  |  | 0 |  | 0
1.18 | Providing and fixing of a Data outlet plate mounted outlet unit (RJ-45) with moulded cover plate in recessed zinc chromate passivated MS box complete as directions of Engineer-in-charge and as required for Data system. | nos | 22 | 768.32 | 16903.04 | 16 | 12293.12 | 0 | 0
1.19 | Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair computer cable with 24 AWG solid copper conductors in surface/concealed conduit/raceways/modular furniture , complete as directions of Engineer-in-charge and as required. | Mtrs | 250 | 72.03 | 18007.5 | 387.8 | 27933.234 | 0 | 0
1.2 | Supplying, Installation, testing and commissioning of 6U Networking Rack with all accessories and complete as required | nos | 1 | 9604 | 9604 | 1 | 9604 | 0 | 0
1.21 | Supplying, Installation, testing and commissioning of Occupancy Sensor for light control with all accessories and complete as directions of Engineer-in-charge and as required. | nos | 1 | 5282.2 | 5282.2 | 1 | 5282.2 | 0 | 0
1.22 | Supplying and drawing wiring with single core stranded copper conductor PVC insulated 1100 volt grade LSZH PVC insulated wires in existing conduit systems including the cost of running copper conductor LSZH PVC insulated loop earthing wire complete as directions of Engineer-in-charge and as required as below. | [5 empty] | 0
a) | 2 x 1.5 sq mm with 1 x 1.5 sq mm earth wire | Mtrs | R/o | 72.03 |  |  | 0 |  | 0
a) | 2 x 2.5 sq mm with 1 x 2.5 sq mm earth wire | Mtrs | R/o | 124.852 |  |  | 0 |  | 0
b) | 2 x 4 sq mm with 1 x 4.0 sq mm earth wire | Mtrs | R/o | 216.09 |  |  | 0 |  | 0
c) | 2 x 6 sq mm with 1 x 6.0 sq mm earth wire | Mtrs | 20 | 297.724 | 5954.48 |  | 0 |  | 0
d) | 2 x 10 sq mm with 1 x 10 sq mm earth wire | Mtrs | R/o | 480.2 |  |  | 0 |  | 0
e) | 4 x 2.5 sq mm with 2 x 2.5 sq mm earth wire | Mtrs | R/o | 244.902 |  |  | 0 |  | 0
f) | 4 x 4 sq mm with 2 x 4.0 sq mm earth wire | Mtrs | 60 | 384.16 | 23049.6 |  | 0 |  | 0
g) | 4 x 6 sq mm with 2 x 6.0 sq mm earth wire | Mtrs | 60 | 585.844 | 35150.64 |  | 0 |  | 0
h) | 4 x 10 sq mm with 2 x 10 sq mm earth wire | Mtrs | 50 | 960.4 | 48020 |  | 0 |  | 0
i) | 4 x 16 sq mm with 2 x 16 sq mm earth wire | Mtrs | R/o | 1555.848 |  |  | 0 |  | 0
i) | 4 x 25 sq mm with 2 x 25 sq mm earth wire | Mtrs | R/o | 2401 |  |  | 0 |  | 0
1.23 | Supplying and drawing recessed/surface IS embossed GI conduiting system including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer-in-charge and as required as below. | [5 empty] | 0
a) | 25 mm 16 SWG | Mtrs | 50 | 216.09 | 10804.5 | 39.56 | 8548.5204 | 0 | 0
b) | 32 mm 14 SWG | Mtrs | 50 | 288.12 | 14406 |  | 0 |  | 0
c) | 40 mm 14 SWG | Mtrs | 100 | 432.18 | 43218 |  | 0 |  | 0
d) | 50 mm 14 SWG | Mtrs | R/o | 624.26 |  |  | 0 |  | 0
1.24 | Supply and fixing GI flexible conduit including all fittings complete as required as below. |  |  | 0 |  |  | 0 |  | 0
a) | 20 mm 16 SWG | Mtrs | R/o | 96.04 |  |  | 0 |  | 0
b) | 25 mm 16 SWG | Mtrs | 50 | 120.05 | 6002.5 | 88 | 10564.4 | 0 | 0
c) | 32 mm 14 SWG | Mtrs | 60 | 144.06 | 8643.6 |  | 0 |  | 0
d) | 40 mm 14 SWG | Mtrs | 60 | 192.08 | 11524.8 |  | 0 |  | 0
e) | 50 mm 14 SWG | Mtrs | R/o | 288.12 |  |  | 0 |  | 0
[7 empty] | 0 |  | 0
| TOTAL SUB-HEAD I carried over to Summary |  |  |  | 628725.86 |  | 395383.2344 |  | 192080 |  | 54646.76
0
B | SUB HEAD-II- CABLES & RACEWAYS
1 | Supplying, laying, connecting ,terminating on both side testing & commissioning of following size of 1.1 kv grade single/multicore aluminium conductor XLPE insulated and PVC sheathed armoured cable as per IS: 7098:1988 (Part-I) with upto date amendments. | [5 empty] | 0
a) | 3.5 core 50 Sq mm | Mtrs | 25 | 648.27 | 16206.75 |  | 0 |  | 0
2 | Cable end termination of the following XLPE insulated and PVC sheathed aluminium conductor cable 1100 Volt grade including cost of crimping heavy duty copper lugs,nickel plated brass double compression glands,insulation tape and all requisite material for completion of termination complete as required and as below. | [5 empty] | 0
a) | 3.5 core 50 Sq mm | Nos | 2 | 960.4 | 1920.8 |  | 0 |  | 0
3 | Supplying, laying, connecting ,terminating on both side testing & commissioning of following size of 1.1 kv grade single/multicore copper conductor XLPE insulated and PVC sheathed armoured cable as per IS: 7098:1988 (Part-I) with upto date amendments. | [5 empty] | 0
a) | 4 core 4 Sq mm | Mtrs | R/o | 432.18 |  | 79.6 | 34401.528 | 0 | 0
b | 4 core 6 Sq mm | Mtrs | R/o | 624.26 |  | 51.8 | 32336.668 | 0 | 0
c | 4 core 10 Sq mm | Mtrs | R/o | 1056.44 |  | 10.3 | 10881.332 | 0 | 0
4 | Cable end termination of the following XLPE insulated and PVC sheathed copper conductor cable 1100 Volt grade including cost of crimping heavy duty copper lugs,nickel plated brass double compression glands,insulation tape and all requisite material for completion of termination complete as required and as below. | [5 empty] | 0
a) | 4 core 4 Sq mm | Nos | R/o | 768.32 |  | 4 | 3073.28 | 0 | 0
b | 4 core 6 Sq mm | Nos | R/o | 960.4 |  | 6 | 5762.4 | 0 | 0
c | 4 core 10 Sq mm | Nos | R/o | 1440.6 |  | 2 | 2881.2 | 0 | 0
5 | Supply and fixing of perforated sheet steel slotted cable trays with vertical sides on both ends as per approved design and GI angle supports spaced 1000 mm apart throughout the length as specified, including the cost of 1 meter GI rod hangers, hooks, dash fasteners, painting etc. for suspension from ceiling complete as required. | [5 empty] | 0
a) | 150 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cover | Mtrs | 100 | 1296.54 | 129654 | 2.5 | 3241.35 | 0 | 0
0
| GI Raceway & Junction boxes (IP 55) | [5 empty] | 0
4 | Supply, assembly and laying of under floor trunking made out of minimum 1.6mm thick pre galavised sheet with enamel paint finish complete with jointing sleeve, horizontal bends, vertical bends, level adjustment components and closer, vertical elbow, covers, access outlet. etc. complete with all other accessories under floor installation including cutting and chasing the floor/ or on surface, making good the same, placing in position and cleaning from inside complete etc. as required. | [5 empty] | 0
a) | 100 mm x 40 mm (3 compartment)- 1 For Power, 1 for Data, 1 blank for seperation ) | Mtrs | 20 | 1440.6 | 28812 |  | 0 |  | 0
b) | 75 mm x 40 mm (3 compartment)- 1 For Power, 1 for Data, 1 blank for seperation ) | Mtrs | 20 | 1200.5 | 24010 |  | 0 |  | 0
c) | 75 mm x 40 mm (1 compartment)- For Power | Mtrs | 20 | 960.4 | 19208 |  | 0 |  | 0
d) | 50 mm x 40 mm (1 compartment) for Data | Mtrs | 5 | 864.36 | 4321.8 |  | 0 |  | 0
e) | Providing and fixing 150 x 150 x 50 mm deep junction box | Nos | 3 | 960.4 | 2881.2 |  | 0 |  | 0
f) | Providing and fixing 100 x 100 x 50 mm deep junction box | Nos | 3 | 768.32 | 2304.96 | 22 | 16903.04 | 0 | 0
g) | Providing and fixing 75 x 75 x 50 mm deep junction box | Nos | 5 | 672.28 | 3361.4 |  | 0 |  | 0
0
| TOTAL SUB-HEAD II carried over to Summary |  |  |  | 232680.91 |  | 109480.798 |  | 0 |  | 0
0
C | SUB HEAD III - DISTRIBUTION SYSTEM & EARTHING
0
1 | Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof distribution boards constructed from 1.2mm sheet steel IP 42 construction, finished with rust proof red oxide coating and two coats of paint with hinged gasketted door and housing the following complete with suitably rated PVC insulated copper busbars with interconnections and neutral bar assembly, earthing terminals complete as approved by Architects. Padlocking facility shall be provided on the door. | [5 empty] | 0
a) | 10 WAY TPN - Power DB | nos | 1 | 33614 | 33614 | 1 | 33614 | 1 | 33614
| 1-40 amp TPN 10 kA MCB with thermal magnetic protective releases incoming with 3 single phase banks each comprising of 1-40 amp DP 30 mA RCCB incoming and 30 nos 6/16/20/25/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings. | [5 empty] | 0 |  | 0
b) | 6 WAY TPN - Lighting DB | nos | 1 | 28812 | 28812 | 1 | 28812 | 1 | 28812
| 1-32 amp TPN 10 kA MCB with thermal magnetic protective releases incoming with 3 single phase banks each comprising of 1-32 amp DP 30 mA RCCB incoming and 18 nos 6/16/20/25/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings. |  |  | 0 |  |  | 0 |  | 0
c) | 6 WAY TPN - Kitchen DB | nos | 1 | 28812 | 28812 | 0 | 0 | 0 | 0
| 1-63 amp TPN 10 kA MCB with thermal magnetic protective releases incoming with 3 single phase banks each comprising of 1-63 amp DP 30 mA RCCB incoming and 18 nos 6/16/20/25/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings. |  |  | 0 |  |  | 0 |  | 0
d) | 12 WAY SPN | nos | 1 | 9604 | 9604 | 1 | 9604 | 1 | 9604
| 1-32 amp DP 10 kA MCB with thermal magnetic protective releases incoming with single phase banks comprising of 1-32 amp DP 30 mA RCCB incoming and 12 nos 6/10/16/20/25/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings. | [5 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
2 | Design, Manufacture, Supply, delivery and coordination for Installation of the following front operated modular compartmentalised construction cubicle type, front access, dead back, 2mm thick steel enclosed free standing on leg at 400mm above from FFL / wall mounted, dust and vermin proof, switchboard with IP67/Specified protection with hinged and lockable doors duly powder coated complete with interconnections, tinned copper crimping lugs, bonding to earth and painting, suitable for use at 415 volts, 3 phase 4 wire 50 Hertz system, and to withstand a symetrical fault level of 25 kA | [5 empty] | 0 |  | 0
| All Switchboards shall have provision for entry of cables from the top or bottom as required. | [5 empty] | 0 |  | 0
| All live accessible parts shall be shrouded and all equipment shall be finger touch proof. The Busbars insulation shall be with heat shrinkable sleeves. SMC/DMC shrouds and busbar supports shall be used. Padlocking facility shall be provided on all outgoing feeders doors and switch handles shall be lockable in OFF position | [5 empty] | 0 |  | 0
| All kA values indicated shall be Ics breaking capacity. | [5 empty] | 0 |  | 0
| All MCCB above 250 amp shall have variable settings. | [5 empty] | 0 |  | 0
| The cost shall include providing and fixing of 75 x 50 x 6 mm channels for switchboard support. | [5 empty] | 0 |  | 0
| All MCCB shall have rotary handles & extension terminal, phase barrier on both sides as required at site. | [5 empty] | 0 |  | 0
| All metering panel shall be extendable type with cable alley. | [5 empty] | 0 |  | 0
| GA drawings shall be got approved from Owners/ Architects/ Consultants before fabrication. | [5 empty] | 0 |  | 0
| Note:- The Manufacturer/Supplier shall supervise the installation, testing and commissioning of the cubicle panels by the electrical contractor | [5 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
A | INCOMING - In Kitchen | [5 empty] | 0 |  | 0
| 1 no 125 A 4POLE MCCB | [5 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
| INDICATING PANEL | [5 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
| The incomers shall have the following indicating panel | [5 empty] | 0 |  | 0
a) | 3 nos Cast resin current transformers of 125/5 ratio Class 1.0 for metering | [5 empty] | 0 |  | 0
b) | 1 no Multi function meter | [5 empty] | 0 |  | 0
c) | 1 set of three White phase indicating lamps | [5 empty] | 0 |  | 0
d) | Red / Green ON/OFF indicator (LED type) | [5 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
| BUSBAR | [5 empty] | 0 |  | 0
| Electrolytic high conductivity aluminium TPN busbars rated at 160 amps suitable to with stand symmetrical fault level of 25kA at 415 volts. The neutral busbar is to be of 100% capacity. | [5 empty] | 0
[7 empty] | 0 |  | 0
| OUTGOING UNITS | [5 empty] | 0 |  | 0
| 1 nos 63 amp 4P 10 kA MCB with thermal magnetic protective releases | [5 empty] | 0 |  | 0
| 1 nos 40 amp 4P 10 kA MCB with thermal magnetic protective releases | [5 empty] | 0 |  | 0
| 8 nos 32 amp 4P 10 kA MCB with thermal magnetic protective releases | [5 empty] | 0 |  | 0
| 3 nos 25 amp 4P 10 kA MCB with thermal magnetic protective releases | [5 empty] | 0 |  | 0
| 1 nos 32 amp DP 10 kA MCB with thermal magnetic protective releases | [5 empty] | 0 |  | 0
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required | nos | 1 | 168070 | 168070 | 1 | 168070 | 1 | 168070
[7 empty] | 0 |  | 0
| UPS 5KVA | [5 empty] | 0 |  | 0
3 | Supply, installation, testing and commissioning of 5kVA UPS system comprising of online units with a battery backup of 30 minutes duration for full load and with all standards fittings, accessories, protection, instruments, indications and controls including but not restricted to transformer, rectifier, inverter, SMF battery with float cum boost battery charger, static bypass switch, maintenance bypass, interconnections etc. The UPS shall be suitble for single phase Input and output supply of 230V. The UPS shall have 2 body earthing connection which shall be looped with existing earting system. | nos | 1 | 240100 | 240100 | 1 | 240100 | 1 | 240100
4 | Supplying and laying of the following earthing strip on cable tray/ wall clamped to wall with suitable clamps saddles and fixing bolts/soldering /riveting in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All joints shall be timed. | [5 empty] | 0 |  | 0
a) | 32 mm x 6 mm GI strip | Mtrs | R/o |  |  |  | 0 |  | 0
b) | 25 mm x 3 mm GI strip | Mtrs | 30 | 144.06 | 4321.8 |  | 0 |  | 0
c) | 6 SWG GI Wire | Mtrs | R/o | 72.03 |  |  | 0 |  | 0
d) | 8 SWG GI Wire | Mtrs | R/o | 62.426 |  | 25 | 1560.65 | 0 | 0
e) | 4 Sqmm bare, tinned-copper stranded conductor | Mtrs | 100 | 67.228 | 6722.8 |  | 0 |  | 0
| TOTAL SUB-HEAD III carried over to Summary |  |  |  | 520056.6 |  | 481760.65 |  | 480200 |  | 0
0
D | SUB HEAD IV - FIRE DETECTION & PA SYSTEM
[7 empty] | 0 |  | 0
| Fire Detection System | [5 empty] | 0 |  | 0
1 | Supply, installation, testing and commissioning of 1 Loop wall recess mounting microprocessor based networkable analogue addressable Fire Control Panel having a Fire Alarm Capability of 100/125/150 detectors/devices per loop with each loops length being restricted to 80% of manufacturer specified maximum loop length). The Fire control panel shall have 100% hot redundancy for CPU, load etc. It shall be expandable by minimum 1 additional loops. The operating panel shall have minimum 80 character LCD display, 4 access levels, 1000 events historical logging, flash E-PROM, 240 volts ac power supply, automatic battery charger, 24V sealed lead-acid battery suitable operating the system for 24 hours in emergency condition. The Panel shall be Integrated with the PA System and with suitable power amplifiers for the hooter/strobes. | [5 empty] | 0 |  | 0
| The Panel shall be Integrated with the BMS System and shall include cost of supply of any additional modules, software and interfaces as required for the same and as required by the Client. The Panel shall provide either or all BACNET/RS485/ LON/MODBUS protocols as required. The panel shall be complete as per specifications and as required. | [5 empty] | 0 |  | 0
a) | 1 Loop | nos | 1 | 144060 | 144060 | 1 | 144060 | 1 | 144060
2 | Supply, installation, testing and commissioning of plug-in type intelligent analogue addressable multi criteria photo electric cum Smoke detectors including the cost of base plate, 75 mm dia M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. | nos | 23 | 3361.4 | 77312.2 | 25 | 84035 | 23 | 77312.2 | 2 | 6722.8
3 | Supply, installation, testing and commissioning of plug-in type intelligent analogue addressable rate of rise cum fixed temperature Heat detectors including the cost of base plate, 75 mm dia M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. | nos | 1 | 3361.4 | 3361.4 | 2 | 6722.8 | 1 | 3361.4 | 1 | 3361.4
4 | Supply, installation, testing and commissioning of Addressable type fault for isolating shorted, dewired and loose circuits between two successive fault isolators with automatic resetting arrangement (base Model) | nos | R/o | 4802 |  |  | 0 |  | 0
5 | Supply, installation, testing and commissioning of Addressable type Response indicatior. | nos | 12 | 672.28 | 8067.36 | 13 | 8739.64 | 12 | 8067.36 | 1 | 672.28
6 | Supply, installation, testing and commissioning of intelligent analogue addressable Control Modules including the cost of 75 mm dia MS outlet box for fixing of the module, mounting accessories complete as per specifications and as required. | nos | 3 | 4802 | 14406 | 3 | 14406 | 0 | 0
7 | Supply, installation, testing and commissioning of intelligent analogue addressable dry contact Monitor Modules including the cost of 75 mm dia MS outlet box for fixing of the module, mounting accessories complete as per specifications and as required. | nos | R/o | 5762.4 |  | 0 | 0 | 0 | 0
8 | Supply, installation, testing and commissioning of recess/surface mounting dust and vermin proof intelligent addressable analogue Manual Pull stations including cost of all required modules, mounting accessories etc including the cost of M.S. outlet box for fixing of the station, mounting accessories etc. complete as per specifications and as required. | nos | 1 | 7203 | 7203 | 1 | 7203 | 1 | 7203
9 | Supply, Installation, Testing and commissioning of high intensity hooters cum Strobe Lights with 110 cd. The strobes shall be synchronized for better evacuation. | nos | 1 | 6242.6 | 6242.6 | 1 | 6242.6 | 1 | 6242.6
10 | Supply, laying, testing and commissioning of 2 core 1.5 sqmm copper conductor fire survival cable 1100 volt wires in FRLS PVC embossed black enameled 25mm dia recessed and/or surface conduiting system including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting as required and including the cost of crimped termination's complete as required. (For FACP & PA system) | Mtrs | 650 | 216.09 | 140458.5 | 296.1 | 63984.249 | 0 | 0
11 | Supplying and fixing heavy gauge ISI embossed black enameled FRLSH PVC recessed and/or surface conduits including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting complete as per specifications, as required and as below. |  |  | 0 |  |  | 0 |  | 0
a) | 25 mm Dia FRLSH PVC | Mtrs | 85 | 96.04 | 8163.4 |  | 0 |  | 0
|  |  |  | 0 |  |  | 0 |  | 0
| Public Address system |  |  | 0 |  |  | 0 |  | 0
1 | Supply, installation, testing and commissioning of recess/ surface mounting 2W CEILING SPEAKER ,metal grille, dia 150mm and Spring clamps suitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required. (MAKE HONEYWELL) | nos | 9 | 1440.6 | 12965.4 | 13 | 18727.8 | 9 | 12965.4 | 4 | 5762.4
2 | Supply, installation, testing and commissioning of Wall surface mounting 2W CEILING SPEAKER with 6W/3W optionssuitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required. | nos | R/o | 2401 |  | 1 | 2401 | 0 | 0
3 | Digital PA System Supply, installation, testing and commissioning of MS Amplifier Rack Assembly with 30 minutes power backup including 1 no. CD player unit, 1 nos 300 W POWER AMPLIFIER, connectors, internal wiring, interconnection etc capable of voice operated priority complete as required. (PA System fully integrated type with Fire Alarm System with facility for automatic override of music for emergency announcements) ( MAKE HONEYWELL) | nos | 1 | 19208 | 19208 | 1 | 19208 | 0 | 0
4 | Supply, installation, testing and commissioning of CONTROL PANEL with single zone selection, ascending 4 tone chime, emergency microphone, expandable upto 5 zones using expansion control panel complete as required. (MAKE HONEYWELL) | nos | 1 | 9604 | 9604 | 1 | 9604 | 0 | 0
5 | Supply, installation, testing and commissioning of Wireless lepal microphone DB technology complete as required | nos | 1 | 9604 | 9604 | 1 | 9604 | 0 | 0
6 | Supply, installation, testing and commissioning of Microphone with table stand | nos | 1 | 7203 | 7203 | 1 | 7203 | 1 | 7203
[7 empty] | 0 |  | 0
| TOTAL SUB-HEAD IV carried over to Summary |  |  |  | 467858.86 |  | 402141.089 |  | 266414.96 |  | 16518.88
0
E | SUB HEAD V - CCTV SYSTEM
0
1 | Design, Engineering, Supply, Receiving, handling, storage, installation, testing and commissioning of the CLOSED CIRCUIT TELEVESION (CCTV) SURVEILLANCE SYSTEM with IP based indoor type fixed varifocal dome camera 2MP with resolution 1920x1080, IP67 with 30m IR range for the proposed application with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation. MAKE CP PLUS | nos | 6 | 4802 | 28812 | 12 | 57624 | 6 | 28812 | 6 | 28812
2 | Supply of Network Video/Disk Recorder -16 channel (Including HDD for minimum recording of 30 days) with minimum 500GB Usable Space with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation. (6TB HDD TO BE USED DUE TO INCREASE IN CAMERA QTY) | nos | 1 | 19208 | 19208 | 1 | 19208 | 0 | 0
3 | Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair with 24 AWG solid copper conductors in surface/concealed conduit/raceways complete as required | Mtrs | 200 | 72.03 | 14406 | 224.2 | 16149.126 | 0 | 0
0
| TOTAL SUB-HEAD V carried over to Summary |  |  |  | 62426 |  | 92981.126 |  | 28812 |  | 28812
0
| Grand Total Amount | [5 empty] | 1481746.8974 |  | 967506.96 |  | 99977.64
0
| EXTRA NON TENDER ITEMS |  |  | NT RATES |  |  | NT AMT
4 | 16 POE system | Nos |  | 15000 |  | 1 | 15000
5 | SFF convertor | Nos |  | 3000 |  | 1 | 3000
6 | Media convertor | Nos |  | 5900 |  | 1 | 5900
7 | CCTV monitor and stand | Nos |  | 18500 |  | 1 | 18500
8 | Providing and fixing energy meter on terrece along scrubber and LT panel | Nos |  | 8000 |  | 2 | 16000
0
A | Supply & wiring of general power point with 2X4+2.5 Sq.mm PVC insulated multistranded copper conductor cable (FRLS) in surface/recess MS/PVC conduit including cutting the chases in wall & making good the same including providing & fixing of M.S. Switch & o modular range 1 No,s 6Amp Socket with 2M USB Charger port input 240v ,50Hz,/500mA, Out put 5V=3000ma modular cover plate, etc. complete as required. (First point)Supply of MS/PVC conduit included in this item. |  |  | 4500 |  | 15 | 67500 | 0
0
a) | Supply & wiring of general power point with 2X4+2.5 Sq.mm PVC insulated multistranded copper conductor cable (FRLHS) in surface/recess MS/PVC conduit including cutting the chases in wall & making good the same including providing & fixing of M.S. Switch & o modular range 1 No,s 6Amp Socket with 2M USB Charger port input 240v ,50Hz,/500mA, Out put 5V=3000ma modular cover plate, etc. complete as required. (Secondary loop point)Supply of MS/PVC conduit included in this item. |  |  | 4000 |  | 7 | 28000 | 0
0
B | Supply & wiring of general power point with 2X4+2.5 Sq.mm PVC insulated multistranded copper conductor cable (FRLHS) in surface/recess MS/PVC conduit including cutting the chases in wall & making good the same including providing & fixing of M.S. Switch & o modular range 2No,s 6Amp switch with 3 pin 6Amp socket, modular cover plate, etc. complete as required. (First point)Supply of MS/PVC conduit included in this item. |  |  | 3000 |  | 6 | 18000 | 0
0
b) | Supply & wiring of general power point with 2X4+2.5 Sq.mm PVC insulated multistranded copper conductor cable (FRLHS) in surface/recess MS/PVC conduit including cutting the chases in wall & making good the same including providing & fixing of M.S. Switch & o modular range 2No,s 6Amp switch with 3 pin 6Amp socket, modular cover plate, etc. complete as required. (Secondary loop point)Supply of MS/PVC conduit included in this item. |  |  | 2300 |  | 6 | 13800 | 0
0
C | Supplying and fixing heavy gauge ISI embossed black enameled FRLSH GI recessed and/or surface conduits including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting complete as per specifications, as required and as below. |  |  | 225 |  | 336.8 | 75780 | 0
0
D | Supply & installation of GI Earth Bus of size 50 x 6 x 300 mm long with insulator support for earth bus |  |  | 1800 |  | 1 | 1800 | 0
| TOTAL | [5 empty] | 263280 |  |  |  | 0

## MB ELELCTRICAL
S.NO. | Service Code | Description | Unit | No,s | L | B | H | Total
MEASUREMENTS
1 | Part I | ELECTRICAL
2 | A | SUB HEAD I - WIRING
3 | 1.1 | Wiring for primary light points for Switch controlled points with 2.5 sq. mm LSZH PVC insulated stranded /multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia FRLSH PVC surface /concealed conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting, and including the cost of Supply and fixing a 6 amp 240 Volt grid plate mounted switch with moulded cover plate in zinc chromate passivated GI box and including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. | No,s
LDB (LIGHT DB)
4 |  | PWR LAY,2x2.5+1.5sqmm Primary ckt
5 |  | LDB-R1 To L1 | No,s | 1 |  |  |  | 1
6 |  | LDB-R2 To L1 | No,s | 1 |  |  |  | 1
7 |  | LDB-R3 To L1 | No,s | 1 |  |  |  | 1
8 |  | LDB-Y1 To L1 | No,s | 1 |  |  |  | 1
9 |  | LDB-Y2 To L1 | No,s | 1 |  |  |  | 1
10 |  | LDB-Y3 To L1 | No,s | 1 |  |  |  | 1
11 |  | LDB-B1 To L1 | No,s | 1 |  |  |  | 1
12 |  | LDB-B2 To L1 | No,s | 1 |  |  |  | 1
13 |  | LDB-B3 To L1 | No,s | 1 |  |  |  | 1
|  | LDB-B4 To L1 | No,s | 1 |  |  |  | 1
18 |  | Sub Total | [5 empty] | 10
29 | 1.2 | Wiring for primary light points for DB / Dimmer/ Sensor/ Automation controlled points with 2.5 sq. mm LSZH PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia FRLSH PVC surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item)(Normal) | nos
|  | LDB-R4 To Admin area Senor light | No,s | 1 |  |  |  | 1
|  | LDB-Y4 To Admin Fixture light | No,s | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 2
30 | 1.3 | Wiring for primary light points for DB/ Dimmer/ Sensor/ Automation controlled points with 2.5 sq. mm LSZH PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia FRLSH PVC surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item). (Emergency) | nos
EDB( INDICATE EMERGENCY LIGHT DB)
|  | EDB-C1 To EL1 | No,s | 1 |  |  |  | 1
|  | EDB-C2 To EL1 | No,s | 1 |  |  |  | 1
|  | EDB-C3 TO EL1 | No,s | 1 |  |  |  | 1
|  | CHEKED Sub Total | [5 empty] | 3
|  | TENDER QTY | [5 empty] | 2
|  | AMENDED QTY | [5 empty] | 1
|  | TOTAL | [5 empty] | 3
31 | 1.4 | Wiring for secondary light points with 2.5 sq. mm LSZH PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia FRLSH PVC conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Normal) | nos
LDB-R1 Secondary loop point
|  | Primary L1 TO Secondary L1 | No,s | 1 |  |  |  | 1
|  | L1 TO L2 | No,s | 1 |  |  |  | 1
|  | L2 TO L3 | No,s | 1 |  |  |  | 1
|  | L3 TO L4 | No,s | 1 |  |  |  | 1
|  | L4 TO L5 | No,s | 1 |  |  |  | 1
|  | LDB-R2 Secondary loop point | [5 empty] | 5
|  | Primary L1 TO Secondary L1 | No,s | 1 |  |  |  | 1
|  | L1 TO L2 | No,s | 1 |  |  |  | 1
|  | L2 TO L3 | No,s | 1 |  |  |  | 1
|  | L3 TO L4 | No,s | 1 |  |  |  | 1
|  | L4 TO L5 LED Strip | No,s | 1 |  |  |  | 1
5
LDB-R3 Secondary loop point LED Stip
|  | Primary L1 TO Secondary L1 | No,s | 1 |  |  |  | 1
|  | L1 TO L2 | No,s | 1 |  |  |  | 1
|  | L2 TO L3 | No,s | 1 |  |  |  | 1
|  | L3 TO L4 | No,s | 1 |  |  |  | 1
|  | L4 TO L5 | No,s | 1 |  |  |  | 1
5
LDB-Y1 Secondary loop point
|  | Primary L1 TO Secondary L1 | No,s | 1 |  |  |  | 1
|  | L1 TO L2 | No,s | 1 |  |  |  | 1
|  | L2 TO L3 | No,s | 1 |  |  |  | 1
|  | L3 TO L4 | No,s | 1 |  |  |  | 1
|  | L4 TO L5 | No,s | 1 |  |  |  | 1
|  | L5 TO L6 | No,s | 1 |  |  |  | 1
|  | L6 TO L7 | No,s | 1 |  |  |  | 1
|  | L7 TO L8 | No,s | 1 |  |  |  | 1
8
LDB-Y2 Secondary loop point
|  | Primary L1 TO Secondary L1 | No,s | 1 |  |  |  | 1
|  | L1 TO L2 | No,s | 1 |  |  |  | 1
|  | L2 TO L3 | No,s | 1 |  |  |  | 1
|  | L3 TO L4 | No,s | 1 |  |  |  | 1
|  | L4 TO L5 | No,s | 1 |  |  |  | 1
5
LDB-Y3 Secondary loop point
|  | Primary L1 TO Secondary L1 | No,s | 1 |  |  |  | 1
|  | L1 TO L2 | No,s | 1 |  |  |  | 1
|  | L2 TO L3 | No,s | 1 |  |  |  | 1
|  | L3 TO L4 | No,s | 1 |  |  |  | 1
|  | L4 TO L5 | No,s | 1 |  |  |  | 1
5
LDB-B1 Secondary loop point
|  | Primary L1 TO Secondary L1 KITCHEN AREA | No,s | 1 |  |  |  | 1
LDB-B2 Secondary loop point
|  | Primary L1 TO Secondary L1 | No,s | 1 |  |  |  | 1
|  | L1 TO L2 | No,s | 1 |  |  |  | 1
|  | L2 TO L3 | No,s | 1 |  |  |  | 1
|  | L3 TO L4 | No,s | 1 |  |  |  | 1
|  | L4 TO L5 | No,s | 1 |  |  |  | 1
5
LDB-B3 Secondary loop point LED Strip
|  | Primary L1 TO Secondary L1 | No,s | 1 |  |  |  | 1
|  | L1 TO L2 | No,s | 1 |  |  |  | 1
|  | L2 TO L3 | No,s | 1 |  |  |  | 1
3
|  | Sub Total | [5 empty] | 42
|  | TENDER QTY | [5 empty] | 34
|  | AMENDED QTY | [5 empty] | 8
|  | TOTAL | [5 empty] | 42
32 | 1.5 | Wiring for secondary light points with 2.5 sq. mm LSZH PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia FRLSH PVC conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 2.5 sq. mm LSZH PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Emergency) | nos
EDB-C1 Secondary loop point
|  | Primary EL1 TO Secondary EL1 | No,s | 1 |  |  |  | 1
|  | E.L1 TO E.L2 | No,s | 1 |  |  |  | 1
|  | E.L2 TO E.L3 | No,s | 1 |  |  |  | 1
3
EDB-C2 Secondary loop point
|  | Primary EL1 TO Secondary EL1 | No,s | 1 |  |  |  | 1
|  | E.L1 TO E.L2 | No,s | 1 |  |  |  | 1
|  | E.L2 TO E.L3 | No,s | 1 |  |  |  | 1
3
EDB-C3 Secondary loop point
|  | Primary EL1 TO Secondary EL1 | No,s | 1 |  |  |  | 1
|  | E.L1 TO E.L2 | No,s | 1 |  |  |  | 1
|  | E.L2 TO E.L3 | No,s | 1 |  |  |  | 1
|  | E.L3 TO E.L4 | No,s | 1 |  |  |  | 1
|  | E.L4 TO E.L5 | No,s | 1 |  |  |  | 1
|  | E.L5 TO E.L6 | No,s | 1 |  |  |  | 1
6
|  | Sub Total | [5 empty] | 12
33 | 1.6 | Wiring for 240 volt 6 amp Multistandard single phase and neutral switch socket outlet with 4.0 sq. mm LSZH PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia FRLSH PVC surface/concealed conduit including cost of providing circuit wiring with 4.0 sq mm LSZH PVC insulated stranded/ multistranded copper conductor 1100 volt grade wires and including the cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and Supply and fixing of a 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 4.0 sq. mm LSZH PVC insulated copper earth wire conductor wires complete as directions of Engineer-in-charge and as required. | nos
|  | PDB-Y4 To Premium Lounge side Screen Tv 1 power point | nos | 1 |  |  |  | 1
|  | PDB-B8 To Premium Lounge side Screen Tv 2 power point | nos | 1 |  |  |  | 1
|  | PDB-Y7 To Admin side LED Screen TV 3 Power poit | nos | 1 |  |  |  | 1
|  | PDB-B4 To INDIA MAP ARTWORK SIDE Power point | nos | 1 |  |  |  | 1
|  | PDB-R5 To NEAR MERCHANDISE DISPLAY | nos | 1 |  |  |  | 1
|  | EDB-C9 To NEAR FACP UPS POWER | nos | 1 |  |  |  | 1
|  | EDB-C10 To FOR WI-FI UPS POWER | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 7
34 | 1.7 | Wiring as in Item 1.6 above looped from an adjacent switch socket outlet as required and Supply and fixing of a combined 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 4.0 sq. mm LSZH PVC insulated copper earth wire conductor wires complete as directions of Engineer-in-charge and as required. | nos
Secondary loop point
|  | Premium Lounge side Screen Tv 1 power point To FDS | nos | 2 |  |  |  | 2
|  | Premium Lounge side Screen Tv 2 power point To FDS | nos | 1 |  |  |  | 1
|  | Admin side LED Screen TV 3 Power poit To SB1 | nos | 1 |  |  |  | 1
|  | INDIA MAP ARTWORK SIDE Power point To Reception | nos | 1 |  |  |  | 1
|  | Reception To 6U Networking Rack | nos | 1 |  |  |  | 1
|  | EDB-C9 To NEAR FACP UPS POWER | nos | 3 |  |  |  | 3
|  | WI-FI,1 UPS POWER To WI-FI,2 | nos | 1 |  |  |  | 1
|  | WI-FI,2 UPS POWER To WI-FI,3 | nos | 1 |  |  |  | 1
Sub Total
35 | 1.8 | Wiring for a multi-pin 240 volt 6-13 amp single phase and neutral universal switch socket outlet with 4.0 sq. mm LSZH PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia LSZH PVC surface/concealed conduit including the cost of providing circuit wiring with 4.0 sq mm LSZH PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a combined multi-pin 240 volt 6-13 amp universal socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed galvanized box and including earthing of the 3rd pin with 4.0 sq mm 1100 volt grade LSZH PVC insulated stranded copper conductor wires complete as directions of Engineer-in-charge and as required. | nos
EDB TO UPS POWER POINT 6/13A, SWITCH & SOCKET
|  | EDB-C4 To LED Screen UPS Power | No,s | 1 |  |  |  | 1
|  | EDB-C5 To Admin side Sceen Tv | No,s | 1 |  |  |  | 1
|  | EDB-C6 To FDS | No,s | 1 |  |  |  | 1
|  | EDB-C7 To Reception Table | No,s | 1 |  |  |  | 1
|  | EDB-C8 To FDS | No,s
|  | PDB TO RAW POWER | No,s
|  | PDB-Y8 TO SB1 RAW POWER FDS NEAR DECK CHILLER SIDE | No,s | 1 |  |  |  | 1
|  | PDB-B7 TO ADMIN SCREEN TV SIDE | No,s | 1 |  |  |  | 1
|  | PDB-Y7 TO SB1 LED TV | No,s | 1 |  |  |  | 1
|  | PDB-R8 To SB1NEAR DECK CHILLER | No,s | 1 |  |  |  | 1
|  | PDB-Y11 To FDS | No,s | 1 |  |  |  | 1
|  | PDB-B11 To SB1 NEAR FDS | No,s | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 10
36 | 1.9 | Wiring as in Item 1.8 above looped from an adjacent switch socket outlet as per specifications and directions of Engineer-in-charge and providing and fixing of a modular type multi-pin 240 Volt 6-13 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole rocker type switch in a recessed galvanized boxes with internal wiring and moulded front plates complete as directions of Engineer-in-charge and as required. | nos
UPS POWER POINT 6/13A, SWITCH & SOCKET
|  | EDB-C4 LED Screen UPS Power | No,s | 1 |  |  |  | 1
|  | EDB-C5 Admin side Sceen Tv | No,s | 1 |  |  |  | 1
|  | EDB-C6 FDS | No,s | 1 |  |  |  | 1
|  | EDB-C7 Reception Table | No,s | 2 |  |  |  | 2
|  | EDB-C8 FDS | No,s | 1 |  |  |  | 1
|  | PDB TO RAW POWER | No,s
|  | PDB-Y8 SB1 RAW POWER FDS NEAR DECK CHILLER SIDE | No,s | 1 |  |  |  | 1
|  | PDB-B7 ADMIN SCREEN TV SIDE | No,s | 1 |  |  |  | 1
|  | PDB-Y7 SB1 LED TV | No,s | 1 |  |  |  | 1
|  | PDB-R8 SB1NEAR DECK CHILLER | No,s | 1 |  |  |  | 1
|  | PDB-Y11 FDS | No,s | 1 |  |  |  | 1
|  | PDB-B11 SB1 NEAR FDS | No,s | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 12
|  | TENDER QTY | [5 empty] | 2
|  | AMENDED QTY | [5 empty] | 10
|  | TOTAL | [5 empty] | 12
37 | 1.1 | Supply , Installation, Testing and comissioning of IP 66 EGA Boxes with all standard accessories consisting of following: a) 3nos 6-13 amp socket with single Switch b) 2nos Data outlets with includes of Data wiring and terminations. Wiring for socket outlet with 4.0 sq. mm LSZH PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia LSZH PVC surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 4.0 sq mm LSZH PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a EGA Box complete as directions of Engineer-in-charge and as required. | nos
38 | 1.11 | Wiring for 6 pin 240 volt 16 amp single phase and neutral Universal switch socket outlets with 4.0 sq. mm LSZH PVC insulated stranded/multi stranded copper conductor 1100 volt grade wires in IS embossed 25mm dia FRLSH PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including Supply and fixing of a 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switch with moulded cover plate in a recessed zinc chromate passivated GI box including earthing of the 3rd pin with 4.0 sq. mm 1100 volt grade LSZH PVC insulated stranded copper earth wire complete as directions of Engineer-in-charge and as required. | Nos.
|  | PDB1 To R5 | No,s | 1 |  |  |  | 1
|  | PDB1 To B10 NEAR FDS | No,s | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 2
39 | 1.12 | Wiring for 25 amp SPN isolator for Geyser with 4.0 sq. mm LSZH PVC insulated standed/multi stranded copper conductor 1100 volt grade wires in PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including providing and fixing of a 25 amp terminal block in recessed GI box with conduit Bend out for connection to equipment including earthing with 2 nos 4.0 sq mm 1100 volt grade PVC insulated FRLS multistranded copper conductor wire complete as directions of Engineer-in-charge and as required. | Nos.
PDB-R1 To Geyser used Power point
|  | Sub Total | No,s | 1
40 | 1.13 | Wiring for 25 amp TPN isolator for HVAC Fan & Scrubber with 4.0 sq. mm LSZH PVC insulated standed/multi stranded copper conductor 1100 volt grade wires in PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including providing and fixing of a 25 amp terminal block in recessed GI box with conduit Bend out for connection to equipment including earthing with 2 nos 4.0 sq mm 1100 volt grade PVC insulated FRLS multistranded copper conductor wire complete as directions of Engineer-in-charge and as required. | Nos.
|  | Electrical Panel to Scrubber Isolater HVAC Fan | No,s | 1 |  |  |  | 1
|  | Electrical Panel to Scrubber Isolater | No,s | 1 |  |  |  | 1
Sub Total
41 | 1.14 | Wiring for a multi-pin 240 volt 5/15 amp single phase and neutral universal switch socket outlet with 4.0 sq. mm LSZH PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia LSZH PVC surface/concealed conduit including the cost of providing circuit wiring with 4.0 sq mm LSZH PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a combined multi-pin 240 volt 5/15 amp universal socket outlet with safety shutters and 15 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed galvanized box and including earthing of the 3rd pin with 4.0 sq mm 1100 volt grade LSZH PVC insulated stranded copper conductor wires complete as directions of Engineer-in-charge and as required. | Nos.
|  | KDB TO POWER POINT | No,s
|  | KDB-R1 To Open Chiller | No,s | 1 |  |  |  | 1
|  | KDB-R2 To Heat Lamp | No,s | 1 |  |  |  | 1
|  | KDB-R3 To Trap 25.5Ltrs | No,s | 1 |  |  |  | 1
|  | KDB-R4 To Used work table | No,s | 1 |  |  |  | 1
|  | KDB-R5 To U/C Chiller | No,s | 1 |  |  |  | 1
|  | KDB-R7 To UC Chiller | No,s | 1 |  |  |  | 1
|  | KDB-Y1 To Conveyer/Toaster | No,s | 1 |  |  |  | 1
|  | KDB-Y2 To Juice Dispenser | No,s | 1 |  |  |  | 1
|  | KDB-Y3 To Sunk cold power point | No,s | 1 |  |  |  | 1
|  | KDB-Y4 To Tea & Coffee power point | No,s | 1 |  |  |  | 1
|  | KDB-Y5 To Induction | No,s | 1 |  |  |  | 1
|  | KDB-Y6 To Induction | No,s | 1 |  |  |  | 1
|  | KDB-Y7 To Exhaust Chimney power point | No,s | 1 |  |  |  | 1
|  | KDB-Y8 To Milk Storage area | No,s | 1 |  |  |  | 1
|  | KDB-B1 To Induction power point | No,s | 1 |  |  |  | 1
|  | KBD-B2 To Induction power point | No,s | 1 |  |  |  | 1
|  | KBD-B3 To Induction power point | No,s | 1 |  |  |  | 1
|  | KBD-B4 To Induction power point | No,s | 1 |  |  |  | 1
|  | KBD-B5 To Induction power point | No,s | 1 |  |  |  | 1
|  | KDB-B6 To Saup Turreh power point | No,s | 1 |  |  |  | 1
|  | KDB-B7 To Chemical Storage Area power | No,s | 1 |  |  |  | 1
|  | KDB-B8 To Electrical Room Power point | No,s | 1 |  |  |  | 1
|  | KDB-B9 To Chiller power point | No,s | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 23
|  | TENDER QTY | [5 empty] | 15
|  | AMENDED QTY | [5 empty] | 8
|  | TOTAL | [5 empty] | 23
42 | 1.15 | Wiring for 32 amp SPN isolator for Kitchen Equipments with 4.0 sq. mm LSZH PVC insulated standed/multi stranded copper conductor 1100 volt grade wires in PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including providing and fixing of a 32 amp terminal block in recessed GI box with conduit Bend out for connection to equipment including earthing with 2 nos 4.0 sq mm 1100 volt grade PVC insulated FRLS multistranded copper conductor wire complete as directions of Engineer-in-charge and as required. | Nos.
|  | KDB-R7 TO Fiyer 6Ltrs. Cap. | No,s | 1 |  |  |  | 1
|  | KDB-R8 TO Fiyer 6Ltrs. Cap. | No,s | 1 |  |  |  | 1
|  | KDB-R6 TO Freezer | No,s | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 3
43 | 1.16 | Wiring for 32 amp Three phase 5Pole industrial socket outlets with 6.0 sq mm FRLS PVC insulated 1100 volt grade stranded copper conductor wires in 25 mm dia FRLS PVC surface/concealed conduit including cost of providing brackets, saddles etc as per specifications and directions of Engineer-in-charge for surface conduiting and/or cost of cutting and filling chases and including the cost of supplying and fixing 32 amp 10 kA TPN MCB, industrial type socket outlet in galvanized box, industrial plug top and including the cost of loop earthing with 6.0 sq mm FRLS PVC insulated copper conductor wires complete as per specifications and directions of Engineer-in-charge.(MCB shall be 'B' Curve) | Nos.
Electrical panel to hot plate kitchen side
|  | Sub Total | No,s | 1
44 | 1.17 | Wiring for 32 amp TPN isolator for Kitchen with 6.0 sq. mm LSZH PVC insulated standed/multi stranded copper conductor 1100 volt grade wires in PVC surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including providing and fixing of a 32 amp terminal block in recessed GI box with conduit Bend out for connection to equipment including earthing with 2 nos 4.0 sq mm 1100 volt grade PVC insulated FRLS multistranded copper conductor wire complete as directions of Engineer-in-charge and as required. | Nos.
A |  | Electrical panel To Dish washer power point in kitchen area | No,s | 1 |  |  |  | 1
|  | Electrical panel To Combi oven power point in kitchen area | No,s | 1 |  |  |  | 1
|  | Electrical panel To Table Top Hot plate power point in kitchen area | No,s | 1 |  |  |  | 1
|  | Electrical panel To 4 Zone hot plate power point in kitchen area | No,s | 1 |  |  |  | 1
45 |  | Sub Total
46 | 1.18 | Providing and fixing of a Data outlet plate mounted outlet unit (RJ-45) with moulded cover plate in recessed zinc chromate passivated MS box complete as directions of Engineer-in-charge and as required for Data system. | nos
|  | SCREEN TV1 NEAR ELECTRICAL BACKE WALL SIDE C2 | No,s | 2 |  |  |  | 2
|  | FDS PREMIUM LOUNGE C2 | No,s | 2 |  |  |  | 2
|  | SCREEN TV2 NEAR ELECTRICAL BACKE WALL SIDE C2 | No,s | 2 |  |  |  | 2
|  | FDS PREMIUM LOUNGE C2 | No,s | 2 |  |  |  | 2
|  | FDS PREMIUM LOUNGE C2 | No,s | 2 |  |  |  | 2
|  | LED SCREEN TV3 ADMIN AREA C2 | No,s | 2 |  |  |  | 2
|  | RECEPTIN FDS C2 | No,s | 2 |  |  |  | 2
|  | MERCHANDISE | No,s | 2 |  |  |  | 2
Sub Total
47 | 1.19 | Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair computer cable with 24 AWG solid copper conductors in surface/concealed conduit/raceways/modular furniture , complete as directions of Engineer-in-charge and as required. | Mtrs
NVR TO DATA/VOICE CAT-6 WIRE LAYING
|  | NETWORK RACK TO D1 | 1 | 27 |  |  |  | 27
|  | D2,V1 | 2 | 27 |  |  |  | 54
|  | D3 | 1 | 25.5 |  |  |  | 25.5
|  | D4 | 1 | 24.5 |  |  |  | 24.5
|  | D5,V2 | 2 | 23.5 |  |  |  | 47
|  | D6, | 1 | 20 |  |  |  | 20
|  | D7 | 1 | 19.1 |  |  |  | 19.1
|  | D8 | 1 | 20.9 |  |  |  | 20.9
|  | D9 | 1 | 21.8 |  |  |  | 21.8
|  | D10,V3 | 2 | 20.5 |  |  |  | 41
|  | D11 | 1 | 10 |  |  |  | 10
|  | D12,V4 | 2 | 11 |  |  |  | 22
|  | D13,V5 | 2 | 10 |  |  |  | 20
|  |  | 2 | 17.5 |  |  |  | 35
Sub Total
48 | 1.2 | Supplying, Installation, testing and commissioning of 6U Networking Rack with all accessories and complete as required
|  | Sub Total | nos | 1
49 | 1.21 | Supplying, Installation, testing and commissioning of Occupancy Sensor for light control with all accessories and complete as directions of Engineer-in-charge and as required.
|  | Sub Total | nos | 1
50 | 1.22 | Supplying and drawing wiring with single core stranded copper conductor PVC insulated 1100 volt grade LSZH PVC insulated wires in existing conduit systems including the cost of running copper conductor LSZH PVC insulated loop earthing wire complete as directions of Engineer-in-charge and as required as below.
51 | a) | 2 x 1.5 sq mm with 1 x 1.5 sq mm earth wire | Mtrs
52 | a) | 2 x 2.5 sq mm with 1 x 2.5 sq mm earth wire | Mtrs
53 | b) | 2 x 4 sq mm with 1 x 4.0 sq mm earth wire | Mtrs
54 | c) | 2 x 6 sq mm with 1 x 6.0 sq mm earth wire | Mtrs
55 | d) | 2 x 10 sq mm with 1 x 10 sq mm earth wire | Mtrs
56 | e) | 4 x 2.5 sq mm with 2 x 2.5 sq mm earth wire | Mtrs
57 | f) | 4 x 4 sq mm with 2 x 4.0 sq mm earth wire | Mtrs
58 | g) | 4 x 6 sq mm with 2 x 6.0 sq mm earth wire | Mtrs
59 | h) | 4 x 10 sq mm with 2 x 10 sq mm earth wire | Mtrs
60 | i) | 4 x 16 sq mm with 2 x 16 sq mm earth wire | Mtrs
61 | i) | 4 x 25 sq mm with 2 x 25 sq mm earth wire | Mtrs
62 | 1.23 | Supplying and drawing recessed/surface IS embossed GI conduiting system including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer-in-charge and as required as below.
63 | a) | 25 mm 16 SWG | Mtrs
under floor 25mm conduit used power Premium lounge(19 pax) area side
|  | junctoin box1 to box2 | Mtrs |  | 0.23 |  |  | 0.23
|  | junctoin box2 to box3 | Mtrs |  | 0.23 |  |  | 0.23
|  | junctoin box3 to box4 | Mtrs |  | 2.18 |  |  | 2.18
|  | junctoin box4 to box5 | Mtrs |  | 2.42 |  |  | 2.42
|  | junctoin box5 to box6 | Mtrs |  | 2.32 |  |  | 2.32
|  | junctoin box6 to box7 | Mtrs |  | 0.23 |  |  | 0.23
|  | junctoin box7 to box8 | Mtrs |  | 0.23 |  |  | 0.23
|  | junctoin box8 to box9 | Mtrs |  | 2.18 |  |  | 2.18
|  | junctoin box9 to box10 | Mtrs |  | 2.42 |  |  | 2.42
|  | junctoin box10 to box11 | Mtrs |  | 2.32 |  |  | 2.32
Executive Lounge(28 Pax) area side
|  | junctoin box1 to box2 | Mtrs |  | 2 |  |  | 2
|  | junctoin box2 to box3 | Mtrs |  | 2 |  |  | 2
|  | junctoin box3 to box4 | Mtrs |  | 0.9 |  |  | 0.9
|  | junctoin box4 to box5 | Mtrs |  | 0.6 |  |  | 0.6
|  | junctoin box5 to box6 | Mtrs |  | 2 |  |  | 2
|  | junctoin box6 to box7 | Mtrs |  | 2 |  |  | 2
|  | junctoin box7 to box8 | Mtrs |  | 0.9 |  |  | 0.9
|  | junctoin box8 to box9 | Mtrs |  | 2.7 |  |  | 2.7
|  |  | Mtrs |  | 4.7 |  |  | 4.7
Premium Lounge(19 Pax) area side
|  | junctoin box1 to box2 | Mtrs |  | 1.3 |  |  | 1.3
|  | junctoin box2 to box3 | Mtrs |  | 2.35 |  |  | 2.35
|  | junctoin box3 to box4 | Mtrs |  | 2.5 |  |  | 2.5
|  | junctoin box4 to box5 | Mtrs |  | 0.85 |  |  | 0.85
Sub Total
64 | b) | 32 mm 14 SWG | Mtrs
65 | c) | 40 mm 14 SWG | Mtrs
66 | d) | 50 mm 14 SWG | Mtrs
67 | 1.24 | Supply and fixing GI flexible conduit including all fittings complete as required as below.
68 | a) | 20 mm 16 SWG | Mtrs
69 | b) | 25 mm 16 SWG | Mtrs
LIGHT LOOP WIRING FIXING FLEXIBLE CONDUIT
|  | L1 | Mtrs |  | 1.6 |  |  | 1.6
|  | L2 | Mtrs |  | 1.6 |  |  | 1.6
|  | L3 | Mtrs |  | 1.6 |  |  | 1.6
|  | L4 | Mtrs |  | 1.6 |  |  | 1.6
|  | L5 | Mtrs |  | 1.6 |  |  | 1.6
|  | L6 | Mtrs |  | 1.6 |  |  | 1.6
|  | L7 | Mtrs |  | 1.6 |  |  | 1.6
|  | L8 | Mtrs |  | 1.6 |  |  | 1.6
|  | L9 | Mtrs |  | 1.6 |  |  | 1.6
|  | L10 | Mtrs |  | 1.6 |  |  | 1.6
|  | L11 | Mtrs |  | 1.6 |  |  | 1.6
|  | L12 | Mtrs |  | 1.6 |  |  | 1.6
|  | L13 | Mtrs |  | 1.6 |  |  | 1.6
|  | L14 | Mtrs |  | 1.6 |  |  | 1.6
|  | L15 | Mtrs |  | 1.6 |  |  | 1.6
|  | L16 | Mtrs |  | 1.6 |  |  | 1.6
|  | L17 | Mtrs |  | 1.6 |  |  | 1.6
|  | L18 | Mtrs |  | 1.6 |  |  | 1.6
|  | L19 | Mtrs |  | 1.6 |  |  | 1.6
|  | L20 | Mtrs |  | 1.6 |  |  | 1.6
|  | L21 | Mtrs |  | 1.6 |  |  | 1.6
|  | L22 | Mtrs |  | 1.6 |  |  | 1.6
|  | L23 | Mtrs |  | 1.6 |  |  | 1.6
|  | L24 | Mtrs |  | 1.6 |  |  | 1.6
|  | L25 | Mtrs |  | 1.6 |  |  | 1.6
|  | L26 | Mtrs |  | 1.6 |  |  | 1.6
|  | L27 | Mtrs |  | 1.6 |  |  | 1.6
|  | L28 | Mtrs |  | 1.6 |  |  | 1.6
|  | L29 | Mtrs |  | 1.6 |  |  | 1.6
|  | L30 | Mtrs |  | 1.6 |  |  | 1.6
|  | L31 | Mtrs |  | 1.6 |  |  | 1.6
|  | L32 | Mtrs |  | 1.6 |  |  | 1.6
|  | L33 | Mtrs |  | 1.6 |  |  | 1.6
|  | L34 | Mtrs |  | 1.6 |  |  | 1.6
|  | L35 | Mtrs |  | 1.6 |  |  | 1.6
|  | L36 | Mtrs |  | 1.6 |  |  | 1.6
|  | L37 | Mtrs |  | 1.6 |  |  | 1.6
|  | L38 | Mtrs |  | 1.6 |  |  | 1.6
|  | L39 | Mtrs |  | 1.6 |  |  | 1.6
|  | L40 | Mtrs |  | 1.6 |  |  | 1.6
|  | L41 | Mtrs |  | 1.6 |  |  | 1.6
|  | L42 | Mtrs |  | 1.6 |  |  | 1.6
|  | L43 | Mtrs |  | 1.6 |  |  | 1.6
|  | L44 | Mtrs |  | 1.6 |  |  | 1.6
|  | L45 | Mtrs |  | 1.6 |  |  | 1.6
|  | L46 | Mtrs |  | 1.6 |  |  | 1.6
|  | L47 | Mtrs |  | 1.6 |  |  | 1.6
|  | L48 | Mtrs |  | 1.6 |  |  | 1.6
|  | L49 | Mtrs |  | 1.6 |  |  | 1.6
|  | L50 | Mtrs |  | 1.6 |  |  | 1.6
|  | L51 | Mtrs |  | 1.6 |  |  | 1.6
|  | L52 | Mtrs |  | 1.6 |  |  | 1.6
|  | L53 | Mtrs |  | 1.6 |  |  | 1.6
|  | L54 | Mtrs |  | 1.6 |  |  | 1.6
|  | L55 | Mtrs |  | 1.6 |  |  | 1.6
Sub Total
70 | c) | 32 mm 14 SWG | Mtrs
71 | d) | 40 mm 14 SWG | Mtrs
72 | e) | 50 mm 14 SWG | Mtrs
73
74 |  | TOTAL SUB-HEAD I carried over to Summary
75
76 | B | SUB HEAD-II- CABLES & RACEWAYS
77 | 1 | Supplying, laying, connecting ,terminating on both side testing & commissioning of following size of 1.1 kv grade single/multicore aluminium conductor XLPE insulated and PVC sheathed armoured cable as per IS: 7098:1988 (Part-I) with upto date amendments.
78 | a) | 3.5 core 50 Sq mm | Mtrs
79 | 2 | Cable end termination of the following XLPE insulated and PVC sheathed aluminium conductor cable 1100 Volt grade including cost of crimping heavy duty copper lugs,nickel plated brass double compression glands,insulation tape and all requisite material for completion of termination complete as required and as below.
80 | a) | 3.5 core 50 Sq mm | Nos
81 | 3 | Supplying, laying, connecting ,terminating on both side testing & commissioning of following size of 1.1 kv grade single/multicore copper conductor XLPE insulated and PVC sheathed armoured cable as per IS: 7098:1988 (Part-I) with upto date amendments.
82 | a) | 4 core 4 Sq mm | Mtrs
|  | LT PANEL TO LDB | Mtrs |  | 10.5 |  |  | 10.5
|  | LT PANEL TO TABLE TOP HOT PLATE | Mtrs |  | 7.7 |  |  | 7.7
|  | LT TO 1.5 HP DOL STARTER | Mtrs |  | 25.7 |  |  | 25.7
|  | STARTER TO SCRUBBER MOTOR | Mtrs |  | 5 |  |  | 5
|  | LT TO 0.75KW DOL STAR | Mtrs |  | 25.7 |  |  | 25.7
|  |  | Mtrs |  | 5 |  |  | 5
|  | Sub Total | Mtrs
83 | b | 4 core 6 Sq mm | Mtrs
|  | LT TO COMBI OVEN | Mtrs |  | 9.5 |  |  | 9.5
|  | LT TO DISH WASHER | Mtrs |  | 9.7 |  |  | 9.7
|  | LT TO 4 ZNE HOT PLATE | Mtrs |  | 11 |  |  | 11
|  | LT TO UPS INPUT | Mtrs |  | 8.1 |  |  | 8.1
|  | INPUT TO UPS | Mtrs |  | 6 |  |  | 6
|  | UPS TO OUT PUT | Mtrs |  | 6 |  |  | 6
|  | OUT PUT TO UPS DB | Mtrs |  | 1.5 |  |  | 1.5
Sub Total
84 | c | 4 core 10 Sq mm | Mtrs
|  | LT PANEL TO PDB | Mtrs | 1 | 10.3 |  |  | 10.3
Sub Total
85 | 4 | Cable end termination of the following XLPE insulated and PVC sheathed copper conductor cable 1100 Volt grade including cost of crimping heavy duty copper lugs,nickel plated brass double compression glands,insulation tape and all requisite material for completion of termination complete as required and as below.
86 | a) | 4 core 4 Sq mm | Nos
|  | LT PANEL TO LDB | Nos | 2 |  |  |  | 2
|  | LT PANEL TO TABLE TOP HOT PLATE | Nos | 2 |  |  |  | 2
Sub Total
87 | b | 4 core 6 Sq mm | Nos
|  | LT TO COMBI OVEN | Nos | 2 |  |  |  | 2
|  | LT TO DISH WASHER | Nos | 2 |  |  |  | 2
|  | LT TO 4 ZNE HOT PLATE | Nos | 2 |  |  |  | 2
Sub Total
88 | c | 4 core 10 Sq mm | Nos
|  | LT PANEL TO PDB | Nos | 2 |  |  |  | 2
Sub Total
89 | 5 | Supply and fixing of perforated sheet steel slotted cable trays with vertical sides on both ends as per approved design and GI angle supports spaced 1000 mm apart throughout the length as specified, including the cost of 1 meter GI rod hangers, hooks, dash fasteners, painting etc. for suspension from ceiling complete as required.
90 | a) | 150 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cover | Mtrs
|  | TL PANEL TO PDB,S LOCATION AREA | Mtrs | 1 | 2.5 |  |  | 2.5
Sub Total
92 |  | GI Raceway & Junction boxes (IP 55)
93 | 4 | Supply, assembly and laying of under floor trunking made out of minimum 1.6mm thick pre galavised sheet with enamel paint finish complete with jointing sleeve, horizontal bends, vertical bends, level adjustment components and closer, vertical elbow, covers, access outlet. etc. complete with all other accessories under floor installation including cutting and chasing the floor/ or on surface, making good the same, placing in position and cleaning from inside complete etc. as required.
94 | a) | 100 mm x 40 mm (3 compartment)- 1 For Power, 1 for Data, 1 blank for seperation ) | Mtrs
95 | b) | 75 mm x 40 mm (3 compartment)- 1 For Power, 1 for Data, 1 blank for seperation ) | Mtrs
96 | c) | 75 mm x 40 mm (1 compartment)- For Power | Mtrs
97 | d) | 50 mm x 40 mm (1 compartment) for Data | Mtrs
98 | e) | Providing and fixing 150 x 150 x 50 mm deep junction box | Nos
99 | f) | Providing and fixing 100 x 100 x 50 mm deep junction box | Nos
|  | UNDER FLOOR PEDESTAL TABLE | Nos | 22 |  |  |  | 22
Sub Total
100 | g) | Providing and fixing 75 x 75 x 50 mm deep junction box | Nos
101
102 |  | TOTAL SUB-HEAD II carried over to Summary
103
104 | C | SUB HEAD III - DISTRIBUTION SYSTEM & EARTHING
105
106 | 1 | Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof distribution boards constructed from 1.2mm sheet steel IP 42 construction, finished with rust proof red oxide coating and two coats of paint with hinged gasketted door and housing the following complete with suitably rated PVC insulated copper busbars with interconnections and neutral bar assembly, earthing terminals complete as approved by Architects. Padlocking facility shall be provided on the door.
107 | a) | 10 WAY TPN - Power DB | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 1
108 |  | 1-40 amp TPN 10 kA MCB with thermal magnetic protective releases incoming with 3 single phase banks each comprising of 1-40 amp DP 30 mA RCCB incoming and 30 nos 6/16/20/25/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings.
109 | b) | 6 WAY TPN - Lighting DB | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 1
110 |  | 1-32 amp TPN 10 kA MCB with thermal magnetic protective releases incoming with 3 single phase banks each comprising of 1-32 amp DP 30 mA RCCB incoming and 18 nos 6/16/20/25/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings.
111 | c) | 6 WAY TPN - Kitchen DB | nos
112 |  | 1-63 amp TPN 10 kA MCB with thermal magnetic protective releases incoming with 3 single phase banks each comprising of 1-63 amp DP 30 mA RCCB incoming and 18 nos 6/16/20/25/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings.
113 | d) | 12 WAY SPN- UPS DB
114 |  | 1-32 amp DP 10 kA MCB with thermal magnetic protective releases incoming with single phase banks comprising of 1-32 amp DP 30 mA RCCB incoming and 12 nos 6/10/16/20/25/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings. | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 1
115
116 | 2 | Design, Manufacture, Supply, delivery and coordination for Installation of the following front operated modular compartmentalised construction cubicle type, front access, dead back, 2mm thick steel enclosed free standing on leg at 400mm above from FFL / wall mounted, dust and vermin proof, switchboard with IP67/Specified protection with hinged and lockable doors duly powder coated complete with interconnections, tinned copper crimping lugs, bonding to earth and painting, suitable for use at 415 volts, 3 phase 4 wire 50 Hertz system, and to withstand a symetrical fault level of 25 kA
117 |  | All Switchboards shall have provision for entry of cables from the top or bottom as required.
118
119 |  | All kA values indicated shall be Ics breaking capacity.
120 |  | All MCCB above 250 amp shall have variable settings.
121 |  | The cost shall include providing and fixing of 75 x 50 x 6 mm channels for switchboard support.
122 |  | All MCCB shall have rotary handles & extension terminal, phase barrier on both sides as required at site.
123 |  | All metering panel shall be extendable type with cable alley.
124 |  | GA drawings shall be got approved from Owners/ Architects/ Consultants before fabrication.
125 |  | Note:- The Manufacturer/Supplier shall supervise the installation, testing and commissioning of the cubicle panels by the electrical contractor
126
127 | A | INCOMING - In Kitchen
128 |  | 1 no 125 A 4POLE MCCB
129
130 |  | INDICATING PANEL
131
132 |  | The incomers shall have the following indicating panel
133 | a) | 3 nos Cast resin current transformers of 125/5 ratio Class 1.0 for metering
134 | b) | 1 no Multi function meter
135 | c) | 1 set of three White phase indicating lamps
136 | d) | Red / Green ON/OFF indicator (LED type)
137
138 |  | BUSBAR
139 |  | Electrolytic high conductivity aluminium TPN busbars rated at 160 amps suitable to with stand symmetrical fault level of 25kA at 415 volts. The neutral busbar is to be of 100% capacity.
140
141 |  | OUTGOING UNITS
142 |  | 1 nos 63 amp 4P 10 kA MCB with thermal magnetic protective releases
143 |  | 1 nos 40 amp 4P 10 kA MCB with thermal magnetic protective releases
144 |  | 8 nos 32 amp 4P 10 kA MCB with thermal magnetic protective releases
145 |  | 3 nos 25 amp 4P 10 kA MCB with thermal magnetic protective releases
146 |  | 1 nos 32 amp DP 10 kA MCB with thermal magnetic protective releases
147 |  | The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required
148 |  |  | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 1
149 |  | UPS 5KVA
150 | 3 | Supply, installation, testing and commissioning of 5kVA UPS system comprising of online units with a battery backup of 30 minutes duration for full load and with all standards fittings, accessories, protection, instruments, indications and controls including but not restricted to transformer, rectifier, inverter, SMF battery with float cum boost battery charger, static bypass switch, maintenance bypass, interconnections etc. The UPS shall be suitble for single phase Input and output supply of 230V. The UPS shall have 2 body earthing connection which shall be looped with existing earting system. | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 1
151 | 4 | Supplying and laying of the following earthing strip on cable tray/ wall clamped to wall with suitable clamps saddles and fixing bolts/soldering /riveting in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All joints shall be timed.
152 | a) | 32 mm x 6 mm GI strip | Mtrs
153 | b) | 25 mm x 3 mm GI strip | Mtrs
154 | c) | 6 SWG GI Wire | Mtrs
155 | d) | 8 SWG GI Wire | Mtrs
|  | ALL DB,s Body earthing | Mtrs | 1 | 25 |  |  | 25
Sub Total
156 | e) | 4 Sqmm bare, tinned-copper stranded conductor | Mtrs
157 |  | TOTAL SUB-HEAD III carried over to Summary
158
159 | D | SUB HEAD IV - FIRE DETECTION & PA SYSTEM
160
161 |  | Fire Detection System
162 | 1 | Supply, installation, testing and commissioning of 1 Loop wall recess mounting microprocessor based networkable analogue addressable Fire Control Panel having a Fire Alarm Capability of 100/125/150 detectors/devices per loop with each loops length being restricted to 80% of manufacturer specified maximum loop length). The Fire control panel shall have 100% hot redundancy for CPU, load etc. It shall be expandable by minimum 1 additional loops. The operating panel shall have minimum 80 character LCD display, 4 access levels, 1000 events historical logging, flash E-PROM, 240 volts ac power supply, automatic battery charger, 24V sealed lead-acid battery suitable operating the system for 24 hours in emergency condition. The Panel shall be Integrated with the PA System and with suitable power amplifiers for the hooter/strobes.
163 |  | The Panel shall be Integrated with the BMS System and shall include cost of supply of any additional modules, software and interfaces as required for the same and as required by the Client. The Panel shall provide either or all BACNET/RS485/ LON/MODBUS protocols as required. The panel shall be complete as per specifications and as required.
164 | a) | 1 Loop | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 1
165 | 2 | Supply, installation, testing and commissioning of plug-in type intelligent analogue addressable multi criteria photo electric cum Smoke detectors including the cost of base plate, 75 mm dia M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. | nos
|  | SMOKE DETECTORS BELLOW & ABOVE | No,s | 1 |  |  |  | 1
|  | SD1 | No,s | 1 |  |  |  | 1
|  | SD2 | No,s | 1 |  |  |  | 1
|  | SD3 | No,s | 1 |  |  |  | 1
|  | SD4 | No,s | 1 |  |  |  | 1
|  | SD5 | No,s | 1 |  |  |  | 1
|  | SD6 | No,s | 1 |  |  |  | 1
|  | SD7 | No,s | 1 |  |  |  | 1
|  | SD8 | No,s | 1 |  |  |  | 1
|  | SD9 | No,s | 1 |  |  |  | 1
|  | SD10 | No,s | 1 |  |  |  | 1
|  | SD11 | No,s | 1 |  |  |  | 1
|  | SD12 | No,s | 1 |  |  |  | 1
|  | SD13 | No,s | 1 |  |  |  | 1
|  | SD14 | No,s | 1 |  |  |  | 1
|  | SD15 | No,s | 1 |  |  |  | 1
|  | SD16 | No,s | 1 |  |  |  | 1
|  | SD17 | No,s | 1 |  |  |  | 1
|  | SD18 | No,s | 1 |  |  |  | 1
|  | SD19 | No,s | 1 |  |  |  | 1
|  | SD20 | No,s | 1 |  |  |  | 1
|  | SD21 | No,s | 1 |  |  |  | 1
|  | SD22 | No,s | 1 |  |  |  | 1
|  | SD23 | No,s | 1 |  |  |  | 1
|  | SD24 | No,s | 1 |  |  |  | 1
|  | SD25 | No,s | 1 |  |  |  | -
|  | Sub Total | [5 empty] | 25
|  | TENDER QTY | [5 empty] | 23
|  | AMENDED QTY | [5 empty] | 2
|  | TOTAL | [5 empty] | 25
166 | 3 | Supply, installation, testing and commissioning of plug-in type intelligent analogue addressable rate of rise cum fixed temperature Heat detectors including the cost of base plate, 75 mm dia M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. | nos
|  | Kitchen area Heat detector | no,s | 2 |  |  |  | 2
|  | Sub Total | [5 empty] | 2
|  | TENDER QTY | [5 empty] | 1
|  | AMENDED QTY | [5 empty] | 1
|  | TOTAL | [5 empty] | 2
167 | 4 | Supply, installation, testing and commissioning of Addressable type fault for isolating shorted, dewired and loose circuits between two successive fault isolators with automatic resetting arrangement (base Model) | nos
168 | 5 | Supply, installation, testing and commissioning of Addressable type Response indicatior. | nos
|  | RI (Response indicatior) | nos | 13 |  |  |  | 13
|  | Sub Total | [5 empty] | 13
|  | TENDER QTY | [5 empty] | 12
|  | AMENDED QTY | [5 empty] | 1
|  | TOTAL | [5 empty] | 13
169 | 6 | Supply, installation, testing and commissioning of intelligent analogue addressable Control Modules including the cost of 75 mm dia MS outlet box for fixing of the module, mounting accessories complete as per specifications and as required. | nos | 3 |  |  |  | 3
Sub Total
170 | 7 | Supply, installation, testing and commissioning of intelligent analogue addressable dry contact Monitor Modules including the cost of 75 mm dia MS outlet box for fixing of the module, mounting accessories complete as per specifications and as required. | nos
171 | 8 | Supply, installation, testing and commissioning of recess/surface mounting dust and vermin proof intelligent addressable analogue Manual Pull stations including cost of all required modules, mounting accessories etc including the cost of M.S. outlet box for fixing of the station, mounting accessories etc. complete as per specifications and as required. | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 1
172 | 9 | Supply, Installation, Testing and commissioning of high intensity hooters cum Strobe Lights with 110 cd. The strobes shall be synchronized for better evacuation. | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 1
173 | 10 | Supply, laying, testing and commissioning of 2 core 1.5 sqmm copper conductor fire survival cable 1100 volt wires in FRLS PVC embossed black enameled 25mm dia recessed and/or surface conduiting system including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting as required and including the cost of crimped termination's complete as required. (For FACP & PA system) | Mtrs
|  | FACP TO SD1 | Mtrs |  | 7.3 |  |  | 7.3
|  | SD1 TO SD2 | Mtrs |  | 3.2 |  |  | 3.2
|  | RI SD2 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD2 TO SD3 | Mtrs |  | 6 |  |  | 6
|  | SD3 TO SD4 | Mtrs |  | 2.6 |  |  | 2.6
|  | RI SD4 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD4 TO SD5 | Mtrs |  | 9.5 |  |  | 9.5
|  | SD5 TO SD6 | Mtrs |  | 2.4 |  |  | 2.4
|  | RI SD6 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD6 TO SD7 | Mtrs |  | 5.6 |  |  | 5.6
|  | SD7 TO SD8 | Mtrs |  | 2.8 |  |  | 2.8
|  | RI SD8 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD8 TO HD9 | Mtrs |  | 4.3 |  |  | 4.3
|  | HD9 TO SD10 | Mtrs |  | 6.5 |  |  | 6.5
|  | RI SD10 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD10 TO SD11 | Mtrs |  | 4 |  |  | 4
|  | SD11 TO SD12 | Mtrs |  | 5.6 |  |  | 5.6
|  | RI SD12 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD12 TO HD13 | Mtrs |  | 6.3 |  |  | 6.3
|  | HD13 TO SD14 | Mtrs |  | 3.7 |  |  | 3.7
|  | SD14 TO SD15 | Mtrs |  | 2.4 |  |  | 2.4
|  | RI SD15 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD15 TO SD16 | Mtrs |  | 3.7 |  |  | 3.7
|  | SD16 TO SD17 | Mtrs |  | 2.5 |  |  | 2.5
|  | RI SD17 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD17 TO SD18 | Mtrs |  | 7.1 |  |  | 7.1
|  | RI SD18 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD18 TO SD19 | Mtrs |  | 2.6 |  |  | 2.6
|  | SD19 TO SD20 | Mtrs |  | 10.1 |  |  | 10.1
|  | SD20 TO SD21 | Mtrs |  | 3 |  |  | 3
|  | RI SD21 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD21 TO SD22 | Mtrs |  | 12.6 |  |  | 12.6
|  | SD22 TO SD23 | Mtrs |  | 2.5 |  |  | 2.5
|  | RI SD23 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD23 TO SD24 | Mtrs |  | 9.2 |  |  | 9.2
|  | SD24 TO SD25 | Mtrs |  | 2.5 |  |  | 2.5
|  | RI SD25 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD25 TO HOOTER | Mtrs |  | 7.8 |  |  | 7.8
|  | HOOTER TO MCP | Mtrs |  | 0.9 |  |  | 0.9
|  | MCP TO SD26 | Mtrs |  | 8.3 |  |  | 8.3
|  | SD26 TO SD27 | Mtrs |  | 2.6 |  |  | 2.6
|  | RI SD27 | Mtrs |  | 2.1 |  |  | 2.1
|  | SD27 TO FACP | Mtrs |  | 8.5 |  |  | 8.5
PA SYSTEM WIRING
|  | AMPLIFIER TO SP1 | Mtrs |  | 7.3 |  |  | 7.3
|  | SP1 TO SP2 | Mtrs |  | 9 |  |  | 9
|  | SP1 TO SP3 | Mtrs |  | 6.1 |  |  | 6.1
|  | SP1 TO SP4 | Mtrs |  | 8.5 |  |  | 8.5
|  | SP1 TO SP5 | Mtrs |  | 11.7 |  |  | 11.7
|  | SP1 TO SP6 | Mtrs |  | 10.1 |  |  | 10.1
|  | SP1 TO SP7 | Mtrs |  | 9.2 |  |  | 9.2
|  | SP1 TO SP8 | Mtrs |  | 4.9 |  |  | 4.9
|  | SP1 TO SP9 | Mtrs |  | 6.4 |  |  | 6.4
|  | SP1 TO SP10 | Mtrs |  | 9.5 |  |  | 9.5
|  | SP1 TO SP11 | Mtrs |  | 12.4 |  |  | 12.4
|  | SP1 TO SP12 | Mtrs |  | 10.4 |  |  | 10.4
|  | SP1 TO SP13 | Mtrs |  | 7.2 |  |  | 7.2
Sub Total
174 | 11 | Supplying and fixing heavy gauge ISI embossed black enameled FRLSH PVC recessed and/or surface conduits including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting complete as per specifications, as required and as below.
175 | a) | 25 mm Dia FRLSH PVC
177 |  | Public Address system
178 | 1 | Supply, installation, testing and commissioning of recess/ surface mounting 2W CEILING SPEAKER ,metal grille, dia 150mm and Spring clamps suitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required. | nos
|  | SP1 | No,s | 1 |  |  |  | 1
|  | SP2 | No,s | 1 |  |  |  | 1
|  | SP3 | No,s | 1 |  |  |  | 1
|  | SP4 | No,s | 1 |  |  |  | 1
|  | SP5 | No,s | 1 |  |  |  | 1
|  | SP6 | No,s | 1 |  |  |  | 1
|  | SP7 | No,s | 1 |  |  |  | 1
|  | SP8 | No,s | 1 |  |  |  | 1
|  | SP9 | No,s | 1 |  |  |  | 1
|  | SP10 | No,s | 1 |  |  |  | 1
|  | SP11 | No,s | 1 |  |  |  | 1
|  | SP12 | No,s | 1 |  |  |  | 1
|  | SP13 | No,s | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 13
|  | TENDER QTY | [5 empty] | 9
|  | AMENDED QTY | [5 empty] | 4
|  | TOTAL | [5 empty] | 13
179 | 2 | Supply, installation, testing and commissioning of Wall surface mounting 2W CEILING SPEAKER with 6W/3W optionssuitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required. | nos | 1 |  |  |  | 1
Sub Total
180 | 3 | Digital PA System Supply, installation, testing and commissioning of MS Amplifier Rack Assembly with 30 minutes power backup including 1 no. CD player unit, 1 nos 300 W POWER AMPLIFIER, connectors, internal wiring, interconnection etc capable of voice operated priority complete as required. (PA System fully integrated type with Fire Alarm System with facility for automatic override of music for emergency announcements) | nos | 1 |  |  |  | 1
Sub Total
181 | 4 | Supply, installation, testing and commissioning of CONTROL PANEL with single zone selection, ascending 4 tone chime, emergency microphone, expandable upto 5 zones using expansion control panel complete as required. | nos | 1 |  |  |  | 1
Sub Total
182 | 5 | Supply, installation, testing and commissioning of Wireless lepal microphone DB technology complete as required | nos | 1 |  |  |  | 1
Sub Total
183 | 6 | Supply, installation, testing and commissioning of Microphone with table stand | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 1
184
185 |  | TOTAL SUB-HEAD IV carried over to Summary
186
187 | E | SUB HEAD V - CCTV SYSTEM
188
189 | 1 | Design, Engineering, Supply, Receiving, handling, storage, installation, testing and commissioning of the CLOSED CIRCUIT TELEVESION (CCTV) SURVEILLANCE SYSTEM with IP based indoor type fixed varifocal dome camera 2MP with resolution 1920x1080, IP67 with 30m IR range for the proposed application with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation. | nos
|  | C1 | nos | 1 |  |  |  | 1
|  | C2 | nos | 1 |  |  |  | 1
|  | C3 | nos | 1 |  |  |  | 1
|  | C4 | nos | 1 |  |  |  | 1
|  | C5 | nos | 1 |  |  |  | 1
|  | C6 | nos | 1 |  |  |  | 1
|  | C7 | nos | 1 |  |  |  | 1
|  | C8 | nos | 1 |  |  |  | 1
|  | C9 | nos | 1 |  |  |  | 1
|  | C10 | nos | 1 |  |  |  | 1
|  | C11 | nos | 1 |  |  |  | 1
|  | C12 | nos | 1 |  |  |  | 1
|  | Sub Total | [5 empty] | 12
|  | TENDER QTY | [5 empty] | 6
|  | AMENDED QTY | [5 empty] | 6
|  | TOTAL | [5 empty] | 12
190 | 2 | Supply of Network Video/Disk Recorder -16 channel (Including HDD for minimum recording of 30 days) with minimum 500GB Usable Space with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation. | nos | 1 |  |  |  | 1
Sub Total
191 | 3 | Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair with 24 AWG solid copper conductors in surface/concealed conduit/raceways complete as required | Mtrs |  |  |  |  | 0
192 |  | CCTV WIRING
193 |  | C1 | Mtrs |  | 11 |  |  | 11
194 |  | C2 | Mtrs |  | 17.1 |  |  | 17.1
195 |  | C3 | Mtrs |  | 19 |  |  | 19
196 |  | C4 | Mtrs |  | 22.4 |  |  | 22.4
197 |  | C5 | Mtrs |  | 24 |  |  | 24
198 |  | C6 | Mtrs |  | 19.9 |  |  | 19.9
199 |  | C7 | Mtrs |  | 24.8 |  |  | 24.8
200 |  | C8 | Mtrs |  | 19.4 |  |  | 19.4
201 |  | C9 | Mtrs |  | 27.8 |  |  | 27.8
202 |  | C10 | Mtrs |  | 22.1 |  |  | 22.1
203 |  | C11 | Mtrs |  | 8.5 |  |  | 8.5
204 |  | C12 | Mtrs |  | 8.2 |  |  | 8.2
Sub Total
206
207 |  | NON PO ITEM,S
208 | A | Supply & wiring of general power point with 2X4+2.5 Sq.mm PVC insulated multistranded copper conductor cable (FRLS) in surface/recess MS/PVC conduit including cutting the chases in wall & making good the same including providing & fixing of M.S. Switch & o modular range 1 No,s 6Amp Socket with 2M USB Charger port input 240v ,50Hz,/500mA, Out put 5V=3000ma modular cover plate, etc. complete as required. (First point)Supply of MS/PVC conduit included in this item.
210 |  | PBD-1 TO Pedestal furniture R1 | NO,S | 1 |  |  |  | 1
211 |  | PBD-1 TO Pedestal furniture R2 | NO,S | 1 |  |  |  | 1
212 |  | PBD-1 TO Pedestal furniture R3 | NO,S | 1 |  |  |  | 1
213 |  | PBD-1 TO Pedestal furniture R4 | NO,S | 1 |  |  |  | 1
214 |  | PBD-1 TO Pedestal furniture R9 | NO,S | 1 |  |  |  | 1
215 |  | PBD-1 TO Pedestal furniture R10 | NO,S | 1 |  |  |  | 1
216 |  | PBD-1 TO Pedestal furniture R11 | NO,S | 1 |  |  |  | 1
217 |  | PBD-1 TO Pedestal furniture Y1 | NO,S | 1 |  |  |  | 1
218 |  | PBD-1 TO Pedestal furniture Y2 | NO,S | 1 |  |  |  | 1
219 |  | PBD-1 TO Pedestal furniture Y3 | NO,S | 1 |  |  |  | 1
221 |  | PBD-1 TO Pedestal furniture Y9 | NO,S | 1 |  |  |  | 1
222 |  | PBD-1 TO Pedestal furniture Y10 | NO,S | 1 |  |  |  | 1
223 |  | PBD-1 TO Pedestal furniture B1 | NO,S | 1 |  |  |  | 1
224 |  | PBD-1 TO Pedestal furniture B2 | NO,S | 1 |  |  |  | 1
225 |  | PBD-1 TO Pedestal furniture B3 | NO,S | 1 |  |  |  | 1
Sub Total
| a) | Supply & wiring of general power point with 2X4+2.5 Sq.mm PVC insulated multistranded copper conductor cable (FRLHS) in surface/recess MS/PVC conduit including cutting the chases in wall & making good the same including providing & fixing of M.S. Switch & o modular range 1 No,s 6Amp Socket with 2M USB Charger port input 240v ,50Hz,/500mA, Out put 5V=3000ma modular cover plate, etc. complete as required. (Secondary loop point)Supply of MS/PVC conduit included in this item.
SECONDARY LOOP POINT
|  | R8 LOOP |  | 1 |  |  |  | 1
|  | Y8 LOOP |  | 2 |  |  |  | 2
|  | Y11 LOOP |  | 2 |  |  |  | 2
|  | B8 LOOP |  | 1 |  |  |  | 1
|  | B11 LOOP |  | 1 |  |  |  | 1
Sub Total
| B | Supply & wiring of general power point with 2X4+2.5 Sq.mm PVC insulated multistranded copper conductor cable (FRLHS) in surface/recess MS/PVC conduit including cutting the chases in wall & making good the same including providing & fixing of M.S. Switch & o modular range 2No,s 6Amp switch with 3 pin 6Amp socket, modular cover plate, etc. complete as required. (First point)Supply of MS/PVC conduit included in this item. | No,s
226 |  | PBD-1 TO Square Table 2No,s switch & socket 6A,
228 |  | PBD-1 TO Square table R6 | NO,S | 1 |  |  |  | 1
229 |  | PBD-1 TO Square table R7 | NO,S | 1 |  |  |  | 1
230 |  | PBD-1 TO Square table Y5 | NO,S | 1 |  |  |  | 1
231 |  | PBD-1 TO Square table Y6 | NO,S | 1 |  |  |  | 1
232 |  | PBD-1 TO Square table B5 | NO,S | 1 |  |  |  | 1
233 |  | PBD-1 TO Square table B6 | NO,S | 1 |  |  |  | 1
Sub Total
| b) | Supply & wiring of general power point with 2X4+2.5 Sq.mm PVC insulated multistranded copper conductor cable (FRLHS) in surface/recess MS/PVC conduit including cutting the chases in wall & making good the same including providing & fixing of M.S. Switch & o modular range 2No,s 6Amp switch with 3 pin 6Amp socket, modular cover plate, etc. complete as required. (Secondary loop point)Supply of MS/PVC conduit included in this item.
236 |  | SECONDARY LOOP POINT
238 |  | LOOP TO Square table R6 | NO,S | 1
239 |  | LOOP TO Square table R7 | NO,S | 1 |  |  |  | 1
240 |  | LOOP TO Square table Y5 | NO,S | 1 |  |  |  | 1
241 |  | LOOP TO Square table Y6 | NO,S | 1 |  |  |  | 1
242 |  | LOOP TO Square table B5 | NO,S | 1 |  |  |  | 1
243 |  | LOO TO Square table B6 | NO,S | 1 |  |  |  | 1
245 |  |  | NO,S | 1 |  |  |  | 1
Sub Total
247 | C | Supplying and fixing heavy gauge ISI embossed black enameled FRLSH GI recessed and/or surface conduits including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting complete as per specifications, as required and as below.
248 | 1 | 25 mm Dia Ms CONDUIT | Mtrs
249 |  | PA SYSTEM CONDUIT | Mtrs
250 |  | AMPLIFIER TO SP1 | Mtrs |  | 5.5 |  |  | 5.5
251 |  | SP1 TO SP2 | Mtrs |  | 5.4 |  |  | 5.4
252 |  | SP1 TO SP3 | Mtrs |  | 2.5 |  |  | 2.5
253 |  | SP1 TO SP4 | Mtrs |  | 4.9 |  |  | 4.9
254 |  | SP1 TO SP5 | Mtrs |  | 8.1 |  |  | 8.1
255 |  | SP1 TO SP6 | Mtrs |  | 6.5 |  |  | 6.5
256 |  | SP1 TO SP7 | Mtrs |  | 5.6 |  |  | 5.6
257 |  | SP1 TO SP8 | Mtrs |  | 1.3 |  |  | 1.3
258 |  | SP1 TO SP9 | Mtrs |  | 2.8 |  |  | 2.8
259 |  | SP1 TO SP10 | Mtrs |  | 5.9 |  |  | 5.9
260 |  | SP1 TO SP11 | Mtrs |  | 8.8 |  |  | 8.8
261 |  | SP1 TO SP12 | Mtrs |  | 6.8 |  |  | 6.8
262 |  | SP1 TO SP13 | Mtrs |  | 3.6 |  |  | 3.6
263 |  |  | Mtrs
264 |  | NVR TO DATA/VOICE CONDUIT | Mtrs
265 |  | NETWORK RACK TO D1 | Mtrs |  | 25 |  |  | 25
266 |  | D2,V1 | Mtrs |  | 25 |  |  | 25
267 |  | D3 | Mtrs |  | 17.5 |  |  | 17.5
268 |  | D4 | Mtrs |  | 22.5 |  |  | 22.5
269 |  | D5,V2 | Mtrs |  | 21.5 |  |  | 21.5
270 |  | D6,D7 | Mtrs |  | 18 |  |  | 18
271 |  | D9,DB | Mtrs |  | 18.8 |  |  | 18.8
272 |  | D10,V3 | Mtrs |  | 18.5 |  |  | 18.5
273 |  | D11,D12,V4 | Mtrs |  | 10 |  |  | 10
274 |  | D13,V5 | Mtrs |  | 15.5 |  |  | 15.5
275 |  |  | Mtrs
276 |  | CCTV WIRING CONDUIT | Mtrs
277 |  | C1,C6 | Mtrs |  | 17.9 |  |  | 17.9
278 |  | C2,C9,C10 | Mtrs |  | 22.4 |  |  | 22.4
279 |  | C3,C8 | Mtrs |  | 15.4 |  |  | 15.4
280 |  | C4,C5,C7 | Mtrs |  | 18.6 |  |  | 18.6
281 |  | C11.C12 | Mtrs |  | 2.5 |  |  | 2.5
Sub Total
283
| D | Supply & installation of GI Earth Bus of size 50 x 6 x 300 mm long with insulator support for earth bus
284 |  | SUP&INST OF GI EARTH BUS 50X6X300MM Electrical room | No,s |  | 1 |  |  | 1
Sub Total

## HVAC
INTERNATIONAL CIP LOUNGE_JAI T2_HVAC
Part II | HVAC
SECTION-"A" AIR-CONDITIONING SYSTEM
1.0 | EQUIPMENT
|  | UOM | BOQ QTY | BOQ RATE | BOQ AMOUNT | RAB -02 SUBMITTED BOQ | RAB -02 SUBMITTED AMOUNT | RA-2 CHECKED TENDER QTY | RA-2 CHECKED TENDER AMOUNT | RA-2 CHECKED AMD QTY | RA-2 CHECKED AMD AMT
1.1 | VENTILATION FANS
1.1.1 | INLINE FANS WITHOUT FILTER
Supply, installation, testing and commissioning of duct mounted IN-LINE FANS for exhaust air as shown in drawings. Each fan shall be complete with motor, mounting flanges, accessories like bird screen, fixed louvers and GI sheet canopy for weather protection as required. Quoted price shall be inclusive of electronic speed regulator and wiring between fan & speed regulator for single phase fans. Incase of 3 phase fans quoted price shall be inclusive of DOL starter panel with cabling between starter panel and fan.
Quoted prices shall be inclusive of all necessary supports by MS structural steel if required, hangers, clamp supports from walls, floors and ceiling with painting with one coat of primer and two coats of paint to supports of MS work.
Fan Selection arrangement shall be as follows:
Fan Capacity S.P Area to
No. (Cfm) (mmWG) to be exhausted
a. | IF-1(Circular) 300 16-17 Store | No | R/o | 9604
Contactor to check/calculate static pressure drop as per shop drawing.
| TOTAL ITEM NO. 1 (EQUIPMENT) |  |  | Rs. | 0
2 | AIR DISTRIBUTION
2.1 | Supply, installation and testing of SITE Fabricated GI sheet metal ducts as per IS-655 Standard in accordance with the approved shop drawings as required by the specifications. Quoted price shall be inclusive of all necessary supports by MS structural steel if required, hangers, clamp supports from walls, floors and ceiling including cutting holes and chases in brick, R.C.C. work, making good the same to original condition complete in all respects with painting with one coat of primer and two coats of paint to supports of MS work. Quoted price shall be inclusive of scaffolding work as required. Note:All exposed surfaces & duct shall be painted in black mat finish by the HVAC contractor.
2.1.1 | 24 gauge galvanised sheet steel (0.63 mm) | Sqm. | 225 | 1440.6 | 324135 | 197.645 | 284727.387 | 104.785 | 150953.271 |  | 0
2.1.2 | 22 gauge galvanised sheet steel (0.8 mm) | Sqm. | 5 | 1728.72 | 8643.6 | 37.9 | 65518.488 | 5 | 8643.6 | 22.5 | 38896.2
2.1.3 | 20 gauge galvanised sheet steel (1.0 mm) | Sqm. | 5 | 2112.88 | 10564.4
2.1.4 | 18 gauge galvanised sheet steel (1.25 mm) | Sqm. | R/o | 2881.2
2.1.5 | Dismantling of existing supply air ducts which are supplied the existing AHU supply withing new development of CIP Lounge. | Sqm. | 600 | 144.06 | 86436 | 231.45 | 33342.687 |  | 0
2.1.6 | Dismantling of glass panel towards façade to run the exhaust & fresh air ducts. | Sqm. | 50 | 192.08 | 9604
2.2 | Supply, Installation,Testing and Balancing of flexible ducting comprising of inner as well as outer skin constructed out of aluminium & fibre glass insulation 25mm thick of minimum 24 kg/cu.m density insulation sandwitched in between. Duct should confirm to fire rating standards BS-476 part 5, 6 & 7. Flexible Ducts of following sizes as per approved shop drawings, specifications :
2.2.1 | 350 mm dia. | Mtr. | RO | 1920.8
2.2.2 | 300 mm dia. | Mtr. | RO | 1824.76
2.2.3 | 200 mm dia. | Mtr. | RO | 1680.7
2.2.4 | 150 mm dia. | Mtr. | RO | 1440.6
2.2.5 | 100 mm dia. | Mtr. | RO | 1344.6
2.3 | Supply, installation and testing of GI construction Opposed blade Volume control dampers within ducts to be provided with suitable ducts lever and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system. | Sqm. | 1.5 | 9604 | 14406
2.4 | Supply, installation, testing and balancing of powder coated Extruded Aluminium Supply Air Grilles with multiblade type key operated grille louver dampers in accordance with the approved shop drawings and specifications. | Sqm. | 3.5 | 9604 | 33614 | 4.6 | 44178.4 |  | 0
2.5 | Supply, installation, testing and balancing of powder coated extruded Aluminium Exhaust/Return Air Grilles without multiblade type grille louver dampers | Sqm. | 3 | 8163.4 | 24490.2 | 1.96 | 16000.264 |  | 0
0
2.6 | Supply, installation, testing and balancing of Powder coated extruded aluminium construction square / round shape Supply Air Diffusers with removable core & anti smudge ring & key operated volume control dampers as per approved drawings and specifications. | Sqm. | RO | 12965.4
0
2.7 | Supply, installation, testing and balancing of Powder coated extruded aluminium construction square / round shape Return Air Diffusers as per approved drawings and specifications. | Sqm. | RO | 14406
0
2.8 | Supply, installation, testing and balancing of Powder coated/Anodised extruded aluminium construction. Louvers with bird screen for exhaust air as per specifications and approved drawings. | Sqm. | 0.5 | 9604 | 4802 | 1 | 9604 |  | 0
0
2.9 | THERMAL INSULATION |  |  | 0
0
2.9.1 | THERMAL INSULATION FOR DUCTWORK |  |  | 0
| Supply and Application of external thermal insulation of supply /return air ducting using closed cell elastomeric nitrile rubber insulation with class 'O' fire retardant properties as per the specifications and drawings. Quoted price shall be inclusive of adhesive, tapes as per specification. insulation shall be provided with aluminium foil, factory laminated. |  |  | 0
| Insulation thickness/application will be as per approved shop drawing notes. |  |  | 0
a. | 25 mm thick | Sqm | RO | 2401
b. | 19 mm thick | Sqm | RO | 2016.84
c. | 16 mm thick | Sqm | RO | 1728.72
d. | 13 mm thick | Sqm | 225 | 1200.56 | 270126 | 258.5 | 310344.76 | 0 | 0
e. | 9 mm thick | Sqm | RO | 1152.48
0
2.9.2 | ACOUSTIC LINING OF DUCTS |  |  | 0
0
| Supply and Application of internal acoustic lining of supply air ducting using open cell nitrile rubber insulation with density within 140-180 Kg/m3 as per the approved shop drawings and specifications. Insulation material shall be bonded with the ducts using metal screw and washers to facilitate grip to the GI sheet. |  |  | 0
0
a. | 10mm thick lining | SqM | 20 | 1200.5 | 24010 |  | 0
b. | 25mm thick lining | SqM | R/o | 1920.8
0
2.1 | Air Transfer Grilles |  |  | 0
| Supply, Installation and testing of extruded aluminium powder coated air transfer grilles to be provided at the door of toilets/pantry. | SqM | 0.2 | 14406 | 2881.2 |  | 0
| TOTAL ITEM NO. 2 (AIR DISTRIBUTION) |  |  |  | 813712.4 |  | 763715.986 |  | 159596.871 |  | 38896.2
| TOTAL "SECTION-A" |  |  | Rs. | 813712.4 |  | 763715.986 |  | 159596.871 |  | 38896.2
SECTION-B: KITCHEN VENTILATION SYSTEM (COOKING KITCHEN)
1.0 | EQUIPMENT
1.1.1 | Supply, Installation, Testing and Commissioning of Dry Type Scrubber each comprising of extract air intake section, electrostatic precipitation technology, dry type air cleaner to remove oil, smoke and fumes from exhaust air, as per the Specifications.
Electrostatic section shall be made of 16/18 gauge galvanised sheet, high baked epoxy powder coated, washable type aluminium mesh filters, stainless steel spiked ionizers to create high voltage DC field, aluminum collector plates which should be alternatively charged positive and negative with large collecting area with 14" deep cell, to work as magnet for charged smoke and oil particles. Average efficiency of 90-95% in single pass as per ASHRAE test method. Electrostatic Precipitator should be able to charge particles from 0.01 micron to 10 microns through solid state power supply. Collector cell should be of permanent type and incorporate slide out facility for easy removal for cleaning. Power supplies shall be 100% solid state UL Listed, Module of capacity above 3000 CFM shall be equipped with Pulse width modulating (PWM)The system should be fitted with interlock switch for safety . The system should allow connection to a fan section to achieve 500 FPM velocity across the air cleaner. Vendor to include cost of MCB & single phase wiring for AC supply to the Scrubber.
Operating Voltage : 220V, 50 Hz Ionizing Voltage : 12.5 to 13 KVDC Collector Cell Voltage : 6 to 6.5 KVDC Power Consumption : Not more than 50W per cell.
The Scrubber Machines (EAC) shall be of following duty parameters :
M/c No Capacity (CFM)
| AS-1 3000 | No | 1 | 216090 | 216090 | 1 | 216090 | 1 | 216090
0
1.1.2 | Supply, installation, testing and commissioning of single width single inlet class I centrifugal fans for ventilation system. Each fan shall be complete with totally enclosed fan cooled motor, belt drive, pulley mounted on motor (IE2) with efficiency ≥60 % & fan shaft, belt guard, motor mount and vibration isolators. The motor shall be suitable for 415±10% volts 3 phase 50 cycles, AC supply. The motor selected shall be energy efficient having efficiency at full load ranging between 82.5% to 92% in accordance with motor rating as per specification. Fan capacities shall be as follows: |  |  | 0
0
| M/c No Capacity (CFM) S.P (mm) Motor (HP) Area |  |  | 0
0
| AS-1 3000 75 1.5 Kitchen | No | 1 | 105644 | 105644 | 1 | 105644 | 1 | 105644
0
1.1.3 | Supply, Installation, Testing & Commissioning of direct driven TUBE/VANE AXIAL FLOW FAN. Vane Axial flow fan for Normal Fresh air supply. Fan motor shall be suitable for 415 ± 10% volts, 50 cycles, 3 phase power supply with high efficiency, IE-3 type for normal application and fan total efficiency should not be less than 65%. The fan shall be equipped with mounting bracket & spring isolators for the installation of the fans. Fan static pressure shall be as indicated but actual duting & fan static pressure to be checked by vendor. Fan shall be with fire proof flexible connection at inlet and outlet. Noise level for normal application fans shall be less than 70 dbA @1 meter distance. If required, shall be included to meet the desired sound levels. All Fans shall be with back draft damper and cost will be included in the cost. |  |  | 0
| Description CFM ESP (mm.of wg) Suggested Motor kW |  |  | 0
| Kitchen Fresh Air 1500 40 0.75 | No | 1 | 57624 | 57624 | 1 | 57624 | 1 | 57624
0
| TOTAL ITEM NO. 1 (EQUIPMENT) |  |  | 0 | 379358 |  | 379358 |  | 379358 |  | 0
0
2 | AIR DISTRIBUTION |  |  | 0
0
2.1 | Supply, installation and testing of SITE Fabricated GI sheet metal ducts as per IS-655 Standard in accordance with the approved shop drawings as required by the specifications. Quoted price shall be inclusive of all necessary supports by MS structural steel if required, hangers, clamp supports from walls, floors and ceiling including cutting holes and chases in brick, R.C.C. work, making good the same to original condition complete in all respects with painting with one coat of primer and two coats of paint to supports of MS work Note:Note:All kitchen exhaust duct shall be painted with fire rated paint tested by CBRI & BS 476 part 6,7,20&24. |  |  | 0
0
2.1.1 | 24 gauge galvanised sheet steel (0.63 mm) | Sqm. | 130 | 1440.6 | 187278 | 82.89 | 119411.334 |  | 0
2.1.2 | 22 gauge galvanised sheet steel (0.8 mm) | Sqm. | 10 | 1632.68 | 16326.8 | 79.44 | 129700.0992 |  | 0
2.1.3 | 20 gauge galvanised sheet steel (1.0 mm) | Sqm. | 5 | 1920.8 | 9604
2.1.4 | 18 gauge galvanised sheet steel (1.25 mm) | Sqm. | 0 | 2881.2 | 0
0
0
2.2 | Supply, installation and testing of GI construction Opposed blade Volume control dampers within ducts to be provided with suitable ducts lever and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system. | Sqm. | 0.5 | 9604 | 4802 | 1.25 | 12005 |  | 0
0
2.3 | Supply, installation, testing and balancing of Powder coated extruded aluminium construction square / round shape Supply Air Diffusers with removable core & anti smudge ring & key operated volume control dampers as per approved drawings and specifications. | Sqm. | 2 | 12485.2 | 24970.4
0
2.4 | Supply, installation, testing and balancing of Powder coated extruded aluminium construction square / round shape Return Air Diffusers as per approved drawings and specifications. | Sqm. | RO | 14406
0
2.5 | Supply, installation, testing and balancing of Powder coated/Anodised extruded aluminium construction. Louvers with bird screen for exhaust air as per specifications and approved drawings. | Sqm. | 1 | 11524.8 | 11524.8
0
2.6 | Supply, Installation, Testing of 125mm deep antivibration flexible joints at the outlet of air handling units/ductable split units//inline fans. Flexible connections shall be constructed using imported fire retardant fabric with extruded aluminium frame/flange on both sides of approved make. | RM | 1 | 4802 | 4802
0
2.7 | THERMAL INSULATION |  |  | 0
0
2.7.1 | THERMAL INSULATION OF DUCTS-(FOR AIR SCRUBBER DUCT) |  |  | 0
| (Using Factory Laminated fibre glass insulation) |  |  | 0
0
| Supply and Application of external thermal insulation of ducting using aluminium foil faced fibre glass insulation of density not less than 24Kg/CuM and aluminium foil thickness of 22 microns as per the specifications and drawings. |  |  | 0
a. | 25mm thick | SqM | RO | 960.4
b. | 50mm thick | SqM | RO | 1440.6
0
2.7.2 | THERMAL INSULATION OF DUCTS-(FOR AIR SCRUBBER DUCT) - EXPOSED |  |  | 0
| (Using Factory Laminated fibre glass insulation) |  |  | 0
0
| Supply and Application of external thermal insulation of ducting using aluminium foil faced fibre glass insulation of density not less than 24Kg/CuM and aluminium foil thickness of 22 microns as per the specifications and drawings. Insulation shall be covered necessary glass cloth & UV protection paint. |  |  | 0
0
a. | 25mm thick | SqM | RO | 1200.5
b. | 50mm thick | SqM | RO | 1920.8
0
2.7.3 | THERMAL INSULATION FOR EXPOSED DUCTS-AIR WASHER DUCT |  |  | 0
0
| Supply and Application of external thermal insulation of supply air ducting using closed cell elastomeric nitrile rubber insulation with class 'O' fire retardant properties as per the specifications and drawings. Quoted price shall be inclusive of adhesive, tapes as per specification. insulation shall be provided with necessary glass cloth & UV protection paint for ducts exposed to atmosphere as per specifications. |  |  | 0
0
a. | 25 mm thick | Sqm | RO | 2401
a. | 19mm thick | SqM | RO | 2016.84
0
2.7.4 | THERMAL INSULATION FOR DUCTWORK-AIR WASHER DUCT IN AC AREA |  |  | 0
| Supply and Application of external thermal insulation of supply /return air ducting using closed cell elastomeric nitrile rubber insulation with class 'O' fire retardant properties as per the specifications and drawings. Quoted price shall be inclusive of adhesive, tapes as per specification. insulation shall be provided with aluminium foil, factory laminated. |  |  | 0
0
a. | 25 mm thick | Sqm | RO | 1920.8
| TOTAL ITEM NO. 2 (AIR DISTRIBUTION) |  |  | Rs. | 259308 |  | 261116.4332 |  | 0
3 | ELECTRICAL WORKS
3.1 | VENTILATION FAN PANELS
Design, manufacture, supply, installation, testing and commissioning of the following cubicle type, dead front, sheet steel, wall mounted control panels, including anchoring into the wall. Incoming wiring terminating into MCCB and G.I. earthing, in each panel shall be provided by the electrical contractor. All outgoing shall be provided with Stop /Manual /Auto selector switch to facilitate operation through BAS. All starters shall be provided with potential free Contact for Connections to Building Automation System.
The panel shall include the following components & accessories.
MCCB/MCB as per the ratings given below, suitable for motor duty and able to withstand fault level of 20 KA.
DOL / SD starter as per HP ratings given.
Terminal block for power distribution as required.
Contactor, over load relay with built in single phasing protection.
Phase indicating lights and indicating light for ON/ Trip status & ON/ Off push button.
144 mm x 144 mm voltmeter and digital ammeter.
Time delay relay for delayed automatic restart of motor.
Wiring for microswitch for stopping the fan.
For on/off/remote and local operation, 3 pole single throw switch shall be provided in each panel to facilitate override of the automatic operation.
All starters shall be provided with suitable potential free contract for connections to the Building Automation System.
All Cable trays shall be MS Powder coated and Conduits shall be MS.
The number of control panels shall be as follows.
3.1.2 | KVF PANEL (Location: Terrace IP 65)
For Scrubber, 1.5KW
| Suitable rating MPCB along with 1.5 HP DOL starter | No | 1 | 72030 | 72030 | 1 | 72030 | 1 | 72030 | 1 | 72030
| 1 No. 25 Amp single Phase switch socket & control Cable for interlocking between scrubber & fan shall be included. |  |  | 0
0
3.1.3 | Suitable Rating TP MPCB for 0.75 kW DOL Starter | No | 1 | 14406 | 14406 | 1 | 14406 | 1 | 14406 | 1 | 14406
0
3.2 | CABLING |  |  | 0
0
3.2.1 | Supply, laying, affecting connections and Testing of the following sizes of 1.1 KV armoured PVC insulated aluminium/ copper conductor cables. Cables shall be inclusive of all clamps, saddles, screws, cable identification tags, cable terminal joints including terminal lugs, insulating tapes, affecting terminal connections to the equipment as per the specifications and as required. Quoted price shall be inclusive of perforated duly painted 2mm thick MS trays to be installed inside and GI trays to be installed outside exposed and 8SWG copper earth wire for all equipment except chillers for which 32mmx6mm GI strip shall be used. All cables shall be LSHF type. |  |  | 0
0
a. | 3 C x 6 Sqmm cable (Copper) | RM | 10 | 720.3 | 7203 | 10 | 7203 | 0 | 0
b. | 3 C x 4 Sqmm cable (Copper) | RM | 50 | 672.28 | 33614 | 50 | 33614 | 0 | 0
c. | 3 C x 2.5 Sqmm cable (Copper) | RM | 10 | 576.24 | 5762.4
d. | 3 C x 2.5 Sqmm cable( Copper Control cabling) | RM | 10 | 576.24 | 5762.4
e. | 3 C x 1.5 Sqmm cable(Copper Control cabling) | RM | 50 | 576.24 | 28812
1.1 KV dielectric strength in front of
| each panel. | RM | 1 | 1800
| TOTAL ITEM NO. 3 (ELECTRICAL) |  |  | Rs.
TOTAL "SECTION-B"
Part III | PL & FF
A | SANITARY FIXTURES AND FITTINGS
Note:
a) | All Sanitary fixtures including bottle traps (from approved make list), shall be issued free of cost by the "Employer". The contractor rates to include for supply all fixing/supporting accessories like nuts, bolts, screws, hangers, rubber buffers, CI or MS brackets, anchor fastners, sealents, washers, adhesives, Flanges, plumber's tape, white cement, masking tape (if required for protection), which are required for the successful installation of the fixtures/fittings in a neat workman like manner.
b) | Rates are inclusive of fixing/ work at all the heights, depths and locations within the project premises.
c) | Rates are inclusive of fixing/work for underslung plumbing system or embeded piping. Mostly, all the toilets in the residencial units have been designed for under slung piping.
d) | Provision of extension piece for final connection of CP fitting shall be supplied and installed by the contractor accordingly (as required)
e) | All pressure pipe will be tested on 1.5 times of there working pressure
1 | Providing, Supply, installation, testing and commisning of white vitreous china Wall mounted type "European" water closet pan with seat cover, closed coupled dual flush cistern (with all internal moving parts) with PVC heavy duty connectors, bolts, nuts, supporting arrangements, bakelite seat & cover with CP hinges & rubber buffers, P or S trap, connection to main pipe on shaft complete with all accessories including cutting & making good masonry holes/chasing in the walls & floors wherever required & health faucet with regulator with flexible pipe 1.5 m long, wall hooked complete as required, with all required accessories that includes Flush Plate ,bib cock made of CP brass complete as required. | No. | 9 | 14400
2 | Providing, Supply, installation, testing and commisning of white vitreous china "Floor mounted" type Composite Water closet (European type W.C. pan) with seat and lid, including with white Vitreous Chinaware matching Cistern complete with all accessories , also including with matching W.C. Pan with ISI marked white/Black solid plastic seat and Lid.Details of COST of one Pan composite with Cistern, Flush Pipe, EWC & Cistern complete with Fittings & Seat Cover,and one no. of Faucet for WB,with all required accessories that includes bib cock made of CP brass complete as required. (for Handicapped person's Toilet) | No. | 1 | 17725
3 | Providing and fixing white vitreous china rectangular Half pedestal Wash Basin & its accessories etc, also with all fittings and fixtures complete including cutting and making good the walls and floors wherever required. (for Handicapped person's Toilet) (colour- Star White) painted white, 32mm C.P. waste coupling, 32mm dia C.P. bottle trap and connection pipe upto wall with wall flange and rubber adopter for waste connection, complete including cutting and making good the walls, wherever required. | No. | 1 | 7130
4 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass basin mixer top mounted with C.P. wall flange of approved quality | No. | 12 | 3400
5 | Providing, Supply, installation, testing and commisning of CP Grab Bar swing type (in horizontal & vertical grabbing) & Grab rails 60 cm, complete including cutting and making good the walls, wherever required. | No. | 1 | 7700
6 | Providing, Supply, installation, testing and commisning of CP Grab rails 60 cm, complete including cutting and making good the walls, wherever required. | No. | 1 | 2425
7 | Providing, Supply, installation, testing and commisning of C.P. toilet paper holder with roller, with C.P brass screws, complete including cutting and making good the walls wherever required. | No. | 10 | 1100
8 | Providing, Supply, installation, testing and commisning of C.P. brass double towel rack 100mm wide and 600 long fixed with C.P. brass screws including cutting and making good the walls wherever required. | No. | 2 | 2600
9 | Providing, Supply, installation, testing and commisning of C.P twin Robt hook, fixed to wooden cleats with C.P. brass screws including cutting and making good the walls wherever required. | No. | 10 | 360
10 | Providing, Supply, installation, testing and commisning of Twin manual 0.5 liter liquid soap dispenser with simple push lever fitted with liquid soap (one time),C.P. brass screws including cutting and making good the walls wherever required. | No. | 8 | 3410
11 | Providing, Supply, installation, testing and commisning of Automatic liquid soap dispenser with simple push lever fitted with liquid soap (one time),C.P. brass screws including cutting and making good the walls wherever required. | No. | 1 | 3100
12 | Providing, Supply, installation, testing and commisning of SS Baby Diaper changing station with all its accessories and components | No. | 1 | 44150
13 | Providing, Supply, installation, testing and commisning of SS 204 Grade Bin | No. | 13 | 1770
14 | Providing, Supply, installation, testing and commisning of C.P. Paper Towel Dispenser,with C.P brass screws, complete including cutting and making good the walls wherever required. | No. | 6 | 1925
15 | Providing and fixing white vitreous china rectangular wash basin under / over counter mounting, specially fabricated brackets to support the wash basin as per standard practice, painted white, 32mm C.P. waste coupling, 32mm dia C.P. bottle trap and connection pipe upto wall with wall flange and rubber adopter for waste connection, complete including cutting and making good the walls, wherever required. | No. | 11 | 5150
16 | Providing, Supply, installation, testing and commisning of Rain shower and total rain shower assembly including Concealed stop cock, long body bib cock & short body bib cock including wall chasing etc complete in toilet,with all required accessories for shower. | No. | 2 | 520
17 | Providing, Supply, installation,testing and commissioning of Stainless steel shower drain channel 100 mm wide 800 mm length (max.) suitable to connect 50 mm drain outlet. | No | 2 | 44700
18 | Providing, fixing, testing and commissioning of white viterous china large flat back / half stall urinal supported by CI / MS bracket (duly painted with 2 coats of paints over a coat of primer), including CP brass waste with dome type grating, CP cast brass bottle trap with extension piece, wall flanges complete with all accessories & urinal partition with concealed CI bracket, cutting and making good, Including battery operated sensor based automatic flushing system for urinals, including sensor and required electrical and water connections etc, complete in all respect to make it fully functional including cutting and making good the walls etc. | No. | 6 | 2100
19 | Providing, Supply, installation, testing and commissioning of Stainless steel sink 304 Grade SS, Matt Finish medium size (220X440X200) supported by CI / MS Brackets duly painted, CP cast brass bottle trap with extension piece, rubber adaptor, CP copper connecting pipes, wall flange, union, CP brass chain, rubber plug, nuts, washers, waste connection complete & making good the walls, floor wherever required. | No. | 2 | 17500
20 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass with dual lever faucet with C.P. wall flange of approved quality | No. | 2 | 3410
21 | Providing, Supply, installation, testing and commisning of C.P. brass angle valve with C.P. wall flange, Nut and Washer etc. complete as required for 15 mm & 20 mm dia | No. | 30 | 560
22 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass bib cock with C.P. wall flange of approved quality | No. | 2 | 340
23 | Providing, Supply, installation,testing and commissioning of Stainless steel sink (Single bowl with drainboard sink) 304 Grade SS,Matt Finish medium size 1000 X 500MM) supported by CI / MS Brackets duly painted, CP cast brass bottle trap with extension piece, rubber adaptor, CP copper connecting pipes, wall flange, union, CP brass chain, rubber plug, nuts, washers, waste connection complete & making good the walls, floor wherever required. | No. | 3 | 11100
24 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass sink mixer (wall mounted ) with 150 MM swivel spout, with C.P. wall flange of approved quality | No | 3 | 6625
25 | Providing, Supply, installation,testing and commissioning of High Speed hand dryer suitable to be operated with 230 volts, single phase, with fully hygienic operations with all accessories including cutting and making good the walls, wherever required. | No. | 6 | 12700
26 | Providing and fixing CP Brass 32mm size Bottle Trap of approved quality & make and as per the direction of Engineer-in-charge. | No. | 14 | 975
27 | Providing, Structural steel members in position at all levels and at all heights as specified in the drawings made out of standard MS sections consisting of MS angles, ISMC, ISMB conforming to local & international standards Cost to include fabricating necessary Gusset Plates, Stiffener plates, Brackets, Bolts, Cleats, seating angles etc., to the required size, shape, alignment etc, as per the drawings. Cost to include welding of members using structural steel welding electrodes as per ocal & international standards , necessary equipments, tools and tackles, staging, scaffolding required etc.,complete. including a coat of zinc chromate primer. | KG | R/O | 61
Total
B | WATER SUPPLY
28 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain & brass threaded fittings, including fixing the pipe with clamps at 1.00 m spacing. This includes jointing of pipes & fittings with one step CPVC solvent cement and testing of joints complete as per direction of Engineer in Charge.
Internal work - Exposed on wall
| 15 mm dia | RM | 185 | 255.9
| 20 mm dia | RM | 110 | 325.1
| 25 mm dia | RM | 40 | 408.55
| 32 mm dia | RM | 30 | 500.95
| 40 mm dia | RM | 25 | 674.35
| 50 mm dia | RM | 25 | 927
| 65 mm dia | RM | 5 | 1576.9
29 | Providing and fixing CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure - 7 Bar @ 82 Deg C and 28 Bar @ 23 Deg C)for pipes from 1/2 Inch to 2 Inch. Schedule 40 Pipe to be used from 2-1/2 Inch to 6 Inch. Pipes shall be joined using solvent welded CPVC fittings i.e. Tees, Elbows, Couplers, Unions, Reducers, brushings etc. including transition fittings (connection between CPVC & metal pipe/GI) i.e. Brass Adaptors (both Male & Female threaded) conforming to ASTM D-2846. ASTM F441 with only CPVC solvent cement conforming to ASTM F-493.
Cost shall be inclusive of (a)Making maximum of 7.5 x 7.5 cm chasing in wall and floors for the pipe, making good the same by using 1:1 cement mortar over the wire mesh and providing protection to embedded pipes and fittings (in wall chase) by wrapping two layers of 400 micron polythene sheet including proper overlaps on joints complete as required or (b) Fixing/supporting the pipes (& fittings) at wall/ceiling level supported by galvanized clamps, hangers etc, as per specification. Exposed pipes to be painted of legends with direction arrow. GI pipe sleeves suitable higher size shall be provided wherever the pipes are crossing the fire rated walls / floors slab and sealing the sleeves with glass wool in between and fire sealant compound at either end all as per Project Manager's / Consultant requirement. All termination points for installation of faucets shall have brass termination fittings. Installation shall be to as per Technical Manual of manufacturer of pipes & fittings.
| 15 mm dia | RM | 305 | 441.15
| 20 mm dia | RM | 12 | 513.75
| 25 mm dia | RM | 5 | 626.05
30 | Providing & fixing full way lever operated forged brass ball valve of brass body with forged brass hard chromeplated steel ball tested to a pressure not less than 15 Kg / sqcm with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc.
| 20 mm dia | Nos. | 3 | 559.792
| 25 mm dia | Nos. | 1 | 867.536
| 32 mm dia | Nos. | 2 | 1482.08
| 40 mm dia | Nos. | 1 | 2157.984
31 | Providing & fixing of butterfly valve (PN 16) with flanges, nut bolts, gaskets and necessary pad locking arrangement complete required.
| 50 mm dia | Nos. | 1 | 2929.232
| 65 mm dia | Nos. | 1 | 3134.08
32 | Supplying, laying/ fixing, testing and commissioning of following thickness resin bonded fiber glass pipe section insulation having density 80 kg/cum or mineral wool (non combustible) having density of 144 Kg/ cu m duly covered with a layer of 120 gm/sqm polythene sheet (vapour barrier) on existing pipe and finally applying 0.63mm aluminium sheet cladding complete with type3 , grade 1 roofing feltstrip(as per IS:1322 as amended up to date ) at joints etc. as per specifications and as required.
| 25 mm thick mineral wool insulation (15 mm dia) | RM | 86.4252 | 853
| 25 mm thick mineral wool insulation (20 mm dia) | RM | 6.2083 | 986
| 25 mm thick mineral wool insulation (25 mm dia) | RM | 0.64998 | 1075
| 25 mm thick mineral wool insulation (32 mm dia) | RM | 1.0291 | 1185
| 25 mm thick mineral wool insulation (40 mm dia) | RM | 0.81247 | 1349
Total
C | DRAINAGE
33 | Providing, Supply, installation,testing and commissioning of UPVC Soil, Waste & Vent system conforming to IS : 13592 - Type B and UPVC fittings (moulded as well as fabricated) like bends, tees, Y-tees, crosses, boss connections, access pieces, saddle pieces, cleanouts, adaptors for connections to other materials, plugs, reducers, cowls, offSet and other specials. Jointing shall be done with pushfit EPDM ring jointing technique in general. Solvent cement joints may be provided for fittings and specials which are not manufactured with pushfit rubber joints. Pipes may be laid / fixed in sunken floors, under slung from ceiling. The pipes laid in sunken floor shall be encased with 75 mm thick cement concrete (1:2:4) all around. The installation shall be complete in all respects including cutting chases / holes in walls, slabs and making good the same as per specifications.
Providing GI pipe sleeves of suitable higher size wherever pipes crossing a fire rated wall / floor slab and sealing of space around pipe and pipe sleeve with glass wool in between and fire proof sealent at either end to the satisfaction of the Project Manager / Consultants and making good the same after pipes have been duly laid and testing complete.
| 110 mm dia | RM | 175 | 319.75
| 75 mm dia | RM | 70.15 | 213
| 50 mm dia | RM | 5 | 186.0467
| 40 mm dia | RM | 110 | 275.7267
34 | Providing, fixing, jointing, testing and commissioning UPVC (Class III) Rain water downtake pipe conforming to IS:4985 cut to required lengths including all necessary fittings and specials.UPVC fittings (moulded as well as fabricated) like bends, tees, Y-tees, crosses, boss connections, access pieces, saddle pieces, cleanouts, adaptors for connections to other materials, plugs, reducers, cowls, offsets and other specials. Fixing at wall/ceiling level supported by galvanized steel clamps & hangers etc. Making proper connection with cement solvent joint as per BIS / manufacturer. Cutting, chases / holes in floors / walls / slab and making good wherever required. (All major MS structure to hold the stack with fixing including anchor fasteners,sand,cement etc is included in this item).
| 110 mm dia. | RM | 75 | 119.95
35 | Providing and fixing of UPVC Floor Traps formed out of bore 'P' trap with 50 mm water seal, setting in 1:2:4 mix cement concrete block or clamping to the wall or suspending with the ceiling including cutting and making good the walls and floors wherever required, With Heavy class SS grating with Cockroach proof SS strainer of approved design including setting in floor with cement motor to match with floor finish as per architect requirement suitable for waster F.D. & F.T.
| 110 mm inlet and 75 mm outlet. | Nos. | 25 | 750.716
36 | Providing and fixing of UPVC Urinal Traps formed out of bore 'P' trap with 50 mm water seal, setting in 1:2:4 mix cement concrete block or clamping to the wall or suspending with the ceiling including cutting and making good the walls and floors wherever required, With SS grating with Cockroach proof SS strainer of approved design including setting in floor with cement motor to match with floor finish as per architect requirement suitable for waster U.T.
| 110 mm inlet and 110 mm outlet. | Nos. | 3 | 750.716
37 | Providing and fixing clean out/floor clean out plug consist of CI bend & GI socket heavy class with cap & key for opening male threaded cap etc. including lead caulked to CI pipes complete in all respects as per drawing/ sample approved by Engineer -in -Charge FCO (floor clean out plug shall be flushed with floor finish).: 100 mm dia. and Matching with Item no.31 or as per Architure approvals. | Nos. | 12 | 344.56
38 | Providing and fixing floor drain made out of 110x75 mm OD uPVC. elbow connected to uPVC pipe complete as per direction of Project Manager. | Nos. | 3 | 251.104
39 | Making khurras 45x45 cm with average minimum thickness of 5 cm cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate of 20 mm nominal size) over P.V.C. sheet 1 m x1 m x 400 micron, finished with 12 mm cement plaster 1:3 (1 cement : 3 coarse sand) and a coat of neat cement, rounding the edges and making and finishing the outlet complete. | Nos. | 4 | 266.6
Total
D | FIRE FIGHTING
40 | Supply, installation, testing and commissioning of following sizes of pipes conforming to IS-1239 with all accessories like all fittings ( all pipes & fittings upto 50mm dia threaded shall be the threaded Ductile Iron (ASTM A536) or Cast Iron (ASTM A126) or Forged Steel fittings and for pipes above 50 mm dia MS fitting with welded joint shall be used) including tees, elbows, reducers, union, flanges, rubber gaskets, GI nuts bolts, washer including supporting/fixing the pipe on wall /ceiling with clamps, hangers (using anchor fastners) as per specification, Including synthetic enamel paint of approved shade over a coat of primer. Prior to application of primer the surface should be cleaned for any dirt, rusts, rough substance etc. Including painting of legends both direction arrow as per the approval of the Project Manager
MS pipe sleeve of suitable higher size shall be provided wherever the pipes are crossing the walls/floors and sealing the sleeves with glass wool in between & fire sealent compound at either end all as per Project Manager’s requirements including cutting holes and chases in brick, R.C.C work and making good the same to original conditions complete in all respects. All hangers, clamps, brackets etc. shall be of galvanized iron unless specified otherwise and the supply of the same shall also be included in rates under this head. Welding of any kind on the galvanized support / hanger shall not be permitted.
For Sprinkler system - MS `C' Heavy class pipe
Ground Floor
| 25 mm dia | RM | 217 | 565.2
| 32 mm dia | RM | R/o | 632.4
| 40 mm dia | RM | 75 | 781.2
| 50 mm dia | RM | 65.0325 | 944.4
| 65 mm dia | RM | 30 | 1204.8
| 80 mm dia | RM | 35.305 | 1346.4
| 100 mm dia | RM | 20 | 1798.8
| 150 mm dia | RM | 93 | 2476.8
41 | Supply, installation, testing and commissioning of brass quartzoid sprinklers (UL approved) of 15 mm dia size, suitable for sustaining the pressure on the seat & water hammer effect. The type & temperature rating shall be as follows :
Note : i)All sprinkler shall be chrome finish / powder coated. ii) Contractor shall ensure provision of sprinkler guard at no additional cost, as required by the Client.
| Spray recessed (adjustable) rossette (68°C) sprinkler quick response upright type | Nos. | 150 | 580.8
| Spray recessed (adjustable) rossette (68°C) sprinkler quick response pendent type | Nos. | 150 | 580.8
| Horizontal side wall sprinkler - (68°C) sprinkler quick response | Nos. | 4 | 752.7
42 | Supplying, installation, testing & commissioning of sprinkler flexible pipe (UL Listed) of stainless steel complete with 15 NPT on reducer thread with maximum working pressure of 175 PSI test pressure of 875 PSI (Burst) with branch line (Inlet) 25mm NPT male thread to sprinkler head (Outlet) 15mm NPT female thread with reducer, nipple, 2 side brackets, center bracket, stockbar of following sizes complete as required.
| 1000mm | Nos. | 150 | 2002
43 | Providing and fixing fully charged ABC powder type (Mono-Ammonium Phosphate - MAP 90) portable fire extinguishers conforming to IS:15683, fixed to wall with brackets complete with initial charge. (Note: The cost for stand of fire extinguisher shall be included in this rate)
| Capacity 6 Kg. | Nos. | 16 | 4354
44 | Providing and fixing CO2 type cylindrical shape fire extinguisher with fixing hangers, hose, brackets, screws to required size etc.complete as per IS:15683:2006 - wall mounted type.
| Capacity 4.5 Kg. | Nos. | 16 | 11545
45 | Supply, installation, testing and commissioning of forged brass ball valve with forged brass ball (suitable for test pressure of not less than 15 Kg /sq.cm of the following size including providing necessary union / flange.
| 25 mm dia | No. | 1 | 967
| 32 mm dia | No. | 1 | 1482.08
| 40 mm dia | No. | 1 | 2157.984
46 | Providing & fixing of butterfly valve (PN 16) with flanges, nut bolts, gaskets and necessary pad locking arrangement complete required.
| 150 mm dia | No. | 1 | 10438.8
47 | Providing & fixing flow switch in following sizes M.S. pipe including connection etc as required.
| 150 mm dia | No. | 1 | 10642.8
48 | Supplying,fixing and commissioning of single headed internal hydrant valve with instantaneous Gunmetal/Stainless Steel coupling of 63 mm dia with cast iron wheel ISI marked conforming to IS 5290 (Type -A) with blank Gunmetal/Stainless Steel cap and chain as required : Single headed Gunmetal :- | No. | 1 | 7646
49 | Supplying,fixing and commissioning of 63 mm dia, 30 m long RRL hose pipe with 63 mm dia male and female couplings duly bound with GI wire, rivets etc. conforming to IS 636 (type-A) as required : Gun Metal :- | Nos. | 2 | 9202
50 | Supplying and fixing first-aid Hose Reel with MS construction spray painted in post office red, conforming to IS 884 complete with the following as required. 20 mm nominal internal dia water hose thermoplastic (Textile reinforced) type -2 as per IS: 12585 20 mm nominal internal dia gun metal globe valve & nozzle. Drum and brackets for fixing the equipmets on wall. Connections from riser with 25 mm dia stop gun metal valve & M.S. Pipe and socket. 40 m :- | No. | 1 | 12073
51 | Supplying & fixing 63 mm dia gun metal short branch pipe with 20 mm nominal internal diameter size nozzle conforming to IS 903 suitable for instantaneous connection to interconnect hose pipe coupling as required : Gun metal :- | No. | 1 | 2416
| Total |  |  |  | 167589.8 |  | 127253 |  | 86436 |  | 86436
| TOTAL "SECTION-B" |  |  | Rs. | 806255.8 |  | 767727.4332 |  | 465794 |  | 86436
Note on I191: ADMIN: CHECKED QTY 2 , TENDER 1 BALANCE IN RAB 3
Note on I194: ADMIN: ACTUAL QTY 2 , CHEKCED 2 , IN TENDER 1

## MB HVAC
JAIPUR AIRPORT LOUNGE HVAC M.B
S.NO | L-1 | W-1 | L-2 | W-2 | PARAMETER | H-1 | H-2 | AVERAGE | PIECES | 24 G | 22 G | 20 G | 18 G
SUPPLY AIR DUCT
1 | 450 | 300 | 450 | 300 | 1500 | 2700 |  | 2700 | 3 | 12.15 | X | X | X
2 | 450 | 200 | 450 | 200 | 1300 | 2600 |  | 2600 | 3 | 10.14 | X | X | X
3 | 750 | 250 | 750 | 250 | 2000 | 1400 |  | 1400 | 8 | 22.4 | X | X | X
4 | 300 | 250 | 300 | 250 | 1100 | 1350 |  | 1350 | 1 | 1.485 | X | X | X
5 | 300 | 250 | 300 | 250 | 1100 | 2700 |  | 2700 | 1 | 2.97 | X | X | X
6 | 750 | 250 | 750 | 250 | 2000 | 1400 |  | 1400 | 8 |  | X | X | X
7 | 600 | 400 | 600 | 400 | 2000 | 750 |  |  | 1 |  | X | X | X | hold
8 | 600 | 400 | 600 | 400 | 2000 | 1100 |  |  | 1 |  | X | X | X
9 | 850 | 250 | 850 | 250 | 2200 | 1400 |  | 1400 | 2 | X | 6.16 | X | X
10 | 850 | 250 | 850 | 250 | 2200 | 600 |  | 600 | 1 | X | 1.32 | X | X
11 | 750 | 250 | 750 | 250 | 2000 | 1400 |  |  | 2 |  | X | X | X
12 | 750 | 250 | 750 | 250 | 2000 | 1650 |  |  | 1 |  | X | X | X
13 | 650 | 250 | 650 | 250 | 1800 | 2300 |  | 2300 | 2 | 8.28 | X | X | X
14 | 450 | 200 | 450 | 200 | 1300 | 2700 |  | 2700 | 2 | 7.02 | X | X | X
15 | 450 | 200 | 450 | 200 | 1300 | 1450 |  | 1450 | 1 | 1.885 | X | X | X
16 | 500 | 600 | 500 | 600 | 2200 | 1300 |  | 1300 | 1 | 2.86 | X | X | X
17 | 500 | 600 | 500 | 600 | 2200 | 1300 |  | 1300 | 1 | 2.86 | X | X | X
18 | 850 | 250 | 850 | 250 | 2200 | 1950 |  | 1950 | 1 | X | 4.29 | X | X
19 | 850 | 250 | 850 | 250 | 2200 | 1350 |  |  | 1 | X | 2.97 | X | X
20 | 850 | 250 | 850 | 250 | 2200 | 1600 |  | 1600 | 2 | X | 7.04 | X | X
21 | 850 | 250 | 850 | 250 | 2200 | 2600 |  | 2600 | 1 | X | 5.72 | X | X
22 | 650 | 250 | 650 | 250 | 1800 | 1600 |  | 1600 | 1 | 2.88 | X | X | X
23 | 650 | 250 | 650 | 250 | 1800 | 1600 |  |  | 2 |  | X | X | X
24 | 650 | 250 | 650 | 250 | 1800 | 2700 |  | 2700 | 1 | 4.86 | X | X | X
25 | 650 | 250 | 650 | 250 | 1800 | 850 |  | 850 | 1 | 1.53 | X | X | X
26 | 450 | 250 | 450 | 250 | 1400 | 2700 |  |  | 2 |  | X | X | X
27 | 800 | 250 | 800 | 250 | 2100 | 1300 |  | 1300 | 1 | 2.73 | X | X | X
28 | 700 | 250 | 700 | 250 | 1900 | 2700 |  | 2700 | 2 | 10.26 | X | X | X
29 | 700 | 250 | 700 | 250 | 1900 | 1350 |  | 1350 | 1 | 2.565 | X | X | X
30 | 400 | 250 | 400 | 250 | 1300 | 1250 |  | 1250 | 1 | 1.625 | X | X | X
31 | 300 | 250 | 300 | 250 | 1100 | 1100 |  | 1100 | 1 | 1.21 | X | X | X
32 | 400 | 250 | 400 | 250 | 1300 | 750 |  | 750 | 1 | 0.975 | X | X | X
FRESH AIR DUCT
1 | 450 | 300 | 450 | 300 | 1500 | 1950 |  | 1950 | 1 |  | X | X | X
2 | 450 | 300 | 450 | 300 | 1500 | 1300 |  | 1300 | 1 |  | X | X | X
3 | 450 | 300 | 450 | 300 | 1500 | 1900 |  | 1900 | 3 |  | X | X | X
4 | 450 | 300 | 450 | 300 | 1500 | 1500 |  | 1500 | 2 |  | X | X | X
5 | 450 | 300 | 450 | 300 | 1500 | 1600 |  | 1600 | 2 |  | X | X | X
6 | 450 | 300 | 450 | 300 | 1500 | 2800 |  | 2800 | 2 |  | X | X | X
7 | 450 | 300 | 450 | 300 | 1500 | 1300 |  | 1300 | 2 |  | X | X | X
8 | 450 | 200 | 450 | 200 | 1300 | 2800 |  | 2800 | 2 |  | X | X | X
9 | 450 | 200 | 450 | 200 | 1300 | 1300 |  | 1300 | 2 |  | X | X | X
EXHAUST AIR DUCT
1 | 450 | 300 | 450 | 300 | 1500 | 2800 |  | 2800 | 2 |  | X | X | X
2 | 450 | 450 | 450 | 450 | 1800 | 1300 |  | 1300 | 1 |  | X | X | X
3 | 450 | 300 | 450 | 300 | 1500 | 1500 |  | 1500 | 3 |  | X | X | X
4 | 450 | 300 | 450 | 300 | 1500 | 1750 |  | 1750 | 1 |  | X | X | X
5 | 450 | 300 | 450 | 300 | 1500 | 1250 |  | 1250 | 3 |  | X | X | X
6 | 450 | 300 | 450 | 300 | 1500 | 1400 |  | 1400 | 1 |  | X | X | X
7 | 450 | 300 | 450 | 300 | 1500 | 1800 |  | 1800 | 3 |  | X | X | X
8 | 450 | 200 | 450 | 200 | 1300 | 2800 |  | 2800 | 2 |  | X | X | X
9 | 450 | 200 | 450 | 200 | 1300 | 1400 |  | 1400 | 2 |  | X | X | X
10 | 600 | 600 | 600 | 600 | 2400 | 600 |  | 600 | 3 |  | X | X | X
[12 empty] | 0 | 0
EXHAUST LINE
1 | 600 | 500 | 350 | 350 | 1800 | 1200 |  | 1200 | 1 |  | X | X | X
2 | 600 | 500 | 450 | 450 | 2000 | 700 |  | 700 | 1 | 1.4 | X | X | X
3 | 450 | 450 | 450 | 450 | 1800 | 500 |  | 500 | 1 | 0.9 | X | X | X
4 | 450 | 450 | 450 | 450 | 1800 | 1000 |  | 1000 | 1 | 1.8 | X | X | X
FRESHAIR LINE
6 | 500 | 500 | 500 | 500 | 2000 | 500 |  | 500 | 1 |  | X | X | X
7 | 650 | 650 | 650 | 650 | 2600 |  |  |  | 1 |  | X | X | X
8 | 500 | 500 | 500 | 500 | 2000 | 1200 |  | 1200 | 1 |  | X | X | X
9 | 500 | 300 | 450 | 300 | 1550 | 1200 |  | 1200 | 1 |  | X | X | X
10 | 450 | 300 | 450 | 300 | 1500 | 2500 |  | 2500 | 1 |  | X | X | X
BRANCHES
12 | 500 | 150 | 500 | 150 | 1300 | 1500 |  | 1500 | 1 |  | X | X | X
13 | 550 | 550 | 550 | 550 | 2200 |  |  |  | 1 |  | X | X | X
14 | 200 | 200 | 200 | 200 | 800 | 800 | 1000 | 900 | 1 |  | X | X | X
15 | 200 | 200 | 200 | 200 | 800 | 1500 |  | 1500 | 3 |  | X | X | X
16 | 250 | 200 | 200 | 200 | 850 | 300 |  | 300 | 2 |  | X | X | X
17 | 200 | 200 | 200 | 200 | 800 | 1500 |  | 1500 | 1 |  | X | X | X
18 | 300 | 150 | 250 | 150 | 850 | 800 | 1000 | 900 | 2 |  | X | X | X
19 | 250 | 150 | 250 | 150 | 800 | 2600 |  | 2600 | 1 |  | X | X | X
20 | 750 | 150 | 700 | 150 | 1750 | 300 |  | 300 | 2 |  | X | X | X
21 | 700 | 150 | 700 | 150 | 1700 | 2600 |  | 2600 | 2 |  | X | X | X
22 | 300 | 150 | 300 | 150 | 900 | 700 |  | 700 | 1 |  | X | X | X
23 | 300 | 150 | 300 | 150 | 900 | 2700 |  | 2700 | 2 |  | X | X | X
24 | 500 | 150 | 500 | 150 | 1300 | 1200 |  | 1200 | 3 |  | X | X | X
25 | 200 | 200 | 250 | 200 | 850 | 200 |  | 200 | 1 |  | X | X | X
26 | 200 | 200 | 200 | 200 | 800 | 2500 |  | 2500 | 2 |  | X | X | X
27 | 200 | 200 | 200 | 200 | 800 | 400 | 600 | 500 | 2 |  | X | X | X
28 | 200 | 200 | 200 | 200 | 800 | 2500 |  | 2500 | 2 |  | X | X | X
SUPPLY AIR DUCTING
30 | 900 | 100 | 900 | 100 | 2000 | 1400 | 1200 | 1300 | 4 |  |  | X | X
31 | 700 | 100 | 700 | 100 | 1600 | 1200 | 1000 | 1100 | 2 |  | X | X | X
32 | 700 | 100 | 700 | 100 | 1600 | 2000 |  | 2000 | 1 |  | X | X | X
33 | 700 | 100 | 700 | 100 | 1600 | 1000 |  | 1000 | 1 |  | X | X | X
34 | 500 | 100 | 500 | 100 | 1200 | 1500 |  | 1500 | 2 |  | X | X | X
35 | 600 | 600 | 600 | 600 | 2400 |  |  |  | 1 |  | X | X | X
36 | 700 | 100 | 700 | 100 | 1600 | 800 | 600 | 700 | 1 |  | X | X | X
37 | 700 | 100 | 700 | 100 | 1600 | 650 | 800 | 725 | 1 |  | X | X | X
38 | 700 | 100 | 700 | 100 | 1600 | 1700 |  | 1700 | 2 |  | X | X | X
39 | 700 | 100 | 700 | 100 | 1600 | 1500 |  | 1500 | 2 |  | X | X | X
40 | 700 | 100 | 700 | 100 | 1600 | 1000 |  | 1000 | 2 |  | X | X | X
FRESH AIR DUCT
42 | 500 | 100 | 500 | 100 | 1200 | 600 |  | 600 | 1 |  | X | X | X
43 | 600 | 600 | 600 | 600 | 2400 |  |  |  | 1 |  | X | X | X
44 | 500 | 100 | 500 | 100 | 1200 | 600 | 400 | 500 | 1 |  | X | X | X
45 | 500 | 100 | 500 | 100 | 1200 | 2000 |  | 2000 | 1 |  | X | X | X
46 | 500 | 100 | 500 | 100 | 1200 | 800 |  | 800 | 1 |  | X | X | X
47 | 450 | 450 | 450 | 450 | 1800 | 1200 |  | 1200 | 8 |  | X | X | X
48 | 600 | 600 | 600 | 600 | 2400 | 600 |  | 600 | 3 |  | X | X | X
| TOTAL | [8 empty] | 104.785 | 27.5
Uninstallation
1 | 1300 | 700 | 1300 | 700 | 4000 | 1500 |  | 1500 | 14 |  |  | X | X
2 | 600 | 600 | 600 | 600 | 2400 | 1300 |  | 1300 | 4 |  |  | X | X
3 | 550 | 550 | 550 | 550 | 2200 | 1300 |  | 1300 | 2 |  |  | X | X
4 | 500 | 500 | 500 | 500 | 2000 | 2500 |  | 2500 | 4 |  |  | X | X
5 | 450 | 450 | 450 | 450 | 1800 | 2600 |  | 2600 | 2 |  |  | X | X
6 | 1200 | 550 | 1200 | 550 | 3500 | 1600 |  | 1600 | 3 |  |  | X | X
7 | 1100 | 500 | 1100 | 500 | 3200 | 1400 |  | 1400 | 5 |  |  | X | X
8 | 1300 | 700 | 1300 | 700 | 4000 | 1500 |  | 1500 | 10 |  |  | X | X
[10 empty] | 0 | 0
SECTION-"A" AIR-CONDITIONING SYSTEM |  |  |  | 24 G
2 | AIR DISTRIBUTION |  |  | IN TENDER | CHEKCED BALANCE | TOTAL
2.1.1 | 24 gauge galvanised sheet steel (0.63 mm) |  | 104.785 | 104.785 | 0 | 104.785
2.1.2 | 22 gauge galvanised sheet steel (0.8 mm) |  | 27.5 | 5 | 22.5 | 27.5
THERMAL INSULATION
2.9.1 | THERMAL INSULATION FOR DUCTWORK
d. | 13 mm thick |  | 258.5
SECTION-B: KITCHEN VENTILATION SYSTEM (COOKING KITCHEN)
2 | AIR DISTRIBUTION
2.1.1 | 24 gauge galvanised sheet steel (0.63 mm) |  | 82.89
2.1.2 | 22 gauge galvanised sheet steel (0.8 mm) |  | 79.44
162.33
3.1.2 | STARTER DOL PANEL 1.5 HP |  |  | 1 | 1 | 2
| MCP FOR STARTER PANEL |  |  | 1 | 1 | 2

## PHE &FF
INTERNATIONAL CIP LOUNGE_JAI T1-PHE &FF
Sl No. | Description | Unit | BOQ Qty. | BOQ Rate | BOQ Amount |  |  | CHECKED RA-1 TENDEREDQTY | CHECKED RA-1 AMOUNT | CHECKED RA-2 AMD QTY | CHECKED RA-2 AMD AMOUNT
[6 empty] | RAB02 submitted qty | RAB -02 submitted amount
Part II | PHE & FF
B | WATER SUPPLY
1 | Providing and fixing CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure - 7 Bar @ 82 Deg C and 28 Bar @ 23 Deg C)for pipes from 1/2 Inch to 2 Inch. Schedule 40 Pipe to be used from 2-1/2 Inch to 6 Inch. Pipes shall be joined using solvent welded CPVC fittings i.e. Tees, Elbows, Couplers, Unions, Reducers, brushings etc. including transition fittings (connection between CPVC & metal pipe/GI) i.e. Brass Adaptors (both Male & Female threaded) conforming to ASTM D-2846. ASTM F441 with only CPVC solvent cement conforming to ASTM F-493.
Cost shall be inclusive of (a)Making maximum of 7.5 x 7.5 cm chasing in wall and floors for the pipe, making good the same by using 1:1 cement mortar over the wire mesh and providing protection to embedded pipes and fittings (in wall chase) by wrapping two layers of 400 micron polythene sheet including proper overlaps on joints complete as required or (b) Fixing/supporting the pipes (& fittings) at wall/ceiling level supported by galvanized clamps, hangers etc, as per specification. Exposed pipes to be painted of legends with direction arrow. GI pipe sleeves suitable higher size shall be provided wherever the pipes are crossing the fire rated walls / floors slab and sealing the sleeves with glass wool in between and fire sealant compound at either end all as per Project Manager's / Consultant requirement. All termination points for installation of faucets shall have brass termination fittings. Installation shall be to as per Technical Manual of manufacturer of pipes & fittings.
a) | 15 mm dia | RM | 30 | 384.16 | 11524.8
b) | 20 mm dia | RM | 20 | 432.18 | 8643.6 | 14 | 6050.52 | 0 | 0
c) | 25 mm dia | RM | 10 | 504.21 | 5042.1 | 3 | 1512.63 | 0 | 0
d) | 32 mm dia | RM | R/o | 550 |  | 21 | 11550 | 0 | 0
2 | Providing & fixing full way lever operated forged brass ball valve of brass body with forged brass hard chromeplated steel ball tested to a pressure not less than 15 Kg / sqcm with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc.
a) | 15 mm dia | Nos. | 1 | 1440.6 | 1440.6
b) | 20 mm dia | Nos. | 5 | 1920.8 | 9604
c) | 25 mm dia | Nos. | 1 | 2401 | 2401 | 1 | 2401 |  | 0
d) | 32 mm dia | Nos. | 1 | 2881.2 | 2881.2 | 1 | 2881.2 |  | 0
3 | Supplying, laying/ fixing, testing and commissioning of following thickness resin bonded fiber glass pipe section insulation having density 80 kg/cum or mineral wool (non combustible) having density of 144 Kg/ cu m duly covered with a layer of 120 gm/sqm polythene sheet (vapour barrier) on existing pipe and finally applying 0.63mm aluminium sheet cladding complete with type3 , grade 1 roofing feltstrip(as per IS:1322 as amended up to date ) at joints etc. as per specifications and as required.
a) | 25 mm thick mineral wool insulation (20 mm dia) | RM | 25 | 192.08 | 4802
4 | Supply Installation Testing and Commissioning of Horizontal Wall mounted storage type 25 litres Electric water Heater ( Geyser) as per specifications Inclduing supply and fixing of Anchor fastners, nut bolts, supply of accessories ,modification/rectification of civil works such as plumbing ,wiring etc.if any required to install the Geyser at desired location. | No. | 1 | 14406 | 14406 | 1 | 14406 |  | 0
| Total |  |  |  | 60745.3 |  | 38801.35 |  | 0 |  | 0
C | DRAINAGE
1 | Providing, Supply, installation,testing and commissioning of UPVC Soil, Waste & Vent system conforming to IS : 13592 - Type B and UPVC fittings (moulded as well as fabricated) like bends, tees, Y-tees, crosses, boss connections, access pieces, saddle pieces, cleanouts, adaptors for connections to other materials, plugs, reducers, cowls, offSet and other specials. Jointing shall be done with pushfit EPDM ring jointing technique in general. Solvent cement joints may be provided for fittings and specials which are not manufactured with pushfit rubber joints. Pipes may be laid / fixed in sunken floors, under slung from ceiling. The pipes laid in sunken floor shall be encased with 75 mm thick cement concrete (1:2:4) all around. The installation shall be complete in all respects including cutting chases / holes in walls, slabs and making good the same as per specifications.
Providing GI pipe sleeves of suitable higher size wherever pipes crossing a fire rated wall / floor slab and sealing of space around pipe and pipe sleeve with glass wool in between and fire proof sealent at either end to the satisfaction of the Project Manager / Consultants and making good the same after pipes have been duly laid and testing complete.
a) | 110 mm dia | RM | 20 | 960.4 | 19208 | 30 | 28812 | 20 | 19208 | 10 | 9604
b) | 75 mm dia | RM | 20 | 768.32 | 15366.4 | 6 | 4609.92 | 6 | 4609.92
c) | 50 mm dia | RM | 32 | 624.26 | 19976.32
2 | Providing and fixing of UPVC Floor Traps formed out of bore 'P' trap with 50 mm water seal, setting in 1:2:4 mix cement concrete block or clamping to the wall or suspending with the ceiling including cutting and making good the walls and floors wherever required, With Heavy class SS grating with Cockroach proof SS strainer of approved design including setting in floor with cement motor to match with floor finish as per architect requirement suitable for waster F.D. & F.T.
a) | 110 mm inlet and 110 mm outlet. | Nos. | 4 | 1440.6 | 5762.4 | 4 | 5762.4 | 4 | 5762.4
3 | Providing and fixing clean out/floor clean out plug consist of CI bend & GI socket heavy class with cap & key for opening male threaded cap etc. including lead caulked to CI pipes complete in all respects as per drawing/ sample approved by Engineer -in -Charge FCO (floor clean out plug shall be flushed with floor finish).: 100 mm dia. and Matching with Item no.31 or as per Architure approvals. | Nos. | 2 | 3841.6 | 7683.2 | 2 | 7683.2 | 1 | 3841.6
| Total |  |  |  | 67996.32 |  | 46867.52 |  | 33421.92 |  | 9604
D | FIRE FIGHTING
1 | Supply, installation, testing and commissioning of following sizes of pipes conforming to IS-1239 with all accessories like all fittings ( all pipes & fittings upto 50mm dia threaded shall be the threaded Ductile Iron (ASTM A536) or Cast Iron (ASTM A126) or Forged Steel fittings and for pipes above 50 mm dia MS fitting with welded joint shall be used) including tees, elbows, reducers, union, flanges, rubber gaskets, GI nuts bolts, washer including supporting/fixing the pipe on wall /ceiling with clamps, hangers (using anchor fastners) as per specification, Including synthetic enamel paint of approved shade over a coat of primer. Prior to application of primer the surface should be cleaned for any dirt, rusts, rough substance etc. Including painting of legends both direction arrow as per the approval of the Project Manager
MS pipe sleeve of suitable higher size shall be provided wherever the pipes are crossing the walls/floors and sealing the sleeves with glass wool in between & fire sealent compound at either end all as per Project Manager’s requirements including cutting holes and chases in brick, R.C.C work and making good the same to original conditions complete in all respects. All hangers, clamps, brackets etc. shall be of galvanized iron unless specified otherwise and the supply of the same shall also be included in rates under this head. Welding of any kind on the galvanized support / hanger shall not be permitted.
For Sprinkler system - MS `C' Heavy class pipe
a) | 25 mm dia | RM | 75 | 1104.46 | 82834.5 | 67 | 73998.82 |  | 0
b) | 32 mm dia | RM | 15 | 1344.56 | 20168.4 | 11 | 14790.16 |  | 0
c) | 40 mm dia | RM | 10 | 1776.74 | 17767.4
d) | 50 mm dia | RM | 10 | 2160.9 | 21609 | 36 | 77792.4 |  | 0
e) | 65 mm dia | RM | 10 | 2737.14 | 27371.4
f) | 80 mm dia | RM | 10 | 3121.3 | 31213
g) | 100 mm dia | RM | 10 | 3601.5 | 36015
2 | Supply, installation, testing and commissioning of brass quartzoid sprinklers (UL approved) of 15 mm dia size, suitable for sustaining the pressure on the seat & water hammer effect. The type & temperature rating shall be as follows :
Note : i)All sprinkler shall be chrome finish / powder coated. ii) Contractor shall ensure provision of sprinkler guard at no additional cost, as required by the Client.
| Spray recessed (adjustable) rossette (68°C) sprinkler quick response upright type | Nos. | 28 | 960.4 | 26891.2 | 28 | 26891.2 | 27 | 25930.8
0
| Spray recessed (adjustable) rossette (68°C) sprinkler quick response pendent type | Nos. | 28 | 960.4 | 26891.2 | 28 | 26891.2 | 27 | 25930.8
3 | Providing and fixing fully charged ABC powder type (Mono-Ammonium Phosphate - MAP 90) portable fire extinguishers conforming to IS:15683, fixed to wall with brackets complete with initial charge. (Note: The cost for stand of fire extinguisher shall be included in this rate)
| Capacity 6 Kg. | No. | 2 | 7683.2 | 15366.4 | 2 | 15366.4 | 0 | 0
4 | Providing and fixing CO2 type cylindrical shape fire extinguisher with fixing hangers, hose, brackets, screws to required size etc.complete as per IS:15683:2006 - wall mounted type.
| Capacity 4.5 Kg. | No. | 2 | 9604 | 19208 | 2 | 19208 | 0 | 0
5 | Providing & fixing of butterfly valve (PN 16) with flanges, nut bolts, gaskets and necessary pad locking arrangement complete required.
| 80 mm dia | Nos. | 1 | 12005 | 12005 | 1 | 12005 | 1 | 12005 | 1 | 12005
| Total |  |  |  | 337340.5 |  | 266943.18 |  | 63866.6 |  | 12005
NON TENDERED ITEMS
DRAINAGE
1 | Providing and fixing of clean out chambers with 50 mm water seal, setting in 1:2:4 mix cement concrete block or clamping to the wall or suspending with the ceiling including cutting and making good the walls and floors wherever required, With Heavy class SS grating with Cockroach proof SS strainer of approved design including setting in floor with cement motor to match with floor finish as per architect requirement suitable for waster F.D. & F.T.
A | 1'x1' SIZE | Nos. | 0 | 7000 |  | 2 | 14000 | 0 | 0
2 | Providing & fixing of PRESSURE GUAGE in FF line as required by EIC | Nos. | 0 | 6500 |  | 2 | 13000 | 0 | 0
| Total | [5 empty] | 27000 |  | 0 |  | 0

## MB PHE
JAIPUR AIRPORT (PHE & FF M.B SHEET)
Part II | PHE & FF | `
B | WATER SUPPLY | NOS | L | B | H | Total
1 | Providing and fixing CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure - 7 Bar @ 82 Deg C and 28 Bar @ 23 Deg C)for pipes from 1/2 Inch to 2 Inch. Schedule 40 Pipe to be used from 2-1/2 Inch to 6 Inch. Pipes shall be joined using solvent welded CPVC fittings i.e. Tees, Elbows, Couplers, Unions, Reducers, brushings etc. including transition fittings (connection between CPVC & metal pipe/GI) i.e. Brass Adaptors (both Male & Female threaded) conforming to ASTM D-2846. ASTM F441 with only CPVC solvent cement conforming to ASTM F-493.
Cost shall be inclusive of (a)Making maximum of 7.5 x 7.5 cm chasing in wall and floors for the pipe, making good the same by using 1:1 cement mortar over the wire mesh and providing protection to embedded pipes and fittings (in wall chase) by wrapping two layers of 400 micron polythene sheet including proper overlaps on joints complete as required or (b) Fixing/supporting the pipes (& fittings) at wall/ceiling level supported by galvanized clamps, hangers etc, as per specification. Exposed pipes to be painted of legends with direction arrow. GI pipe sleeves suitable higher size shall be provided wherever the pipes are crossing the fire rated walls / floors slab and sealing the sleeves with glass wool in between and fire sealant compound at either end all as per Project Manager's / Consultant requirement. All termination points for installation of faucets shall have brass termination fittings. Installation shall be to as per Technical Manual of manufacturer of pipes & fittings.
b) | 20 mm dia
| Oven wall hot and cold pipe | 1 | 6 |  |  | 6
| Oven wall for equipment pipe connection | 1 | 2 |  |  | 2
| Basin wall hot and cold pipe | 1 | 6 |  |  | 6
Sub Total
c) | 25 mm dia
| Oven, Basin and eqiupment connection | 1 | 3 |  |  | 3
Sub Total
d) | 32 mm dia
| Main pipe line connection | 7 | 3 |  |  | 21
Sub Total
C | DRAINAGE
1 | Providing, Supply, installation,testing and commissioning of UPVC Soil, Waste & Vent system conforming to IS : 13592 - Type B and UPVC fittings (moulded as well as fabricated) like bends, tees, Y-tees, crosses, boss connections, access pieces, saddle pieces, cleanouts, adaptors for connections to other materials, plugs, reducers, cowls, offSet and other specials. Jointing shall be done with pushfit EPDM ring jointing technique in general. Solvent cement joints may be provided for fittings and specials which are not manufactured with pushfit rubber joints. Pipes may be laid / fixed in sunken floors, under slung from ceiling. The pipes laid in sunken floor shall be encased with 75 mm thick cement concrete (1:2:4) all around. The installation shall be complete in all respects including cutting chases / holes in walls, slabs and making good the same as per specifications.
Providing GI pipe sleeves of suitable higher size wherever pipes crossing a fire rated wall / floor slab and sealing of space around pipe and pipe sleeve with glass wool in between and fire proof sealent at either end to the satisfaction of the Project Manager / Consultants and making good the same after pipes have been duly laid and testing complete.
a) | 110 mm dia
| Kitchen to basement connection from runway(Airbay side) | 5 | 6 |  |  | 30
| Sub Total |  |  |  |  | 30
| Total tender qty |  |  |  |  | 20
| balance TBE in RAB |  |  |  |  | 10
a) | Total |  |  |  |  | 30
b) | 75 mm dia
| kitchen area | 1 | 6 |  |  | 6
| Sub Total |  |  |  |  | 6
2 | Providing and fixing of UPVC Floor Traps formed out of bore 'P' trap with 50 mm water seal, setting in 1:2:4 mix cement concrete block or clamping to the wall or suspending with the ceiling including cutting and making good the walls and floors wherever required, With Heavy class SS grating with Cockroach proof SS strainer of approved design including setting in floor with cement motor to match with floor finish as per architect requirement suitable for waster F.D. & F.T.
a) | 110 mm inlet and 110 mm outlet. | 4 |  |  |  | 4
| Sub Total |  |  |  |  | 4
3 | Providing and fixing clean out/floor clean out plug consist of CI bend & GI socket heavy class with cap & key for opening male threaded cap etc. including lead caulked to CI pipes complete in all respects as per drawing/ sample approved by Engineer -in -Charge FCO (floor clean out plug shall be flushed with floor finish).: 100 mm dia. and Matching with Item no.31 or as per Architure approvals. | 2 |  |  |  | 1
| Sub Total |  |  |  |  | 1
D | FIRE FIGHTING
1 | PIPING
25 MM DIA
32 MM DIA
50 MM DIA
2 | SPRINKLER
| UPRIGHT |  |  |  |  | 27
| PENDANT |  |  |  |  | 27
3 | ABC CYLINDER
6KG
4 | CO2 CYLINDER
4.5 KG
5 | BUTTER FLY VALVE 80 MM checked |  |  |  |  | 2
| tender qry |  |  |  |  | 1
| balance |  |  |  |  | 1
| Sub Total |  |  |  |  | 2

## LIGHT FITTING
PROJECT : JAIPUR T2 CIP LOUNGE
DATE: 08.12.2023
LIGHTING FIXTURES - ELCTRICAL RAB -01
S.NO | ITEM DESCRIPTION | UNIT | BOQ QTY. | BOQ RATE | BOQ AMT | RAB -01 CHECKED QTY | RA-1 CHECKED AMT
A. | LIGHT FITTING
1 | Supply, assembling, erection, connecting, testing and commissioning of the following LED light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required
a) | LINOS LED COB DL320905 3W 3K 15D WHT+SLV (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | nos | 3 | 1152.48 | 3457.44 | 3 | 3457.44
b) | ORRIN DL75231106 7.5W 4K R 45D WH (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | nos | 38 | 1440.6 | 54742.8 | 38 | 54742.8
c) | EAGLE LED COB DL DL15312116 15W 4K+ IVEX RING T-HB46366W RR WHT DR (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | nos | 1 | 3361.4 | 3361.4 | 1 | 3361.4
d) | ASTER PRO LED PNL BP361625D 2X2 36W 65K (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | nos | 5 | 2401 | 12005 | 5 | 12005
e) | TROMPE SP12149 WATT - 12 x 1.5W= 18W LED (P2 Feature Pendant) Approved Makes-TISVA, TROMPE (USHA) | nos | 1 | 7203 | 7203 | 1 | 7203
| 1.5W each LED lamp wattage G4 lamp holder ( Total Wattage- 1.5* 12= 18W) |  | 12 | 3361.4 | 40336.8 | 12 | 40336.8
f) | CALLIGO CG11001 WATT - 11 x 2W LED Approved Makes-TISVA, CALLIGO (USHA) | nos | 8 | 14406 | 115248 | 8 | 115248
| 2 W each LED lamp wattage G9 lamp holder ( Total Wattage- 2* 11= 22W) |  | 88 | 4321.8 | 380318.4 | 88 | 380318.4
g) | LED STRIP LIGHT LS20WD0505D LUME LED SP 05W 4000K (5 Meter roll) + LUME LED Driver A23A24VP1 72W 24V ND P20 (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | Feet | 275 | 144.06 | 39616.5 |  | 0
| TOTAL |  |  |  | 656289.34 |  | 616672.84
C.1 | EXTRA NEW ITEMS AS PER DRAWING CHANGE (NON TENDERED ITEM) |  |  | NT RATE
H) | TABLE LAMP COLOR : ROSEGOLD , HAIRLINE | Nos | 0 | 8500
b) | ORRIN DL75231106 7.5W 4K R 45D WH (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | Nos |  | 1440.6 |  | 3 | 4321.8 | cheked in 41
| TOTAL AMOUNT | [5 empty] | 4321.8

## LIGHT MB
PROJECT : JAIPUR T2 CIP LOUNGE
DATE: 08.12.2023
LIGHTING FIXTURES - ELCTRICAL RAB -01
S.NO | ITEM DESCRIPTION | UNIT | BOQ QTY. | SUBMITTED QTY | CHECKED QTY | IMAGES
A. | LIGHT FITTING
1 | Supply, assembling, erection, connecting, testing and commissioning of the following LED light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required
a) | LINOS LED COB DL320905 3W 3K 15D WHT+SLV (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | nos | 3 | 3 | 3
b) | ORRIN DL75231106 7.5W 4K R 45D WH (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | nos | 38 | 38 | 38 | 41 LIGHTS EXECUTED AS PER DRAWING AND CHECKED
c) | EAGLE LED COB DL DL15312116 15W 4K+ IVEX RING T-HB46366W RR WHT DR (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | nos | 1 | 1 | 1
d) | ASTER PRO LED PNL BP361625D 2X2 36W 65K (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | nos | 5 | 5 | 5
e) | TROMPE SP12149 WATT - 12 x 1.5W= 18W LED (P2 Feature Pendant) Approved Makes-TISVA, TROMPE (USHA) | nos | 1 | 1 | 1
| 1.5W each LED lamp wattage G4 lamp holder ( Total Wattage- 1.5* 12= 18W) |  | 12 | 12 | 12
f) | CALLIGO CG11001 WATT - 11 x 2W LED Approved Makes-TISVA, CALLIGO (USHA) | nos | 8 | 8 | 8
| 2 W each LED lamp wattage G9 lamp holder ( Total Wattage- 2* 11= 22W) |  | 88 | 88 | 88
g) | LED STRIP LIGHT LS20WD0505D LUME LED SP 05W 4000K (5 Meter roll) + LUME LED Driver A23A24VP1 72W 24V ND P20 (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) | Feet | 275 | 275 | 0
TOTAL
C.1 | EXTRA NEW ITEMS AS PER DRAWING CHANGE (NON TENDERED ITEM)
H) | TABLE LAMP COLOR : ROSEGOLD , HAIRLINE | Nos | 0 | 22 | 0
B | ORRIN DL75231106 7.5W 4K R 45D WH (Approved Makes -TISVA(USHA)/ PHILIPS/ WIPRO/ HAVELLS) |  |  | 3 | 3 | CHECKED ABOVE IN 41
TOTAL AMOUNT

## FURNITURE BOQ
FURNITURE WORK RAB-02
S.NO. | DETAIL | CODE | UNIT | BOQ QTY. | BOQ RATE | BOQ AMOUNT | RAB -01 CHECKED QTY | RAB-01 AMOUNT | REMARKS
C | FURNITURE WORK
1 | Providing & supply SOFACHAIR as per approved sample ( W 535x D 540 x H 815mm ) ( EXECUTIVE LOUNGE) | F-01 | No | 21 | 18247.6 | 383199.6 | 14 | 255466.4 | CHECKED
[6 empty] | 0 |  | 0
2 | Providing & supply SOFACHAIR as per approved sample ( W 535x D 540 x H 815mm ) ( EXECUTIVE LOUNGE) | F-02 | No | 21 | 18247.6 | 383199.6 | 14 | 255466.4 | CHECKED
[6 empty] | 0 |  | 0
3 | Providing & supply ARM Chair as per approved sample ( W 690 x D 640 x H 800mm ) ( PREMIUM LOUNGE) | F-03 | No | 24 | 36015 | 864360 | 37 | 1332555 | CHECKED
[6 empty] | 0 |  | 0
4 | Providing & supply ARMCHAIR + OTTOMAN as per approved sample ( W 640 x D 680 x H 980mm ) ( SPA & QUIET Zone Area ) | F-04 | No | 2 | 36015 | 72030 | 0 | 0
[6 empty] | 0 |  | 0
5 | Providing & supply chair as per approved sample (W 580 x D 630x H 960mm) ( Admin & Reception Area ) | F-05 | No | 5 | 19208 | 96040 | 3 | 57624
[6 empty] | 0 |  | 0
6 | Providing & supply Square Dining Table as per approved sample (W 600 x D 600 x H 750mm ) ( PREMIUM LOUNGE) | F-06 | No | 14 | 14406 | 201684 | 0 | 0
[6 empty] | 0 |  | 0
7 | Providing & supply Square Dining Table as per approved sample (W 600 x D 600 x H 750mm ) ( PREMIUM LOUNGE) | F-07 | No | 14 | 14406 | 201684 | 0 | 0
[6 empty] | 0 |  | 0
8 | Providing & Supplying AdminTable (2670x600mmxH 750mm) | F-09 | No | 1 | 21609 | 21609 | 1 | 21609 | checked
[6 empty] | 0 |  | 0
10 | Providing & Supply mobile pedistal ( 450mm W x 500mm D x 650mm H ) for Admin area finished in laminate | F-09 | No | 1 | 7203 | 7203 | 1 | 7203 | checked
0
[6 empty] | 0 |  | 0
11 | Providing Metal Screen as per design of approved sample with cluster of 4 no.s. panels having panel size(1325 x 38 x 2800mm ) of each. (PREMIUM LOUNGE) | F-10 | No | 4 | 216090 | 864360 | 4 | 864360 | checked
0
12 | Providing Metal Screen as per design of approved sample with cluster of 4 no.s. panels having panel size(2400 x 38 x 2800mm ) of each. (PREMIUM LOUNGE) | F-10.1 | No | 1 | 384160 | 384160 | 1 | 384160 | checked
0
| Total of Furniture Work |  |  |  |  | 3479529.2 |  | 3178443.8
KINDLY NOTE:
1 | All mentioned products to be delivered within 150 days after receipt of order confirmation with 50% advance payment. 25% of the balance payment must be cleared half way through the production time when strucutres are ready at the factory. Balance 25% (last instalment) to be paid 1 week prior the scheduled dispatch date.
2 | Cost of fabric upto Rs. 1000/- included in the BOQ. Any extra cost of fabric shall be borne by the client.
C.1 | EXTRA NEW ITEMS AS PER DRAWING CHANGE (NON TENDERED ITEM) |  |  |  | NT RATE
1 | Providing & supply Pedestal as per approved sample (W 300 x D 1200x H 500mm) | F-06 | No | 0 | 38000 |  | 9 | 342000
2 | Providing & supply Pedestal as per approved sample (W 300 x D 600x H 500mm) | F-06.01 | No | 0 | 28500 |  | 13 | 370500
3 | Providing & supply Square Dining Table as per approved sample (W 600 x D 600 x H 750mm ) ( PREMIUM LOUNGE) | F-07 | No | 0 | 24000 |  | 14 | 336000
| Total of Furniture Work | [6 empty] | 1048500

## FURNITURE MB
FURNITURE WORK RAB-02
S.NO. | DETAIL | CODE | UNIT | BOQ QTY. | SUBMITTED QTY | CHECKED QTY | REMARKS
C | FURNITURE WORK
1 | Providing & supply SOFACHAIR as per approved sample ( W 535x D 540 x H 815mm ) ( EXECUTIVE LOUNGE) | F-01 | No | 21 | 14 | 14 | CHECKED
2 | Providing & supply SOFACHAIR as per approved sample ( W 535x D 540 x H 815mm ) ( EXECUTIVE LOUNGE) | F-02 | No | 21 | 14 | 14 | CHECKED
3 | Providing & supply ARM Chair as per approved sample ( W 690 x D 640 x H 800mm ) ( PREMIUM LOUNGE) | F-03 | No | 24 | 37 | 37 | CHECKED
4 | Providing & supply ARMCHAIR + OTTOMAN as per approved sample ( W 640 x D 680 x H 980mm ) ( SPA & QUIET Zone Area ) | F-04 | No | 2 | 0 | 0
5 | Providing & supply chair as per approved sample (W 580 x D 630x H 960mm) ( Admin & Reception Area ) | F-05 | No | 5 | 3 | 3
6 | Providing & supply Square Dining Table as per approved sample (W 600 x D 600 x H 750mm ) ( PREMIUM LOUNGE) | F-06 | No | 14 | 0 | 0
7 | Providing & supply Square Dining Table as per approved sample (W 600 x D 600 x H 750mm ) ( PREMIUM LOUNGE) | F-07 | No | 14 | 0 | 0
8 | Providing & Supplying AdminTable (2670x600mmxH 750mm) | F-09 | No | 1 | 1 | 1 | CHECKED
10 | Providing & Supply mobile pedistal ( 450mm W x 500mm D x 650mm H ) for Admin area finished in laminate | F-09 | No | 1 | 1 | 1 | CHECKED
11 | Providing Metal Screen as per design of approved sample with cluster of 4 no.s. panels having panel size(1325 x 38 x 2800mm ) of each. (PREMIUM LOUNGE) | F-10 | No | 4 | 4 | 4 | CHECKED
12 | Providing Metal Screen as per design of approved sample with cluster of 4 no.s. panels having panel size(2400 x 38 x 2800mm ) of each. (PREMIUM LOUNGE) | F-10.1 | No | 1 | 1 | 1 | CHECKED
Total of Furniture Work
KINDLY NOTE:
1 | All mentioned products to be delivered within 150 days after receipt of order confirmation with 50% advance payment. 25% of the balance payment must be cleared half way through the production time when strucutres are ready at the factory. Balance 25% (last instalment) to be paid 1 week prior the scheduled dispatch date.
2 | Cost of fabric upto Rs. 1000/- included in the BOQ. Any extra cost of fabric shall be borne by the client.
C.1 | EXTRA NEW ITEMS AS PER DRAWING CHANGE (NON TENDERED ITEM)
1 | Providing & supply Pedestal as per approved sample (W 300 x D 1200x H 500mm) | F-06 | No | 0 | 9 | 9 | CHECKED
2 | Providing & supply Pedestal as per approved sample (W 300 x D 600x H 500mm) | F-06.01 | No | 0 | 13 | 13 | CHECKED
3 | Providing & supply Square Dining Table as per approved sample (W 600 x D 600 x H 750mm ) ( PREMIUM LOUNGE) | F-07 | No | 0 | 14 | 14 | CHECKED
Total of Furniture Work

## C&S Extra items
CIVIL & INTERIOR WORK BOQ FOR PROPOSED LOUNGE AT JAIPUR AIRPORT
S.NO | DESCRIPTION OF ITEMS | UNIT | QTY | RATE in INR | AMOUNT in INR | Remarks
I | DIAMANTLING WORK
2 | Dismantling of existing false ceiling work including frame electrical conduits, wiring, DBS, switches, switch boards, sockets , PA system , Speakers ( 10Speakes approx ) , Lights 2' x 4" , smoke detectorsand ceiling lightsand stacking the serviceable materials at a designated place at our site premises | Sqm | 180 | 400 | 72000 | It has been told by TFS and Adani Team to Remove the excess items from true ceiling so as to make the area workable , reference MOM Dated 09.09.23
7 | Dismantling of existing Fire fighting Line of 25 mm , 32mm , 40mm , 50 mm along with sprinklers and pendent , including labour cost for staking material at our site premises | Mtr | 50 | 325 | 16250 | It has been told by TFS and Adani Team to Remove the existing line which has been obstructing the routing of FF line as per new layout , reference MOM Dated 09.09.23
9 | Dismantling of existing Wall cladding of ACP and aluminum strips including framing and labour cost for staking material to designated place at our site premises (area it rack side wall , kitchen back wall , railing back side cover , ceiling over railing ) | Sqm | 100 | 300 | 30000 | It has been told by Adani design Team to Remove the existing ACP required so as to make the area workable , reference MOM Dated 09.09.23
10 | Dismantling of existing ceiling support , tie rods , MS ducting Supports , Gi channels , Squre lights Ms supports etc at our site premises | Job | 1 | 11000 | 11000 | It has been told by Adani design Team to Remove all excess item of true ceiling so as to make the area workable , reference MOM Dated 09.09.23, 14.09.23
11 | Removing teh existing carpet along with base materials if any any disposal of serviceable & un serviceable materials at the respective designated place for final disposal as per directions of Project In Charge complete. (total area 1700 sft) | Sqm | 180 | 150 | 27000 | Removed from exisitng floor to make area workable as per GFC
13 | Dismantling of toilet Duct (8'x 3.') out side premises of toilet gallery and shifting upwards to get the ceiling height near reception area including MS support dismantling and insulation as instructed by Mr Kalpant and EIC | Job | 1 | 27000 | 27000 | This duct is out side our premises ,toilet side and we have been told to work by Kalpant sir to remove the operational duct in single night and make the HVAC system of airport operational within 4 -5 hours on dated 08 OCT 2023
15 | Dismantling of existing stone flooring and disposal of Malwa at the designated place for final disposal as per directions of Project-in-Charge complete including cleaning teh RCC slab top with wire brushes after shifting of all teh materials as per above items. | LS | 1 | 11000 | 11000 | Removal of existing flooring at site to make the area workable at site as per GFC
16 | Dismantling of existing SS railing and removal of railing glass with all accessories complete in all respect and stacking of material at our site premises | Sqm | 15 | 1200 | 18000 | It has been told by TFS and Adani design Team to Remove railing and railing glass to make more space in the lounge , reference MOM Dated 09.09.23 , 14.09.23 , mail of 08th sep 2023 ( kallol sir )
17 | Idle Manpower due to design change and revision in drawings from the period of (1st September 2023 to 10th Oct 2023 ) as per submitted sheet | Wages | 169 | 1250 | 211250 | Taken wages of idle payment due to design change and revised GFC as intimated to all stakeholders over mail dated 09 OCT 2023
18 | Fixing and tieing of cable , wires m conduits , IT cable of IT Rack at 11 ft above ceiling height level of CISF IT rack as directed by EIC (M.S pipe support for wiring L-type frame at marchantise area) | Job | 1 | 8000 | 8000 | Bulk of IT rack ( belong to airport CISF and IT Team adani ) wires and conduit lying over IT Rack and obstructing the ceiling height which need to be dressed again so that we can achieve the ceiling height
18.01 | Lobour and trolley trip for Disposal of dismantled items , malba , ceiling fixture , ctrical conduits, wiring, DBS, switches, switch boards, sockets , PA system , Speakers ( 8 Speakes approx ) , Lights 2' x 4" ,SD , 8'x8' platform , railing , glass , ACP , existing MS structure , etc from our site premises to 800 mtr away designated store area outside airport | Trip | 25 | 3500 | 87500 | Labour and trolley for removal of dismantled items mentioned above and below considered in this item
18.02 | Front side premium longe LCD wall ceiling M.S framing removing and fixing as required. | Job | 1 | 10000 | 10000 | E&M REQUIRMENTS
18.03 | FIDS stand fixing for T.V unit | Nos | 4 | 2000 | 8000
18.04 | Trap door making and fixing runway side, admin room front side premium lounge and marchantise area | Nos | 4 | 4000 | 16000
19 | Outer site Premises Work for installing the scrubber and Fan from GF level to the 4th floor terrace level
19.1 | Providing and Fixing of aluminum Scaffolding with platform for area 2625 sft of size (15'x10'x 70') with support structure of 5'x5'x70' from GF bus gate to 4th floor terrace for exhaust Air and scrubber duct installation on rental basis . Cost including to make other necessary arrangements at bus gate GF to make it safe as per authorities safety norms | Days | 60 | 2250 | 135000 | It has been told by TFS and Adani Team to Remove the excess items from true ceiling so as to make the area workable , reference MOM Dated 09.09.23, 14.09.23,
19.2 | Dismantling of existing Wall cladding of ACP including framing from 2nd floor to 4th floor till terrace and labour cost for staking material to designated store 800 Mtr away outside premises | Sqm | 80 | 900 | 72000
19.3 | Removal and refixing of façade glass at GF level to make the route of Duct from our primes to 4th Floor terrace (size 9'x 4') total in NOS 4 Nos and place them at GF designated area defined by airport authorities | Job | 1 | 25000 | 25000
19.4 | Dismantling of Air-conditioning existing ducts as new layout out side our premises beyond façade glass to make the route for new duct and connect it from new duct, including labour cost for staking material to designated store 800 Mtr away outside premises | Job | 1 | 15000 | 15000
19.5 | providing and fixing MS stand for Scrabber & Exaust fan at terrace | Nos | 3 | 5000 | 15000 | Requirement given by Kallol Sir
19.6 | providing and fixing Outside premises grid false ceiling of lounge | Sqm | 27.78 | 2300 | 63894 | Requirment given by ashutosh Sir
20 | Plumbing Line outside premises
20.1 | Removal of necessary item Support structure , Other line if any , provision in Basement to connect it to basement drain manhole in shaft to make the route of drain line from GF to basement | Lot | 1 | 20000 | 20000 | Due to design change and site contraints , Adani MEP team told us make the new route throught shaft and take the drainage line to basment and connect it to nearby drain pot/Manhole
9 | Dismantling of existing Wall cladding of ACP and aluminum strips including framing and labour cost for staking material to designated place at our site premises | Sqm | 20 | 800 | 16000
21 | Providing & fixing 3mm thick xxx COLOUR ACP cladded on MS frame work supported with necessory section as per shown in drawings.Job including fabrication & erection. Rate inclusive of all necessory hardware and fixing with 3M tape and joint filling with silicon, completed as per the details are provided in drawings or as directed by Architect/Engineer. (Base rate of ACP Rs 400 per sft) Approved makes: Alucobond/Alumax/Aludecore . area to be covered | SQM | 80 | 7500 | 600000 | Due to design change and site contraints , ACP need to be removed and refix after all operations
| TOTAL |  |  |  |  | 1514894

## HVAC EXTRA ITEM
HVAC WORK FOR OF 2ND FLOOR AS PER DRAWING RECEIVED
2 | AIR DISTRIBUTION | UOM | QTY | RATE | AMOUNT | Remarks
2.1 | Supply, installation and testing of SITE Fabricated GI sheet metal ducts as per IS-655 Standard in accordance with the approved shop drawings as required by the specifications. Quoted price shall be inclusive of all necessary supports by MS structural steel if required, hangers, clamp supports from walls, floors and ceiling including cutting holes and chases in brick, R.C.C. work, making good the same to original condition complete in all respects with painting with one coat of primer and two coats of paint to supports of MS work. Quoted price shall be inclusive of scaffolding work as required. Note:All exposed surfaces & duct shall be painted in black mat finish by the HVAC contractor. |  |  |  |  | Requirment given by E&M , Kallol Sir and reference of MOM Dated 09.09.23, 14.09.23, and the sketch received from MEP team to execute the work
2.1.1 | 24 gauge galvanised sheet steel (0.63 mm) | Sqm. | 60 | 1441 | 86460
2.1.2 | 22 gauge galvanised sheet steel (0.8 mm) | Sqm. | 100 | 1729 | 172900
2.1.3 | 20 gauge galvanised sheet steel (1.0 mm) | Sqm. | 10 | 2113 | 21130
2.1.4 | 18 gauge galvanised sheet steel (1.25 mm) | Sqm. | R/o
2.9.1 | THERMAL INSULATION FOR DUCTWORK
Supply and Application of external thermal insulation of supply /return air ducting using closed cell elastomeric nitrile rubber insulation with class 'O' fire retardant properties as per the specifications and drawings. Quoted price shall be inclusive of adhesive, tapes as per specification. insulation shall be provided with aluminium foil, factory laminated.
Insulation thickness/application will be as per approved shop drawing notes.
d. | 13 mm thick | Sqm | 160 | 1201 | 192160
3 | JET NOZZLE
TheJet Nozzle shall be constructed of High Grade Aluminium Alloy, External ring with a curved profile and spherical inner nozzle using the mechanical principle of eye ball (ball and socket principle) engineered to swivel 360º. The Colour to be approved by Architect/ Client.
a) | 275mm Dia | Nos | 4 | 9000 | 36000
| TOTAL |  |  |  |  | 508650