## Healthy Eats
| Delhi T1 _ Healthy Eats | INDOOR AREA _2000x2575x2700H(mm)_BOQ |  | PO : TFSPL/PO/24-25/000526 |  |  |  | Final Bill
S.No | Head | Description | Make | UOM | QTY | Rate | Amount (INR) | QTY | Amount (INR)
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer and powder coated paint of approved shared at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. | Jindal/Tata | Kgs | 170 | 165 | 28050 | 170 | 28050
2 | Base & Flooring | Providing and fixing of 18 bison board over MS pipe 50mm SHS , C/C 600x600mm grid, | NCL | Sqm | 5.15 | 2000 | 10300 | 5.15 | 10300
3 | Rubber Mat | Rubber Mat Rubber Mat Rolls, Thickness: 5 Mm ₹ 45/ Square Feet Thickness: 3 mm |  | Sqm | 5.15 | 850 | 4377.5 | 4.8925 | 4158.625
4 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. | Century or equivalent | Sqm | 24.66 | 2800 | 69048 | 24.66 | 69048
5 | Paint | Apply of 2 coat white enamel emulsion paint on pillar & side partition left&right | Asian Berger, Indgo | Sqm | 2.28 | 650 | 1482 | 2.28 | 1482
6 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with laminate finish , hinges, SS knob, tower bolt etch. | Century, Merino, Ebco | No | 1 | 6500 | 6500 | 1 | 6500
7 | Kitchen Door With Vision Panel | Providing & Fixing of Kitchen door made of 32mm FR Ply with Flush door with both side laminate, with vision panel, 300x150mm, with hardware accessories & MS 50x50mm Frame work iwith paint finish | Century, Merino, Ebco, Jindal | No | 1 | 28000 | 28000 | 1 | 28000
8 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with Laminate finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | Century/Merino/ FGV | No. | 0 | 35000 | 0 |  | 0
9 | Side Storages | Providing and installation of make of 18mm & 12mm Fr Plywood with approved laminate finish with hinges soft closed shutter. | Century/Merino/ FGV | Nos. | 0 | 24000 | 0 |  | 0
10 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) | Havells, Syska or equivalent | No. | 2 | 2500 | 5000 | 2 | 5000
11 | Linear Profile Light T5 | Providing & fixing linear profile light consealed in Rafter | Custom Make | No. | 2 | 650 | 1300 | 2 | 1300
12 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, DB panel, MCB, ELCB, as per requirement or as approved electrical drawing | Polycab, Finolex, Roma, Crompton | No. | 1 | 25200 | 25200 | 1 | 25200
13 | Industrial Socket | Industrial Socket & Panel Box (32amp ) |  | No. | 2 | 3500 | 7000 | 2 | 7000
14 | DB Panel | Supply & Fixing of 12mm Way DB Panel wit 1 No. RCB & MCB 12 No's. | L&T | No | 0 | 15000 | 0 |  | 0
15 | Main Cable | Supply & Fixing of 4 core 10 Sqm Coppe Cable for main DB to Meter | Polycab, Finolex, Roma, Crompton | Mtr. | 0 | 850 | 0 |  | 0
16 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork | HP Latex, 3M , LG Vinyl or equivalent | Sqft. | 97.3066 | 150 | 14595.984 | 97.31 | 14596.5
17 | Healthy Eats | Front logo signaged fixed front façade , UV Printed 3mm raised acrylic . | A cast , NGX , Osram | No. | 0 | 12000 | 0 |  | 0
18 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. | A cast , NGX , Osram | No. | 0 | 4500 | 0 |  | 0
19 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 2 nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire | Hikvision | Set | 0 | 25000 | 0 |  | 0
20 | Installation | T-1 Delhi Airport |  | EA | 1 | 32000 | 32000 | 1 | 32000
21 | Transportation | T-1 Delhi Airport |  | EA | 1 | 12500 | 12500 | 1 | 12500
0
| TOTAL | [5 empty] | 245353.484 |  | 245135.125
Less 3.5% Discount | [8 empty] | -8579.7294
Gross total | [8 empty] | 236555.3956
IGST @ 18% | [8 empty] | 42579.9712
Grand total | [8 empty] | 279135.3668

## Healthy Eats MB
| Healthy Eats | INDOOR AREA _2000x2575x2700H(mm) | LOCATION | T-1 IGI DELHI | PO Qty | Measurement sheet
S.No | Head | Description | Make | Size |  | UOM | Length | Width | Height | Nos/Wt | Qty | Final to billing BOQ | Balance to be Bill
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer and powder coated paint of approved shared at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. | Jindal/Tata |  | 170 | Kgs |  |  |  |  | 170 | 170 | 0
|  | Back Structure - 40x40x1.5mm | [7 empty] | 35 |  |  | 0
|  | Bottom Structure -50x50x1.5mm | [7 empty] | 40 |  |  | 0
|  | Left Side-40x40x1.5 Full Height & Righ | [7 empty] | 40 |  |  | 0
|  | Front Side-40x40x1.5 | [7 empty] | 20 |  |  | 0
|  | Pillar (50x50x1.5) | [7 empty] | 20 |  |  | 0
|  | Roof Horizontal Pipe (50mmx50mmx1.5) | [7 empty] | 15 |  |  | 0
2 | Base & Flooring | Providing and fixing of 18mm FR Ply with 1.5mm thick aluminium checker sheet finish mounted over MS pipe 50mm SHS , C/C 600x600mm grid, | Century Ply, Tata/ Jindal |  | 5.15 | Sqm | 2 | 2.575 |  | 1 | 5.15 | 5.15 | 0
3 | Rubber Mat | Rubber Mat Rubber Mat Rolls, Thickness: 5 Mm ₹ 45/ Square Feet Thickness: 3 mm |  |  | 5.15 | Sqm | 1.9 | 2.575 |  | 1 | 4.8925 | 4.8925 | 0
4 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. | Century or equivalent |  | 24.66 | Sqm |  |  |  |  | 28.09 | 24.66 | 3.43
|  | Back Wall |  |  |  |  | 2 | 2.7 | 2 | 10.8 |  |  | 0
|  | Front |  |  |  |  | 2 | 0.6 | 2 | 2.4 |  |  | 0
|  | Left Wall |  |  |  |  | 2.5 | 2.7 | 1 | 6.75 |  |  | 0
|  | Façade |  |  |  |  | 5 | 0.4 | 2 | 4 |  |  | 0
|  | Branding Side Wall(Righ front) |  |  |  |  | 2.7 | 1.6 | 1 | 4.32 |  |  | 0
|  | Less Flap Door |  |  |  |  | 0.9 | 0.1 | -2 | -0.18 |  |  | 0
5 | Paint | Apply of 2 coat white enamel emulsion paint on pillar & side partition left&right | Duco Paint |  | 2.28 | Sqm |  |  |  |  | 2.42 | 2.28 | 0.14
|  | Roof Horizontal Pipe (50mmx50mm) |  |  |  |  | 2 | 0.2 | 2 | 0.8 |  |  | 0
|  | Pillar |  |  |  |  | 0.2 | 2.7 | 3 | 1.62 |  |  | 0
6 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with laminate finish , hinges, SS knob, tower bolt etch. |  |  | 1 | No | 1 | 0.07 | 0.9 |  | 1 | 1 | 0
7 | Kitchen Door With Vision Panel | Providing & Fixing of Kitchen door made of 32mm FR Ply with Flush door with both side laminate, with vision panel, 300x150mm, with hardware accessories & MS 50x50mm Frame work iwith paint finish |  |  | 1 | No | 1 | 0.05 | 2.4 |  | 1 | 1 | 0
8 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with Laminate finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | Century/Merino/ FGV | 825x750x900 | 0 | No. |  |  |  |  | 0 | 0 | 0
9 | Side Storages | Providing and installation of make of 18mm & 12mm Fr Plywood with approved laminate finish with hinges normal | Century/Merino/ FGV | 900x900x750 | 0 | Nos. |  |  |  |  | 0 | 0 | 0
10 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) | Havells, Syska or equivalent |  | 2 | No. |  |  |  |  | 2 | 2 | 0
11 | Linear Profile Light T5 | Providing & fixing linear profile light consealed in Rafter | Custom Make | 1200x1 | 2 | No. |  |  |  |  | 2 | 2 | 0
12 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, DB panel, MCB, ELCB, as per requirement or as approved electrical drawing | Polycab, Finolex, Roma, Crompton | 2550x2576 | 1 | No. |  |  |  |  | 1 | 1 | 0
13 | Industrial Socket | Industrial Socket & Panel Box (32amp ) |  |  | 2 | No. |  |  |  |  | 2 | 2 | 0
14 | DB Panel | Supply & Fixing of 12mm Way DB Panel wit 1 No. RCB & MCB 12 No's. | L&T |  | 0 | No |  |  |  |  | 0 | 0 | 0
15 | Main Cable | Supply & Fixing of 4 core 10 Sqm Coppe Cable for main DB to Meter | Polycab, Finolex, Roma, Crompton |  | 0 | Mtr. |  |  |  |  | 0 | 0 | 0
16 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork | HP Latex, 3M , LG Vinyl or equivalent |  | 97.3066 | Sqft. |  |  |  |  | 149.4043 | 97.31 | 52.0943
|  | Façade |  |  |  |  | 2 | 0.4 | 1 | 0.8 |  |  | 0
|  | Front Counter side |  |  |  |  | 2 | 0.6 | 1 | 1.2 |  |  | 0
|  | Back Wall Above Counter 1200mm |  |  |  |  | 2 | 2.7 | 1 | 5.4 |  |  | 0
|  | Left Side Wall |  |  |  |  | 2.7 | 1.6 | 1 | 4.32 |  |  | 0
|  | Left Kitchen Door |  |  |  |  | 2.4 | 0.9 | 1 | 2.16 |  |  | 0
17 | Healthy Eats | Front logo signaged fixed front façade , UV Printed 3mm raised acrylic . | A cast , NGX , Osram | 400x750 | 0 | No. |  |  |  |  | 0 | 0 | 0
18 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. | A cast , NGX , Osram | 2x 3 | 0 | No. |  |  |  |  | 0 | 0 | 0
19 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 2nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire | Hikvision |  | 0 | Set |  |  |  |  | 0 | 0 | 0
20 | Installation | T-1 Delhi Airport |  |  | 1 | EA |  |  |  |  | 1 | 1 | 0
21 | Transportation | T-1 Delhi Airport |  |  | 1 | EA |  |  |  |  | 1 | 1 | 0