## Summary
Semolina Projects
Project : Dominos NT Items
Details : Project Invoicing
PO No.: Semolina/PO/24-25/000706
Vendor : VSAS Group
Dominos NT Items - BILL SUMMARY
S. No. | Items | PO Value | Previous Bills | This Bill | Cumulative | Varition (In Amount)
1 | Miscellaneous Work - NT items 1 | 490340.07 | 0 | 531700 | 531700 | 0
2 | Miscellaneous Work - NT items 3 | 584464.43 | 0 | 633763.7 | 633763.7
3 | Fire Fighting - NT items 2 | 110739.21 | 0 | 120010.25 | 120010.25
| Subtotal | 1185543.71 |  | 1285473.95 | 1285473.95
| Discount | - |  | 100000 | -
|  | - |  | 1185473.95 | -
| GST 18% | 213397.8678 |  | 213385.311 | 213385.311
| Grand Total | 1398941.5778 |  | 1398859.261 | 1398859.261

## Dominos Non Items Abstract
DOMINOS NON-PO ITEMS
Miscellaneous Work - NT items 3
Sr. No. | Name of Item | Description of Item | Unit | BOQ QTY | Rate | RA Quantity |  |  | Amount |  |  | Varition
[6 empty] | Previous Bill | This Bill | Up to Date | Previous Bill | This Bill | Up to Date
1 | ANLGLE VOLVE | MAKE : HINDWARE | NOS | 6 | 1100 | 0 | 6 | 6 | 0 | 6600 | 6600
2 | Water Meter | MAKE : KRANTI | NOS | 1 | 4250 | 0 | 1 | 1 | 0 | 4250 | 4250
3 | Brass Ball Valve | MAKE : SANT | NOS | 2 | 900 | 0 | 2 | 2 | 0 | 1800 | 1800
4 | Water Meter Installation |  | JOB | 1 | 1500 | 0 | 1 | 1 | 0 | 1500 | 1500
5 | Cockroch Jali | SS 304 GRADE WITH INSTALLATION & FINISHING WITH GROUT i/c all COMPLETE | NOS | 6 | 1150 | 0 | 6 | 6 | 0 | 6900 | 6900
6 | Connection Pipe | From Angle Volve to Equipments i/c all labour and Installation | NOS | 4 | 600 | 0 | 4 | 4 | 0 | 2400 | 2400
7 | Grease Trap Fitting | Grease Trap Installation i/c all labour and fittings complete | NOS | 1 | 2000 | 0 | 1 | 1 | 0 | 2000 | 2000
8 | Pressure Pump | Pressure Pump Crompton Make with 0.5 hp Motar (Booster Pump) i/c all | NOS | 1 | 18000 | 0 | 1 | 1 | 0 | 18000 | 18000
9 | Pressure Pump Fitting | with all necessary fitting (Elbow,Union,PVC Pipe,Tee, Brass Connector) of needed sizes | NOS | 1 | 4200 | 0 | 1 | 1 | 0 | 4200 | 4200
10 | Water Tank 100 Ltr | supply & installation of 100 liter water storage tank above loft | NOS | 1 | 5000 | 0 | 1 | 1 | 0 | 5000 | 5000
11 | Manager Cable | supply & installation of manager cable i/c all necessary cutting & fixing | NOS | 6 | 200 | 0 | 6 | 6 | 0 | 1200 | 1200
12 | Manager Table | Providing and fixing of manager table of size 1200x750x600 with keyboard holder and shutter as per drawing finished with approved colour laminate as per engineer incharge | NOS | 1 | 18500 | 0 | 1 | 1 | 0 | 18500 | 18500
13 | Over Head Cabinet | Providing and fixing of manager table of size 1200x700 with approved laminate and shutter as per drawing finished as per engineer incharge | NOS | 1 | 15500 | 0 | 1 | 1 | 0 | 15500 | 15500
14 | Flap Door | Providing and fixing of Flap Door 19mm thik Front Side laminate finish with Haring Bone Pattern Back Side Colour Laminate with Tower bolt, Buffer, necessary hinges all complete | NOS | 1 | 7000 | 0 | 1 | 1 | 0 | 7000 | 7000
15 | Buffer | Providing and Fixing of Buffers of required sizes behind the equipments | NOS | 6 | 50 | 0 | 6 | 6 | 0 | 300 | 300
16 | Electrical Meter | Providing and Fixing Electric Meter of approved Brand as per airport | NOS | 1 | 26000 | 0 | 1 | 1 | 0 | 26000 | 26000
17 | Sink Installation |  | NOS | 1 | 1000 | 0 | 1 | 1 | 0 | 1000 | 1000
18 | Sink Jali Installation |  | NOS | 1 | 300 | 0 | 1 | 1 | 0 | 300 | 300
19 | Sink Over Head Cabinet Installation |  | NOS | 1 | 1000 | 0 | 1 | 1 | 0 | 1000 | 1000
20 | Makeline Installation |  | NOS | 2 | 300 | 0 | 2 | 2 | 0 | 600 | 600
21 | Tray Installation |  | NOS | 1 | 300 | 0 | 1 | 1 | 0 | 300 | 300
22 | Sink Near Cold Room |  | NOS | 1 | 1500 | 0 | 1 | 1 | 0 | 1500 | 1500
23 | CPVC Union | MAKE : SUPREME | NOS | 3 | 320 | 0 | 3 | 3 | 0 | 960 | 960
24 | DMB Switch Socket | Providing and Fixing of 6 way Plate with 2 Socket 2 Switch With Installation complete | NOS | 2 | 800 | 0 | 2 | 2 | 0 | 1600 | 1600
25 | Airport Networking | Providing and Fixing Cat-6A Cable for Airport CCTV, POS & Data Points (Approx 20 Meter Each length) @ 70 per meter | Pt | 6 | 1000 | 0 | 6 | 6 | 0 | 6000 | 6000
26 | Signages Point | Providing and Fixing Electrical Points For Signages (16 Meter 2.5 Sqmm 3 Wires ) | Pt | 4 | 2500 | 0 | 4 | 4 | 0 | 10000 | 10000
27 | Cold Room Corner Cover | Providing and Fixing Corner Joints of Cold Room Existing wall | NOS | 2 | 2100 | 0 | 2 | 2 | 0 | 4200 | 4200
28 | Ceilling Trap Door | Providing and Fixing Ceilling Trap Door for Excecing AHU and Cold Room Top | NOS | 3 | 400 | 0 | 3 | 3 | 0 | 1200 | 1200
29 | Industrial Socket 32 Amp |  | NOS | 4 | 900 | 0 | 4 | 4 | 0 | 3600 | 3600
30 | 4Cx6mm FRLS Cable 100 Meter | Supply of 4Cx6mm FRLS Cable | Bundle | 2 | 42500 | 0 | 2 | 2 | 0 | 85000 | 85000
31 | MCB GI Box |  | NOS | 2 | 1200 | 0 | 2 | 2 |  | 2400 | 2400
32 | 32 Amp 4 Pole MCCB |  | NOS | 2 | 3400 | 0 | 2 | 2 | 0 | 6800 | 6800
33 | 6 Amp 3 Pin Top |  | NOS | 4 | 250 | 0 | 4 | 4 | 0 | 1000 | 1000
34 | False Ceiling | Providing and Fixing in position suspended type 8 mm Bison Board False Ceiling with required M.S frame (40x40 mm ,18 gauge with 1 coat of primer & 2 or more coat of paint until achieved smooth finish as per drawing) work/ fixing arrangement of 2'x2' c/c and accessories, including groove joint filler, tapes, cut out for lights, & fixing for cove/ pelmet / box of approved size with necessary M.S. brackets / supports for light fittings / A.C. grills / Blinds, cleaning etc. complete as per detail drawing, as specified and as directed by Site Engineer. | Sqft | 516 | 455 | 0 | 430.86 | 430.86 | 0 | 196041.3 | 196041.3
|  | Kitchen+Cold Store | Sqft | 99.28 | 455 | 0 | 99.28 | 99.28 | 0 | 45172.4 | 45172.4
|  | Rework of Above Item | Sqft | 40 | 455 | 0 | 40 | 40 | 0 | 18200 | 18200
35 | Painting - Asain coal mine 8301 (Ceiling) | Providing and applying Plastic Emulsion Paint on Ceiling of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sqft | 516 | 70 | 0 | 516 | 516 | 0 | 36120 | 36120
|  | Rework of Above Item | Sqft | 516 | 70 | 0 | 516 | 516 | 0 | 36120 | 36120
36 |  | REMOVAL OF GYPSUM PARTITION BOARD IN THE EXISTING STRUCTURE | Sqft | 100 | 80 | 0 | 100 | 100 | 0 | 8000 | 8000
37 |  | SHERA BOARD PANNELLING ABOVE FRAME STRUCTURE MADE OF MS WORK | Sqft | 100 | 455 | 0 | 100 | 100 | 0 | 45500 | 45500
[6 empty] | Total |  |  |  | 633763.7 | 633763.7
Fire Fighting - NT Items 2
(PIPING AND ACCESSORIES)
| a | SLFTC of MS pipes on surface
Supplying, laying, fixing, testing and commissioning of following sizes (NB) of ISI marked heavy class M.S. pipes including cutting, threading, welding etc. and providing all fittings e.g. elbows, reducers, clamps, hangers, flanges, gaskets, nuts, bolts and washers etc. including painting of pipes and fittings with red paint over a coat of ready mixed primer, both of approved quality and shade including cutting holes and chases in brick or RCC walls/slabs and making good the same etc. complete in all respect as required. Pipes and fittings shall be confirming to IS 1239 Part -1
| a.5 | 50mm dia. | Meter | 14 | 1900 | 0 | 14 | 14 | 0 | 26600 | 26600
| a.8 | 25mm dia. | Meter | 9.6 | 1550 | 0 | 9.555 | 9.555 | 0 | 14810.25 | 14810.25
| b | SITC of butterfly valves
Supplying, Installation, Testing and Commissioning of butterfly valves of PN 1.6 rating of following sizes with nitrile seat and stainless steel stem with lever/gear operation and cast iron body in powder coated finish for fire fighting application complete in all respects as required.
| b.4 | 50 mm | Each | 1 | 10000 | 0 | 1 | 1 | 0 | 10000 | 10000
| g | SITC of Pressure gauge
|  | Supply, installation, testing & commissioning of 100 mm dia Bourden type, Stainless Steel dial type pressure gauge including brass isolation valve and pipe having calibration of 0-16 Kg/cm2. | Each | 1 | 7000 | 0 | 1 | 1 | 0 | 7000 | 7000
| f | Supplying, Installation, Testing and Commissioning of 15mm dia. Quartzoid bulb type sprinkler with temperature rating at 68°/79°C made out of forged brass and in powder coated finish., It shall be QR (Quick Response), Discharge Coefficient K=5.6 with Cover plates of same make, both shall be UL Listed & FM Approved.Make-Tyco, Viking.
| f.1 | Pendent/Upright 68° C Chrome Plated | Each | 6 | 2050 | 0 | 6 | 6 | 0 | 12300 | 12300
| f.2 | Pendent 141° C Chrome Plated | Each
| f.3 | Pendent/Upright 79° C Chrome Plated | Each | 2 | 2650 | 0 | 2 | 2 | 0 | 5300 | 5300
A.4.0 |  | Fire Extinguisher
|  | Supply and Installation of ABC powder type fire extinguisher of 6 Kgs. Capacity as per IS :15683, with initial filling in brand new cylinder with powder coated finish , extinguisher to be floor mounted and placed with SS stand fitted with, Gun metal union, discharge hose etc. complete. | Each | 2 | 12000 | 0 | 2 | 2 | 0 | 24000 | 24000
|  | Supply and Installation of CO2 type fire extinguisher of 4.5 Kgs. Capacity as per IS :15683, with initial filling in brand new cylinder with powder coated finish,extinguisher to be floor mounted and placed with SS stand fitted with, Gun metal union, discharge hose etc. complete. | Each | 2 | 10000 | 0 | 2 | 2 | 0 | 20000 | 20000
[6 empty] | Total |  |  |  | 120010.25 | 120010.25
Miscellaneous Work - NT items 1
1 |  | Supply & installation of 3-Way Motorised Valves with Motor, Thermostat, complete in all respect.
| 1A | 32 mm dia | NOS | 1 | 32000 | 0 | 1 | 1 | 0 | 32000 | 32000
2 |  | Supply & installation of BTU Metercomplete in all respect. Make Belimo
| 2A | 32 mm dia | NOS | 1 | 65000 | 0 | 1 | 1 | 0 | 65000 | 65000
3 |  | SITC of Startor Pannel for AHU with suitable size incoming MCCB, complete with conector, relay, Push button, Auto/ Manual switch, on/off indication, compatiable for power and control wirring complete in all respect. | NOS | 1 | 39000 | 0 | 1 | 1 |  | 39000 | 39000
4 |  | SITC of Thermostat for controlling of Temprature | NOS | 1 | 9000 | 0 | 1 | 1 | 0 | 9000 | 9000
5 |  | Supply and Installation of MS pipe for Air Handling Unit | RMT | 6 | 800 | 0 | 6 | 6 | 0 | 4800 | 4800
6 |  | Chilled Water Pipe | RMT | 39 | 1100 | 0 | 39 | 39 | 0 | 42900 | 42900
7 |  | Hot Water Pipe | RMT | 39 | 1100 | 0 | 39 | 39 | 0 | 42900 | 42900
8 |  | Supply and Installation of BaII Valve | NOS | 3 | 3600 | 0 | 3 | 3 | 0 | 10800 | 10800
9 |  | Labour Charges for above Work | NOS | 1 | 15000 | 0 | 1 | 1 | 0 | 15000 | 15000
10 |  | SITC of Spring Isolator for AHU | NOS | 4 | 2400 | 0 | 4 | 4 | 0 | 9600 | 9600
11 |  | SITC OF DRAIN PUMP COMPITIABLE FOR AHU UNIT. | NOS | 1 | 11000 | 0 | 1 | 1 | 0 | 11000 | 11000
12 |  | Supply installation24 G GI Square Ducting
| 12A | Supply installation24 G GI Square Ducting FRESH AIR DUCTING I C ALL (0.5x0.3 meter) Location - AROUND HOOD Length 7.0 x Breath 1.6 | SQM | 11.2 | 2000 | 0 | 11.2 | 11.2 | 0 | 22400 | 22400
|  | Location - HOOD TO MOD Length 10.5 x Breath 1.6 |  | 16.8 | 2000 | 0 | 16.8 | 16.8 | 0 | 33600 | 33600
|  | Location - MOD TO AIRPORT Length 7.5 x Breath 1.6 |  | 12 | 2000 | 0 | 12 | 12 | 0 | 24000 | 24000
| 12B | EXAUST AIR DUCTING I C ALL Location - AROUND HOOD Length 7.0 x Breath 1.6 | SQM | 11.2 | 2000 | 0 | 11.2 | 11.2 | 0 | 22400 | 22400
|  | Location - HOOD TO MOD Length 10.5 x Breath 1.6 |  | 16.8 | 2000 | 0 | 16.8 | 16.8 | 0 | 33600 | 33600
|  | Location - MOD TO AIRPORT Length 7.5 x Breath 1.6 |  | 12 | 2000 | 0 | 12 | 12 | 0 | 24000 | 24000
13 |  | Supply and Installation of Fire damper | SQM | 0
14 |  | Hood installation | NOS | 0
15 |  | 2 way GATE VALVE | NOS | 1 | 7000 | 0 | 1 | 1 | 0 | 7000 | 7000
16 |  | BUTTERFLY VALVE | NOS | 3 | 10000 | 0 | 3 | 3 | 0 | 30000 | 30000
17 |  | FRESH AIR GRILL | NOS | 3 | 4500 | 0 | 3 | 3 | 0 | 13500 | 13500
18 |  | LINER GRILL 150MM X 800MM WITH COLLAR DAMPER | NOS | 3 | 2900 | 0 | 3 | 3 | 0 | 8700 | 8700
19 |  | FIRE DAMPER WITH MOTORISED VALVE | NOS | 1 | 21000 | 0 | 1 | 1 | 0 | 21000 | 21000
20 |  | THERMOSTATE | NOS | 1 | 9500 | 0 | 1 | 1 | 0 | 9500 | 9500
[6 empty] | Total |  |  |  | 531700 | 531700
GRAND TOTAL - NT ITEM 1 & NT ITEM 2 & NT ITEM 3 | [9 empty] | 1285473.95 | 1285473.95
DISCOUNT- | [9 empty] | 100000 | 100000
GRAND TOTAL - | [9 empty] | 1185473.95 | 1185473.95

## Dominos Non Items MB Sheet
DOMINOS NON-PO ITEMS
Sr. No. | Name of Item | Description of Item | Unit | BOQ QTY | Location | Site Quantity |  | Our Qty | Sign
[6 empty] | Length | Breath
1 | ANLGLE VOLVE | MAKE : HINDWARE | NOS | 6 |  |  |  | 6
2 | Water Meter | MAKE : KRANTI | NOS | 1 |  |  |  | 1
3 | Brass Ball Valve | MAKE : SANT | NOS | 2 |  |  |  | 2
4 | Water Meter Installation |  | JOB | 1 |  |  |  | 1
5 | Cockroch Jali | SS 304 GRADE WITH INSTALLATION & FINISHING WITH GROUT i/c all COMPLETE | NOS | 6 |  |  |  | 6
6 | Connection Pipe | From Angle Volve to Equipments i/c all labour and Installation | NOS | 4 |  |  |  | 4
7 | Grease Trap Fitting | Grease Trap Installation i/c all labour and fittings complete | NOS | 1 |  |  |  | 1
8 | Pressure Pump | Pressure Pump Crompton Make with 0.5 hp Motar (Booster Pump) i/c all | NOS | 1 |  |  |  | 1
9 | Pressure Pump Fitting | with all necessary fitting (Elbow,Union,PVC Pipe,Tee, Brass Connector) of needed sizes | NOS | 1 |  |  |  | 1
10 | Water Tank 100 Ltr | supply & installation of 100 liter water storage tank above loft | NOS | 1 |  |  |  | 1
11 | Manager Cable | supply & installation of manager cable i/c all necessary cutting & fixing | NOS | 6 |  |  |  | 6
12 | Manager Table | Providing and fixing of manager table of size 1200x750x600 with keyboard holder and shutter as per drawing finished with approved colour laminate as per engineer incharge | NOS | 1 |  |  |  | 1
13 | Over Head Cabinet | Providing and fixing of manager table of size 1200x700 with approved laminate and shutter as per drawing finished as per engineer incharge | NOS | 1 |  |  |  | 1
14 | Flap Door | Providing and fixing of Flap Door 19mm thik Front Side laminate finish with Haring Bone Pattern Back Side Colour Laminate with Tower bolt, Buffer, necessary hinges all complete | NOS | 1 |  |  |  | 1
15 | Buffer | Providing and Fixing of Buffers of required sizes behind the equipments | NOS | 6 |  |  |  | 6
16 | Electrical Meter | Providing and Fixing Electric Meter of approved Brand as per airport | NOS | 1 |  |  |  | 1
17 | Sink Installation |  | NOS | 1 |  |  |  | 1
18 | Sink Jali Installation |  | NOS | 1 |  |  |  | 1
19 | Sink Over Head Cabinet Installation |  | NOS | 1 |  |  |  | 1
20 | Makeline Installation |  | NOS | 2 |  |  |  | 2
21 | Tray Installation |  | NOS | 1 |  |  |  | 1
22 | Sink Near Cold Room |  | NOS | 1 |  |  |  | 1
23 | CPVC Union | MAKE : SUPREME | NOS | 3 |  |  |  | 3
24 | DMB Switch Socket | Providing and Fixing of 6 way Plate with 2 Socket 2 Switch With Installation complete | NOS | 2 |  |  |  | 2
25 | Airport Networking | Providing and Fixing Cat-6A Cable for Airport CCTV, POS & Data Points (Approx 20 Meter Each length) @ 70 per meter | Pt | 6 |  |  |  | 6
26 | Signages Point | Providing and Fixing Electrical Points For Signages (16 Meter 2.5 Sqmm 3 Wires ) | Pt | 4 |  |  |  | 4
27 | Cold Room Corner Cover | Providing and Fixing Corner Joints of Cold Room Existing wall | NOS | 2 |  |  |  | 2
28 | Ceilling Trap Door | Providing and Fixing Ceilling Trap Door for Excecing AHU and Cold Room Top | NOS | 3 |  |  |  | 3
29 | Industrial Socket 32 Amp |  | NOS | 4 |  |  |  | 4
30 | 4Cx6mm FRLS Cable 100 Meter | Supply of 4Cx6mm FRLS Cable | Bundle | 2 |  |  |  | 2
31 | MCB GI Box |  | NOS | 2 |  |  |  | 2
32 | 32 Amp 4 Pole MCCB |  | NOS | 2 |  |  |  | 2
33 | 6 Amp 3 Pin Top |  | NOS | 4 |  |  |  | 4
34 | False Ceiling | Providing and Fixing in position suspended type 8 mm Bison Board False Ceiling with required M.S frame (40x40 mm ,18 gauge with 1 coat of primer & 2 or more coat of paint until achieved smooth finish as per drawing) work/ fixing arrangement of 2'x2' c/c and accessories, including groove joint filler, tapes, cut out for lights, & fixing for cove/ pelmet / box of approved size with necessary M.S. brackets / supports for light fittings / A.C. grills / Blinds, cleaning etc. complete as per detail drawing, as specified and as directed by Site Engineer. | Sqft | 516 |  | 16.7 | 25.8 | 430.86
|  | Kitchen+Cold Store | Sqft | 99.28 |  | 14.6 | 6.8 | 99.28
|  | Rework of Above Item | Sqft | 40 |  |  |  | 40
35 | Painting - Asain coal mine 8301 (Ceiling) | Providing and applying Plastic Emulsion Paint on Ceiling of approved make & shade filling the dents with approved Acrylic putty gypsum / or approved crack filler, binder, cleaning and making the surface dust free, preparing surfaces, applying a coat of sealer or primer as per the manufacturers specifications, applying two under coats and one finished coat of paint to achieve the required finish including scrapping the existing paint, scaffolding, cleaning etc. complete as per detail drawing, as specified and as directed by Engineer-in-charge. | Sqft | 516 |  |  |  | 516
|  | Rework of Above Item | Sqft | 516 |  |  |  | 516
36 |  | REMOVAL OF GYPSUM PARTITION BOARD IN THE EXISTING STRUCTURE | Sqft | 100 |  |  |  | 100
37 |  | SHERA BOARD PANNELLING ABOVE FRAME STRUCTURE MADE OF MS WORK | Sqft | 100 |  |  |  | 100
A.2.0 |  | (PIPING AND ACCESSORIES)
| a | SLFTC of MS pipes on surface
Supplying, laying, fixing, testing and commissioning of following sizes (NB) of ISI marked heavy class M.S. pipes including cutting, threading, welding etc. and providing all fittings e.g. elbows, reducers, clamps, hangers, flanges, gaskets, nuts, bolts and washers etc. including painting of pipes and fittings with red paint over a coat of ready mixed primer, both of approved quality and shade including cutting holes and chases in brick or RCC walls/slabs and making good the same etc. complete in all respect as required. Pipes and fittings shall be confirming to IS 1239 Part -1
| a.5 | 50mm dia. | Meter | 14 |  |  |  | 14
| a.8 | 25mm dia. | Meter | 9.6 |  | 7.35 | 1.3 | 9.555
| b | SITC of butterfly valves
Supplying, Installation, Testing and Commissioning of butterfly valves of PN 1.6 rating of following sizes with nitrile seat and stainless steel stem with lever/gear operation and cast iron body in powder coated finish for fire fighting application complete in all respects as required.
| b.4 | 50 mm | Each | 1 |  |  |  | 1
| g | SITC of Pressure gauge
|  | Supply, installation, testing & commissioning of 100 mm dia Bourden type, Stainless Steel dial type pressure gauge including brass isolation valve and pipe having calibration of 0-16 Kg/cm2. | Each | 1 |  |  |  | 1
| f | Supplying, Installation, Testing and Commissioning of 15mm dia. Quartzoid bulb type sprinkler with temperature rating at 68°/79°C made out of forged brass and in powder coated finish., It shall be QR (Quick Response), Discharge Coefficient K=5.6 with Cover plates of same make, both shall be UL Listed & FM Approved.Make-Tyco, Viking.
| f.1 | Pendent/Upright 68° C Chrome Plated | Each | 6 |  |  |  | 6
| f.2 | Pendent 141° C Chrome Plated | Each
| f.3 | Pendent/Upright 79° C Chrome Plated | Each | 2 |  |  |  | 2
A.4.0 |  | Fire Extinguisher
|  | Supply and Installation of ABC powder type fire extinguisher of 6 Kgs. Capacity as per IS :15683, with initial filling in brand new cylinder with powder coated finish , extinguisher to be floor mounted and placed with SS stand fitted with, Gun metal union, discharge hose etc. complete. | Each | 2 |  |  |  | 2
|  | Supply and Installation of CO2 type fire extinguisher of 4.5 Kgs. Capacity as per IS :15683, with initial filling in brand new cylinder with powder coated finish,extinguisher to be floor mounted and placed with SS stand fitted with, Gun metal union, discharge hose etc. complete. | Each | 2 |  |  |  | 2
1 |  | Supply & installation of 3-Way Motorised Valves with Motor, Thermostat, complete in all respect.
| 1A | 32 mm dia | NOS | 1 |  |  |  | 1
2 |  | Supply & installation of BTU Metercomplete in all respect. Make Belimo
| 2A | 32 mm dia | NOS | 1 |  |  |  | 1
3 |  | SITC of Startor Pannel for AHU with suitable size incoming MCCB, complete with conector, relay, Push button, Auto/ Manual switch, on/off indication, compatiable for power and control wirring complete in all respect. | NOS | 1 |  |  |  | 1
4 |  | SITC of Thermostat for controlling of Temprature | NOS | 1 |  |  |  | 1
5 |  | Supply and Installation of MS pipe for Air Handling Unit | RMT | 6 |  |  |  | 6
6 |  | Chilled Water Pipe | RMT | 39 |  |  |  | 39
7 |  | Hot Water Pipe | RMT | 39 |  |  |  | 39
8 |  | Supply and Installation of BaII Valve | NOS | 3 |  |  |  | 3
9 |  | Labour Charges for above Work | NOS | 1 |  |  |  | 1
10 |  | SITC of Spring Isolator for AHU | NOS | 4 |  |  |  | 4
11 |  | SITC OF DRAIN PUMP COMPITIABLE FOR AHU UNIT. | NOS | 1 |  |  |  | 1
12 |  | Supply installation24 G GI Square Ducting
| 12A | Supply installation24 G GI Square Ducting FRESH AIR DUCTING I C ALL (0.5x0.3 meter) Location - AROUND HOOD Length 7.0 x Breath 1.6 | SQM | 11.2 | AROUND HOOD | 7 | 1.6 | 11.2
|  | Location - HOOD TO MOD Length 10.5 x Breath 1.6 |  | 16.8 | HOOD TO MOD | 10.5 | 1.6 | 16.8
|  | Location - MOD TO AIRPORT Length 7.5 x Breath 1.6 |  | 12 | MOD TO AIRPORT | 7.5 | 1.6 | 12
| 12B | EXAUST AIR DUCTING I C ALL Location - AROUND HOOD Length 7.0 x Breath 1.6 | SQM | 11.2 | AROUND HOOD | 7 | 1.6 | 11.2
|  | Location - HOOD TO MOD Length 10.5 x Breath 1.6 |  | 16.8 | HOOD TO MOD | 10.5 | 1.6 | 16.8
|  | Location - MOD TO AIRPORT Length 7.5 x Breath 1.6 |  | 12 | MOD TO AIRPORT | 7.5 | 1.6 | 12
13 |  | Supply and Installation of Fire damper | SQM | 0
14 |  | Hood installation | NOS | 0
15 |  | 2 way GATE VALVE | NOS | 1 |  |  |  | 1
16 |  | BUTTERFLY VALVE | NOS | 3 |  |  |  | 3
17 |  | FRESH AIR GRILL | NOS | 3 |  |  |  | 3
18 |  | LINER GRILL 150MM X 800MM WITH COLLAR DAMPER | NOS | 3 |  |  |  | 3
19 |  | FIRE DAMPER WITH MOTORISED VALVE | NOS | 1 |  |  |  | 1
20 |  | THERMOSTATE | NOS | 1 |  |  |  | 1