## Sheet1
ARROW ELECTRICALS-MUMBAI
BOQ FOR RA-1 BILL-SUBWAY-ELECTRICALS WORK DELHI-T1
|  |  |  | AS PER WO |  |  | RA-1 BILL
| ItemCode | ItemName | UOM | Quantity | SupplierRate | Amount | % | Amount
1 | I | PANEL SWITCHGEAR
2 | 1 | Supply, installation, testing commissioning of Switchgears.(Standard Product)
3 |  | MAIN PANEL-1 | Nos. | 1.00 | 165000 | 165000 | 75% | 123750
4 |  | Incomer 63 AMPS 4P MCB, 10kA
5 |  | Meter Protection ELR with CBCT; 60 5A, 15VA, CL-1 CT s -3 Nos. for Schneider make Digital Load Manager (EM 6400 NG)
6 |  | Indication Phase indicating lamps with 6A MCB
7 |  | Busbar 75A TPN AL Busbar
8 |  | Outgoings
9 |  | a) 63A 4P MCB, C TYPE - 3 Nos
10 |  | b) 40A 4P MCB, C TYPE - 2 Nos
11 |  | c) 32A DP MCB, C TYPE - 2 Nos
12 |  | d) 20A 4P MCB, C TYPE - 2 Nos
13 |  | e) MPCB SUITABLE for 1.5 kw motor DOL Starter, Phase Indicating lamps, ON OFF TRIP Indication, ON OFF Push Button-1 Nos.
14 |  | f) MPCB SUITABLE for 1.1 kw motor DOL Starter, Phase Indicating lamps, ON OFF TRIP Indication, ON OFF Push Button-2 Nos.
15 | 1.1 | Supply,Installation,Testing and Commissioning of 20 Amps,DP ELMCB 100mA for HVAC Outdoor Isolation all complete with mounting accessories | Nos. | 0.00 | 9500
16 | 1.2 | Supply,Installation,Testing and Commissioning of 63 Amps,3Pole MCB for HVAC Outdoor Isolation all complete with mounting accessories. | Nos. | 0.00 | 7800
17 | 1.3 | Supply,Installation,Testing and Commissioning of 40 Amps,4Pole MCB for HVAC Outdoor Isolation all complete with mounting accessories. | Nos. | 3.00 | 4500 | 13500 | 75% | 10125
18 | 1.4 | Supply,Installation,Testing and Commissioning of 32 Amps, DP, MCB for UPS Isolation all complete with mounting accessories for UPS. | Nos. | 2.00 | 3050 | 6100 | 75% | 4575
19 | 1.14 | 32 amps 4P MCB with 32A 5 Pin Ray Roll Socket complete with all mounting accessories – for Kitchen Legrand make model No. 6078 80 | Nos. | 2.00 | 11110 | 22220 | 75% | 16665
20 | 1.17 | 20 32A Rey roll socket complete with 25 amps SPMCB with 3 pin metal clad socket Plug top | Nos. | 2.00 | 2810 | 5620 | 75% | 4215
21 |  | I) 25A, 3Pin industrial metal clad Socket with MCB – 1nos
22 |  | I) 20A, 3Pin industrial metal clad Socket with MCB – 1nos
23 |  | ii)set of 2nos 16A Bakelite Socket with 2nos 16A Switch –3nos
24 |  | iii) Data Socket – 2nos
25 |  | iv) Telephone Socket – 1no.
26 | II | UPS
27 | 1 | Supply, Installation, testing and commissioning of 3.0 KVA UPS System Single Phase I C Single Phase O G complete with 30 Minutes Battery Back-up the required accessories as specified in the drawings the specifications. | Nos. | 1.00 | 75000 | 75000 | 75% | 56250
28 | III | DISTRIBUTION BOARDS
29 |  | Supply, installation, testing commissioning of Distribution Boards surface flush mounted with Double door containing MCB ELMCB as incomer and SPMCB as outgoing. All MCBs are of 10KA breaking capacity and ELMCBs RCCB should be of 30mA 100 300 mA sensiv
30 | 2 | Kitchen Power DB - KPDB | Nos. | 1.00 | 24500 | 24500 | 75% | 18375
31 |  | 8 way TPN DB
32 |  | I C-63A FP MCB -1 Nos
33 |  | SUB I C 40A DP RCCB @ 100mA - 3 Nos
34 |  | O G -18 # 10 16 20A SP MCB
35 | 3 | LDB | Nos. | 1.00 | 9000 | 9000 | 75% | 6750
36 |  | 12 way SPN DB
37 |  | I C-32A RCBO 30mA-1 Nos
38 |  | O G -8 # 6 10A SP MCB
39 | 4 | UPSDB | Nos. | 1.00 | 9000 | 9000 | 75% | 6750
40 |  | 12 way SPN DB
41 |  | I C-32A RCBO 30mA-1 Nos
42 |  | O G -8 # 6 10A SP MCB
43 | IV | CABLES ACCESSORIES
44 |  | Supply installation of following LT XLPE FRLS cables rated for 600 1100 volts AC as per IS standard 1554 Part 1 with necessary M.S. clamps. All cables shall be properly clamped or tied when run on cable trays. All such cables shall be provided with
45 | 9 | 4C x 25 Sq. mm A2XFY | Mtr. | 30.00 | 310 | 9300 | 75% | 6975
46 | 10 | 4C x 16 Sq. mm A2XFY | Mtr. | 10.00 | 220 | 2200 | 75% | 1650
47 | 11 | 4C x 10 Sq. mm A2XFY | Mtr. | 10.00 | 190 | 1900 | 75% | 1425
48 | 12 | 4C x 10 Sq. mm 2XFY ( Cu ) | Mtr. | 10.00 | 700 | 7000 | 75% | 5250
49 | 13 | 4C x 16 Sq. mm 2XFY Cable ( Cu ) | Mtr. | 10.00 | 940 | 9400 | 75% | 7050
50 | 14 | 4C x 6 Sq. mm 2XFY Cable ( Cu ) | Mtr. | 10.00 | 455 | 4550 | 75% | 3412.5
51 | 15 | 4C x 2.5 Sq. mm 2XFY Cable ( Cu ) | Mtr. | 10.00 | 280 | 2800 | 75% | 2100
52 | 17 | 3C x 4sq. mm YWY cable ( Cu ) | Mtr. | 20.00 | 295 | 5900 | 75% | 4425
53 | 18 | 3C x 2.5 Sq. mm YWY cable ( Cu ) | Mtr. | 80.00 | 228 | 18240 | 75% | 13680
54 | 24 | 5Rx1Cx6 Sq.mm YY FRLS Cable (Cu) | Mtr. | 45.00 | 495 | 22275 | 75% | 16706.25
55 | 25 | 1Rx1Cx4 Sq.mm YY FRLS Cable (Cu) | Mtr. | 50.00 | 62 | 3100 | 75% | 2325
56 | B | Termination of following sizes of cables with Single compression cable gland.(COMET BRAKO)
57 | 9 | 4C x 25 Sq. mm A2XFY | Nos. | 2.00 | 550 | 1100 | 75% | 825
58 | 10 | 4C x 16 Sq. mm A2XFY | Nos. | 2.00 | 450 | 900 | 75% | 675
59 | 18 | 3C x 2.5 Sq. mm YWY cable ( Cu ) | Nos. | 6.00 | 250 | 1500 | 75% | 1125
60 | 24 | 5Rx1Cx6 Sq.mm YY FRLS Cable (Cu) | Nos. | 4.00 | 365 | 1460 | 75% | 1095
61 | 25 | 1Rx1Cx4 Sq.mm YY FRLS Cable (Cu) | Nos. | 2.00 | 65 | 130 | 75% | 97.5
62 | V | WIRING ACCESSORIES
63 |  | 1) Rates for point wiring shall include supply installation of Wires wiring acccessories such as angle holders ceiling roses as required. conduits, conduit accessories such as junction boxes, Ts, elbows etc,Switches, sockets fixtures shall not be
64 |  | 2) Unless otherwise specified, all wires in point wiring shall be 2.5 sq.mm
65 |  | Stranded copper conductor 1.1 KV grade, I.S.I. marked (P+N+E),
66 |  | (FRLSH) PVC insulated .
67 |  | Wires shall be colour coded (Red, Yellow and Blue for Phases,
68 |  | Black for Neutral Green for earth).
69 |  | 3) Looping of wires shall be in fittings and switch boxes only
70 |  | 4) Location of switches sockets DBs shown on the drawings shall
71 |  | be confirmed with the Architect Consultant Project Manager
72 |  | before installation.
73 |  | 5) All Surface and concealed Conduits shall be rigid GI conduits of
74 |  | size not less than 20 mm dia as per applicable IS.
75 |  | 6)The Contractor can take more than one circuit in the same conduit
76 |  | provided they are of the same phase. The size of conduit shall be
77 |  | decided according to the number of wires in it as per applicable IS as
78 |  | specified.
79 |  | 7) Payments for light fixtures fans will be made separately as per the
80 |  | items given in Light Fixtures Accessories .
81 |  | 8) Type location of light fixtures shown in the drawings are
82 |  | tentative and subject to revision as per the recommendation of
83 |  | Architect Consultant. The quantities (number of points and accessories)
84 |  | of point wiring will be revised as actual installed on account of such
85 |  | revisions in the layouts.
86 |  | 9) Circuit wiring from DBs to the switch boards or first light point shall
87 |  | Be included as primary points remaining points of the same looping
88 |  | shall be considered as Secondary points and shall be counted in nos.
89 |  | 10) Circuit Wiring from DB to Kitchen Power points shall be measured in running meters
90 | 1 | Supply, installation, testing commissioning of point wiring for light points, power points. Point wiring for primary point shall include wiring from Distribution Board upto First point of the circuit and shall be measured in nos. Secondary points shall
91 | a) | Primary Light points controlled by MCB (1R 3Cx 2.5 sqmm wire) | Nos. | 0.00 | 4250
92 | b) | Secondary Light points looped in the same circuit. (1R 3Cx 2.5 sqmm wire) | Nos. | 0.00 | 2500
93 | 1 | Supply, installation, testing commissioning of point wiring for EMER light points, power points. Point wiring for primary point shall include wiring from Distribution Board upto First point of the circuit and shall be measured in nos. Secondary points
94 | a) | Primary Light points controlled by MCB (1R 3Cx 2.5 sqmm wire) | Nos. | 0.00 | 4250
95 | b) | Secondary Light points looped in the same circuit. (1R 3Cx 2.5 sqmm wire) | Nos. | 0.00 | 2500
96 | 2 | Supply, installation, testing commissioning of point wiring for light Point points, power points. Point wiring for primary point shall include wiring from Switch Board upto First point of the circuit and shall be measured in nos. Secondary points shal
97 | a) | Primary Light Fan points controlled by Switch (1R 3Cx 2.5 sqmm wire) | Nos. | 15.00 | 3800 | 57000 | 75% | 42750
98 | b) | Secondary Light Fan points looped in the same circuit. (1R 3Cx 2.5 sqmm wire) | Nos. | 22.00 | 1550 | 34100 | 75% | 25575
99 | c) | DB to SB SB to SB circuit wiring Wiring for switch board controlled by MCB already installed in DB by using 3 X 2.5 sq. mm flexible FRLSH copper wires in 25mm rigid GI conduits as per IS 9537 part-3 or surface mounted. | Mtrs | 80.00 | 290 | 23200 | 75% | 17400
100 | 5 | Providing point wiring for a cluster of 2 nos.6 amps socket outlets and 1 no. 16A switch pop up box for Computer POS Power Points using 3Cx4 sq. mm PVC insulated copper conductor wires from UPSDB to plug point in Existing Floor Raceway GI Conduits a
101 | a) | Primary Point | Nos. | 1.00 | 4150 | 4150 | 75% | 3112.5
102 | b) | Secondary points | Nos. | 1.00 | 1810 | 1810 | 75% | 1357.5
103 | 7 | Providing point wiring for Raw Power points 1no. 6 16A switch socket outlet on Skirting level to be looped from the nearest point using 3Cx4 sq. mm copper conductor wires . (Cost of GI Conduit is included and switch sockets are considered elsewhere).
104 | a) | Primary Point | Nos. | 15.00 | 4110 | 61650 | 75% | 46237.5
105 | b) | Secondary points | Nos. | 14.00 | 1850 | 25900 | 75% | 19425
106 | 8 | Providing point wiring for Raw Power points 1no. 6A switch socket outlet on Skirting level to be looped from the nearest point using 3Cx4sq. mm copper conductor wires (Cost of GI Conduit is included and switch sockets are considered elsewhere). (Wires
107 | a) | Primary Point | Nos. | 10.00 | 4050 | 40500 | 75% | 30375
108 | b) | Secondary points | Nos. | 10.00 | 2210 | 22100 | 75% | 16575
109 | 10 | Providing point wiring for Primary Secondary CCTV points using 3Cx4 sq. mm PVC insulated copper flexible FRLSH cable in already laid 25 mm dia. GI conduit surface mounted on ceiling, concealed in wall and or through partitions with necessary boxes pul | Mtr. | 10.00 | 320 | 3200 | 75% | 2400
110 | 11 | Supply and laying of following PVC insulated copper conductor 1100 volt grade stranded flexible FRLS wire in already laid GI conduit concealed or surface mounted making connections where ever required to complete the installation.(For Kitchen Power Poi
111 | a) | 3Cx4 Sqmm Cu. Wires | Mtr. | 300.00 | 210 | 63000 | 75% | 47250
112 | b) | 4R x 4Sqmm + 1R x 2.5Sqmm Cu. Wires | Mtr. | 10.00 | 255 | 2550 | 75% | 1912.5
113 | 12 | Supply installation of 25 mm dia. GI conduit with pull box junction box all accessories for Kitchen Bar Power wiring as per the requirement
114 | a | - do - but conduit pipe shall be Rigid type. | Mtr. | 150.00 | 220 | 33000 | 75% | 24750
115 | b | - do - but flexible conduit pipe | Mtr. | 20.00 | 65 | 1300 | 75% | 975
116 | 13 | Supply installation of 20 mm dia. GI conduit with pull box junction box all accessories for Lighting Power wiring as per the requirement
117 | a | - do - but conduit pipe shall be Rigid type. | Mtr. | 50.00 | 185 | 9250 | 75% | 6937.5
118 | 14 | Supply and installation of Perforated Cable Tray (ASIAN)out of 14 gauge GI sheet complete with necessary fixing arrangement with Anchor Fastener and all other accessories as per the final approval of the Consultant Architect
119 | a | 300 x 50 x 2mm | Mtr. | 20.00 | 1160 | 23200 | 75% | 17400
120 | c | 150 x 50 x 2mm | Mtr. | 30.00 | 590 | 17700 | 75% | 13275
121 | 15 | Supply and installation of GI trunking (SV POWER ASIAN) with 2 mm thickness properties clamps for suspension at appropriate intervals as per the route approved by Architect Consultant. (For DATA CONTROL WIRING LIGHTING POWER CIRCUITS KITCHEN)
122 | e | 50 x 50 x 2mm | Mtr. | 20.00 | 550 | 11000 | 75% | 8250
123 | 16 | Supply and installation of GI raceway with 2 mm thickness proper ties clamps at appropriate intervals as per the route approved by Architect Consultant. (Cost of cutting the floor for laying of raceways to be included).
124 | c | 1 runs of underfloor GI raceways of size 100 x 40 mm | Mtr. | 20.00 | 342 | 6840 | 75% | 5130
125 | 17 | Supply installation of GI junction boxes with 2 mm thickness, 2mm thick SS cover with 2” extra on all sides SS cover on top and having screw fixed plates on all four sides with knock out holes for conduits. The plates shall be retained on the sidezs ha
126 | d | suitable for 150 x 150 x 50 mm | Nos. | 3.00 | 500 | 1500 | 75% | 1125
127 | 18 | Supply, installation, testing commissioning of flush mounted plate type switch and switch + sockets with hot dipped GI box complete as per the final approval of Architect Consultant
128 | a | 6A one way plate type switch | Nos. | 20.00 | 230 | 4600 | 75% | 3450
129 | b | 6A 5 pin Socket outlet | Nos. | 2.00 | 375 | 750 | 75% | 562.5
130 | c | 6A 5pin switch socket outlet for CCTV Charging point | Nos. | 12.00 | 600 | 7200 | 75% | 5400
131 | d | 2 nos 6A switch socket outlet | Nos. | 2.00 | 1210 | 2420 | 75% | 1815
132 | f | 1 nos. 6 16A socket controlled by1nos 6 16A switch for Kitchen | Nos. | 25.00 | 750 | 18750 | 75% | 14062.5
133 | h | Data Socket (D-Link) | Nos. | 10.00 | 555 | 5550 | 75% | 4162.5
134 | i | Telephone Socket | Nos. | 2.00 | 550 | 1100 | 75% | 825
135 | j | TV Socket | Nos. | 4.00 | 350 | 1400 | 75% | 1050
136 | 16 | Supply, installation of temporary lighting power arrangement for construction purpose of with industrial type switch sockets MCB s ELCB s lighting fittings as required to finish the work for interior contractor necessary electrical protections thr | Job | 1.00 | 22000 | 22000 | 75% | 16500
137 | 1 | 22 W DOWN LIGHT | Nos. | 32.00 | 200 | 6400 | 75% | 4800
138 | 4 | TUBE LIGHT | Nos. | 2.00 | 100 | 200 | 75% | 150
139 | VII | EARTHING
140 | 3 | Supply erection of G.I. strip of 25 x 3 mm used for earthing on wall, cable trays with necessary clamps fixed on wall painted with bituminous paint in an approved manner. | Mtr. | 60.00 | 180 | 10800 | 75% | 8100
141 | 5 | Supplying erecting bare copper conductor of 8 swg for earthing purpose | Mtr. | 40.00 | 90 | 3600 | 75% | 2700
142 | 9 | Supplying installation testing commissioning of earth terminal box | Nos. | 1.00 | 2500 | 2500 | 75% | 1875
143 | VIII | MISCELLANEOUS
144 | 1 | Supply Installation of 6A 3 pin plug top | Nos. | 4.00 | 110 | 440 | 75% | 330
145 | 2 | Supply Installation of 16A 3 pin plug top | Nos. | 8.00 | 150 | 1200 | 75% | 900
146 | 4 | Supply laying of Rubber Mats, CPRI tested conforming to standards like BS 921, ASTM-D 178 IEC 479 for different operatng voltage ratings as below.
147 | 7 | Supply fixing of the best quality LT Danger Boards(415V) for of approved shape and size as specified by the local electrical authorities written in English, and local Language | Nos. | 1.00 | 400 | 400 | 75% | 300
148 | A | DATA AND TELEPHONE SYSTEM
149 | 1 | Supply Installation of 25mm.dia. HMS GI conduit with pull box junction box all accessories for DATA VOICE WIFI wiring as per the requirement. | Mtr. | 150.00 | 190 | 28500 | 75% | 21375
150 | 2 | Supply Installation of Cat-6 E Cable in above conduits for DATA System. | Mtr. | 200.00 | 90 | 18000 | 75% | 13500
|  | TOTAL AMOUNT |  |  |  | 1000455 |  | 750341.25
|  | GST |  |  | 18% | 180081.9 |  | 135061.425
|  | GRAND TOTAL WITH GST |  |  |  | 1180536.9 |  | 885402.675
| CERTIFIED BY NAME:….................................. |  | DATE:…................................ |  |  | Sign..................................