## summary
Intercare Enterprise
To,
| Travel Food Services Private Limited | Date: 04/11/2024
| Kolkata | PO No: TFSKPL/PO/24-25/000136
Final Performa bill for Civil & Interior of Irish House project.
Sr. No. | Item Description | BOQ Amount | Actual Bill Amount
1 | P&F of Civil & Interior work | 1227264 | 1181710
TOTAL without taxes |  | 1227264 | 1181710
18% GST |  | 220907.52 | 212707.8
| Grand Total | 1448171.52 | 1394417.8

## Bill
Performa bill for Civil & Interior of Irish House project.
Sr. No. | Item Description | Units | BOQ Qty | Actual qty | Rate/Unit | Amount
1 | Providing and applying wood Polish of approved shade on existing heigh table, complete as per instruction received from Engineer incharge. | Nos | 2 | 2 | 12000 | 24000
2 | Repairing of existing door frame: Providing and applying of wood polish over Door frame of approved shade and as per instruction of Engineer incharge. | Nos | 6 | 6 | 4500 | 27000
3 | Providing and applying Painting on existing Main signage (The Irish House) of approved make and shade, as per provided details and as per instruction of Engineer incharge. | Nos | 2 | 2 | 8500 | 17000
4 | Demolition of Existing wall tiles and removing of debris to required location, all as per instruction and satisfaction of Engineer incharge | Sq ft | 150 | 128 | 35 | 4480
5 | Demolition of Existing 2x2 metal grid ceiling and removing of debris to required location, all as per instruction and satisfaction of Engineer incharge | Sq ft | 420 | 408 | 10 | 4080
6 | Removing/ Breaking of Existing wall tiles and fixing of 2 x 2 wall tiles as per existing matching tiles with debris' cleaning from site to required location. | Sq ft | 150 | 148 | 295 | 43660
7 | Supply and installation of 2 x 2 metal grid ceiling as per approved design or as per instruction of Engineer incharge. | Sq ft | 420 | 425 | 180 | 76500
8 | Repairing work- Demolition of existing Kota stone flooring and Supply and installation of kota stone flooring for required area with debris shifting to required location all as per intruction of Engineer incharge/ Site inchrage. | Sq ft | 50 | 44 | 260 | 11440
9 | Polish the Kota Stone tiles using a buffing machine or Poilishig pads to enhance their natural shine and Kota Stone design. Apply a sealant or Polish to protect the stone and improve its longevity. | Sq ft | 420 | 462 | 75 | 34650
10 | All BOH & FOH area cleaning with wall tiles area acid wash as per instruction and satisfaction of Engineer incharge. | Nos | 1 | 1 | 5000 | 5000
11 | Removing of Existing Wooden Flooring and carting away debris from site at required location as instructed by Engineer incharge. | Sq ft | 1076.4 | 1140 | 21 | 23940
12 | Demolition of Existing wall tiles and carting away debris material from site to required location all as per satisfaction and instruction of Engineer incharge. | Sq ft | 200 | 148 | 35 | 5180
13 | Providing and laying Venyl Flooring similar to existing flooring and fixing on existing tiles of approved make and shade all as per detail design or as pn instruction and satisfaction of Engineer incharge. | Sq ft | 1076.4 | 1114 | 150 | 167100
14 | Flooring - Supply and installation of FL01 - 1200mm x 150mm Wooden Plank flooring laid in Pattern including all necessary consumables in accordance with the drawings and specifications. | Sq ft | 1076.4 | 1042 | 250 | 260500
15 | Cleaning of Existing wall surface and prepare for Painting work, supply and application of Three coats of acrylic emulsion paint, Complete as per manufacturer's specifications. | Sq ft | 4900 | 4874.5 | 40 | 194980
16 | Providing and fixing fire rated 12mm Ply on existing walls and finish with approved finish laminate as per satisfaction and instruction of Engineer incharge. | Sq ft | 200 | 128 | 450 | 57600
17 | Providing and laying Water Based PU work on existing brick tiles and sleeper wood area. | Sq ft | 3500 | 3432 | 25 | 85800
18 | Supply and fixing SS Guard Railing work in bar counter area | R ft | 100 | 91 | 1200 | 109200
19 | Cleaning/ Rust removing of existing MS railing and Painting with Oil paint of approved make and shade (Asian paint of equivalent) on all specified surfaces as per design or as all per satisfaction of Engineer incharge. | Nos | 2 | 2 | 5000 | 10000
20 | Proving and applying duct paint on existing ducts of approved shade, complete as per instruction received from Engineer incharge. | Sq ft | 420 | 490 | 40 | 19600
Total without taxes | [5 empty] | 1181710

## MB
Measurement sheet for for Civil & Interior of Irish House project.
Sr. No | Description | Unit | Qty | Length | Breadth | Total
1 | Providing and applying wood Polish of approved shade on existing heigh table, complete as per instruction received from Engineer incharge. | Nos | 2 |  |  | 2
2 | Repairing of existing door frame: Providing and applying of wood polish over Door frame of approved shade and as per instruction of Engineer incharge. | Nos | 6 |  |  | 6
3 | Providing and applying Painting on existing Main signage (The Irish House) of approved make and shade, as per provided details and as per instruction of Engineer incharge. | Nos | 2 |  |  | 2
4 | Demolition of Existing wall tiles and removing of debris to required location, all as per instruction and satisfaction of Engineer incharge
| Kitchen wall tiles | ft | 32 | 2 | 2 | 128
[5 empty] | Total | 128
5 | Demolition of Existing 2x2 metal grid ceiling and removing of debris to required location, all as per instruction and satisfaction of Engineer incharge
| Kitchen Ceiling | ft | 1 | 34 | 12 | 408
[5 empty] | Total | 408
6 | Removing/Breaking of Existing wall tiles and fixing of 2x2 wall tiles as per existing matching tiles with debris' cleaning from site to required location.
| Kitchen wall tiles | ft | 37 | 2 | 2 | 148
[5 empty] | Total | 148
7 | Supply and installation of 2 x 2 metal grid ceiling as per approved design or as per instruction of Engineer incharge.
| Kitchen Ceiling | ft | 1 | 34 | 12.5 | 425
[5 empty] | Total | 425
8 | Repairing work- Demolition of existing Kota stone flooring and Supply and installation of kota stone flooring for required area with debris shifting to required location all as per intruction of Engineer incharge/ Site inchrage.
| Kitchen flooring | ft | 11 | 2 | 2 | 44
[5 empty] | Total | 44
9 | Polish the Kota Stone tiles using a buffing machine or Poilishig pads to enhance their natural shine and Kota Stone design. Apply a sealant or Polish to protect the stone and improve its longevity.
| Kitchen flooring | ft | 1 | 33 | 14 | 462
[5 empty] | Total | 462
10 | All BOH & FOH area cleaning with wall tiles area acid wash as per instruction and satisfaction of Engineer incharge. | Nos | 1 |  |  | 1
11 | Removing of Existing Wooden Flooring and carting away debris from site at required location as instructed by Engineer incharge.
| Flooring | ft | 1 | 45 | 16 | 720
| Flooring | ft | 1 | 15 | 8 | 120
| Ply partition | ft | 1 | 30 | 10 | 300
[5 empty] | Total | 1140
12 | Demolition of Existing wall tiles and carting away debris material from site to required location all as per satisfaction and instruction of Engineer incharge.
| Kitchen wall tiles | ft | 37 | 2 | 2 | 148
[5 empty] | Total | 148
13 | Providing and laying Venyl Flooring similar to existing flooring and fixing on existing tiles of approved make and shade all as per detail design or as pn instruction and satisfaction of Engineer incharge.
| Vinyl flooring | ft | 1 | 37 | 18 | 666
|  | ft | 1 | 14 | 8 | 112
|  | ft | 1 | 12 | 28 | 336
[5 empty] | Total | 1114
14 | Flooring - Supply and installation of FL01 - 1200mm x 150mm Wooden Plank flooring laid in Pattern including all necessary consumables in accordance with the drawings and specifications.
| Flooring | ft | 1 | 52 | 16 | 832
| Flooring | ft | 1 | 15 | 10 | 150
| Flooring | ft | 1 | 10 | 6 | 60
[5 empty] | Total | 1042
15 | Cleaning of Existing wall surface and prepare for Painting work, supply and application of Three coats of acrylic emulsion paint, Complete as per manufacturer's specifications.
| Painting | ft | 1 | 60 | 19 | 1140
|  | ft | 1 | 52 | 25 | 1300
|  | ft | 1 | 27 | 15 | 405
|  | ft | 1 | 15 | 10 | 150
|  | ft | 1 | 32 | 11 | 352
|  | ft | 1 | 17 | 58 | 986
|  | ft | 1 | 9.5 | 57 | 541.5
[5 empty] | Total | 4874.5
16 | Providing and fixing fire rated 12mm Ply on existing walls and finish with approved finish laminate as per satisfaction and instruction of Engineer incharge.
| Kitchen ceiling | ft | 1 | 8 | 4 | 32
| Signage | ft | 1 | 8 | 12 | 96
[5 empty] | Total | 128
17 | Providing and laying Water Based PU work on existing brick tiles and sleeper wood area.
| Counter | ft | 4 | 14.5 | 4 | 232
| Counter | ft | 4 | 18 | 4 | 288
| Pirrer | ft | 10 | 4 | 10 | 400
| beam | ft | 8 | 59 | 3.5 | 1652
| beam | ft | 7 | 4 | 8 | 224
| beam | ft | 1 | 4 | 22 | 88
| Red brick | ft | 1 | 4 | 22 | 88
| Red brick | ft | 1 | 10 | 46 | 460
[5 empty] | Total | 3432
18 | Supply and fixing SS Guard Railing work in bar counter area | R ft | 51 |  |  | 91
19 | Cleaning/ Rust removing of existing MS railing and Painting with Oil paint of approved make and shade (Asian paint of equivalent) on all specified surfaces as per design or as all per satisfaction of Engineer incharge. | Nos | 2 |  |  | 2
20 | Proving and applying duct paint on existing ducts of approved shade, complete as per instruction received from Engineer incharge.
| Ducting | ft | 1 | 7 | 70 | 490
[5 empty] | Total | 490