## Summery
AJ KITCHEN - Bill Summary
S.N | Item | PO Value | RA-01 Value | RA-02 Value | Cumulative | Varition ( In Amt ) | % Billing | Po No.
1 | Gas | 63746 | 34217.56 | 11118.2 | 45335.76 | 18410.24 | 17.4414 | Semolina/PO/23-24/000716
| SUB TOTAL | 63746 | 34217.56 | 11118.2 | 45335.76 | 18410.24
| GST -18% | 11474.28 | 6159.1608 | 2001.276 | 8160.4368 | 3313.8432
| TOTAL | 75220.28 | 40376.7208 | 13119.476 | 53496.1968 | 21724.0832

## Gas BOQ
| AJ KITCHEN -AHMEDABAD AIRPORT | PO Qty |  |  |  | RA-01 | RA-02 | Cumm | RA-01 | RA-02 | Cumm
BOQ FOR GAS PIPING SYSTEM- FDT |  |  |  | Rate | Amount | Qty | Qty | Qty | Amount | Amount | Amount
[5 empty] | 63424.8 |  |  |  | 34217.56 | 11118.2 | 45335.76
S/NO | DESCRIPTION | QUANTITY | UNIT
1 | Supply , instllation ,testing and commissioning of 32 NB CS seamless Sch. 40 pipe and fittings. Pipe conforming to ASTM A 106 Gr. B including required pipe supports | 12 | RMT | 1150 | 13800 | 4.3 |  | 4.3 | 4945 | 0 | 4945
2 | Supply , instllation ,testing and commissioning of 25 NB CS seamless Sch. 40 pipe and fittings. Pipe conforming to ASTM A 106 Gr. B including required pipe supports | 12 | RMT | 1058 | 12696 |  | 4.3 | 4.3 | 0 | 4549.4 | 4549.4
3 | Supply of 32 NB L&T ball valve. Flanged end 150 # single pc design Fire Safe | 2 | No. | 4498.8 | 8997.6 | 1 | 1 | 2 | 4498.8 | 4498.8 | 8997.6
4 | Supply of 25 NB L&T ball valve. Screwed end, 3 pcs design | 2 | Nos. | 3376.4 | 6752.8 | 2 |  | 2 | 6752.8 | 0 | 6752.8
5 | Painting of pipes. 2 coats of red oxide and 2 coats of Golden Yellow final paint. Total 120 microns thickness | 24 | RMT | 55.2 | 1324.8 | 4.3 |  | 4.3 | 237.36 | 0 | 237.36
6 | 2 mtrs long flexible Suraksha rubber hose for equipment connections | 2 | Nos. | 496.8 | 993.6 | 2 |  | 2 | 993.6 | 0 | 993.6
7 | 2nd Stage low pressure regulator for equipment connection. United works make | 2 | Nos. | 3220 | 6440 | 2 |  | 2 | 6440 | 0 | 6440
8 | Pressure testing as per MGL requirement. Drawing for MGL and CFO submissions | 1 | JOB | 8280 | 8280 | 1 |  | 1 | 8280 | 0 | 8280
9 | Installation, commissioning charges for all above including tranportation | 1 | JOB | 4140 | 4140 | 0.5 | 0.5 | 1 | 2070 | 2070 | 4140
| Sub - TOTAL |  |  |  | 63424.8 |  |  |  | 34217.56 | 11118.2 | 45335.76

## GAS JMR
AJ KITCHEN -AHMEDABAD AIRPORT
BOQ FOR GAS PIPING SYSTEM- FDT |  | PO Qty |  | RA-01 | JMR |  |  | Total Approved Qty | RA-02
S/NO | DESCRIPTION | QUANTITY | UNIT | Qty | Qty |  |  | Qty | Qty
[5 empty] | Length | Nos | Qty
1 | Supply , instllation ,testing and commissioning of 32 NB CS seamless Sch. 40 pipe and fittings. Pipe conforming to ASTM A 106 Gr. B including required pipe supports | 12 | RMT | 4.3 |  |  |  | 4.3 | 0
2 | Supply , instllation ,testing and commissioning of 25 NB CS seamless Sch. 40 pipe and fittings. Pipe conforming to ASTM A 106 Gr. B including required pipe supports | 12 | RMT |  | 4.3 | 1 | 4.3 | 4.3 | 4.3
3 | Supply of 32 NB L&T ball valve. Flanged end 150 # single pc design Fire Safe | 2 | No. | 1 |  |  | 1 | 2 | 1
4 | Supply of 25 NB L&T ball valve. Screwed end, 3 pcs design | 2 | Nos. | 2 |  |  |  | 2 | 0
5 | Painting of pipes. 2 coats of red oxide and 2 coats of Golden Yellow final paint. Total 120 microns thickness | 24 | RMT | 4.3 |  |  |  | 4.3 | 0
6 | 2 mtrs long flexible Suraksha rubber hose for equipment connections | 2 | Nos. | 2 |  |  |  | 2 | 0
7 | 2nd Stage low pressure regulator for equipment connection. United works make | 2 | Nos. | 2 |  |  |  | 2 | 0
8 | Pressure testing as per MGL requirement. Drawing for MGL and CFO submissions | 1 | JOB | 1 |  |  |  | 1 | 0
9 | Installation, commissioning charges for all above including tranportation | 1 | JOB | 0.5 |  |  | 0.5 | 1 | 0.5