## Summary
Summary For Additional Work TFS-Chennai
Sr. No | Description | Amount | G&B-R1 amount 8 th Dec 23 | TFS Agreed Amount 8 th Dec 23 | TFS Need to reconsider Amount 8 th Dec 2023 | Remark
A | Total Amount- Plumbing | 499010 | 452217 | 452217 | 0
B | Total Amount- Civil NT | 407888.3 | 397630.27 | 397630.27 | 0
C | Total Amount- Interior | 4208909.9331 | 3107513 | 1205977 | 1901536
D | Total Amount- HVAC | 494498 | 390626 | 180626 | 210000.5872
E | Total Amount- Electrical | 784712 | 644762 | 334682 | 426250
| Total Amendment PO Required | 6395018.2331 | 4992748.27 | 2571132.27 | 2537786.5872
| Electrical Pacakge -Quantity variation, total amount within total PO amount |  | 6438466

## G&B Acceptable rates
Civil items, Wooden doors, Sanitary fixtures, Fire sprinkler works, Exhaust Hood
Hill Assessment
S.No. | Description of Works | Unit | Quantity | Rate (in Rs.) | Amount (in Rs.) | Agreed Amount | Disagreed Amount /Need to be reworkout | Remark | Remark | Quantity | Rate (in Rs.) | Amount (in Rs.) | Remarks
A | Plumbing NT Items
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given.
1 | Pot wash area | Nos | 1 | 27986 | 27986 | 27986 |  | Missing in MEP BOQ | Installation costing is very high from Godrej end, Binu to discuss and close, 1.43 Lacs approval already given for the supply of sanitory fixture & fitting items.
2 | Kitchen Sink 1 | Nos | 1 | 23084 | 23084 | 23084
3 | Kitchen Sink 2 | Nos | 1 | 19938 | 19938 | 19938
4 | Dishwasher Area | Nos | 1 | 21180 | 21180 | 21180
5 | Pedal operated sink for hand wash(Kitchen,Pantry,CHL live Kitchen,BCL Live Kitchen) | Nos | 1 | 50825 | 50825 | 50825
6 | Pantry | Nos | 1 | 12866 | 12866 | 12866
7 | BCL Bar Counter | Nos | 1 | 54468 | 54468 | 54468
8 | CHL Bar Counter | Nos | 1 | 50856 | 50856 | 50856
9 | BCL Live Kitchen/CHL Live Kitchen | Nos | 1 | 30596 | 30596 | 30596
10 | CHL Buffet area | Nos | 1 | 3849 | 3849 | 3849
11 | Common Materials | Nos | 1 | 16099 | 16099 | 16099
12 | Providing , fixing and commissioning of Geyser (Type- Electric , Make - Havells) |  |  |  |  | 0
a | 3L | Nos | 2 | 9165 | 18330 | 18330
b | 10L | Nos | 3 | 12982 | 38946 | 38946
c | 15L | Nos | 3 | 15790 | 47370 | 47370
d | 25L | Nos | 2 | 17912 | 35824 | 35824
| Total Amount- Plumbing |  |  |  | 452217 | 452217 | 0
B | Civil NT Items
1 | Finsihing of jambs in door/lintel openings, walls at mullion/MS support provision on the existing authority walls after demolishion, rate including materials, manual shifting from yard, labours, scaffolding etc.,-Approx 50mm plaster done | Rft | 231.03 | 209 | 48285.27 | 48285.27 |  | What is the location ??? All additional works for entrance wall was a later part of the scope and got added due to planning changes made by the airport. | Godrej to revert/confirm
2 | AC Duckt big Wall breakking work& All Packing Material Shifting Using Stair case, Block Cutting & Fixing work & Finishing work -1600mm x 900mm | Nos | 3 | 12128 | 36384 | 36384 |  | This was a part of demolition - the approved cost of for demolition is 84Rs / sqft - additional cost of plastering and finishing is already being charged in respective items | Godrej to revert/confirm
3 | AC Duckt Small Wall baraking work& All Packing Material Shifting Using Stair case, Block Cutting & Fixing work & Finishing work
a | 600mmx600mm | Nos | 1 | 3032 | 3032 | 3032 |  | This was a part of demolition - the approved cost of for demolition is 84Rs / sqft - additional cost of plastering and finishing is already being charged in respective items | Godrej to revert/confirm
b | 1000mmx900mm | Nos | 3 | 7580 | 22740 | 22740 |  | This was a part of demolition - the approved cost of for demolition is 84Rs / sqft - additional cost of plastering and finishing is already being charged in respective items | Godrej to revert/confirm
4 | AC Duckt Medium Wall baraking work& All Packing Material Shifting Using Stair case, Block Cutting & Fixing work & Finishing work | [6 empty] | This was a part of demolition - the approved cost of for demolition is 84Rs / sqft - additional cost of plastering and finishing is already being charged in respective items | Godrej to revert/confirm
a | 1900mmx600mm | Nos | 6 | 9601 | 57606 | 57606 |  | This was a part of demolition - the approved cost of for demolition is 84Rs / sqft - additional cost of plastering and finishing is already being charged in respective items | Godrej to revert/confirm
b | 800mmx800mm-Dia | Nos | 3 | 5390 | 16170 | 16170 |  | This was a part of demolition - the approved cost of for demolition is 84Rs / sqft - additional cost of plastering and finishing is already being charged in respective items | Godrej to revert/confirm
5 | CH Bar counter Top Concrete 100mm Braking work & Cement morter material Shifting ,andFinishing work- Including curve area length is around 26'-3" | Nos | 2 | 14018 | 28036 | 28036 |  | Site team to confirm - as these were on site decisions | Wrongly done from Godrej end. Not to be included.
6 | BL Bar counter Top Concrete 100mm Braking work & Cement morter material Shifting and Finishing work | Nos | 2 | 14018 | 28036 | 28036 |  | Site team to confirm - as these were on site decisions | Wrongly done from Godrej end. Not to be included.
7 | BL Live kitchen Top 100mm Braking & Cement morter material Shifting and Finishing work | Nos | 2 | 7009 | 14018 | 14018 |  | Site team to confirm - as these were on site decisions | Wrongly done from Godrej end. Not to be included.
8 | CH Live kitchen Top 50mm Braking work, Cement morter material Shifting & Finishing work | Nos | 3 | 4731 | 14193 | 14193 |  | Site team to confirm - as these were on site decisions | Wrongly done from Godrej end. Not to be included.
9 | Live Kitchen Door Exten work ( AS Per Drwg 0.75 mtrs But Now Change 0.9mtrs ( Wall Cutting & Braking & Cement morter material Shifting and Finishing work ) | Nos | 2 | 5435 | 10870 | 10870 |  | Rate too high only for wall breaking. The drawings were provided by Kicthen consultant - this was noticed on site by our team when the door looked too small and that the kitchen equipments wouldn’t pass through the same so the change was madee. | Binu to check on costing part
10 | DRY Store room Door Exten work ( Wall Cutting & Braking & Cement morter material Shifting and Finishing work ) | Nos | 2 | 5435 | 10870 | 10870 |  | Site team to confirm - as these were on site decisions | OK.
11 | Pantry area Drian pipe Laying work( Floor chiping & Pipe laying & Modiform filling & Cement morter material Shifting Concrete filling & Finishing work | Nos | 1 | 8058 | 8058 | 8058 |  | Missed in MEP-Plumbing | Ok, costing needs to check
12 | BL Live kitchen Inlet pipe alteration work | Nos | 2 | 684 | 1368 | 1368 |  | Site team to confirm - as these were on site decisions | ok
12A | DB Box Tiles Cutting work & chiping work (SFT) | Sft | 124 | 107 | 13268 | 13268 |  | This is due to DB's wrongly fixed by Godrej without consulting TFS site team. | Godrej to revert/confirm
14 | CH Bar counter Door elbow fixing ( Cocrete & Block work braking & Pipe cutting & Door elbow fixing Using Coupling & Material Shifting ,Block work & Concrete Filling & Plastering work | Job | 1 | 4347 | 4347 | 4347 |  | Pls do not approve | Godrej to revert/confirm
15 | Bund Wall work( Marble Cutting & Removing , Material Shifting Using Stair case ,Block work laying , concret filling & Plastering work ( QTY-Rft) | Rft | 75 | 729 | 54675 | 54675 |  | Site team to confirm - as these were on site decisions | Godrej to confirm area?
16 | MS Collumn4.2 mtrs Concrete Filling work (Shatering work & Material Shifting Using Stair Case , Cocrete filling work , De Shatering Work | Rft | 12.6 | 450 | 5670 | 5670 |  | Already Approved in NT-01 | NA
17 | Lounge area MS Angle Marbel Floor Cutting & Concrete Filling & Marbel Re laying | Nos | 12 | 1553 | 18636 | 18636 |  | Site team to confirm - as these were on site decisions | Godrej to discuss and confirm on which area this work is done.
18 | CH & BL Bar counter Geyser Inlet & Out Let Supply Changing Work | Nos | 2 | 684 | 1368 | 1368 |  | Wrongly mentioned in MEP detailing. | ok
| Total Amount- Civil NT |  |  |  | 397630.27 | 397630.27 | 0
C | Interior Work
1 | Providing & Fixing aluminium framing with Ply with all including at Main Corridor Entry Archi-tray | Rft | 44 | 1642 | 72248 | 72248 |  | additional area given by AI team (main corridor area). This is not part of work order. this is only plyboxing with aluminium framework. | Why these costing are not included during NT1 discussion, its missed from Godrej end. Binu to check on costing part. | 35.26 | #REF! | #REF! | Measurement Verified at site. Signed JMR available. Measurement corrected as per actual.
2 | Labour charges for Marble cladding in main corridor entry arch- tray including consumables | Rft | 44 | 1630 | 71720 | 71720 |  | additional area given by AI team (main corridor area). This is not part of work order. |  | 35.26 | #REF! | #REF! | Measurement Verified at site. Signed JMR available. Measurement corrected as per actual.
3 | Main Corridor Entry fabric cladding with fabric and foam strich as per the instruction of architect | Sft | 35 | 1996 | 69860 | 69860 |  | additional area given by AI team (main corridor area). This is not part of work order. |  | 32.28 | #REF! | #REF! | Measurement Verified at site. Signed JMR available. Measurement corrected as per actual.
4 | Providing & Fixing DB niche Door as per drawing inside laminate & outer venner | Sft | 84 | 1566 | 131544 | 131544 |  | additional area given by AI team (main corridor area). This is not part of work order. |  | 87.156 | #REF! | #REF! | Measurement Verified at site. Signed JMR available. Measurement corrected as per actual.
5 | CHL SPA Arch wall-Ply Boxing using 19mm thick ply with 12mm thk ply with flexi ply with MDF for final finish with all necessary hardware & Fitting on wall & Ceiling arch type As per details & Drawing – 4.480 x 2.55 – Measured all wall area – | Sft | 125 | 1593 | 199125 | 199125 |  | Part of the new spa design. The has design changed by TFS team. NT item. | Binu to check on costing part | 122.9222 | #REF! | #REF! | Measurement Verified at site. Signed JMR available. Measurement corrected as per actual.
6 | CHL SPA Full height Storage-Providing & fixing Full height storage in spa with Ply & Laminate - 900 x 2400 x 600 | Sft | 25 | 1989 | 49725 | 49725 |  | Part of the new spa design. The has design changed by TFS team. NT item. |  | 14.2032 | #REF! | #REF! | Measurement Verified at site. Signed JMR available. Measurement corrected as per actual.
7 | CHL Massage room Vanity Counter as per details drawing with veneer shutter – 900 x 600 (Deep) x 400 (height) | Nos | 1 | 18077 | 18077 | 18077 |  | Design was not finalise at the time of tendering. NT item. | Binu to check on costing part | 1 | #REF! | #REF! | Measurement Verified at site. Signed JMR not available
8 | CHL Shower Room Vanity Counter as per details drawing with veneer shutter – 900 x 600 (Deep) x 400 (height) | Nos | 1 | 18077 | 18077 | 18077 |  | Design was not finalise at the time of tendering. NT item. | Binu to check on costing part | 1 | #REF! | #REF! | Measurement Verified at site. Signed JMR not available
9 | Supply and Installation of saint gobain shower cubicles with 8 mm tempered clear glass asper detail given. | Nos | 3 | 31659 | 94977 | 94977 |  | Design was not finalise at the time of tendering. NT item. | Binu to check on costing part | 3 | #REF! | #REF! | Measurement Verified at site. Signed JMR available.
10 | CHL live kitchen front counter for equipments -Providing & fixing wooden counter with 19mm Ply with laminate - Deep up to 550 , with marble counter top | Nos | 1 | 63525 | 63525 | 63525 |  | NT item. Missed from our side. | Binu to check on costing part | 1 | #REF! | #REF! | Measurement Verified at site. Signed JMR not available
11 | CHL Bar Counter Storage Rectification as per change in equipment layout | Job | 1 | 25000 | 25000 | 25000 |  | Site team to confirm - as these were on site decisions | This is due to drawings issues, Binu to check on costing part. | 1 | 25000 | 25000 | Measurement not verified at site. Retained Contractor Claimed Quantity as backup is not available
12 | BCL Bar Counter Storage Rectification as per change in equipment layout | Job | 1 | 30400 | 30400 | 30400 |  | Site team to confirm - as these were on site decisions | This is due to drawings issues, Binu to check on costing part. | 1 | 30400 | 30400
12A | BCL live kitchen front counter for equipments -Providing & fixing wooden counter with 19mm Ply with laminate - Deep up to 550 , with marble counter top | Nos | 1 | 63525 | 63525 | 63525 |  | NT item. Missed from our side. | Binu to check on costing part | 1 | #REF! | #REF! | Measurement Verified at site. Signed JMR not available
14 | BCL Massage room Vanity Counter as per details drawing with veneer shutter – 900 x 600 (Deep) x 400 (height) | Nos | 2 | 18077 | 36154 | 36154 |  | Design was not finalise at the time of tendering. NT item. | Binu to check on costing part | 2 | #REF! | #REF! | Measurement Verified at site. Signed JMR not available
15 | BCL Shower Room Vanity Counter as per details drawing with veneer shutter – 900 x 600 (Deep) x 400 (height) | Nos | 2 | 18077 | 36154 | 36154 |  | Design was not finalise at the time of tendering. NT item. | Binu to check on costing part | 2 | #REF! | #REF! | Measurement Verified at site. Signed JMR not available
16 | Providing and fixing Fluted glass partition on wall with Powder coated aluminium frame as per the instruction of architect | Sft | 80 | 2990 | 239200 |  | 239200 | Part of the new spa design. The has design changed by TFS team. NT item. | Binu to check on costing part | 79.0214 | #REF! | #REF! | Measurement Verified at site. Signed JMR available. Measurement corrected as per actual.
17 | Providing and Applying texture paint on designer ceiling as per detail given. | Sft | 7000 | 126 | 882000 |  | 882000 | Pls do not approve. | NA | 7000 | #REF! | #REF! | Measurement not verified at site. Retained Contractor Claimed Quantity as backup is not available
18 | Supply & Installation of Fire Door External trim with cylindrical lock as per detail given. | Nos | 5 | 8807 | 44035 | 44035 |  | due to time constraint item removed. | NA | 5 | #REF! | #REF!
19 | Providing and fixing Cherry Blossom planter over BCL bar counter as per detail given. | Nos | 350 | 249 | 87150 | 87150 |  | due to time constraint item removed. | NA | 350 | 249 | 87150
20 | Providing and fixing SS plate for Raceway Junction Box at floor as per detail given. | KG | 83 | 617 | 51211 | 51211 |  |  |  | 83 | #REF! | #REF!
21 | Providing & fixing Fire Hydrant Door with glass as per detail given. | Nos | 1 | 43470 | 43470 | 43470 |  |  |  | 1 | #REF! | #REF!
22 | Providing In fixing 20 mm x 20 mm square tube frame work and approval RAL power coating , 20 mm Thk MDF Shelf both side Finished in Black DUCO Paint , 6mm ply with Back side Panel in 1.5 mm Thk Steel Plate with Brass pvd coating with Necessary adhesive Hardware etc as per detail given. | Sft | 135.734 | 4809 |  |  |  |  | Item Descoped | 135.734 | #REF! | #REF!
23 | Prvoiding & fixing MS Planter railing Height 2.4 m as per drawing as per detail given. | Sft | 84 | 6379 | 535836 |  | 535836 |  |  | 90.3302 | #REF! | #REF! | Measurement Verified at site. Signed JMR available. Measurement corrected as per actual.
24 | Prvoiding & fixing SS corner guard as per specification normal corner guard as per detail given.(50mm x 50mm) | Rft | 500 | 489 | 244500 |  | 244500 |  |  | 398.52 | #REF! | #REF! | Measurement Verified at site. Signed JMR available. Measurement corrected as per actual.
| Total Amount- Interior |  |  |  | 3107513 | 1205977 | 1901536 |  |  |  |  | #REF!
D | HVAV NT Items
1 | Supply, Installation, testing & commissioning of Butterfly damper as per detail given. | Nos | 4 | 1331 | 5324 | 5324 |  | Major missed in MEP - Plumbing BOQ | Binu to check on costing part
2 | Supply, Installation, testing & commissioning Flexible duct as per detail given. |  |  |  | 0 | 0
a | 200mm Dia | Rmt | 12 | 1331 | 15972 | 15972
b | 400mm Dia | Rmt | 40 | 3076 | 123040 | 123040 | 0.5872
3 | Supply, Installation, testing & commissioning Mixing box as per detail given. |  |  |  | 0 | 0
a | 450x150x250mm | Nos | 2 | 2747 | 5494 | 5494
b | 300x150x250mm | Nos | 2 | 2514 | 5028 | 5028
c | 600x100x250mm | Nos | 2 | 3181 | 6362 | 6362
d | 375x375x250mm | Nos | 2 | 3445 | 6890 | 6890
4 | Supply, Installation, testing & commissioning Diffusers-595x595, 375x375mm as per detail given. | Nos | 4 | 3129 | 12516 | 12516
5 | Supply & Hand fabrication at site, installation opf 24 Guage Fabrication Sheet as per detail given. | Smt | 120 | 1750 | 210000 |  | 210000
| Total Amount- HVAC |  |  |  | 390626 | 180626 | 210000.5872
E | Electrical NT Items
A | LT CABLE | [6 empty] | Missing in MEP BOQ | Binu to check on costing part
1 | Supply and laying, effecting proper connections, testing & commissioning of the following sizes of 1.1 KV XLPE FRLS armoured/ unarmoured PVC insulated PVC sheathed aluminium /copper conductor cables conforming to IS : 1554 and IS 694 for Flexible copper cable Part I - 1976 with latest amendments laid over MS supports in existing RCC ducts/ laid in ground /laid on Cable Trays including clamping the cables to supports in an approved manner as required complete with all accessories.All cables shall have thermo setting insulation XLPE and low emission of smoke and corrosive gas when affected by fire. Necessary Markers shall be provided at the intervals as per the specifications.
A | Aluminium cables
1 | 3.5C x 120 Sq.mm. | Mtr. | 150 | 1650 | 247500 |  | 247500
2 | 3.5C x 25 Sq.mm. | Mtr. | 110 | 925 | 101750 | 101750 | 101750
3 | 4C x 16 Sq.mm. | Mtr. | 110 | 700 | 77000 | 77000 | 77000
B | CABLE TERMINATION
Making cable and terminations including brass single compression glands and crimping type copper lugs for cable sizes mentioned below for aluminium or copper.
1 | 3.5C x 120 Sq.mm. | Nos. | 2 | 1941 | 3882 | 3882
2 | 3.5C x 25 Sq.mm. | Nos. | 2 | 621 | 1242 | 1242
3 | 4C x 16 Sq.mm. | Nos. | 4 | 472 | 1888 | 1888
C | Providing and fixing in position the following GI RIGID conduits including all accessories concealed in F. ceiling/wall/floor as required including pull boxes with 3mm thick perspex sheet cover plate complete with 1.6 mm dia. G.I. pull wires in the length of conduit. -32 mm dia GI Conduit | Rmt | 30 | 540 | 16200 | 16200
D | DB Enclosure & Dimmer Controller
1 | Supply & installation of Metal Enclosure box with wire connector for modification of existing DB as per detail given. | Nos. | 2 | 2240 | 4480 | 4480
2 | Supply & installation of Enclosure box for light dimmer controller as per detail given. | Nos. | 20 | 3129 | 62580
3 | Supply & Installation of Light Dimmer Controller with Enclosuer box as per detail given. | Nos. | 40 | 3206 | 128240 | 128240
| Total Amount- Electrical |  |  |  | 644762 | 334682 | 426250

## NT2-Meas
NT2 Measurement sheet |  |  | Measurement Correction
Sl.No | Description | Unit | No | Length | Breadth | Depth | Qty MKS | Cer Qty FPS | Remarks
1 | Providing & Fixing aluminium framing with Ply with all including at Main Corridor Entry Archi-tray
| Corridor Entry | Rft | 1 | 10.75 |  |  | 10.75 | 35.26
|  | Rft | 1 | 1.82 |  |  |  | 0 | Qty duplicated
|  | Rft | 1 | 0.25 |  |  |  | 0 | Qty duplicated
| Total | [5 empty] | 10.75 | 35.26
3 | Main Corridor Entry fabric cladding with fabric and foam strich as per the instruction of architect
| Corridor Entry | Sft | 1 | 2.4 | 1.25 |  | 3 | 32.28
| Total | [5 empty] | 3 | 32.28
4 | Providing & Fixing DB niche Door as per drawing inside laminate & outer venner
| Corridor Entry left | Sft | 1 | 3 | 2.7 |  | 8.1 | 87.156
| Total | [5 empty] | 8.1 | 87.156
5 | CHL SPA Arch wall-Ply Boxing using 19mm thick ply with 12mm thk ply with flexi ply with MDF for final finish with all necessary hardware & Fitting on wall & Ceiling arch type As per details & Drawing – 4.480 x 2.55 – Measured all wall area –
| Card holder SPA room | Sft | 1 | 4.48 |  | 2.55 | 11.424 | 122.9222 | Measured wall area only. Since curved portion cost shall be included in the unit rate.
| Total | [5 empty] | 11.424 | 122.9222
6 | CHL SPA Full height Storage-Providing & fixing Full height storage in spa with Ply & Laminate - 900 x 2400 x 600
| SPA room | Sft | 1 | 0.55 |  | 2.4 | 1.32 | 14.2032
| Total | [5 empty] | 1.32 | 14.2032
9 | Supply and Installation of saint gobain shower cubicles with 8 mm tempered clear glass asper detail given.
| Business lounge - Shower | Nos | 2 |  |  |  | 2
| Card holder lounge - Shower | Nos | 1 |  |  |  | 1
| Total | [5 empty] | 3
16 | Providing and fixing Fluted glass partition on wall with Powder coated aluminium frame as per the instruction of architect
Card holder lounge
| Massage room | Sft | 1 | 3.06 |  | 2.4 | 7.344 | 79.0214
| Total | [5 empty] | 7.344 | 79.0214
23 | Prvoiding & fixing MS Planter railing Height 2.4 m as per drawing as per detail given.
| SPA room entrance | Sft | 1 | 3.65 |  | 2.3 | 8.395 | 90.3302
| Total | [5 empty] | 8.395 | 90.3302
24 | Prvoiding & fixing SS corner guard as per specification normal corner guard as per detail given.
| Preparation room | Rft | 4 | 2.4 |  |  | 9.6 | 31.488
| Pot wash room | Rft | 8 | 2.4 |  |  | 19.2 | 62.976
| Dish wash room | Rft | 3 | 2.4 |  |  | 7.2 | 23.616
| Wash basin side | Rft | 2 | 2.4 |  |  | 4.8 | 15.744
| Dry store room | Rft | 9 | 2.4 |  |  | 21.6 | 70.848
| Garbage room | Rft | 5 | 2.4 |  |  | 12 | 39.36
| Electrical room | Rft | 2 | 2.4 |  |  | 4.8 | 15.744
| Bond room | Rft | 4 | 2.4 |  |  | 9.6 | 31.488
| Bar counter CH | Rft | 2 | 1.2 |  |  | 2.4 | 7.872
| Bar counter BL | Rft | 2 | 1.2 |  |  | 2.4 | 7.872
| CH Live kitchen | Rft | 3 | 2.4 |  |  | 7.2 | 23.616
| BL-Love kitchen | Rft | 3 | 2.4 |  |  | 7.2 | 23.616
| Pantry | Rft | 4 | 2.4 |  |  | 9.6 | 31.488
| CHL-Shower room | Rft | 2 | 1.3 |  |  | 2.6 | 8.528
|  | Rft | 1 | 1 |  |  | 1 | 3.28
|  | Rft | 2 | 0.15 |  |  | 0.3 | 0.984
| Total | [5 empty] | 121.5 | 398.52

## Sheet 1- Rate Analysis
BCL FURNITURES & INTERIOR WORKS
Project :- | TFS
G&B rate submission
Sr. No. | Particulars | Unit | Nos | Dimensions |  |  | Density | Wastage | Qty | Rate | Amount | Remarks
|  |  |  | L | B | D
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 27986
1 | Pot wash area
Consider Size Per Nos
A | Material Consumed
a | Cost of Wall mounted hot & Cold Mixer with Swinging spout-Make Jaquar, Model FUS - 29165 | Nos | 1 |  |  |  |  | 0% | 1 | 4290 | 4290
b | Cost of Angle Cock-Make Jaquar,Model FUS-29053 | Nos | 4 |  |  |  |  | 0% | 4 | 1280.4 | 5121.6
c | Cost of 1.1/2" PVC Union | Nos | 3 |  |  |  |  | 0% | 3 | 260.04 | 780.12
d | Cost of 1.1/2" PVC End Cap | Nos | 1 |  |  |  |  | 0% | 1 | 46.2 | 46.2
e | Cost of 4" PVC End Cap | Nos | 2 |  |  |  |  | 0% | 2 | 72.6 | 145.2
f | Cost of 3" CP Extension Nipple | Nos | 4 |  |  |  |  | 0% | 4 | 217.8 | 871.2
g | Cost of 1.1/2" PVC FTA | Nos | 2 |  |  |  |  | 0% | 2 | 62.04 | 124.08
h | Cost of 3" PVC MTA | Nos | 2 |  |  |  |  | 0% | 2 | 138.6 | 277.2
i | Cost of 3" - 1.1/2" PVC Bush | Nos | 2 |  |  |  |  | 0% | 2 | 44.88 | 89.76
j | Cost of 1.1/2" PVC Elbow | Nos | 4 |  |  |  |  | 0% | 4 | 67.32 | 269.28
k | Cost of 1.1/2" PVC MTA | Nos | 2 |  |  |  |  | 0% | 2 | 73.92 | 147.84
l | Cost of 1.1/2" PVC T | Nos | 2 |  |  |  |  | 0% | 2 | 72.6 | 145.2
| Sub Total -- A | [9 empty] | 12307.68
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 9500 | 9500 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 9500
C | Add for
a | Transportation | [7 empty] | @ | 4% | 492.3072 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 369.2304 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 218.0768
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 1448.75
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 2528.3644
D | Total -- D = A + B + C | [9 empty] | 24336.0444
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 3650.4067
G | Total G = D + E + F per Nos | [9 empty] | 27986.4511
| Rate per Nos (Taxes Extra) | [9 empty] | 27986
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 23084
2 | Kitchen Sink 1
Consider Size Per Nos
A | Material Consumed
a | cost of 1.1/2" PVC Unions | Nos | 2 |  |  |  |  | 0% | 2 | 260.04 | 520.08
b | cost of 1.1/2" PVC Elbow | Nos | 5 |  |  |  |  | 0% | 5 | 67.32 | 336.6
c | cost of 1.1/2" PVC FTA | Nos | 1 |  |  |  |  | 0% | 1 | 62.04 | 62.04
d | cost of Angle Cock | Nos | 3 |  |  |  |  | 0% | 3 | 1280.4 | 3841.2
e | cost of Single side lever sink mixer with swinging spout | Nos | 1 |  |  |  |  | 0% | 1 | 4250.4 | 4250.4
f | cost of 4" PVC End Cap | Nos | 1 |  |  |  |  | 0% | 1 | 72.6 | 72.6
g | cost of 1.1/2" PVC End Cap | Nos | 1 |  |  |  |  | 0% | 1 | 46.2 | 46.2
h | cost of 1.1/2" PVC MTA | Nos | 2 |  |  |  |  | 0% | 2 | 73.92 | 147.84
i | cost of 15mm CP Braided hose 1meter length | Nos | 1 |  |  |  |  | 0% | 1 | 483.12 | 483.12
| Sub Total -- A | [9 empty] | 9760.08
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 8200 | 8200 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 8200
C | Add for
a | Transportation | [7 empty] | @ | 4% | 390.4032 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 292.8024 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 179.6008
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 1250.5
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 2113.3064
D | Total -- D = A + B + C | [9 empty] | 20073.3864
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 3011.008
G | Total G = D + E + F per Nos | [9 empty] | 23084.3944
| Rate per Nos (Taxes Extra) | [9 empty] | 23084
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 19938
3 | Kitchen Sink 2
Consider Size Per Nos
A | Material Consumed
a | cost of 1.1/2" PVC Unions | Nos | 2 |  |  |  |  | 0% | 2 | 260.04 | 520.08
b | cost of 1.1/2" PVC Elbow | Nos | 4 |  |  |  |  | 0% | 4 | 67.32 | 269.28
c | cost of Single side lever sink mixer with swinging spout-Make Jaquar, Model FLR-5179B | Nos | 1 |  |  |  |  | 0% | 1 | 4250.4 | 4250.4
d | cost of Angle Cock-Make Jaquar,Model FUS-29053 | Nos | 1 |  |  |  |  | 0% | 1 | 1280.4 | 1280.4
e | cost of 1.1/2" PVC FTA | Nos | 1 |  |  |  |  | 0% | 1 | 62.04 | 62.04
f | cost of 2" PVC MTA | Nos | 2 |  |  |  |  | 0% | 2 | 138.6 | 277.2
g | cost of 2" x 1.1/2" PVC Bush | Nos | 2 |  |  |  |  | 0% | 2 | 42.24 | 84.48
h | cost of 15mm CP Braided hose 1meter length | Nos | 1 |  |  |  |  | 0% | 1 | 483.12 | 483.12
| Sub Total -- A | [9 empty] | 7227
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 8200 | 8200 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 8200
C | Add for
a | Transportation | [7 empty] | @ | 4% | 289.08 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 216.81 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 154.27
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 1250.5
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 1910.66
D | Total -- D = A + B + C | [9 empty] | 17337.66
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 2600.649
G | Total G = D + E + F per Nos | [9 empty] | 19938.309
| Rate per Nos (Taxes Extra) | [9 empty] | 19938
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 21180
4 | Dishwasher Area
Consider Size Per Nos
A | Material Consumed
a | Cost of Angle Cock-Make Jaquar,Model FUS-29053 | Nos | 4 |  |  |  |  | 0% | 4 | 1280.4 | 5121.6
b | Cost of 1.1/2" PVC Unions | Nos | 3 |  |  |  |  | 0% | 3 | 260.04 | 780.12
c | Cost of 3" PVC MTA | Nos | 2 |  |  |  |  | 0% | 2 | 138.6 | 277.2
d | Cost of 3" x 1.1/2" PVC Bush | Nos | 2 |  |  |  |  | 0% | 2 | 47.52 | 95.04
e | Cost of 4" PVC End Cap | Nos | 2 |  |  |  |  | 0% | 2 | 72.6 | 145.2
f | Cost of 1.1/2" PVC End Cap | Nos | 1 |  |  |  |  | 0% | 1 | 46.2 | 46.2
g | Cost of 1.1/2" PVC Tee | Nos | 3 |  |  |  |  | 0% | 3 | 219.12 | 657.36
h | Cost of 1.1/2" PVC Elbow | Nos | 6 |  |  |  |  | 0% | 6 | 67.32 | 403.92
i | Cost of 1.1/2" PVC FTA | Nos | 3 |  |  |  |  | 0% | 3 | 62.04 | 186.12
j | Cost of 15mm CP Braided hose 1meter length | Nos | 2 |  |  |  |  | 0% | 2 | 483.12 | 966.24
k | Cost of 1/2" x 3/4" CP Bush | Nos | 3 |  |  |  |  | 0% | 3 | 100.32 | 300.96
| Sub Total -- A | [9 empty] | 8979.96
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 7500 | 7500 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 7500
C | Add for
a | Transportation | [7 empty] | @ | 4% | 359.1984 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 269.3988 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 164.7996
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 1143.75
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 1937.1468
D | Total -- D = A + B + C | [9 empty] | 18417.1068
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 2762.566
G | Total G = D + E + F per Nos | [9 empty] | 21179.6728
| Rate per Nos (Taxes Extra) | [9 empty] | 21180
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 50825
5 | Pedal operated sink for hand wash(Kitchen,Pantry,CHL live Kitchen,BCL Live Kitchen)
Consider Size Per Nos
A | Material Consumed
a | Cost of Angle Cock-Make Jaquar,Model FUS-29053 | Nos | 8 |  |  |  |  | 0% | 8 | 1280.4 | 10243.2
b | Cost of 15mm CP Tee | Nos | 4 |  |  |  |  | 0% | 4 | 232.32 | 929.28
c | Cost of 15mm CP braided hose 2feet | Nos | 4 |  |  |  |  | 0% | 4 | 483.12 | 1932.48
d | Cost of 15mm CP Braided hose 1meter length | Nos | 16 |  |  |  |  | 0% | 16 | 483.12 | 7729.92
e | Cost of Single spout fixed type for pedal operated | Nos | 1 |  |  |  |  | 0% | 1 | 9550 | 9550 | Purchase bill to be verified
f | Cost of Hex Nipple | Nos | 8 |  |  |  |  | 0% | 8 | 213.84 | 1710.72
| Sub Total -- A | [9 empty] | 32095.6
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 8200 | 8200 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 8200
C | Add for
a | Transportation | [7 empty] | @ | 4% | 1283.824 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 962.868 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 402.956
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 1250.5
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 3900.148
D | Total -- D = A + B + C | [9 empty] | 44195.748
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 6629.3622
G | Total G = D + E + F per Nos | [9 empty] | 50825.1102
| Rate per Nos (Taxes Extra) | [9 empty] | 50825
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 12866
6 | Pantry
Consider Size Per Nos
A | Material Consumed
a | Cost of 2" x 1.1/2" PVC MTA | Nos | 2 |  |  |  |  | 0% | 2 | 121.44 | 242.88
b | Cost of 1.1/2" FTA | Nos | 1 |  |  |  |  | 0% | 1 | 62.04 | 62.04
c | Cost of Angle Cock | Nos | 2 |  |  |  |  | 0% | 2 | 1280.4 | 2560.8
d | Cost of Sink Cock with swinging spout (wall mounted Model) With Wall Flange | Nos | 1 |  |  |  |  | 0% | 1 | 1584 | 1584
e | Cost of 2" x 1.1/2" PVC Bush | Nos | 2 |  |  |  |  | 0% | 2 | 42.24 | 84.48
f | Cost of 1.1/2" PVC Unions | Nos | 2 |  |  |  |  | 0% | 2 | 260.04 | 520.08
g | Cost of 1.1/2" PVC Elbow | Nos | 4 | [5 empty] | 4 | 67.32 | 269.28
h | Cost of 4" PVC End Cap | Nos | 2 | [5 empty] | 2 | 72.6 | 145.2
i | Cost of 1.1/2" PVC End Cap | Nos | 1 | [5 empty] | 1 | 46.2 | 46.2
| Sub Total -- A | [9 empty] | 5514.96
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 4500 | 4500 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 4500
C | Add for
a | Transportation | [7 empty] | @ | 4% | 220.5984 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 165.4488 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 100.1496
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 686.25
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 1172.4468
D | Total -- D = A + B + C | [9 empty] | 11187.4068
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 1678.111
G | Total G = D + E + F per Nos | [9 empty] | 12865.5178
| Rate per Nos (Taxes Extra) | [9 empty] | 12866
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 54468
7 | BCL Bar Counter
Consider Size Per Nos
A | Material Consumed
a | Cost of 1.1/2" PVC FTA | Nos | 2 |  |  |  |  | 0% | 2 | 62.04 | 124.08
b | Cost of 1.1/2"PVC MTA | Nos | 4 |  |  |  |  | 0% | 4 | 71.544 | 286.176
c | Cost of 1.1/2" PVC Unions | Nos | 4 |  |  |  |  | 0% | 4 | 260.04 | 1040.16
d | Cost of 1.1/2" PVC Elbow | Nos | 8 |  |  |  |  | 0% | 8 | 67.32 | 538.56
e | Cost of Hot and Cold pillar cock sink mixer with revolving spout-Make Jaquar, Model-CQT-23309B | Nos | 1 |  |  |  |  | 0% | 1 | 3049.2 | 3049.2
f | Cost of Single side lever sink mixer with swinging spout-Make Jaquar, Model FLR-5179B | Nos | 1 |  |  |  |  | 0% | 1 | 4250.4 | 4250.4
g | Cost of 15mm CP braided hose 1mtrs length | Nos | 6 |  |  |  |  | 0% | 6 | 483.12 | 2898.72
h | Cost of Hex nipple | Nos | 4 |  |  |  |  | 0% | 4 | 213.84 | 855.36
i | Cost of Angle Cock-Make Jaquar,Model FUS-29053 | Nos | 8 |  |  |  |  | 0% | 8 | 1280.4 | 10243.2
j | Cost of 1/2" x 3/4" CP Bush | Nos | 2 |  |  |  |  | 0% | 2 | 100.32 | 200.64
k | Cost of 4" PVC End Cap | Nos | 5 |  |  |  |  | 0% | 5 | 72.6 | 363
l | Cost of 1.1/2" PVC End Cap | Nos | 2 |  |  |  |  | 0% | 2 | 46.2 | 92.4
| Sub Total -- A | [9 empty] | 23941.896
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 18500 | 18500 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 18500
C | Add for
a | Transportation | [7 empty] | @ | 4% | 957.6758 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 718.2569 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 424.419
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 2821.25
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 4921.6017
D | Total -- D = A + B + C | [9 empty] | 47363.4977
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 7104.5247
G | Total G = D + E + F per Nos | [9 empty] | 54468.0223
| Rate per Nos (Taxes Extra) | [9 empty] | 54468
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 50856
8 | CHL Bar Counter
Consider Size Per Nos
A | Material Consumed
a | Cost of Angle Cock | Nos | 7 |  |  |  |  | 0% | 7 | 1280.4 | 8962.8
b | Cost of 1.1/2" PVC FTA | Nos | 2 |  |  |  |  | 0% | 2 | 62.04 | 124.08
c | Cost of 2" PVC MTA | Nos | 4 |  |  |  |  | 0% | 4 | 100.32 | 401.28
d | Cost of 2" x 1.1/2" PVC Bush | Nos | 2 |  |  |  |  | 0% | 2 | 121.44 | 242.88
e | Cost of 1.1/2" PVC Elbow | Nos | 8 |  |  |  |  | 0% | 8 | 67.32 | 538.56
f | Cost of 1.1/2" PVC Unions | Nos | 4 |  |  |  |  | 0% | 4 | 260.04 | 1040.16
g | Cost of Hot and Cold pillar cock sink mixer with revolving spout | Nos | 1 |  |  |  |  | 0% | 1 | 3049.2 | 3049.2
h | Cost of 4" PVC End Cap | Nos | 5 |  |  |  |  | 0% | 5 | 72.6 | 363
i | Cost of 1.1/2" PVC End Cap | Nos | 3 |  |  |  |  | 0% | 3 | 46.2 | 138.6
j | Cost of 15mm CP braided hose 1mtrs length | Nos | 6 |  |  |  |  | 0% | 6 | 483.12 | 2898.72
k | Cost of Single side lever sink mixer with swinging spout | Nos | 1 |  |  |  |  | 0% | 1 | 4250.4 | 4250.4
l | Cost of 1/2" x 3/4" CP Bush | Nos | 1 |  |  |  |  | 0% | 1 | 100.32 | 100.32
| Sub Total -- A | [9 empty] | 22110
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 17500 | 17500 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 17500
C | Add for
a | Transportation | [7 empty] | @ | 4% | 884.4 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 663.3 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 396.1
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 2668.75
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 4612.55
D | Total -- D = A + B + C | [9 empty] | 44222.55
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 6633.3825
G | Total G = D + E + F per Nos | [9 empty] | 50855.9325
| Rate per Nos (Taxes Extra) | [9 empty] | 50856
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 30596
9 | BCL Live Kitchen/CHL Live Kitchen
Consider Size Per Nos
A | Material Consumed
a | Cost of 1.1/2" PVC FTA | Nos | 2 |  |  |  |  | 0% | 2 | 62.04 | 124.08
b | Cost of 1.1/2" PVC MTA | Nos | 4 |  |  |  |  | 0% | 4 | 73.92 | 295.68
c | Cost of 1.1/2" PVC Unions | Nos | 4 |  |  |  |  | 0% | 4 | 260.04 | 1040.16
d | Cost of 1.1/2" PVC Elbow | Nos | 8 |  |  |  |  | 0% | 8 | 67.32 | 538.56
e | Cost of 15mm CP Braided Hose | Nos | 2 |  |  |  |  | 0% | 2 | 483.12 | 966.24
f | Cost of Angle Cock Make Jaquar,Model FUS-29053 | Nos | 2 |  |  |  |  | 0% | 2 | 1280.4 | 2560.8
g | Cost of Single side lever sink mixer with swinging Make Jaquar, Model FLR-5179B spout | Nos | 2 |  |  |  |  | 0% | 2 | 4250.4 | 8500.8
h | Cost of 4" PVC End Cap | Nos | 4 |  |  |  |  | 0% | 4 | 72.6 | 290.4
i | Cost of 1.1/2" PVC End Cap | Nos | 2 |  |  |  |  | 0% | 2 | 46.2 | 92.4
| Sub Total -- A | [9 empty] | 14409.12
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 9500 | 9500 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 9500
C | Add for
a | Transportation | [7 empty] | @ | 4% | 576.3648 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 432.2736 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 239.0912
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 1448.75
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 2696.4796
D | Total -- D = A + B + C | [9 empty] | 26605.5996
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 3990.8399
G | Total G = D + E + F per Nos | [9 empty] | 30596.4395
| Rate per Nos (Taxes Extra) | [9 empty] | 30596
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 3849
10 | CHL Buffet area
Consider Size Per Nos
A | Material Consumed
a | Cost of Angle Cock Make Jaquar,Model FUS-29053 | Nos | 2 |  |  |  |  | 0% | 2 | 1280.4 | 2560.8
| Sub Total -- A | [9 empty] | 2560.8
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 2 | [5 empty] | 2 | 250 | 500 | Please check with Vendor the Labour cost is very high
| Sub Total -- B | [9 empty] | 500
C | Add for
a | Transportation | [7 empty] | @ | 4% | 102.432 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 76.824 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 30.608
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 76.25
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 286.114
D | Total -- D = A + B + C | [9 empty] | 3346.914
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 502.0371
G | Total G = D + E + F per Nos | [9 empty] | 3848.9511
| Rate per Nos (Taxes Extra) | [9 empty] | 3849
1 | Providing Plumbing arrengement for with require material for below mentioned locations as per detail given. | Nos | [8 empty] | 16099
11 | Common Materials
Consider Size Per Nos
A | Material Consumed
a | Cost of Teflon Tape 10mtrs | Nos | 30 |  |  |  |  | 0% | 30 | 26.4 | 792
b | Cost of PVC Solutions | Ltrs | 2 |  |  |  |  | 0% | 2 | 712.8 | 1425.6
c | Cost of Angle Cock female threaded cap | Nos | 20 |  |  |  |  | 0% | 20 | 469.92 | 9398.4
d | Cost of 1.1/2" PVC Pipe 10KG(20feet length) | Length | 6 |  |  |  |  | 0% | 6 | 224.4 | 1346.4
| Sub Total -- A | [9 empty] | 12962.4
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 2 | [5 empty] | 2 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 518.496 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 388.872 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 129.624
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 1036.992
D | Total -- D = A + B + C | [9 empty] | 13999.392
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 2099.9088
G | Total G = D + E + F per Nos | [9 empty] | 16099.3008
| Rate per Nos (Taxes Extra) | [9 empty] | 16099
12 | Providing , fixing and commissioning of Geyser (Type- Electric , Make - Havells) | Nos | [8 empty] | 9165
a | 3L
Consider Size Per Nos
A | Material Consumed
a | Cost of Geyser- 3L | Nos | 1 |  |  |  |  | 0% | 1 | 4334 | 4334
b | Cost of Angle Cock-Make Jaquar,Model FUS-29053 | Nos | 2 |  |  |  |  | 0% | 2 | 1280.4 | 2560.8
| Sub Total -- A | [9 empty] | 6894.8
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 450 | 450
| Sub Total -- B | [9 empty] | 450
C | Add for
a | Transportation | [7 empty] | @ | 4% | 275.792 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 206.844 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 73.448
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 68.625
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 624.709
D | Total -- D = A + B + C | [9 empty] | 7969.509
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 1195.4263
G | Total G = D + E + F per Nos | [9 empty] | 9164.9353
| Rate per Nos (Taxes Extra) | [9 empty] | 9165
12 | Providing , fixing and commissioning of Geyser (Type- Electric , Make - Havells) | Nos | [8 empty] | 12982
b | 10L
Consider Size Per Nos
A | Material Consumed
a | Cost of Geyser- 10L | Nos | 1 |  |  |  |  | 0% | 1 | 7407 | 7407
b | Cost of Angle Cock-Make Jaquar,Model FUS-29053 | Nos | 2 |  |  |  |  | 0% | 2 | 1280.4 | 2560.8
| Sub Total -- A | [9 empty] | 9967.8
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 450 | 450
| Sub Total -- B | [9 empty] | 450
C | Add for
a | Transportation | [7 empty] | @ | 4% | 398.712 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 299.034 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 104.178
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 68.625
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 870.549
D | Total -- D = A + B + C | [9 empty] | 11288.349
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 1693.2523
G | Total G = D + E + F per Nos | [9 empty] | 12981.6013
| Rate per Nos (Taxes Extra) | [9 empty] | 12982
12 | Providing , fixing and commissioning of Geyser (Type- Electric , Make - Havells) | Nos | [8 empty] | 15790
c | 15L
Consider Size Per Nos
A | Material Consumed
a | Cost of Geyser- 15L | Nos | 1 |  |  |  |  | 0% | 1 | 9345 | 9345
b | Cost of Angle Cock-Make Jaquar,Model FUS-29053 | Nos | 2 |  |  |  |  | 0% | 2 | 1280.4 | 2560.8
| Sub Total -- A | [9 empty] | 11905.8
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 750 | 750 | Please check with Vendor the cost is high
| Sub Total -- B | [9 empty] | 750
C | Add for
a | Transportation | [7 empty] | @ | 4% | 476.232 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 357.174 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 126.558
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 114.375
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 1074.339
D | Total -- D = A + B + C | [9 empty] | 13730.139
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 2059.5208
G | Total G = D + E + F per Nos | [9 empty] | 15789.6599
| Rate per Nos (Taxes Extra) | [9 empty] | 15790
12 | Providing , fixing and commissioning of Geyser (Type- Electric , Make - Havells) | Nos | [8 empty] | 17912
d | 25L
Consider Size Per Nos
A | Material Consumed
a | Cost of Geyser- 25L | Nos | 1 |  |  |  |  | 0% | 1 | 10731 | 10731
b | Cost of Angle Cock-Make Jaquar,Model FUS-29053 | Nos | 2 |  |  |  |  | 0% | 2 | 1280.4 | 2560.8
| Sub Total -- A | [9 empty] | 13291.8
B | Labour Deployed
a | Labour Charges for fixing of the same | Nos | 1 | [5 empty] | 1 | 1050 | 1050 | Please check with Vendor the cost is high
| Sub Total -- B | [9 empty] | 1050
C | Add for
a | Transportation | [7 empty] | @ | 4% | 531.672 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 398.754 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 143.418
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 160.125
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 1233.969
D | Total -- D = A + B + C | [9 empty] | 15575.769
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 2336.3654
G | Total G = D + E + F per Nos | [9 empty] | 17912.1344
| Rate per Nos (Taxes Extra) | [9 empty] | 17912
B | Civil NT Items
1 | Finsihing of jambs in door/lintel openings, walls at mullion/MS support provision on the existing authority walls after demolishion, rate including materials, manual shifting from yard, labours, scaffolding etc.,-Approx 50mm plaster done | Rft | [8 empty] | 209
Consider Size Per Rft
A | Material Consumed
a | Cost of Plaster work - as per BOQ-Civil-05- cost of 12mm plaster work Rs.- 58 therefore cost for 50mm is = 58 x 3 | Rft | 1 | 1 |  |  |  | 0% | 1 | 174 | 174
| Sub Total -- A | [9 empty] | 174
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Rft | 1 | 1 |  |  |  |  | 1 | 30 | 30
| Sub Total -- B | [9 empty] | 30
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 204
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 4.5
G | Total G = D + E + F per Rft | [9 empty] | 208.5
| Rate per Rft (Taxes Extra) | [9 empty] | 209
2 | AC Duckt big Wall breakking work& All Packing Material Shifting Using Stair case, Block Cutting & Fixing work & Finishing work -1600mm x 900mm | Nos | [8 empty] | 12128
Consider Size Per Nos
A | Material Consumed
| Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 1600x 900 is= (1600x 900x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 12128 | 12128
| Sub Total -- A | [9 empty] | 12128
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 12128
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 12128
| Rate per Nos (Taxes Extra) | [9 empty] | 12128
3 | AC Duckt Small Wall baraking work& All Packing Material Shifting Using Stair case, Block Cutting & Fixing work & Finishing work | Nos | [8 empty] | 3032
Consider Size Per Nos-600mm x 600mm
A | Material Consumed
| Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 600x 600 is= (600x 600x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 3032 | 3032
| Sub Total -- A | [9 empty] | 3032
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 3032
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 3032
| Rate per Nos (Taxes Extra) | [9 empty] | 3032
3 | AC Duckt Small Wall baraking work& All Packing Material Shifting Using Stair case, Block Cutting & Fixing work & Finishing work | Nos | [8 empty] | 7580
Consider Size Per Nos-1000mm x 900mm
A | Material Consumed
| Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 600x 600 is= (1000x 900x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 7580 | 7580
| Sub Total -- A | [9 empty] | 7580
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 7580
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 7580
| Rate per Nos (Taxes Extra) | [9 empty] | 7580
4 | AC Duckt Medium Wall baraking work& All Packing Material Shifting Using Stair case, Block Cutting & Fixing work & Finishing work | Nos | [8 empty] | 7580
Consider Size Per Nos-1000mm x 900mm
A | Material Consumed
| Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 600x 600 is= (1000x 900x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 7580 | 7580
| Sub Total -- A | [9 empty] | 7580
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 7580
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 7580
| Rate per Nos (Taxes Extra) | [9 empty] | 7580
4 | AC Duckt Medium Wall baraking work& All Packing Material Shifting Using Stair case, Block Cutting & Fixing work & Finishing work | Nos | [8 empty] | 9601
Consider Size Per Nos-1900mm x 600mm
A | Material Consumed
| Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 600x 600 is= (1900x 600x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 9601.3333 | 9601.3333
| Sub Total -- A | [9 empty] | 9601.3333
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 9601.3333
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 9601.3333
| Rate per Nos (Taxes Extra) | [9 empty] | 9601
4 | AC Duckt Medium Wall baraking work& All Packing Material Shifting Using Stair case, Block Cutting & Fixing work & Finishing work | Nos | [8 empty] | 5390
Consider Size Per Nos-800mm x 800mm-Dia
A | Material Consumed
| Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 600x 600 is= (800x 800x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 5390.2222 | 5390.2222
| Sub Total -- A | [9 empty] | 5390.2222
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 5390.2222
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 5390.2222
| Rate per Nos (Taxes Extra) | [9 empty] | 5390
5 | CH Bar counter Top Concrete 100mm Braking work & Cement morter material Shifting ,andFinishing work- Including curve area length is around 26'-3" | Nos | [8 empty] | 14018
Consider Size Per Nos-26'-3"Rft
A | Material Consumed
a | Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 8000x 100 is= (8000x 100x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 6737.7778 | 6737.7778
b | Cost of PCC for 50mm to 75mm as per BOQ line -Civil Int-6- is Rs.99 Sft therefor cost for 8000x 100 is= (8000x 99)/(300x100) | Nos | 1 |  |  |  |  | 0% | 1 | 2640 | 2640
c | Cost of PCC for Plaster as per BOQ line -Civil Int-5- is Rs.58 Sft therefor cost for 8000x 100 is= (8000x 99)/(300x100)- 3sides | Nos | 3 |  |  |  |  | 0% | 3 | 1546.6667 | 4640
| Sub Total -- A | [9 empty] | 14017.7778
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 14017.7778
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 14017.7778
| Rate per Nos (Taxes Extra) | [9 empty] | 14018
6 | BL Bar counter Top Concrete 100mm Braking work & Cement morter material Shifting and Finishing work | Nos | [8 empty] | 14018
Consider Size Per Nos-26'-3"Rft
A | Material Consumed
a | Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 8000x 100 is= (8000x 100x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 6737.7778 | 6737.7778
b | Cost of PCC for 50mm to 75mm as per BOQ line -Civil Int-6- is Rs.99 Sft therefor cost for 8000x 100 is= (8000x 99)/(300x100) | Nos | 1 |  |  |  |  | 0% | 1 | 2640 | 2640
c | Cost of PCC for Plaster as per BOQ line -Civil Int-5- is Rs.58 Sft therefor cost for 8000x 100 is= (8000x 99)/(300x100)- 3sides | Nos | 3 |  |  |  |  | 0% | 3 | 1546.6667 | 4640
| Sub Total -- A | [9 empty] | 14017.7778
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 14017.7778
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 14017.7778
| Rate per Nos (Taxes Extra) | [9 empty] | 14018
7 | BL Live kitchen Top 100mm Braking & Cement morter material Shifting and Finishing work | Nos | [8 empty] | 7009
Consider Size Per Nos-13'-3"Rft
A | Material Consumed
a | Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 4000x 100 is= (4000x 100x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 3368.8889 | 3368.8889
b | Cost of PCC for 50mm to 75mm as per BOQ line -Civil Int-6- is Rs.99 Sft therefor cost for 4000x 100 is= (4000x 99)/(300x100) | Nos | 1 |  |  |  |  | 0% | 1 | 1320 | 1320
c | Cost of PCC for Plaster as per BOQ line -Civil Int-5- is Rs.58 Sft therefor cost for 4000x 100 is= (4000x 99)/(300x100)- 3sides | Nos | 3 |  |  |  |  | 0% | 3 | 773.3333 | 2320
| Sub Total -- A | [9 empty] | 7008.8889
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 7008.8889
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 7008.8889
| Rate per Nos (Taxes Extra) | [9 empty] | 7009
8 | CH Live kitchen Top 50mm Braking work, Cement morter material Shifting & Finishing work | Nos | [8 empty] | 4731
Consider Size Per Nos-8'-10"Rft
A | Material Consumed
a | Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 2700x 100 is= (2700x 100x758)/(300x300) | Nos | 1 |  |  |  |  | 0% | 1 | 2274 | 2274
b | Cost of PCC for 50mm to 75mm as per BOQ line -Civil Int-6- is Rs.99 Sft therefor cost for 2700x 100 is= (2700x 99)/(300x100) | Nos | 1 |  |  |  |  | 0% | 1 | 891 | 891
c | Cost of PCC for Plaster as per BOQ line -Civil Int-5- is Rs.58 Sft therefor cost for 2700x 100 is= (2700x 99)/(300x100)- 3sides | Nos | 3 |  |  |  |  | 0% | 3 | 522 | 1566
| Sub Total -- A | [9 empty] | 4731
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 4731
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 4731
| Rate per Nos (Taxes Extra) | [9 empty] | 4731
9 | Live Kitchen Door Exten work ( AS Per Drwg 0.75 mtrs But Now Change 0.9mtrs ( Wall Cutting & Braking & Cement morter material Shifting and Finishing work ) | Nos | [8 empty] | 5435
Consider Size Per Nos-900mm x 2400mm
A | Material Consumed
a | Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 2400x 100 is= (2400x 100x758)/(300x300)- 2sides | Nos | 2 |  |  |  |  | 0% | 2 | 2021.3333 | 4042.6667
b | Cost of Plaster as per BOQ line -Civil Int-5- is Rs.58 Sft therefor cost for 2400x 100 is= (2400x 100x58)/(300x100)- 3sides | Nos | 3 |  |  |  |  | 0% | 3 | 464 | 1392
| Sub Total -- A | [9 empty] | 5434.6667
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 5434.6667
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 5434.6667
| Rate per Nos (Taxes Extra) | [9 empty] | 5435
10 | DRY Store room Door Exten work ( Wall Cutting & Braking & Cement morter material Shifting and Finishing work ) | Nos | [8 empty] | 5435
Consider Size Per Nos-900mm x 2400mm
A | Material Consumed
a | Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 2400x 100 is= (2400x 100x758)/(300x300)- 2sides | Nos | 2 |  |  |  |  | 0% | 2 | 2021.3333 | 4042.6667
b | Cost of Plaster as per BOQ line -Civil Int-5- is Rs.58 Sft therefor cost for 2400x 100 is= (2400x 100x58)/(300x100)- 3sides | Nos | 3 |  |  |  |  | 0% | 3 | 464 | 1392
| Sub Total -- A | [9 empty] | 5434.6667
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 5434.6667
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 5434.6667
| Rate per Nos (Taxes Extra) | [9 empty] | 5435
11 | Pantry area Drian pipe Laying work( Floor chiping & Pipe laying & Modiform filling & Cement morter material Shifting Concrete filling & Finishing work | Nos | [8 empty] | 8058
Consider Size Per Nos-13'-2" Rft
A | Material Consumed
a | Cost of duct wall breaking as per BOQ line -Civil Demolition-4-for AC copper piper & drain pipe Approx 300mm x 300mm is Rs.758 therefor cost fr 4000x 100 is= (4000x 100x758)/(300x300)- 2sides (waterproofing removing too) | Nos | 2 |  |  |  |  | 0% | 2 | 3368.8889 | 6737.7778
b | Cost of PCC for 50mm to 75mm as per BOQ line -Civil Int-6- is Rs.99 Sft therefor cost for 4000x 100 is= (4000x 99)/(300x100) | Nos | 1 |  |  |  |  | 0% | 1 | 1320 | 1320
| Sub Total -- A | [9 empty] | 8057.7778
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 8057.7778
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 8057.7778
| Rate per Nos (Taxes Extra) | [9 empty] | 8058
12 | BL Live kitchen Inlet pipe alteration work | Nos | [8 empty] | 684
Consider Size Per Nos-4'-11" Rft
A | Material Consumed
a | Cost of wall chasing as per BOQ-Civil-Demolition-3 | Nos | 2 | 1.5 |  |  |  | 0% | 3 | 228 | 684
| Sub Total -- A | [9 empty] | 684
B | Labour Deployed
a | Labour Charges | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 684
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 684
| Rate per Nos (Taxes Extra) | [9 empty] | 684
12A | DB Box Tiles Cutting work & chiping work (SFT) | Sft | [8 empty] | 107
Consider Size Per Sft-4'-11" Rft
A | Material Consumed
a | Cost of | Sft | 1 | 1 |  | 1 |  | 0% | 1 |  | 0
| Sub Total -- A | [9 empty] | 0
B | Labour Deployed
a | Labour Charges for Cutting & chipping with the help for hammer & machine to minimize tile damage | Sft | 1 | 1 |  | 1 |  |  | 1 | 80 | 80
| Sub Total -- B | [9 empty] | 80
C | Add for
a | Transportation | [7 empty] | @ | 4% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 0.8
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 12.2
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 13
D | Total -- D = A + B + C | [9 empty] | 93
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 13.95
G | Total G = D + E + F per Sft | [9 empty] | 106.95
| Rate per Sft (Taxes Extra) | [9 empty] | 107
14 | CH Bar counter Door elbow fixing ( Cocrete & Block work braking & Pipe cutting & Door elbow fixing Using Coupling & Material Shifting ,Block work & Concrete Filling & Plastering work | Job | [8 empty] | 4347
Consider Size Per Job
A | Material Consumed
a | Cost of Drain pipe & Lbow fixing with cutting of marble & making blockwork & finishing the sides with plaster | Job | 1 |  |  |  |  | 0% | 1 | 3500 | 3500
| Sub Total -- A | [9 empty] | 3500
B | Labour Deployed
a | Labour Charges | Job | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 140
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 105
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 35
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 280
D | Total -- D = A + B + C | [9 empty] | 3780
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 567
G | Total G = D + E + F per Job | [9 empty] | 4347
| Rate per Job (Taxes Extra) | [9 empty] | 4347
15 | Bund Wall work( Marble Cutting & Removing , Material Shifting Using Stair case ,Block work laying , concret filling & Plastering work ( QTY-Rft) | Rft | [8 empty] | 729
Consider Size Per Rft
A | Material Consumed
a | Cost of block work-Civil- Interior-3a Rs-198 per sft- 2 rows | Rft | 1 | 1 | 1 |  |  | 0% | 1 | 198 | 198
b | Cost of PCC for 50mm to 75mm as per BOQ line -Civil Int-6- is Rs.99 Sft | Rft | 1 | 1 | 1 |  |  | 0% | 1 | 99 | 99
c | Cost of Plaster as per BOQ line -Civil Int-5- is Rs.58 Sft | Nos | 5 |  |  |  |  | 0% | 5 | 58 | 290
| Sub Total -- A | [9 empty] | 587
B | Labour Deployed
a | Labour Charges | Rft | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 23.48
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 17.61
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 5.87
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 46.96
D | Total -- D = A + B + C | [9 empty] | 633.96
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 95.094
G | Total G = D + E + F per Rft | [9 empty] | 729.054
| Rate per Rft (Taxes Extra) | [9 empty] | 729
17 | Lounge area MS Angle Marbel Floor Cutting & Concrete Filling & Marbel Re laying | Job | [8 empty] | 1553
Consider Size Per Job
A | Material Consumed
a | Cost of MS pole fixing Inclduing cutting of marble , fixing pole,PCC & Marble refixing etc | Job | 1 |  |  |  |  | 0% | 1 | 1250 | 1250
| Sub Total -- A | [9 empty] | 1250
B | Labour Deployed
a | Labour Charges | Job | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 50
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 37.5
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 12.5
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 100
D | Total -- D = A + B + C | [9 empty] | 1350
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 202.5
G | Total G = D + E + F per Job | [9 empty] | 1552.5
| Rate per Job (Taxes Extra) | [9 empty] | 1553
18 | CH & BL Bar counter Geyser Inlet & Out Let Supply Changing Work | Nos | [8 empty] | 684
Consider Size Per Nos-4'-11" Rft
A | Material Consumed
a | Cost of wall chasing as per BOQ-Civil-Demolition-3 | Nos | 2 | 1.5 |  |  |  | 0% | 3 | 228 | 684
| Sub Total -- A | [9 empty] | 684
B | Labour Deployed
a | Labour Charges | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 0% | 0
b | Loading/Unloading & lifting | [7 empty] | @ | 0% | 0
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 0% | 0
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 0% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 0
D | Total -- D = A + B + C | [9 empty] | 684
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 0% | 0
G | Total G = D + E + F per Nos | [9 empty] | 684
| Rate per Nos (Taxes Extra) | [9 empty] | 684
Interior Work
1 | Providing & Fixing aluminium framing with Ply with all including at Main Corridor Entry Archi-tray | Rft | [8 empty] | 1642
Consider Size for 1'-0" x 9'-0"x 1 '6" x 0'-6"
A | Material Consumed
Kg/Ft
a | Cost of Aluminium Pipe-25mm x 50mm -16 gague | Kg | 4 | 10 | 0.28 |  |  | 0% | 11.2 | 330 | 3696 | Horizontal Plywood missing | 0.767 | 0.23378
b | Cost of 19mm plywood | Sft | 2 | 1 |  | 9 |  | 7% | 19.26 | 95 | 1829.7
|  | Sft | 1 | 1.5 |  | 9 |  | 7% | 14.445 | 95 | 1372.275
|  | Sft | 1 | 0.5 |  | 9 |  | 7% | 4.815 | 95 | 457.425
c | Cost of harware & L corner for joining etc | Rft | [6 empty] | 0 | 7% | 514.878
| Sub Total -- A | [9 empty] | 7870.278
B | Labour Deployed
a | Labour Charges for framing | Sft | 1 | 3 |  | 9 |  |  | 27 | 50 | 1350
b | Labour Charges for fixing- Plywood Fixing | Sft | 1 | 38.52 |  | 1 |  |  | 38.52 | 55 | 2118.6
| Sub Total -- B | [9 empty] | 3468.6
C | Add for
a | Transportation | [7 empty] | @ | 4% | 314.8111
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 236.1083
c | Scaffolding | [7 empty] | @ | 4% | 314.8111
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 113.3888
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 528.9615
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 1508.0809
D | Total -- D = A + B + C | [9 empty] | 12846.9589
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 1927.0438
G | Total G = D + E + F per Rft for (1'-0" x 9'-0") | [9 empty] | 1641.5559
| Rate per Rft (Taxes Extra) | [9 empty] | 1642
2 | Labour charges for Marble cladding in main corridor entry arch- tray including consumables | Rft | [8 empty] | 1630
Consider Size for 1'-0" x 9'-0"x 1 '6" x 0'-6"
A | Material Consumed
a | Cost of Marble fixing | Sft | 2 | 1 |  | 9 |  | 7% | 19.26 |  | 0
|  | Sft | 1 | 1.5 |  | 9 |  | 7% | 14.445 |  | 0
|  | Sft | 1 | 1 |  | 9 |  | 7% | 9.63 |  | 0
b | Cost of araldite adhesive | Sft | 1 | 43.335 |  | 1 |  |  | 43.335 | 50 | 2166.75
| Sub Total -- A | [9 empty] | 2166.75
B | Labour Deployed
a | Labour Charges for Marble fixing | Sft | 2 | 1 |  | 9 |  | 7% | 19.26 | 95 | 1829.7
|  | Sft | 1 | 1.5 |  | 9 |  | 7% | 14.445 | 95 | 1372.275
|  | Sft | 1 | 1 |  | 9 |  | 7% | 9.63 | 95 | 914.85
b | Labour Charges for Marble Polishing | Sft | 1 | 43.335 |  | 1 |  |  | 43.335 | 110 | 4766.85
| Sub Total -- B | [9 empty] | 8883.675
C | Add for
a | Transportation | [7 empty] | @ | 4% | 86.67
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 65.0025
c | Scaffolding | [7 empty] | @ | 4% | 86.67
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 110.5043
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 1354.7604
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 1703.6072
D | Total -- D = A + B + C | [9 empty] | 12754.0322
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 1913.1048
G | Total G = D + E + F per Rft for (1'-0" x 9'-0") | [9 empty] | 1629.6819
| Rate per Rft (Taxes Extra) | [9 empty] | 1630
3 | Main Corridor Entry fabric cladding with fabric and foam strich as per the instruction of architect | Sft | [8 empty] | 1996
Consider Size for
A | Material Consumed
a | Cost of 19mm plywoord | Sft | 1 | 1 |  | 1 |  | 7% | 1.07 | 95 | 101.65
b | Cost of Faric & foam stich etc | Sft | 1 | 1 |  | 1 |  | 15% | 1.15 | 880 | 1012
d | Cost of hardware | Sft | 1 | 1 |  | 1 |  | 7% | 1.07 | 15 | 16.05
| Sub Total -- A | [9 empty] | 1129.7
B | Labour Deployed
a | Labour Charges for foam & Fabric as per design | Sft | 1 | 1 |  | 1 |  |  | 1 | 350 | 350
b | Labour Charges for fixing- Plywood Fixing | Sft | 1 | 1 |  | 1 |  |  | 1 | 55 | 55
| Sub Total -- B | [9 empty] | 405
C | Add for
a | Transportation | [7 empty] | @ | 4% | 45.188
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 33.891
c | Scaffolding | [7 empty] | @ | 4% | 45.188
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 15.347
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 61.7625
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 201.3765
D | Total -- D = A + B + C | [9 empty] | 1736.0765
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 260.4115
G | Total G = D + E + F per Sft | [9 empty] | 1996.488
| Rate per Sft (Taxes Extra) | [9 empty] | 1996
4 | Providing & Fixing DB niche Door as per drawing inside laminate & outer venner | Sft | [8 empty] | 1566
Consider Size for -8'-0" x 8'-0"-8'-0" x 1'-3" fixed
A | Material Consumed
a | Cost of 19mm plywoord | Sft | 1 | 8 |  | 8 |  | 7% | 68.48 | 95 | 6505.6
|  | Sft | 1 | 8 |  | 1.25 |  | 7% | 10.7 | 95 | 1016.5
| End Sides | Sft | 2 | 1 |  | 8 |  | 7% | 17.12 | 95 | 1626.4
| Horizontal | Sft | 1 | 1 |  | 8 |  | 7% | 8.56 | 95 | 813.2
| Middle sides | Sft | 3 | 1 |  | 8 |  | 7% | 25.68 | 95 | 2439.6
b | Cost of Aluminium Pipe-25mm x 50mm -16 gague | Kg | 2.5 | 10 | 0.28 |  |  | 0% | 7 | 330 | 2310
c | cost of Veneer | Sft | 1 | 8 |  | 8 |  | 10% | 70.4 | 145 | 10208 | Please check Veneer Basic price
|  | Sft | 1 | 8 |  | 1.25 |  | 10% | 11 | 145 | 1595 | Please check Veneer Basic price
d | Cost of Laminate= 2xTotal qty of plywood - Veneer qty | Sft | 2 | 179.68 |  | 1 |  | 7% | 384.5152 | 40 | 15380.608 | Please check Laminate Basic price ( where is this laminate coming)
d | Cost of hardware &Fevicol , lock etc | Sft | 1 |  |  |  |  | 0% | 1 | 6284.2362 | 6284.2362
| Sub Total -- A | [9 empty] | 48179.1442
B | Labour Deployed
a | Labour Charges for framing | Sft | 1 | 8 |  | 1.25 |  |  | 10 | 50 | 500
b | Labour Charges for fixing- DB shutter with Veneer & Laminate | Sft | 1 | 8 |  | 9.25 |  |  | 74 | 450 | 33300
c | Labour Charges for Veneer Polishing | Sft | 1 | 81.4 |  | 1 |  |  | 81.4 | 100 | 8140
| Sub Total -- B | [9 empty] | 41940
C | Add for
a | Transportation | [7 empty] | @ | 4% | 1927.1658
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 1445.3743
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 901.1914
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 6395.85
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 10669.5815
D | Total -- D = A + B + C | [9 empty] | 100788.7257
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 15118.3089
G | Total G = D + E + F per Sft (8'-0" x 9'-3") | [9 empty] | 1566.3113
| Rate per Sft (Taxes Extra) | [9 empty] | 1566
5 | CHL SPA Arch wall-Ply Boxing using 19mm thick ply with 12mm thk ply with flexi ply with MDF for final finish with all necessary hardware & Fitting on wall & Ceiling arch type As per details & Drawing – 4.480 x 2.55 – Measured all wall area – | Sft | [8 empty] | 1593
Consider Size for Sft-13'-9" x 3'-0"
A | Material Consumed
a | Cost of 19mm plywood frame- for farma- 9 box required for farma -2'-4"x 2'-0"x 0-6"x 0'-2"thk | Sft | 18 | 2 |  | 2.33 |  | 7% | 89.7516 | 95 | 8526.402 | Nos 9 boxes Missing
|  | Sft | 9 | 0.5 |  | 0.25 |  | 7% | 1.2038 | 95 | 114.3563
|  | Sft | 9 | 2 |  | 0.25 |  | 7% | 4.815 | 95 | 457.425
|  | Sft | 1 | 2.33 |  | 0.25 |  | 7% | 0.62328 | 95 | 59.2111
b | Cost for 19mm Plywood- Flexi | Sft | 1 | 13.75 |  | 3 |  | 15% | 47.4375 | 145 | 6878.4375
|  | Sft | 1 | 13.75 |  | 0.5 |  | 15% | 7.9062 | 145 | 1146.4062
c | Cost for 6mm MDF | Sft | 1 | 13.75 |  | 3 |  | 15% | 47.4375 | 45 | 2134.6875
|  | Sft | 1 | 13.75 |  | 0.5 |  | 15% | 7.9062 | 45 | 355.7812
d | Cost of Aluminium Pipe-25mm x 50mm -16 gague | Sft | 1 | 13.75 |  | 3 |  | 0% | 41.25 | 125 | 5156.25
e | Cost of Hardware | Sft | 1 | 13.75 |  | 3 |  | 0% | 41.25 | 15 | 618.75
| Sub Total -- A | [9 empty] | 25447.7069
B | Labour Deployed
a | Labour Charges for fixing- Plywood Boxes & arc marking with MDF ETC | Sft | 1 | 13.75 |  | 3 |  |  | 41.25 | 575 | 23718.75
| Sub Total -- B | [9 empty] | 23718.75
C | Add for
a | Transportation | [7 empty] | @ | 4% | 1017.9083
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 763.4312
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 491.6646
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 3617.1094
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 5890.1134
D | Total -- D = A + B + C | [9 empty] | 55056.5703
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 8258.4855
G | Total G = D + E + F per Sft 13'-9" x 3'-0" | [9 empty] | 1592.8316
| Rate per Sft (Taxes Extra) | [9 empty] | 1593
6 | CHL SPA Full height Storage-Providing & fixing Full height storage in spa with Ply & Laminate - 900 x 2400 x 600 | Sft | [8 empty] | 1989
Consider Size for -4'-0" x 8'-0"x 2'-8"
A | Material Consumed
a | Cost of 19mm plywoord | Sft | 1 | 4 |  | 8 |  | 7% | 34.24 | 95 | 3252.8
| End Sides | Sft | 2 | 2 |  | 8 |  | 7% | 34.24 | 95 | 3252.8
| Horizontal- Shelves | Sft | 3 | 4 |  | 2.67 |  | 7% | 34.2828 | 95 | 3256.866
| Top & Bottom | Sft | 1 | 4 |  | 2.67 |  | 7% | 11.4276 | 95 | 1085.622
| Back | Sft | 1 | 4 |  | 8 |  | 7% | 34.24 | 95 | 3252.8
b | cost of Veneer- Total Qty of Plywood | Sft | 1 | 148.4304 |  | 1 |  | 10% | 163.2734 | 145 | 23674.6488 | Please check Veneer Basic price
d | Cost of Laminate=Total qty of plywood | Sft | 1 | 148.4304 |  | 1 |  | 7% | 158.8205 | 40 | 6352.8211 | Please check Laminate Basic price
d | Cost of hardware &Fevicol , lock etc | Sft | 1 |  |  |  |  | 0% | 1 | 6619.2537 | 6619.2537
| Sub Total -- A | [9 empty] | 50747.6116
B | Labour Deployed
a | Labour Charges for fixing- DB shutter with Veneer & Laminate | Sft | 1 | 8 |  | 9.25 |  |  | 74 | 650 | 48100
b | Labour Charges for Veneer Polishing | Sft | 1 | 148.4304 |  | 1 |  |  | 148.4304 | 100 | 14843.04
| Sub Total -- B | [9 empty] | 62943.04
C | Add for
a | Transportation | [7 empty] | @ | 4% | 2029.9045
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 1522.4283
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 1136.9065
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 9598.8136
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 14288.0529
D | Total -- D = A + B + C | [9 empty] | 127978.7045
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 19196.8057
G | Total G = D + E + F per Sft (4'-0" x 8'-0") | [9 empty] | 1988.8582
| Rate per Sft (Taxes Extra) | [9 empty] | 1989
7 | CHL Massage room Vanity Counter as per details drawing with veneer shutter – 900 x 600 (Deep) x 400 (height) | Nos | [8 empty] | 18077
Consider Size for -3'-0" x 1'-4"x 2'-0"- Nos
A | Material Consumed
a | Cost of 19mm plywoord front & Back | Sft | 2 | 3 |  | 1.33 |  | 7% | 8.5386 | 95 | 811.167
| End Sides | Sft | 2 | 2 |  | 1.33 |  | 7% | 5.6924 | 95 | 540.778
| Horizontal- Shelves | Sft | 1 | 2 |  | 1.33 |  | 7% | 2.8462 | 95 | 270.389
| Top & Bottom | Sft | 1 | 3 |  | 1.33 |  | 7% | 4.2693 | 95 | 405.5835
b | cost of Veneer- Total Qty of Plywood | Sft | 1 | 21.3465 |  | 1 |  | 10% | 23.4812 | 145 | 3404.7668
c | Cost of Laminate=Total qty of plywood | Sft | 1 | 21.3465 |  | 1 |  | 7% | 22.8408 | 40 | 913.6302
d | Cost of hardware &Fevicol , lock etc | Sft | 1 |  |  |  |  | 0% | 1 | 951.9472 | 951.9472
e | Cost of Adhesive for Marble fixing | Sft | 1 | 2 |  | 1.33 |  | 0% | 2.66 | 60 | 159.6
| Sub Total -- A | [9 empty] | 7457.8616
B | Labour Deployed
a | Labour Charges for fixing- DB shutter with Veneer & Laminate | Sft | 1 | 3 |  | 2 |  |  | 6 | 650 | 3900
b | Labour Charges for Veneer Polishing | Sft | 1 | 21.3465 |  | 1 |  |  | 21.3465 | 100 | 2134.65
c | Labour Charges for Marble cutting & Fixing | Sft | 1 | 3 |  | 1.33 |  |  | 3.99 | 75 | 299.25
d | Labour Charges for Marble Polishing | Sft | 1 | 3 |  | 1.33 |  |  | 3.99 | 65 | 259.35
| Sub Total -- B | [9 empty] | 6593.25
C | Add for
a | Transportation | [7 empty] | @ | 4% | 298.3145
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 223.7358
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 140.5111
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 1005.4706
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 1668.0321
D | Total -- D = A + B + C | [9 empty] | 15719.1437
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 2357.8716
G | Total G = D + E + F per Nos | [9 empty] | 18077.0152
| Rate per Nos (Taxes Extra) | [9 empty] | 18077
9 | Supply and Installation of saint gobain shower cubicles with 8 mm tempered clear glass asper detail given. | Nos | [8 empty] | 31659
Consider Size for- Nos
A | Material Consumed
a | Octs of Shower cubical | Nos | 1 |  |  |  |  | 0% | 1 | 25490 | 25490 | Please verify the purchase bill from Contractor
| Sub Total -- A | [9 empty] | 25490
B | Labour Deployed
a | Labour Charges for fixing- | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 1019.6
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 764.7
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 254.9
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 2039.2
D | Total -- D = A + B + C | [9 empty] | 27529.2
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 4129.38
G | Total G = D + E + F per Nos | [9 empty] | 31658.58
| Rate per Nos (Taxes Extra) | [9 empty] | 31659
10 | CHL live kitchen front counter for equipments -Providing & fixing wooden counter with 19mm Ply with laminate - Deep up to 550 , with marble counter top | Nos | [8 empty] | 63525
Consider Size for -9'-0" x 3'-0"x 2'-5"- Nos
A | Material Consumed
a | Cost of 19mm plywoord front & Back | Sft | 1 | 9 |  | 3 |  | 7% | 28.89 | 95 | 2744.55
| End Sides | Sft | 2 | 3 |  | 2.58 |  | 7% | 16.5636 | 95 | 1573.542
| Horizontal- Shelves | Sft | 1 | 3 |  | 2.58 |  | 7% | 8.2818 | 95 | 786.771 | Horizontal shelf could not be seen in the presentation photo
| Top & Bottom | Sft | 1 | 9 |  | 2.58 |  | 7% | 24.8454 | 95 | 2360.313
| Vertical | Sft | 3 | 3 |  | 2.58 |  | 7% | 24.8454 | 95 | 2360.313
b | cost of Laminate- Total Qty of Plywood | Sft | 1 | 103.4262 |  | 1 |  | 10% | 113.7688 | 145 | 16496.4789 | Cost of Veneer considered by Contractor
d | Cost of hardware &Fevicol , lock etc | Sft | 1 |  |  |  |  | 0% | 1 | 3948.2952 | 3948.2952
e | Cost of Adhesive for Marble fixing | Sft | 1 | 9 |  | 2.58 |  | 0% | 23.22 | 60 | 1393.2
| Sub Total -- A | [9 empty] | 31663.4631
B | Labour Deployed
a | Labour Charges for fixing- DB shutter with Laminate | Sft | 1 | 9 |  | 3 |  |  | 27 | 550 | 14850
b | Labour Charges for Marble cutting & Fixing | Sft | 1 | 9 |  | 2.58 |  |  | 23.22 | 75 | 1741.5
c | Labour Charges for Marble Polishing | Sft | 1 | 9 |  | 2.58 |  |  | 23.22 | 65 | 1509.3
| Sub Total -- B | [9 empty] | 18100.8
C | Add for
a | Transportation | [7 empty] | @ | 4% | 1266.5385
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 949.9039
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 497.6426
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 2760.372
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 5474.457
D | Total -- D = A + B + C | [9 empty] | 55238.7201
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 8285.808
G | Total G = D + E + F per Nos | [9 empty] | 63524.5282
| Rate per Nos (Taxes Extra) | [9 empty] | 63525
16 | Providing and fixing Fluted glass partition on wall with Powder coated aluminium frame as per the instruction of architect | Sft | [8 empty] | 2990
Consider Size for - Sft
A | Material Consumed
a | Cost of Fluted glass partiton | Sft | 1 | 1 |  | 1 |  | 7% | 1.07 | 2250 | 2407.5 | Purchase bill of Fluted glass to be verified
| Sub Total -- A | [9 empty] | 2407.5
B | Labour Deployed
a | Labour Charges for fixing- | Sft | 1 | 1 |  | 1 |  |  | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 96.3
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 72.225
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 24.075
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 192.6
D | Total -- D = A + B + C | [9 empty] | 2600.1
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 390.015
G | Total G = D + E + F per Sft | [9 empty] | 2990.115
| Rate per Sft (Taxes Extra) | [9 empty] | 2990
17 | Providing and Applying texture paint on designer ceiling as per detail given. | Sft | [8 empty] | 126
Consider Size for - Sft
A | Material Consumed
a | Cost of Texture paint | Sft | 1 | 1 |  | 1 |  | 7% | 1.07 | 95 | 101.65
| Sub Total -- A | [9 empty] | 101.65
B | Labour Deployed
a | Labour Charges for fixing- | Sft | 1 | 1 |  | 1 |  |  | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 4.066
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 3.0495
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 1.0165
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 8.132
D | Total -- D = A + B + C | [9 empty] | 109.782
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 16.4673
G | Total G = D + E + F per Sft | [9 empty] | 126.2493
| Rate per Sft (Taxes Extra) | [9 empty] | 126
18 | Supply & Installation of Fire Door External trim with cylindrical lock as per detail given. | Nos | [8 empty] | 8807
Consider Size for - Nos
A | Material Consumed
a | Cost of Cylindrical lock with handle | Nos | 1 | [5 empty] | 1 | 6822 | 6822 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 6822
B | Labour Deployed
a | Labour Charges for fixing- | Nos | 1 | [5 empty] | 1 | 250 | 250
| Sub Total -- B | [9 empty] | 250
C | Add for
a | Transportation | [7 empty] | @ | 4% | 272.88
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 204.66
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 70.72
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 38.125
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 586.385
D | Total -- D = A + B + C | [9 empty] | 7658.385
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 1148.7577
G | Total G = D + E + F per Nos | [9 empty] | 8807.1428
| Rate per Nos (Taxes Extra) | [9 empty] | 8807
20 | Providing and fixing SS plate for Raceway Junction Box at floor as per detail given. | KG | [8 empty] | 617
Consider Size for - KG
A | Material Consumed
a | Cost of Cylindrical lock with handle | KG | 1 |  |  |  |  | 7% | 1.07 | 464 | 496.48 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 496.48
B | Labour Deployed
a | Labour Charges for fixing- | KG | 1 | [5 empty] | 1 | 0 | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 19.8592
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 14.8944
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 4.9648
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 39.7184
D | Total -- D = A + B + C | [9 empty] | 536.1984
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 80.4298
G | Total G = D + E + F per KG | [9 empty] | 616.6282
| Rate per KG (Taxes Extra) | [9 empty] | 617
21 | Providing & fixing Fire Hydrant Door with glass as per detail given. | Nos | [8 empty] | 43470
Consider Size for - Nos
A | Material Consumed
a | Cost of Fire Hydrant door with glass | Nos | 1 | [5 empty] | 1 | 35000 | 35000 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 35000
B | Labour Deployed
a | Labour Charges for fixing- | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 1400
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 1050
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 350
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 2800
D | Total -- D = A + B + C | [9 empty] | 37800
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 5670
G | Total G = D + E + F per Nos | [9 empty] | 43470
| Rate per Nos (Taxes Extra) | [9 empty] | 43470
22 | Providing In fixing 20 mm x 20 mm square tube frame work and approval RAL power coating , 20 mm Thk MDF Shelf both side Finished in Black DUCO Paint , 6mm ply with Back side Panel in 1.5 mm Thk Steel Plate with Brass pvd coating with Necessary adhesive Hardware etc as per detail given. | Nos | [8 empty] | 4809
Consider Size for - Nos
A | Material Consumed
a | Cost of Library rack | Nos | 1 | 1 |  | 1 |  | 7% | 1.07 | 3618.5433 | 3871.8413 | Purchase bill to be verified/ Break up required
| Sub Total -- A | [9 empty] | 3871.8413
B | Labour Deployed
a | Labour Charges for fixing- | Nos | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 154.8737
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 116.1552
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 38.7184
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 309.7473
D | Total -- D = A + B + C | [9 empty] | 4181.5886
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 627.2383
G | Total G = D + E + F per Nos | [9 empty] | 4808.8269
| Rate per Nos (Taxes Extra) | [9 empty] | 4809
23 | Prvoiding & fixing MS Planter railing Height 2.4 m as per drawing as per detail given. | Rft | [8 empty] | 6379
Consider Size for - Rft
A | Material Consumed
a | Cost of MS planter railing | Rft | 1 | 1 |  |  |  | 7% | 1.07 | 4800 | 5136
| Sub Total -- A | [9 empty] | 5136
B | Labour Deployed
a | Labour Charges for fixing- | Rft | 1 | [5 empty] | 1 |  | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 205.44
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 154.08
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 51.36
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 410.88
D | Total -- D = A + B + C | [9 empty] | 5546.88
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 832.032
G | Total G = D + E + F per Rft | [9 empty] | 6378.912
| Rate per Rft (Taxes Extra) | [9 empty] | 6379
24 | Prvoiding & fixing SS corner guard as per specification normal corner guard as per detail given.(50mm x 50mm) | Rft | [8 empty] | 628
Consider Size for - Rft
A | Material Consumed
a | Cost of SS Corner guard | Rft | 1 | 1 |  |  |  | 7% | 1.07 | 426.2195 | 456.0549 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 456.0549
B | Labour Deployed
a | Labour Charges for fixing- | Rft | 1 | 1 |  |  |  |  | 1 | 45.7317 | 45.7317
| Sub Total -- B | [9 empty] | 45.7317
C | Add for
a | Transportation | [7 empty] | @ | 4% | 18.2422
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 13.6816
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 5.0179
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 6.9741
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 43.9158
D | Total -- D = A + B + C | [9 empty] | 545.7024
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 81.8554
G | Total G = D + E + F per Rft | [9 empty] | 627.5577
| Rate per Rft (Taxes Extra) | [9 empty] | 628
HVAV NT Items
1 | Supply, Installation, testing & commissioning of Butterfly damper as per detail given. | Nos | [8 empty] | 1331
Consider Size per Nos
A | Material Consumed
a | Cost of 200mm dia butterfly damper | Nos | 1 |  |  |  |  | 0% | 1 | 937.5 | 937.5 | 1
| Sub Total -- A | [9 empty] | 937.5
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | [5 empty] | 1 | 125 | 125
| Sub Total -- B | [9 empty] | 125
C | Add for
a | Transportation | [7 empty] | @ | 4% | 37.5 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 28.125 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 10.625
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 19.0625
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 95.3125
D | Total -- D = A + B + C | [9 empty] | 1157.8125
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 173.6719
G | Total G = D + E + F per Nos | [9 empty] | 1331.4844
| Rate per Nos (Taxes Extra) | [9 empty] | 1331
2 | Supply, Installation, testing & commissioning Flexible duct as per detail given. | Rmt | [8 empty] | 1331
a | 200mm Dia
Consider Size per Rmt
A | Material Consumed
a | Cost of 200mm dia Flexible duct | Rmt | 1 |  |  |  |  | 0% | 1 | 937.5 | 937.5
| Sub Total -- A | [9 empty] | 937.5
B | Labour Deployed
a | Labour Charges for fixing | Rmt | 1 | [5 empty] | 1 | 125 | 125
| Sub Total -- B | [9 empty] | 125
C | Add for
a | Transportation | [7 empty] | @ | 4% | 37.5 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 28.125 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 10.625
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 19.0625
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 95.3125
D | Total -- D = A + B + C | [9 empty] | 1157.8125
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 173.6719
G | Total G = D + E + F per Rmt | [9 empty] | 1331.4844
| Rate per Rmt (Taxes Extra) | [9 empty] | 1331
2 | Supply, Installation, testing & commissioning Flexible duct as per detail given. | Rmt | [8 empty] | 3076
b | 400mm Dia
Consider Size per Rmt
A | Material Consumed
a | Cost of 400mm dia Flexible duct | Rmt | 1 |  |  |  |  | 0% | 1 | 2275 | 2275
| Sub Total -- A | [9 empty] | 2275
B | Labour Deployed
a | Labour Charges for fixing | Rmt | 1 | [5 empty] | 1 | 187.5 | 187.5
| Sub Total -- B | [9 empty] | 187.5
C | Add for
a | Transportation | [7 empty] | @ | 4% | 91 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 68.25 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 24.625
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 28.5938
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 212.4688
D | Total -- D = A + B + C | [9 empty] | 2674.9688
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 401.2453
G | Total G = D + E + F per Rmt | [9 empty] | 3076.2141
| Rate per Rmt (Taxes Extra) | [9 empty] | 3076
3 | Supply, Installation, testing & commissioning Mixing box as per detail given. | Nos | [8 empty] | 2747
a | 450x150x250mm
Consider Size per Nos
A | Material Consumed
a | Cost of 450x150x250 box | Nos | 1 |  |  |  |  | 0% | 1 | 1875 | 1875 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 1875
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | [5 empty] | 1 | 312.5 | 312.5
| Sub Total -- B | [9 empty] | 312.5
C | Add for
a | Transportation | [7 empty] | @ | 4% | 75 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 56.25 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 21.875
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 47.6562
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 200.7812
D | Total -- D = A + B + C | [9 empty] | 2388.2812
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 358.2422
G | Total G = D + E + F per Nos | [9 empty] | 2746.5234
| Rate per Nos (Taxes Extra) | [9 empty] | 2747
3 | Supply, Installation, testing & commissioning Mixing box as per detail given. | Nos | [8 empty] | 2514
b | 300x150x250mm
Consider Size per Nos
A | Material Consumed
a | Cost of 300x150x250 box | Nos | 1 |  |  |  |  | 0% | 1 | 1687.5 | 1687.5 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 1687.5
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | [5 empty] | 1 | 312.5 | 312.5
| Sub Total -- B | [9 empty] | 312.5
C | Add for
a | Transportation | [7 empty] | @ | 4% | 67.5 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 50.625 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 20
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 47.6562
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 185.7812
D | Total -- D = A + B + C | [9 empty] | 2185.7812
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 327.8672
G | Total G = D + E + F per Nos | [9 empty] | 2513.6484
| Rate per Nos (Taxes Extra) | [9 empty] | 2514
3 | Supply, Installation, testing & commissioning Mixing box as per detail given. | Nos | [8 empty] | 3181
c | 600x100x250mm
Consider Size per Nos
A | Material Consumed
a | Cost of 600x150x250 box | Nos | 1 |  |  |  |  | 0% | 1 | 2225 | 2225 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 2225
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | [5 empty] | 1 | 312.5 | 312.5
| Sub Total -- B | [9 empty] | 312.5
C | Add for
a | Transportation | [7 empty] | @ | 4% | 89 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 66.75 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 25.375
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 47.6562
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 228.7812
D | Total -- D = A + B + C | [9 empty] | 2766.2812
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 414.9422
G | Total G = D + E + F per Nos | [9 empty] | 3181.2234
| Rate per Nos (Taxes Extra) | [9 empty] | 3181
3 | Supply, Installation, testing & commissioning Mixing box as per detail given. | Nos | [8 empty] | 3445
d | 375x375x250mm
Consider Size per Nos
A | Material Consumed
a | Cost of 375x375x250 box | Nos | 1 |  |  |  |  | 0% | 1 | 2437.5 | 2437.5 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 2437.5
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | [5 empty] | 1 | 312.5 | 312.5
| Sub Total -- B | [9 empty] | 312.5
C | Add for
a | Transportation | [7 empty] | @ | 4% | 97.5 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 73.125 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 27.5
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 47.6562
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 245.7812
D | Total -- D = A + B + C | [9 empty] | 2995.7812
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 449.3672
G | Total G = D + E + F per Nos | [9 empty] | 3445.1484
| Rate per Nos (Taxes Extra) | [9 empty] | 3445
4 | Supply, Installation, testing & commissioning Diffusers-595x595, 375x375mm as per detail given. | Nos | [8 empty] | 3129
Consider Size per Nos
A | Material Consumed
a | Cost of diffuser | Nos | 1 |  |  |  |  | 0% | 1 | 2250 | 2250 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 2250
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | [5 empty] | 1 | 250 | 250
| Sub Total -- B | [9 empty] | 250
C | Add for
a | Transportation | [7 empty] | @ | 4% | 90 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 67.5 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 25
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 38.125
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 220.625
D | Total -- D = A + B + C | [9 empty] | 2720.625
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 408.0938
G | Total G = D + E + F per Nos | [9 empty] | 3128.7188
| Rate per Nos (Taxes Extra) | [9 empty] | 3129
5 | Supply & Hand fabrication at site, installation opf 24 Guage Fabrication Sheet as per detail given. | Smt | [8 empty] | 2213
Consider Size per Smt
A | Material Consumed
a | Cost of 24 guage sheet | Smt | 1 | 1 |  | 1 |  | 7% | 1.07 | 1225 | 1310.75 | * Purchase bill to be verified * Please check with Vendor the wastage is high (3% enough)
| Sub Total -- A | [9 empty] | 1310.75
B | Labour Deployed
a | Labour Charges for fixing | Smt | 1 | [5 empty] | 1 | 437.5 | 437.5
| Sub Total -- B | [9 empty] | 437.5
C | Add for
a | Transportation | [7 empty] | @ | 4% | 52.43 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 39.3225 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 17.4825
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 66.7188
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 175.9538
D | Total -- D = A + B + C | [9 empty] | 1924.2038
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 288.6306
G | Total G = D + E + F per Smt | [9 empty] | 2212.8343
| Rate per Smt (Taxes Extra) | [9 empty] | 2213
Electrical NT Items
1 | 3.5C x 120 Sq.mm. | Rmt | [8 empty] | 2005
Consider Size per Rmt
A | Material Consumed
a | Cost of 3.5C x 120 Sq.mm. | Rmt | 1 | 1 |  |  |  | 7% | 1.07 | 1081.25 | 1156.9375 | Please check with Vendor the cost is high, if cable is Aluminium armoured (as per market Polycab cable Rs.737/mtr) & wastage is high (3% enough)
| Sub Total -- A | [9 empty] | 1156.9375
B | Labour Deployed
a | Labour Charges for fixing | Rmt | 1 | [5 empty] | 1 | 425 | 425 | Please check with Vendor the Labour cost is high
| Sub Total -- B | [9 empty] | 425
C | Add for
a | Transportation | [7 empty] | @ | 4% | 46.2775 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 34.7081 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 15.8194
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 64.8125
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 161.6175
D | Total -- D = A + B + C | [9 empty] | 1743.555
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 261.5333
G | Total G = D + E + F per Rmt | [9 empty] | 2005.0883
| Rate per Rmt (Taxes Extra) | [9 empty] | 2005
A | 3.5C x 25 Sq.mm. | Rmt | [8 empty] | 993
Consider Size per Rmt
A | Material Consumed
a | Cost of 3.5C x 25 Sq.mm. | Rmt | 1 | 1 |  |  |  | 7% | 1.07 | 345 | 369.15 | Please check with Vendor the cost is high, if cable is Aluminium armoured (as per market Polycab cable Rs.215/mtr) & wastage is high (3% enough)
| Sub Total -- A | [9 empty] | 369.15
B | Labour Deployed
a | Labour Charges for fixing | Rmt | 1 | [5 empty] | 1 | 400 | 400 | Please check with Vendor the Labour cost is high
| Sub Total -- B | [9 empty] | 400
C | Add for
a | Transportation | [7 empty] | @ | 4% | 14.766 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 11.0745 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 7.6915
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 61
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 94.532
D | Total -- D = A + B + C | [9 empty] | 863.682
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 129.5523
G | Total G = D + E + F per Rmt | [9 empty] | 993.2343
| Rate per Rmt (Taxes Extra) | [9 empty] | 993
3 | 4C x 16 Sq.mm. | Rmt | [8 empty] | 750
Consider Size per Rmt
A | Material Consumed
a | Cost of 4C x 16 Sq.mm. | Rmt | 1 | 1 |  |  |  | 7% | 1.07 | 312.5 | 334.375 | Please check with Vendor the cost is high, if cable is Aluminium armoured (as per market Polycab cable Rs.186/mtr) & wastage is high (3% enough)
| Sub Total -- A | [9 empty] | 334.375
B | Labour Deployed
a | Labour Charges for fixing | Rmt | 1 | [5 empty] | 1 | 250 | 250 | Please check with Vendor the Labour cost is high
| Sub Total -- B | [9 empty] | 250
C | Add for
a | Transportation | [7 empty] | @ | 4% | 13.375 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 10.0312 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 5.8438
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 38.125
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 67.375
D | Total -- D = A + B + C | [9 empty] | 651.75
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 97.7625
G | Total G = D + E + F per Rmt | [9 empty] | 749.5125
| Rate per Rmt (Taxes Extra) | [9 empty] | 750
B | Making cable and terminations including brass single compression glands and crimping type copper lugs for cable sizes mentioned below for aluminium or copper. | Nos | [8 empty] | 1941
1 | 3.5C x 120 Sq.mm.
Consider Size per Nos
A | Material Consumed
a | Cost of 3.5C x 120 Sq.mm | Nos | 1 | [5 empty] | 1 | 1562.5 | 1562.5
| Sub Total -- A | [9 empty] | 1562.5
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | [5 empty] | 1 | 0 | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 62.5 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 46.875 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 15.625
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 125
D | Total -- D = A + B + C | [9 empty] | 1687.5
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 253.125
G | Total G = D + E + F per Nos | [9 empty] | 1940.625
| Rate per Nos (Taxes Extra) | [9 empty] | 1941
B | Making cable and terminations including brass single compression glands and crimping type copper lugs for cable sizes mentioned below for aluminium or copper. | Nos | [8 empty] | 621
2 | 3.5C x 25 Sq.mm.
Consider Size per Nos
A | Material Consumed
a | Cost of 3.5C x 25 Sq.mm | Nos | 1 | [5 empty] | 1 | 500 | 500
| Sub Total -- A | [9 empty] | 500
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | [5 empty] | 1 | 0 | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 20 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 15 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 5
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 40
D | Total -- D = A + B + C | [9 empty] | 540
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 81
G | Total G = D + E + F per Nos | [9 empty] | 621
| Rate per Nos (Taxes Extra) | [9 empty] | 621
B | Making cable and terminations including brass single compression glands and crimping type copper lugs for cable sizes mentioned below for aluminium or copper. | Nos | [8 empty] | 472
3 | 4C x 16 Sq.mm.
Consider Size per Nos
A | Material Consumed
a | Cost of 4C x 16 Sq.mm | Nos | 1 | [5 empty] | 1 | 380 | 380
| Sub Total -- A | [9 empty] | 380
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | [5 empty] | 1 | 0 | 0
| Sub Total -- B | [9 empty] | 0
C | Add for
a | Transportation | [7 empty] | @ | 4% | 15.2 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 11.4 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 3.8
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 0
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 30.4
D | Total -- D = A + B + C | [9 empty] | 410.4
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 61.56
G | Total G = D + E + F per Nos | [9 empty] | 471.96
| Rate per Nos (Taxes Extra) | [9 empty] | 472
C | Providing and fixing in position the following GI RIGID conduits including all accessories concealed in F. ceiling/wall/floor as required including pull boxes with 3mm thick perspex sheet cover plate complete with 1.6 mm dia. G.I. pull wires in the length of conduit. -32 mm dia GI Conduit | Rmt | [8 empty] | 540
Consider Size per Rmt
A | Material Consumed
a | Cost of 32mm GI Conduit | Rmt | 1 | 1 |  |  |  | 7% | 1.07 | 356.25 | 381.1875
| Sub Total -- A | [9 empty] | 381.1875
B | Labour Deployed
a | Labour Charges for fixing | Rmt | 1 | 1 |  |  |  |  | 1 | 50 | 50
| Sub Total -- B | [9 empty] | 50
C | Add for
a | Transportation | [7 empty] | @ | 4% | 15.2475 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 11.4356 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 4.3119
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 7.625
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 38.62
D | Total -- D = A + B + C | [9 empty] | 469.8075
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 70.4711
G | Total G = D + E + F per Rmt | [9 empty] | 540.2786
| Rate per Rmt (Taxes Extra) | [9 empty] | 540
D | DB Enclosure & Dimmer Controller
1 | Supply & installation of Metal Enclosure box with wire connector for modification of existing DB as per detail given. | Nos | [8 empty] | 2240
Consider Size per Nos
A | Material Consumed
a | Cost of Metal box with wire | Nos | 1 |  |  |  |  | 0% | 1 | 1750 | 1750 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 1750
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | 1 |  |  |  |  | 1 | 50 | 50
| Sub Total -- B | [9 empty] | 50
C | Add for
a | Transportation | [7 empty] | @ | 4% | 70 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 52.5 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 18
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 7.625
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 148.125
D | Total -- D = A + B + C | [9 empty] | 1948.125
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 292.2188
G | Total G = D + E + F per Nos | [9 empty] | 2240.3438
| Rate per Nos (Taxes Extra) | [9 empty] | 2240
2 | Supply & installation of Enclosure box for light dimmer controller as per detail given. | Nos | [8 empty] | 3129
Consider Size per Nos
A | Material Consumed
a | Cost of light dimmer Enclosure box controller | Nos | 1 |  |  |  |  | 0% | 1 | 2250 | 2250 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 2250
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | 1 |  |  |  |  | 1 | 250 | 250
| Sub Total -- B | [9 empty] | 250
C | Add for
a | Transportation | [7 empty] | @ | 4% | 90 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 67.5 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 25
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 38.125
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 220.625
D | Total -- D = A + B + C | [9 empty] | 2720.625
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 408.0938
G | Total G = D + E + F per Nos | [9 empty] | 3128.7188
| Rate per Nos (Taxes Extra) | [9 empty] | 3129
3 | Supply & Installation of Light Dimmer Controller with Enclosuer box as per detail given. | Nos | [8 empty] | 3206
Consider Size per Nos
A | Material Consumed
a | Cost of light dimmer controller | Nos | 1 |  |  |  |  | 0% | 1 | 2312.5 | 2312.5 | Purchase bill to be verified
| Sub Total -- A | [9 empty] | 2312.5
B | Labour Deployed
a | Labour Charges for fixing | Nos | 1 | 1 |  |  |  |  | 1 | 250 | 250
| Sub Total -- B | [9 empty] | 250
C | Add for
a | Transportation | [7 empty] | @ | 4% | 92.5 | Please check with Vendor the cost is high
b | Loading/Unloading & lifting | [7 empty] | @ | 3% | 69.375 | Please check with Vendor the cost is high
c | Scaffolding | [7 empty] | @ |  | 0
d | Material Handling Charges | [7 empty] | @ | 0% | 0 | Please check with Vendor the cost is high
e | Water & Electricity (DG )charges | [7 empty] | @ | 0% | 0
f | HSE | [7 empty] | @ | 1% | 25.625
g | PF & ESIC ( 12% +3.25% on 33% or Labour ) | [7 empty] | @ | 15.25% | 38.125
h | Tool & Plants | [7 empty] | @ | 0% | 0
| Sub Total -- C | [9 empty] | 225.625
D | Total -- D = A + B + C | [9 empty] | 2788.125
E | Taxes on 'D'
a | Overheads | [7 empty] | @ | 0% | 0
| Sub Total -- E | [9 empty] | 0
F | Profit, On D + E | [7 empty] | @ | 15% | 418.2188
G | Total G = D + E + F per Nos | [9 empty] | 3206.3438
| Rate per Nos (Taxes Extra) | [9 empty] | 3206
0
[6 empty] | 0.1 | 0 | 145 | 0
[6 empty] | 0.15 | 0 | 55 | 0
[6 empty] | 0.07 | 0 | 45 | 0
[6 empty] | 0.07 | 0 | 280 | 0
[6 empty] | 0.07 | 0 | 280 | 0
[7 empty] | 0 | 50 | 0
[7 empty] | 0 | 150 | 0
0
[7 empty] | 0 | 40 | 0
[7 empty] | 0 | 100 | 0
[7 empty] | 0 | 100 | 0
[7 empty] | 0 | 350 | 0
[7 empty] | 0 | 240 | 0
0
[7 empty] | @ | 0.04 | 0
[7 empty] | @ | 0.03 | 0
[7 empty] | @ |  | 0
[7 empty] | @ | 0.05 | 0
[7 empty] | @ | 0 | 0
[7 empty] | @ | 0.01 | 0
[7 empty] | @ | 0.1525 | 0
[7 empty] | @ | 0.02 | 0
0
0
[7 empty] | @ | 0.05 | 0
0
[7 empty] | @ | 0.15 | 0
0
0
0
[6 empty] | 0.1 | 0 | 145 | 0
[6 empty] | 0.1 | 0 | 145 | 0
[6 empty] | 0.15 | 0 | 55 | 0
[6 empty] | 0.07 | 0 | 45 | 0
[6 empty] | 0.07 | 0 | 45 | 0
[6 empty] | 0.07 | 0 | 280 | 0
[6 empty] | 0.07 | 0 | 280 | 0
[6 empty] | 0 | 0 | 180 | 0
[7 empty] | 0 | 50 | 0
[7 empty] | 0 | 150 | 0
0
[7 empty] | 0 | 50 | 0
[7 empty] | 0 | 50 | 0
[7 empty] | 0 | 50 | 0
[7 empty] | 0 | 120 | 0
[7 empty] | 0 | 100 | 0
[7 empty] | 0 | 350 | 0
[7 empty] | 0 | 240 | 0
0
[7 empty] | @ | 0.04 | 0
[7 empty] | @ | 0.03 | 0
[7 empty] | @ |  | 0
[7 empty] | @ | 0.05 | 0
[7 empty] | @ | 0 | 0
[7 empty] | @ | 0.01 | 0
[7 empty] | @ | 0.1525 | 0
[7 empty] | @ | 0.02 | 0
0
0
[7 empty] | @ | 0.05 | 0
0
[7 empty] | @ | 0.15 | 0
0
0