## Summary
Summary Sheet - Plumbing Work
B03 &B04-Cafeccino, T3, Lucknow Airport
PO | Semolina/PO/23-24/000221
S.NO. | Item description | PO AMOUNT(INR) | Variation | Total Billed | RA-01 | Final Bill
|  | Amount ( INR ) | Amount ( INR ) | Amount ( INR ) | Amount ( INR ) | Amount ( INR )
1 | Plumbing Work | 56200 | -7450 | 48750 | 2550 | 46200
| SUB -TOTAL | 56200 | -7450 | 48750 | 2550 | 46200
| GST 18 % | 10116 | -1341 | 8775 | 459 | 8316
| G.TOTAL | 66316 | -8791 | 57525 | 3009 | 54516

## Abtract
LKN_B03&B04_Cafeccino_ Plumbing Work
SR. NO. | Material | Item description | PO |  |  |  | RA -01 |  | Final Bill
|  |  | Unit | Qty | Rate | Amount | Qty | Amount | Qty | Amount
[6 empty] | 56200 |  | 2550 |  | 46200
1 |  | WATER SUPPLY PIPES
| CPVC Pipes | Supply, laying, testing & commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia. (Make – SUPREME / KASTA) including all necessary fitting as per site.
1.01 |  | 15mm dia | R.M. |  | 50 | 0
1.02 |  | 20mm dia | R.M. | 30 | 75 | 2250 | 28 | 2100
1.03 |  | 25mm dia | R.M. |  | 125 | 0
| TOTAL |  |  |  |  | 2250 |  | 2100 |  | 0
2 |  | WATER DRAIN PIPES
| UPVC WASTE PIPE | UPVC Pipe for Drainage (Make – SUPREME / KASTA) including all necessary fitting as per site.
2.01 |  | 150mm dia | R.M. |  | 950 | 0
2.02 |  | 100mm dia | R.M. |  | 450 | 0
2.03 |  | 75mm dia | R.M. |  | 250 | 0
2.04 |  | 50mm dia | R.M. | 15 | 150 | 2250 | 3 | 450
| TOTAL |  |  |  |  | 2250 |  | 450 |  | 0
3 |  | CHAMBER & GRATING
3.01 | INSPECTION CHAMBER | Supply, Laying, Testing & Commissioning of Approved SS Inspection Chamber along of Size- 300mmx300mm with SS Cover & SS Grating over it. Make Jaquar / Ozone. Including trenching and finishing with ceramic tiles as per dwg and details. | Nos. |  | 5000 | 0
3.02 | OPEN GRATING | Providing & Fixing 20mm heavy quality SS triple layer Grating along with Perforated Mesh & Angle Frame of width 200mm, complete as per detail Drawings. Rate inclusive of chamber construction
|  | Size - 560mm x 200mm | R.M. |  | 4500 | 0
|  | Size - 1000mm x 200mm | R.M. |  | 6000 | 0
| TOTAL |  |  |  |  | 0 |  | 0 |  | 0
4 |  | FLOOR TRAP
4.01 | FLOOR TRAP | Supply, Laying, Testing & Commissioning of 75x75mm Floor Trap with Approved Make heavy duty round or Square. | Nos. | 1 | 3500 | 3500
| TOTAL |  |  |  |  | 3500 |  | 0 |  | 0
5 |  | VALVE AND TAP
5.01 | ANGLE VALVE | Providing & Fixing Angle Valve with connector pipe. | Nos. | 7 | 1000 | 7000 |  |  | 5 | 5000
5.02 | LONG BODY TAP | Providing & Fixing Sink Cock. with foot operated | Nos. |  | 4500 | 0
5.03 | Table Mixer | Providing & Fixing Sink Cock. | Nos. | 1 | 2500 | 2500 |  |  | 1 | 2500
5.04 | Gate Valves | Providing & Fixing PPR Ball Valve ISI mark. (For Inlet) | Nos. | 1 | 1200 | 1200 |  |  | 1 | 1200
| TOTAL |  |  |  |  | 10700 |  | 0 |  | 8700
6 |  | ACCESSORIES
6.01 | Grease Trap | Providing & Fixing of portable grease trap NGT-14 from Nugreen | Nos. |  | 35000 | 0
6.02 | Grease Trap | Providing & Fixing of portable grease trap NGT-50 from Nugreen | Nos. |  | 35000 | 0
6.03 | Bottle Trap | Providing & fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR / OZONE) | Nos. |  | 1500 | 0
6.04 | Water Meter digital display | 25mm Dia Water meter - Kent/Marshal/Dashmesh | Nos. | 1 | 3000 | 3000 |  |  | 1 | 3000
6.05 | GEYSER | 6 LITER GEYSER | Nos. | 1 | 7500 | 7500 |  |  | 1 | 7500
6.06 | GEYSER | 35 LITER GEYSER | Nos. |  | 21000 | 0
6.07 | Waste Coupling | Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. | Nos. |  | 850 | 0
6.08 | Water supply connection | water supply connection taken from existing point complete with all necessary fittings. | Nos. | 1 | 3500 | 3500 |  |  | 1 | 3500
6.09 | Drainage connection | Drainage connection connect to existing drain point complete with all necessary fittings including cleanout plug | Nos. | 1 | 3500 | 3500 |  |  | 1 | 3500
6.1 | Pressure Pump | Pressure Pump | Nos. |  | 5000 | 0
6.11 | RO Plant | Providing and fixing of RO Plant on MS platform with all necessary valves and fiting required. | Nos. |  | 45000 | 0
6.12 | Domestic RO | Providing and fixing of Domestic RO with water storage with all necessary valves and fiting required. | Nos. | 1 | 20000 | 20000 |  |  | 1 | 20000
6.13 | Water Tank | Providing and fixing of 200 Ltr. Storage Loft Tank on MS Platform with all necessary valves and fiting required. | Nos. |  | 3000 | 0
6.14 | Trench (125 mm wide) | Making 125 mm wide 300 mm deep trench with 4" thk. Block wall on both side of trench. Floor & inner surfaces of walls to be finished with plaster followed with 12mm ceramic tiles. Top of the trench to be covered with floor tile fixed inside L-angle frame placed over another L-angle which is fixed on trench top, complete as per dwg/details. Rate inclusive of making trench, providing finish tiles & top tiles in frame. | RMT | 0 | 2500
| TOTAL |  |  |  |  | 37500 |  | 0 |  | 37500

## JMR
LKN_B03&B04_Cafeccino_ Plumbing Work |  |  |  |  | Joint Measurement Report
SR. NO. | Material | Item description | PO |  | RA -01 | Final Bill
|  |  | Unit | Qty | Approved Qty | Approved Qty
1 |  | WATER SUPPLY PIPES
| CPVC Pipes | Supply, laying, testing & commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia. (Make – SUPREME / KASTA) including all necessary fitting as per site.
1.01 |  | 15mm dia | R.M.
1.02 |  | 20mm dia | R.M. | 30 | 28
1.03 |  | 25mm dia | R.M.
2 |  | WATER DRAIN PIPES
| UPVC WASTE PIPE | UPVC Pipe for Drainage (Make – SUPREME / KASTA) including all necessary fitting as per site.
2.01 |  | 150mm dia | R.M.
2.02 |  | 100mm dia | R.M.
2.03 |  | 75mm dia | R.M.
2.04 |  | 50mm dia | R.M. | 15 | 3
3 |  | CHAMBER & GRATING
3.01 | INSPECTION CHAMBER | Supply, Laying, Testing & Commissioning of Approved SS Inspection Chamber along of Size- 300mmx300mm with SS Cover & SS Grating over it. Make Jaquar / Ozone. Including trenching and finishing with ceramic tiles as per dwg and details. | Nos.
3.02 | OPEN GRATING | Providing & Fixing 20mm heavy quality SS triple layer Grating along with Perforated Mesh & Angle Frame of width 200mm, complete as per detail Drawings. Rate inclusive of chamber construction
|  | Size - 560mm x 200mm | R.M.
|  | Size - 1000mm x 200mm | R.M.
4 |  | FLOOR TRAP
4.01 | FLOOR TRAP | Supply, Laying, Testing & Commissioning of 75x75mm Floor Trap with Approved Make heavy duty round or Square. | Nos. | 1
5 |  | VALVE AND TAP
5.01 | ANGLE VALVE | Providing & Fixing Angle Valve with connector pipe. | Nos. | 7 |  | 5
5.02 | LONG BODY TAP | Providing & Fixing Sink Cock. with foot operated | Nos.
5.03 | Table Mixer | Providing & Fixing Sink Cock. | Nos. | 1 |  | 1
5.04 | Gate Valves | Providing & Fixing PPR Ball Valve ISI mark. (For Inlet) | Nos. | 1 |  | 1
6 |  | ACCESSORIES
6.01 | Grease Trap | Providing & Fixing of portable grease trap NGT-14 from Nugreen | Nos.
6.02 | Grease Trap | Providing & Fixing of portable grease trap NGT-50 from Nugreen | Nos.
6.03 | Bottle Trap | Providing & fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR / OZONE) | Nos.
6.04 | Water Meter digital display | 25mm Dia Water meter - Kent/Marshal/Dashmesh | Nos. | 1 |  | 1
6.05 | GEYSER | 6 LITER GEYSER | Nos. | 1 |  | 1
6.06 | GEYSER | 35 LITER GEYSER | Nos.
6.07 | Waste Coupling | Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. | Nos.
6.08 | Water supply connection | water supply connection taken from existing point complete with all necessary fittings. | Nos. | 1 |  | 1
6.09 | Drainage connection | Drainage connection connect to existing drain point complete with all necessary fittings including cleanout plug | Nos. | 1 |  | 1
6.1 | Pressure Pump | Pressure Pump | Nos.
6.11 | RO Plant | Providing and fixing of RO Plant on MS platform with all necessary valves and fiting required. | Nos.
6.12 | Domestic RO | Providing and fixing of Domestic RO with water storage with all necessary valves and fiting required. | Nos. | 1 |  | 1
6.13 | Water Tank | Providing and fixing of 200 Ltr. Storage Loft Tank on MS Platform with all necessary valves and fiting required. | Nos.
6.14 | Trench (125 mm wide) | Making 125 mm wide 300 mm deep trench with 4" thk. Block wall on both side of trench. Floor & inner surfaces of walls to be finished with plaster followed with 12mm ceramic tiles. Top of the trench to be covered with floor tile fixed inside L-angle frame placed over another L-angle which is fixed on trench top, complete as per dwg/details. Rate inclusive of making trench, providing finish tiles & top tiles in frame. | RMT | 0