## PI
DAYSPRING ENTERPRISES
B/14, HAPPY HOME APTS, OPP. SWEEKAR HOTEL
SAIBABA NAGAR, BORIVLI (WEST), MUMBAI - 400 092
Contact no: +91 98202 30523 Email : dayspringent@gmail.com
Proforma Invoice for Irish House Kitchen Work
To, | Simolina Kitchen Pvt. Ltd. |  | Date |  | 2024-12-19
Lucknow Airport terminal -3 , Irish House Kitchen
Kindly Attn.:- Mr. Irfaan
Sr. No. | Category | Description | Unit | QTY | Rate | Amount
1 |  | Irish House Kitchen work RA-1st Bill | nos | 1 | 324012.0578 | 324012.0578
[5 empty] | Basic Total | 324012.0578
[5 empty] | Add GST @ 18% | 58322.1704
[5 empty] | Grand Total | 382334.2283
For DAYSPRING ENTERPRISES
Authorised Signatory

## Abstract
Bill Of Quantites
Sr No | Item Description | As Per Boq |  |  |  | QTY |  |  | AMOUNT |  |  | Remarks
|  | UOM | Qty. | Rate | Amount | Previous | This Bill | Up To Date | Previous | This Bill | Up To Date
1 | ANTI TERMITE TREATMENT ALL MOH and FOH Providing and doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 inch in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 ft center to center barrier all over as per manufacturer specification and ISI standards. ( OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | Sq.m. | 28 | 240 | 6720 |  | 27.0524 | 27.0524 |  | 6492.5856 | 6492.5856
2 | CIVIL WORK WATERPROOFING Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. 1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush and Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions and on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface and Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope and main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring | Sq.m. | 55 | 950 | 52250 |  | 51.2644 | 51.2644 |  | 48701.1562 | 48701.1562
3 | Flex on glass - Flex on glass from airo bridge side as per approved airport guidelines. Actual measurements to be taken at site before executing. Size 21 ft *12 ft = 252 | Sq. ft | 252 | 35 | 8820
4 | Block WORK 100 MM THICK BLOCK MASONARY Providing and Laying of block masonry of thickness 100mm in super structure, bund wall, in raised MOH counter area using cement mortar 1 4 (1 cement 4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. | Sq.m. | 70 | 1450 | 101500 |  | 62.97 | 62.97 |  | 91306.5 | 91306.5
5 | PLASTER - P L12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 155 | 550 | 85250 |  | 114.3574 | 114.3574 |  | 62896.57 | 62896.57
6 | RCC LINTEL BEAM - P L in place (cast in situ) RCC lintel beams in 100mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1 4 8) 100mm high with 4 no. ft s 8mm th. Steel bars as per general specifications, complete in all respects | Rm | 60 | 1250 | 75000 |  | 45.162 | 45.162 |  | 56452.5 | 56452.5
7 | Board out with flex - Providing and fixing barricaded work with 12mm thick commecial ply board with 50*50 mm wooden batten and all necessary fixing arrangement with door as required, its including flex printing as per approved airport guidelines and existing board out to be modified removed. Left side size - 16 ft *12 ft =192 (Passage area boardout). actual measurements to be taken at site before executing. | Sq. ft | 192 | 90 | 17280 |  | 0 |  |  | 0 | 0
8 | CINDER LIGHT WT. SIPORAX BLOCK BATS FILLING MOH RAISED AREA (up to 200 mm) Providing and Filling light wt. Siporex block bats to conceal drainage and plumbing lines. The Top layer should be finished properly to receive P .C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect . | Sq.m. | 40 | 1450 | 58000 |  | 27.0524 | 27.0524 |  | 39226.038 | 39226.038
9 | PCC LAYER - Providing and Laying P.C.C 1 3 6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 40 | 700 | 28000 |  | 27.0524 | 27.0524 |  | 18936.708 | 18936.708
| Total |  |  |  | 432820 |  |  |  | 0 | 324012.0578 | 324012.0578
| GSt 18% |  |  |  | 77907.6 |  |  |  | 0 | 58322.1704 | 58322.1704
| G.total |  |  |  | 510727.6 |  |  |  | 0 | 382334.2283 | 382334.2283

## MB
MB SHEET
Project -Irish House kitchen Dom Airport terminal-3 (Lucknow)
Sr No | Item Name | UOM | Boq Qty | No. | Length | Width | Height | Total | Remarks
1 | ANTI TERMITE TREATMENT ALL MOH and FOH Providing and doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 inch in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 ft center to center barrier all over as per manufacturer specification and ISI standards. ( OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | Sq.m. | 28
| Floor area |  |  | 1 | 4.47 | 6.052 |  | 27.0524
| Total Qty | Sqm | [5 empty] | 27.0524
| Previous Qty | Sqm | [5 empty] | 0
| This Bill Qty | Sqm | [5 empty] | 27.0524
2 | CIVIL WORK WATERPROOFING Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. 1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush and Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions and on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface and Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope and main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring | Sq.m. | 55
| Floor area | Sqm |  | 1 | 4.47 | 6.052 |  | 27.0524
| Back wall glass side | Sqm |  | 1 | 6.052 |  | 0.615 | 3.722
| Right side cooridor | Sqm |  | 2 | 4.535 |  | 0.615 | 5.5781
| Both side bond room | Sqm |  | 2 | 2.55 |  | 0.615 | 3.1365
| small wall | Sqm |  | 2 | 0.9 |  | 0.615 | 1.107
| small wall | Sqm |  | 2 | 0.62 |  | 0.615 | 0.7626
| Wall Face With all the wall side | Sqm |  | 3 | 0.12 |  | 0.615 | 0.2214
| Irish wall only one side | Sqm |  | 1 | 3.435 |  | 0.615 | 2.1125
| irish wall partation for idli.com | Sqm |  | 2 | 6.156 |  | 0.615 | 7.5719
| Total Qty | Sqm | [5 empty] | 51.2644
| Previous Qty | Sqm | [5 empty] | 0
| This Bill Qty | Sqm | [5 empty] | 51.2644
3 | Flex on glass - Flex on glass from airo bridge side as per approved airport guidelines. Actual measurements to be taken at site before executing. Size 21 ft *12 ft = 252 | Sq. ft | 252
4 | Block WORK 100 MM THICK BLOCK MASONARY Providing and Laying of block masonry of thickness 100mm in super structure, bund wall, in raised MOH counter area using cement mortar 1 4 (1 cement 4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. | Sq.m. | 70
| Back wall Glass wall | Sqm |  | 1 | 6.05 |  | 2.8 | 16.94
| Right side cooridor | Sqm |  | 1 | 4.535 |  | 3.2 | 14.512
| Bond room | Sqm |  | 1 | 2.55 |  | 3 | 7.65
| Small wall bond room | Sqm |  | 1 | 1.85 |  | 3 | 5.55
| small wall | Sqm |  | 1 | 0.615 |  | 3 | 1.845
| Partation wall irish and idli.com | Sqm |  | 1 | 6.156 |  | 3 | 18.468
| Dudection of door | Sqm |  | -1 | 0.95 |  | 2.1 | -1.995
| Total Qty | Sqm | [5 empty] | 62.97
| Previous Qty | Sqm | [5 empty] | 0
| This Bill Qty | Sqm | [5 empty] | 62.97
5 | PLASTER - P L12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 155
| Back side Glass wall | Sqm |  | 1 | 6.05 |  | 2.8 | 16.94
| Idli .com side wall | Sqm |  | 2 | 4.535 |  | 3.2 | 29.024
| Centre wall | Sqm |  | 2 | 2.55 |  | 3 | 15.3
| Coridor side wall | Sqm |  | 2 | 1.85 |  | 3 | 11.1
| Irish house wall plaster | Sqm |  | 2 | 0.615 |  | 3 | 3.69
| small wall | Sqm |  | 2 | 6.156 |  | 3.2 | 39.3984
| wall face | Sqm |  | 3 | 0.1 |  | 3 | 0.9
| Dudection of door | Sqm |  | -1 | 0.95 |  | 2.1 | -1.995
| Total Qty | Sqm | [5 empty] | 114.3574
| Previous Qty | Sqm | [5 empty] | 0
| This Bill Qty | Sqm | [5 empty] | 114.3574
6 | RCC LINTEL BEAM - P L in place (cast in situ) RCC lintel beams in 100mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1 4 8) 100mm high with 4 no. ft s 8mm th. Steel bars as per general specifications, complete in all respects | Rm | 60
| Glass wall | Rmt |  | 2 | 6.05 |  |  | 12.1
| Idli .com side wall | Rmt |  | 2 | 4.535 |  |  | 9.07
| Centre wall | Rmt |  | 2 | 2.55 |  |  | 5.1
| Coridor side wall | Rmt |  | 2 | 1.85 |  |  | 3.7
| small wall | Rmt |  | 2 | 0.615 |  |  | 1.23
| small wall | Rmt |  | 2 | 6.156 |  |  | 12.312
| Window Lintel | Rmt |  | 1 | 0.6 |  |  | 0.6
| Door Lintel | Rmt |  | 1 | 1.05 |  |  | 1.05
| Total Qty | Rmt | [5 empty] | 45.162
| Previous Qty | Rmt | [5 empty] | 0
| This Bill Qty | Rmt | [5 empty] | 45.162
7 | Board out with flex - Providing and fixing barricaded work with 12mm thick commecial ply board with 50*50 mm wooden batten and all necessary fixing arrangement with door as required, its including flex printing as per approved airport guidelines and existing board out to be modified removed. Left side size - 16 ft *12 ft =192 (Passage area boardout). actual measurements to be taken at site before executing. | Sq. ft | 192
8 | CINDER LIGHT WT. SIPORAX BLOCK BATS FILLING MOH RAISED AREA (up to 200 mm) Providing and Filling light wt. Siporex block bats to conceal drainage and plumbing lines. The Top layer should be finished properly to receive P .C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect . | Sq.m. | 40
| Floor area |  |  | 1 | 4.47 | 6.052 |  | 27.0524
| Total Qty | Sqm | [5 empty] | 27.0524
| Previous Qty | Sqm | [5 empty] | 0
| This Bill Qty | Sqm | [5 empty] | 27.0524
9 | PCC LAYER - Providing and Laying P.C.C 1 3 6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 40
| Floor area |  |  | 1 | 4.47 | 6.052 |  | 27.0524
| Total Qty | Sqm | [5 empty] | 27.0524
| Previous Qty | Sqm | [5 empty] | 0
| This Bill Qty | Sqm | [5 empty] | 27.0524