## Summary Sheet
Summary Sheet Mumbai Joshh T2 csmia
Semolina Project Pvt Ltd. | [5 empty] | Date :- 08-11-2024
Vendor Name : Intercare Enterprise
PO No: Semolina/PO/24-25/000692
Sr no | Description | PO value | Previous Bill Amount | Present RA Bill-1 Amount | Cumulative Amount | Variance Amount
1 | Plumbing Work | 155305.09 | 0 | 56020.92 | 56020.92 | 99284.17
2 | Electric Work | 209724.85 | 0 | 170085.67 | 170085.67 | 39639.18
3 | Civil & Interior Work | 1985186.62 | 0 | 1130605.9397 | 1130605.9397 | 854580.6803
| Total Amount (Without GST) | 2350216.56 |  | 1356712.5297 | 1356712.5297 | 993504.0303
| GST 18 % | 423038.9808 |  | 244208.2553 | 244208.2553 | 178830.7255
Gross Total Amount |  | 2773255.5408 |  | 1600920.785 | 1600920.785 | 1172334.7558

## Abstract Sheet
RA-01 - Abstract
WO No :-Semolina/PO/24-25/000692 | [6 empty] | Date:- 08-11-2024
Joshh Revamp
RA1 BILL OF INTERIOR WORK PROJECT : JOSHH @ MUMBAI AIRPORT T2 | [6 empty] | RA - 1 (Current Bill) |  | Variation |  | Remarks
SR. NO. | MATERIAL | DESCRIPTION | UNIT | PO QTY. | PO RATE | PO AMOUNT | QTY | AMOUNT (Rs) | QTY | AMOUNT (Rs)
1 | WATER SUPPLY PIPING - | WATER SUPPLY PIPING - CPVC Pipes conforming to ASTM D-2846, SDR-11 grade and CPVC solvent weld fittings like elbows, tees, couplers, brass threaded adapters, insert ring etc. suitable for (domestic flushing and hot water) applications rated, concealed piping within wall floor including jointing with fittings using solvent cement ,brass threaded end fittings for making connection to fixtures. The work shall also include chasing the walls with machine wherever required for concealed piping and making good the same after laying of pipes necessary pressure testing Chasing finishing shall be done with 1 1 cement mixed mortar, restore the same original condition for internal and shaft piping, including necessary hot deep galvanized supports vertical horizontal, as per direction of Site in charge direction. The rate shall include supply of S. S. screws and nut bolts etc. chasing in walls done by machine Make - Supreme, Prince, Astral , Ashirvad
2 |  | 20 mm Dia | R.mt | 35 | 443.31 | 15515.85 | 35 | 15515.85 | 0 | 0 | 100% Claimed in RA Bill 1
3 |  | 25 mm Dia | R.mt | 5 | 459.73 | 2298.65 | 5 | 2298.65 | 0 | 0 | 100% Claimed in RA Bill 1
4 | Ball Valves | Providing Fixing of gun metal heavy approved make Ball Valves screwed type for water system of the following diameters(10Kg Sq.cm). Valve shall have with unions. Make - Zoloto, Danfos, KSB, Audco India |  |  |  | 0 |  | 0 | 0 | 0
5 |  | 20mm Dia | Nos | 3 | 1970.25 | 5910.75 | 2 | 3940.5 | -1 | -1970.25 | 67% Claimed in RA Bill 1
6 |  | 25mm Dia | Nos | 1 | 2134.44 | 2134.44 | 1 | 2134.44 | 0 | 0 | 100% Claimed in RA Bill 1
7 | Water Meter | Providing ,fixing, testing and commissioning capstan make Water Meter including providing fixing matching Isolation valves ,strainer, non-return valve,complete with all necessary fittings etc screwed type(15Kgs Sq.cm). Valve shall have with union. 25 mm Dia incoming line (Optional) Make- Capstan | Nos | 1 | 8209.38 | 8209.38 | 1 | 8209.38 | 0 | 0 | 100% Claimed in RA Bill 1
8 | Electric Hot Water Generator | Supply, installation,testing commissioning of Storage Type Electric Hot Water Generator of mentioned capacity , suitable for 3 KG cm2 pressure, Wall Mounted Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories (Optional in pantry) 20 L Capacity ( Optional -Subject to requirement from Kitchen consultant) Make- Racold, Jauqar | Nos | 1 | 12970.81 | 12970.81 | 0 | 0 | -1 | -12970.81 | 0% Claimed in RA Bill 1
9 | RO system | Supply, installation, testing and commissioning of standalone RO system -10-12 lit ( Optional) Make - LG Kent Alfa Iron Exchange | Nos | 1 | 15597.81 | 15597.81 | 0 | 0 | -1 | -15597.81 | 0% Claimed in RA Bill 1
10 |  | DRAINAGE |  | 0 | 0 | 0 |  | 0 | 0 | 0
11 | UPVC Type B pipe | UPVC Type B pipe confirming to IS 13592 (6 Kg CM2) for Soil, Waste upto 65mm dia. confirming to IS 13592 and PVC Agriculture 6kg Pipe for Soil, Waste above 65mm dia including all necessary fittings and specials such as as 45 or 90 deg. bends, Tee s, Y s, `P trap, NT (as required) access pipe with solvant cement jointing. Make - Supreme, Prince, Astral , Ashirvad |  | 0 | 0 | 0 |  | 0 | 0 | 0
12 |  | 50mm Dia | R.mt | 5 | 1083.64 | 5418.2 | 5 | 5418.2 | 0 | 0 | 100% Claimed in RA Bill 1
13 |  | 75mm Dia | R.mt | 12 | 1280.66 | 15367.92 | 11.5 | 14727.59 | -0.5 | -640.33 | 96% Claimed in RA Bill 1
14 |  | 100 mm Dia | R.mt | 12 | 1444.85 | 17338.2 | 1 | 1444.85 | -11 | -15893.35 | 8% Claimed in RA Bill 1
15 | Multi floor Traps | Supply, Install multi floor Traps including fixing with necessary consumables with Circular SS Grating with anti cockroach jali Suitable for taking 40mm Dia 50mm Dia Back Inlet Connection with 75mm Dia outlet make - Supreme, Prince, Astral , Ashirvad | Nos | 2 | 886.61 | 1773.22 | 2 | 1773.22 | 0 | 0 | 100% Claimed in RA Bill 1
16 |  | Supply, Install CLEAN OUT PLUGS - 75mm Dia | Nos | 1 | 558.24 | 558.24 | 1 | 558.24 | 0 | 0 | 100% Claimed in RA Bill 1
17 |  | Supply, Install Grease trap of nugreen make NGT-30 . Shall be order based on the space available below sink. | Nos | 2 | 26105.81 | 52211.62 | 0 | 0 | -2 | -52211.62 | 0% Claimed in RA Bill 1
18 |  | NOTES 1. TAXES DUTIES shall be Extra as actual 2. kKitchen and Bar Gratings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Grand Total Amount |  |  | 155305.09 |  | 56020.92 |  | -99284.17
Electrical Work :
19 |  | DISTRIBUTION SWITCHGEAR
20 |  | Supply, installation, testing commissioning of Distribution Boards surface or flush mounted with Double door containing MCB or ELMCB as incomer and SPMCB as outgoing. All MCBs are of 10KA breaking capacity and ELMCBs or RCCB should be of 30mA or 100 or 300 mA sensivity. The DB shall have appropriate no. of top and bottom knock outs for outgoing circuits and shall be complete with necessary busbars, interconnection terminals and earth studs. All terminations in DB shall be complete with ferulling, dressing and all circuits shall be properly labeled with PVC strip (sticker type) having identification as per the final approval of Consultant. For UPS DB MCB shall be D type and other MCBs shall be C category for lighting and raw power DB. Lighting power DB - VTPN DB 12 way VTPN DB I or C- 80A FP RCBO, 100mA -1 Nos O or G -5 # 16 or 20 or 32A TP MCB O or G -21 # 10 or 16 or 20A SP MCB | Nos | 1 | 34706.93 | 34706.93 | 1 | 34706.93 | 0 | 0 | 100% Claimed in RA Bill 1
21 |  | Supply, installation, testing commissioning of Switchgears. (Standard Product) |  |  | 0 | 0 |  | 0 | 0 | 0
22 |  | 63 amps 4P MCB with 63A 5 Pin Ray Roll Socket complete with all mounting accessories – for Kitchen Legrand make | Nos | 1 | 3330.46 | 3330.46 | 0.5 | 1665.23 | -0.5 | -1665.23 | 50% Claimed in RA Bill 1
23 |  | 32A Rey roll socket complete with 32 amps SPMCB with 3 pin metal clad socket - Legrand make Model No. 6078 41 - kitchen power | Nos | 4 | 2278.73 | 9114.92 | 2 | 4557.46 | -2 | -4557.46 | 50% Claimed in RA Bill 1
24 |  | 16A Rey roll socket complete with 16 amps SPMCB with 3 pin metal clad socket. | Nos | 15 | 2138.5 | 32077.5 | 10 | 21385 | -5 | -10692.5 | 67% Claimed in RA Bill 1
25 |  | CABLES ACCESSORIES |  |  | 0 | 0 |  | 0 | 0 | 0
26 |  | Supply installation of following LT XLPE FRLS cables rated for 600 or 1100 volts AC as per IS standard 1554 Part 1 with necessary M.S. clamps. All cables shall be properly clamped or tied when run on cable trays. All such cables shall be provided with temporary labelling at every 10 mtrs and ten finally with metal identification tags showing the size and the location from or to the specific Panel or DB at both ends. |  |  |  | 0 |  | 0 | 0 | 0
27 |  | 4C x 6 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Mtr | 15 | 358.98 | 5384.7 | 14.5 | 5205.21 | -0.5 | -179.49 | 97% Claimed in RA Bill 1
28 |  | 4C x 4 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Mtr | 25 | 312.01 | 7800.25 | 24 | 7488.24 | -1 | -312.01 | 96% Claimed in RA Bill 1
29 |  | Termination of following sizes of cables with Single compression cable gland.(COMET or BRAKO) |  | 0 | 0 | 0 |  | 0 | 0 | 0
30 |  | 4C x 6 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Nos | 2 | 287.47 | 574.94 | 2 | 574.94 | 0 | 0 | 100% Claimed in RA Bill 1
31 |  | 4C x 4 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Nos | 4 | 283.96 | 1135.84 | 4 | 1135.84 | 0 | 0 | 100% Claimed in RA Bill 1
32 |  | WIRING ACCESSORIES |  |  | 0 | 0 |  | 0 | 0 | 0
33 |  | Notes 1) Rates for point wiring shall include supply installation of Wires wiring acccessories such as angle holders or ceiling roses as required. conduits, conduit accessories such as junction boxes, Ts, elbows etc,Switches, sockets fixtures shall not be included in the point wiring rates. These will be counted paid separately. 2) Unless otherwise specified, all wires in point wiring shall be 2.5 sq.mm Stranded copper conductor 1.1 KV grade, I.S.I. marked (P+N+E), Fire Retardant (FRLS) PVC insulated . Wires shall be colour coded (Red, Yellow and Blue for Phases, Black for Neutral Green for earth). 3) Looping of wires shall be in fittings and switch boxes only 4) Location of switches or sockets or DBs shown on the drawings shall be confirmed with the Architect or Consultant or Project Manager before installation. 5) All Surface and concealed Conduits shall be rigid GI conduits of size not less than 20 mm dia as per applicable IS. 6)The Contractor can take more than one circuit in the same conduit provided they are of the same phase. The size of conduit shall be decided according to the number of wires in it as per applicable IS as specified. 7) Payments for light fixtures fans will be made separately as per the items given in Light Fixtures Accessories . 8) Type location of light fixtures shown in the drawings are tentative and subject to revision as per the recommendation of Architect or Consultant. The quantities (number of points and accessories) of point wiring will be revised as actual installed on account of such revisions in the layouts. 9) Circuit wiring from DBs to the switch boards or first light point shall Be included as primary points remaining points of the same looping shall be considered as Secondary points and shall be counted in nos. 10) Circuit Wiring from DB to Kitchen Power points shall be measured in running meters |  | 0 | 0 | 0 |  | 0 | 0 | 0
34 |  | Supply, installation, testing commissioning of point wiring for light points, power points. Point wiring for primary point shall include wiring from Distribution Board upto First point of the circuit and shall be measured in nos. Secondary points shall also be measured in nos and shall include the remaining light points of the circuit controlled from same distribution board where primary points are controlling. The Power points shall be measured in Nos. Cost of GI conduits and accessories shall be included. (Normal Light) Average length Primary point - 6 mtr Secondary point - 3 mt |  |  |  | 0 |  | 0 | 0 | 0
35 |  | Primary Light points controlled by MCB (3R x 1.5 sqmm wire) | Nos | 3 | 1384.77 | 4154.31 | 3 | 4154.31 | 0 | 0 | 100% Claimed in RA Bill 1
36 |  | Secondary Light points looped in the same circuit. (3R x 1.5 sqmm wire) | Nos | 9 | 946.55 | 8518.95 | 9 | 8518.95 | 0 | 0 | 100% Claimed in RA Bill 1
37 |  | Providing point wiring for a cluster of 3 nos., 13 amps socket outlets and 1 no. 16A switch or pop up box for Computer Points or POS using 2 x 2.5 sq. mm PVC insulated copper conductor wires and minimum 2.5 Sq. mm copper conductor PVC insulated green colour earth wire for continuous earthing from NPDB to plug point in GI Conduits as specified and then in flexible Rigid PVC Conduits. (maximum 4 nos. clusters shall be connected on one circuit) switch and sockets to be mounted on front plate on partitions of furniture on hot dipped GI boxes concealed in wall 16A single pole plate switch with interconnections complete as per final approval of Architect or Consultant. (Cost of GI Conduits or Floor Raceway and switch sockets are considered elsewhere). ( Wires shall be FRLS type ) |  |  |  | 0 |  | 0 | 0 | 0
38 |  | Primary Point | Nos | 1 | 2243.68 | 2243.68 | 1 | 2243.68 | 0 | 0 | 100% Claimed in RA Bill 1
39 |  | Secondary points | Nos | 1 | 1893.1 | 1893.1 | 1 | 1893.1 | 0 | 0 | 100% Claimed in RA Bill 1
40 |  | Providing point wiring for Raw Power points 1no. 6 or 16A switch socket outlet on Skirting level to be looped from the nearest point using 2 x 2.5 sq. mm copper conductor wires and minimum 2.5 sq. mm copper conductor PVC insulated green colour earth wire as per approval of Architect or Consultant. (Cost of GI Conduit is included and switch sockets are considered elsewhere). (Wires shall be FRLS type) Note Average primary or secondary point length to be derived by Contractor, from the drawing or site provided AND + or - 1 Mtr Measured Radially. |  |  |  | 0 |  | 0 | 0 | 0
41 |  | Primary Point | Nos | 4 | 1472.41 | 5889.64 | 3 | 4417.23 | -1 | -1472.41 | 75% Claimed in RA Bill 1
42 |  | Secondary points | Nos | 8 | 981.61 | 7852.88 | 7 | 6871.27 | -1 | -981.61 | 88% Claimed in RA Bill 1
43 |  | Supply and laying of following PVC insulated copper conductor 1100 volt grade stranded flexible FRLS wire in already laid GI conduit concealed or surface mounted making connections where ever required to complete the installation.(For Kitchen Power Points) |  |  |  | 0 |  | 0 | 0 | 0
44 |  | 2R x 2.5Sqmm + 1R x 2.5Sqmm Cu. Wires | Mtr | 100 | 208.24 | 20824 | 96 | 19991.04 | -4 | -832.96 | 96% Claimed in RA Bill 1
45 |  | 2R x 4Sqmm + 1R x 2.5Sqmm Cu. Wires | Mtr | 50 | 157.75 | 7887.5 | 44 | 6941 | -6 | -946.5 | 88% Claimed in RA Bill 1
46 |  | Supply installation of 25 mm dia. GI conduit with pull box or junction box all accessories for Kitchen Bar Power wiring as per the requirement |  |  |  | 0 |  | 0 | 0 | 0
47 |  | do- but conduit pipe shall be Rigid type. | Mtr | 100 | 208.24 | 20824 | 96 | 19991.04 | -4 | -832.96 | 96% Claimed in RA Bill 1
48 |  | do - but flexible conduit pipe | Mtr | 20 | 157.75 | 3155 | 16 | 2524 | -4 | -631 | 80% Claimed in RA Bill 1
49 |  | Supply and installation of Perforated Cable Tray (ASIAN)out of 14 gauge GI sheet complete with necessary fixing arrangement with Anchor Fastener and all other accessories as per the final approval of the Consultant or Architect 150 x 50 x 2mm | Mtr | 20 | 288.87 | 5777.4 | 0 | 0 | -20 | -5777.4 | 0% Claimed in RA Bill 1
50 |  | Supply, installation, testing commissioning of flush mounted plate type switch and switch + sockets with hot dipped GI box complete as per the final approval of Architect or Consultant |  | 0 | 0 | 0 |  | 0 | 0 | 0
51 |  | 6A 5 pin Socket outlet | Nos | 2 | 473.27 | 946.54 | 0 | 0 | -2 | -946.54 | 0% Claimed in RA Bill 1
52 |  | 6 or 16A 5pin switch socket outlet | Nos | 12 | 525.86 | 6310.32 | 0 | 0 | -12 | -6310.32 | 0% Claimed in RA Bill 1
53 |  | 3nos 6 or 13A 5pin switch socket outlet | Nos | 2 | 964.08 | 1928.16 | 0 | 0 | -2 | -1928.16 | 0% Claimed in RA Bill 1
54 |  | Data Socket | Nos | 4 | 288.87 | 1155.48 | 0 | 0 | -4 | -1155.48 | 0% Claimed in RA Bill 1
55 |  | Telephone Socket | Nos | 1 | 217.35 | 217.35 | 0 | 0 | -1 | -217.35 | 0% Claimed in RA Bill 1
56 |  | Supply, installation of temporary lighting power arrangement for construction purpose of with industrial type switch sockets or MCB s or ELCB s lighting fittings as required to finish the work for interior contractor necessary electrical protections throughout the site for construction work till the handover of site. Contractor shall maintain the saftey rules regulations as per Airport Security Department. The material shall be taken back by the contractor. | Job | 1 | 14023 | 14023 | 1 | 14023 | 0 | 0 | 100% Claimed in RA Bill 1
57 |  | EARTHING - Supplying erecting bare GI conductor of 8 swg for earthing purpose | Mtr | 50 | 39.96 | 1998 | 45 | 1798.2 | -5 | -199.8 | 90% Claimed in RA Bill 1
|  |  | Grand Total Amount |  |  | 209724.85 |  | 170085.67 |  | -39639.18
Civil & Interior Work
58 |  | False flooring - False Flooring With Steel Frame and Members Raised Flooring of height 150mm with MS platform to pass electricals. A grid as per drawing to be made using sections as mentioned in MS to be of Tata or Jindal Make. | Sqft | 300 | 357.61 | 107283 | 299.9997 | 107283 | 0 | 0 | 100% Claimed in RA Bill 1
59 |  | Main framework - P or F MS framework of various section sizes finished with approved shade of powder coating with all necessary hardware, baseplate etc complete |  |  |  | 0 |  | 0 | 0
60 |  | 75X75mm MS box section (main vertical support) | Rft | 80 | 327.5 | 26200 | 78 | 25545 | -2 | -655 | 98% Claimed in RA Bill 1
61 |  | 50X50mm MS box section (main horizontal frame) | Rft | 70 | 263.5 | 18445 | 68 | 17918 | -2 | -527 | 97% Claimed in RA Bill 1
62 |  | 25X25mm MS box section (intermediate horizontal) | Rft | 300 | 222.1 | 66630 | 290 | 64409 | -10 | -2221 | 97% Claimed in RA Bill 1
63 |  | MS framework for counter front - P or F MS framework using 40X20mm MS sections at 600mm center to center with all necessary hardware, baseplate etc complete - Counter front partition | Sqft | 270 | 207.04 | 55900.8 | 204 | 42236.16 | -66 | -13664.64 | 76% Claimed in RA Bill 1
64 |  | MS framework for bulkhead - P or F MS framework using 20X20mm MS sections finished with approved shade of powder coating and MS mesh powder coated in approved shade to be fixed in between the frames with all necessary hardware, baseplate etc complete |  | 0 | 0 | 0 |  | 0 | 0 | 0
65 |  | Bulkhead framework | Rft | 250 | 169.4 | 42350 | 200 | 33880 | -50 | -8470 | 80% Claimed in RA Bill 1
66 |  | MS mesh | Sqft | 100 | 357.61 | 35761 | 57.14 | 20433.8354 | -42.86 | -15327.1646 | 57% Claimed in RA Bill 1
[6 empty] | 0 |  | 0 | 0 | 0
67 |  | Bison board partition - Designing, providing, installing Dry wall systems made out of cement boards and MS framework for story wall as detailed in Architectural drawings and as per approved manufacturer s specifications. Further system including providing | Sqft | 60 | 564.65 | 33879 | 0 | 0 | -60 | -33879 | 0% Claimed in RA Bill 1
68 |  | Tile cladding - Providing and fixing Glazed subway wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1 3 cement mortar not less than 12mm thick as where ever required, joint filler | Sqft | 120 | 237.15 | 28458 | 0 | 0 | -120 | -28458 | 0% Claimed in RA Bill 1
69 |  | Ply Panels - P or F 25mm thk Marine Board for Floor | Sqft | 300 | 297.38 | 89214 | 299.9997 | 89213.9168 | -0.00027975 | -0.083192 | 100% Claimed in RA Bill 1
70 |  | Tile Flooring - Floor Tiling with vitrified tiles of 2 x 2 size of approved shade of Kajaria, Asian, Nitco or Johnson Make. (Basic Rate 90-95 psft) | Sqft | 300 | 207.04 | 62112 | 0 | 0 | -300 | -62112 | 0% Claimed in RA Bill 1
71 |  | Grout Filling - Grout Filling using epoxy grout with Laticrete | Rft | 100 | 56.47 | 5647 | 0 | 0 | -100 | -5647 | 0% Claimed in RA Bill 1
72 |  | Skirting - STAINLESS STEEL STRIP 8 inch WIDE | Rft | 70 | 432.9 | 30303 | 69.5 | 30086.55 | -0.5 | -216.45 | 100% Claimed in RA Bill 1
73 |  | Debris removal - Debris Removal to contractor s own yard as per the guidelines provided in the site manual (Truck Load) | Nos | 1 | 11293.05 | 11293.05 | 1 | 11293.05 | 0 | 0 | 99% Claimed in RA Bill 1
74 |  | Plumbing fixtures - Sink - fixing under counter ss sink including pillar cock, waste coupling ,angle cock.bottle trap connection pipe etc all required to complete the work and make it functional.(Make - Nirali or Hindware or Parryware or equivalent | Nos | 1 | 13175.22 | 13175.22 | 0 | 0 | -1 | -13175.22 | 0% Claimed in RA Bill 1
75 |  | Counter front panelling - Making the counter front using ply and flexible ply on curve sides with MS Frame as per the design finished with Corian and fluted wooden panels on front façade |  |  |  | 0 |  | 0 | 0 | 0
76 |  | a - Ply Panelling | Sqft | 270 | 263.5 | 71145 | 210 | 55335 | -60 | -15810 | 78% Claimed in RA Bill 1
77 |  | b - Corian cladding | Sqft | 200 | 1317.52 | 263504 | 0 | 0 | -200 | -263504 | 0% Claimed in RA Bill 1
78 |  | c - Fluted wooden panel | Sqft | 70 | 658.76 | 46113.2 | 53.2 | 35046.032 | -16.8 | -11067.168 | 76% Claimed in RA Bill 1
79 |  | d - inside laminate (basic rate Rs. 35 or sft) | Sqft | 270 | 79.05 | 21343.5 | 210 | 16600.5 | -60 | -4743 | 78% Claimed in RA Bill 1
80 |  | Counter Top - Counter Top finish in corian with 18mm ply base as per the design. | Sqft | 150 | 1919.82 | 287973 | 67.4975 | 129583.0504 | -82.5025 | -158389.9495 | 45% Claimed in RA Bill 1
81 |  | Corian Band for story wall - 20mm thk Corian band of approved shade fixed on Bison board | Rft | 55 | 715.23 | 39337.65 | 0 | 0 | -55 | -39337.65 | 0% Claimed in RA Bill 1
82 |  | Undercounter Storage - Providing and fixing600mm deep storage unit ( 900mm high) made of 19mm thick fire retardent plywood and finished with 1.0mm thick laminate externally. Shutter, Intermidiate shelves made of 19mm thick fire retardent plywood to be pro | Sqft | 70 | 3143.23 | 220026.1 | 60 | 188593.8 | -10 | -31432.3 | 86% Claimed in RA Bill 1
83 |  | Flap door - Providing and fixing 600X750mm flap door made of 19mm thick fire retardent plywood and finished with corian same as counter top externally. Shutter made of 19mm thick fire retardent plywood to be provided finished with 1.0mm thick laminate int | Nos | 1 | 16939.57 | 16939.57 | 0.5 | 8469.785 | -0.5 | -8469.785 | 50% Claimed in RA Bill 1
84 |  | Shelves for display - Providing and fixing Shelves finished with corian with 18mm ply base fixed on MS framework with all necessary hardware etc. complete - Size- 2700x750mm | Nos | 2 | 26915.1 | 53830.2 | 1 | 26915.1 | -1 | -26915.1 | 50% Claimed in RA Bill 1
85 |  | Ply boxing for TV - Providing and fixing ply boxing made of 19mm thick fire retardent plywood to be provided finished with 1.0mm thick laminate on both sides. All complete including necessary hardwares, heavy duty hinges, handles, locks etc. | Sqft | 50 | 564.65 | 28232.5 | 23 | 12986.95 | -27 | -15245.55 | 46% Claimed in RA Bill 1
86 |  | PVC grill for counter ventilation - Providing and fixing PVC grill finished with approved shade of powdercoating for counter ventilation - Size- 1500x200mm | Nos | 1 | 4140.78 | 4140.78 | 0 | 0 | -1 | -4140.78 | 0% Claimed in RA Bill 1
87 |  | Fluted Glass panel - P or F Fluted glass panel with MS framework using 40X20mm MS sections finished with approved shade of powder coating and fluted glass in between fixed on framework with 10X10mm beading patti with all necessary hardware, baseplate etc |  |  | 0 | 0 |  | 0 | 0 | 0
88 |  | a - 40X20mm MS framework | Rft | 75 | 207.04 | 15528 | 51 | 10559.04 | -24 | -4968.96 | 68% Claimed in RA Bill 1
89 |  | b - Fluted glass penel | Sqft | 40 | 432.9 | 17316 | 30 | 12987 | -10 | -4329 | 75% Claimed in RA Bill 1
90 |  | c - Curved Fluted glass penel | Sqft | 10 | 752.87 | 7528.7 | 6 | 4517.22 | -4 | -3011.48 | 60% Claimed in RA Bill 1
91 |  | SS Railing - P or F SS Railing using 40X20mm 20X20mm SS sections brush finished as per approved sample with all necessary hardware, baseplate etc complete |  | 0 | 0 | 0 |  | 0 | 0 | 0
92 |  | a - 40X20mm SS section | Rft | 100 | 414.08 | 41408 | 0 | 0 | -100 | -41408 | 0% Claimed in RA Bill 1
93 |  | b - 20X20mm SS section | Rft | 50 | 319.97 | 15998.5 | 0 | 0 | -50 | -15998.5 | 0% Claimed in RA Bill 1
94 |  | Sink Storage Unit - Providing and fixing 800mm deep storage unit ( 900mm high) made of 25mm corain top made up of 19mm thick fire retardent plywood and finished with 1.0mm thick laminate internally 6mm thk corian externally. Storage unit made up of 19m | Sqft | 15 | 4893.65 | 73404.75 | 15 | 73404.75 | 0 | 0 | 100% Claimed in RA Bill 1
95 |  | Counter Guard Railing - P or F SS guard Railing using 35mm dia SS sections brush finished as per approved sample with all necessary supports from floor or counter, baseplate hardware etc complete a - Counter top | Rft | 70 | 715.23 | 50066.1 | 40 | 28609.2 | -30 | -21456.9 | 57% Claimed in RA Bill 1
96 |  | Temprary barricading - Providing and fixing flex board out. Cost to include framework cost, opening for door, flex printing and installation. ( digital file provided by client ) Sizes as mentioned below | Sqft | 500 | 169.4 | 84700 | 499.9994 | 84700 | 0 | 0 | 100% Claimed in RA Bill 1
|  |  | Grand Total Amount |  |  | 1985186.62 |  | 1130605.9397 |  | -854580.6803

## Measurement Sheet
Sr. No. | 1 |  | Name of site In charge : | [6 empty] | Ashish Nagar
PO No.: | Semolina/PO/24-25/000692 |  | Agency Name : | [6 empty] | Semolina Kitchen Pvt.Ltd
PO Date : | 31/07/2024 |  | Date : 08-11-2024
PO Validity : |  |  | Name of Work: MUMBAI JOSHH T2 CSMIA
Measurement Sheet No. of this PO: | 1 |  | Period of work Executed :
JOSHH |  |  | Measurement Sheet | [5 empty] | Total Qty | Claimable % | Claimable Qty
SR. NO. | MATERIAL | DESCRIPTION | UNIT | PO QTY. | Nos | Length | Breadth | Height |  | RA-1
PLUMBING WORK :
1 | WATER SUPPLY PIPING - | WATER SUPPLY PIPING - CPVC Pipes conforming to ASTM D-2846, SDR-11 grade and CPVC solvent weld fittings like elbows, tees, couplers, brass threaded adapters, insert ring etc. suitable for (domestic flushing and hot water) applications rated, concealed piping within wall floor including jointing with fittings using solvent cement ,brass threaded end fittings for making connection to fixtures. The work shall also include chasing the walls with machine wherever required for concealed piping and making good the same after laying of pipes necessary pressure testing Chasing finishing shall be done with 1 1 cement mixed mortar, restore the same original condition for internal and shaft piping, including necessary hot deep galvanized supports vertical horizontal, as per direction of Site in charge direction. The rate shall include supply of S. S. screws and nut bolts etc. chasing in walls done by machine Make - Supreme, Prince, Astral , Ashirvad
2 |  | 20 mm Dia | R.mt | 35 | 1 | 35 |  |  | 35 | 100% | 35
3 |  | 25 mm Dia | R.mt | 5 | 1 | 5 |  |  | 5 | 100% | 5
4 | Ball Valves | Providing Fixing of gun metal heavy approved make Ball Valves screwed type for water system of the following diameters(10Kg Sq.cm). Valve shall have with unions. Make - Zoloto, Danfos, KSB, Audco India
5 |  | 20mm Dia | Nos | 3 | 2 |  |  |  | 2 | 66.67% | 2
6 |  | 25mm Dia | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
7 | Water Meter | Providing ,fixing, testing and commissioning capstan make Water Meter including providing fixing matching Isolation valves ,strainer, non-return valve,complete with all necessary fittings etc screwed type(15Kgs Sq.cm). Valve shall have with union. 25 mm Dia incoming line (Optional) Make- Capstan | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
8 | Electric Hot Water Generator | Supply, installation,testing commissioning of Storage Type Electric Hot Water Generator of mentioned capacity , suitable for 3 KG cm2 pressure, Wall Mounted Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories (Optional in pantry) 20 L Capacity ( Optional -Subject to requirement from Kitchen consultant) Make- Racold, Jauqar | Nos | 1 | 0 |  |  |  | 0 | 0% | 0
9 | RO system | Supply, installation, testing and commissioning of standalone RO system -10-12 lit ( Optional) Make - LG Kent Alfa Iron Exchange | Nos | 1 | 0 |  |  |  | 0 | 0% | 0
10 |  | DRAINAGE |  | 0
11 | UPVC Type B pipe | UPVC Type B pipe confirming to IS 13592 (6 Kg CM2) for Soil, Waste upto 65mm dia. confirming to IS 13592 and PVC Agriculture 6kg Pipe for Soil, Waste above 65mm dia including all necessary fittings and specials such as as 45 or 90 deg. bends, Tee s, Y s, `P trap, NT (as required) access pipe with solvant cement jointing. Make - Supreme, Prince, Astral , Ashirvad |  | 0
12 |  | 50mm Dia | R.mt | 5 | 1 | 5 |  |  | 5 | 100% | 5
13 |  | 75mm Dia | R.mt | 12 | 1 | 11.5 |  |  | 11.5 | 95.83% | 11.5
14 |  | 100 mm Dia | R.mt | 12 | 1 | 1 |  |  | 1 | 8.333% | 1
15 | Multi floor Traps | Supply, Install multi floor Traps including fixing with necessary consumables with Circular SS Grating with anti cockroach jali Suitable for taking 40mm Dia 50mm Dia Back Inlet Connection with 75mm Dia outlet make - Supreme, Prince, Astral , Ashirvad | Nos | 2 | 2 |  |  |  | 2 | 100% | 2
16 |  | Supply, Install CLEAN OUT PLUGS - 75mm Dia | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
17 |  | Supply, Install Grease trap of nugreen make NGT-30 . Shall be order based on the space available below sink. | Nos | 2 | 0 |  |  |  | 0 | 0% | 0
18 |  | NOTES 1. TAXES DUTIES shall be Extra as actual 2. kKitchen and Bar Gratings |  | 0
Electrical Work :
19 |  | DISTRIBUTION SWITCHGEAR
20 |  | Supply, installation, testing commissioning of Distribution Boards surface or flush mounted with Double door containing MCB or ELMCB as incomer and SPMCB as outgoing. All MCBs are of 10KA breaking capacity and ELMCBs or RCCB should be of 30mA or 100 or 300 mA sensivity. The DB shall have appropriate no. of top and bottom knock outs for outgoing circuits and shall be complete with necessary busbars, interconnection terminals and earth studs. All terminations in DB shall be complete with ferulling, dressing and all circuits shall be properly labeled with PVC strip (sticker type) having identification as per the final approval of Consultant. For UPS DB MCB shall be D type and other MCBs shall be C category for lighting and raw power DB. Lighting power DB - VTPN DB 12 way VTPN DB I or C- 80A FP RCBO, 100mA -1 Nos O or G -5 # 16 or 20 or 32A TP MCB O or G -21 # 10 or 16 or 20A SP MCB | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
21 |  | Supply, installation, testing commissioning of Switchgears. (Standard Product) |  | 0 |  |  |  |  | 0
22 |  | 63 amps 4P MCB with 63A 5 Pin Ray Roll Socket complete with all mounting accessories – for Kitchen Legrand make | Nos | 1 | 0.5 |  |  |  | 0.5 | 50% | 0.5
23 |  | 32A Rey roll socket complete with 32 amps SPMCB with 3 pin metal clad socket - Legrand make Model No. 6078 41 - kitchen power | Nos | 4 | 2 |  |  |  | 2 | 50% | 2
24 |  | 16A Rey roll socket complete with 16 amps SPMCB with 3 pin metal clad socket. | Nos | 15 | 10 |  |  |  | 10 | 66.67% | 10
25 |  | CABLES ACCESSORIES
26 |  | Supply installation of following LT XLPE FRLS cables rated for 600 or 1100 volts AC as per IS standard 1554 Part 1 with necessary M.S. clamps. All cables shall be properly clamped or tied when run on cable trays. All such cables shall be provided with temporary labelling at every 10 mtrs and ten finally with metal identification tags showing the size and the location from or to the specific Panel or DB at both ends.
27 |  | 4C x 6 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Mtr | 15 | 1 | 14.5 |  |  | 14.5 | 96.67% | 14.5
28 |  | 4C x 4 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Mtr | 25 | 1 | 24 |  |  | 24 | 96% | 24
29 |  | Termination of following sizes of cables with Single compression cable gland.(COMET or BRAKO)
30 |  | 4C x 6 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Nos | 2 | 2 |  |  |  | 2 | 100% | 2
31 |  | 4C x 4 Sq. mm 2XFY Cable ( Cu ) (Kitchen 3Ph equipments) | Nos | 4 | 4 |  |  |  | 4 | 100% | 4
32 |  | WIRING ACCESSORIES
33 |  | Notes 1) Rates for point wiring shall include supply installation of Wires wiring acccessories such as angle holders or ceiling roses as required. conduits, conduit accessories such as junction boxes, Ts, elbows etc,Switches, sockets fixtures shall not be included in the point wiring rates. These will be counted paid separately. 2) Unless otherwise specified, all wires in point wiring shall be 2.5 sq.mm Stranded copper conductor 1.1 KV grade, I.S.I. marked (P+N+E), Fire Retardant (FRLS) PVC insulated . Wires shall be colour coded (Red, Yellow and Blue for Phases, Black for Neutral Green for earth). 3) Looping of wires shall be in fittings and switch boxes only 4) Location of switches or sockets or DBs shown on the drawings shall be confirmed with the Architect or Consultant or Project Manager before installation. 5) All Surface and concealed Conduits shall be rigid GI conduits of size not less than 20 mm dia as per applicable IS. 6)The Contractor can take more than one circuit in the same conduit provided they are of the same phase. The size of conduit shall be decided according to the number of wires in it as per applicable IS as specified. 7) Payments for light fixtures fans will be made separately as per the items given in Light Fixtures Accessories . 8) Type location of light fixtures shown in the drawings are tentative and subject to revision as per the recommendation of Architect or Consultant. The quantities (number of points and accessories) of point wiring will be revised as actual installed on account of such revisions in the layouts. 9) Circuit wiring from DBs to the switch boards or first light point shall Be included as primary points remaining points of the same looping shall be considered as Secondary points and shall be counted in nos. 10) Circuit Wiring from DB to Kitchen Power points shall be measured in running meters |  | 0 |  |  |  |  | 0
34 |  | Supply, installation, testing commissioning of point wiring for light points, power points. Point wiring for primary point shall include wiring from Distribution Board upto First point of the circuit and shall be measured in nos. Secondary points shall also be measured in nos and shall include the remaining light points of the circuit controlled from same distribution board where primary points are controlling. The Power points shall be measured in Nos. Cost of GI conduits and accessories shall be included. (Normal Light) Average length Primary point - 6 mtr Secondary point - 3 mt
35 |  | Primary Light points controlled by MCB (3R x 1.5 sqmm wire) | Nos | 3 | 3 |  |  |  | 3 | 100% | 3
36 |  | Secondary Light points looped in the same circuit. (3R x 1.5 sqmm wire) | Nos | 9 | 9 |  |  |  | 9 | 100% | 9
37 |  | Providing point wiring for a cluster of 3 nos., 13 amps socket outlets and 1 no. 16A switch or pop up box for Computer Points or POS using 2 x 2.5 sq. mm PVC insulated copper conductor wires and minimum 2.5 Sq. mm copper conductor PVC insulated green colour earth wire for continuous earthing from NPDB to plug point in GI Conduits as specified and then in flexible Rigid PVC Conduits. (maximum 4 nos. clusters shall be connected on one circuit) switch and sockets to be mounted on front plate on partitions of furniture on hot dipped GI boxes concealed in wall 16A single pole plate switch with interconnections complete as per final approval of Architect or Consultant. (Cost of GI Conduits or Floor Raceway and switch sockets are considered elsewhere). ( Wires shall be FRLS type )
38 |  | Primary Point | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
39 |  | Secondary points | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
40 |  | Providing point wiring for Raw Power points 1no. 6 or 16A switch socket outlet on Skirting level to be looped from the nearest point using 2 x 2.5 sq. mm copper conductor wires and minimum 2.5 sq. mm copper conductor PVC insulated green colour earth wire as per approval of Architect or Consultant. (Cost of GI Conduit is included and switch sockets are considered elsewhere). (Wires shall be FRLS type) Note Average primary or secondary point length to be derived by Contractor, from the drawing or site provided AND + or - 1 Mtr Measured Radially.
41 |  | Primary Point | Nos | 4 | 3 |  |  |  | 3 | 75% | 3
42 |  | Secondary points | Nos | 8 | 7 |  |  |  | 7 | 87.5% | 7
43 |  | Supply and laying of following PVC insulated copper conductor 1100 volt grade stranded flexible FRLS wire in already laid GI conduit concealed or surface mounted making connections where ever required to complete the installation.(For Kitchen Power Points)
44 |  | 2R x 2.5Sqmm + 1R x 2.5Sqmm Cu. Wires | Mtr | 100 | 96 |  |  |  | 96 | 96% | 96
45 |  | 2R x 4Sqmm + 1R x 2.5Sqmm Cu. Wires | Mtr | 50 | 44 |  |  |  | 44 | 88% | 44
46 |  | Supply installation of 25 mm dia. GI conduit with pull box or junction box all accessories for Kitchen Bar Power wiring as per the requirement
47 |  | do- but conduit pipe shall be Rigid type. | Mtr | 100 | 1 | 96 |  |  | 96 | 96% | 96
48 |  | do - but flexible conduit pipe | Mtr | 20 | 1 | 16 |  |  | 16 | 80% | 16
49 |  | Supply and installation of Perforated Cable Tray (ASIAN)out of 14 gauge GI sheet complete with necessary fixing arrangement with Anchor Fastener and all other accessories as per the final approval of the Consultant or Architect 150 x 50 x 2mm | Mtr | 20 | 0 |  |  |  | 0 | 0% | 0
50 |  | Supply, installation, testing commissioning of flush mounted plate type switch and switch + sockets with hot dipped GI box complete as per the final approval of Architect or Consultant
51 |  | 6A 5 pin Socket outlet | Nos | 2 | 0 |  |  |  | 0 | 0% | 0
52 |  | 6 or 16A 5pin switch socket outlet | Nos | 12 | 0 |  |  |  | 0 | 0% | 0
53 |  | 3nos 6 or 13A 5pin switch socket outlet | Nos | 2 | 0 |  |  |  | 0 | 0% | 0
54 |  | Data Socket | Nos | 4 | 0 |  |  |  | 0 | 0% | 0
55 |  | Telephone Socket | Nos | 1 | 0 |  |  |  | 0 | 0% | 0
56 |  | Supply, installation of temporary lighting power arrangement for construction purpose of with industrial type switch sockets or MCB s or ELCB s lighting fittings as required to finish the work for interior contractor necessary electrical protections throughout the site for construction work till the handover of site. Contractor shall maintain the saftey rules regulations as per Airport Security Department. The material shall be taken back by the contractor. | Job | 1 | 1 |  |  |  | 1 | 100% | 1
57 |  | EARTHING - Supplying erecting bare GI conductor of 8 swg for earthing purpose | Mtr | 50 | 1 | 45 |  |  | 45 | 90% | 45
Civil & Interior Work
58 |  | False flooring - False Flooring With Steel Frame and Members Raised Flooring of height 150mm with MS platform to pass electricals. A grid as per drawing to be made using sections as mentioned in MS to be of Tata or Jindal Make. | Sqft | 300 | 1 | 17.3205 | 17.3205 |  | 299.9997 | 100% | 299.9997
59 |  | Main framework - P or F MS framework of various section sizes finished with approved shade of powder coating with all necessary hardware, baseplate etc complete
60 |  | 75X75mm MS box section (main vertical support) | Rft | 80 | 1 | 78 |  |  | 78 | 97.5% | 78
61 |  | 50X50mm MS box section (main horizontal frame) | Rft | 70 | 1 | 68 |  |  | 68 | 97.14% | 68
62 |  | 25X25mm MS box section (intermediate horizontal) | Rft | 300 | 1 | 290 |  |  | 290 | 96.67% | 290
63 |  | MS framework for counter front - P or F MS framework using 40X20mm MS sections at 600mm center to center with all necessary hardware, baseplate etc complete - Counter front partition | Sqft | 270 | 1 | 68 |  | 3 | 204 | 75.56% | 204
64 |  | MS framework for bulkhead - P or F MS framework using 20X20mm MS sections finished with approved shade of powder coating and MS mesh powder coated in approved shade to be fixed in between the frames with all necessary hardware, baseplate etc complete
65 |  | Bulkhead framework | Rft | 250 | 1 | 200 |  |  | 200 | 80% | 200
66 |  | MS mesh | Sqft | 100 | 1 | 40 |  | 1.4285 | 57.14 | 57.14% | 57.14
67 |  | Bison board partition - Designing, providing, installing Dry wall systems made out of cement boards and MS framework for story wall as detailed in Architectural drawings and as per approved manufacturer s specifications. Further system including providing | Sqft | 60 | 0 |  |  |  | 0 | 0% | 0
68 |  | Tile cladding - Providing and fixing Glazed subway wall tiles which includes-approved make of adhesive like bal Endura or equivalent, grey cement paste with backing coat of 1 3 cement mortar not less than 12mm thick as where ever required, joint filler | Sqft | 120 | 0 |  |  |  | 0 | 0% | 0
69 |  | Ply Panels - P or F 25mm thk Marine Board for Floor | Sqft | 300 | 1 | 17.3205 | 17.3205 |  | 299.9997 | 100% | 299.9997
70 |  | Tile Flooring - Floor Tiling with vitrified tiles of 2 x 2 size of approved shade of Kajaria, Asian, Nitco or Johnson Make. (Basic Rate 90-95 psft) | Sqft | 300 | 0 |  |  |  | 0 | 0% | 0
71 |  | Grout Filling - Grout Filling using epoxy grout with Laticrete | Rft | 100 | 0 |  |  |  | 0 | 0% | 0
72 |  | Skirting - STAINLESS STEEL STRIP 8 inch WIDE | Rft | 70 | 1 | 69.5 |  |  | 69.5 | 99.29% | 69.5
73 |  | Debris removal - Debris Removal to contractor s own yard as per the guidelines provided in the site manual (Truck Load) | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
74 |  | Plumbing fixtures - Sink - fixing under counter ss sink including pillar cock, waste coupling ,angle cock.bottle trap connection pipe etc all required to complete the work and make it functional.(Make - Nirali or Hindware or Parryware or equivalent | Nos | 1 | 0 |  |  |  | 0 | 0% | 0
75 |  | Counter front panelling - Making the counter front using ply and flexible ply on curve sides with MS Frame as per the design finished with Corian and fluted wooden panels on front façade
76 |  | a - Ply Panelling | Sqft | 270 | 1 | 70 |  | 3 | 210 | 77.78% | 210
77 |  | b - Corian cladding | Sqft | 200 | 0 | 0 |  |  | 0 | 0% | 0
78 |  | c - Fluted wooden panel | Sqft | 70 | 1 | 20 |  | 2.66 | 53.2 | 76% | 53.2
79 |  | d - inside laminate (basic rate Rs. 35 or sft) | Sqft | 270 | 1 | 70 |  | 3 | 210 | 77.78% | 210
80 |  | Counter Top - Counter Top finish in corian with 18mm ply base as per the design. | Sqft | 150 | 1 | 25.375 | 2.66 |  | 67.4975 | 45% | 67.4975
81 |  | Corian Band for story wall - 20mm thk Corian band of approved shade fixed on Bison board | Rft | 55 | 0 |  |  |  | 0 | 0% | 0
82 |  | Undercounter Storage - Providing and fixing600mm deep storage unit ( 900mm high) made of 19mm thick fire retardent plywood and finished with 1.0mm thick laminate externally. Shutter, Intermidiate shelves made of 19mm thick fire retardent plywood to be pro | Sqft | 70 | 1 | 20 |  | 3 | 60 | 85.71% | 60
83 |  | Flap door - Providing and fixing 600X750mm flap door made of 19mm thick fire retardent plywood and finished with corian same as counter top externally. Shutter made of 19mm thick fire retardent plywood to be provided finished with 1.0mm thick laminate int | Nos | 1 | 0.5 |  |  |  | 0.5 | 50% | 0.5
84 |  | Shelves for display - Providing and fixing Shelves finished with corian with 18mm ply base fixed on MS framework with all necessary hardware etc. complete - Size- 2700x750mm | Nos | 2 | 1 |  |  |  | 1 | 50% | 1
85 |  | Ply boxing for TV - Providing and fixing ply boxing made of 19mm thick fire retardent plywood to be provided finished with 1.0mm thick laminate on both sides. All complete including necessary hardwares, heavy duty hinges, handles, locks etc. | Sqft | 50 | 1 | 11.5 |  | 2 | 23 | 46% | 23
86 |  | PVC grill for counter ventilation - Providing and fixing PVC grill finished with approved shade of powdercoating for counter ventilation - Size- 1500x200mm | Nos | 1 | 0 |  |  |  | 0 | 0% | 0
87 |  | Fluted Glass panel - P or F Fluted glass panel with MS framework using 40X20mm MS sections finished with approved shade of powder coating and fluted glass in between fixed on framework with 10X10mm beading patti with all necessary hardware, baseplate etc
88 |  | a - 40X20mm MS framework | Rft | 75 | 1 | 51 |  |  | 51 | 68% | 51
89 |  | b - Fluted glass penel | Sqft | 40 | 1 | 20 |  | 1.5 | 30 | 75% | 30
90 |  | c - Curved Fluted glass penel | Sqft | 10 | 1 | 4 |  | 1.5 | 6 | 60% | 6
91 |  | SS Railing - P or F SS Railing using 40X20mm 20X20mm SS sections brush finished as per approved sample with all necessary hardware, baseplate etc complete
92 |  | a - 40X20mm SS section | Rft | 100 | 0 |  |  |  | 0 | 0% | 0
93 |  | b - 20X20mm SS section | Rft | 50 | 0 |  |  |  | 0 | 0% | 0
94 |  | Sink Storage Unit - Providing and fixing 800mm deep storage unit ( 900mm high) made of 25mm corain top made up of 19mm thick fire retardent plywood and finished with 1.0mm thick laminate internally 6mm thk corian externally. Storage unit made up of 19m | Sqft | 15 | 1 | 5 |  | 3 | 15 | 100% | 15
95 |  | Counter Guard Railing - P or F SS guard Railing using 35mm dia SS sections brush finished as per approved sample with all necessary supports from floor or counter, baseplate hardware etc complete a - Counter top | Rft | 70 | 1 | 40 |  |  | 40 | 57.14% | 40
96 |  | Temprary barricading - Providing and fixing flex board out. Cost to include framework cost, opening for door, flex printing and installation. ( digital file provided by client ) Sizes as mentioned below | Sqft | 500 | 1 | 52.192 | 9.58 |  | 499.9994 | 100% | 499.9994

## Sheet1 (hidden)
15nos nhani trap
15nos 75*110 reducer
40ft 160mm pvc pipe
4nos 110mm Y
4nos 110mm shoe bend
70ft. 110mm pvc pipe
4nos 110mm bend
4nos 250gm solution pvc
6nos 110 coupling
1/2“ cpvc 60 ft
3/4” cpvc 50ft
1/2” cpvc elbow 25nos
3/4” cpvc elbow 25nos
1/2” cpvc T 6nos
3/4” cpvc T 6nos
1/2” cpvc 8nos
3/4” cpvc 8nos
3/4*1/2 bushing 5nos
1”*3/4” bushing 5nos
Ro ka ek motar