## Summary
PO NO : | SEMOLINA/PO/23-24/000664
SR NO | DISCRIPTION | PO VALUE | PRESENT BILL AMT | CUMULATIVE AMT | VARIANCE AMT
1 | CIVIL WORK | 946470 | 615941.821 | 615941.821 | -330528.179
2 | PLUMBING WORK | 287050 | 11742.5 | 11742.5 | -275307.5
|  | 1233520 | 627684.321 | 627684.321 | -605835.679
| GST 18 % | 222033.6 | 112983.1778 | 112983.1778 | -109050.4222
| TOTAL | 1455553.6 | 740667.4988 | 740667.4988 | -714886.1012

## Abstract
|  |  |  | AS PER PO | Vendor Name : Pioneer Infra And Turnkey Solutions | AS PER SITE
Sr No. | Item Description | UOM | Qty | Unit Price | Amount | Qty | Amount
1 | Civil & Interior Work BOQ for LKN Budweiser bar | no | 1
1 | ANTI TERMITE TREATMENT - Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). AREA - ALL MOH FOH | Sq.m. | 225 | 110 | 24750 | 227.7128 | 25048.408
2 | CIVIL WORK
3 | WATERPROOFING - Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. 1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring | Sq.m. | 98 | 950 | 93100 | 62.4748 | 59351.06
4 | CINDER LIGHT WT. SIPORAX BLOCK BATS FILLING
5 | Providing Filling light wt. Siporex block bats to conceal drainage plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. AREA - MOH RAISED AREA (up to 150 mm) | Sq.m. | 14 | 1650 | 23100 | 14.82 | 24453
6 | Providing Filling light wt. Siporex block bats to conceal drainage plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. AREA - BOH RAISED AREA (up to 300 mm) | Sq.m. | 39 | 1450 | 56550 | 33.1488 | 48065.76
7 | PCC LAYER - Providing Laying P.C.C 1 3 6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 225 | 650 | 146250 | 244.7893 | 159113.045
8 | Block WORK - Providing Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1 4 (1 cement 4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. AREA - 150 MM THICK BLOCK MASONARY | Sq.m. | 93 | 1350 | 125550 | 0 | 0
9 | PLASTER - P L12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 185 | 592 | 109520 | 94.999 | 56239.408
10 | RCC LINTEL BEAM - P L in place (cast in situ) RCC lintel beams in 150mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1 4 8) 100mm high with 4 no. s 8mm th. Steel bars as per general specifications, complete in all respects | Rm | 3 | 700 | 2100 | 0 | 0
11 | TILING WORKS, FLOORING
12 | Providing and laying of Anti-skid VITRIFIED Commercial floor tile of size 600 x 600 mm of approved make and Shade laid over 40 mm thick cement mortar 1 4 (1 cement 4 coarse sand) mix jointed with white cement slurry, mixed with pigment to match color of tile. Cost to include chamfering if any, cutting , edge rubbing etc., complete as per design and drawing, with 3 mm Spacers finished with Matching Epoxy Grouting. Necessary Protection by covering with PVC sheet shall be provided for Flooring till the handover of the Outlet.It has to meet the specs of RA level. Make Endura grey, Nitco (Basic Rate - 66 persqft) Anti-skid Commercial Tiles ( BOH Area) | Sq.m. | 50 | 1800 | 90000 | 33.0948 | 59570.64
13 | Providing and laying of White Ceramic- 600m.m x 300m,m Tiles on Wall with 1 4 Cement Moratar with 3m.m Spacers .This Include Cutting Fixing of Electrical Boxes , Plumbing Fixtures others . with Matching Epoxy Groutings neat Clean in all respects 1Rate includes Cutting all wastage, underlay as required, treatment of corners and finishing as per the instruction of the Project Manager.Top Portion of the Skirting to be Neatly Grouted .Finishsed AREA - WALLS TILES KITCHEN BOH | Sq.m. | 100 | 1900 | 190000 | 96.895 | 184100.5
14 | Providing Fixing of S.S.304 Corner Angles Z Type 40m.m x 40mm Thickness 1.5m.m on Walls for the Ceramic Wall Tiles Complete in all Respects AREA - S.S Corner Angles in 304 Grade 40m.m x 40m.m | Rm | 3 | 1850 | 5550 | 0 | 0
15 | Providing and fixing of 19 mm thk. Black Granite Jamb in floor wall over a bed of 20 mm thk. Cement mortar 1 4 (1 Cement 4 coarse sand) joints filled with epoxy adhesive to match the color of granite. Rate shall be including polished granite, necessary wastage, cutting, edge grinding and polishing as per the instructions of the Project Manager, complete. Width of Jamb 200 mm.Basic Door Jambs in Granite - BOH Area | Rm | 2 | 1000 | 2000 | 0 | 0
16 | CEILINGS (BOH)
17 | Providing fixing Metal Grid False ceiling 2 x 2 in plain metal powder coated 24 mm wide sectionfinish as per approved colour. The system to be Lay-in- type. There should be M.S. channel for every 3rd GRID to completed as per details design given in drawing Architect instruction. Note - Corner cutting tiling should be moulding. Make Vendor Armstrong USG AREA - METAL GRID CEILING | Sq.m. | 40 | 1950 | 78000 | 0 | 0
| Civil & Interior Work BOQ for LKN Budweiser bar |  |  |  | 946470 |  | 615941.821
2 | Plumbing Work BOQ for LKN Budweiser bar | no | 1
18 | WATER SUPPLY PIPES CPVC Pipes Supply, laying, testing commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia. (Make – SUPREME KASTA) including all necessary fitting as per site.
19 | 15mm dia | R.M. | 25 | 550 | 13750 | 0 | 0
20 | 20mm dia | R.M. | 45 | 650 | 29250 | 0 | 0
21 | WATER DRAIN PIPES- UPVC WASTE PIPE - UPVC Pipe for Drainage (Make – SUPREME KASTA) including all necessary fitting as per site.
22 | 100mm dia | R.M. | 25 | 550 | 13750 | 21.35 | 11742.5
23 | 50mm dia | R.M. | 5 | 650 | 3250 | 0 | 0
24 | CHAMBER GRATING INSPECTION CHAMBER- Supply, Laying, Testing Commissioning of Approved SS Inspection Chamber along of Size- 300mmx300mm with SS Cover SS Grating over it. Make Jaquar Ozone. Including trenching and finishing with ceramic tiles as per dwg and details. | Nos. | 3 | 7000 | 21000 | 0 | 0
25 | FLOOR TRAP - Supply, Laying, Testing Commissioning of 100x100mm Floor Trap with Approved Make heavy duty round or Square. | Nos. | 6 | 1650 | 9900 | 0 | 0
26 | VALVE AND TAP
27 | ANGLE VALVE - Providing Fixing Angle Valve with connector pipe. | Nos. | 10 | 1860 | 18600 | 0 | 0
28 | LONG BODY TAP - Providing Fixing Sink Cock. with foot operated | Nos. | 1 | 4100 | 4100 | 0 | 0
29 | Table Mixer - Providing Fixing Sink Cock. | Nos. | 3 | 2800 | 8400 | 0 | 0
30 | Gate Valves - Providing Fixing PPR Ball Valve ISI mark. (For Inlet) | Nos. | 1 | 2350 | 2350 | 0 | 0
31 | ACCESSORIES
32 | Grease Trap - Providing Fixing of portable grease trap NGT-8 from Nugreen | Nos. | 3 | 33000 | 99000 | 0 | 0
33 | Bottle Trap - Providing fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR OZONE) | Nos. | 3 | 2450 | 7350 | 0 | 0
34 | Water Meter 25mm Dia Water meter | Nos. | 1 | 4100 | 4100 | 0 | 0
35 | GEYSER - 6 LITER GEYSER | Nos. | 2 | 7500 | 15000 | 0 | 0
36 | Waste Coupling - Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. | Nos. | 1 | 1250 | 1250 | 0 | 0
37 | Water supply connection - water supply connection taken from existing point complete with all necessary fittings. | Nos. | 1 | 5000 | 5000 | 0 | 0
38 | Drainage connection - Drainage connection connect to existing drain point complete with all necessary fittings including cleanout plug | Nos. | 1 | 8500 | 8500 | 0 | 0
39 | Domestic RO - Providing and fixing of Domestic RO with water storage with all necessary valves and fiting required. | Nos. | 1 | 12500 | 12500 | 0 | 0
40 | Water Tank - Providing and fixing of 200 Ltr. Storage Loft Tank on MS Platform with all necessary valves and fiting required. | Nos. | 1 | 10000 | 10000 | 0 | 0
| Plumbing Work BOQ for LKN Budweiser bar |  |  |  | 287050 |  | 11742.5
| Total OF Civil Interior & Plumbing |  |  |  | 1233520 |  | 627684.321

## M Sheet
Sr No. | Item Description | UOM | Qty | Length | Width | Height | Nos | Qty | Remark
1 | Civil & Interior Work BOQ for LKN Budweiser bar | no | 1
1 | ANTI TERMITE TREATMENT - Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). AREA - ALL MOH FOH | Sq.m. | 225
1 | Add Area |  |  | 0.89 | 2.5 |  | 1 | 2.225
2 | FOH Area GF To GH |  |  | 0.8 | 3.5 |  | 1 | 2.8
3 | FOH Area ED To EJ |  |  | 2.85 | 5.96 |  | 1 | 16.986
4 | FOH Area CD To CL |  |  | 1.25 | 3.63 |  | 1 | 4.5375
5 | FOH Area SB To SM |  |  | 5.86 | 8.3 |  | 1 | 48.638
6 | FOH Area RO To ON |  |  | 8.98 | 5 |  | 1 | 44.9
7 | FOH Area AQ To PQ |  |  | 9.24 | 4 |  | 1 | 36.96
8 | FOH Area AQ To T |  |  | 9.74 | 3.85 |  | 1 | 37.499
9 | Kitchen AK - AB |  |  | 2.7 | 2.22 |  | 1 | 5.994
10 | Kitchen JI - JL |  |  | 7.77 | 2.54 |  | 1 | 19.7358
11 | Kitchen HC - CD |  |  | 1.85 | 3.55 |  | 1 | 6.5675
12 | Kitchen EF - FG |  |  | 1.45 | 0.6 |  | 1 | 0.87
[7 empty] | Total | 227.7128
2 | CIVIL WORK
3 | WATERPROOFING - Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. 1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring | Sq.m. | 98
| Kitchen AK - AB |  |  | 2.7 | 2.22 |  | 1 | 5.994
| Kitchen JI - JL |  |  | 7.77 | 2.54 |  | 1 | 19.7358
| Kitchen HC - CD |  |  | 1.85 | 3.54 |  | 1 | 6.549
| Kitchen EF - FG |  |  | 1.45 | 0.6 |  | 1 | 0.87
| Bar Side - HO - ON |  |  | 2.6 | 5.7 |  | 1 | 14.82
| Wall L To B |  |  | 2.85 |  | 0.4 | 1 | 1.14
| Wall A To B |  |  | 2.18 |  | 0.4 | 1 | 0.872
| Wall A To K |  |  | 2.18 |  | 0.4 | 1 | 0.872
| Wall P To K |  |  | 0.65 |  | 0.4 | 1 | 0.26
| Wall L To C |  |  | 7.6 |  | 0.4 | 1 | 3.04
| Wall J To I |  |  | 6.5 |  | 0.4 | 1 | 2.6
| Less Door J Tto I |  |  | 1.05 |  |  | -1 | -1.05
| Wall J To P |  |  | 0.8 |  | 0.4 | 1 | 0.32
| Wall I To C |  |  | 2.52 |  | 0.4 | 1 | 1.008
| Less Door I To C |  |  | 0.9 |  |  | -1 | -0.9
| Wall H To C |  |  | 1.89 |  | 0.4 | 1 | 0.756
| Less Door H To C |  |  | 0.9 |  |  | -1 | -0.9
| Wall C To D |  |  | 3.84 |  | 0.4 | 1 | 1.536
| Wall H To G |  |  | 5.07 |  | 0.4 | 1 | 2.028
| Wall F To G |  |  | 0.6 |  | 0.4 | 1 | 0.24
| Bar Wall O To H |  |  | 1.6 |  | 0.4 | 1 | 0.64
| Bar Wall H To G |  |  | 5.11 |  | 0.4 | 1 | 2.044
[7 empty] | Total | 62.4748
4 | CINDER LIGHT WT. SIPORAX BLOCK BATS FILLING
5 | Providing Filling light wt. Siporex block bats to conceal drainage plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. AREA - MOH RAISED AREA (up to 150 mm) | Sq.m. | 14
| Bar Side - HO - ON |  |  | 2.6 | 5.7 |  | 1 | 14.82
[7 empty] | Total | 14.82
6 | Providing Filling light wt. Siporex block bats to conceal drainage plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. AREA - BOH RAISED AREA (up to 300 mm) | Sq.m. | 39
| Kitchen AK - AB |  |  | 2.7 | 2.22 |  | 1 | 5.994
| Kitchen JI - JL |  |  | 7.77 | 2.54 |  | 1 | 19.7358
| Kitchen HC - CD |  |  | 1.85 | 3.54 |  | 1 | 6.549
| Kitchen EF - FG |  |  | 1.45 | 0.6 |  | 1 | 0.87
[7 empty] | Total | 33.1488
7 | PCC LAYER - Providing Laying P.C.C 1 3 6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 225
1 | FOH Area GF To GH |  |  | 0.8 | 3.5 |  | 1 | 2.8
2 | FOH Area ED To EJ |  |  | 2.85 | 5.96 |  | 1 | 16.986
3 | FOH Area CD To CL |  |  | 1.25 | 5.63 |  | 1 | 7.0375
4 | FOH Area SB To SM |  |  | 5.86 | 8.3 |  | 1 | 48.638
5 | FOH Area RO To ON |  |  | 8.98 | 5 |  | 1 | 44.9
6 | FOH Area AQ To PQ |  |  | 9.74 | 4 |  | 1 | 38.96
7 | FOH Area AQ To T |  |  | 9.74 | 3.85 |  | 1 | 37.499
8 | Kitchen AK - AB |  |  | 2.7 | 2.22 |  | 1 | 5.994
9 | Kitchen JI - JL |  |  | 7.77 | 2.54 |  | 1 | 19.7358
10 | Kitchen HC - CD |  |  | 1.85 | 3.54 |  | 1 | 6.549
11 | Kitchen EF - FG |  |  | 1.45 | 0.6 |  | 1 | 0.87
12 | Bar Side - HO - ON |  |  | 2.6 | 5.7 |  | 1 | 14.82
[7 empty] | Total | 244.7893
8 | Block WORK - Providing Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1 4 (1 cement 4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. AREA - 150 MM THICK BLOCK MASONARY | Sq.m. | 93
[7 empty] | Total | 0
9 | PLASTER - P L12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 185
| Wall AB |  |  | 2.23 |  | 2.6 | 1 | 5.798
| Wall BC |  |  | 10.635 |  | 2.6 | 1 | 27.651
| Wall CD |  |  | 2.5 |  | 2.6 | 1 | 6.5
| Less Door CD |  |  | 0.9 |  | 2.04 | -1 | -1.836
| Add Door Patta CD |  |  |  | 0.15 | 2.05 | 1 | 0.3075
|  |  |  | 0.9 | 0.15 |  | 1 | 0.135
| Wall DE |  |  | 8 |  | 2.6 | 1 | 20.8
| Less Door DE |  |  | 1.05 |  | 2.05 | -1 | -2.1525
| Add Door Patta DE - CI |  |  |  | 0.15 | 2.05 | 1 | 0.3075
|  |  |  | 1.05 | 0.15 |  | 1 | 0.1575
| Wall EF |  |  | 0.8 |  | 2.6 | 1 | 2.08
| Wall GF |  |  | 0.15 |  | 2.6 | 1 | 0.39
| Wall GH |  |  | 0.4 |  | 2.6 | 1 | 1.04
| Wall HA |  |  | 2.8 |  | 2.6 | 1 | 7.28
| Wall IC |  |  | 1.8 |  | 2.6 | 1 | 4.68
| Less Door IC |  |  | 0.09 |  | 2.05 | -2 | -0.369
| Wall CM |  |  | 3.56 |  | 2.6 | 1 | 9.256
| Wall JI |  |  | 4.99 |  | 2.6 | 1 | 12.974
[7 empty] | Total | 94.999
10 | RCC LINTEL BEAM - P L in place (cast in situ) RCC lintel beams in 150mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1 4 8) 100mm high with 4 no. s 8mm th. Steel bars as per general specifications, complete in all respects | Rm | 3
[7 empty] | Total | 0
11 | TILING WORKS, FLOORING
12 | Providing and laying of Anti-skid VITRIFIED Commercial floor tile of size 600 x 600 mm of approved make and Shade laid over 40 mm thick cement mortar 1 4 (1 cement 4 coarse sand) mix jointed with white cement slurry, mixed with pigment to match color of tile. Cost to include chamfering if any, cutting , edge rubbing etc., complete as per design and drawing, with 3 mm Spacers finished with Matching Epoxy Grouting. Necessary Protection by covering with PVC sheet shall be provided for Flooring till the handover of the Outlet.It has to meet the specs of RA level. Make Endura grey, Nitco (Basic Rate - 66 persqft) Anti-skid Commercial Tiles ( BOH Area) | Sq.m. | 50
| Kitchen AK - AB |  |  | 2.7 | 2.2 |  | 1 | 5.94
| Kitchen JI - IC |  |  | 7.77 | 2.54 |  | 1 | 19.7358
| Kitchen HC - CD |  |  | 1.85 | 3.54 |  | 1 | 6.549
| Kitchen EF - FG |  |  | 1.45 | 0.6 |  | 1 | 0.87
[7 empty] | Total | 33.0948
13 | Providing and laying of White Ceramic- 600m.m x 300m,m Tiles on Wall with 1 4 Cement Moratar with 3m.m Spacers .This Include Cutting Fixing of Electrical Boxes , Plumbing Fixtures others . with Matching Epoxy Groutings neat Clean in all respects 1Rate includes Cutting all wastage, underlay as required, treatment of corners and finishing as per the instruction of the Project Manager.Top Portion of the Skirting to be Neatly Grouted .Finishsed AREA - WALLS TILES KITCHEN BOH | Sq.m. | 100
| Wall AB |  |  | 2.23 |  | 2.6 | 1 | 5.798
| Wall BC |  |  | 10.635 |  | 2.6 | 1 | 27.651
| Wall CD |  |  | 2.5 |  | 2.6 | 1 | 6.5
| Less Door CD |  |  | 0.9 |  | 2.04 | -1 | -1.836
| Add Door Patta CD |  |  |  | 0.15 | 2.05 | 2 | 0.615
|  |  |  | 0.9 | 0.15 |  | 1 | 0.135
| Wall DE |  |  | 8 |  | 2.6 | 1 | 20.8
| Less Door DE |  |  | 1.05 |  | 2.05 | -1 | -2.1525
| Add Door Patta DE - CI |  |  |  | 0.15 | 2.05 | 1 | 0.3075
|  |  |  | 1.05 | 0.15 |  | 1 | 0.1575
| Wall EF |  |  | 0.8 |  | 2.6 | 1 | 2.08
| Wall GF |  |  | 0.15 |  | 2.6 | 1 | 0.39
| Wall GH |  |  | 0.4 |  | 2.6 | 1 | 1.04
| Wall HA |  |  | 2.8 |  | 2.6 | 1 | 7.28
| Wall IC |  |  | 1.8 |  | 2.6 | 1 | 4.68
| Less Door IC |  |  | 0.09 |  | 2.05 | -1 | -0.1845
| Wall CM |  |  | 3.5 |  | 2.6 | 1 | 9.1
| Wall KJ |  |  | 0.6 |  | 2.6 | 1 | 1.56
| Wall JI |  |  | 4.99 |  | 2.6 | 1 | 12.974
[7 empty] | Total | 96.895
14 | Providing Fixing of S.S.304 Corner Angles Z Type 40m.m x 40mm Thickness 1.5m.m on Walls for the Ceramic Wall Tiles Complete in all Respects AREA - S.S Corner Angles in 304 Grade 40m.m x 40m.m | Rm | 3
Add Door Patta CD
Add Door Patta DE - CI
Add Door Patta ML
[7 empty] | Total | 0
15 | Providing and fixing of 19 mm thk. Black Granite Jamb in floor wall over a bed of 20 mm thk. Cement mortar 1 4 (1 Cement 4 coarse sand) joints filled with epoxy adhesive to match the color of granite. Rate shall be including polished granite, necessary wastage, cutting, edge grinding and polishing as per the instructions of the Project Manager, complete. Width of Jamb 200 mm.Basic Door Jambs in Granite - BOH Area | Rm | 2
Add Door Patta CD
Add Door Patta DE - CI
Add Door Patta ML
[7 empty] | Total | 0
16 | CEILINGS (BOH)
17 | Providing fixing Metal Grid False ceiling 2 x 2 in plain metal powder coated 24 mm wide sectionfinish as per approved colour. The system to be Lay-in- type. There should be M.S. channel for every 3rd GRID to completed as per details design given in drawing Architect instruction. Note - Corner cutting tiling should be moulding. Make Vendor Armstrong USG AREA - METAL GRID CEILING | Sq.m. | 40
[7 empty] | Total | 0
Civil & Interior Work BOQ for LKN Budweiser bar
2 | Plumbing Work BOQ for LKN Budweiser bar | no | 1
18 | WATER SUPPLY PIPES CPVC Pipes Supply, laying, testing commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia. (Make – SUPREME KASTA) including all necessary fitting as per site.
19 | 15mm dia | R.M. | 25
[7 empty] | Total | 0
20 | 20mm dia | R.M. | 45
[7 empty] | Total | 0
21 | WATER DRAIN PIPES- UPVC WASTE PIPE - UPVC Pipe for Drainage (Make – SUPREME KASTA) including all necessary fitting as per site.
22 | 100mm dia | R.M. | 25
| Chember 1 to A |  |  | 0.8 |  |  | 1 | 0.8
| Chember 1 to B |  |  | 1.4 |  |  | 1 | 1.4
| Chember 1 to C |  |  | 0.8 |  |  | 1 | 0.8
| Chember 1 to Chember 2 |  |  | 5 |  |  | 1 | 5
| Chember 2 to Chember 3 |  |  | 4.9 |  |  | 1 | 4.9
| Chember E |  |  | 1.65 |  |  | 1 | 1.65
| Chember F |  |  | 2.9 |  |  | 1 | 2.9
| Chember G |  |  | 2.6 |  |  | 1 | 2.6
| Chember H |  |  | 1.3 |  |  | 1 | 1.3
[7 empty] | Total | 21.35
23 | 50mm dia | R.M. | 5
[7 empty] | Total | 0
24 | CHAMBER GRATING INSPECTION CHAMBER- Supply, Laying, Testing Commissioning of Approved SS Inspection Chamber along of Size- 300mmx300mm with SS Cover SS Grating over it. Make Jaquar Ozone. Including trenching and finishing with ceramic tiles as per dwg and details. | Nos. | 3
[7 empty] | Total | 0
25 | FLOOR TRAP - Supply, Laying, Testing Commissioning of 100x100mm Floor Trap with Approved Make heavy duty round or Square. | Nos. | 6
[7 empty] | Total | 0
26 | VALVE AND TAP
27 | ANGLE VALVE - Providing Fixing Angle Valve with connector pipe. | Nos. | 10
[7 empty] | Total | 0
28 | LONG BODY TAP - Providing Fixing Sink Cock. with foot operated | Nos. | 1
[7 empty] | Total | 0
29 | Table Mixer - Providing Fixing Sink Cock. | Nos. | 3
[7 empty] | Total | 0
30 | Gate Valves - Providing Fixing PPR Ball Valve ISI mark. (For Inlet) | Nos. | 1
[7 empty] | Total | 0
31 | ACCESSORIES
32 | Grease Trap - Providing Fixing of portable grease trap NGT-8 from Nugreen | Nos. | 3
[7 empty] | Total | 0
33 | Bottle Trap - Providing fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR OZONE) | Nos. | 3
[7 empty] | Total | 0
34 | Water Meter 25mm Dia Water meter | Nos. | 1
[7 empty] | Total | 0
35 | GEYSER - 6 LITER GEYSER | Nos. | 2
[7 empty] | Total | 0
36 | Waste Coupling - Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. | Nos. | 1
[7 empty] | Total | 0
37 | Water supply connection - water supply connection taken from existing point complete with all necessary fittings. | Nos. | 1
[7 empty] | Total | 0
38 | Drainage connection - Drainage connection connect to existing drain point complete with all necessary fittings including cleanout plug | Nos. | 1
[7 empty] | Total | 0
39 | Domestic RO - Providing and fixing of Domestic RO with water storage with all necessary valves and fiting required. | Nos. | 1
[7 empty] | Total | 0
40 | Water Tank - Providing and fixing of 200 Ltr. Storage Loft Tank on MS Platform with all necessary valves and fiting required. | Nos. | 1
[7 empty] | Total | 0
Plumbing Work BOQ for LKN Budweiser bar
Total OF Civil Interior & Plumbing