## Summary
Semolina Projects
Project : Mad Over Donuts NT Items
Details : Project Invoicing
PO No.: Semolina/PO/24-25/000803
MAD OVER DONUTS - BILL SUMMARY
S. No. | Items | PO Value | Previous Bills | This Bill | Cumulative | Varition (In Amount)
1 | NT items of Civil Interior work | 282637 | 0 | 282637 | 282637 | 0
| Subtotal | 282637 |  | 282637 | 282637
| GST @ 18% | 50874.66 |  | 50874.66 | 50874.66
| Grand Total | 333511.66 |  | 333511.66 | 333511.66

## NON PO Items Abstract Sheet
MOD - NON PO ITEMS
SN | LOCATION | ITEM DESCRIPTION | UNIT | BOQ Qty | Rate | RA Quantity |  |  | Amount
[6 empty] | Previous Bill | This Bill | Up to Date | Previous Bill | This Bill | Up to Date | Varition
1 | Façade Bulk Head | Providing and fixing of Bulkhead made of 12 mm thk ply with frame work of grid size 1.5x1.5 finished with orange paint of aproved shade, pannels fixed properly without any cavity or undulations. To inch thk Portal for running profile light on the edges & on top fornt smooth surface of 300 mm white for recieving toughned glass with all screw fashners etc complete. | SQFT | 60 | 2000 | 0 | 60 | 60 | 0 | 120000 | 120000
2 | Electric Meter | P/F Secure Prepaid Meter 3P (10-100A) Liberty 370 | Nos | 1 | 19500 | 0 | 1 | 1 | 0 | 19500 | 19500
Previously Approved Rate
3 | Signage Connection | P/L 3x2.5 sqm FRLS wire, MS Conduit with 10Amp MCB from main DB to the outer bulkhead | Job | 1 | 4800 | 0 | 1 | 1 | 0 | 4800 | 4800
4 | Seating Area Tiles | P/L 600x600 mm Vetrified Floor Tiles | SQFT | 343.76 | 180 | 0 | 343.76 | 343.76 | 0 | 61876.8 | 61876.8
5 | Brick Pattern Tiles | P/L 50x230 mm Brick Pattern Tiles with 3 mm Spacer | SQFT | 177.59 | 380 | 0 | 177.59 | 177.59 | 0 | 67484.2 | 67484.2
6 | Electrical Conduit | P/L MS Conduit 25 mm Dia in Seating Area | RFT | 112.2 | 80 | 0 | 112.2 | 112.2 | 0 | 8976 | 8976
|  |  | TOTAL |  |  |  |  | 695.55 |  | 282637 | 282637

## NON PO Items MB Sheet
MOD - NON PO ITEMS MB
SN | LOCATION | ITEM DESCRIPTION | UNIT | L | B | H | QUANTITY | SING
1 | Façade Bulk Head | Providing and fixing of Bulkhead made of 12 mm thk ply with frame work of grid size 1.5x1.5 finished with orange paint of aproved shade, pannels fixed properly without any cavity or undulations. To inch thk Portal for running profile light on the edges & on top fornt smooth surface of 300 mm white for recieving toughned glass with all screw fashners etc complete. | SQFT | 30 | 2 |  | 60
2 | Electric Meter | P/F Secure Prepaid Meter 3P (10-100A) Liberty 370 | Nos |  |  |  | 1
3 | Signage Connection | P/L 3x2.5 sqm FRLS wire, MS Conduit with 10Amp MCB from main DB to the outer bulkhead | Job |  |  |  | 1
4 | Seating Area Tiles | P/L 600x600 mm Vetrified Floor Tiles | SQFT | 37.4 | 4.75 |  | 177.65
|  |  |  | 8.26 | 6.41 |  | 52.9466
|  |  |  | 8.8 | 12.86 |  | 113.168
|  |  |  | Total |  |  | 343.7646
5 | Brick Pattern Tiles | P/L 50x230 mm Brick Pattern Tiles with 3 mm Spacer | SQFT | 21.5 | 8.26 |  | 177.59
6 | Electrical Conduit | P/L MS Conduit 25 mm Dia in Seating Area | RFT | 112.2 |  |  | 112.2