## Bill Summary
Semolina Projects
Project : Mad Over Donuts
Details : Project Invoicing
PO No.: PO/23-24/000534
MAD OVER DONUTS - BILL SUMMARY
S. No. | Items | PO Value | Previous Bills | This Bill | Cumulative | Varition (In Amount)
1 | Wet Work of Water proofing and Wall | 82825 | 0 | 66794.2 | 66794.2 | 0
2 | Carpentry Work | 399475 | 0 | 324870 | 324870 | 0
3 | Civil & Interior Work | 371700 | 0 | 188344 | 188344 | 0
4 | Electrical Work | 199600 | 0 | 172900 | 172900 | 0
5 | Plumbing Work | 39000 | 0 | 31500 | 31500 | 0
6
| Subtotal | 1092600 |  | 784408.2 | 784408.2
| GST @ 18% | 196668 |  | 141193.476 | 141193.476
| Grand Total | 1289268 |  | 925601.676 | 925601.676

## C&I Abstract
MOD BOQ ABSTRACT
WET WORK
| SN. | AREA | ITEM | UNIT | QTY. | RATE | RA QUANTITY |  |  | AMOUNT |  |  | REMARK
[7 empty] | Previous Bill | This Bill | Upto Date | Previous Bill | This Bill | Upto Date
| 1 |  | ANTI TERMITE TREATMENT
| 1.1 | ALL MOH & FOH | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | Sq.m. | 15 | 15 | 0 | 15 | 15 |  | 225 | 225
SUB TOTAL OF ANTI TERMITE TREATMENT
2
| 2.1 |  | WATERPROOFING
|  |  | Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. | Sq.m. | 32 | 700 |  | 17.6 | 17.6 |  | 12320 | 12320
1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush & Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions & on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface & Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope & main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring
| 2.2 |  | CINDER/ LIGHT WT. SIPORAX BLOCK BATS FILLING
| a | MOH RAISED AREA (up to 75 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m. | 7 | 1200 |  | 7 | 7 |  | 8400 | 8400
| b | MOH RAISED AREA (up to 600 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m.
| 2.3 |  | PCC LAYER
|  |  | Providing & Laying P.C.C 1:3:6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement :3 coarse sand:6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 17.55 | 350 |  | 8 | 8 |  | 2800 | 2800
| 2.4 |  | Block WORK
|  | 150 MM THICK BLOCK MASONARY | Providing & Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1:4 (1 cement :4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. | Sq.m. | 11.2 | 2100 |  | 11.128 | 11.128 |  | 23368.8 | 23368.8
| 2.5 |  | PLASTER
|  |  | P/L12-15mm thick plaster in cement mortar 1:4 (1 cement : 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 28 | 550 |  | 24.328 | 24.328 |  | 13380.4 | 13380.4
| 2.6 | RCC LINTEL BEAM | P/L in place (cast in situ) RCC lintel beams in 150mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1:4:8) 100mm high with 4 no.'s 8mm th. Steel bars as per general specifications, complete in all respects | Rmt | 10 | 700 |  | 9 | 9 |  | 6300 | 6300
[9 empty] | TOTAL |  | 66794.2 | 66794.2
CARPENTRY WORK
| SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY | RATE | RA QUANTITY |  |  | AMOUNT |  |  | REMARK
[7 empty] | Previous Bill | This Bill | UpTo Date | Previous Bill | This Bill | UpTo Date
| 1 | WOODEN PARTITION FOR BACK STORE | Providing and fixing of 75mm partition upto false ceiling height consisting of wooden partition with 12mm commercial ply with 1.5" x 2" Aluminium framing with inside approved laminate. (GreenLam - 5080 PURE ELM) | SQFT | 94 | 600 | 0 | 93.6 | 93.6 |  | 56160 | 56160
| 2 | MERCHANDISING WALL SHELF | Providng and fixing Wooden shelves with laminate finish on the back partiton wall as shown in the 3D views. The shelves will have profile light fit by creating a niche and flushed to the bottom of the shelves. L - 3' x W - 7" x H - 2" (GreenLam - 5080 PURE ELM) | Nos | 2 | 30000 | 0 | 2 | 2 |  | 60000 | 60000
| 3 | TV FITTING | Providing and fixing TV BRACKET WITH TV INSTALLATION. Single SS structure of 2" x 2" with ply boxing finished with white laminate for fixing the TV screens. | NOS | 1 | 6000 | 0 | 1 | 1 |  | 6000 | 6000
| 4 | POS | Providing and Fixing Customer interface Counter POS with drawers and shutters and will have louver grills for ventilation as per drawing.The counter will be finished in 18mm thk ply with basic white laminate finish inside while the top and front will be finished in White Corian as per the drawings. (Corian Make - LG) (L - 14'9" x W - 1'11" x H - 3') | SQFT | 14.5 | 5000 | 0 | 14.49 | 14.49 |  | 72450 | 72450
| 5 | BACK COUNTER TABLE | Providing and fixing of 18mm ply with white marble top for accomodating the coffee machine, blender, etc. The counter to have shelves and shutters as shown in the elevations. A cutout to be made in the marble top to fit a SS sink as per dimensions shown in layout. The counter dimensions L - 9'2" x W - 2' x H - 3' Marble used to be of approx 600/SqFt cost, plain white colour | SQFT | 27 | 2500 | 0 | 27 | 27 |  | 67500 | 67500
| 6 | FAÇADE BULKHEAD | Providing and fixing of bulkhead made of 1.5 x 1.5 aluminium frame work with a grid of 1.5x1.5 feet finished with brand approved ACP panels fixed properly without any cavity or undulations. The edges to be nicely finished with matching colour silicon and all edges to be prevented from water seepage. Use of ply for ACP backing is not required. 2 inch portal thick portal for running profile light on the edges. Orange ACP - Eurobond - Super Bond - SB 331 Purple ACP - Eurobond - Ruby - ER 139 | SQFT | 25
| 7 | WOODEN COUNTER | The counter under the glass display of L - 6' x W - 2' x H - 1'6" will be finished in 18mm thk ply with open drawers and with 1 nos box packing tray. The inside of the fixture will be finished in basic black laminate and outside finished in brand approved White Corian (Make - LG). Note : Rate should be inclusive of all Hardware, Polish and laminate finish , as per drawing | SQFT | 12 | 2500 | 0 | 12 | 12 |  | 30000 | 30000
| 8 | Display GLASS | Providing and Fixing Customer interface Counter of L - 6' x W - 2' x H - 20". The counter will finished in 12mm thik extra clear toughened glass, the base will be back painted white glass fixed with UV lighting and 25mm X 25mm hollow box section in matt 305 SS frame work. With profile lights Note : Rate should be inclusive of all hardware, polish,LED lights and paint. | SQFT | 12
| 9 | BACK STORE DOOR | Providing and fixing of back store room door made of 35mm thick solid core flush single shutter door with approved laminate finish on inside and outside will be finished in TEAL colour paint to match the backpainted glass. Rate to be included with all hardwares, handle, door stopper, lock, etc. ( L - 2'6" x H - 7' ) | SqFt | 18 | 1800 | 0 | 18.2 | 18.2 |  | 32760 | 32760
| 10 | BOARDOUT | Providing and fixing of only the flex on existing board out | SQFT | 143
| 11 | BACK PAINTED GLASS | Providing and fixing of TEAL BACK PAINTED 6 mm thick toughened glass on the wall in FOH area as shown in the elevations. ( Teal colour - 9272 Green Wave - Asian Paint) | sqft | 52
| 12 | DUSTBIN | Providing and installing of SS dustbin with a front frame of 12mm ply with a door and flap at the front to dispose garbage into the bin. | SQFT | 6
| 13 | SS L ANGLE | Proving & Fixing 3 Inches SS L – Patti for corner wall edge protection ( 12x12 mm or 6x6 mm ) | RFT | 30
[9 empty] | TOTAL |  | 324870 | 324870
CIVIL WORK ABSTRACT
| SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY | RATE | RA QAUNTITY |  |  | AMOUNT |  |  | REMARK
[7 empty] | Previous Bill | This Bill | Upto Date | Previous Bill | This Bill | Upto Date
| 1 | Debris | Debris Truck | Nos | 2 | 2000 | 0 | 2 | 2 | 0 | 4000 | 4000
| 2 | Pest control | Providing Pest control and Anti-termite treatment by appointing a specialised agency as per the specifications mentioned by the Bureau of Indian Standards (Mode of measurement to be on carpet-area of floor) | SQFT | 192 | 15
| 3 | WATER PROOFING | Providing and applying of chemical water proofing in complete store to prevent any kind of seepage or leakage due to the usage of water. The chemical to be applied throught the back area flooring and upto 4 feet of wall height. | SQFT | 318 | 500
| 4 | WALL TILES FOR BACK AREA | Providing , Fixing Vitrified tile of 18” X 12” in Dado as detailed in drawing. Tile to be fixed with cement paste over surface including , joints to be cleaned and grouted with matching colour approved epoxy based grout, curing, cleaning, including making cut-outs for plumbing and electrical points, any sleeves in tiles, scaffolding,etc. to required line, level, etc. all complete at all heights, lifts and leads to the entire satisfaction of the Project Head.(Make: KAJARIA/SOMANY - WHITE GLOSSY) | SQFT | 323 | 180 | 0 | 323 | 323 | 0 | 58140 | 58140
| 5 | VITRIFIED TILE FLOORING | Providing and laying matt finish vitrified floor tiles with water absorption less than 0.08% , of approved make, laid on 20mm thick cement mortar 1:4 (1 cement : 4 coarse sand), jointing with grey cement slurry @ 3.3 kg/ sqm including grouting the joints with white cement and matching pigments etc., complete. Tile Size: 600x600mm (Nitco - Vega Silver) | SQFT | 192 | 250 |  | 186.69 | 186.69 |  | 46672.5 | 46672.5
| 6 | BRICK TILE ON WALLS | Providing and laying of brick pattern tiles on the walls in the retail FOH area as sown in the detaile drawings. Tile to be fixed with cement paste over surface including , joints to be cleaned and grouted with matching colour approved epoxy based grout, curing, cleaning, including making cut-outs for plumbing and electrical points, any sleeves in tiles, scaffolding,etc. to required line, level, etc. all complete at all heights, lifts and leads to the entire satisfaction of the Project Head. (White brick tile Morbi Make) | SQFT | 184 | 260 |  | 112.02 | 112.02 |  | 29125.2 | 29125.2
| 8 | GYPSUM FALSE CEILING | Providing and fixing 12mm thk gypsum board (India Gypsum) false ceiling as per design and details on G.I. metal frame as per manufacturer's specification (India Gypsum) & drawing. Main GI Channels at 3' 0" c/c and secondary channels at 2'-0" c/c spacing, GI adjustable suspenders 4' C/C or Screwing as per design & drawings ,GI anchor fastener/Screws,GI L patti at wall junction including all jointing material, ceiling finishing, making grooves, making lighting coffers, making openings for light fitting with required GI framing wherever required, scaffolding, making dhar and surface finished & prepared to paint as per approved drawing | SQFT | 192 | 160 |  | 186.69 | 186.69 |  | 29870.4 | 29870.4
| 9 | PAINTING | Providing and applying 3 coats of Royal washable /PLASTIC/ACRYLIC EMULSION and oil Paint on ceiling, of approved shade. | SQFT | 192 | 110 |  | 186.69 | 186.69 |  | 20535.9 | 20535.9 | PAINTING WORK IS DONE
[9 empty] | TOTAL |  | 188344 | 188344
ELECTRICAL ABSTRACT
| SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY | RATE | RA QAUNTITY |  |  | AMOUNT
[7 empty] | Previous Bill | This Bill | UpTo Date | Previous Bill | This Bill | UpTo Date
| 16 | ELECTRICAL WORKS | Providing & Fixing electrical FRLS wiring with switch sockets (Make - Roma), led light fittings (Make – Philips/syska), circuits conduit, wiring & boards with switch (Roma). Data (make - D link), Electrical wire, camera wire , Polycab/ RR wiring etc complete, MCB and RCCB & 7 SEGMENT DB (Make - Legrand make.all electrical conduits will be in MS . Inclusive LED Lights , TRACK LIGHTS , profile patti with lights , Hanging lights ceiling lights etc. | SQFT | 192 | 800 | 0 | 188 | 188 | 0 | 150400 | 150400
|  | CEILING LIGHTS | Providing and fixing of round ceiling COB lights of 30W HYBEC / Philips / Syska / Focus ( 4000K ) | Nos | 18 | 1500 | 0 | 15 | 15 | 0 | 22500 | 22500
|  | MISCELLANEOUS WORK | LIT Exit signage | Nos | 1 |  |  | - | -
|  |  | Electrical rubber matt | Nos | 1 |  |  | - | -
|  |  | Caution Signages | Nos | 4 |  |  | - | -
[9 empty] | TOTAL |  | 172900 | 172900
PLUMBING ABSTRACT
| SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY | RATE | RA QAUNTITY |  |  | AMOUNT
[7 empty] | Previous Bill | This Bill | UpTo Date | Previous Bill | This Bill | UpTo Date
|  | PLUMBING WORK | P&F Necessary Plumbing Connection with conceal pvc Pipe & angle cock mixture completed, nahani trap, grease trap with all necessary fittings and water meter as directed with drainage system(as per required) | RM | 5 | 7000 | 0 | 4.5 | 4.5 | 0 | 31500 | 31500
|  |  | Providing & Fixing Sink Mixer Seiko | Nos | 1 | 1500 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | TOTAL |  | 31500
| GRAND TOTAL (WET WORK+CARPENTRY WORK+CIVIL WORK+ ELECTRICAL WORK+PLUMBING WORK) | [5 empty] | 784408.2

## C&I MB
MOD BOQ MB SHEET
WET WORK
| SN. | AREA | ITEM | UNIT | QTY. |  | L | B | H | RA QTY. | SIGN
| 1 |  | ANTI TERMITE TREATMENT
| 1.1 | ALL MOH & FOH | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). | Sq.m. | 15 |  | 3.7 | 4 |  | 15
SUB TOTAL OF ANTI TERMITE TREATMENT
2
| 2.1 |  | WATERPROOFING
|  |  | Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. | Sq.m. | 32 |  | 4.4 | 4 |  | 17.6
1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush & Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions & on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface & Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope & main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring
| 2.2 |  | CINDER/ LIGHT WT. SIPORAX BLOCK BATS FILLING
| a | MOH RAISED AREA (up to 75 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m. | 7 |  | 1.75 | 4 |  | 7
| b | MOH RAISED AREA (up to 600 mm) | Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. | Sq.m.
| 2.3 |  | PCC LAYER
|  |  | Providing & Laying P.C.C 1:3:6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement :3 coarse sand:6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 17.55 |  | 2 | 4 |  | 8
| 2.4 |  | Block WORK
|  | 150 MM THICK BLOCK MASONARY | Providing & Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1:4 (1 cement :4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. | Sq.m. | 11.2 |  |  | 4 | 3.2 | 12.8
|  |  |  | Deduction |  |  | Door | 2.2 | -0.76 | -1.672
| 2.5 |  | PLASTER |  |  |  |  | Total |  | 11.128
|  |  | P/L12-15mm thick plaster in cement mortar 1:4 (1 cement : 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 28 |  |  | 4 | 3.2 | 12.8
[8 empty] | 4 | 3.3 | 13.2
|  |  |  | Deduction |  |  |  | 2.2 | -0.76 | -1.672
[8 empty] | Total |  | 24.328
| 2.6 | RCC LINTEL BEAM | P/L in place (cast in situ) RCC lintel beams in 150mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1:4:8) 100mm high with 4 no.'s 8mm th. Steel bars as per general specifications, complete in all respects | Rmt | 10 |  |  | 9 |  | 9
CARPENTRY WORK RA 1st
| SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY |  | L | B | H | RA QTY | SING
| 1 | WOODEN PARTITION FOR BACK STORE | Providing and fixing of 75mm partition upto false ceiling height consisting of wooden partition with 12mm commercial ply with 1.5" x 2" Aluminium framing with inside approved laminate. (GreenLam - 5080 PURE ELM) | SQFT | 93.6 |  | 12.7 |  | 10.1 | 128.27
[7 empty] | -7.1 |  | 2.4 | -17.04
[8 empty] | Total |  | 111.23
[8 empty] | BOQ Qty |  | 93.6
[8 empty] | Extra Qty |  | 17.63
| 2 | MERCHANDISING WALL SHELF | Providng and fixing Wooden shelves with laminate finish on the back partiton wall as shown in the 3D views. The shelves will have profile light fit by creating a niche and flushed to the bottom of the shelves. L - 3' x W - 7" x H - 2" (GreenLam - 5080 PURE ELM) | Nos | 2 |  |  |  |  | 2
| 3 | TV FITTING | Providing and fixing TV BRACKET WITH TV INSTALLATION. Single SS structure of 2" x 2" with ply boxing finished with white laminate for fixing the TV screens. | NOS | 1 |  |  |  |  | 1
| 4 | POS | Providing and Fixing Customer interface Counter POS with drawers and shutters and will have louver grills for ventilation as per drawing.The counter will be finished in 18mm thk ply with basic white laminate finish inside while the top and front will be finished in White Corian as per the drawings. (Corian Make - LG) (L - 14'9" x W - 1'11" x H - 3') | SQFT | 14.5 |  | 4.83 |  | 3 | 14.49
| 5 | BACK COUNTER TABLE | Providing and fixing of 18mm ply with white marble top for accomodating the coffee machine, blender, etc. The counter to have shelves and shutters as shown in the elevations. A cutout to be made in the marble top to fit a SS sink as per dimensions shown in layout. The counter dimensions L - 9'2" x W - 2' x H - 3' Marble used to be of approx 600/SqFt cost, plain white colour | SQFT | 27 |  | 9 |  | 3 | 27
| 6 | FAÇADE BULKHEAD | Providing and fixing of bulkhead made of 1.5 x 1.5 aluminium frame work with a grid of 1.5x1.5 feet finished with brand approved ACP panels fixed properly without any cavity or undulations. The edges to be nicely finished with matching colour silicon and all edges to be prevented from water seepage. Use of ply for ACP backing is not required. 2 inch portal thick portal for running profile light on the edges. Orange ACP - Eurobond - Super Bond - SB 331 Purple ACP - Eurobond - Ruby - ER 139 | SQFT | 25
| 7 | WOODEN COUNTER | The counter under the glass display of L - 6' x W - 2' x H - 1'6" will be finished in 18mm thk ply with open drawers and with 1 nos box packing tray. The inside of the fixture will be finished in basic black laminate and outside finished in brand approved White Corian (Make - LG). Note : Rate should be inclusive of all Hardware, Polish and laminate finish , as per drawing | SQFT | 12 |  | 6 |  | 2 | 12
| 8 | Display GLASS | Providing and Fixing Customer interface Counter of L - 6' x W - 2' x H - 20". The counter will finished in 12mm thik extra clear toughened glass, the base will be back painted white glass fixed with UV lighting and 25mm X 25mm hollow box section in matt 305 SS frame work. With profile lights Note : Rate should be inclusive of all hardware, polish,LED lights and paint. | SQFT | 12
| 9 | BACK STORE DOOR | Providing and fixing of back store room door made of 35mm thick solid core flush single shutter door with approved laminate finish on inside and outside will be finished in TEAL colour paint to match the backpainted glass. Rate to be included with all hardwares, handle, door stopper, lock, etc. ( L - 2'6" x H - 7' ) | SqFt | 17.5 |  | 2.6 | 7 |  | 18.2
| 10 | BOARDOUT | Providing and fixing of only the flex on existing board out | SQFT | 143
| 11 | BACK PAINTED GLASS | Providing and fixing of TEAL BACK PAINTED 6 mm thick toughened glass on the wall in FOH area as shown in the elevations. ( Teal colour - 9272 Green Wave - Asian Paint) | sqft | 52
| 12 | DUSTBIN | Providing and installing of SS dustbin with a front frame of 12mm ply with a door and flap at the front to dispose garbage into the bin. | SQFT | 6
| 13 | SS L ANGLE | Proving & Fixing 3 Inches SS L – Patti for corner wall edge protection ( 12x12 mm or 6x6 mm ) | RFT | 30
TOTAL
CIVIL WORK
| SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY | LOCATION | L | B | H | RA QTY | SIGN | REMARK
| 1 | Debris | Debris Truck | Nos | 2 |  |  |  |  | 2
| 2 | Pest control | Providing Pest control and Anti-termite treatment by appointing a specialised agency as per the specifications mentioned by the Bureau of Indian Standards (Mode of measurement to be on carpet-area of floor) | SQFT | 192 |  | 13.2 | 14.8 |  | 0
| 3 | WATER PROOFING | Providing and applying of chemical water proofing in complete store to prevent any kind of seepage or leakage due to the usage of water. The chemical to be applied throught the back area flooring and upto 4 feet of wall height. | SQFT | 318 |  | 14.2 | 15.8 |  | 0
| 4 | WALL TILES FOR BACK AREA | Providing , Fixing Vitrified tile of 18” X 12” in Dado as detailed in drawing. Tile to be fixed with cement paste over surface including , joints to be cleaned and grouted with matching colour approved epoxy based grout, curing, cleaning, including making cut-outs for plumbing and electrical points, any sleeves in tiles, scaffolding,etc. to required line, level, etc. all complete at all heights, lifts and leads to the entire satisfaction of the Project Head.(Make: KAJARIA/SOMANY - WHITE GLOSSY) | SQFT | 323 | BACK WALL | 12.7 |  | 9.7 | 123.19
[6 empty] | FRONT WALL | 12.7 |  | 9.7 | 123.19
[6 empty] | RIGHT WALL | 6 |  | 9.7 | 58.2
[6 empty] | LEFT WALL | 6 |  | 9.7 | 58.2
[6 empty] | DEDUCTION | 2.6 |  | -7.8 | -20.28
[8 empty] | Total |  | 342.5
[8 empty] | BOQ Qty |  | 323
[8 empty] | Extra Qty |  | 19.5
| 5 | VITRIFIED TILE FLOORING | Providing and laying matt finish vitrified floor tiles with water absorption less than 0.08% , of approved make, laid on 20mm thick cement mortar 1:4 (1 cement : 4 coarse sand), jointing with grey cement slurry @ 3.3 kg/ sqm including grouting the joints with white cement and matching pigments etc., complete. Tile Size: 600x600mm (Nitco - Vega Silver) | SQFT | 192 |  | 12.7 | 14.7 |  | 186.69
| 6 | BRICK TILE ON WALLS | Providing and laying of brick pattern tiles on the walls in the retail FOH area as sown in the detaile drawings. Tile to be fixed with cement paste over surface including , joints to be cleaned and grouted with matching colour approved epoxy based grout, curing, cleaning, including making cut-outs for plumbing and electrical points, any sleeves in tiles, scaffolding,etc. to required line, level, etc. all complete at all heights, lifts and leads to the entire satisfaction of the Project Head. (White brick tile Morbi Make) | SQFT | 184 | RIGHT WALL | 10.1 | 5.1 |  | 51.51
[6 empty] | LEFT WALL | 10.1 | 5.1 |  | 51.51
[6 empty] | COUNTER WALL | 9 | 1 |  | 9
[7 empty] | TOTAL |  |  | 112.02
| 8 | GYPSUM FALSE CEILING | Providing and fixing 12mm thk gypsum board (India Gypsum) false ceiling as per design and details on G.I. metal frame as per manufacturer's specification (India Gypsum) & drawing. Main GI Channels at 3' 0" c/c and secondary channels at 2'-0" c/c spacing, GI adjustable suspenders 4' C/C or Screwing as per design & drawings ,GI anchor fastener/Screws,GI L patti at wall junction including all jointing material, ceiling finishing, making grooves, making lighting coffers, making openings for light fitting with required GI framing wherever required, scaffolding, making dhar and surface finished & prepared to paint as per approved drawing | SQFT | 192 |  | 12.7 | 14.7 |  | 186.69
| 9 | PAINTING | Providing and applying 3 coats of Royal washable /PLASTIC/ACRYLIC EMULSION and oil Paint on ceiling, of approved shade. | SQFT | 192 |  | 12.7 | 14.7 |  | 186.69 |  | PAINTING WORK IS DONE
ELECTRICAL RA
| SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY | RA Qty |  | SIGN
| 16 | ELECTRICAL WORKS | Providing & Fixing electrical FRLS wiring with switch sockets (Make - Roma), led light fittings (Make – Philips/syska), circuits conduit, wiring & boards with switch (Roma). Data (make - D link), Electrical wire, camera wire , Polycab/ RR wiring etc complete, MCB and RCCB & 7 SEGMENT DB (Make - Legrand make.all electrical conduits will be in MS . Inclusive LED Lights , TRACK LIGHTS , profile patti with lights , Hanging lights ceiling lights etc. | SQFT | 192 | 188
|  | CEILING LIGHTS | Providing and fixing of round ceiling COB lights of 30W HYBEC / Philips / Syska / Focus ( 4000K ) | Nos | 18 | 15
|  | MISCELLANEOUS WORK | LIT Exit signage | Nos | 1 | -
|  |  | Electrical rubber matt | Nos | 1 | -
|  |  | Caution Signages | Nos | 4 | -
PLUMBING BILL
| SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY | RA Qty |  | SIGN
|  | PLUMBING WORK | P&F Necessary Plumbing Connection with conceal pvc Pipe & angle cock mixture completed, nahani trap, grease trap with all necessary fittings and water meter as directed with drainage system(as per required) | RM | 5 | 4.5
|  |  | Providing & Fixing Sink Mixer Seiko | Nos | 1 | -

## EXTRA QUANTITY
EXTRA QUANTITY
SN | LOCATION | ITEM DESCRIPTION | UNIT | QUANTITY | RATE |  |  | AMOUNT
1 | WOODEN PARTITION FOR BACK STORE | Providing and fixing of 75mm partition upto false ceiling height consisting of wooden partition with 12mm commercial ply with 1.5" x 2" Aluminium framing with inside approved laminate. (GreenLam - 5080 PURE ELM) | SQFT | 93.6 | 600
[6 empty] | Total | 111.23
[6 empty] | BOQ Qty | 93.6
[6 empty] | Extra Qty | 17.63 | 10578
2 | WALL TILES FOR BACK AREA | Providing , Fixing Vitrified tile of 18” X 12” in Dado as detailed in drawing. Tile to be fixed with cement paste over surface including , joints to be cleaned and grouted with matching colour approved epoxy based grout, curing, cleaning, including making cut-outs for plumbing and electrical points, any sleeves in tiles, scaffolding,etc. to required line, level, etc. all complete at all heights, lifts and leads to the entire satisfaction of the Project Head.(Make: KAJARIA/SOMANY - WHITE GLOSSY) | SQFT | 323 | 180
[6 empty] | Total | 342.5
[6 empty] | BOQ Qty | 323
[6 empty] | Extra Qty | 19.5 | 3510
[6 empty] | TOTAL |  | 14088