## Summary
Semolina Project Pvt Ltd.
Vendor Name : LOK PRATIK CONSTRUCTION
PO No: Semolina/PO/24-25/000857
Sr no | Description | PO value | Previous Bill Amount | Present Bill Amount | Cumulative Amount | Variance Amount
1 | Additional Civil Interior Fit-outs and MEP works | 2099224.7 | 0 | 2099224.7 | 2099224.7 | 0
| Total | 2099224.7 |  | 2099224.7 | 2099224.7 | 0
| GST 18 % | 377860.446 |  | 377860.446 | 377860.446 | 0
| Gross Total | 2477085.146 |  | 2477085.146 | 2477085.146 | 0

## Abstract(RA 1)
RA-01 Final - Abstract
WO No :- Semolina/PO/24-25/000857
Additional Civil Interior Fit-outs and MEP works for Dominos Outlet at T1 CSMIA Mumbai
SR.NO. | DESCRIPTION | UNIT | PO QTY | PO RATE (Rs) | PO AMOUNT (Rs) | RA - 1 (Current Bill) |  | VARIATION |  | REMARKS
[6 empty] | QTY | AMOUNT (Rs) | QTY | AMOUNT (Rs)
CIVIL & INTERIOR WORKS
1 | Removal of Cold Storage and shifting the same outside airport premise SIZE - 10'-0" L X 8'-0" W X 8'-0" H | Lump | 1 | 10000 | 10000 | 1 | 10000 | 0 | 0
2 | Disconnecting all the cables and removal and shifting the existing HT electrical panel outside the store premise SIZE -1.70 L X 1.90 H X 0.45 W | Lump | 1 | 30000 | 30000 | 1 | 30000 | 0 | 0
3 | Shifting the HT electrical panel inside the store / Testing / Connecting / Commissioning the same. SIZE -1.70 L X 1.90 H X 0.45 W | Lump | 1 | 45000 | 45000 | 1 | 45000 | 0 | 0
4 | Removal of HOOD and shifting the same. SIZE - 1.85 X 2.0 | Lump | 1 | 4000 | 4000 | 1 | 4000 | 0 | 0
5 | Existing Cable Trays ,Duct Removing from the site and carting away from the site | sft | 573.49 | 60 | 34409.4 | 573.49 | 34409.4 | 0 | 0
6 | Removal PCC of thickness between 6 inches to 12 inches | Sq.ft | 379.9 | 100 | 37990 | 379.899 | 37989.9016 | - | 0
7 | False Ceiling removing inclusive wire & Light | Sq.ft | 573.9 | 75 | 43042.5 | 573.9 | 43042.5 | 0 | 0
8 | Removal from Façade - Glass ,Signgage with ACP Boxing ,Frames etc | Sq.ft | 94.31 | 100 | 9431 | 94.3114 | 9431.14 | 0.0014 | 0
9 | Dismantling existing counter along with shifting of debris. SIZE -17'-0" L X 3'-0"H X 2'-6" W | Lump | 1 | 10000 | 10000 | 1 | 10000 | 0 | 0
10 | Laying 12mm on mother slab mortar including cement punning for smoothening of surface for Membrane purpose | sft | 573.9 | 65 | 37303.5 | 573.9 | 37303.5 | 0 | 0
11 | Providing & fixing perforated GI powder coated grid ceiling system of size 600mm x 600mm including framing of Armstrong make etc complete | sft | 573.9 | 315 | 180778.5 | 573.9 | 180778.5 | - | 0
12 | Supply and installation of Fire damper | EA | 2 | 30000 | 60000 | 2 | 60000 | 0 | 0
13 | Supply and installation of fresh air unit as per required 3000 CFM | EA | 1 | 175000 | 175000 | 1 | 175000 | 0 | 0
14 | Supply and installation of 1.5 tier split air conditioner make - Blue Star (5 star Inverter ) | EA | 1 | 55000 | 55000 | 1 | 55000 | 0 | 0
15 | Supply and installation of 2 tier split air conditioner make - Blue Star (5 star Inverter ) | EA | 1 | 72000 | 72000 | 1 | 72000 | 0 | 0
16 | Supply and installation of 3 tier cassete air conditioner make - Blue Star | EA | 1 | 150000 | 150000 | 1 | 150000 | 0 | 0
17 | Supply and Fixing Copper pipe for AC | M | 57.34 | 1500 | 86010 | 57.34 | 86010 | 0 | 0
18 | Supply and installation of exhaust air unit as per site requirement -2800 CFM | EA | 1 | 180000 | 180000 | 1 | 180000 | 0 | 0
19 | Filling 3mm wide x 20mm Deep Grove with Zed Black shade Epoxy Grout matching with Dominos Design Tile. | Sft | 574.14 | 45 | 25836.3 | 574.14 | 25836.3 | 0 | 0
20 | Providing and Making Wooden table with 19mm Marine ply,1mm laminate on both sides,Drawers ,computer try and all necessary Hardware etc Complete.Size - 4'-0" X 2'-0" | EA | 1 | 19000 | 19000 | 1 | 19000 | 0 | 0
21 | Removing & Refixing wooden Barricading.Size- 40'-0" x 12'-0" | LS | 1 | 15000 | 15000 | 1 | 15000 | 0 | 0
22 | Providing & Fixing Wooden frame, 6mm ply as per MIAL standards. And install White FLEX as per artworks provided by Client. The cost includes Labour, Transportation, Hardwares, etc Complete including Removing the same after completion of work. | Sft | 96 | 120 | 11520 | 96 | 11520 | 0 | 0
| Fire Detection and Alarm System |  |  |  | 0 | 0 | 0 | 0 | 0
23 | SITC of Smoke Detector with Base -EST-3 make. | EA | 5 | 5000 | 25000 | 5 | 25000 | 0 | 0
24 | SITC of Heat Detector with Base -EST-3 make. | EA | 1 | 5100 | 5100 | 1 | 5100 | 0 | 0
25 | MCP -EST-3 make. | EA | 1 | 6000 | 6000 | 1 | 6000 | 0 | 0
26 | Hooter Cum strobe -EST-3 make. | EA | 1 | 6800 | 6800 | 1 | 6800 | 0 | 0
27 | Response Indicator | EA | 2 | 350 | 700 | 2 | 700 | 0 | 0
28 | Supplying and erecting PVC armoured cable 2 core 1.5 sq. mm FRLS copper conductor complete erected on wall / celling as per specification | M | 80 | 160 | 12800 | 80 | 12800 | 0 | 0
29 | Junction Box ( 400x 400 ) | EA | 3 | 700 | 2100 | 3 | 2100 | 0 | 0
30 | Installation & Commissioning. | Lot | 1 | 14000 | 14000 | 1 | 14000 | 0 | 0
31 | Providing and fixing/welding in position Signage panelling made out of MS Pipe 50mm x 25mm , 0.6mm GI Corrugated Sheet, 12mm thick Bison board ,hanging with ceiling rafters and finished with 2 coat of primer & finaly finished with Duco paint-Armada blue or colour matching to Pantone shade PMS 2965 C Complete as per store front Detail and as specified in Drawing. Size - 5150 mm Long X 760mm High. | EA | 1 | 40000 | 40000 | 1 | 40000 | 0 | 0
32 | SITC of 600mm x 600mm 40W Sleek LED Panel of Wipro make. | EA | 18 | 2700 | 48600 | 18 | 48600 | 0 | 0
33 | SITC of 2 Mega Pixel 180 dig HD CCTV IP Dome Camara of Hikvision make. | EA | 7 | 4500 | 31500 | 7 | 31500 | 0 | 0
34 | SITC of 8 port DVR- IDS- 7108HQHI-M1/S of Hikvision make. | EA | 1 | 15000 | 15000 | 1 | 15000 | 0 | 0
35 | SITC of 2TB HDD Memory Card Seagate SV35 HDD | EA | 1 | 9000 | 9000 | 1 | 9000 | 0 | 0
36 | SITC of 24 Port Patch Panel of Dlink. | EA | 1 | 4900 | 4900 | 1 | 4900 | 0 | 0
37 | Supply, installation, testing and commissioning of Data outlet RJ 45 jack mounted with plates . Make: D-link. | EA | 5 | 1500 | 7500 | 5 | 7500 | 0 | 0
38 | Crimping, ferroling, testing & commisioning, lebling of I/O's both user end & rack side. | EA | 48 | 500 | 24000 | 48 | 24000 | 0 | 0
39 | SITC of IT Rack VE Tech make. Size - 600mm L X 600mm W x 2000mm H | EA | 1 | 40000 | 40000 | 1 | 40000 | 0 | 0
40 | Providing and Fixing 4 mm thk ACP in cladding in Grey colour of Timex or equivalent make with Aluminium Frame including cutting joint filling with silicone etc complete | Sqmt | 2.46 | 4900 | 12054 | 2.46 | 12054 | 0 | 0
41 | Providing and fixing Mirror polish Kota stone with Cement morter 1:4 ,filling joints etc. | Sft | 73.96 | 175 | 12943 | 73.96 | 12943 | 0 | 0
42 | Supplying & Fixing Angle cock Jaquar Make. | EA | 4 | 1800 | 7200 | 4 | 7200 | 0 | 0
43 | Supplying & Fixing Bottel Trap Jaquar Make. | EA | 1 | 1800 | 1800 | 1 | 1800 | 0 | 0
44 | Supplying & Fixing SS finish Flxible PVC Connector. | EA | 7 | 650 | 4550 | 7 | 4550 | 0 | 0
45 | Making Manhole with AAC Blocks with cement morter 1:6 , Cement plaster all sides with cement morter 1:4 & Finaly finished with Ceramic Tiles etc Complete. SIZE - Internal 350mm X 650mm | EA | 1 | 7500 | 7500 | 1 | 7500 | 0 | 0
46 | Making Manhole with AAC Blocks with cement morter 1:6 , Cement plaster all sides with cement morter 1:4 & Finaly finished with Ceramic Tiles etc Complete. SIZE - Internal 350mm X 500mm | EA | 1 | 7500 | 7500 | 1 | 7500 | 0 | 0
47 | Supplying & Fixing 4 piece SS 304 GRADE Manhole Cover with Lid using SS Angle frame with Hold fast , SS Hollow pipe grating , SS Mesh and SS sheet Lid with Handle etc Complete. SIZE - Internal 350mm X 650mm | EA | 1 | 14000 | 14000 | 1 | 14000 | 0 | 0
48 | Supplying & Fixing 4 piece SS 304 GRADE Manhole Cover with Lid using SS Angle frame with Hold fast , SS Hollow pipe grating , SS Mesh and SS sheet Lid with Handle etc Complete. SIZE - Internal 350mm X 500mm | EA | 1 | 12500 | 12500 | 1 | 12500 | 0 | 0
49 | Supplying and erecting PVC Flexible cable 16Sqmm 5 core FRLS copper conductor complete erected on wall / celling as per specification | M | 32 | 1300 | 41600 | 32 | 41600 | 0 | 0
50 | Supplying and erecting PVC Flexible cable 10Sqmm 5 core FRLS copper conductor complete erected on wall / celling as per specification | M | 6 | 950 | 5700 | 6 | 5700 | 0 | 0
51 | Supply, Installation, Testing & Commissioning of 63A Industrial Point with Powder coated MS Box, 63A 4 Pole MCB ,5 Pin Industrial Socket & Top of Legrand make. | EA | 2 | 18000 | 36000 | 2 | 36000 | 0 | 0
52 | Supply, Installation, Testing & Commissioning of 32A Industrial Point with Powder coated MS Box,MCB ,5 Pin Industrial Socket & Top of Legrand make. | EA | 2 | 9800 | 19600 | 2 | 19600 | 0 | 0
53 | Supplying & Fixing 50 x 50mm Aluminium pipe Skirting i/c fillig gap with silicon. | M | 21.82 | 900 | 19638 | 21.82 | 19638 | 0 | 0
54 | Providing & Fixing 12mm thk Pinup board with 12mm thk backing ply and alround frame and finished with approved Cloth with all necessary hard ware etc.completed. | sft | 6.51 | 450 | 2929.5 | 6.51 | 2929.5 | 0 | 0
55 | Providing & Fixing LED Tube Light. | EA | 5 | 800 | 4000 | 5 | 4000 | 0 | 0
56 | Supplying & Fixing wall Mounted Broom Stick /Mop Holder with 5 slots of approved make. | EA | 1 | 2500 | 2500 | 1 | 2500 | 0 | 0
57 | Fixing Cold storage Out door unit. | EA | 1 | 5000 | 5000 | 1 | 5000 | 0 | 0
58 | Supplying & Fixing Self Adhesive Silicon Door Bottom gap Sealing strip for air gap,cockroach insect bug stopper etc . | M | 1 | 3000 | 3000 | 1 | 3000 | 0 | 0
59 | Supplying & Fixing PVC Clear Strip curtain with all necessary hardware etc complete. | sft | 50.13 | 300 | 15039 | 50.13 | 15039 | 0 | 0
60 | Unloading Dominos Equipment at Airport entry, Shifting the same inside T1C and site carefully.Placing all the Equipment as per Layout and instruction of Incharge. | LS | 1 | 90000 | 90000 | 1 | 90000 | 0 | 0
61 | 12 Way SPN DB for Power comprising of following:- 40A ELCB-1 & 16A MCB -8 nos | EA | 2 | 22000 | 44000 | 2 | 44000 | 0 | 0
62 | Supply, Installation, Testing & Commissioning of mains with 2 X 6 sq.mm and earth wire 6 sqmm FRLS PVC copper wire ,in rigid MS conduit min.20 mm dia,including all required accessories,etc as per specification. | RMT | 109 | 350 | 38150 | 109 | 38150 | 0 | 0
63 | Supply, Installation, Testing & Commissioning of CCTV 4+1 Cable. | RMT | 110 | 130 | 14300 | 110 | 14300 | 0 | 0
64 | Supplying and erecting PVC armoured cable 4sqmm 4 core FRLS copper conductor complete erected on wall / celling as per specification | RMT | 96 | 400 | 38400 | 96 | 38400 | 0 | 0
65 | Supplying and erecting PVC armoured cable 6sqmm 4 core FRLS copper conductor complete erected on wall / celling as per specification | RMT | 58 | 600 | 34800 | 58 | 34800 | 0 | 0
66 | Termination of cables with Brass Glands ,Lags etc. |  |  |  | 0 | 0 | 0 | 0 | 0
a | 120Sqmm Alu Armoured Cable | EA | 2 | 3000 | 6000 | 2 | 6000 | 0 | 0
b | 16sqmm X 5 core Copper Flexible cable | EA | 2 | 2000 | 4000 | 2 | 4000 | 0 | 0
c | 10sqmm X 5 core Copper Flexible cable | EA | 2 | 1500 | 3000 | 2 | 3000 | 0 | 0
d | 6Sqmm x 4 core Copper Armoured Cable | EA | 2 | 1200 | 2400 | 2 | 2400 | 0 | 0
e | 4Sqmm x 4 core Copper Armoured Cable | EA | 4 | 1200 | 4800 | 4 | 4800 | 0 | 0
TOTAL | [6 empty] | 2099224.7

## Measurements
| Mumbai International Airport Pvt. Ltd. Measurement Sheet (Civil) |  | Document No.: MIAL/EN-CL/FMT/01 Issue No. : 01 Issue Date: 22-Apr-15 Revision No. : 00 Revision Date: Nil
Sr. No. | 1 |  | Name of site In charge : |  |  |  | Ashish Nagar
PO No.: | Semolina/PO/24-25/000857 |  | Agency Name : |  |  |  | TFS
PO Date : | 2024-09-24 |  | Date :
PO Validity : |  |  | Name of WorkAdditional Civil Interior Fit-outs and MEP works for Dominos Outlet at T1 CSMIA Mumbai
Measurement Sheet No. of this PO: | 1 |  | Period of work Executed : Aug'24
Sr.No | Details of Work | Measurements |  |  |  |  | Total Qty | Claimable % | ClaimablQty
|  | Unit | No. | Length | Breadth | Height
RA-1 (Current Bill)
CIVIL & INTERIOR WORKS
1 | Removal of Cold Storage and shifting the same outside airport premise SIZE - 10'-0" L X 8'-0" W X 8'-0" H | Lump | 1 | 1 |  |  | 1 | 100% | 1
0
2 | Disconnecting all the cables and removal and shifting the existing HT electrical panel outside the store premise SIZE -1.70 L X 1.90 H X 0.45 W | Lump | 1 | 1 |  |  | 1 | 100% | 1
0
3 | Shifting the HT electrical panel inside the store / Testing / Connecting / Commissioning the same. SIZE -1.70 L X 1.90 H X 0.45 W | Lump | 1 | 1 |  |  | 1 | 100% | 1
4 | Removal of HOOD and shifting the same. SIZE - 1.85 X 2.0 | Lump | 1 | 1 |  |  | 1 | 100% | 1
5 | Existing Cable Trays ,Duct Removing from the site and carting away from the site | Sft | 1 | 4.97 |  | 6.96 | 34.5912
|  |  | 1 | 3.57 |  | 5.24 | 18.7068
53.3
|  |  |  | 10.76 |  |  | 573.49 | 100% | 573.49
6 | Removal PCC of thickness between 6 inches to 12 inches | Sft | 1 | 4.97 |  | 3.34 | 16.5998
|  |  | 1 | 3.57 |  | 5.24 | 18.7068
35.3066
|  |  | 10.76 |  |  |  | 379.899 | 100% | 379.899
7 | False Ceiling removing inclusive wire & Light | Sft | 1 | 4.97 |  | 6.96 | 34.5912
|  |  | 1 | 3.57 |  | 5.24 | 18.7068
53.298
|  |  | 10.76 |  |  |  | 573.9 | 100% | 573.9
8 | Removal from Façade - Glass ,Signgage with ACP Boxing ,Frames etc | Sft | 1 | 4.8 |  | 0.8 | 3.84
|  |  | 1 | 1.97 |  | 2.5 | 4.925
8.765
|  |  | 10.76 |  |  |  | 94.3114 | 100% | 94.3114
9 | Dismantling existing counter along with shifting of debris. SIZE -17'-0" L X 3'-0"H X 2'-6" W | Lump | 1 | 1 |  |  | 1 | 100% | 1
10 | Laying 12mm on mother slab mortar including cement punning for smoothening of surface for Membrane purpose | Sft | 1 | 4.97 |  | 6.96 | 34.5912
|  |  | 1 | 3.57 |  | 5.24 | 18.7068
53.3
|  |  | 10.76 |  |  |  | 573.9 | 100% | 573.9
11 | Providing & fixing perforated GI powder coated grid ceiling system of size 600mm x 600mm including framing of Armstrong make etc complete | Sft | 1 | 4.97 |  | 6.96 | 34.5912
|  |  | 1 | 3.57 |  | 5.24 | 18.7068
53.298
|  |  | 10.76 |  |  |  | 573.9 | 100% | 573.9
12 | Supply and installation of fire damper | Nos | 1 | 2 |  |  | 2 | 100% | 2
13 | Supply and installation of fresh air unit as per required 3000 CFM | EA | 1 | 1 |  |  | 1 | 100% | 1
14 | Supply and installation of 1.5 tier split air conditioner make - Blue Star (5 star Inverter ) | EA | 1 | 1 |  |  | 1 | 100% | 1
15 | Supply and installation of 2 tier split air conditioner make - Blue Star (5 star Inverter ) | EA | 1 | 1 |  |  | 1 | 100% | 1
16 | Supply and installation of 3 tier cassete air conditioner make - Blue Star | EA | 1 | 1 |  |  | 1 | 100% | 1
17 | Supply and Fixing Copper pipe for AC
| For 3 tier cassete AC | M | 1 | 22.31 |  |  | 22.31
| For 2 Tier Split AC |  | 1 | 16.73 |  |  | 16.73
| For 1.5 Tier Split AC |  | 1 | 18.3 |  |  | 18.3
[7 empty] | 57.34 | 100% | 57.34
18 | Supply and installation of exhaust air unit as per site requirement -2800 CFM | EA | 1 | 1 |  |  | 1 | 100% | 1
19 | Filling 3mm wide x 20mm Deep Grove with Zed Black shade Epoxy Grout matching with Dominos Design Tile.
| Counter Front Side | Sft | 1 | 4.9 |  | 0.9 | 4.41
| Counter Back Side |  | 1 | 4.9 |  | 0.85 | 4.165
| LHS wall |  | 1 | 7.17 |  | 2.4 | 17.208
|  |  | 2 | 1.4 |  | 2.4 | 6.72
| RHS Wall |  | 1 | 5.27 |  | 2.4 | 12.648
| cold room wall |  | 1 | 2.8 |  | 2.4 | 6.72
|  |  | 1 | 0.62 |  | 2.4 | 1.488
53.36
|  |  | 10.76 |  |  |  | 574.14 | 100% | 574.14
20 | Providing and Making Wooden table with 19mm Marine ply,1mm laminate on both sides,Drawers ,computer try and all necessary Hardware etc Complete.Size - 4'-0" X 2'-0" | EA | 1 | 1 |  |  | 1 | 100% | 1
21 | Removing & Refixing wooden Barricading.Size- 40'-0" x 12'-0" | LS | 1 | 1 |  |  | 1 | 100% | 1
22 | Providing & Fixing Wooden frame, 6mm ply as per MIAL standards. And install printed FLEX as per artworks provided by Client. The cost includes Labour, Transportation, Hardwares, etc Complete including Removing the same after completion of work. | Sft | 2 | 4 |  | 12 | 96 | 100% | 96
23 | SITC of Smoke Detector with Base -EST-3 make. | EA | 1 | 5 |  |  | 5 | 100% | 5
24 | SITC of Heat Detector with Base -EST-3 make. | EA | 1 | 1 |  |  | 1 | 100% | 1
25 | MCP -EST-3 make. | EA | 1 | 1 |  |  | 1 | 100% | 1
26 | Hooter Cum strobe -EST-3 make. | EA | 1 | 1 |  |  | 1 | 100% | 1
27 | Response Indicator | EA | 1 | 2 |  |  | 2 | 100% | 2
28 | Supplying and erecting PVC armoured cable 2 core 1.5 sq. mm FRLS copper conductor complete erected on wall / celling as per specification | M
| Main Panel ( Loop-6) to Loop -6/ D-90 |  | 1 | 11 |  |  | 11
| Loop -6/ D-90 to Loop -6/ D-91 |  | 1 | 9 |  |  | 9
| Loop -6/ MCP-1to Loop -6/ D-92 |  | 1 | 11 |  |  | 11
| Loop -6/ D-92 to Loop -6/ D-93 |  | 1 | 10 |  |  | 10
| Loop -6/ D-93 to Loop -6/ D-94 |  | 1 | 12 |  |  | 12
| Loop -6/ D-94 & RI to Loop -6/ D-95 |  | 1 | 13 |  |  | 13
| Loop -6/ D-95 to Existing Loop |  | 1 | 14 |  |  | 14
[7 empty] | 80 | 100% | 80
29 | Junction Box ( 400x 400 ) | EA | 1 | 3 |  |  | 3 | 100% | 3
30 | Installation & Commissioning. | Lot | 1 | 1 |  |  | 1 | 100% | 1
31 | Providing and fixing/welding in position Signage panelling made out of MS Pipe 50mm x 25mm , | EA | 1 | 1 |  |  | 1 | 100% | 1
32 | SITC of 600mm x 600mm 40W Sleek LED Panel of Wipro make. | EA
| Operation Area |  | 1 | 13 |  |  | 13
| Off Area |  | 1 | 4 |  |  | 5
[7 empty] | 18 | 100% | 18
33 | SITC of 2 Mega Pixel 180 dig HD CCTV IP Dome Camara of Hikvision make. | EA
| Operation Area |  | 1 | 5 |  |  | 5
| Off Area |  | 1 | 2 |  |  | 2
[7 empty] | 7 | 100% | 7
34 | SITC of 8 port DVR- IDS- 7108HQHI-M1/S of Hikvision make. | EA | 1 | 1 |  |  | 1 | 100% | 1
35 | SITC of 2TB HDD Memory Card Seagate SV35 HDD | EA | 1 | 1 |  |  | 1 | 100% | 1
36 | SITC of 24 Port Patch Panel of Dlink. | EA | 1 | 1 |  |  | 1 | 100% | 1
37 | Supply, installation, testing and commissioning of Data outlet RJ 45 jack mounted with plates . Make: D-link. | EA
| on TV Unit |  | 1 | 4 |  |  | 4
| On SS Pole |  | 1 | 1 |  |  | 1
[7 empty] | 5 | 100% | 5
38 | Crimping, ferroling, testing & commisioning, lebling of I/O's both user end & rack side. | EA | 1 | 48 |  |  | 48 | 100% | 48
39 | SITC of IT Rack VE Tech make. Size - 600mm L X 600mm W x 2000mm H | EA | 1 | 1 |  |  | 1 | 100% | 1
40 | Providing and Fixing 4 mm thk ACP in cladding in Grey colour of Timex | M2
| Covering area Between Hood & Ceiling |  | 2 | 1.8 |  | 0.41 | 1.48
|  |  | 1 | 2.4 |  | 0.41 | 0.98
[7 empty] | 2.46 | 100% | 2.46
41 | Providing and fixing Mirror polish Kota stone with Cement morter 1:4 ,filling joints etc. | Sft
| Cold Storage |  | 1 | 2.33 |  | 2.95 | 6.8735
|  |  | 10.76 |  |  |  | 73.9589 | 100% | 73.96
42 | Supplying & Fixing Angle cock Jaquar Make.
| Makeline Sink | 1 | 2 |  |  |  | 2
| Ice Machine | 1 | 1 |  |  |  | 1
| Pmax Machine | 1 | 1 |  |  |  | 1
[7 empty] | 4 | 100% | 4
43 | Supplying & Fixing Bottel Trap Jaquar Make. | EA | 1 | 1 |  |  | 1 | 100% | 1
44 | Supplying & Fixing SS finish Flxible PVC Connector. | EA
| GEYSER ABOVE MAKELINE SINK |  | 1 | 2 |  |  | 2
| MAKELINE SINK |  | 1 | 3 |  |  | 3
| Storage Geyser |  | 1 | 2 |  |  | 2
[7 empty] | 7 | 100% | 7
45 | Making Manhole with AAC Blocks with cement morter 1:6 , Cement plaster all sides with cement morter 1:4 & Finaly finished with Ceramic Tiles etc Complete. SIZE - Internal 350mm X 650mm | EA | 1 | 1 |  |  | 1 | 100% | 1
46 | Making Manhole with AAC Blocks with cement morter 1:6 , Cement plaster all sides with cement morter 1:4 & Finaly finished with Ceramic Tiles etc Complete. SIZE - Internal 350mm X 500mm | EA | 1 | 1 |  |  | 1 | 100% | 1
47 | Supplying & Fixing 4 piece SS Manhole Cover with Lid using SS Angle frame with Hold fast , SS Hollow pipe grating , SS Mesh and SS sheet Lid with Handle etc Complete. SIZE - Internal 350mm X 650mm | EA | 1 | 1 |  |  | 1 | 100% | 1
48 | Supplying & Fixing 4 piece SS Manhole Cover with Lid using SS Angle frame with Hold fast , SS Hollow pipe grating , SS Mesh and SS sheet Lid with Handle etc Complete. SIZE - Internal 350mm X 500mm | EA | 1 | 1 |  |  | 1 | 100% | 1
49 | Supplying and erecting PVC Flexible cable 16Sqmm 5 core FRLS copper conductor complete erected on wall / celling as per specification | M
| For Oven |  | 2 | 16 |  |  | 32 | 100% | 32
50 | Supplying and erecting PVC Flexible cable 10Sqmm 5 core FRLS copper conductor complete erected on wall / celling as per specification | M
| For Oven |  | 2 | 3 |  |  | 6 | 100% | 6
51 | Supply, Installation, Testing & Commissioning of 63A Industrial Point with Powder coated MS Box, 63A 4 Pole MCB ,5 Pin Industrial Socket & Top of Legrand make.
| For Oven | EA | 1 | 2 |  |  | 2 | 100% | 2
52 | Supply, Installation, Testing & Commissioning of 32A Industrial Point with Powder coated MS Box,MCB ,5 Pin Industrial Socket & Top of Legrand make. | EA
| For Makeline |  | 1 | 2 |  |  | 2 | 100% | 2
53 | Supplying & Fixing 50 x 50mm Aluminium pipe Skirting. | M
| Cold Storage |  | 2 | 9.66 |  |  | 19.32
|  |  | 2 | 1.7 |  |  | 3.4
|  |  | -1 | 0.9 |  |  | -0.9
[7 empty] | 21.82 | 100% | 21.82
54 | Providing & Fixing 12mm thk Pinup board with 12mm thk backing ply and alround frame. | M
|  |  | 1 | 1.21 |  | 0.5 | 0.61
|  |  | 10.76 |  |  |  | 6.51 | 100% | 6.51
55 | Providing & Fixing LED Tube Light. | EA
| Hood |  | 1 | 2 |  |  | 2
| Cold Storage |  | 1 | 2 |  |  | 2
| on manager Table |  | 1 | 1 |  |  | 1
[7 empty] | 5 | 100% | 5
56 | Supplying & Fixing wall Mounted Broom Stick /Mop Holder with 5 slots of approved make. | EA | 1 | 1 |  |  | 1 | 100% | 1
57 | Fixing Cold storage Out door unit. | EA | 1 | 1 |  |  | 1 | 100% | 1
58 | Supplying & Fixing Self Adhesive Silicon Door Bottom gap Sealing strip for air gap,cockroach insect bug stopper etc . | EA | 1 | 1 |  |  | 1 | 100% | 1
59 | Supplying & Fixing PVC Clear Strip curtain with all necessary hardware etc complete. | Sft
| Between Off & Kitchen |  | 1 | 1.1 |  | 2.29 | 2.519
| Inside Cold Storage |  | 1 | 1 |  | 2.14 | 2.14
|  |  | 10.76 |  |  |  | 4.66
[7 empty] | 50.13 | 100% | 50.13
60 | Unloading Dominos Equipment at Airport entry, Shifting the same inside T1C and site carefully.Placing all the Equipment as per Layout and instruction of Incharge. | Ls | 1 | 1 |  |  | 1 | 100% | 1
61 | 12 Way SPN DB for Power comprising of following:- 40A ELCB-1 & 16A MCB -8 nos | Nos
| UPS DB |  | 1 | 2 |  |  | 2 | 100% | 2
62 | Supply, Installation, Testing & Commissioning of mains with 2 X 6 sq.mm and earth wire 6 sqmm FRLS PVC copper wire ,in rigid MS conduit min.20 mm dia,including all required accessories,etc as per specification. | M
| For makeline |  | 2 | 14 |  |  | 28
| For Gyser |  | 1 | 11 |  |  | 11
| For Gyser |  | 1 | 10 |  |  | 10
| IT Panel |  | 6 | 10 |  |  | 60
[7 empty] | 109 | 100% | 109
63 | Supply, Installation, Testing & Commissioning of CCTV 4+1 cable. | M
| CCTV |  | 1 | 21 |  |  | 21
|  |  | 1 | 16 |  |  | 16
|  |  | 2 | 18 |  |  | 36
|  |  | 1 | 17 |  |  | 17
|  |  | 1 | 9 |  |  | 9
|  |  | 1 | 11 |  |  | 11
[7 empty] | 110 | 100% | 110
64 | Supplying and erecting PVC armoured cable 4sqmm 4 core FRLS copper conductor complete erected on wall / celling as per specification | M
| Fresh Air - Ele Panel to Outdoor Unit |  | 1 | 20 |  |  | 20
| Exhaust - Ele Panel to Outdoor Unit |  | 1 | 20 |  |  | 20
| 2T AC - Ele Panel to Outdoor Unit |  | 1 | 28 |  |  | 28
| 1.5T AC - Ele Panel to Outdoor Unit |  | 1 | 28 |  |  | 28
[7 empty] | 96 | 100% | 96
65 | Supplying and erecting PVC armoured cable 6sqmm 4 core FRLS copper conductor complete erected on wall / celling as per specification | M
| Cold Storage - Ele Panel to Outdoor Unit |  | 1 | 30 |  |  | 30
| 3T Cassette AC - Ele Panel to Outdoor Unit |  | 1 | 28 |  |  | 28
[7 empty] | 58 | 100% | 58
66 | Termination of cables with Brass Glands ,Lags etc.
a | 120Sqmm Alu Armoured Cable | EA | 1 | 2 |  |  | 2 | 100% | 2
b | 16sqmm X 5 core Copper Flexible cable
| Oven | EA | 1 | 2 |  |  | 2 | 100% | 2
c | 10sqmm X 5 core Copper Flexible cable
| Oven | EA | 1 | 2 |  |  | 2 | 100% | 2
d | 6Sqmm x 4 core Copper Armoured Cable | EA
| Cold Storage |  | 1 | 1 |  |  | 1
| 3T Cassette AC |  | 1 | 1 |  |  | 1
[7 empty] | 2 | 100% | 2
e | 4Sqmm x 4 core Copper Armoured Cable | EA
| Fresh Air |  | 1 | 1 |  |  | 1
| Exhaust |  | 1 | 1 |  |  | 1
| 2T AC |  | 1 | 1 |  |  | 1
| 1.5T AC |  | 1 | 1 |  |  | 1
[7 empty] | 4 | 100% | 4
| Measurement Taken By |  |  | Measurement Certified By
| Name & Sign of Vendor |  | Name & Sign of Site In Charge

## Abstract - Costing Diff. (hidden)
ANNEXURE -1
WO No :-5700338947 | [9 empty] | Date:- 30-04-2024
CAR No :-01
Civil & Interior work for Office 1 , 2 & Briefing Room at JCC Office at Level 3 at T2
SECTION: A
SR.NO. | SERVICE CODE | DESCRIPTION | UNIT | PO QTY | PO RATE (Rs) | PO AMOUNT (Rs) | REV QTY | CLAIMABLE QTY | RATE (Rs) | CLAIMABLE AMOUNT (Rs) | NEW RATE | RATE DIFFERENCE | AMOUNT DIFFERENCE | REMARKS
RA - 1 (Current Bill)
2 | 99992504 | Dismantling Dry cladding/Finishes cladding and stacking of serviceable material at MLCP level P2 as directed by engineer incharge | sqm | 250 | 400 | 100000 | #NAME? | #NAME? | 400 | #NAME?
3 | 120021037 | Demolishing brick work/block work including stacking of serviceable material and disposal of unserviceable material within 500 metres lead:a) In cement mortar | cum | 40 | 2000 | 80000 | #NAME? | #NAME? | 2000 | #NAME?
4 | 99992505 | Dismantling aluminium/Gypsum partitions/ply/double skinned bison board with frame, doors,windows, fixed glazing and false ceiling including disposal of unserviceable surplus material and stacking of serviceable material within 500 metres lead as directed by Engineer-in- charge. | sqm | 170 | 750 | 127500 | #NAME? | #NAME? | 750 | #NAME?
5 | 99992135 | Removing metal and wooden door with all its hardware and stacking the same in T2 MLCP as directed by engineer in charge | no | 4 | 2500 | 10000 | #NAME? | #NAME? | 2500 | #NAME?
7 | 120020484 | Demolishing RCC structure /slab,beam,lintel column etc including taking away the reinforcement Rate to offset for credit of steel | cum | 10 | 2800 | 28000 | #NAME? | #NAME? | 2800 | #NAME?
9 | 170002645 | Disposal of building rubbish/malba from building premises from airside,inside building and city side by mechanical transport including loading,unloading etc. and disposal outside the airport premises. | cum | 120 | 1500 | 180000 | #NAME? | #NAME? | 1500 | #NAME?
10 | 120014430 | Providing and constructing Brick/Solid Block for 150MM thick walls till R.C.C slab lvl using in cement mortar 1:4, using 2 nos. with 1:6 CM 12mm thk plastered and finished to match the existing wall. The junction of existing & new wall or brick wall and RCC surface to be plastered after placing wiremesh 6" wide on either side. The block should be of minimum compressive strength of 35 Kg/ sqcm. Rate to be inclusive of filling of voids created by chasing of walls for water supply and electrical works with appropriate material as directed, etc. complete. | cum | 52 | 10000 | 520000 | #NAME? | #NAME? | 10000 | #NAME?
14 | 120020788 | cutting the groove upto 50 mm wide in wall and floor for cable conduits and refiliing it with cement mortar 1:3 and finishing etc complete as directed by engineer incharge | m | 50 | 500 | 25000 | #NAME? | #NAME? | 500 | #NAME?
18 | 90130834 | Providing and fixing 100mm thk gypboard partition from India gypsum with 50mm x 50mm aluminium frame @ 600mm distance vertically & horizontally center to center. The frame shall be rigidly fixed between floor and ceiling. The same shall be filled with 50mm thk. rock wool 48KG/m3 density (1000GSM) for sound insulation and covered with black color kora cloth & shall be finished with double layer 12mm thk gypsum board on both sides. shall be finished with proper grooves, skirting etc,. see detail drawing. not to be painted in the areas above the false ceiling & below false floor. | sqm | 215 | 2300 | 494500 | #NAME? | #NAME? | 2300 | #NAME?
20 | 90132182 | Providing and fixing of Fluted acoustic panel cladding with 12mm thk fluted acoustic panel from Vividha or equivalent with 12mm thk ply backing. A 6x6mm groove shall be made between acoustic panel and gypboard in the gypboard and finished with 6x6mm aluminium c-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the acoustic panel shall not have any gypboard. Panel shall have 0.5 NRC. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing | sqm | 17 | 4200 | 71400 | #NAME? | #NAME? | 4200 | #NAME? | 4800 | 600 | #NAME? | 0.9 NRC USED INSTEAD OF 0.5 NRC
21 | 90100402 | Providing & fixing of 6mm thk white lacquered glass with 6mm thk ply backing to be fitted directly on the framework of the gypsum partition so that the glass is in flush lvl with the gypboard. A 6x6mm groove shall be made between glass and gypboard in the gypboard and finished with 6x6mm aluminium C/T-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the glass shall not have any gypboard. | sqm | 31 | 6200 | 192200 | #NAME? | #NAME? | 6200 | #NAME? | 6800 | 600 | #NAME? | 12MM PLY USED INSTEAD OF 6MM
22 | 170002758 | Providing and fixing 12mm thk soft board to be fitted above 6mm ply with rounded edge on all sides to stretch the fabric properly. soft board shall be fitted above table skirting upto same ht as writing board. there shall be a 6mm groove fitted with aluminium channel between softboard and skirting and shall run all round the softboard. .Color of the fabric to be selected. samples to be shown. skirting shall be made of 19mm thk ply and finished with laminate same as table top. softboard shall be in flush level with gypboard partition. see detail in typical details sheet. | sqm | 33 | 1800 | 59400 | #NAME? | #NAME? | 1800 | #NAME? | 2400 | 600 | #NAME? | 12MM PLY USED INSTEAD OF 6MM
25 | 99992398 | Providing and fixing 600x600mm ceramic tile dado of KAJARIA make or equivalent for wall above pantry counter upto 600mm ht as per the drawing. Shall be provided with suitable white cement backing on existing surface, with colour cement finishing including dilute acid. Epoxy joint filler to be used in the joint between tiles.(See Toilet details) | sqm | 2.5 | 2400 | 6000 | #NAME? | #NAME? | 2400 | #NAME?
26 | 90132182 | Providing and fixing of acoustic panel cladding with 12mm thk acoustic panel from Vividha or equivalent with 12mm thk ply backing. A 6x6mm groove shall be made between acoustic panel and gypboard in the gypboard and finished with 6x6mm aluminium c-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the acoustic panel shall not have any gypboard. Panel shall have 0.5 NRC. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing | sqm | 18 | 4200 | 75600 | #NAME? | #NAME? | 4200 | #NAME? | 4800 | 600 | #NAME? | 0.9 NRC USED INSTEAD OF 0.5 NRC
28 | 170002757 | Base cabinet shall be made of 19mm BWP ply with 2400MM x 600mm depth and 825mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. counter top shall be finished with 19mm thk granite as per selection with 19mm thk BWP ply base. Kitchen sink of Franke or equivalent. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, 75mm high & 75mm recessed skirting, etc. refer detail drawing. | sqm | 2.4 | 15000 | 36000 | #NAME? | #NAME? | 15000 | #NAME?
29 | 170002757 | Overhead cabinet shall be made of 19mm BWP ply with 2400MM x 300mm depth and 750mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, etc. refer detail drawing. | sqm | 2 | 15000 | 30000 | #NAME? | #NAME? | 15000 | #NAME?
48 | 90131332 | SILHOUETTE GRID CEILING :Providing and fixing in true horizontal level false ceiling grid of SILHOUTTE GRID 15mm using hot dipped galvonized steel section, Exposed surface chemically cleaned capping prefinished in baked polyster paint, main Tee of size 15 x 44 x 0.3 at every 1200 mm C/C max and rotary stiched Croos Tee of size 15 x 44 x 0.3 mm at every 1200 mm centrally between the 1200mm cross tees and 18 x 18 x 0.5 mm Wall angles all round the the wall to form a grid of size 600 mm x 600mm and suspended the grid using suitable rigid hangers at every 1200 mm intervals at the Main ' T ' and laying tile with edge CONSTILATION TILE of size 600 x 600 x 15 mm over the formed grid., Tile Specs; NRC of the tile to 0.9 ,Class 1 FIRE PERFORMANCE AND HUMIDITY RESISTANCE RH 99 %.The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. | sqm | 2 | 3500 | 7000 | #NAME? | #NAME? | 3500 | #NAME?
49 | 90132107 | Providing and fixing Linear metal ceiling tiles of size 1200,1500 & 1800mm x 150mm, thickness of 15mm with galvanised steel grid system, as per vendor detail and specification. From Armstrong/Tranquil or equivalent. | sqm | 45 | 3500 | 157500 | #NAME? | #NAME? | 3500 | #NAME?
50 | 90132185 | AOUSTIC BAFFLE CEILING - Providing and fixing in true horizontal level false ceiling using 50X100MM Extruded aluminium sections arranged at100mmc/c. The sections to be wrapped with acoustic panles and finished as per architects approval. The cost shall include all necessary hardwares as per vendor specifications | sqm | 34 | 6600 | 224400 | #NAME? | #NAME? | 6600 | #NAME? | 6200 | -400 | #NAME? | USED EXISTING SUPPORT
55 | 99992174 | FALSE FLOORING - Providing & Fixing of UNITILE OR EQUIVALENT CEMENTATIOUS INFILL TILE raised flooring system with necessary metal framework (GI/Epoxy coated) as per site requirements. The understructure shall be capable of level adjustment of ±50mm. The flooring to also include thermal insulation (15mm Armaduct Insulation) | sqm | 3 | 8500 | 25500 | #NAME? | #NAME? | 8500 | #NAME?
57 | 99992385 | To prepare & finish 3 coats of tractor emulsion paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of tractor emulsion paint, touching up with putty & applying two final roller coats of tractor emulsion paint, to internal wall/ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. | sqm | 455 | 360 | 163800 | #NAME? | #NAME? | 360 | #NAME?
94 | 99992409 | Fire line GYPBOARD FALSE CEILING- Providing and fixing MF suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. Metal expanded rawl plugs shall be bolted to the beam/deck slab and suspenders of the required length shall be provided using GI hangers. Metal expanded rawl plugs and suspenders are to be positiioned at such spacing so that the runner when connected shall have support not exceeding 4' intervals. Main runners coonsisting of GI intermediate channels shall be provided at not exceeding 4' centre in one direction and connected to the suspenders with GI bolts and nuts. GI ceiling channels shall be placed in the opposite direction to the Intermediate channel at not exceeding 2' centres and connected to the intermediate channel using special connecting clips. Gi perimeter channel shall be fixed along the periphery walls, columns, etc. and the ceiling channel shall be inserted and screwed to this perimeter channel. | sqm | 121 | 2400 | 290400 | #NAME? | #NAME? | 2400 | #NAME? | 2150 | -250 | #NAME? | EXISTING MAIN SUPPORT FOR BRIEFING ROOM & OFFICE 1 CABIN
96 | 90132185 | ACOUSTIC CEILING - Providing and fixing acoustic suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. ceiling shall be finished with 12mm thk acoustic panel with 0.9 NRC rating with 12mm thk ply backing. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. | sqm | 25 | 6500 | 162500 | #NAME? | #NAME? | 6500 | #NAME? | 6100 | -400 | #NAME?
[8 empty] | TOTAL |  | #NAME? |  |  | #NAME?
[8 empty] | 18% GST |  | #NAME?
[8 empty] | GROSS TOTAL |  | #NAME?

## DIS (hidden)
ANNEXURE -1
WO No :-5700338947 | [8 empty] | Date:- 30-04-2024
CAR No :-01
Civil & Interior work for Office 1 , 2 & Briefing Room at JCC Office at Level 3 at T2
SECTION: A (DEVIATED ITEMS)
SR.NO. | SERVICE CODE | DESCRIPTION | UNIT | PO QTY | PO RATE (Rs) | PO AMOUNT (Rs) | REV QTY | REV RATE (Rs) | REV AMOUNT (Rs) | VARIATION{(+)/(-)} |  | REMARKS
[10 empty] | QTY. | AMOUNT (Rs)
1 | 230002422 | Providing and fixing temporary site barricading, with wooden runners of size 50mm x50mmas a basic framework and cladding with 6mm plywood.The barricades shall be pasted with printed artwork vinyl on outside.The material will be contractors property after its usage as a barricade.Cost to include dismantalling also. upto a height of 4.5. m | sqm | 84 | 1800 | 151200 | #NAME? | 1800 | #NAME? | #NAME? | #NAME?
2 | 99992504 | Dismantling Dry cladding/Finishes cladding and stacking of serviceable material at MLCP level P2 as directed by engineer incharge | sqm | 250 | 400 | 100000 | #NAME? | 400 | #NAME? | #NAME? | #NAME?
3 | 120021037 | Demolishing brick work/block work including stacking of serviceable material and disposal of unserviceable material within 500 metres lead:a) In cement mortar | cum | 40 | 2000 | 80000 | #NAME? | 2000 | #NAME? | #NAME? | #NAME?
4 | 99992505 | Dismantling aluminium/Gypsum partitions/ply/double skinned bison board with frame, doors,windows, fixed glazing and false ceiling including disposal of unserviceable surplus material and stacking of serviceable material within 500 metres lead as directed by Engineer-in- charge. | sqm | 170 | 750 | 127500 | #NAME? | 750 | #NAME? | #NAME? | #NAME?
5 | 99992135 | Removing metal and wooden door with all its hardware and stacking the same in T2 MLCP as directed by engineer in charge | no | 4 | 2500 | 10000 | #NAME? | 2500 | #NAME? | #NAME? | #NAME?
6 | 99992504 | Dismantling existing SS skirting | rmt | 90 | 110 | 9900 | #NAME? | 110 | #NAME? | #NAME? | #NAME?
7 | 120020484 | Demolishing RCC structure /slab,beam,lintel column etc including taking away the reinforcement Rate to offset for credit of steel | cum | 10 | 2800 | 28000 | #NAME? | 2800 | #NAME? | #NAME? | #NAME?
8 | 99992262 | Demolishing of flooring tile with mortar | sqm | 170 | 650 | 110500 | #NAME? | 650 | #NAME? | #NAME? | #NAME?
9 | 170002645 | Disposal of building rubbish/malba from building premises from airside,inside building and city side by mechanical transport including loading,unloading etc. and disposal outside the airport premises. | cum | 120 | 1500 | 180000 | #NAME? | 1500 | #NAME? | #NAME? | #NAME?
10 | 120014430 | Providing and constructing Brick/Solid Block for 150MM thick walls till R.C.C slab lvl using in cement mortar 1:4, using 2 nos. with 1:6 CM 12mm thk plastered and finished to match the existing wall. The junction of existing & new wall or brick wall and RCC surface to be plastered after placing wiremesh 6" wide on either side. The block should be of minimum compressive strength of 35 Kg/ sqcm. Rate to be inclusive of filling of voids created by chasing of walls for water supply and electrical works with appropriate material as directed, etc. complete. | cum | 52 | 10000 | 520000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
11 | 120008655 | Lintels shall be precast and it should be casted at ground level. Lintel shall be lifted by crane at relevant location, Rate shall include above all activities including lift, lead, casting, shuttering, leaving dowels for chajja etc. | no | 10 | 17000 | 170000 | #NAME? | 17000 | #NAME? | #NAME? | #NAME?
12 | 120020797 | Supplying, fabrication and erection of strucutre steel including plate cutting, assembling hoisting and fixing for helipad, etc in position to alignments and levels and painting / other protection of steelwork for structures including fixtures, fittings, temporary works and supports, and ancillaries. Including fabricated out of rolled steel sections , plates, hollow sections, pipes, cast steel, forgings etc and may involve any or combination of two or more of these in sizes, quantity and quality as specified in the drawings or as directed by the Employer’s Representative . steelwork consist of all types such as columns, beams, trusses, wall beams, girders, brackets, base-plates, floorings, anchors, any other kind as shown in the drawings. | kg | 1000 | 160 | 160000 | #NAME? | 160 | #NAME? | #NAME? | #NAME?
13 | 220013144 | Supply and installation of 16 mm dia and 200mm long Hilti bolts with RE500V4 chemical | NO.S | 50 | 1250 | 62500 | #NAME? | 1250 | #NAME? | #NAME? | #NAME?
14 | 120020788 | cutting the groove upto 50 mm wide in wall and floor for cable conduits and refiliing it with cement mortar 1:3 and finishing etc complete as directed by engineer incharge | m | 50 | 500 | 25000 | #NAME? | 500 | #NAME? | #NAME? | #NAME?
15 | 93011022 | Supply and installation of fully straight single glazed door using 10mm thick toughened glass and fixed with proprietary anodised aluminium WIDE LINE sections of size 100mm x 25mm as per architects approval. Rate to include required accessories as per the manufacturers specifications and shall be inclusive of all accessories like rubber gasket etc.,. Glass panels to be of maximum sizes and it should be executed strictly as per detailed drawings / elevations and as per architects approval. Partition with more number of glass pieces are not advised. Rate to include providing & fixing of necessary G.I./wooden/MS frame supports for the above doors, fixtures & additional suspenders etc., complete as per architects / PM's instruction or approval. Tested in an accredited laboratory as per ASTM/ISO standards. Partition to floor/ceiling junctions shall be sealed with acoustic sealant. To have 12mm thk MDF finished with paint of approved shade to be provided all around on junctions of modular door frames & partitions (All around horizontally and vertically)Height of 2400mm. Size 1050x2400mm.Glass shall have 50% area under frosting. Cost to include frosting. Cost shall include all hinges, handles, hardware and accesories.Vendor to share shop drawings for architect approval. | NO.S | 4 | 25000 | 100000 | #NAME? | 25000 | #NAME? | #NAME? | #NAME?
16 | 93011022 | Supply and installation of fully straight single glazed door using 10mm thick toughened glass and fixed with proprietary anodised aluminium WIDE LINE sections of size 100mm x 25mm as per architects approval. Rate to include required accessories as per the manufacturers specifications and shall be inclusive of all accessories like rubber gasket etc.,. Glass panels to be of maximum sizes and it should be executed strictly as per detailed drawings / elevations and as per architects approval. Partition with more number of glass pieces are not advised. Rate to include providing & fixing of necessary G.I./wooden/MS frame supports for the above doors, fixtures & additional suspenders etc., complete as per architects / PM's instruction or approval. Tested in an accredited laboratory as per ASTM/ISO standards. Partition to floor/ceiling junctions shall be sealed with acoustic sealant. To have 12mm thk MDF finished with paint of approved shade to be provided all around on junctions of modular door frames & partitions (All around horizontally and vertically)Height of 2400mm. Size 900x2400mm.Glass shall have 50% area under frosting. Cost to include frosting. Cost shall include all hinges, handles, hardware and accesories.Vendor to share shop drawings for architect approval. | NO.S | 3 | 24000 | 72000 | #NAME? | 24000 | #NAME? | #NAME? | #NAME?
17 | 93011022 | Supply and installation of fully straight single glazed door using 10mm thick toughened glass and fixed with proprietary anodised aluminium WIDE LINE sections of size 100mm x 25mm as per architects approval. Rate to include required accessories as per the manufacturers specifications and shall be inclusive of all accessories like rubber gasket etc.,. Glass panels to be of maximum sizes and it should be executed strictly as per detailed drawings / elevations and as per architects approval. Partition with more number of glass pieces are not advised. Rate to include providing & fixing of necessary G.I./wooden/MS frame supports for the above doors, fixtures & additional suspenders etc., complete as per architects / PM's instruction or approval. Tested in an accredited laboratory as per ASTM/ISO standards. Partition to floor/ceiling junctions shall be sealed with acoustic sealant. To have 12mm thk MDF finished with paint of approved shade to be provided all around on junctions of modular door frames & partitions (All around horizontally and vertically)Height of 2400mm. Size 900x2400mm.Glass shall have 50% area under frosting. Cost to include frosting. Cost shall include all hinges, handles, hardware and accesories.Vendor to share shop drawings for architect approval. | NO.S | 1 | 24000 | 24000 | #NAME? | 24000 | #NAME? | #NAME? | #NAME?
18 | 90130834 | Providing and fixing 100mm thk gypboard partition from India gypsum with 50mm x 50mm aluminium frame @ 600mm distance vertically & horizontally center to center. The frame shall be rigidly fixed between floor and ceiling. The same shall be filled with 50mm thk. rock wool 48KG/m3 density (1000GSM) for sound insulation and covered with black color kora cloth & shall be finished with double layer 12mm thk gypsum board on both sides. shall be finished with proper grooves, skirting etc,. see detail drawing. not to be painted in the areas above the false ceiling & below false floor. | sqm | 215 | 2300 | 494500 | #NAME? | 2300 | #NAME? | #NAME? | #NAME?
19 | 90130704 | Supply and installation of fully straight single glazed partition using 10mm thick toughened glass and fixed with proprietary anodised aluminium WIDE LINE sections of size 100mm x 25mm as per architects approval. Rate to include required accessories as per the manufacturers specifications and shall be inclusive of all accessories like rubber gasket etc.,. Glass panels to be of maximum sizes and it should be executed strictly as per detailed drawings / elevations and as per architects approval. Partition with more number of glass pieces are not advised. RATE NOT TO INCLUDE DOOR FRAMES. Rate to include 'I' section, 'L' section, 'T' section & capping at the junction of gypsum partitions & glazed partitions. The glass to glass joints to be bonded with " I section" and 3M VHB double side tape with room temperature and dust free. Rate to include providing & fixing of necessary G.I./wooden/MS frame supports for the above doors, fixtures & additional suspenders etc., complete as per architects / PM's instruction or approval. Tested in an accredited laboratory as per ASTM/ISO standards. Partition to floor/ceiling junctions shall be sealed with acoustic sealant. To have 12mm thk MDF finished with paint of approved shade to be provided all around on junctions of modular door frames & partitions (All around horizontally and vertically)Height of 2400mm. 50% of glass shall be under frosting. Cost shall include frosting. Vendor to share shop drawings for architect approval. | sqm | 54 | 6800 | 367200 | #NAME? | 6800 | #NAME? | #NAME? | #NAME?
20 | 90132182 | Providing and fixing of Fluted acoustic panel cladding with 12mm thk fluted acoustic panel from Vividha or equivalent with 12mm thk ply backing. A 6x6mm groove shall be made between acoustic panel and gypboard in the gypboard and finished with 6x6mm aluminium c-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the acoustic panel shall not have any gypboard. Panel shall have 0.5 NRC. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing | sqm | 17 | 4200 | 71400 | #NAME? | 4200 | #NAME? | #NAME? | #NAME?
21 | 90100402 | Providing & fixing of 6mm thk white lacquered glass with 6mm thk ply backing to be fitted directly on the framework of the gypsum partition so that the glass is in flush lvl with the gypboard. A 6x6mm groove shall be made between glass and gypboard in the gypboard and finished with 6x6mm aluminium C/T-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the glass shall not have any gypboard. | sqm | 31 | 6200 | 192200 | #NAME? | 6200 | #NAME? | #NAME? | #NAME? | Ply backing is 12mm istead of 6mm
22 | 170002758 | Providing and fixing 12mm thk soft board to be fitted above 6mm ply with rounded edge on all sides to stretch the fabric properly. soft board shall be fitted above table skirting upto same ht as writing board. there shall be a 6mm groove fitted with aluminium channel between softboard and skirting and shall run all round the softboard. .Color of the fabric to be selected. samples to be shown. skirting shall be made of 19mm thk ply and finished with laminate same as table top. softboard shall be in flush level with gypboard partition. see detail in typical details sheet. | sqm | 33 | 1800 | 59400 | #NAME? | 1800 | #NAME? | #NAME? | #NAME? | Ply backing is 19mm istead of 6mm
23 | 90130832 | Providing and fixing wallpaper as per architect approval. Wall to be leveled properly to recieve the wallpaper. Installation will be contractors responsibility. care shall be taken for air bubbles not to form and joints shall not be visible. measurement will be given only on the laid area. Basic rate: 90rs/sft | sqm | 41 | 140 | 5740 | #NAME? | 140 | #NAME? | #NAME? | #NAME?
24 | 100000391 | Providing and fixing vinyl stickering as per architect approval. installation will be contractors responsibility. care shall be taken for air bubbles not to form and joints shall not be visible. measurement will be given only on the laid area. | sqm | 12 | 2500 | 30000 | #NAME? | 2500 | #NAME? | #NAME? | #NAME?
25 | 99992398 | Providing and fixing 600x600mm ceramic tile dado of KAJARIA make or equivalent for wall above pantry counter upto 600mm ht as per the drawing. Shall be provided with suitable white cement backing on existing surface, with colour cement finishing including dilute acid. Epoxy joint filler to be used in the joint between tiles.(See Toilet details) | sqm | 2.5 | 2400 | 6000 | #NAME? | 2400 | #NAME? | #NAME? | #NAME?
26 | 90132182 | Providing and fixing of acoustic panel cladding with 12mm thk acoustic panel from Vividha or equivalent with 12mm thk ply backing. A 6x6mm groove shall be made between acoustic panel and gypboard in the gypboard and finished with 6x6mm aluminium c-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the acoustic panel shall not have any gypboard. Panel shall have 0.5 NRC. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing | sqm | 18 | 4200 | 75600 | #NAME? | 4200 | #NAME? | #NAME? | #NAME?
27 | 90131175 | CABIN DESK - 1500mmx 675mm x750mm Ht- Table top - 25mm thick Pre-laminate particle board finished with 2mm edge lipping on the other two sides Supports – MS powder coated 50mm Square MS perform series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top | NOS | 3 | 8500 | 25500 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
28 | 170002757 | Base cabinet shall be made of 19mm BWP ply with 2400MM x 600mm depth and 825mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. counter top shall be finished with 19mm thk granite as per selection with 19mm thk BWP ply base. Kitchen sink of Franke or equivalent. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, 75mm high & 75mm recessed skirting, etc. refer detail drawing. | sqm | 2.4 | 15000 | 36000 | #NAME? | 15000 | #NAME? | #NAME? | #NAME?
29 | 170002757 | Overhead cabinet shall be made of 19mm BWP ply with 2400MM x 300mm depth and 750mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, etc. refer detail drawing. | sqm | 2 | 15000 | 30000 | #NAME? | 15000 | #NAME? | #NAME? | #NAME?
30 | 90131175 | Linear Workstation Size : 1650 x 1650x 1200 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping on the other two sides Screen : 30mm split screen ( fabric magnetic & glass marker ) , 30mm thick with aluminum anodised trim ( 1500 x 300ht ) fabric on longer side and glass marker on shorter side. Supports – MS powder coated 50mm Perform Series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top CPU trolley on castors for the above | NOS | 5 | 18000 | 90000 | #NAME? | 18000 | #NAME? | #NAME? | #NAME?
31 | 99992776 | Pedestal ( 2D + 1 F ) - with Cushion top Size : 450 x 450 x 600ht Top: 18mm Thk pre laminated particle board Back: 9mm Thk pre laminated particle board with 2mm PVC edge lipping Shutters: 18mm Thk pre laminated particle board Edge: All exposed area with 2mm thick PVC edge lipping Handle: Finger groove handles Lock: Regular lock | NOS | 5 | 5000 | 25000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
32 | 90131175 | Linear Workstation Size : 3200 x 600x 750 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping on the other two sides Screen : 30mm split screen ( fabric magnetic & glass marker ) , 30mm thick with aluminum anodised trim ( 1500 x 300ht ) fabric on longer side and glass marker on shorter side. Supports – MS powder coated 50mm Perform Series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top PVC Keyboard tray with a mouse pad CPU trolley on castors for the above | NOS | 1 | 22500 | 22500 | #NAME? | 22500 | #NAME? | #NAME? | #NAME?
33 | 99992776 | Pedestal ( 2D + 1 F ) - with Cushion top Size : 400 x 450 x 600ht Top: 18mm Thk pre laminated particle board Back: 9mm Thk pre laminated particle board with 2mm PVC edge lipping Shutters: 18mm Thk pre laminated particle board Edge: All exposed area with 2mm thick PVC edge lipping Handle: Finger groove handles Lock: Regular lock | NOS | 3 | 5000 | 15000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
34 | 90131175 | Linear Workstation Size : 1200 x 600x 750 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping on the other two sides Screen : 30mm split screen ( fabric magnetic & glass marker ) , 30mm thick with aluminum anodised trim ( 1500 x 300ht ) fabric on longer side and glass marker on shorter side. Supports – MS powder coated 50mm Perform Series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top CPU trolley on castors for the above PVC Keyboard tray with a mouse pad | NOS | 10 | 7100 | 71000 | #NAME? | 7100 | #NAME? | #NAME? | #NAME?
35 | 99992776 | Pedestal ( 2D + 1 F ) - with Cushion top Size : 400 x 450 x 600ht Top: 18mm Thk pre laminated particle board Back: 9mm Thk pre laminated particle board with 2mm PVC edge lipping Shutters: 18mm Thk pre laminated particle board Edge: All exposed area with 2mm thick PVC edge lipping Handle: Finger groove handles Lock: Regular lock | NOS | 10 | 5000 | 50000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
36 | 90131175 | POUFF SEATING - 600X600X450MM To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 2 | 4500 | 9000 | #NAME? | 4500 | #NAME? | #NAME? | #NAME?
37 | 90131175 | CABIN DESK - 1200mmx 675mm x750mm Ht- Table top - 25mm thick Pre-laminate particle board finished with 2mm edge lipping on the other two sides Supports – MS powder coated 50mm Square MS perform series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top | NOS | 1 | 8500 | 8500 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
38 | 90131175 | Meeting table Size : 1050DIA x 750 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping Supports – MS powder coated 50mm perform MS powdercoated leg understructure, with necessary supports Wire Management -450mm flip open with ABS cable tray without switches and sockets | NOS | 1 | 8000 | 8000 | #NAME? | 8000 | #NAME? | #NAME? | #NAME?
39 | 99992487 | Medium Back Chairs (FEATHERLITE) - Nylon Back With Nylon Mesh Up/Down Adjustable Arms ( 1-D ) Nylon Base With Nylon Wheels Single Locking Position Synchro Tilt Mechansim Class IV Gas Lift. | Nos | 30 | 5000 | 150000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
40 | 99992487 | High Back Chairs (FEATHERLITE) - Nylon Back With Nylon Mesh Up/Down Adjustable Arms ( 1-D ) Nylon Base With Nylon Wheels Single Locking Position Synchro Tilt Mechansim Class IV Gas Lift. | Nos | 4 | 6000 | 24000 | #NAME? | 6000 | #NAME? | #NAME? | #NAME?
41 | 99992487 | HIGH CHAIR - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 8 | 4500 | 36000 | #NAME? | 4500 | #NAME? | #NAME? | #NAME?
42 | 90131175 | HIGH TABLE - 600 x 1200 x 1050 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 7800 | 7800 | #NAME? | 7800 | #NAME? | #NAME? | #NAME?
43 | 90131175 | HIGH TABLE - 1100DIA x 1050 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 8500 | 8500 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
44 | 99992487 | CHAIRS - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 2 | 4500 | 9000 | #NAME? | 4500 | #NAME? | #NAME? | #NAME?
45 | 90131175 | 600DIA x 450 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 5300 | 5300 | #NAME? | 5300 | #NAME? | #NAME? | #NAME?
46 | 99992409 | Fire line GYPBOARD FALSE CEILING- Providing and fixing MF suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. Metal expanded rawl plugs shall be bolted to the beam/deck slab and suspenders of the required length shall be provided using GI hangers. Metal expanded rawl plugs and suspenders are to be positiioned at such spacing so that the runner when connected shall have support not exceeding 4' intervals. Main runners coonsisting of GI intermediate channels shall be provided at not exceeding 4' centre in one direction and connected to the suspenders with GI bolts and nuts. GI ceiling channels shall be placed in the opposite direction to the Intermediate channel at not exceeding 2' centres and connected to the intermediate channel using special connecting clips. Gi perimeter channel shall be fixed along the periphery walls, columns, etc. and the ceiling channel shall be inserted and screwed to this perimeter channel. | sqm | 102 | 2200 | 224400 | #NAME? | 2200 | #NAME? | #NAME? | #NAME?
47 | 99992321 | Providing and fixing carpet flooring of imported loopile carpet of Divine/unitex/armstrong make of approved shade and colour. complete in all respect including fixing of 5 mm thick poly urethene foam rolls below the carpet. Rates quoted should include cost of adhesives, fixing , cutting welding of carpet etc complete in all respects.. Laid on site including wastage. (basic rate: 110rs/sft) | sqm | 145 | 2800 | 406000 | #NAME? | 2800 | #NAME? | #NAME? | #NAME?
48 | 90131332 | SILHOUETTE GRID CEILING :Providing and fixing in true horizontal level false ceiling grid of SILHOUTTE GRID 15mm using hot dipped galvonized steel section, Exposed surface chemically cleaned capping prefinished in baked polyster paint, main Tee of size 15 x 44 x 0.3 at every 1200 mm C/C max and rotary stiched Croos Tee of size 15 x 44 x 0.3 mm at every 1200 mm centrally between the 1200mm cross tees and 18 x 18 x 0.5 mm Wall angles all round the the wall to form a grid of size 600 mm x 600mm and suspended the grid using suitable rigid hangers at every 1200 mm intervals at the Main ' T ' and laying tile with edge CONSTILATION TILE of size 600 x 600 x 15 mm over the formed grid., Tile Specs; NRC of the tile to 0.9 ,Class 1 FIRE PERFORMANCE AND HUMIDITY RESISTANCE RH 99 %.The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. | sqm | 2 | 3500 | 7000 | #NAME? | 3500 | #NAME? | #NAME? | #NAME?
49 | 90132107 | Providing and fixing Linear metal ceiling tiles of size 1200,1500 & 1800mm x 150mm, thickness of 15mm with galvanised steel grid system, as per vendor detail and specification. From Armstrong/Tranquil or equivalent. | sqm | 45 | 3500 | 157500 | #NAME? | 3500 | #NAME? | #NAME? | #NAME?
50 | 90132185 | AOUSTIC BAFFLE CEILING - Providing and fixing in true horizontal level false ceiling using 50X100MM Extruded aluminium sections arranged at100mmc/c. The sections to be wrapped with acoustic panles and finished as per architects approval. The cost shall include all necessary hardwares as per vendor specifications | sqm | 34 | 6600 | 224400 | #NAME? | 6600 | #NAME? | #NAME? | #NAME?
51 | 90131163 | Providing and fixing trap doors for access to the areas above false ceiling. The trap door shall have an external frame made using 2" x 2" teakwood frame on which the shutter is hinged. Shutter shall be made using 19mm thk ply. The exposed side shall be finished with 12mm thk gypboard from India Gypsum painted in approved quality and colour. Heavy duty brass hinges shall be used to mount the shutters and locking shall be provided with panel locks. The shutter shall be moulded in level with the false ceiling forming a groove all around. further 6x6mm grooves shall be made on the shutter as per design. Sufficient number of hinges and locks shall be provided to avoid sagging of the shutter. Key also shall be supplied. (No extra rate shall be provided for suspenders or frame work all around for linking the trap door to gypboard false) | sqm | 12 | 11800 | 141600 | #NAME? | 11800 | #NAME? | #NAME? | #NAME?
52 | 90132171 | Providing & fixing alluminium skirting profile of 75mm height. Cost inclusive of adhesive. | rmt | 130 | 150 | 19500 | #NAME? | 150 | #NAME? | #NAME? | #NAME?
53 | 120020840 | Providing & fixing aluminium floor transition profiles from inside spaes or equivalent. | rmt | 11 | 1500 | 16500 | #NAME? | 1500 | #NAME? | #NAME? | #NAME?
54 | 90132171 | Providing & fixing VINYL skirting profile of 75mm height. Cost inclusive of adhesive. | rmt | 20 | 250 | 5000 | #NAME? | 250 | #NAME? | #NAME? | #NAME?
55 | 99992174 | FALSE FLOORING - Providing & Fixing of UNITILE OR EQUIVALENT CEMENTATIOUS INFILL TILE raised flooring system with necessary metal framework (GI/Epoxy coated) as per site requirements. The understructure shall be capable of level adjustment of ±50mm. The flooring to also include thermal insulation (15mm Armaduct Insulation) | sqm | 3 | 8500 | 25500 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
56 | 90111172 | Supply and laying of Cementitious Self Leveling Underlay Material. The surface to be prepared and should be clean , sound and free from loose material and contamination such as plaster ,oil, paint and grease. Thereafter applying one coat of Primer and after the primer application gets dried , the self levelling compound to be applied as per the manufacturers specifications... PRODUCT : ARDEX ENDURA , PRIMER : ARDEX P51 , SELF LEVELLING UNDERLAY : ARDEX CL11 , THICKNESS TO BE 6mm | sqm | 55 | 570 | 31350 | #NAME? | 570 | #NAME? | #NAME? | #NAME?
57 | 99992385 | To prepare & finish 3 coats of tractor emulsion paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of tractor emulsion paint, touching up with putty & applying two final roller coats of tractor emulsion paint, to internal wall/ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. | sqm | 455 | 360 | 163800 | #NAME? | 360 | #NAME? | #NAME? | #NAME?
58 | 90130762 | To prepare & finish 3 coats of asian texture paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of asian texture paint, touching up with putty & applying two final roller coats of texture paint. The application shall be carried out using spray gun and the sprayed surface shall be trowelled for a head cut finish. | sqm | 10 | 500 | 5000 | #NAME? | 500 | #NAME? | #NAME? | #NAME?
59 | 99993108 | Providing and fixing of RUGS | NO.S | 2 | 8000 | 16000 | #NAME? | 8000 | #NAME? | #NAME? | #NAME?
60 | 240001910 | ARTWORK -Providing & fixing of artwork as per selection. | NO.S | 10 | 20000 | 200000 | #NAME? | 20000 | #NAME? | #NAME? | #NAME?
61 | 250003450 | providing and fixing of PLANTERS | NO.S | 20 | 8500 | 170000 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
62 | 230002422 | Providing and fixing temporary site barricading, with wooden runners of size 50mm x50mmas a basic framework and cladding with 6mm plywood.The barricades shall be fixed with printed artwork vinyl on outside.The material will be contractors property after its usage as a barricade.Cost to include dismantalling also. upto a height of 4.5. m | sqm | 72 | 1800 | 129600 | #NAME? | 1800 | #NAME? | #NAME? | #NAME?
63 | 99992504 | Dismantling Dry cladding/Finishes cladding and stacking of serviceable material at MLCP level P2 as directed by engineer incharge | sqm | 225 | 400 | 90000 | #NAME? | 400 | #NAME? | #NAME? | #NAME?
64 | 99992505 | Dismantling aluminium/Gypsum partitions/ply/double skinned bison board with frame, doors,windows, fixed glazing and false ceiling including disposal of unserviceable surplus material and stacking of serviceable material within 500 metres lead as directed by Engineer-in- charge. | sqm | 150 | 750 | 112500 | #NAME? | 750 | #NAME? | #NAME? | #NAME?
65 | 99992135 | Removing metal and wooden door with all its hardware and stacking the same in T2 MLCP as directed by engineer in charge | NO.s | 1 | 2500 | 2500 | #NAME? | 2500 | #NAME? | #NAME? | #NAME?
66 | 99992504 | Dismantling existing SS skirting | rmt | 80 |  | 0 | #NAME? | 0 | #NAME? | #NAME? | #NAME?
67 | 99992262 | Demolishing of flooring tile with mortar | sqm | 150 | 650 | 97500 | #NAME? | 650 | #NAME? | #NAME? | #NAME?
68 | 170002645 | Disposal of building rubbish/malba from building premises from airside,inside building and city side by mechanical transport including loading,unloading etc. and disposal outside the airport premises. | cum | 50 | 1500 | 75000 | #NAME? | 1500 | #NAME? | #NAME? | #NAME?
69 | 120008655 | Providing & plastering to internal block masonry wall/concrete surface 12mm tk in CM1:6,including providing & removing scaffolding,rounding off all corners wherever required,smooth lime rendering(hydrating the lime 24hrs before starting of the work),curing, hacking etc.,complete.With all lead & lift as directed by engineer incharge. | sqm | 7 | 425 | 2975 | #NAME? | 425 | #NAME? | #NAME? | #NAME?
70 | 99992734 | Lintels shall be precast and it should be casted at ground level. Lintel shall be lifted by crane at relevant location, Rate shall include above all activities including lift, lead, casting, shuttering, leaving dowels for chajja etc. | no | 10 | 17000 | 170000 | #NAME? | 17000 | #NAME? | #NAME? | #NAME?
71 | 120014430 | Providing and constructing Brick/Solid Block for 150MM thick walls till R.C.C slab lvl using in cement mortar 1:4, using 2 nos. with 1:6 CM 12mm thk plastered and finished to match the existing wall. The junction of existing & new wall or brick wall and RCC surface to be plastered after placing wiremesh 6" wide on either side. The block should be of minimum compressive strength of 35 Kg/ sqcm. Rate to be inclusive of filling of voids created by chasing of walls for water supply and electrical works with appropriate material as directed, etc. complete. | cum | 0.8 | 10000 | 8000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
72 | 99992441 | Providing and fixing of 35 mm thk flush door as per detail design. Item to be finished with laminates with all necessary joints, grooves, hardware such as hinges, door handle, door closer, door stopper, mortice lock, lock cover plate etc. The door frame shall be 2.5"X5" made out of second grade teak wood with provision of bottom louvers for wshrooms (Pls refer detail drawing) Size: 1000x2100mm | NO.S | 3 | 26000 | 78000 | #NAME? | 26000 | #NAME? | #NAME? | #NAME?
73 | 90130832 | Providing and fixing wallpaper as per architect approval. Wall to be leveled properly to recieve the wallpaper. Installation will be contractors responsibility. care shall be taken for air bubbles not to form and joints shall not be visible. measurement will be given only on the laid area. Basic rate: 90rs/sft | sqm | 117 | 140 | 16380 | #NAME? | 140 | #NAME? | #NAME? | #NAME?
74 | 99992398 | PANTRY TILE DADO - Providing and fixing 600x600mm ceramic tile dado of KAJARIA make or equivalent for wall above pantry counter upto 600mm ht as per the drawing. Shall be provided with suitable white cement backing on existing surface, with colour cement finishing including dilute acid. Epoxy joint filler to be used in the joint between tiles.(See Toilet details) | sqm | 2 | 2450 | 4900 | #NAME? | 2450 | #NAME? | #NAME? | #NAME?
75 | 90131592 | Wall to be fitted with 12mm thk ply and finished with 12mm thk wooden fluted panel as per selection. Panel to be finished with melamine polish.shall be finished with proper grooves,skirting, etc,. | SQM | 47 | 4200 | 197400 | #NAME? | 4200 | #NAME? | #NAME? | #NAME?
76 | 90131592 | Providing and fixing of laminate paneling with 19mm thk ply finished with laminate as per selection. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing. | sqm | 56 | 3400 | 190400 | #NAME? | 3400 | #NAME? | #NAME? | #NAME?
77 | 90131592 | Providing and fixing ply boxing made with 12mm thk ply with proper salwood or GI framework at the back and finished with 12mm thk wooden fluted panel. Boxing to be done to flush the around the column as shown in drawing. To be fixed from floor to false ceiling with proper skirting,etc. to be painted as per selection. wooden fluted panel already considered in wall & surace finishes.item no.05. | sqm | 11 | 9000 | 99000 | #NAME? | 9000 | #NAME? | #NAME? | #NAME?
78 | 170002757 | Providing & fixing of full height storage with shutters made out of 12mm thk ply and finished with approved 12mm thick wooden fluted panel with necessary hardware such as soft close hinges, push-to-open mechanism,locks etc. from HAFELE / or equivalent. internally the cabinets shall be vertically divided equally into with shelves made of 12mm thk ply. all internal areas shall be finished with a 0.8mm laminate as per selection. The item shall be provided with proper grooves, skirting etc,. as per drawing. wooden fluted panel already considered in wall & surace finishes.item no.05. | sqm | 11 | 10500 | 115500 | #NAME? | 10500 | #NAME? | #NAME? | #NAME?
79 | 170002757 | PLY BOXING FOR TV NICHE - Providing and fixing ply boxing made with 19mm thk ply with proper salwood or GI framework at the back and finished with 4mm thk veneer panel. To be fixed from floor to false ceiling with proper skirting,etc. to be painted as per selection. niche to be made in the boxing as required to fit the led screens as required. AV vendor shop drawing is required. veneer panel already considered in wall & surace finishes.item no.05. | sqm | 45 | 7800 | 351000 | #NAME? | 7800 | #NAME? | #NAME? | #NAME?
80 | 170002757 | PANTRY BOTTOM COUNTER - Base cabinet shall be made of 19mm BWP ply with 2200MM x 600mm depth and 825mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. counter top shall be finished with 19mm thk granite as per selection with 19mm thk BWP ply base. Kitchen sink of Franke or equivalent. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, 75mm high & 75mm recessed skirting, etc. refer detail drawing. | sqm | 2.2 | 15000 | 33000 | #NAME? | 15000 | #NAME? | #NAME? | #NAME?
81 | 99992487 | Medium Back Chairs (FEATHERLITE) - Nylon Back With Nylon Mesh Up/Down Adjustable Arms ( 1-D ) Nylon Base With Nylon Wheels Single Locking Position Synchro Tilt Mechansim Class IV Gas Lift. | Nos | 9 | 5000 | 45000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
82 | 170002757 | Providing and fixing shutters made with 19mm thk ply finished with 4mm thk veneer as per selection with a 50x50mm wooden framework as per drawing. Shutters shall have 19mm slits at every 25mm gaps done by CNC machine. Item shall have all necassry hardware such as hinges, locks, handles, etc. shall have a 75mm high skirting depressed in by 75mm made with 19mm thk ply finished with same laminate as shutter. shutter shall be upto 2400mm ht from ffl. the remaining area upto false ceiling will be a fixed panel. item to be finished with proper grooves, skirting, etc. see detailed drawing. | sqm | 10 | 10000 | 100000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
83 | 90131175 | L-SHAPE Workstation Size : 600,1200 x 600x 750 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping on the other two sides Screen : 30mm split screen ( fabric magnetic & glass marker ) , 30mm thick with aluminum anodised trim ( 1500 x 300ht ) fabric on longer side and glass marker on shorter side. Supports – MS powder coated 50mm Perform Series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top CPU trolley on castors for the above PVC Keyboard tray with a mouse pad | NOS | 1 | 10500 | 10500 | #NAME? | 10500 | #NAME? | #NAME? | #NAME?
84 | 99992776 | Pedestal ( 2D + 1 F ) - with Cushion top Size : 450 x 450 x 600ht Top: 18mm Thk pre laminated particle board Back: 9mm Thk pre laminated particle board with 2mm PVC edge lipping Shutters: 18mm Thk pre laminated particle board Edge: All exposed area with 2mm thick PVC edge lipping Handle: Finger groove handles Lock: Regular lock | NOS | 1 | 5500 | 5500 | #NAME? | 5500 | #NAME? | #NAME? | #NAME?
85 | 90131175 | Meeting table Size : 4800 x 1500 x 750 ht Table top - 12mm thk corian top with double layer 19mm thk ply base Supports – MS powder coated 50mm perform MS powdercoated leg understructure, with necessary supports Wire Management -450mm flip open with ABS cable tray without switches and sockets | NOS | 1 | 165000 | 165000 | #NAME? | 165000 | #NAME? | #NAME? | #NAME?
86 | 99992487 | High Back Chairs (FEATHERLITE) - Nylon Back With Nylon Mesh Up/Down Adjustable Arms ( 1-D ) Nylon Base With Nylon Wheels Single Locking Position Synchro Tilt Mechansim Class IV Gas Lift. | Nos | 1 | 6500 | 6500 | #NAME? | 6500 | #NAME? | #NAME? | #NAME?
87 | 99992696 | SINGLE SEATER SOFA - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 2 | 10000 | 20000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
88 | 90131758 | 3- SEATER SOFA - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 1 | 28000 | 28000 | #NAME? | 28000 | #NAME? | #NAME? | #NAME?
89 | 99992696 | SINGLE SEATER SOFA - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 2 | 10000 | 20000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
90 | 90131175 | 600DIA x 450 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 5500 | 5500 | #NAME? | 5500 | #NAME? | #NAME? | #NAME?
91 | 90131175 | 600 x 900 x 450 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 6500 | 6500 | #NAME? | 6500 | #NAME? | #NAME? | #NAME?
92 | 90131175 | 1100dia x 750 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 9800 | 9800 | #NAME? | 9800 | #NAME? | #NAME? | #NAME?
93 | 99992487 | CHAIRS - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 4 | 5000 | 20000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
94 | 99992409 | Fire line GYPBOARD FALSE CEILING- Providing and fixing MF suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. Metal expanded rawl plugs shall be bolted to the beam/deck slab and suspenders of the required length shall be provided using GI hangers. Metal expanded rawl plugs and suspenders are to be positiioned at such spacing so that the runner when connected shall have support not exceeding 4' intervals. Main runners coonsisting of GI intermediate channels shall be provided at not exceeding 4' centre in one direction and connected to the suspenders with GI bolts and nuts. GI ceiling channels shall be placed in the opposite direction to the Intermediate channel at not exceeding 2' centres and connected to the intermediate channel using special connecting clips. Gi perimeter channel shall be fixed along the periphery walls, columns, etc. and the ceiling channel shall be inserted and screwed to this perimeter channel. | sqm | 121 | 2400 | 290400 | #NAME? | 2400 | #NAME? | #NAME? | #NAME?
95 | 90131332 | 600X600MM WOODEN GRID CEILING - Providing and fixing Wooden ceiling, fabricate and install 12 mm thk. plywood ceiling with appropriate reinforcement with suitable 2" x 2" frame supports at every 2' x 2' c/c supported from the slab with cut outs for light fixtures, ac grilles etc. The ply is to be finished with 1mm thk laminate over 4mm thk ply to form 4mm x 4mm grooves as per design. The wooden ceiling will have drops or coves as per design from adjacent ceiling by 150mm , and hence facia of 150mm is visible. Area / quantity indicated is surface area, including vertical facia of 150mm . . Coves as per design to be provided of 200mm width and 100mm heght ALL VERTICALS UPTO 150MM WILL NOT BE PAYABALE AND SHOUDL BE PART OF RATE QUOTED, | sqm | 35 | 5000 | 175000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
96 | 90132185 | ACOUSTIC CEILING - Providing and fixing acoustic suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. ceiling shall be finished with 12mm thk acoustic panel with 0.9 NRC rating with 12mm thk ply backing. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. | sqm | 25 | 6500 | 162500 | #NAME? | 6500 | #NAME? | #NAME? | #NAME?
97 | 99992321 | Providing and fixing carpet flooring of imported loopile carpet of Divine/unitex/armstrong make of approved shade and colour. complete in all respect including fixing of 5 mm thick poly urethene foam rolls below the carpet. Rates quoted should include cost of adhesives, fixing , cutting welding of carpet etc complete in all respects.. Laid on site including wastage. (basic rate: 110rs/sft) | sqm | 165 | 3000 | 495000 | #NAME? | 3000 | #NAME? | #NAME? | #NAME?
98 | 90132171 | Providing & fixing alluminium skirting profile of 75mm height. Cost inclusive of adhesive. | rmt | 120 | 1200 | 144000 | #NAME? | 1200 | #NAME? | #NAME? | #NAME?
99 | 99992385 | To prepare & finish 3 coats of tractor emulsion paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of tractor emulsion paint, touching up with putty & applying two final roller coats of tractor emulsion paint, to internal wall/ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. | sqm | 3080 | 360 | 1108800 | #NAME? | 360 | #NAME? | #NAME? | #NAME?
100 | 90130762 | To prepare & finish 3 coats of asian texture paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of asian texture paint, touching up with putty & applying two final roller coats of texture paint. The application shall be carried out using spray gun and the sprayed surface shall be trowelled for a head cut finish. | sqm | 616 | 500 | 308000 | #NAME? | 500 | #NAME? | #NAME? | #NAME?
101 | 170002764 | Providing & fixing of Shelf made out of 19mm thk ply and finished with approved 4mm thick Veneer as per selection,melamine polish with necessary hardware from HAFELE / or equivalent. the bookshelf shall be divided into equal parts with shelves made of 12mm thk ply. all internal areas shall be finished with 4mm veneer as per selection. The item shall be provided with proper grooves, 75mm high & 75mm recessed skirting etc,. as per drawing. 1700X250X3000MM | Nos. | 1 | 125000 | 125000 | #NAME? | 125000 | #NAME? | #NAME? | #NAME?
102 | 170002764 | SIDE RETURN TABLE - 900mmx450mmx750mm Ht | NOS | 1 | 15000 | 15000 | #NAME? | 15000 | #NAME? | #NAME? | #NAME?
103 | 90131975 | Plaster of paris or gypboard moulded as per the design and detail of the architect shall be fixed to the GI frame work for indirect lighting. The mould shall be properly finished and levelled. For indirect lighting | rmt | 42 | 225 | 9450 | #NAME? | 225 | #NAME? | #NAME? | #NAME?
104 | 170002764 | SEATER WITH STORAGE - Providing & fixing of 600mm deep, 4500mm length & 450mm height seating with storage. item carcass to bemade with 19mm thk ply finished with 4mm thk veneer as per drawing with shutters made out of 19mm thk ply and finished with approved 4mm thick veneer with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent. internal area to be divided finished with laminate as per selection the top shall be made with ply covered with a seating made with 100mm foam filling and wrapped around with a fabric as per selection. The item shall be provided with proper grooves, skirting etc,. as per drawing. | Nos. | 2 | 75000 | 150000 | #NAME? | 75000 | #NAME? | #NAME? | #NAME?
105 | 170002764 | Providing & fixing of storage with shutters made out of 19mm thk ply and finished with approved 1mm thick laminate with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent. internally the cabinets shall be vertically divided into 2 equal parts with shelves made of 12mm thk ply. all internal areas shall be finished with a 0.8mm laminate as per selection. Top of the storage shall be made with 19mm thk ply and finished with laminate postformed with matching edge banding. Overhead storage shutters to be finished with 1mm thk laminate matt finish as per selection, all internal surfaces to be finished with 0.8mm laminate as per selection. The item shall be provided with proper grooves, 75mm high & 75mm recessed skirting etc,. as per drawing. 2100X450X450MM | no | 1 | 40000 | 40000 | #NAME? | 40000 | #NAME? | #NAME? | #NAME?
106 | 90131975 | Plaster of paris or gypboard moulded as per the design and detail of the architect shall be fixed to the GI frame work for indirect lighting. The mould shall be properly finished and levelled. For indirect lighting | rmt | 120 | 250 | 30000 | #NAME? | 250 | #NAME? | #NAME? | #NAME?
107 | 120019346 | Providing & plastering to internal block masonry wall/concrete surface 12mm tk in CM1:6,including providing & removing scaffolding,rounding off all corners wherever required,smooth lime rendering(hydrating the lime 24hrs before starting of the work),curing, hacking etc.,complete.With all lead & lift as directed by engineer incharge. | sqm | 30 | 425 | 12750 | #NAME? | 425 | #NAME? | #NAME? | #NAME?
|  |  |  | SUB TOTAL |  | 10959145 |  |  | #NAME?
|  |  |  | SGST @ 9% |  | 986323.05 |  |  | #NAME?
|  |  |  | CGST @ 9% |  | 986323.05 |  |  | #NAME?
|  |  |  | GRAND TOTAL |  | 12931791.1 |  |  | #NAME?