## RAB Sheet
| Masala Kitchen | BOQ for Masala Kitchen Cart : 6x2.550x3 (mtr.) | Lucknow | Outdoor |  |  |  |  | For PO | Remarks | Billing Qty
S.No | Head | Description | Drawing Ref No. | Make | Size | UOM | Qty | Rate | Amount(INR) |  | QTY | Amount | Difference
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer and powder coated paint of approved shared at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. |  | Jindal/Tata |  | Kgs | 670 | 165 | 110550 |  | 670 | 110550 | 0
2 | Base & Flooring | Providing and fixing of 18mm FR Ply with 1.5mm thick aluminium checker sheet finish mounted over MS pipe 50mm SHS , C/C 600x600mm grid, 4mm thick MS Sheet |  | Century Ply, Tata/ Jindal | 6000x2550 | Sqm | 15.3 | 4000 | 61200 |  | 14.4 | 57600 | -3600
3 | ACP Work (for Ceiling) | Providing , installing and fixing in position FR Aluminium Composite Panel Cladding for linear as well as curvilinear portions of the building , for all heights and all levels etc. including: a) Structural analysis & design and preparation of shop drawings') Back framing for panel as suited to site condition.eg.Alluminium or MS box sections etc c) Providing, fabricating and supplying and fixing panels of aluminium composite panel cladding in pan shape in metallic colour of approved shades as per specifications below. The Contractor shall provide wall with aluminium composite panel cladding, having all the performance characteristics all complete . (MS Structure cost not included in it) |  | Timex Alu decor or equivalent | 6000x3600 | Sqm | 21.6 | 3500 | 75600 |  | 14.58 | 51030 | -24570
4 | Shade for Roof | Providing & fixing of of 6mm Semi Transparent/opac sheet with MS Framing fix with self screw with required paint finish. (note : MS Structure is not included in this cost) |  |  | 6x 4 | Sqm | 24 | 1500 | 36000 |  | 15 | 22500 | -13500
5 | Rafter's Foof | Providing and fixing of Wooden Rafter 12mm HDMR Laminate cladding with approved shade matt finish. |  | Century Ply & Merino |  | Rmt. | 19.2 | 1650 | 31680 |  | 17.08 | 28182 | -3498
6 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. |  | Century or equivalent |  | Sqm | 51.12 | 3200 | 163584 |  | 50.936 | 162995.2 | -588.8
7 | Wall Tile | Providing , installing and fixing in of yellow moroccon pattern tile on back wall |  | Customise Make | 6000x2700, 6000x600 | Sqm | 19.8 | 2400 | 47520 |  | 17.802 | 42724.8 | -4795.2
8 | Corian Cladding | Providing & fixing of 12mm Acrylic solid surface outside of side partion & front low height partion (Base Rate : 850 Sqft.) |  | LG Hi mac | 1000x950, 6800x300 | Sqm | 2.99 | 12500 | 37375 |  | 2.99 | 37375 | 0
9 | Paint | Apply of 2 coat white duco paint on pillar & side partition left&right |  | Duco Paint | 2400x600 x2, 300x3000x5, 900x900 | Sqm | 7.38 | 2400 | 17712 |  | 5.762 | 13828.8 | -3883.2
10 | Wooden Panelling | Providing & fixing of vertical groove laminate outside of side partion & horizontal groove wooden front full height cladding on existing plywood partition (Marino Laminate Base Rate : 65 Sqft.) |  |  | 2400x600x2, 2250x900x1, | Sqm | 5.175 | 3600 | 18630 |  | 4.5 | 16200 | -2430
11 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with solid acrylic surface & inside laminate finish , Hydraulic hinges, SS knob, tower bolt etch. |  |  | 1x.9 | EA | 1 | 8800 | 8800 |  | 1 | 8800 | 0
12 | Awning/Canvas | P& F Awnings on both of side Red & White Colour SRF make cloths with 40 mm x 40mm x3mm Thick Asian make squire aluminium pipe frame including 02 coat red oxide paint , 02 coat Asian make primer, and 02 coat Asian make oil paint on Rolling frame. |  | Cavas, HP Latex | 6000x1000x1, 3000x1000x2 | Sqm | 12 | 3600 | 43200 |  | 12 | 43200 | 0
13 | Kitchen Wooden Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, , two solft close drawers storage shutter door, (As per approved GFC) | 2 | Century Ply, FGV hinges | 1900x750x900 | No. | 2 | 36000 | 72000 |  | 2 | 72000 | 0
14 | Sink Cabinet | Providing and fixing of Sink counter made of 18mm FR Ply with laminate finish, 450x500mm SS 304 sink, shutter storage, plumbing fitting etc.(As Per approved GFC) | 9 | Century/Merino, SS Sink | 1500x750x900 | No. | 1 | 45760 | 45760 |  | 1 | 45760 | 0
15 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with solid acryilc surface top finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | 7 | Century/Merino/ FGV | 825x750x900 | No. | 2 | 45000 | 90000 |  | 2 | 90000 | 0
16 | Skink New Sensor Tap | Providing & Fitting of Sensor Tap as required |  | Euronics |  | Nos. | 1 | 7500 | 7500 |  | 1 | 7500 | 0
17 | Water Pump | Providing & Fitting of Waterpump as required |  | Crompton AQUAGOLD 100-33 Residential Water Pump Self Priming Regenerative 1 HP Single Phase |  | Nos. | 1 | 8500 | 8500 |  | 1 | 8500 | 0
18 | Site Storages | Providing and installation of make of 18mm & 12mm Fr Plywood with approved laminate finish with hinges soft closed shutter. |  | Century/Merino/ FGV | 1155x650x640 | Nos. | 1 | 22500 | 22500 |  | 1 | 22500 | 0
19 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) |  | Havells, Syska or equivalent |  | No. | 5 | 2500 | 12500 |  | 4 | 10000 | -2500
20 | Linear Profile Light | Providing & fixing linear profile light consealed in Rafter |  | Custom Make | 1200x1 | No. | 8 | 1800 | 14400 |  | 7 | 12600 | -1800
21 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, DB panel, MCB, ELCB, as per requirement or as approved electrical drawing |  | Polycab, Finolex, Roma, Crompton | 6000x3000 | No. | 1 | 88000 | 88000 |  | 1 | 88000 | 0
22 | Industrial Socket | Industrial Socket & Panel Box (32amp ) |  |  |  | No. | 8 | 3500 | 28000 |  | 4 | 14000 | -14000
23 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork |  | HP Latex, 3M , LG Vinyl or equivalent |  | Sqft. | 0 | 150 | 0 |  | 0 | 0 | 0
24 | Masala Kitchen Logo | Front logo signaged fixed front chiller counter, UV Printed 3mm raised acrylic . |  | A cast , NGX , Osram | 900x900 | No. | 1 | 12000 | 12000 |  | 1 | 12000 | 0
25 | Header Signage | Providing and fixing of backlit channelium raised signages, NGX LED & Osram water proof supply with all required support structure (2100x 500x 1pcs) |  | A cast , NGX , Osram |  | No. | 1 | 22500 | 22500 |  | 1 | 22500 | 0
26 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. |  | A cast , NGX , Osram | 2x 3 | No. | 3 | 4500 | 13500 |  | 3 | 13500 | 0
27 | TV Screen Menu | 32" LED TV with hanging Stand |  | Samsung/LG |  | No. |  | 28000 | 0 | If Required | 0 | 0 | 0
28 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 4 nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire |  | Hikvision |  | Set | 1 | 48000 | 48000 |  | 0 | 0 | -48000
29 | Installation | Lucknow Airport |  |  |  | EA | 1 | 48000 | 48000 |  | 1 | 48000 | 0
30 | Transportation | Lucknow Airport |  |  |  | EA | 1 | 26000 | 26000 |  | 1 | 26000 | 0
31 | Labour Union Charges | Extra as on actual | [9 empty] | 0 | 0
[12 empty] | 0 | 0
| TOTAL | [7 empty] | 1211011 |  |  | 1087845.8 | -123165.2
NOTE: | GST Extra | [10 empty] | -123165.2

## MB Sheet
| Masala Kitchen | BOQ for Masala Kitchen Cart : 6x2.550x3 (mtr.) | Lucknow | Outdoor |  | PO Qty. |  | Actual Qty Measurement |  |  |  |  | Billed Qty
S.No | Head | Description | Drawing Ref No. | Make | Size | UOM | Qty | Length | Width | Height | Nos/Wt | Qty
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer and powder coated paint of approved shared at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. |  | Jindal/Tata |  | Kgs | 670 |  |  |  |  | 675.5 | 670
|  | Back Structure - 40x40x2mm | [8 empty] | 168
|  | Top Structure - 40x40x2 | [8 empty] | 146
|  | Bottom Structure -50x50x2mm | [8 empty] | 198
|  | Right & Left Side-40x40x2 | [8 empty] | 78
|  | Front Side-40x40x2 | [8 empty] | 36
|  | Pillar (50x50x2) | [8 empty] | 49.5
2 | Base & Flooring | Providing and fixing of 18mm FR Ply with 1.5mm thick aluminium checker sheet finish mounted over MS pipe 50mm SHS , C/C 600x600mm grid, 4mm thick MS Sheet |  | Century Ply, Tata/ Jindal |  | Sqm | 15.3 | 6 | 2.4 |  | 1 | 14.4 | 14.4
3 | ACP Work (for Ceiling) | Providing , installing and fixing in position FR Aluminium Composite Panel Cladding for linear as well as curvilinear portions of the building , for all heights and all levels etc. including: a) Structural analysis & design and preparation of shop drawings') Back framing for panel as suited to site condition.eg.Alluminium or MS box sections etc c) Providing, fabricating and supplying and fixing panels of aluminium composite panel cladding in pan shape in metallic colour of approved shades as per specifications below. The Contractor shall provide wall with aluminium composite panel cladding, having all the performance characteristics all complete . (MS Structure cost not included in it) |  | Timex Alu decor or equivalent |  | Sqm | 21.6 | 6 | 2.43 |  | 1 | 14.58 | 14.58
4 | Shade for Roof | Providing & fixing of of 6mm Semi Transparent/opac sheet with MS Framing fix with self screw with required paint finish. (note : MS Structure is not included in this cost) |  |  |  | Sqm | 24 | 6 | 2.5 |  | 1 | 15 | 15
5 | Rafter's Foof | Providing and fixing of Wooden Rafter 12mm HDMR Laminate cladding with approved shade matt finish. |  | Century Ply & Merino |  | Rmt. | 19.2 | 2.44 |  |  | 7 | 17.08 | 17.08
6 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. |  | Century or equivalent |  | Sqm | 51.12 |  |  |  |  | 50.936 | 50.936
|  | Back Wall | [5 empty] | 6 | 2.7 | 2 | 32.4
|  | Front | [5 empty] | 6 | 0.95 | 2 | 11.4
|  | Left Wall | [5 empty] | 2.44 | 0.95 | 2 | 4.636
|  | Right Wall | [5 empty] | 2.44 | 0.95 | 2 | 4.636
|  | Less | [5 empty] | 2.67 | 0.4 | -2 | -2.136
7 | Wall Tile | Providing , installing and fixing in of yellow moroccon pattern tile on back wall |  | Customise Make |  | Sqm | 19.8 |  |  |  |  | 17.802 | 17.802
[8 empty] | 6 | 2.7 | 1 | 16.2
[8 empty] | 2.67 | 0.6 | 1 | 1.602
8 | Corian Cladding | Providing & fixing of 12mm Acrylic solid surface outside of side partion & front low height partion (Base Rate : 850 Sqft.) |  | LG Hi mac |  | Sqm | 2.99 |  |  |  |  | 2.99 | 2.99
[8 empty] | 1 | 0.95 | 1 | 0.95
[8 empty] | 6.8 | 0.15 | 2 | 2.04
9 | Paint | Apply of 2 coat white duco paint on pillar & side partition left&right |  | Duco Paint |  | Sqm | 7.38 |  |  |  |  | 5.762 | 5.762
[8 empty] | 2 | 0.2 | 5 | 2
[8 empty] | 6 | 0.2 | 1 | 1.2
[8 empty] | 2.562 | 1 | 1 | 2.562
10 | Wooden Panelling | Providing & fixing of vertical groove laminate outside of side partion & horizontal groove wooden front full height cladding on existing plywood partition (Marino Laminate Base Rate : 65 Sqft.) |  |  |  | Sqm | 5.175 |  |  |  |  | 4.5 | 4.5
[8 empty] | 6 | 0.75 |  | 1 | 4.5
11 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with solid acrylic surface & inside laminate finish , Hydraulic hinges, SS knob, tower bolt etch. |  |  | 1x.9 | EA | 1 |  |  |  | 1 | 1 | 1
12 | Awning/Canvas | P& F Awnings on both of side Red & White Colour SRF make cloths with 40 mm x 40mm x3mm Thick Asian make squire aluminium pipe frame including 02 coat red oxide paint , 02 coat Asian make primer, and 02 coat Asian make oil paint on Rolling frame. |  | Cavas, HP Latex | 6000x1000x1, 3000x1000x2 | Sqm | 12 |  |  |  |  | 12 | 12
[8 empty] | 6 | 1 | 1 | 6
[8 empty] | 3 | 1 | 2 | 6
13 | Kitchen Wooden Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, , two solft close drawers storage shutter door, (As per approved GFC) | 2 | Century Ply, FGV hinges | 1900x750x900 | No. | 2 |  |  |  |  | 2 | 2
14 | Sink Cabinet | Providing and fixing of Sink counter made of 18mm FR Ply with laminate finish, 450x500mm SS 304 sink, shutter storage, plumbing fitting etc.(As Per approved GFC) | 9 | Century/Merino, SS Sink | 1500x750x900 | No. | 1 |  |  |  |  | 1 | 1
15 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with solid acryilc surface top finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | 7 | Century/Merino/ FGV | 825x750x900 | No. | 2 |  |  |  |  | 2 | 2
16 | Skink New Sensor Tap | Providing & Fitting of Sensor Tap as required |  | Euronics |  | Nos. | 1 |  |  |  |  | 1 | 1
17 | Water Pump | Providing & Fitting of Waterpump as required |  | Crompton AQUAGOLD 100-33 Residential Water Pump Self Priming Regenerative 1 HP Single Phase |  | Nos. | 1 |  |  |  |  | 1 | 1
18 | Site Storages | Providing and installation of make of 18mm & 12mm Fr Plywood with approved laminate finish with hinges soft closed shutter. |  | Century/Merino/ FGV | 1155x650x640 | Nos. | 1 |  |  |  |  | 1 | 1
19 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) |  | Havells, Syska or equivalent |  | No. | 5 |  |  |  |  | 4 | 4
20 | Linear Profile Light | Providing & fixing linear profile light consealed in Rafter |  | Custom Make | 1200x1 | No. | 8 |  |  |  |  | 7 | 7
21 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, DB panel, MCB, ELCB, as per requirement or as approved electrical drawing |  | Polycab, Finolex, Roma, Crompton | 6000x3000 | No. | 1 |  |  |  |  | 1 | 1
22 | Industrial Socket | Industrial Socket & Panel Box (32amp ) |  |  |  | No. | 8 |  |  |  |  | 4 | 4
23 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork |  | HP Latex, 3M , LG Vinyl or equivalent |  | Sqft. | 0 |  |  |  |  | 0 | 0
24 | Masala Kitchen Logo | Front logo signaged fixed front chiller counter, UV Printed 3mm raised acrylic . |  | A cast , NGX , Osram | 900x900 | No. | 1 |  |  |  |  | 1 | 1
25 | Header Signage | Providing and fixing of backlit channelium raised signages, NGX LED & Osram water proof supply with all required support structure (2100x 500x 1pcs) |  | A cast , NGX , Osram |  | No. | 1 |  |  |  |  | 1 | 1
26 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. |  | A cast , NGX , Osram | 2x 3 | No. | 3 |  |  |  |  | 3 | 3
27 | TV Screen Menu | 32" LED TV with hanging Stand |  | Samsung/LG |  | No. | [5 empty] | 0 | 0
28 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 4 nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire |  | Hikvision |  | Set | 1 | [5 empty] | 0
29 | Installation | Lucknow Airport |  |  |  | EA | 1 |  |  |  |  | 1 | 1
30 | Transportation | Lucknow Airport |  |  |  | EA | 1 |  |  |  |  | 1 | 1
Signature