## 111
[5 empty] | Yashvas Interiors |  | As per site | As per | As per
Sl.No. | Materials Description | Qty | UOM | GST | Rate | Amount | Status of work | site qty | site value
1 | Corian top wooden with laminate storage front counter need to cut the size of 950x750mm for to be placed display chiller | 1 | NOS | 18% | 8500 | 8500 | Completed | 1 | 8500
2 | Providing and fixing 19mm ply with laminate finish at two sides of display chiller 36"x37" | 2 | NOS | 18% | 6000 | 12000 | Completed | 2 | 12000
3 | Providing and fixing storage rack and door with 19mm plywood with laminate finish size -(17x34" - 1no, 28x34" - 2) , Laminate - 40', Plywood -22' | 3 | NOS | 18% | 19500 | 58500 | Completed | 3 | 58500
4 | Corian re polish of front and back counter tops | 1 | NOS | 18% | 12000 | 12000 | Nil |  | 0
5 | Providing and fixing laminate on existing laminate ( Yellow,green & white col col) | 300 | SFT | 18% | 350 | 105000 | Completed | 347 | 121450
6 | Make cutout on corian top couter the size of 36"x24" for table top bain-marie placing | 1 | no | 18% | 8500 | 8500 | Completed | 1 | 8500
7 | After cutout for bain-marie to be finished at 3 sides with ply & laminate size - 3'x2'x3' | 1 | Nos | 18% | 16000 | 16000 | Completed | 1 | 16000
8 | Providing & fixing 19 mm ply with laminate finish partition at front side for dosa tawa area 50" x17"x 3" ( laminate at two sides) | 1 | nos | 18% | 12500 | 12500 | Completed | 1 | 12500
9 | Providing & fixing counter top with storage and shutters for Placing dosa Tawa ( 19mm plywood with laminate) 50" x 37" x 37" | 1 | no | 18% | 32000 | 32000 | Completed | 1 | 32000
10 | Provide and fixing white col corian for counter top - 6 mm, 130"x38" ( Providingn & fixing with 19 mm marine plywood ofm counter and make coutout for bain marie size- 1200x650 | 1 | no | 18% | 38000 | 38000 | completed | 1 | 38000
11 | Providing and fixing 12 mm plywood on wall glass | 100 | Sft | 18% | 250 | 25000 | completed | 30 | 7500
12 | Providing and fixing side partition 19mm plywood with laminate finish 37"x36"x 3" | 1 | no | 18% | 9000 | 9000 | completed | 3 | 27000
13 | Make plywood with laminate finish poles 2 nos ( 4" x 4" x90") | 1 | no | 18% | 24000 | 24000 | completed | 2 | 48000
14 | Make plywood with laminate finish supports to be taken from side wall and mother slab of wooden pillers for lights and TV, Size - 130" x 4 " x 4" - 4 nos, 102" x 4" x 4" - 4 nos | 8 | no | 18% | 6500 | 52000 | completed | 8 | 52000
15 | Providing and fixing 12 mm plywood with laminate finish at front side counter size - 130"x20" - 1 no ( laminate on one side only ) | 1 | no | 18% | 9000 | 9000 | Completed | 1 | 9000
16 | Back counter corian top polishing | 1 | no | 18% | 4000 | 4000 |  |  | 0
17 | 12 mm toughened glass with polished for bainmarie covering (3'.6"X 12" - 2 Nos,15"x12" - 2 nos ) | 3 | no | 18% | 7000 | 21000 | completed | 2 | 14000
18 | Providing & fixing Flexxible plywoode for curve shap 60' | 100 | Sft | 18% | 350 | 35000 | completed | 96 | 33600
19 | Providing & fixing corian at top of flexi plywood | 100 | Sft | 18% | 750 | 75000 | completed | 75 | 56250
20 | Dismantling the existing partition | 1 |  | 18% | 10000 | 10000 | completed | 1 | 10000
21 | Idli.com Sinage | 1 | nos | 18% |  | 0 | nil |  | 0
22 | 2.5 sqmm single core cable | 150 | mtr | 18% | 75 | 11250 | completed | 150 | 11250
23 | 1.5 sqmm single core cable | 50 | mtr | 18% | 50 | 2500 | completed | 40 | 2000
24 | 15 Amp 6 mod legrand brand switch & socket | 3 | nos | 18% | 550 | 1650 | completed | 6 | 3300
25 | 3 Plus One camera cable | 75 | mtr | 18% | 20 | 1500 | completed | 65 | 1300
26 | Single phase Legrand industrial socket | 3 | nos | 18% | 2500 | 7500 | completed | 4 | 10000
27 | LED round 12w ceiling lights | 6 | Nos | 18% | 1350 | 8100 | completed | 3 | 4050
28 | 1" Metal contitude | 20 | nos | 18% | 250 | 5000 | completed | 20 | 5000
29 | Metal spiral hose | 10 | mtr | 18% | 50 | 500 | completed | 10 | 500
30 | 6 Modular box with seat | 4 | Nos | 18% | 900 | 3600 | completed | 4 | 3600
31 | Labour Charges | 1 | Nos | 18% | 22000 | 22000 | completed | 1 | 22000
[6 empty] | 630600 |  |  | 627800
Note on I19: Author: 2 nos = 8 sft As per 3 os = 6 sft