## SUMMARY
SL NO | PO NO | AMOUNT
1 | Semolina/PO/24-25/000896 | 186719.4
2 | Semolina/PO/24-25/000846 | 129699.157
3 | Semolina/PO/24-25/000848 | 138813.2235
Total |  | 455231.7805
GST 18% |  | 81941.7205
Grand Total (With GST) |  | 537173.501

## PO
|  |  |  | AS PER BOQ |  |  | AS ACTUAL
SL NO | PO NO | DESCRIPTION OF WORK | UNIT | QTY | RATE | AMOUNT | QTY | AMOUNT
1 | Semolina/PO/24-25/000896 | P F of MS Framework with 50mm x 50mm x 16 gauge MS tube framing out of vertical members at 600mm c c with horizontal members at 600 mm c c, the framework b or w main MS members by welding to fix cement board on it. Area: Kitchen Back Wall Partition | Sqm | 46 | 3577 | 164542 | 52.2 | 186719.4
2 | Semolina/PO/24-25/000846 | BOH, TOILET & BAR RAISED AREA (up to 300 mm) - Providing & Filling light wt. Siporex block bats to conceal drainage & plumbing lines. The Top layer should be finished properly to receive P .C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect . | Sqm | 53 | 2690 | 142570 | 48.2153 | 129699.157
3 | Semolina/PO/24-25/000848 | Providing and laying in position cement concrete of specified grade excluding the cost of centring & shuttering all work upto 60 mm from existing lvl. 1:4:8 (1 cement: 4 coarse sand: 8 graded stone aggregate 40mm nominal size) Area: FOH | Sqm | 110 | 1161 | 127710 | 119.5635 | 138813.2235
| TOTAL |  |  |  |  | 434822 |  | 455231.7805

## NT items Measurement Sheet
SL NO | DESCRIPTION OF WORK | UNIT | NO | LENGTH | BREADTH | HEIGHT | QUANTITY | REMARKS
1 | Semolina/PO/24-25/000896 Ms Framing | Sqm | 1 | 780 |  | 2400 | 1.872
|  |  | 1 | 4500 |  | 2400 | 10.8
|  |  | 1 | 4030 |  | 2400 | 9.672
|  |  | 1 | 1100 |  | 2400 | 2.64
|  |  | 1 | 1410 |  | 2400 | 3.384
|  |  | 1 | 4000 |  | 2400 | 9.6
|  |  | 1 | 2900 |  | 2400 | 6.96
|  |  | 1 | 1960 |  | 2400 | 4.704
|  |  | 1 | 1070 |  | 2400 | 2.568
52.2
2 | Semolina/PO/24-25/000846 BOH Area PCC raise 300mm | Sqm | 1 | 2630 | 2100 |  | 5.523 | Bar
|  |  | 1 | 1940 | 1070 |  | 2.0758 | Bond room
|  |  | 1 | 6780 | 1960 |  | 13.2888 | Kitchen
|  |  | 1 | 7900 | 2110 |  | 16.669 | Kitchen
|  |  | 1 | 1050 | 500 |  | 0.525
|  |  | 1 | 1330 | 1570 |  | 2.0881
|  |  | 1 | 1660 | 1180 |  | 1.9588
|  |  | 1 | 1720 | 1190 |  | 2.0468
|  |  | 1 |  |  |  | 2 | exposed toilet entry (As Per Drawing shape)
|  |  | 1 | 1700 | 1200 |  | 2.04 | Infront of Bond Room
48.2153
3 | Semolina/PO/24-25/000848 FOH Area PCC raise avg 60mm | Sqm | 1 | 9080 | 5210 |  | 47.3068 | Teracotta jali to Buffet counter 2
|  |  | 1 | 5900 | 3450 |  | 20.355 | Buffet counter 2 to live kitchen wall
|  |  | 1 | 4130 | 1540 |  | 6.3602 | Gap b/w FOH and Carpet flooring
|  |  | 1 | 4610 | 3130 |  | 14.4293 | Reception area
|  |  | 1 | 1100 | 1000 |  | 1.1 | Drumseater
|  |  | 1 | 6010 | 3770 |  | 22.6577 | Carpet tile area
|  |  | 1 | 2240 | 1300 |  | 2.912 | Carpet tile area
|  |  | 1 | 1550 | 1550 |  | 2.4025 | Carpet tile area
|  |  | 1 | 1700 | 1200 |  | 2.04 | Carpet tile area
119.5635
Date:
Client Sign: