## SUMMARY
BOQ Of Barrication Work Domestic Lounge Phase II Banglore
Shah Enterprises Work Order No : : BLR/PO/23-24/000030
FINAL BILL
Sr. No. | Item Description | BOQ | FINAL BILL
1 | Boq & Ex Items | 3974940 | 3241442.2398
TOTAL AMOUNT |  | 3974940 | 3241442.2398
LESS: CERTIFIED IN RA-1 |  |  | 1899640
VALUE OF WORK DONE IN FINAL BILL |  |  | 1341802.2398
| GST |  | 241524.4032
VALUE OF WORK DONE IN FINAL BILL WITH GST |  |  | 1583326.643
(Rupees Fifteen lakhs eighty three thousand three hundred twenty seven only)
| CERTIFIED BY |  | ACCEPTED BY
| RANJANDAS SHETTY |  | SHAH ENTERPRISES

## BOQ
BOQ Of Barrication Work Domestic Lounge Phase II Banglore
Shah Enterprises Work Order No : : BLR/PO/23-24/000030
Date : 29/05/2024
[6 empty] | RA-1 |  |  | FINAL
Sr.No | DESCRIPTION | Quantity | Unit | Rate | Amount | Qty | % | Amount | Qty | % | RA Amount
1 | P F of Temporary Barricade work. with 50mm x 50mm x 19 gauge MS tube framing out of vertical members at 1150mm c c with horizontal members at 1200 mm c c, after fixing the framework on floorings supporting by ms stand as per drawing, 19mm thick fire rated plywood to be fixed on the both side of the framing including 50mm thick rockwool solution without foil. Rate including ms welding works with necessary protection all necessary hardware fittings to install the framing including approved anchor fastner, including all necessary supports etc including 3.2meter height vinyl flex as per approved art work to be fix in stappler pins. | 450 | Sqm | 6536 | 2941200 | 285 | 70% | 1303932 | 282.56 | 100% | 1846812.16
2 | P F of Temporary Plywood Barricade work. with 50mm x 50mm x 19 gauge MS tube framing out of vertical members at 1150mm c c with horizontal members at 1200 mm c c, after fixing the framework on floorings supporting by ms stand as per drawing, 19mm thick fire rated plywood to be fixed on the one side of the framing. Rate including ms welding works with necessary protection all necessary hardware fittings to install the framing including approved anchor fastner, including all necessary supports etc including 3.2meter height vinyl flelx as per approved art work to be fixed with stappler pins. | 30 | Sqm | 5649 | 169470
3 | P F nylon net barricade above existing plywood barricade of 25mmx25mmx19gauge MS hollow pipe with one coat primer 2coat of enamel paint the rate including cutting,welding and fixing with necessary scaffolding all complete as per sketch dated 13 1 20and instruction from Project manager. this is applicable above existing partion. approximate panel size is 9 9 x9 9 | 270 | Sqm | 3201 | 864270 | 270 | 40% | 345708 | 240.575 | 100% | 770080.575
4 | Ex iems | [6 empty] | 250000 |  |  | 624549.5048
Total Amount |  |  |  |  | 3974940 |  |  | 1899640 |  |  | 3241442.2398

## NT ITEMS
BLR LOUNGE T1 BARRICATION WORK
Item No | Item Description | UOM | Rate | Quantity | Amount | Remarks
1 | Lounge entrance closing with 9mm ply and wooden framing 2x2ft on bk | Sft | 300 | 93 | 27900 | Back side corridor entry door & partition
2 | Staircase door closing with 9mm ply | Sft | 300 | 43 | 12900 | Fire exit stair
3 | 200mm thick kitchen wall dismantling for dirty trolley passage | Sft | 80 | 188 | 15040
4 | Armstrong ceiling demolition | Sft | 25 | 162 | 4050
5 | Dirty trolley corridor for ph-2 with ply and laminate partition | Sft | 425 | 200 | 85000
6 | Ceiling for item 5 | Sft | 425 | 95 | 40375
7 | Service entry corridor wall with laminate | Sft | 425 | 70 | 29750 | Ply & laminate fix on existing unfinished wall
8 | Light weight floor dismantling for Dirty trolly passage | Sft | 250 | 39 | 9750
9 | PCC flooring 75mm thick for dirty trolley corridor | Sft | 375 | 86 | 32250
10 | Dish wash corridor opening closing with 9mm ply | Sft | 300 | 31 | 9300
11 | High Table demolation(Granite structure base plywood with aluminium framing) | Sqft | 150 | 121.1911 | 18178.6704 | This table was runway side and obstructing to fix the barricade
12 | Demolation of fluted Wooden Partitions 150mm thk | Sqft | 200 | 45.9877 | 9197.5416 | Both side it was obstructing to fix the barricade
13 | Providing & Fixing 19mm Ply framing and Partitions one side fixing with Glasswool filling @ C Barricade | Sqft | 400 | 95.0485 | 38019.3906 | Ultavita side opening
14 | Providing & Fixing 19mm Ply framing and partitions both side with 600X600 ply framing. Providing door of 1000X2100 with all necessary Hardwares @LVL 1 | Sqft | 600 | 79.2071 | 47524.2382 | First floor
15 | Providing & Fixing 19mm Ply Partitions one side on 600X600 ply framing @LVL-2 Lift Lobby closing | Sqft | 350 | 79.2071 | 27722.4723 | 2nd floor
16 | Providing & Fixing 6mm Ply Partitions with Ply framing @AHU Duct area and applying enamel paint twice. | Sqft | 325 | 222.0395 | 72162.8289 | Above deck slab towards runway side
17 | Providing Printed Flex of (5000 X 3200 ), 20 Pcs | Sqft | 42 | 3462.6039 | 145429.3629 | New flex . Due to design change
| TOTAL |  |  |  | 624549.5048

## Measurement Sheet
ITEM NO | DESCRIPTION OF NT ITEMS | UNIT | NO | LENGTH | BREADTH | HEIGHT | QUANTITY | REMARKS
1 | Ply Barricade
| Runway side -A |  |  | 42.6 |  | 3.2 | 136.32
| Ph-1 lounge side |  |  | 45.7 |  | 3.2 | 146.24
| Total | [5 empty] | 282.56 | sqm
3 | Net Barricade
| B SIDE |  |  | 27 |  | 3 | 81
|  |  |  | 18.7 |  | 2.45 | 45.815
| A SIDE |  |  | 21 |  | 3 | 63
|  |  |  | 21.6 |  | 2.35 | 50.76
[7 empty] | 240.575 | Sqm
Ex items
11 | High Table demolation(Granite structure base plywood with aluminium framing) | Sqft | 1 | 10000 |  | 1120 | 121.1911
12 | Demolation of fluted Wooden Partitions 150mm thk | Sqft | 1 | 1700 |  | 2500 | 45.9877
13 | Providing & Fixing 19mm Ply Partitions one side fixing with Glasswool filling @ C Barricade | Sqft | 1 | 3600 |  | 2440 | 95.0485
14 | Providing & Fixing 19mm Ply partitions both side with 600X600 ply framing. Providing door of 1000X2100 with all necessary Hardwares @LVL 1 | Sqft | 1 | 2440 |  | 3000 | 79.2071
15 | Providing & Fixing 19mm Ply Partitions one side on 600X600 ply framing @LVL-2 Lift Lobby closing | Sqft | 1 | 3000 |  | 2440 | 79.2071
16 | Providing & Fixing 6mm Ply Partitions with Ply framing finish enamel white matt@AHU Duct area | Sqft | 1 | 21600 |  | 950 | 222.0395
17 | Providing Printed Flex of (5000 X 3200 ), 20 Pcs | Sqft | 20 | 5000 |  | 3200 | 3462.6039
Note on G10: Suman Biswas: taken avg height
Note on G12: Suman Biswas: taken average hieght