## Summery
AJ KITCHEN - Bill Summary
S.N | Item | PO Value | RA-01 Value | RA-02 Value | Cumulative | Varition ( In Amt ) | % Billing | Po No.
1 | Planter | 54550 | 0 | 51884 | 51884 | 2666 | 95.1127 | Semolina/PO/24-25/000108
| SUB TOTAL | 54550 | 0 | 51884 | 51884 | 2666
| GST -18% | 9819 | 0 | 9339.12 | 9339.12 | 479.88
| TOTAL | 64369 | 0 | 61223.12 | 61223.12 | 3145.88

## BOQ Planter
AJ1881 CAFÉ LUCKNOW AIRPORT | [6 empty] | PO |  |  | RA-01 | RA-02 | Cumm | RA-01 | RA-02 | Cumm
SR.NO. | DESCRIPTION | LOCATION | SIZE | CODE | BRAND | IMAGE | QTY | RATE | AMOUNT | QTY | QTY | QTY | AMOUNT | AMOUNT | AMOUNT
| PLANTERS | [7 empty] | 54550 |  |  |  | 0 | 51884 | 51884 | 61223.12
9.1 | Tree (Custom made)- Sample | To be customized |  |  | Buy Artificial Areca Palm Tree From Importer 3.7 Feet - Mumbai (fourwalls.in) |  | 2 | 17161 | 34322 | 0 | 2 | 2 | 0 | 34322 | 34322
9.2 | Plants (Custom made)- Sample | To be customized |  |  | AS PER ATTACHED IMAGE |  | 15 | 560 | 8400 | 0 | 15 | 15 | 0 | 8400 | 8400
9.3 | Supply & installation of round shape planter box with plants with the paint/powder coated finishes as per drawings and renders. Size of planter box: dia. 300mm Note: Samples shall be submitted by contractor. |  |  |  | AS PER ATTACHED IMAGE |  | 2 | 2061 | 4122 | 0 | 2 | 2 | 0 | 4122 | 4122
9.4 | Supply and Installation of PLANTER BOX ABOVE THE COUNTER FINISHED WITH NATURALY LOOKING ARTIFICIAL GRASS AND TREE as per the drawings and renders. To be coordinate with FOH counter drawings. Note: Samples shall be submitted by contractor. | Need to customize 5' height and more leafs |  |  | https://www.thegreenhouseindia.co.in/medium-artificial-tree.html |  | 1 | 2666 | 2666 | 0 | 0 | 0 | 0 | 0 | 0
9.5 | Supply & installation of round shape planter box with plants with the paint/powder coated finishes as per drawings and renders. Size of planter box: dia. 300mm ht to be 600 MM Note: Samples shall be submitted by contractor. |  |  |  | AS PER ATTACHED IMAGE |  | 1 | 5040 | 5040 | 0 | 1 | 1 | 0 | 5040 | 5040

## JMR
AJ1881 CAFÉ LUCKNOW AIRPORT | [6 empty] | PO | JMR
SR.NO. | DESCRIPTION | LOCATION | SIZE | CODE | BRAND | IMAGE | QTY | RA-02
| PLANTERS | [6 empty] | Qty
9.1 | Tree (Custom made)- Sample | To be customized |  |  | Buy Artificial Areca Palm Tree From Importer 3.7 Feet - Mumbai (fourwalls.in) |  | 2 | 2
9.2 | Plants (Custom made)- Sample | To be customized |  |  | AS PER ATTACHED IMAGE |  | 15 | 15
9.3 | Supply & installation of round shape planter box with plants with the paint/powder coated finishes as per drawings and renders. Size of planter box: dia. 300mm Note: Samples shall be submitted by contractor. |  |  |  | AS PER ATTACHED IMAGE |  | 2 | 2
9.4 | Supply and Installation of PLANTER BOX ABOVE THE COUNTER FINISHED WITH NATURALY LOOKING ARTIFICIAL GRASS AND TREE as per the drawings and renders. To be coordinate with FOH counter drawings. Note: Samples shall be submitted by contractor. | Need to customize 5' height and more leafs |  |  | https://www.thegreenhouseindia.co.in/medium-artificial-tree.html |  | 1 | 0
9.5 | Supply & installation of round shape planter box with plants with the paint/powder coated finishes as per drawings and renders. Size of planter box: dia. 300mm ht to be 600 MM Note: Samples shall be submitted by contractor. |  |  |  | AS PER ATTACHED IMAGE |  | 1 | 1