## SUMMARY
summary
Description Amount
| BCL LOUNGE HVAC WORKS | 1245420
| Without gst Total | 1245420
| GST 18% | 224175.6
| TOTAL AMOUNT WITH GST | 1469595.6

## BCL LOUNGE HVAC WORKS
ItemCode : ItemName : Civil BOQ for Chennai T2 BCL Lounge HVAC works. | [7 empty] | RA - 01
Sr No | Item Code | Item Name | UOM | Remarks | Quantity | Supplier Rate | Amount | As for site | As for boq % | Amount
1 | HVAC Grill cutout | P F of aluminium louvered grill size of 600x 500mm with wooden finished. Including fixing and wall cutout all repair work. | NOS |  | 6 | 4100 | 24600 | 6 | 0.9 | 22140
2 | Arch shape existing gypsum ceiling repair work and cutout | Providing, making and reparing of exisitng POP false ceiling as per HVAC drawing and drawing including cut-outs for hvac grille, lights etc.at any all heights. cost includes scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design manufactures specification all complete. Rates do not include painting work.Arch ceiling in 3 levels | SQFT |  | 0 | 3800 | 0 | 36 | 0.85 | 116280
3 | Textured paint touchup on existing bulkhead | Providing applying three (03) coats of approved texture or stucco look alike on walls including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. cost includes scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design manufactures specification all complete. | SFT |  | 1000 | 310 | 310000 |  | 0 | 0
4 | Corridor HVAC Duct box paneiling | P F of plywood boxing made up of 18mm thk Marian plywood with aluminium framework at every 600mm c c. The boxing to be finished with laminate from all visible sizes the unit to have 75mm height skirting. The center of the unit to have 750mm x 100mm deep niche for indirect lighting. The cost to including loading unloading, adhesive, hardware, scaffolding complete in all respect as per detail drawing. | NOS |  | 8 | 95000 | 760000 | 8 | 0.75 | 570000
5 | Ceiling Paint on L shape bulkhead | Providing applying three (03) coats of approved Plastic paint on exposed surface on ceiling including scraping, primer , filling with putty etc. complete with final coat no brush mark to be visible after painting colour shade as specified. cost includes scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design manufactures specification all complete. | SFT |  | 1400 | 70 | 98000 | 1000 | 0.75 | 52500
6 | Railing box Paneling | P fixing of cabinet made up of 18mm thk Marian plywood with inside insulation to cater the hvac ducting. The top of the cabinet to have marble finish. And rest of the area to be finished with veneer and approved polish. The unit to have 75mm height marble skirting. As per detail drawing including loading and unloading of material, all hardware fixiture, adhesive complete in all respect. | rft |  | 110 | 4100 | 451000 | 110 | 0.75 | 338250
7 | Gypsum L shaped Bulkhead | Providing, making and fixing of POP Bulkhead in L shape as per app. design and drawing including cut-outs for hvac duct, lights etc.at any all heights. Rate quoted should be including of vertical drop of heights of 1000mm,and size mentioned in drawings with necessary required framing in 450x 900 ultra Gyproc sections, fittings, and fixtures, scaffolding, floor covering, masking tape and cleaning the area all complete as per drawing, design manufactures specification all complete. Rates do not include painting work. | SFT |  | 1400 | 225 | 315000 | 1000 | 0.65 | 146250
Total : |  |  |  |  | 3924 |  | 1958600 |  |  | 1245420