## Civil & Interior
Rudras Interior Point Pvt Ltd
CIVIL & INTERIORS WORK - KFC
Sr No | Item Code | Item Name | BOQ |  |  |  |  | INVOICE
|  |  | UOM | Remarks | Quantity | Rate | Amount | Work Done % | Amount
1 | 1 | ANTI TERMITE TREATMENT
2 | 1 | PEST CONTROL - Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards.- | Sft | TOTAL AREA | 1070 | 15 | 16050 |  | 0
3 | 2 | CIVIL WORKS |  |  |  |  | 0 |  | 0
4 | 2.1 | 100MM THK SIPOREX WALL - P C light wt. Block masonry of 100mm thk with CM 1 4 in proper line, level plumb (Siporex or Aerocon block of size 600 x 200 x 100 mm) At every 1 tm ht. interval stiffener should be provided . Rate to include the cost of stiffener lintel. | Sft | ALL INTERNAL WALLS,FRONT SIDE PERIPHERALL WALL & BUND WALLS | 2020 | 140 | 282800 | 80% | 226240
5 | 2.2 | INTERNAL PLASTER - P A 12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all types of RCC. work, brick work surfaces at all levels in line, level and plumb including smooth cement finish or roughning of surface to hold tiles and providing necessary grooves at junctions of walls and ceiling, door window frames incl. racking the joints of roughing the RCC. surface, necessary curing scaffolding etc . complete as directed. Note Allow for providing and fixing galvanized chicken mesh 300mm wide (24 gauge, 12mm size) at junction of brick masonry and concrete members to be plastered or clapped or other locations as called for, properly stretched and nailed ensuring equal thickness of plaster on both sides of mesh. Provision for chemical bonding with a layer of Plaster Master from Roff for RCC surfaces and use of REUROn fibres to avoid superficial cracks.No extra payment shall be made for p f chicken mesh, Plaster Master and REUROn. | Sft | ALL INTERNAL WALLS & FRONT SIDE PERIPHERALL WALL | 3200 | 55 | 176000 | 80% | 140800
6 | 3 | BRICK BAT COBA WATERPROOFING WORKS |  |  |  |  | 0 |  | 0
7 | 3.1 | SIPOREX BAT COBA- upto 100MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 100 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sft | BELOW MANAGER TABLE, LT PANEL & CHEMICAL MAINTAINANCE STORAGE | 25 | 150 | 3750 | 80% | 3000
8 | 3.2 | SIPOREX BAT COBA- upto 150MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 150 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sft | BELOW MAIN COUNTER | 20 | 280 | 5600 | 80% | 4480
9 | 3.3 | SIPOREX BAT COBA- upto 375MM P L light wt. Solid Block (siporex or Aerocon) bat coba to conceal drainage plumbing lines for Grease trap of average thk of 375 mm with CM 1 4 top layer should be finished properly to receive flooring layer on it [ DISH WASH AREA] | Sft | 13 RAISED EXCULDING PCC (BOH AREA) | 950 | 375 | 356250 | 100% | 356250
10 | 3.4 | WATER PROOFING- MEMBRANE Providing and laying water- proofing treatment to hand wash, BOH area consisting of 4 mm Thk Apex Apcon Sheild Dr Fixit Torchsheild or equivalent polyster reinforced APP modified bitumen membrane sheet (Basic Rate Rs.2000 Roll of 10mX1m) as approved, cleaning and smoothing of entire surface, smooth plaster upto 600mm from raw floor lvl, 12mmx12mm groove at 150mm from floor rising lvl, one coat of Bitcote Dr Fixit Apex equivalent (as approved)-heavy body bitumen primer (Basic Rate Rs.82 Kg) coating as a primer on surface and till 450mm from floor rising lvl, application of membrane sheet as per application detail and packing the hole cuts for pipe line and checking the area which is water proofed. Rate includes of laying the protective layer of Plaster. Measurement to be done of floor area, wall area not to be paid, if ht. is < 600 mm, difference of 600mm will be paid. | Sft | BOH AREA (WITH WALL UPTO 3 -4 ) | 2000 | 170 | 340000 | 80% | 272000
11 | 4 | PCC WORKS |  |  |  |  | 0 |  | 0
12 | 4.1 | 50mm PCC Providing Laying PCC 1 3 6 of average thk 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6graded stone aggregate 10 mm nominal size) BOH AREA | Sft | TOTAL AREA | 1070 | 85 | 90950 | 80% | 72760
13 | 4.2 | IPS Providing Laying IPS of desired thickness | Sft | COLDROOM AREA | 130 | 30 | 3900 | 80% | 3120
14 | 5 | GRANITE WORKS |  |  |  |  | 0 |  | 0
15 | 5.1 | GRANITE PARTITION DOUBLE THICKNESS - P F 36mm thk Granite Partition by sandwiching two 18mm thk granite (3 -6 height) with Araldite adhesive including cutting , fixing, grinding, half round moulding at the edge polishing complete. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | Sft | VERTICAL SUPPORT OF MANAGER TABLE | 8 | 550 | 4400 | 80% | 3520
16 | 5.2 | GRANITE THRESHOLD IN FLOORING AND JAMB LINING P F upto 9 wide 18mm Granite threshold on flooring laid over a properly prepared bed of cement mortar in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | Rft | OUTSIDE AREA TO BOH ENTRY & BELOW SERVICE ENTRY | 35 | 300 | 10500 | 80% | 8400
17 | 5.3 | GRANITE SKIRTING P F upto 4 high 18mm Granite skirting flush with the finish surface of the wall laid over a properly prepared bed of cement in line and level. All joints to be hairline, to be cleaned and filled with approved color Laticrete, to the required line level at all heights and leads, as per detailed designs and drawings, including all labour, edge polish, champhering, moulding, material, curing, cleaning. Base Rate of granite is Rs. 150 - sq.ft. Product- Jet black granite | Rft | 21 -4 SKIRITNG FOR FAÇADE | 22 | 280 | 6160 | 80% | 4928
18 | 6 | FLOORING WORKS |  |  |  |  | 0 |  | 0
19 | 6.1 | KOTA STONE FLOORING - P L Kota stone flooring of size 22 x 22 (25 mm thk) with 40 mm avg thk of cement sand bedding of CM 1 6 neat cement slurry paste with polish KOTA PRE-POLISH KOTA | Sft | BOH AREA & DISH WASH AREA WALL UPTO 5 | 1050 | 180 | 189000 | 80% | 151200
20 | 7 | DADO WORKS |  |  |  |  | 0 |  | 0
21 | 7.1 | DADO TILES (8 -0” HT) FOR KFC P L BLACK BEVELED TILES, JOHNSON MAKE (200mmX100mm) Dado TILE with neat cement paste with avg thk of 6mm in proper line, level plumb. Make color will be approved by architect. Base Rate of tile is Rs. 80 - sq.ft. | Sft | MOH WALL TILES UPTO CEILING LVL (GREY TILE - GLOSSY-4 X 8 SIZE. (MAKE-JOHNSON TILES) WITH BLACK GROUTING) | 280 | 250 | 70000 | 80% | 56000
22 | 7.2 | DADO TILES (8 -0 HT) P LGLAZE CERAMIC WALL TILE of size 600 x 300 mm on 40 mm thk of cement sand bedding with CM 1 4 (fixing to be done with cement slurry paste) for toilet area. Base Rate of tile is Rs. 60 - sq.ft. NO ACCEPTANCE FOR ANY RATE VARIATION ON BASIC RATE. | Sft | BOH AREA WALL TILES UPTO CEILING LVL | 1320 | 155 | 204600 | 80% | 163680
23 |  | GREY TILE - GLOSSY-4 X 8 SIZE. (MAKE-JOHNSON TILES)- maximum one box WILL BE PAID ADDITIONAL BASIS ON SUPPORTING | Box |  | 2 | 1200 | 2400 | 80% | 1920
24 | 8 | SKIRTING WORKS |  |  |  |  | 0 |  | 0
25 | 8.1 | KOTA SKIRTING P F upto 100 mm high kota tile STONE skirting | Rft | BOH AREA | 250 | 115 | 28750 | 80% | 23000
26 | 9 | PARTITIONS AND PANELINGS |  |  |  |  | 0 |  | 0
27 | 9.1 | 12MM PLYWOOD PANELING BOXING - P F 12mm plywood as paneling as per following specs incl of all hardware, labour; in perfect line and plumb, incl of grooves as desired or specified in drawing, complete in all respects. Frame sections of upto 2 x 1.5 size can be of seasoned termite- treated Sal wood, or aluminium sections of same size. |  |  |  |  | 0 |  | 0
28 |  | P F 12mm plywood plain paneling without frame or laminate | Sft | FOR COUNTER BULKHEAD (FIRE RATED PLY) | 65 | 240 | 15600 |  | 0
29 |  | P F 12mm plywood plain paneling with frame, with laminate | Sft | FOR FRONT FAÇADE LHS WALL PANELLING (FIRE RATED PLY) | 80 | 340 | 27200 | 80% | 21760
30 | 9.2 | ACP (ALUMINIUM COMPOSITE SHEET) CLADDING 3mm thick Aluminium Composite sheet cladding of approved make as per details and drawing for signage, incl all scafollding wastage, joint filling with silicon, etc. complete. Trapdoor for rolling shutters will also be measured under same heading- no extra cost to be paid for hinges, locks, etc.Rate to include scaffolding till 1st floor |  |  |  |  | 0 |  | 0
31 |  | P F 3mm thick Aluminium Composite sheet cladding on framework of upto 50 x 25 aluminium sections | Sft | FOR FRONT FAÇADE 6 HT BAND & BOTTOM OF COUNTER BULKHEAD | 50 | 380 | 19000 | 80% | 15200
32 | 9.3 | FULL LOW HEIGHT PARTITION P F Partition made on aluminium sal wood frame of 2 x 1.5 sections fixed at 600 x 600, properly clamped to walls, ceiling and floor. Rate is inclusive all necessary hardware, labour, etc. |  |  |  |  | 0 |  | 0
33 |  | P F 12mm plywood on both sides of frame mentioned above with laminate | Sft | ABOVE FIRE EXIT DOOR, UHC PARTITION & COUNTER LHS PARTITION (FIRE RATED PLY) | 40 | 550 | 22000 | 80% | 17600
34 |  | P F 12mm gypsum boards on both sides of frame mentioned above | Sft | COUNTER BULKHEAD | 35 | 280 | 9800 | 80% | 7840
35 | 10 | COUNTERS AND STORAGES |  |  |  |  | 0 |  | 0
36 | 10.1 | OVERHEAD CABINETS STORAGE CABINETS P F Overhead Cabinet storage cabinet Takeaway counter made out of 19mm marine ply for sides, top, bottom, shelves and shutters. Back of cabinet to be made out of 6mm marine ply. All external surfaces to be finished with approved laminate of 1.0mm thickness. All internal surfaces to be finished in balancing laminate of 0.8mm thickness. All edges of ply to be finished with beading patti finished in paint polish. Costs to include for all hardware and fittings like handles, locks, powder coated M.S wire managers, sliding channels, lipping, nylon bushing for legs, making grooves etc complete as per drawing and details. Open area for data rack shelves (if open area is part of one single complete overhead storage structure will be measured in same heading) |  |  |  |  | 0 |  | 0
37 |  | Upto 18 depth (extra will not be paid if storage depth is 18 + shutters thickness) | Sft | MANAGER OVERHEAD STORAGE | 15 | 1650 | 24750 | 80% | 19800
38 | 10.2 | DISPENSING COUNTER (KFC) P F dispensing counter (ORDER PICKUP) made out of 19mm thk. Marine Ply finished with 1mm THK. laminate FOR ALL INTERNAL SURFACES with provision OF NICHE for KDS (as per detail dwg). complete with TELESCOPIC drawer channels, VERTICAL PARTITIONS SHELVES with neccessary hardware , raceways, SS BASKETS 304 GRADE wire manager,below the counter top to route the electrical wiring for POS machine. All CUTOUTS, hardwares and fixtures to be included in rate. Mode of measurement will be from BOH elevation height. 30 depth, 30 height. Rate to be inclusive of ledge finished in plywood. Rate is INclusive OF Solid Surface (12MM Corian FOR FRONT FACIA TOP) | Sft | POS COUNTER FINISHED WITH CORIAN & LAMINATE - FORMICA 8844-WR AGED ASH | 35 | 4000 | 140000 | 80% | 112000
39 | 11 | MISCELLANEOUS CARPENTRY |  |  |  |  | 0 |  | 0
40 | 11.1 | SOFT BOARD P F 12mm thk. Soft board fixed onto to existing surface finished approved colour fabric as per detailed drawing. Backing plywood if required to be billed in paneling heading above. | Sft | FOR MANAGER | 8 | 400 | 3200 | 80% | 2560
41 | 11.2 | WORK TOP MANAGER DESK P F work top manager desk Top and verticals to be made in 19mm granite fixed on marble surface with vertical supports as per design detail, inclusive of cutout for wire manager. | Rft | 5 -0 LENGTH | 5 | 2600 | 13000 | 80% | 10400
42 | 11.3 | DRAWER FOR MANAGER DESK P F plywood drawer for manager table of size upto 30 width x upto 6 height x upto 24 depth. Sides to be of 12mm plywood, bottom to be of 6mm plywood, front to be of 19mm plywood. To be mandatorily provided with drawer slides of approved make as per attached make list. | Nos |  | 2 | 1500 | 3000 | 80% | 2400
43 | 11.4 | CPU TROLLEY P F metal CPU trolley of earl bihari make | Nos |  | 1 | 2500 | 2500 | 80% | 2000
44 | 11.5 | PELMET Providing and Fixing of 6 high Pelmet Above Manager Table made out of 19mm thk. Ply, covered with approved laminate of 1.0mm thickness, as per detail Drawing | Rft | 5 -0 LENGTH | 5 | 160 | 800 | 80% | 640
45 | 11.6 | KEY HIVE BOX P F Key Box with provision for mounting 50 keys. Space should be available for labeling each hook. |  |  |  |  | 0 |  | 0
46 |  | P F ready made Key Box in PVC powder coated MS. | Nos |  | 1 | 2500 | 2500 | 80% | 2000
47 | 12 | DOORS DOOR FRAMES |  |  |  |  | 0 |  | 0
48 |  | FIRE RATED DOOR | Nos | SERVICE ENTRY DOOR WITH EYE PICK HOLE (3 -11 X 7 HT) DRYSTORE & MANAGER DOOR WITH VISION PANEL (3 -0 X 7 HT) SHAFT DOOR WITH VISION PANEL (1 -11 X 7 HT) | 4 | 35000 | 140000 | 80% | 112000
49 | 13 | SS WORKS |  |  |  |  | 0 |  | 0
50 | 13.1 | SS EDGE PROFILE P F of Stainless steel section edge profile protectors of size 19mm x 19mm x 1.5mm thick to protect all corners of the walls columns in kitchen | Rft | BOH AREA | 200 | 250 | 50000 | 80% | 40000
51 | 14 | MS WORKS (UNIT WEIGHT MUST BE AS PER IS CODE) |  |  |  |  | 0 |  | 0
52 | 14.1 | MS FRAME WORK FOR BACKING FOR OVENS ETC P F of in M.S solid hollow sections of size upto 50x50 Frame work and regular intervals on walls as per detail drawings with necessary base plate and supports from walls complete as per design detail finished with approved paint. RFT of the pipe to be measured for billing. | Rft |  | 11 | 250 | 2750 | 80% | 2200
53 | 14.2 | MS STRUCTURES FOR RO, DG, WATER TANKS, ETC P F of in M.S Frame work in sections of various sizes as required and MS chequered plate with MS supports beams sections at regular intervals as per detail drawings with necessary base plate and supports from walls and slab complete as per design detail finished with approved paint. For base structure in MS for RO, DG, water tanks, etc. Detailed breakup of the weight of each section to be provided | kg | FOR EXHAUST UNIT | 3000 | 170 | 510000 | 10% | 51000
54 | 15 | POP FALSE CEILING WORK |  |  |  |  | 0 |  | 0
55 | 15.1 | GYPSUM CEILING P F seamless Gypsum ceiling with gyp board of 12.5mm fixed to the under side of the suspended grid formed of GI perimeter channel of size 20x27x30mm fixed along the wall by using wood screws metal expansion raw plugs. The GI intermediate channel of size 45x15x0.90mm shall be fixed to the suspended strap hanger GI ceiling angle at intervals not more than 1220mm.The suspended GI ceiling angle strap hanger is to be connected with G.I soffit cleat of size 37x27x25 1.6mm it should be fixed on the roof slab beam by using metal expansion fasteners of 12.5mm dia. to the length of 35mm with screw at top ends, including all drops, coves etc and taping finishing. | Sft | MOH AREA, MANAGER ROOM & DRYSTORE | 250 | 145 | 36250 | 80% | 29000
56 | 15.2 | CUTOUTS FOR LIGHTS Making cutouts for lights. Only to be paid for renovation sites as per project managers approval. | Nos |  | 17 | 50 | 850 | 80% | 680
57 | 15.3 | LAY IN METAL GRID CEILING P F Modular Grid (RH-95 plain tegular edge-Armstrong) G.I. PLANE 1 2 thk , 2 x 2 panels with silhoutte grid as per approved sample in dining area as per manufacturer s specification. inclusive of original Armstrong Frame work. | Sft | BOH AREA | 450 | 185 | 83250 | 80% | 66600
58 | 15.4 | PVC FLOORING PROTECTOR P F PVC flooring protector on floor of 4mm thk to protect floor tiles to damage during the period of execution | Sft | TOTAL AREA | 1070 | 15 | 16050 | 80% | 12840
59 | 16 | PAINTING POLISHING WORKS |  |  |  |  | 0 |  | 0
60 | 19.01 | PLASTIC PAINT - P A 3 coats of plastic paint of approved quality shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of plastic paint, touching up with putty applying two final roller coats of plastic paint, to internal wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing | Sft |  |  |  | 0 |  | 0
61 | 19.02 | LUSTER PAINT P A 3 coats of Luster paint of approved quality shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of luster paint, touching up with putty applying two final roller coats of luster paint, to internal wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing. | Sft | INTERNAL OPEN CEILING SLAB, BOH WALL ABOVE TILE FINISHED LVL, FRONT WALL FROM OUTSIDE | 3000 |  | 0 | 50% | 0
62 | 19.03 | ENAMEL PAINT P A 3 coats of Enamel Paint of approved quality shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of enamel paint, touching up with putty applying two final roller coats of enamel paint, to internal wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing | Sft |  |  |  | 0 |  | 0
63 | 19.04 | APEX PAINT P A 3 coats of Apex Paint of approved quality shade by scrubbing clean the surface, applying one coat of primer, repeating a coat of primer, applying one coat of apex paint, touching up cracks and undulations applying two final coats of apex paint, to external wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing | Sft |  |  |  | 0 |  | 0
64 | 19.05 | DUCO PAINT P A Duco paint (non metallic) approved shade on base coating of water cutting putty sand papered smooth leveled surface with spray | Sft |  |  |  | 0 |  | 0
65 | 19.06 | MELAMINE POLISH P A Melamine polish on wooden surface brushing the surface free from foreign matter, sand papering smooth, filling in all holes and applying polish and sealer before applying three coats of melamine spray. | Sft | MANAGER ROOM, DRYSTORE & CORDON OFF ENTRY DOOR | 60 |  | 0 | 50% | 0
66 | 19.08 | SEALER COAT ON BRICKS P A Sealer coat- Impregnation sealer Imperguard SF of Killick make- on exposed bricks after brushing the surface free from foreign matter. | Sft |  |  |  | 0 |  | 0
67 | 19.09 | SEALER COAT ON PINE WOOD P A Sealer coat- Impregnation sealer Wood Guard Professional of Killick make - on sleeper wood after brushing the surface free from foreign matter. | Sft |  |  |  | 0 |  | 0
68 | 16.1 | LUSTER PAINT P A 3 coats of Luster paint of approved quality shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of luster paint, touching up with putty applying two final roller coats of luster paint, to internal wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing. | Sft | INTERNAL OPEN CEILING SLAB | 300 | 40 | 12000 | 50% | 6000
69 | 16.2 | DUCO PAINT P A 3 coats of Luster paint of approved quality shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of luster paint, touching up with putty applying two final roller coats of luster paint, to internal wall ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. Paint codes to be as shown in drawing. | Sft | INTERNAL OPEN CEILING SLAB | 300 |  | 0 |  | 0
70 | 17 | DUCO PAINT P A Duco paint (non metallic) approved shade on base coating of water cutting putty sand papered smooth leveled surface with spray | Sft | FRONT FAÇADE | 100 | 225 | 22500 | 50% | 11250
71 | 17.1 | Hood Erection (to be paid in KFC ONLY NON-VEG HOOD), VEG HOOD NOT TO BE PAID, AS IT IS FLOOR MOUNTED | Nos |  | 1 | 6500 | 6500 |  | 0
72 | 17.2 | Hood Erection (to be paid in PH -OVEN HOOD) | Nos |  |  |  | 0 |  | 0
73 | 17.3 | HOUSEKEEPING Keeping site clean during works, deep cleaning before handing over the project. | Job | contractor s responsibility to hand over site in spic and span condition | 1 | 7500 | 7500 | 75% | 5625
74 | 17.4 | FIXING OF WHITE GOODS Fixing of white goods for BOH AND FOH AREA like Pestoflash, TVs, DMB, KDS, LCMS, Aircurtains, shelves, hooks, maps, internal signages, PVC buffers, Fire extinguishers, Carpentry works like wire manager holes, hand towel dispenser etc. | Job |  | 1 | 10000 | 10000 | 70% | 7000
75 | 17.5 | ALUMINIUM LADDER P A Aluminium ladder 8 | Nos |  | 1 | 5000 | 5000 | 50% | 2500
76 | 17.6 | TEMPORARY FLEX P F of Temporary flex work printed with art work as specified during project to segregate renovation area as per site requirement. Cost to include temporary door with hinges and locking provision with lock. |  |  |  |  | 0 |  | 0
77 |  | P F temporary flex as per details above with backing frame of wood MS Aluminium sections as required. | Sft | ON FRONT FAÇADE | 260 | 90 | 23400 |  | 0
78 | 17.7 | SCAFFOLDING P E of scaffolding in bamboo MS as per site condition. To be paid only in extreme cases with prior approval from Project manager. Cost to be paid based on 15 days intervel WITH SUPPORTING | Sft |  | 2000 | 40 | 80000 | 50% | 40000
79 | 17.8 | FIRST AID BOX Providing readymade first aid box on completion of the site | Nos |  | 1 | 2500 | 2500 | 50% | 1250
80 | 17.9 | GODREJ NIGHT LATCH P F Additional lock on service door Night Latch of Godrej Make- double turn. To be fixed over and above the existing dead tubular lock as mentioned in the door details. | Nos |  | 1 | 1000 | 1000 | 50% | 500
81 | 17.1 | DOOR AIR TRANSFER GRILL P F Door air transfer grill for washroom and changing room door- on both sides of door- one set to be considered for billing | Set | 1 NOS FOR DRY STORE | 1 | 1500 | 1500 | 70% | 1050
82 | 17.11 | FIRE BLANKET | Nos |  | 1 | 1200 | 1200 | 50% | 600
83 | 17.12 | MAINTENANCE REQUIREMENT WORKS - AMOUNT PAID TO STORE MAINTENANCE Actual bill need to be produced TO BE PAID ON CONFIRMATION OF PM | Nos |  | 1 |  | 0 |  | 0
84 | 17.13 | 1. RO plant till location | Nos | LOADING & UNLOADING - Manual shifting till location as per design (Second floor) | 1 | 45000 | 45000 | 75% | 33750
85 |  | 2. Fresh air Exhaust units AC units AHU units till location |  |  |  |  | 0 |  | 0
86 |  | 3. Electrical panel till location |  |  |  |  | 0 |  | 0
87 |  | 4. UPS with battery till location |  |  |  |  | 0 |  | 0
88 |  | 5. Coldroom Dry store racks till location |  |  |  |  | 0 |  | 0
89 |  | 6. Stabilizer till location |  |  |  |  | 0 |  | 0
90 |  | 7. SS Dead Equipment till location (Handwash sink, 3bowl sink, hoods, tables, shelves, etc) pepsi machine |  |  |  |  | 0 |  | 0
91 |  | 8. IT material till location |  |  |  |  | 0 |  | 0
92 |  | 9. Misc - weighing Scale CCTV Pesto Flash Fire-Extinguisher Music System Gas-Detection System Fire-Suppression System Air-Curtains |  |  |  |  | 0 |  | 0
93 |  | 10. All furnitures till location |  |  |  |  | 0 |  | 0
94 | 17.14 | DEBRIS REMOVAL FROM STORE PREMISES (UP TO 4 VEHICLES) Except Civil vendor debris (Cold room, HVAC, Kitchen Equipment, Signages, Etc) | L S |  | 1 | 20000 | 20000 | 75% | 15000
95 | 17.15 | MATHADI LABOUR UNION Actuall bill to be produced, ONLY TO BE PAID ON CONFIRMATION OF PM (no margin to be paid additional) | L S |  | 1 |  | 0 |  | 0
96 | 17.16 | Installation of amplifier Installation of amplifier 120W for music system suitable to operate on 230 V AC 12V DC, with low impedance microphone input two auxiliary inputs, tone control, protection circuit complete for the speakers output 4 8 16 lines | L S |  | 1 |  | 0 |  | 0
|  | Total Amount |  |  |  |  | 3151710 |  | 2144343