## Plumbing
Rudras Interior Point Pvt Ltd
PLUMBING WORK - KFC
Sr No | Item Code | Item Name | BOQ |  |  |  |  | INVOICE
|  |  | UOM | Remarks | Quantity | Rate | Amount | Work Done % | Amount
1 | 1 | Supply, laying, testing commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia, jointing with CPVC solvent cement of medium body IPS brand or equivalent conform. |  | CPVC Pipes (RO WATER & RAW WATER)
2 | a | 15mm dia | Rmt |  |  |  | 0 |  | 0
3 | b | 20mm dia | Rmt |  | 65 | 320 | 20800 | 80% | 16640
4 | c | 25mm dia | Rmt |  | 18 | 455 | 8190 | 80% | 6552
5 | d | 32mm dia | Rmt |  | 5 | 490 | 2450 |  | 0
6 | e | 40mm dia | Rmt |  |  |  | 0 |  | 0
7 | 2 | Supply, laying, testing commissioning of CPVC - Schedule 80 (ASTM F 441) Pipes and fittings suitable for Domestic hot water application (max. temp.85 Deg.C) rated for a working pressure of 5 kg cm2 and conforming to latest Indian International Standards. WITH Supply Covering (Thermal Insulation) hot water pipes with 6 mm thick performed closed cell nitrite rubber pipe section insulation having density not less than 60 kg cm2 and K valve not more than 0.034 w m Deg. K @ 20 Deg C mean temperature. |  | CPVC Pipes (HOT WATER) WITH Thermal Insulation
8 | a | 15mm dia | Rmt |  |  |  | 0 |  | 0
9 | b | 20mm dia | Rmt |  | 30 | 425 | 12750 | 80% | 10200
10 | c | 25mm dia | Rmt |  |  |  | 0 |  | 0
11 | d | 32mm dia | Rmt |  |  |  | 0 |  | 0
12 | e | 40mm dia | Rmt |  |  |  | 0 |  | 0
13 | 4 | Supply, Installation, Commissioning Testing for Booster Pump WITH FLOW SWITCH GRAVITATIONAL FLOW (top to bottom flow) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 25M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE |  | Booster Pump - Crompton & Greaves KIRLOSKER
14 |  | 1.0 HP | Nos. |  |  |  | 0 |  | 0
15 |  | 1.5 HP | Nos. |  |  |  | 0 |  | 0
16 | 4 | Supply, Installation, Commissioning Testing for HYDROPNEUMATIC Booster Pump WITH FLOW SWITCH with pressure vessel (AGINST GRAVITY bottom to top flow) with both side Sensor operations (60ltr vessel) with both side Sensor operations- A) 3CUM PER HR. B) HEAD 40M, C) PHASE SINGLE PHASE, D) PROTECTION IP55, E) MONOBLOCK TYPE F) WITH VALVE STATION |  | Booster Pump - Crompton & Greaves KIRLOSKER GRUD FOS
17 |  | 1.5HP | Nos. |  |  |  | 0 |  | 0
18 | B | WATER DRAIN PIPES
19 | 1 | Supply, Laying , Testing Commissioning of CI (Cast Iron) CLASS Pipes Conforming to IS 3114 1994 and Fittings Conforming to IS 1538 (1993), Cutting the Pipes to required Lengths, Laying in position to required Grade Level , Jointing , Making holes , Pockets , chases in. |  | CI Class Pipes (WASTE PIPE)
20 | a | 150mm dia | Rmt |  |  |  | 0 |  | 0
21 | b | 100mm dia | Rmt |  |  |  | 0 |  | 0
22 | c | 75mm dia | Rmt |  |  |  | 0 |  | 0
23 | 2 | PVC Plastic Pipe , Schedule 40,80,120 ( ASTM D1785 ) |  | PVC WASTE PIPE FOR WASH ROOM
24 | a | Drain for ac line | Rmt | 25mm |  |  | 0 |  | 0
25 | b | Company Make - Prince , Finolex | Rmt | 50mm |  |  | 0 |  | 0
25 | c | Company Make - Prince , Finolex | Rmt | 75mm |  |  | 0 |  | 0
25 | d | Company Make - Prince , Finolex | Rmt | 100mm |  |  | 0 |  | 0
26 | e | Company Make - Prince, Finolex (Basement Suspended Pipe) | Rmt | 150mm |  |  | 0 |  | 0
27 | f | Drainage Exacavation SITC of 150mm (Underground) PVC Waste Pipe Make Prince Finolex | Rmt | Drain |  |  | 0 |  | 0
28 | 3 | UPVC Plastic Pipe , Schedule 40,80,120 (ASTM D1785 ) |  | UPVC PIPE
29 | a | Company Make - Prince , Finolex | Rmt | 40mm |  |  | 0 |  | 0
29 | b | Company Make - Prince , Finolex | Rmt | 50mm | 23 | 650 | 14950 | 80% | 11960
29 | c | Company Make - Prince , Finolex | Rmt | 75mm | 17 | 990 | 16830 | 80% | 13464
29 | d | Company Make - Prince , Finolex | Rmt | 100mm | 25 | 1580 | 39500 | 80% | 31600
30 | C | CHAMBER GRATING
31 | 1 | Constructing Inspection chamber in 100 mm thick Brick Wall, WATER PROOFING with Plaster. TILE EXTRA TO BE PAID |  | DRAINAGE CHAMBER & COVER
32 | a | 300mm x 300mm | Nos. | Internal |  |  | 0 |  | 0
33 | b | 450mm x 450mm | Nos. | Internal |  |  | 0 |  | 0
34 | c | 450mm x 900mm (with Excavation, C.I. Cover frame) | Nos. | External |  |  | 0 |  | 0
35 | 2 | Constructing Gully trap in 100mm thick Brick Wall with Plaster wih top cover. |  | GULLY TRAP
36 | a | 300mm x 300mm | Nos. | GULLY TRAP |  |  | 0 |  | 0
37 | 3 | Providing Fixing 20mm heavy quality SS Grating along with Perforated Mesh Angle Frame as per Size , Drawings. Weight not more than 60kg. Rate inclusive of chamber construction |  | GRATING
38 | 3.01 | 200mm width
39 | a | 900mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. |  |  |  | 0 |  | 0
40 | b | 600mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. |  |  |  | 0 |  | 0
41 | c | 300mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. |  |  |  | 0 |  | 0
42 | d | 200mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. |  | 8 | 7500 | 60000 | 80% | 48000
43 | 3.02 | 300mm width
44 | a | 900mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. |  |  |  | 0 |  | 0
45 | b | 600mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. |  |  |  | 0 |  | 0
46 | c | 300mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. |  | 5 | 8500 | 42500 | 80% | 34000
47 | d | 200mm X 300mm with SS Perforated Jali. (Grating Set) | Nos. |  |  |  | 0 |  | 0
48 | 3.03 | 450mm width
49 | a | 600mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. |  |  |  | 0 |  | 0
50 | b | 450mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. |  | 1 | 9500 | 9500 | 80% | 7600
51 | c | 300mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. |  |  |  | 0 |  | 0
52 | d | 200mm X 450mm with SS Perforated Jali. (Grating Set) | Nos. |  |  |  | 0 |  | 0
53 | 3.04 | 600mm width
54 | a | 600mm X 600mm with SS Perforated Jali. (Grating Set) | Nos. |  | 2 | 15000 | 30000 | 80% | 24000
55 | 3.05 | 1200mm X 200mm with SS Perforated Jali. (Grating Set) | Nos. |  | 3 | 10500 | 31500 | 80% | 25200
56 | 4 | Providing Fixing 25 x 25 x 3mm thick SS Angle Frame for open drains. As per Size , Drawings. Ready to receive kota. |  | GRATING
57 | 4.01 | 560mm X upto 125mm | Nos. |  |  |  | 0 |  | 0
58 | 4.02 | 560mm X from 130mm upto 200mm | Nos. |  |  |  | 0 |  | 0
59 | 4.03 | 560mm X from 205mm upto 300mm | Nos. |  |  |  | 0 |  | 0
60 | 4.04 | 200mm X 200mm | Nos. |  |  |  | 0 |  | 0
61 | 5 | Fixing of Portable SS grease trap 3 bowl sink as per drg. | Nos. | PORTABLE GREASE TRAP | 1 | 3500 | 3500 | 50% | 1750
62 | 5.01 | Bush for portable grease trap | Nos. |  | 2 | 1800 | 3600 | 50% | 1800
63 | 6 | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - inside the store as per drawing. Rate includes SS angles of 50 x 50 x 6mm as frame; SS cover on frame made by 50 x 50 SS Pipes @ maximum 15 c c, covered with SS Sheet. Inclusive of fabricated SS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Nos. | INTERNAL GREASE TRAP |  |  | 0 |  | 0
64 | 7 | Construction of grease trap with SS cover (2 -6 x 3 -6 x upto 3 -0 deep) - outside the store as per drawing. Rate includes MS angles of 50 x 50 x 6mm as frame; MS cover on frame made by 50 x 50 MS Pipes @ maximum 15 c c, covered with MS chequered plate. Inclusive of fabricated MS T sections made as per detailed drawings (3mm thick) for mounting grease trap partitions. Internal tiling plaster to be paid seperately. | Nos. | EXTERNAL GREASE TRAP |  |  | 0 |  | 0
65 | D | NAHNI TRAP
66 | 1 | Supply, Laying, Testing Commissioning of Approved CI (Cast Iron) CLASS pipes Nahani - Floor Trap with Approved Make leavy Duty round or Square SS Grating etc. Complete. | Nos. | Nahani Trap ( CI 75mm ) |  |  | 0 |  | 0
67 | 2 | Supply, Laying, Testing Commissioning of Approved SS Nahani TRAP WITH Floor Trap COCKROACH JAALI with Approved Make heavy duty round or Square Grating etc. Complete. | Nos. | Nahani Trap (PVC 75mm ) |  |  | 0 |  | 0
68 | E | CP FIXTURES BRASS VALVES -Jaquar (only continental series)
69 | 1 | P F Angle Cock. | Nos. | Angle Cock | 20 | 1200 | 24000 | 75% | 18000
70 | 2 | P F Sink Mixer, Swinging Casted Spout. | Nos. | Sink Mixer Wall Mounted | 4 | 4500 | 18000 | 75% | 13500
70 | 3 | P F Sink Mixer, Swinging Casted Spout. | Nos. | Sink Mixer table Mounted | 3 | 4500 | 13500 | 75% | 10125
71 | 4 | P F Long Neck Bib Cock with wall Flange. Make- Jaquar | Nos. | Long Neck Bib Cock | 5 | 2000 | 10000 | 75% | 7500
72 | 5 | Providing Fixing Bib Cock chrome finish with wall Flange. | Nos. | Bib Cock | 4 | 1500 | 6000 | 75% | 4500
73 | 6 | P F Sink Pillar cock with swinging casted spout. | Nos. | Sink Pillar Cock | 4 | 1500 | 6000 | 75% | 4500
74 | 7 | P F Fixed Sink Cock. | Nos. | Sink Cock | 3 | 2500 | 7500 | 75% | 5625
75 | 8 | P F Tall Pillar Cock for counter flush basin. | Nos. | Pillar Cock | 3 | 2500 | 7500 | 75% | 5625
76 | 9 | P F Pneumatic push cock. | Nos. | Pneumatic Push Cock | 1 | 4500 | 4500 | 75% | 3375
77 | 10 | Foot Paddle Operated Faucet. (Below Hand Wash) | Nos. | Foot Paddle Operated Faucet | 2 | 4500 | 9000 | 75% | 6750
78 | 11 | Dual press |  | Flush Valve
79 |  | P F open Flush valve. | Nos. |  |  |  | 0 |  | 0
80 |  | P F open Flush tank. | Nos. |  |  |  | 0 |  | 0
81 | 12 | P F CP Health Faucet with 1m long CP Flexible Tube with wall Hook. Make- Jaquar | Nos. | Health Faucet |  |  | 0 |  | 0
82 | 13 | P F 2 in 1 bib cock in washrooms for mounting Health Faucet. Health faucet to be paid for separetly. | Nos. | 2 in 1 Bib Cock |  |  | 0 |  | 0
83 | 14 | Providing fixing 32mm CP finished Bottle Trap with wall flanges. | Nos. | Bottle Trap | 10 | 1500 | 15000 |  | 0
84 | 15 | Providing Waste Coupling 32mm size full thread waste coupling to be use. | Nos. | Waste Coupling | 10 | 200 | 2000 | 75% | 1500
85 | 16 | Providing Fixing Ball Valve ISI mark. (For Inlet) |  | Ball Valves (Brass)
86 | a | 15mm dia | Nos. |  |  |  | 0 |  | 0
87 | b | 20mm dia | Nos. |  |  |  | 0 |  | 0
88 | c | 25mm dia | Nos. |  |  |  | 0 |  | 0
89 | d | 32mm dia | Nos. |  | 1 | 2200 | 2200 | 75% | 1650
90 | e | 40mm dia | Nos. |  |  |  | 0 |  | 0
91 | 16A | Providing Fixing Ball Valve ISI mark. (For Inlet) |  | Ball Valves (CPVC)
92 | a | 15mm dia | Nos. |  |  |  | 0 |  | 0
93 | b | 20mm dia | Nos. |  |  |  | 0 |  | 0
94 | c | 25mm dia | Nos. |  |  |  | 0 |  | 0
95 | d | 32mm dia | Nos. |  |  |  | 0 |  | 0
96 | e | 40mm dia | Nos. |  |  |  | 0 |  | 0
97 | 17 | Providing Fixing Brass Non Return Vavles of ISI mark . Rates are for BRASS valves |  | Non Return Valves (NRV)- Brass
98 | a | 25mm | Nos |  |  |  | 0 |  | 0
99 | b | 32mm | Nos |  |  |  | 0 |  | 0
100 | c | 40mm | Nos. |  |  |  | 0 |  | 0
101 | 18 | P F ball valve below 3 bowl sink veg pre RO sink - 75mm dia | Nos. | Drainage Valve | 5 | 1500 | 7500 | 75% | 5625
102 | E | ACCESSORIES MISCELLANEOUS
103 | 1 | Providing Flexible water pipe to connect Angle Valve to faucet | Nos. | Flexible Water Pipe | 20 | 350 | 7000 | 75% | 5250
104 | 2 | Pre rinse spray valve spray. | Nos. | Flexible Pipe | 1 | 1050 | 1050 | 75% | 787.5
105 | 3 | Providing water level Indicator for In Raw tank RO water tank with gauge Glass Cock. In BOH Area. | Nos. | Water Indicator |  |  | 0 |  | 0
106 | 4 | P F water level Indicator on terrace water tank by means of a transparent clear tube fixed along height of the water tank hence making water level visible | Nos. | Water Indicator |  |  | 0 |  | 0
107 | 5 | P F flexible PVC waste pipe on wash basin sink drains | Nos. | Flexible Waste Pipe | 10 | 95 | 950 | 75% | 712.5
108 | 6 | Installation of plumbing fixtures kitchen equipment provided by client with new hardware as required- PLUMBING SCOPE | Job | Installation of Equipment- Plumbing Scope | 1 | 9500 | 9500 | 75% | 7125
109 | F | BOILERS GEYSERS
110 | 1 | Providing Supplying boiler with Mounting Bolts etc. |  | Boiler Storage
111 | a | 35 Liter | Nos. |  | 1 | 18000 | 18000 | 75% | 13500
112 | b | 25 Liter | Nos. |  |  | 18000 | 0 |  | 0
113 | 2 | Geyser Storage |  | Geyser Storage
114 | b | Providing Supplying 6 Liters Geyser with Mounting Bolts etc. | Nos. |  | 2 | 7500 | 15000 | 75% | 11250
115 | G | SANITARYWARE
116 | 1 | P F Wash Basin as per specs |  | Wash Basin
117 |  | P F Counter top Basin, Make Size- PARRYWARE as per drawing | Nos. |  |  |  | 0 |  | 0
118 |  | P F Under Counter Basin, Make size- PARRYWARE as per drawing | Nos. |  |  |  | 0 |  | 0
119 |  | Corner Wash Basin | Nos. |  |  |  | 0 |  | 0
120 | 2 | P F Wall hung EWC with Seat Cover Make size- PARRYWARE as per drawing | Nos. | WC Customer Toilet |  |  | 0 |  | 0
121 | 3 | P F Wall Urinal with brackets. Make size- PARRYWARE as per drawing | Nos. | Urinal Customer Toilet |  |  | 0 |  | 0
122 | 4 | P F pressomatic type flush valve for urinals | Nos. | Urinal Pressomatic Flush Valve |  |  | 0 |  | 0
Total : | [6 empty] | 480270 |  | 359666