## Sheet1
ARROW ELECTRICALS MUMBAI
KFC-DELHI AIRPORT-T1
BOQ FOR RA-BILL
|  | WO NO:TFSPL/PO/24-25/000178 |  | AS PER WO |  |  | RA-1 BILL AMOUNT
S.NO | ItemCode | ItemName | UOM | Quantity | SupplierRate | Total Amount | % | Amount
| 1.01 | Design, fabrication, assembling, wiring supply, installation, testing commissioning of Change over Panel, fabricated steel CRCA painted sheet steel. The boards shall be treated with all anticorrosive process before painting as per standards with final approved shade of powder coated as approved. 2 nos. Earthing terminals shall be provided for all panels. Boards shall be fabricated in length, height, depth etc. To match with site conditions.
2 | a | 125A 4pole Change over Switch AUTO type | Unit | 0.00 | 35650
3 | c | 200A 4pole Change over Switch AUTO type | Unit | 0.00 | 53400
4 | d | 250A 4pole Change over Switch AUTO type | Unit | 0.00 | 66340
5 | 2 | SITC OF ENCLOSURES FOR MCB FOR OUTDOOR APPLICATION WITH MCB DP FP
6 | 2.01 | DP MCB in weather proof enclosure with MCB
7 | a | 40-63A | Nos | 2.00 | 3050 | 6100 | 75% | 4575
8 | b | 6-32A | Nos | 3.00 | 2510 | 7530 | 75% | 5647.5
9 | 2.02 | 4 POLE MCB in weather proof enclosure with MCB |  | 0.00 | 0
10 | c | 6-32A | Nos | 1.00 | 6890 | 6890 | 75% | 5167.5
11 | 3 | SITC OF INDUSTRIAL TYPE LE-GRAND METRA PLUG TEMPRA PLUG FOR EQUIPMENT POWER CONNECTIONS WITH REQUIRED MCB
12 | 3.01 | 40A 5Pin 3 Phase Plug and Socket with TPN MCB | Nos. | 3.00 | 9500 | 28500 | 75% | 21375
13 | 3.02 | 32A 5Pin 3 Phase Plug and Socket with TPN MCB | Nos | 2.00 | 8240 | 16480 | 75% | 12360
14 | 3.03 | 32A 3Pin Single Phase Plug and Socket with SP MCB | Nos | 2.00 | 3250 | 6500 | 75% | 4875
15 | 3.04 | 20A 3Pin SP Metal Clad Socket with SP MCB (Industrial Type) | Nos | 30.00 | 2550 | 76500 | 75% | 57375
16 | 4 | CABLES, TRAYS TERMINATIONS |  | 0.00 | 0
17 | 4.01 | SITC of cables 1.1KV grade PVC XLPE insulated armoured Aluminium Copper conducter cables. The cables shall be laid as per drawings or on cable trays laid over MS supports, cable racks, or fixing on wall including clamping of cable, or in wall chases. Rate to include making good the wall chases with cement mortar.
18 | b | 3 C X 2.5 sq. mm. CU PVC ARMOURED | Rmt | 100.00 | 220 | 22000 | 75% | 16500
19 | c | 3 C X 4 sq. mm. CU PVC ARMOURED | Rmt | 80.00 | 310 | 24800 | 75% | 18600
20 | d | 3 C X 6 sq. mm. CU PVC ARMOURED | Rmt | 40.00 | 430 | 17200 | 75% | 12900
21 | e | 3 C X 6 sq. mm. CU PVC UNARMOURED | Rmt | 35.00 | 375 | 13125 | 75% | 9843.75
22 | j | 4 C X 4 sq. mm. CU PVC ARMOURED | Rmt | 100.00 | 378 | 37800 | 75% | 28350
23 | l | 4 C X 10 sq. mm. CU PVC ARMOURED | Rmt | 140.00 | 780 | 109200 | 75% | 81900
24 | s | 3.5 C X120 sq. mm. AL. XLPE CABLE ARMOURED | Rmt | 45.00 | 1050 | 47250 | 75% | 35437.5
25 | 4.02 | SITC of Cable Terminations including single double compression chrome plated Brass glands and Copper lugs (crimping type). PVC taping as required with all accessories required, complete.
26 | b | 3 C X 2.5 sq. mm. CU PVC ARMOURED | Nos | 8.00 | 300 | 2400 | 75% | 1800
27 | c | 3 C X 4 sq. mm. CU PVC ARMOURED | Nos | 10.00 | 390 | 3900 | 75% | 2925
28 | d | 3 C X 6 sq. mm. CU PVC ARMOURED | Nos | 4.00 | 410 | 1640 | 75% | 1230
29 | e | 3 C X 6 sq. mm. CU PVC UNARMOURED | Nos | 4.00 | 450 | 1800 | 75% | 1350
30 | j | 4 C X 4 sq. mm. CU PVC ARMOURED | Nos | 10.00 | 400 | 4000 | 75% | 3000
31 | l | 4 C X 10 sq. mm. CU PVC ARMOURED | Nos | 8.00 | 560 | 4480 | 75% | 3360
32 | s | 3.5 C X120 sq. mm. AL. XLPE CABLE ARMOURED | Nos | 2.00 | 1150 | 2300 | 75% | 1725
33 | t | 3.5 C X150 sq. mm. AL. XLPE CABLE ARMOURED |  | 0.00 | 0
34 | 4.03 | SITC of prefabricated GI Perforated type 2MM THICK X 50MM HT. cable trays including Tees Bends Crossing Reducers Couping to be laid in cable trench, overhead on wall or hanged from ceiling complete with all accessories as required including support at every 1500mm as required
35 | e | 300mm wide PERFORATED type cable tray with support | Rmt | 30.00 | 1190 | 35700 | 75% | 26775
36 | 6 | SITC OF SWITCHES, SOCKETS, INCLUSIVE OF FRONT MOUNTING PLATE BACK BOXES WITH ALL ACCESSORIES
37 | a | 6A Switch for Lighting control. | Nos | 6.00 | 230 | 1380 | 75% | 1035
38 | b | 6A Power Switch Socket set | Set | 35.00 | 610 | 21350 | 75% | 16012.5
39 | c | 6 16A Power Switch Socket set | Set | 18.00 | 850 | 15300 | 75% | 11475
40 | d | 6A Socket | Nos | 18.00 | 350 | 6300 | 75% | 4725
41 | g | 6 16A Power and Switch Socket in weather proof enclosure | Nos | 12.00 | 2050 | 24600 | 75% | 18450
42 | i | Door bell call bell | Nos | 1.00 | 1200 | 1200 | 75% | 900
43 | 7 | WIRING CONDUITING
44 | 7.01 | SITC of concealed point wiring using 600V grade 3 x 2.5 sqmm FRLS copper conducter insulated wires with proper pulled through GI conduit clamped on over head slab, laid over false ceiling or in wall chases. Rate to include making good the wall chases with cement mortar, WITH JUNCTION BOX ALL REQUIRED ACCESSORIES. (of any wire length, NO EXTRA LENGTH WILL BE PAID)
45 | a | Primary light points on switch BOARD (Without Switch MCB cost- switch to be billed in section 8 above, CIRCUIT LENGTH OF SWITCH BOARD TO PANEL DB TO BE BILLED IN RESPECTIVE SECTION) | Nos | 4.00 | 2250 | 9000 | 75% | 6750
46 | B | Primary light points on MCB control | Nos | 10.00 | 3800 | 38000 | 75% | 28500
47 | C | Secondary light points BY Switch or MCB | Nos | 21.00 | 1450 | 30450 | 75% | 22837.5
48 | 7.02 | SITC of FRLS circuits pulled through GI conduits clamped on over head slab, laid over false ceiling or in wall chases. Rate to include making good the wall chases with cement mortar.
49 | e | 2X6.0 + 1X4.0 sq.mm. CU FRLS wires, circuit from DB or panel to power point (Equipment) | Rmt | 40.00 | 344 | 13760 | 75% | 10320
50 | f | 2X4.0 + 1X2.5 sq.mm. CU FRLS wires, circuit from DB or panel to power point (Equipment) | Rmt | 480.00 | 281 | 134880 | 75% | 101160
51 | H | 2X2.5 + 1X1.5 sq.mm. CU FRLS wires, circuit from DB or panel to power point (Equipment) or switch board for lighting | Rmt | 850.00 | 220 | 187000 | 75% | 140250
52 | 8 | EARTHING
53 | 8.01 | SITC of earthing wire including necessary accessories, clamped on over head slab or walls, laid over false ceiling or in wall chases. Rate to include making good the wall chases with cement mortar. Interconnection between lengths should be as per specifications and as per good installation practice.
54 | b | 25 X 3 mm GI Strip | Rmt | 100.00 | 190 | 19000 | 75% | 14250
55 | d | 8 SWG hard drawn bare GI wire | Rmt | 200.00 | 50 | 10000 | 75% | 7500
56 | e | 12 SWG hard drawn bare GI wire | Rmt | 150.00 | 45 | 6750 | 75% | 5062.5
57 | 8.02 | SITC of runs of insulated copper wire as earthing conducter including necessary accessories, clamped on over head slab or walls, laid over false ceiling or in wall chases. Rate to include making good the wall chases with cement mortar. Interconnection between lengths should be as per specifications and as per good installation practice.
58 | b | 1C X 16 sq. mm. | Rmt | 60.00 | 270 | 16200 | 75% | 12150
59 | 8.03 | SITC of Copper Earthing station as per specification and IS 3043-1985 for equipment earthing for UPS and IT earthing. Following guidelines to be maintained
60 | a | Excavation in hard marrum
61 | b | Watering pipe
62 | c | Earthing strip Earthing cable
63 | d | Plate pipe electrode
64 | e | Hardware
65 | F | Brick masonry chamber with C.I. hinged cover and funnel
66 | G | Charcoal and salt fill
67 | H | Equipotential bar
68 | I | 600 x 600 x 3 mm. Thick CU. Earth electrode type earth station
69 | J | Brick masonry chamber with C.I. hinged cover and funnel | Nos | 0.00 | 0
70 | 8.04 | SITC of GI Earthing station as per specification and IS 3043-1985 for equipment earthing for panel and equipment earthing. Following guidelines to be maintained | Nos | 0.00 | 0
71 | a | Excavation in hard marrum
72 | b | Watering pipe
73 | c | Earthing strip Earthing cable
74 | d | Plate pipe
75 | e | Hardware
76 | F | Charcoal and salt fill
77 | G | Equipotential bar
78 | H | 600 x 600 x 6 mm. Thick GI Earth electrode type earth station
79 | I | Brick masonry chamber with C.I. hinged cover and funnel
80 | 8.05 | SITC of Chemical Earthing station as per specification and IS 3043-1985 for equipment earthing for panel and equipment earthing. Following guidelines to be maintained | Nos | 0.00 | 0
81 | a | Excavation in hard marrum
82 | b | Chemical compound
83 | c | Earthing strip Earthing cable
84 | d | Cu pipe in pipe electrode
85 | e | Hardware
86 | F | Equipotential bar
87 | G | Brick masonry chamber with C.I. hinged cover and funnel | Nos | 0.00 | 0
88 | 8.07 | SITC of 25 x 4mm GI Earth Bus in powder coated box | Nos | 0.00 | 0
89 | 9 | SIEMENS L T MAKE MK1 3 PHASE DOL STARTER FOR ALL EXHAUST FAN FRESH AIR INLINE FAN
90 | 9.01 | 5.5 KW | Nos | 0.00 | 0
91 | 9.02 | 3.7 KW | Nos | 0.00 | 0
92 | 9.03 | 2.2 KW | Nos | 0.00 | 0
93 | 10 | TELEPHONE DATA TV
94 | 10.01 | SITC of RJ45 information outlet with face plate and box | Nos | 10.00 | 560 | 5600 | 75% | 4200
95 | 10.02 | SITC of RJ11 telephone outlet with plate and box | Nos | 3.00 | 550 | 1650 | 75% | 1237.5
96 | 10.03 | SITC of CAT6 data cable EXCLUDING 20mm 25mm dia. conduits | Rmt | 300.00 | 85 | 25500 | 75% | 19125
97 | 10.04 | SITC of CAT5 cable EXCLUDING 20mm 25mm dia. conduits for telephone | Rmt | 80.00 | 65 | 5200 | 75% | 3900
98 | 10.05 | SITC of 10 pair telephone tag block with enclosure | Nos | 1.00 | 950 | 950 | 75% | 712.5
99 | 11 | INSTALLATION OF LIGHTING FIXTURES
100 | A | FIXING OF LIGHT | Nos | 31.00 | 350 | 10850 | 75% | 8137.5
101 | 18 | P L OF PVC TRUNKING WITH CAP
102 | A | 4 WIDE | RMT | 0.00 | 0
103 | B | 6 WIDE | RMT | 0.00 | 0
104 | 1 | Supply Installation
105 | a | Supply of Main LT panels | Nos | 1.00 | 265000 | 265000 | 75% | 198750
106 | b | Supply of 18 Way SPNDB | Nos | 1.00 | 9500 | 9500 | 75% | 7125
107 | 2 | UPS
108 | 2.01 | Supply,Installation,Testing Commissioing of single Three phase UPS with 20minute battery back-up online systems with 2 nos DP MCB in weather proof enclosures. 3KVA -single phase input and single phase output ups with 25A DP MCB and 25A DP MCB on input and output of ups. 6KVA - single phase input and single phase output ups with 40A DP MCB and 40A DP MCB on input and output of ups.
109 | d | 6 KVA Floor Mounted | Nos | 1.00 | 144485 | 144485 | 75% | 108363.75
|  | TOTAL AMOUNT |  |  |  | 1480000 |  | 1110000
|  | DISCOUNT |  |  | 1.4% | 20720 |  | 15540
|  | AFTER DISCOUNT TOTAL AMOUNT |  |  |  | 1459280 |  | 1094460
|  | GST |  |  | 18% | 262670.4 |  | 197002.8
|  | GRAND TOTAL WITH GST AMOUNT |  |  |  | 1721950.4 |  | 1291462.8
| CERTIFIED BY NAME:….................................. |  | DATE:…................................ |  |  | Sign..................................