## SUMMARY
PO NO : | SEMOLINA /PO/23-24/700
SR NO | DISCRIPTION | PO VALUE | PRESENT BILL AMT | CUMULATIVE AMT | VARIANCE AMT
1 | HIGH SIDE HVAC WORK | 851000 | 455750 | 455750 | 395250
2 | Low side HVAC | 1359350 | 827172.75 | 827172.75 | 532177.25
3 | PR for Fire Sprinkler LKN Budweiser bar | 441570 | 400030 | 400030 | 41540
4 | PR for FAS for LKN Budweiser bar | 140090 | 0 | 0 | 140090
|  | 2792010 | 1682952.75
| GST 28% Item no 1 | 238280 | 127610
| GST 18 % item no 2,3,& 4 | 349381.8 | 220896.495
| TOTAL | 3379671.8 | 2031459.245

## ABSTRACT
[5 empty] | AS PER PO |  | AS PER SITE
Sr No. | Item Code | Item Description | UOM | Qty | Unit Price | Amount | Unit Price | Amount
1 |  | ANTI TERMITE TREATMENT- Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). AREA - ALL MOH FOH | Sq.m. | 325 | 110 | 35750 |  | 0
2 |  | WATERPROOFING - Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. 1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring | Sq.m. | 80 | 950 | 76000 |  | 0
3 |  | CINDER LIGHT WT. SIPORAX BLOCK BATS FILLING
4 |  | Providing Filling light wt. Siporex block bats to conceal drainage plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. AREA - MOH RAISED AREA (up to 75 mm) | Sq.m. | 54 | 650 | 35100 |  | 0
5 |  | PCC LAYER- Providing Laying P.C.C 1 3 6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 54 | 600 | 32400 |  | 0
6 |  | Block WORK - Providing Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1 4 (1 cement 4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. AREA - 150 MM THICK BLOCK MASONARY | Sq.m. | 110 | 1450 | 159500 |  | 0
7 |  | PLASTER - P L12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 220 | 650 | 143000 |  | 0
8 |  | P L in place (cast in situ) RCC lintel beams in 150mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1 4 8) 100mm high with 4 no. s 8mm th. Steel bars as per general specifications, complete in all respects AREA - RCC LINTEL BEAM | Rmt | 20 | 650 | 13000 |  | 0
|  | Wet Work BOQ of Water proofing and Wall work - LKN Budweiser bar |  |  |  | 494750 |  | 0
9 | 1.0 | Air Handling Units (Indoor Type)
10 |  | Supply , Installation , testing commissioning Of Double skin Floor mounted Ceiling Suspended Type air handling units of extruded aluminium section with 0.6 mm preplasticized precoated GI sheet outside and 0.6 mm plain Galvanized sheet inside, minimum of 25 mm thick PUF insulation of 38KG m3 , with Plug Fans Backward Type DIDW Blower with TEFC motors, copper cooling coils as mentioned below , with aluminium fins, MERV-8 and MERV 13 Filters. The drain pan shall be constructed out of 18G stainless steel duly insulated. All the AHU s installed under this tender shall have minimum IE2 motor or better. All the cooling coils shall be AHRI Eurovent Certified . The AHU Coil shall be selected at 9 deg C Chilled water Inlet Temp Temperature. Approval of AHU Technical Data by consultant prior to fabrication is required. The cost of AHU shall be inclusive of factory fitted VFD of approved make.
11 |  | Design Parameters- 25 deg C -R.A.Temp, 55% RH, 9 deg C- CHW IN
12 |  | Water Flow Rate- 2.0 GPM TR
13 | 1.1 | Ceiling Suspended Type
14 | 1.1.1 | 3400 CMH(2000 CFM)at 20 mm External Static Pressure, 6 RD Cooling Coil, Approx 5 TR, 1 x 0.75 KW Motor | Nos | 1 | 155000 | 155000 | 0.75 | 116250
15 | 1.1.2 | 5100 CMH(3500 CFM)at 25 mm External Static Pressure, 6 RD Cooling Coil, Approx 7 TR, 1 x 2.25 KW Motor | Nos | 1 | 230000 | 230000 | 0.7 | 161000
16 | 1.1.3 | 10200 CMH(6000 CFM)at 25 mm External Static Pressure, 6 RD Cooling Coil, Approx 12 TR, 1 x 3.75 KW Motor | Nos | 1 | 255000 | 255000 | 0.7 | 178500
17 | 1.2 | Digital Heating Cooling Thermostat for Air Handling Units | Nos. | 3 | 12000 | 36000 | 0 | 0
18 | 2.0 | Kitchen Scrubber (Dry Type) (Ceiling Suspended Type)
19 | 3.1 | Installation, Testing and Commissioning of Dry Type Scrubber each comprising of extract air intake section, electrostatic precipitation technology, dry type air cleaner to remove oil, smoke and fumes from exhaust air, as per the Specifications. Electrostatic section shall be made of 16 gauge galvanised sheet, high bake epoxy powder coated, washable type aluminium mesh filters, stainless steel spiked ionizers to create high voltage DC field, aluminum collector plates which should be alternatively charged positive and negative with large collecting area with 14 deep cell, to work as magnet for charged smoke and oil particles. Average efficiency of 90-95% in single pass as per ASHRAE test method. Electrostatic Precipitator should be able to charge particles from 0.01 micron to 10 microns through solid state power supply. Collector cell should be of permanent type and incorporate slide out facility for easy removal for cleaning. Power supplies shall be 100% solid state UL Listed, Module of capacity above 3000 CFM shall be equipped with Pulse width modulating (PWM)
20 |  | The system should be fitted with interlock switch for safety . The system should allow connection to a fan section to achieve 500 FPM velocity across the air
21 |  | Operating Voltage 220V, 50 Hz
22 |  | Ionizing Voltage 12.5 to 13 KVDC
23 |  | Collector Cell Voltage 6 to 6.5 KVDC
24 |  | Power Consumption Not more than 50W per cell.
25 |  | Capacities 4000 CFM | Nos | 1 | 175000 | 175000 | 0 | 0
|  | High Side - HVAC |  |  |  | 851000 |  | 455750
26 | 1.0 | Chilled Water Piping with Nitrile Rubber Insulation
27 |  | Supplying, laying fixing, testing and commissioning of MS C class chilled water piping (cut of required length and installed with welded joints. The necessary fittings such as elboues, tees etc. shall all to included in this item). The Insulation shall be Class O nitrile Rubber pre-slit, pipe sleeve upto 100 mm dia and sheet for bigger dia with factory Laminated 7 mill woven glass cloth of thicknesses as specified, with approved adhesive. Manufactured supplied, suitable sized nitrile rubber pipe supports with PUF PIR inserts shall be used. Thermal conductivity should not exceed 0.035 W MK at 0 degree celsius and water vaper resisitance > 7000. Manufactures tapes and adhesive to used only. The pipe supports should also be of nitrile rubber with PUF PIR inserts and are to be installed as per manufacturer s recomendation. The pipe fittings shall be MS. class for pipes upto 150 mm and for 200mm and above, same material of the pipe shall be usee all bends Reducess Tee upto 150 mm shall be factory fabricated ready made MS C class. Note Use proper template for marking block colour Arrows pipe. for supply return.
28 | I | 40mm dia with 32 mm thick insulation with factory Laminated 7 mil glass cloth upper layer | Mtrs. | 50 | 1850 | 92500 | 18 | 33300
29 | II | 32mm dia with 32 mm thick insulation with factory Laminated 7 mil glass cloth upper layer | Mtrs. | 30 | 1650 | 49500 | 28 | 46200
30 | 2.0 | Insulated Valves
31 | 2.1 | Dynamic Balancing Valve-PID type
32 |  | Supply installation, testing and commissioning of BMS Compatible electronic self balancing valve with integrated two way modulating control valves in a single body. The actuator shall be capable of accepting 230V 24V 2-10VDC 4-20 mA electrical signed and shall provided similar transduced feed back output singed to control system. The minimum close off pressure of actuator must be 1.5 times shut of head of pump as per Specification of following size. The actuator shall be microprocessor based with self calibration feature. All the valve shall be complete with step down transformers, thermostat, control wiring and probe.
33 | i. | 10-30 USGPM Insulation as per pipes | Nos. | 3 | 7500 | 22500 | 0 | 0
34 | 2.2 | Manual Butterfly Valves (Insulated)
35 |  | Providing and Fixing of the following valves with PN-16 Ratings complete with flanges nuts bolts gaskets etc. Butterfly valve shall have CI body seal of black nitrile rubber (tight shutoff) S.G. iron disc(nylon coated) PTFE coated shafts etc. as required. These valves should be suitable for flow in either direction and seal in both directions and should be integral moulded design.
36 | 2.2.1 | 40 mm dia -PN16 -- Insulation as per Chilled water pipe | Nos. | 2 | 3500 | 7000 | 0 | 0
37 | 2.3 | Y- Strainer (Insulated)
38 |  | Providing and Fixing of the insulated Y-Strainer fabricated out of MS with removable bronze screen, 3mm perforation and permanent magnet etc. complete in all respect and as per specifications and drawings.
39 | 2.3.1 | 40 mm dia -PN16 -- Insulation as per Chilled water pipe | Nos. | 2 | 3600 | 7200 | 0 | 0
40 | 2.4 | Ball Valve with Stariner (Insulated)
41 |  | Providing and Fixing of the following valves with PN-16 Ratings complete as per specifications.
42 | 2.4.1 | 32 mm dia -PN16 -- Insulation as per Chilled water pipe | Nos. | 2 | 3250 | 6500 | 0 | 0
43 | 2.5 | Ball Valve without Stariner (Insulated)
44 |  | Providing and Fixing of the following valves with PN-16 Ratings complete as per specifications.
45 | 2.5.1 | 32 mm dia -PN16 -- Insulation as per Chilled water pipe | Nos. | 2 | 2200 | 4400 | 0 | 0
46 | 2.6 | Providing and Fixing digital type thermometers with copper well, valve probe suitable for binder test point application.
47 | 2.7.1 | 12 long (Insulated) | Nos. | 6 | 4200 | 25200 | 0 | 0
48 | 2.8 | Dial Presure Guages (glycerine filled Type) with SS Encasing with isolating valve piping etc.The gauge should be with appropriate range and valve and fitted with probe suitable for binder test point application as well.
49 | 2.8.1 | 6 Dial (Insulated) | Nos. | 6 | 2200 | 13200 | 0 | 0
50 | 2.9 | Providing and Fixing of automatic air vent of approved make with insulation valves as per specifications drawings
51 | 2.9.1 | 20mm dia | Nos. | 10 | 1250 | 12500 | 0 | 0
52 | 3.0 | Drain Piping
53 |  | Supply, Installation, testing and commissioning of UPVC condensate drain pipe along with necessary clamps, fittings sich as bends, tees, etc. it shall be insulated with 9 mm thick nitrile foam insulation in tubular form as per specifications.
54 | 3.1 | 25 mm dia | Mtrs. | 10 | 950 | 9500 | 0 | 0
55 | 3.2 | 20 mm dia | Mtrs. | 20 | 850 | 17000 | 0 | 0
56 | 4.0 | DUCTING
57 | 4.1 | G.I. Sheet Metal Ducting - Factory Fabricated
58 |  | Installation, Testing and Commissioning of factory fabricated GSS sheet metal rectangular ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
59 | 4.1.1 | 0.50 MM (26 Gauge) | Sqm. | 30 | 1350 | 40500 | 26.68 | 36018
60 | 4.1.2 | 0.63 MM (24 Gauge) | Sqm. | 130 | 1450 | 188500 | 121.04 | 175508
61 | 4.1.3 | 0.80 MM (22 Gauge) | Sqm. | 75 | 1550 | 116250 | 73.88 | 114514
62 | 4.1.4 | 1.00 MM (20 Gauge) | Sqm. | 10 | 1750 | 17500 | 8.94 | 15645
63 | 4.1.5 | 1.25 MM (18 Gauge) | Sqm. | 0 | 0 | 0 |  | 0
64 | 4.1.6 | 1.00 MM (20 Gauge)- Kitchen Exhaust Ducting with 25 mm thick high density of glasswool rockwool insulation of density 48kg m3 . The insulation shall be covered with muslin cloth over which 2 coats of Starbond approved fire paint is applied to make the insulation hard and fire retardant . | Sqm. | 110 | 1910 | 210100 | 42.835 | 81814.85
65 | 4.2 | G.I. Sheet Metal Ducting - Site Fabricated
66 |  | Installation, Testing and Commissioning of site fabricated GSS sheet metal rectangular ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
67 | 4.2.1 | 0.63 MM (24 Gauge) | Sqm. | 20 | 1450 | 29000 | 0 | 0
68 | 4.2.2 | 0.80 MM (22 Gauge) | Sqm. | 20 | 1550 | 31000 | 20.003 | 31004.65
69 | 4.2.3 | 1.00 MM (20 Gauge) | Sqm. | 5 | 1650 | 8250 | 5 | 8250
70 | 4.2.4 | 1.25 MM (18 Gauge) | Sqm. | 0 | 0 | 0 |  | 0
71 | 4.3 | Ducting (Exhaust)- MS Welded Construction- Site Fabricated
72 |  | Supply, fabrication and erection of following gauges of MS ducting complete with welded drip proof seams and having access doors at every change in direction with maximum spacing of 6 meters in horizontal direction and maximun of 3 floors of vertical risers elbows spliters, supports suspenders bends, tees, vanes, double canvas connection of the equipment etc all complete as required. Duct shall be insulated 25 MM Thich High Density Rockwool Insulation 48 KG m3 . The insulation material and its installation shall be in accordance with the specifications as provided. The entire insulation shall be covered with muslin cloth over which 2 coats of Star Bond approved fire paint is applied to make the insulation hard and fire retardant.
73 | 4.3.1 | 16 gauge (1.5 mm thick) | Sqm. | 0 | 0 | 0 |  | 0
74 | 4.4 | Flexible Duct
75 | 4.4.1 | 100 MM Dia | RM | 0 | 0 | 0 |  | 0
76 | 5.0 | INSULATION
77 | 5.1 | Nitrile Rubber Insulation- Class O
78 |  | Supplying and fixing of closed cell elastomeric insulation of density 55 kg cu.m.and K valueof not less than 0.037W mk at 20 deg C as per specifications and drawings (For indoor applications) with factory Laminated 7 mill woven glass cloth
79 | 5.1.1 | 19 mm thick (AC ducts Fresh Air Duct) | Sqm. | 260 | 1150 | 299000 | 247.755 | 284918.25
80 | 5.2 | Acoustic Lining
81 |  | Supplying and Application of Acoustic lining within the Supply Air duct with 15 mm thick class O open cell nitrile Rubber of density 140-160 kg. Cubm. as per spefications.
82 | 5.2.1 | 15 MM Thick | Sqm | 30 | 750 | 22500 | 0 | 0
83 | 6.0 | DUCT ACCESSORIES
84 | 6.1 | Supply, Installation, Testing and Commissioning of GI multiblade volume control duct damper complete with neoprene rubber gaskets, nuts, bolts, screws linkages, flanges etc., as per specifications. | Sqm. | 2 | 9000 | 18000 | 0 | 0
85 | 6.2 | Supply, Installation, Testing and Commissioning of multiblade Al volume control Collar Grille exhaust Air Opening damper complete with suitable links, lever and quadrants for manual control of airflow and with suitable links , lever and quadrants for manual control of airflow and neoprene rubber gaskets, nuts, bolts, screws, flanges etc., as per specifications. | Sqm. | 3 | 12000 | 36000 | 0 | 0
86 | 6.3 | Supply, Installation, Testing and Commissioning fixing of powder coated extruded aluminium Supply Exhaust Air Grills as per specifications | Sqm. | 2 | 8250 | 16500 | 0 | 0
87 | 6.6 | Supply, Installation, Testing and Commissioning fixing of powder coated extruded Aluminium Continuous Grille as per specifications
88 | 6.6.2 | 150 MM Aluminium Continuos Grille | RM | 5 | 1550 | 7750 | 0 | 0
89 | 6.6.3 | 100 MM Aluminium Continuos Grille | RM | 30 | 1450 | 43500 | 0 | 0
90 | 7.0 | Motorised Fire and Smoke Dampers
91 |  | Supply, installation, testing commissioning of motorised fire smoke damper (spring return type) of approved make of atleast 90 min fire rating as per UL555, made out of 16 ga GSS and suitable for duct wall mounting with suitable size 18 Ga Sleeve as per the specification detail given earlier in the relevant section. The damper shall have 90 minute fire rating. It shall be complete with electronic temperature sensor and electrically operated actuator. The fire damper shall be located in supply return air duct and at fire rated crossover. These fire damper shall be interlocaked with BMS system for fire detection and shall trip close in case of fire. Controller for Fire and Smoke Damper with necessary step down transformer , fan interlocking, centralize Fire Alarm panel Integration, Smoke Detector Integration, UL Listed Thermal Cut Off (72 deg C) and remote testing unit for routine testing with spring return motorized assembly shall be suitable to control the mentioned sizes of damper.
92 | 7.1 | Fire Dampers with Factory Fabricated TDC flange. | Sqm. | 0 | 0 | 0 |  | 0
93 | 7.2 | Motorized Actuators and Modbus Compatible Contoller for motorized dampers | Nos. | 0 | 0 | 0 |  | 0
94 | 7.3 | Interconnectng wiring for fire alarm system. | Lot. | 0 | 0 | 0 |  | 0
95 | 7.4 | Loop in and loop out | Lot. | 0 | 0 | 0 |  | 0
96 | 7.5 | Sealing the openings around the sleeve of fire damper with approved fire sealant as per manufacturer recommendation | Lot. | 0 | 0 | 0 |  | 0
97 | 11.0 | Louvers
98 | 11.1 | Providing and fixing of powder coated extruded aluminium exhaust air louvers fresh air louvers with bird screen and mounting arrangement as per specification and drawings. Free Area shall be more than 60% of gross area.
99 | 11.1.1 | Fresh Air Exhaust Air Louvers with Bird Screen Mesh | Sqm. | 1 | 8000 | 8000 | 0 | 0
|  | Low side HVAC |  |  |  | 1359350 |  | 827172.75
100 | 1 | Providing, Laying, Jointing Testing of Pipes for Sprinkler System - G.I Pipe confirming IS Codes Class `C Heavy Pipe with necessary support anchore fastening from slab.
101 | a. | 25 mm dia | Rmt. | 16 | 1250 | 20000 | 16 | 20000
102 | b. | 32 mm dia | Rmt. | 12 | 1350 | 16200 | 12 | 16200
103 | c. | 40 mm dia | Rmt. | 50 | 1450 | 72500 | 50 | 72500
104 | d. | 50 mm dia | Rmt. | 10 | 1550 | 15500 | 10 | 15500
105 | e. | 65mm dia | Rmt. | 15 | 1650 | 24750 | 14 | 23100
106 | f. | 80mm dia | Rmt. | 0 | 0 | 0 |  | 0
107 | 2 | Synthetic Enamel Paint.
108 | a. | 25 mm dia | Rmt. | 17 | 150 | 2550 | 17 | 2550
109 | b. | 32 mm dia | Rmt. | 12 | 160 | 1920 | 12 | 1920
110 | c. | 40 mm dia | Rmt. | 50 | 170 | 8500 | 50 | 8500
111 | d. | 50 mm dia | Rmt. | 10 | 180 | 1800 | 10 | 1800
112 | e. | 65mm dia | Rmt. | 15 | 190 | 2850 | 14 | 2660
113 | f. | 80mm dia | Rmt. | 0 | 0 | 0 |  | 0
114 | 3 | Providing Fixing of Butterfly Valve.
115 | a. | 50 mm dia | No. | 0 | 0 | 0 |  | 0
116 | b. | 80 mm dia | No. | 1 | 6500 | 6500 | 0 | 0
117 | 4 | Providing Fixing of Ball Valve.
118 | a. | 25 mm dia | No. | 0 | 0 | 0 |  | 0
119 | b. | 32 mm dia | No. | 0 | 0 | 0 |  | 0
120 | c. | 40 mm dia | No. | 0 | 0 | 0 |  | 0
121 | d. | 50 mm dia | No. | 0 | 0 | 0 |  | 0
122 | e. | 65 mm dia | No. | 0 | 0 | 0 |  | 0
123 | f. | 80 mm dia | No. | 1 | 8500 | 8500 | 0 | 0
124 | 5 | HEADER FITTING.
125 | a. | Flow Switch | No. | 1 | 3800 | 3800 | 0 | 0
126 | b | Pressure Gauge | No. | 1 | 2200 | 2200 | 0 | 0
127 | c | Air Release Valve | No. | 1 | 4200 | 4200 | 0 | 0
128 | d | 80 mm dia NRV | No. | 1 | 14500 | 14500 | 0 | 0
129 | 6 | Providing Fixing C.P. Brass 68 degree Quartzoid Bulb Sprinklers. Make Tyco viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed EN approved.
130 | a. | Pendant Type | No. | 30 | 1350 | 40500 | 30 | 40500
131 | b. | UP Right Type | No. | 30 | 1450 | 43500 | 30 | 43500
132 | 7 | Providing Fixing C.P. Brass 79 degree(QR) Quartzoid Bulb Sprinklers. Make Tyco viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed EN approved for high temperature area in Kitchen temprating shall be 79degre
133 | a. | Pendant Type | No. | 8 | 1450 | 11600 | 8 | 11600
134 | b. | UP Right Type | No. | 8 | 1550 | 12400 | 8 | 12400
135 | 8 | Flexible Sprinkler Drop.
136 | a. | 25mm | No. | 38 | 3350 | 127300 | 38 | 127300
137 | b. | 100mm | No. | 0 | 0 | 0 |  | 0
138 | c. | 150mm | No. | 0 | 0 | 0 |  | 0
139 | 9 | Drain Valve | No. | 0 | 0 | 0 |  | 0
|  | PR for Fire Sprinkler LKN Budweiser bar |  |  |  | 441570 |  | 400030
140 | 1 | R1 (RESPONSE INDICATORS)
141 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Response indicators are connected to automatic fire detectors in order to indicate quickly the source of an alarm signal from detectors which are not easily accessible or visible. They light up as soon as the connected fire detector gives an alarm.(Wiring from switches to panel and stair case pressurization not included) | Nos | 13 | 1250 | 16250 | 0 | 0
142 | 2 | HD (HEAT DETECTOR) INSTALL NEAR HOOD
143 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) A heat detector is a fire alarm device designed to respond when the convected thermal energy of a fire increases the temperature of a heat sensitive element. The thermal mass and conductivity of the element regulate the rate flow of heat into the element. All heat detectors have this thermal lag (Wiring from switches to panel and stair case pressurization not included) (Edwards Apollo) | Nos | 1 | 3250 | 3250 | 0 | 0
144 | 3 | CONVENTIONAL FIRE PANEL | Nos | 0 | 0 | 0 |  | 0
145 | 4 | MCP (MANUAL CALL POINT) | [5 empty] | 0
146 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Manual call points are used to initiate an alarm signal, and operate by means of a simple button press or when glass is broken revealing a button. They can form part of a manual alarm system or an automatic alarm system.Model Edwards Apollo and FM approved with GI mounting Box | Nos | 3 | 2550 | 7650 | 0 | 0
147 | 5 | H (HOOTER)
148 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Fire Alarm Systems. A fire alarm system is a electrical electronic system which is connected with many type of devices such as main panel, smoke heat detectors, mcp, sounder etc.. to detect the fire event by indiacating audio or visualize signal at the main or individual devices.Model Edwards Apollo with GI mounting Box | Nos | 3 | 4800 | 14400 | 0 | 0
149 | 6 | SD (SMOKE DETECTOR ABOVE CEILING)
150 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay.Model Edwards Apollo. | NOS | 13 | 3100 | 40300 | 0 | 0
151 | 7 | SD (SMOKE DETECTOR BELOW CEILING)
152 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model Edwards Apollo. | NOS | 13 | 3100 | 40300 | 0 | 0
153 | 8 | MSD (MULTI SENSOR DETECTOR BELOW CEILING)
154 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model Edwards Apollo. | NOS | 0 | 0 | 0 |  | 0
155 | 9 | FIRE ALARM SYSTEM LOOPING | RMT. | 92 | 195 | 17940 | 0 | 0
156 | 10 | MONITOR MODULE
157 |  | Providing and fixing Emonitor module . Model Edwards FMM-1 flash scan type UL listed and FM approved. | NOS | 0 | 0 | 0 |  | 0
|  | PR for FAS for LKN Budweiser bar |  |  |  | 140090 |  | 0
[6 empty] | 2792010 |  | 1682952.75

## M Sheet
Sr No. | Item Code | Item Description | UOM | Qty | Length | Width | Height | Nos | QTY | Remark
1 |  | ANTI TERMITE TREATMENT- Providing doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3 in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4 center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect.(Mode of measurement is to be carpet area of floor and not the area of surface treated). AREA - ALL MOH FOH | Sq.m. | 325
2 |  | WATERPROOFING - Providing and Applying Fosroc RFX Brush Bond Coating waterproofing to RCC slabs comprising of the following operations. 1. Removal of Top Screed from the Mother Slab. 2. Cleaning of the Mother Slab with Hard Brush Removal of Dirt from the Surface with Air Blowers 3. Applying of the Fosroc RFX Brush Bond Coating on the mother slab with Brush in Clock wise directions on all 2 Sides Walls till 450m.m Height . If the Floor has to be raised 150m.m 4. After drying of the 1st Coat of the Brush Bond Coating . 2nd Coat is applied in the Anticlockwise Directions 5. After drying of entire Surface say 24 Hours . we will fill Water to 3 Inch Levels for Ponding Testing. 6. Water will be kept for observations for 72 Hours . If Leakage is observed . Water is emptied 7. Above Procedure is Repeated . 8. If No Leakage is observed after 72 Hours . 9. Water will be drained out from the Floor Surface 10. Protective Screeding mixed with FOSROC NITOBOND SBR of Average 25m.m thickness is done on the Water Proofing Surface Coving on Side Walls . 11. After Dryings of Protective Screed say 2 Days. Drain Lines are laid on the Floor with Slope main Drain lines chambers are done . 12 . After this floor raising by Light Seaproax block is done followed by Kota Stone Flooring | Sq.m. | 80
3 |  | CINDER LIGHT WT. SIPORAX BLOCK BATS FILLING
4 |  | Providing Filling light wt. Siporex block bats to conceal drainage plumbing lines. The Top layer should be finished properly to receive P.C.C base flooring layer on it. The same shall be completed as per the details are provided in drawings or as directed by Architect. AREA - MOH RAISED AREA (up to 75 mm) | Sq.m. | 54
5 |  | PCC LAYER- Providing Laying P.C.C 1 3 6 of average thickness of upto 50mm of M 10 grade of concrete ( 1 cement 3 coarse sand 6 graded stone aggregate 20 mm nominal size) as floor base. | Sq.m. | 54
6 |  | Block WORK - Providing Laying of block masonry of thickness 150mm in super structure, bund wall, in raised MOH counter area using cement mortar 1 4 (1 cement 4 coarse sand) mix, joints finished, curing complete as per specification and drawing or as directed by Project Manager. AREA - 150 MM THICK BLOCK MASONARY | Sq.m. | 110
7 |  | PLASTER - P L12-15mm thick plaster in cement mortar 1 4 (1 cement 4coarse sand) to ceiling, all typesof R.C.C. work, brick work surfaces at all levels in line,level and plumb including smooth cement finish and providing necessary grooves at junctions of walls.Rate shall be inclusive of scaffolding and complete with curing etc | Sq.m. | 220
8 |  | P L in place (cast in situ) RCC lintel beams in 150mm th. blockwork @ 1200 mm and at Door lintel lvtl approx. 2400mm from FFLvl. (1 4 8) 100mm high with 4 no. s 8mm th. Steel bars as per general specifications, complete in all respects AREA - RCC LINTEL BEAM | Rmt | 20
Wet Work BOQ of Water proofing and Wall work - LKN Budweiser bar
9 | 1.0 | Air Handling Units (Indoor Type)
10 |  | Supply , Installation , testing commissioning Of Double skin Floor mounted Ceiling Suspended Type air handling units of extruded aluminium section with 0.6 mm preplasticized precoated GI sheet outside and 0.6 mm plain Galvanized sheet inside, minimum of 25 mm thick PUF insulation of 38KG m3 , with Plug Fans Backward Type DIDW Blower with TEFC motors, copper cooling coils as mentioned below , with aluminium fins, MERV-8 and MERV 13 Filters. The drain pan shall be constructed out of 18G stainless steel duly insulated. All the AHU s installed under this tender shall have minimum IE2 motor or better. All the cooling coils shall be AHRI Eurovent Certified . The AHU Coil shall be selected at 9 deg C Chilled water Inlet Temp Temperature. Approval of AHU Technical Data by consultant prior to fabrication is required. The cost of AHU shall be inclusive of factory fitted VFD of approved make.
11 |  | Design Parameters- 25 deg C -R.A.Temp, 55% RH, 9 deg C- CHW IN
12 |  | Water Flow Rate- 2.0 GPM TR
13 | 1.1 | Ceiling Suspended Type
14 | 1.1.1 | 3400 CMH(2000 CFM)at 20 mm External Static Pressure, 6 RD Cooling Coil, Approx 5 TR, 1 x 0.75 KW Motor | Nos | 1
[8 empty] | 0.75 | 0.75
[8 empty] | Total | 0.75
15 | 1.1.2 | 5100 CMH(3500 CFM)at 25 mm External Static Pressure, 6 RD Cooling Coil, Approx 7 TR, 1 x 2.25 KW Motor | Nos | 1
[8 empty] | 0.7 | 0.7
[8 empty] | Total | 0.7
16 | 1.1.3 | 10200 CMH(6000 CFM)at 25 mm External Static Pressure, 6 RD Cooling Coil, Approx 12 TR, 1 x 3.75 KW Motor | Nos | 1
[8 empty] | 0.7 | 0.7
[8 empty] | Total | 0.7
17 | 1.2 | Digital Heating Cooling Thermostat for Air Handling Units | Nos. | 3
[8 empty] | Total | 0
18 | 2.0 | Kitchen Scrubber (Dry Type) (Ceiling Suspended Type)
19 | 3.1 | Installation, Testing and Commissioning of Dry Type Scrubber each comprising of extract air intake section, electrostatic precipitation technology, dry type air cleaner to remove oil, smoke and fumes from exhaust air, as per the Specifications. Electrostatic section shall be made of 16 gauge galvanised sheet, high bake epoxy powder coated, washable type aluminium mesh filters, stainless steel spiked ionizers to create high voltage DC field, aluminum collector plates which should be alternatively charged positive and negative with large collecting area with 14 deep cell, to work as magnet for charged smoke and oil particles. Average efficiency of 90-95% in single pass as per ASHRAE test method. Electrostatic Precipitator should be able to charge particles from 0.01 micron to 10 microns through solid state power supply. Collector cell should be of permanent type and incorporate slide out facility for easy removal for cleaning. Power supplies shall be 100% solid state UL Listed, Module of capacity above 3000 CFM shall be equipped with Pulse width modulating (PWM)
20 |  | The system should be fitted with interlock switch for safety . The system should allow connection to a fan section to achieve 500 FPM velocity across the air
21 |  | Operating Voltage 220V, 50 Hz
22 |  | Ionizing Voltage 12.5 to 13 KVDC
23 |  | Collector Cell Voltage 6 to 6.5 KVDC
24 |  | Power Consumption Not more than 50W per cell.
25 |  | Capacities 4000 CFM | Nos | 1
0
[8 empty] | Total | 0
High Side - HVAC
26 | 1.0 | Chilled Water Piping with Nitrile Rubber Insulation
27 |  | Supplying, laying fixing, testing and commissioning of MS C class chilled water piping (cut of required length and installed with welded joints. The necessary fittings such as elboues, tees etc. shall all to included in this item). The Insulation shall be Class O nitrile Rubber pre-slit, pipe sleeve upto 100 mm dia and sheet for bigger dia with factory Laminated 7 mill woven glass cloth of thicknesses as specified, with approved adhesive. Manufactured supplied, suitable sized nitrile rubber pipe supports with PUF PIR inserts shall be used. Thermal conductivity should not exceed 0.035 W MK at 0 degree celsius and water vaper resisitance > 7000. Manufactures tapes and adhesive to used only. The pipe supports should also be of nitrile rubber with PUF PIR inserts and are to be installed as per manufacturer s recomendation. The pipe fittings shall be MS. class for pipes upto 150 mm and for 200mm and above, same material of the pipe shall be usee all bends Reducess Tee upto 150 mm shall be factory fabricated ready made MS C class. Note Use proper template for marking block colour Arrows pipe. for supply return.
28 | I | 40mm dia with 32 mm thick insulation with factory Laminated 7 mil glass cloth upper layer | Mtrs. | 50
|  | Rutern & Supply |  |  | 9 |  |  | 2 | 18
[8 empty] | Total | 18
29 | II | 32mm dia with 32 mm thick insulation with factory Laminated 7 mil glass cloth upper layer | Mtrs. | 30
|  | Rutern & Supply |  |  | 14 |  |  | 2 | 28
[8 empty] | Total | 28
30 | 2.0 | Insulated Valves
31 | 2.1 | Dynamic Balancing Valve-PID type
32 |  | Supply installation, testing and commissioning of BMS Compatible electronic self balancing valve with integrated two way modulating control valves in a single body. The actuator shall be capable of accepting 230V 24V 2-10VDC 4-20 mA electrical signed and shall provided similar transduced feed back output singed to control system. The minimum close off pressure of actuator must be 1.5 times shut of head of pump as per Specification of following size. The actuator shall be microprocessor based with self calibration feature. All the valve shall be complete with step down transformers, thermostat, control wiring and probe.
33 | i. | 10-30 USGPM Insulation as per pipes | Nos. | 3
[8 empty] | Total | 0
34 | 2.2 | Manual Butterfly Valves (Insulated)
35 |  | Providing and Fixing of the following valves with PN-16 Ratings complete with flanges nuts bolts gaskets etc. Butterfly valve shall have CI body seal of black nitrile rubber (tight shutoff) S.G. iron disc(nylon coated) PTFE coated shafts etc. as required. These valves should be suitable for flow in either direction and seal in both directions and should be integral moulded design.
36 | 2.2.1 | 40 mm dia -PN16 -- Insulation as per Chilled water pipe | Nos. | 2
[8 empty] | Total | 0
37 | 2.3 | Y- Strainer (Insulated)
38 |  | Providing and Fixing of the insulated Y-Strainer fabricated out of MS with removable bronze screen, 3mm perforation and permanent magnet etc. complete in all respect and as per specifications and drawings.
39 | 2.3.1 | 40 mm dia -PN16 -- Insulation as per Chilled water pipe | Nos. | 2
[8 empty] | Total | 0
40 | 2.4 | Ball Valve with Stariner (Insulated)
41 |  | Providing and Fixing of the following valves with PN-16 Ratings complete as per specifications.
42 | 2.4.1 | 32 mm dia -PN16 -- Insulation as per Chilled water pipe | Nos. | 2
[8 empty] | Total | 0
43 | 2.5 | Ball Valve without Stariner (Insulated)
44 |  | Providing and Fixing of the following valves with PN-16 Ratings complete as per specifications.
45 | 2.5.1 | 32 mm dia -PN16 -- Insulation as per Chilled water pipe | Nos. | 2
[8 empty] | Total | 0
46 | 2.6 | Providing and Fixing digital type thermometers with copper well, valve probe suitable for binder test point application.
47 | 2.7.1 | 12 long (Insulated) | Nos. | 6
[8 empty] | Total | 0
48 | 2.8 | Dial Presure Guages (glycerine filled Type) with SS Encasing with isolating valve piping etc.The gauge should be with appropriate range and valve and fitted with probe suitable for binder test point application as well.
49 | 2.8.1 | 6 Dial (Insulated) | Nos. | 6
[8 empty] | Total | 0
50 | 2.9 | Providing and Fixing of automatic air vent of approved make with insulation valves as per specifications drawings
51 | 2.9.1 | 20mm dia | Nos. | 10
[8 empty] | Total | 0
52 | 3.0 | Drain Piping
53 |  | Supply, Installation, testing and commissioning of UPVC condensate drain pipe along with necessary clamps, fittings sich as bends, tees, etc. it shall be insulated with 9 mm thick nitrile foam insulation in tubular form as per specifications.
54 | 3.1 | 25 mm dia | Mtrs. | 10
[8 empty] | Total | 0
55 | 3.2 | 20 mm dia | Mtrs. | 20
[8 empty] | Total | 0
56 | 4.0 | DUCTING
57 | 4.1 | G.I. Sheet Metal Ducting - Factory Fabricated
58 |  | Installation, Testing and Commissioning of factory fabricated GSS sheet metal rectangular ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
59 | 4.1.1 | 0.50 MM (26 Gauge) | Sqm. | 30
| 1 | AHU 12 TR 6000 CFM
Line - 1
|  | Droper No -1 |  |  | 1.1 | 1 |  | 2 | 2.2
[5 empty] | 1.1 | 0.25 |  | 2 | 0.55
|  | Droper No -2 |  |  | 0.6 | 0.7 |  | 2 | 0.84
[5 empty] | 0.6 | 0.25 |  | 2 | 0.3
|  | Droper No -3 |  |  | 0.6 | 0.7 |  | 2 | 0.84
[5 empty] | 0.6 | 0.25 |  | 2 | 0.3
|  | Line- 2, Droper |  |  | 1.1 | 1 |  | 2 | 2.2
[5 empty] | 1.1 | 0.25 |  | 2 | 0.55
Line - 3
|  | Droper No -1 |  |  | 0.7 | 0.9 |  | 2 | 1.26
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
|  | Droper No -2 |  |  | 0.7 | 0.9 |  | 2 | 1.26
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
|  | Droper No -3 |  |  | 0.7 | 0.9 |  | 2 | 1.26
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
Line - 4
|  | Droper No -1 |  |  | 1.7 | 1 |  | 2 | 3.4
[5 empty] | 1.7 | 0.4 |  | 2 | 1.36
|  | Droper No -2 |  |  | 1.7 | 1 |  | 2 | 3.4
[5 empty] | 1.7 | 0.4 |  | 2 | 1.36
|  | Droper No -3 |  |  | 1.7 | 1 |  | 2 | 3.4
[5 empty] | 1.7 | 0.4 |  | 2 | 1.36
[8 empty] | Total | 26.68
60 | 4.1.2 | 0.63 MM (24 Gauge) | Sqm. | 130
| 1 | AHU 12 TR 6000 CFM
|  | Line 1 (Duct 3- 300*250) |  |  | 4.2 | 0.3 |  | 2 | 2.52
[5 empty] | 4.2 | 0.25 |  | 2 | 2.1
|  | Line 2 (Duct 4 - 250*250) |  |  | 1.4 | 0.25 |  | 2 | 0.7
[5 empty] | 1.4 | 0.25 |  | 2 | 0.7
|  | Line 3 (Duct 3 - 300*400) |  |  | 4.2 | 0.3 |  | 2 | 2.52
[5 empty] | 4.2 | 0.4 |  | 2 | 3.36
|  | Line 3 (Duct 4 - 300*400) |  |  | 0.4 | 0.3 |  | 2 | 0.24
[5 empty] | 0.4 | 0.4 |  | 2 | 0.32
|  | Line 3 (Duct 5 - 300*200) |  |  | 2.4 | 0.3 |  | 2 | 1.44
[5 empty] | 2.4 | 0.2 |  | 2 | 0.96
|  | Line 4 (Duct 3 - 700*400) |  |  | 0.9 | 0.7 |  | 2 | 1.26
[5 empty] | 0.9 | 0.4 |  | 2 | 0.72
|  | Line 4 (Duct 4 - 700*400) |  |  | 4 | 0.7 |  | 2 | 5.6
[5 empty] | 4 | 0.4 |  | 2 | 3.2
|  | Line 5 (Duct 1 - 300*400) |  |  | 0.3 | 0.3 |  | 2 | 0.18
[5 empty] | 0.3 | 0.4 |  | 2 | 0.24
|  | Line 5 (Duct 2 - 500*400) |  |  | 0.7 | 0.5 |  | 2 | 0.7
[5 empty] | 0.7 | 0.4 |  | 2 | 0.56
|  | Line 5 (Duct 3 - 500*400) |  |  | 1.6 | 0.5 |  | 2 | 1.6
[5 empty] | 1.6 | 0.4 |  | 2 | 1.28
|  | Line 5 (Duct 4 - 500*400) |  |  | 1 | 0.5 |  | 2 | 1
[5 empty] | 1 | 0.4 |  | 2 | 0.8
|  | Line 5 (Duct 5 - 500*400) |  |  | 4.5 | 0.5 |  | 2 | 4.5
[5 empty] | 4.5 | 0.4 |  | 2 | 3.6
|  | Line 5 (Duct 6 - 500*400) |  |  | 0.5 | 0.5 |  | 2 | 0.5
[5 empty] | 0.5 | 0.4 |  | 2 | 0.4
|  | Line 5 (Duct 7 - 500*400) |  |  | 8 | 0.5 |  | 2 | 8
[5 empty] | 8 | 0.4 |  | 2 | 6.4
|  | Line 5 (Duct 8 - 900*400) |  |  | 0.9 | 0.5 |  | 2 | 0.9
[5 empty] | 0.9 | 0.4 |  | 2 | 0.72
Line - 5
|  | Droper No -1 |  |  | 0.7 | 0.9 |  | 2 | 1.26
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
|  | Droper No -2 |  |  | 0.7 | 0.9 |  | 2 | 1.26
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
|  | Droper No -3 |  |  | 0.7 | 0.9 |  | 2 | 1.26
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
|  | Droper No -4 |  |  | 0.7 | 0.9 |  | 2 | 1.26
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
| 2 | AHU 5 TR 2000 CFM
|  | Line 1 (Duct 4- 600*300) |  |  | 0.8 | 0.6 |  | 2 | 0.96
[5 empty] | 0.8 | 0.3 |  | 2 | 0.48
|  | Line 1 (Duct 5- 600*300) |  |  | 2.6 | 0.6 |  | 2 | 3.12
[5 empty] | 2.6 | 0.3 |  | 2 | 1.56
|  | Line 1 (Duct 6- 600*300) |  |  | 0.6 | 0.6 |  | 2 | 0.72
[5 empty] | 0.6 | 0.3 |  | 2 | 0.36
|  | Line 1 (Duct 7- 400*300) |  |  | 3.9 | 0.4 |  | 2 | 3.12
[5 empty] | 3.9 | 0.3 |  | 2 | 2.34
Line - 1
|  | Droper No -1 |  |  | 0.7 | 0.5 |  | 2 | 0.7
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
|  | Droper No -2 |  |  | 0.7 | 0.5 |  | 2 | 0.7
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
|  | Droper No -3 |  |  | 0.7 | 0.5 |  | 2 | 0.7
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
|  | Droper No -4 |  |  | 0.7 | 0.5 |  | 2 | 0.7
[5 empty] | 0.7 | 0.2 |  | 2 | 0.28
| 3 | AHU 7 TR 3000 CFM
|  | Line 3 (Duct 3 - 600*400) |  |  | 1.1 | 0.6 |  | 2 | 1.32
[5 empty] | 1.1 | 0.3 |  | 2 | 0.66
|  | Line 3 (Duct 4 - 600*400) |  |  | 0.75 | 0.6 |  | 2 | 0.9
[5 empty] | 0.75 | 0.3 |  | 2 | 0.45
|  | Line 3 (Duct 5 - 600*400) |  |  | 1.9 | 0.6 |  | 2 | 2.28
[5 empty] | 1.9 | 0.3 |  | 2 | 1.14
|  | Line 3 (Duct 6 - 600*400) |  |  | 0.8 | 0.6 |  | 2 | 0.96
[5 empty] | 0.8 | 0.3 |  | 2 | 0.48
|  | Line 3 (Duct 7 - 350*300) |  |  | 2.5 | 0.35 |  | 2 | 1.75
[5 empty] | 2.5 | 0.3 |  | 2 | 1.5
|  | Line 1 / Droper No - 1 |  |  | 1 | 0.5 |  | 2 | 1
[5 empty] | 1 | 0.2 |  | 2 | 0.4
|  | Line 2 / Droper No - 1 |  |  | 1 | 0.5 |  | 2 | 1
[5 empty] | 1 | 0.2 |  | 2 | 0.4
Line 3 /Droper No. 1
|  | Duct 1 (900*300) |  |  | 0.2 | 0.9 |  | 2 | 0.36
[5 empty] | 0.2 | 0.3 |  | 2 | 0.12
|  | Duct 2 (900*300) |  |  | 0.5 | 0.9 |  | 2 | 0.9
[5 empty] | 0.5 | 0.3 |  | 2 | 0.3
|  | Duct 3 (900*300) |  |  | 1.5 | 0.9 |  | 2 | 2.7
[5 empty] | 1.5 | 0.3 |  | 2 | 0.9
|  | Duct 4 (900*300) |  |  | 0.6 | 0.9 |  | 2 | 1.08
[5 empty] | 0.6 | 0.3 |  | 2 | 0.36
Line 3 /Droper No. 2
|  | Duct 1 (900*300) |  |  | 0.2 | 0.9 |  | 2 | 0.36
[5 empty] | 0.2 | 0.3 |  | 2 | 0.12
|  | Duct 2 (900*300) |  |  | 0.5 | 0.9 |  | 2 | 0.9
[5 empty] | 0.5 | 0.3 |  | 2 | 0.3
|  | Duct 3 (900*300) |  |  | 1.5 | 0.9 |  | 2 | 2.7
[5 empty] | 1.5 | 0.3 |  | 2 | 0.9
|  | Duct 4 (900*300) |  |  | 0.6 | 0.9 |  | 2 | 1.08
[5 empty] | 0.6 | 0.3 |  | 2 | 0.36
| 4 | 3500 CFM
|  | Duct 1 (650*350) |  |  | 5.4 | 0.65 |  | 2 | 7.02
[5 empty] | 5.4 | 0.35 |  | 2 | 3.78
|  | Duct 2 (650*350) |  |  | 1.4 | 0.65 |  | 2 | 1.82
[5 empty] | 1.4 | 0.35 |  | 2 | 0.98
[8 empty] | Total | 121.04
61 | 4.1.3 | 0.80 MM (22 Gauge) | Sqm. | 75
| 1 | AHU 12 TR 6000 CFM
|  | Line 1 (Duct 1- 450*250) |  |  | 1.5 | 0.45 |  | 2 | 1.35
[5 empty] | 1.5 | 0.25 |  | 2 | 0.75
|  | Line 1 (Duct 2- 450*250) |  |  | 0.5 | 0.45 |  | 2 | 0.45
[5 empty] | 0.5 | 0.25 |  | 2 | 0.25
|  | Line 3 (Duct 1 - 950*400) |  |  | 8 | 0.95 |  | 2 | 15.2
[5 empty] | 8 | 0.4 |  | 2 | 6.4
|  | Line 3 (Duct 2 - 300*400) |  |  | 9 | 0.3 |  | 2 | 5.4
[5 empty] | 9 | 0.4 |  | 2 | 7.2
|  | Line 4 (Duct 1 - 700*400) |  |  | 0.6 | 0.7 |  | 2 | 0.84
[5 empty] | 0.6 | 0.4 |  | 2 | 0.48
|  | Line 4 (Duct 2 - 700*400) |  |  | 1.6 | 0.7 |  | 2 | 2.24
[5 empty] | 1.6 | 0.4 |  | 2 | 1.28
| 2 | AHU 5 TR 2000 CFM
|  | Line 1 (Duct 1- 600*300) |  |  | 0.7 | 0.6 |  | 2 | 0.84
[5 empty] | 0.7 | 0.3 |  | 2 | 0.42
|  | Line 1 (Duct 2- 600*300) |  |  | 2 | 0.6 |  | 2 | 2.4
[5 empty] | 2 | 0.3 |  | 2 | 1.2
|  | Line 1 (Duct 3- 600*300) |  |  | 0.7 | 0.6 |  | 2 | 0.84
[5 empty] | 0.7 | 0.3 |  | 2 | 0.42
| 3 | AHU 7 TR 3000 CFM
|  | Line 1 (Duct 1- 350*300) |  |  | 1.8 | 0.35 |  | 2 | 1.26
[5 empty] | 1.8 | 0.3 |  | 2 | 1.08
|  | Line 1 (Duct 2- 350*300) |  |  | 0.8 | 0.35 |  | 2 | 0.56
[5 empty] | 0.8 | 0.3 |  | 2 | 0.48
|  | Line 2 (Duct 1- 300*250) |  |  | 0.2 | 0.3 |  | 2 | 0.12
[5 empty] | 0.2 | 0.25 |  | 2 | 0.1
|  | Line 2 (Duct 2- 300*250) |  |  | 2.3 | 0.3 |  | 2 | 1.38
[5 empty] | 2.3 | 0.25 |  | 2 | 1.15
|  | Line 3 (Duct 1 - 600*300) |  |  | 0.8 | 0.6 |  | 2 | 0.96
[5 empty] | 0.8 | 0.3 |  | 2 | 0.48
|  | Line 3 (Duct 2 - 600*300) |  |  | 0.75 | 0.6 |  | 2 | 0.9
[5 empty] | 0.75 | 0.3 |  | 2 | 0.45
| 4 | 3500 CFM
|  | Duct 3 (650*350) |  |  | 8.5 | 0.65 |  | 2 | 11.05
[5 empty] | 8.5 | 0.35 |  | 2 | 5.95
[8 empty] | Total | 73.88
62 | 4.1.4 | 1.00 MM (20 Gauge) | Sqm. | 10
| 1 | Plenum AHU 12 TR 6000 CFM (1000*1800*750) |  |  | 0.9 |  | 0.7 | 2 | 1.26
[5 empty] | 1.8 |  | 0.7 | 2 | 2.52
| 2 | Plenum AHU 5 TR 2000 CFM
| 3 | Plenum AHU 7 TR 3000 CFM (1500*1200*750) |  |  | 1.5 |  | 0.7 | 2 | 2.1
[5 empty] | 1.2 |  | 0.7 | 2 | 1.68
|  | Plenum 1 (300*750*400) |  |  | 0.3 |  | 0.75 | 2 | 0.45
[5 empty] | 0.3 |  | 0.4 | 2 | 0.24
|  | Plenum 2 (300*750*400) |  |  | 0.3 |  | 0.75 | 2 | 0.45
[5 empty] | 0.3 |  | 0.4 | 2 | 0.24
[8 empty] | Total | 8.94
63 | 4.1.5 | 1.25 MM (18 Gauge) | Sqm. | 0
64 | 4.1.6 | 1.00 MM (20 Gauge)- Kitchen Exhaust Ducting with 25 mm thick high density of glasswool rockwool insulation of density 48kg m3 . The insulation shall be covered with muslin cloth over which 2 coats of Starbond approved fire paint is applied to make the insulation hard and fire retardant . | Sqm. | 110
|  | Duct 4 (750*400) |  |  | 1.2 | 0.75 |  | 2 | 1.8
[5 empty] | 1.2 | 0.4 |  | 2 | 0.96
|  | Duct 5 (750*400) |  |  | 9 | 0.75 |  | 2 | 13.5
[5 empty] | 9 | 0.4 |  | 2 | 7.2
|  | Duct 6 (750*400) |  |  | 1.1 | 0.75 |  | 2 | 1.65
[5 empty] | 1.1 | 0.4 |  | 2 | 0.88
|  | Duct 7 (750*400) |  |  | 5.6 | 0.75 |  | 2 | 8.4
[5 empty] | 5.6 | 0.4 |  | 2 | 4.48
|  | Duct 8 (750*400) |  |  | 0.75 | 0.75 |  | 2 | 1.125
[5 empty] | 0.75 | 0.4 |  | 2 | 0.6
|  | Duct 11 (450*350) |  |  | 1.4 | 0.45 |  | 2 | 1.26
[5 empty] | 1.4 | 0.35 |  | 2 | 0.98
[8 empty] | Total | 42.835
65 | 4.2 | G.I. Sheet Metal Ducting - Site Fabricated
66 |  | Installation, Testing and Commissioning of site fabricated GSS sheet metal rectangular ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
67 | 4.2.1 | 0.63 MM (24 Gauge) | Sqm. | 20
[8 empty] | Total | 0
68 | 4.2.2 | 0.80 MM (22 Gauge) | Sqm. | 20
|  | Duct 1 (750*400) |  |  | 1 | 0.75 |  | 2 | 1.5
[5 empty] | 1 | 0.4 |  | 2 | 0.8
|  | Duct 2 (750*400) |  |  | 1.1 | 0.75 |  | 2 | 1.65
[5 empty] | 1.1 | 0.4 |  | 2 | 0.88
|  | Duct 3 (750*400) |  |  | 2.51 | 0.75 |  | 2 | 3.765
[5 empty] | 2.51 | 0.4 |  | 2 | 2.008
|  | Duct 9 (650*350) |  |  | 4 | 0.65 |  | 2 | 5.2
[5 empty] | 4 | 0.35 |  | 2 | 2.8
|  | Duct 10 (650*350) |  |  | 0.7 | 0.65 |  | 2 | 0.91
[5 empty] | 0.7 | 0.35 |  | 2 | 0.49
[8 empty] | Total | 20.003
69 | 4.2.3 | 1.00 MM (20 Gauge) | Sqm. | 5
|  | Plenum Box |  |  | 1.6 | 0.89 |  | 2 | 2.848
|  | Dry Scruber |  |  | 1.6 | 0.6 |  | 2 | 1.92
|  | Plenum Box |  |  | 1.6 | 0.6 |  | 2 | 1.92
|  | Less Overrun Qty | [6 empty] | -1.688
[8 empty] | Total | 5
70 | 4.2.4 | 1.25 MM (18 Gauge) | Sqm. | 0
71 | 4.3 | Ducting (Exhaust)- MS Welded Construction- Site Fabricated
72 |  | Supply, fabrication and erection of following gauges of MS ducting complete with welded drip proof seams and having access doors at every change in direction with maximum spacing of 6 meters in horizontal direction and maximun of 3 floors of vertical risers elbows spliters, supports suspenders bends, tees, vanes, double canvas connection of the equipment etc all complete as required. Duct shall be insulated 25 MM Thich High Density Rockwool Insulation 48 KG m3 . The insulation material and its installation shall be in accordance with the specifications as provided. The entire insulation shall be covered with muslin cloth over which 2 coats of Star Bond approved fire paint is applied to make the insulation hard and fire retardant.
73 | 4.3.1 | 16 gauge (1.5 mm thick) | Sqm. | 0
74 | 4.4 | Flexible Duct
75 | 4.4.1 | 100 MM Dia | RM | 0
76 | 5.0 | INSULATION
77 | 5.1 | Nitrile Rubber Insulation- Class O
78 |  | Supplying and fixing of closed cell elastomeric insulation of density 55 kg cu.m.and K valueof not less than 0.037W mk at 20 deg C as per specifications and drawings (For indoor applications) with factory Laminated 7 mill woven glass cloth
79 | 5.1.1 | 19 mm thick (AC ducts Fresh Air Duct) | Sqm. | 260
| 1 | AHU 17 TR 6000 CFM
Line - 1
|  | Droper No -1 |  |  | 1.1 | 1.25 |  | 2 | 2.75
[5 empty] | 1.1 | 0.275 |  | 2 | 0.605
|  | Droper No -2 |  |  | 0.6 | 0.725 |  | 2 | 0.87
[5 empty] | 0.6 | 0.25 |  | 2 | 0.3
|  | Droper No -3 |  |  | 0.6 | 0.725 |  | 2 | 0.87
[5 empty] | 0.6 | 0.25 |  | 2 | 0.3
|  | Line- 2, Droper |  |  | 1.1 | 1.25 |  | 2 | 2.75
[5 empty] | 1.1 | 0.275 |  | 2 | 0.605
Line - 3
|  | Droper No -1 |  |  | 0.7 | 0.925 |  | 2 | 1.295
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
|  | Droper No -2 |  |  | 0.7 | 0.925 |  | 2 | 1.295
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
|  | Droper No -3 |  |  | 0.7 | 0.925 |  | 2 | 1.295
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
Line - 4
|  | Droper No -1 |  |  | 1.7 | 1.25 |  | 2 | 4.25
[5 empty] | 1.7 | 0.425 |  | 2 | 1.445
|  | Droper No -2 |  |  | 1.7 | 1.25 |  | 2 | 4.25
[5 empty] | 1.7 | 0.425 |  | 2 | 1.445
|  | Droper No -3 |  |  | 1.7 | 1.25 |  | 2 | 4.25
[5 empty] | 1.7 | 0.425 |  | 2 | 1.445
| 1 | AHU 17 TR 6000 CFM
|  | Line 1 (Duct 3- 300*250) |  |  | 4.2 | 0.325 |  | 2 | 2.73
[5 empty] | 4.2 | 0.275 |  | 2 | 2.31
|  | Line 2 (Duct 4 - 250*250) |  |  | 1.4 | 0.275 |  | 2 | 0.77
[5 empty] | 1.4 | 0.275 |  | 2 | 0.77
|  | Line 3 (Duct 3 - 300*400) |  |  | 4.2 | 0.325 |  | 2 | 2.73
[5 empty] | 4.2 | 0.425 |  | 2 | 3.57
|  | Line 3 (Duct 4 - 300*400) |  |  | 0.4 | 0.325 |  | 2 | 0.26
[5 empty] | 0.4 | 0.425 |  | 2 | 0.34
|  | Line 3 (Duct 5 - 300*200) |  |  | 2.4 | 0.325 |  | 2 | 1.56
[5 empty] | 2.4 | 0.225 |  | 2 | 1.08
|  | Line 4 (Duct 3 - 700*400) |  |  | 0.9 | 0.725 |  | 2 | 1.305
[5 empty] | 0.9 | 0.425 |  | 2 | 0.765
|  | Line 4 (Duct 4 - 700*400) |  |  | 4 | 0.725 |  | 2 | 5.8
[5 empty] | 4 | 0.425 |  | 2 | 3.4
|  | Line 5 (Duct 1 - 300*400) |  |  | 0.3 | 0.325 |  | 2 | 0.195
[5 empty] | 0.3 | 0.425 |  | 2 | 0.255
|  | Line 5 (Duct 2 - 500*400) |  |  | 0.7 | 0.525 |  | 2 | 0.735
[5 empty] | 0.7 | 0.425 |  | 2 | 0.595
|  | Line 5 (Duct 3 - 500*400) |  |  | 1.6 | 0.525 |  | 2 | 1.68
[5 empty] | 1.6 | 0.425 |  | 2 | 1.36
|  | Line 5 (Duct 4 - 500*400) |  |  | 1 | 0.525 |  | 2 | 1.05
[5 empty] | 1 | 0.425 |  | 2 | 0.85
|  | Line 5 (Duct 5 - 500*400) |  |  | 4.5 | 0.525 |  | 2 | 4.725
[5 empty] | 4.5 | 0.425 |  | 2 | 3.825
|  | Line 5 (Duct 6 - 500*400) |  |  | 0.5 | 0.525 |  | 2 | 0.525
[5 empty] | 0.5 | 0.425 |  | 2 | 0.425
|  | Line 5 (Duct 7 - 500*400) |  |  | 8 | 0.525 |  | 2 | 8.4
[5 empty] | 8 | 0.425 |  | 2 | 6.8
|  | Line 5 (Duct 8 - 900*400) |  |  | 0.9 | 0.925 |  | 2 | 1.665
[5 empty] | 0.9 | 0.425 |  | 2 | 0.765
Line - 5
|  | Droper No -1 |  |  | 0.7 | 0.925 |  | 2 | 1.295
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
|  | Droper No -2 |  |  | 0.7 | 0.925 |  | 2 | 1.295
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
|  | Droper No -3 |  |  | 0.7 | 0.925 |  | 2 | 1.295
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
|  | Droper No -4 |  |  | 0.7 | 0.925 |  | 2 | 1.295
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
| 2 | AHU 5 TR 2000 CFM
|  | Line 1 (Duct 4- 600*300) |  |  | 0.8 | 0.625 |  | 2 | 1
[5 empty] | 0.8 | 0.325 |  | 2 | 0.52
|  | Line 1 (Duct 5- 600*300) |  |  | 2.6 | 0.625 |  | 2 | 3.25
[5 empty] | 2.6 | 0.325 |  | 2 | 1.69
|  | Line 1 (Duct 6- 600*300) |  |  | 0.6 | 0.625 |  | 2 | 0.75
[5 empty] | 0.6 | 0.325 |  | 2 | 0.39
|  | Line 1 (Duct 7- 400*300) |  |  | 3.9 | 0.425 |  | 2 | 3.315
[5 empty] | 3.9 | 0.325 |  | 2 | 2.535
Line - 1
|  | Droper No -1 |  |  | 0.7 | 0.525 |  | 2 | 0.735
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
|  | Droper No -2 |  |  | 0.7 | 0.525 |  | 2 | 0.735
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
|  | Droper No -3 |  |  | 0.7 | 0.525 |  | 2 | 0.735
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
|  | Droper No -4 |  |  | 0.7 | 0.525 |  | 2 | 0.735
[5 empty] | 0.7 | 0.225 |  | 2 | 0.315
| 3 | AHU 7 TR 3000 CFM
|  | Line 3 (Duct 3 - 600*400) |  |  | 1.1 | 0.625 |  | 2 | 1.375
[5 empty] | 1.1 | 0.425 |  | 2 | 0.935
|  | Line 3 (Duct 4 - 600*400) |  |  | 0.75 | 0.625 |  | 2 | 0.9375
[5 empty] | 0.75 | 0.425 |  | 2 | 0.6375
|  | Line 3 (Duct 5 - 600*400) |  |  | 1.9 | 0.625 |  | 2 | 2.375
[5 empty] | 1.9 | 0.425 |  | 2 | 1.615
|  | Line 3 (Duct 6 - 600*400) |  |  | 0.8 | 0.625 |  | 2 | 1
[5 empty] | 0.8 | 0.425 |  | 2 | 0.68
|  | Line 3 (Duct 7 - 350*300) |  |  | 2.5 | 0.375 |  | 2 | 1.875
[5 empty] | 2.5 | 0.325 |  | 2 | 1.625
|  | Line 1 / Droper No - 1 |  |  | 1 | 0.525 |  | 2 | 1.05
[5 empty] | 1 | 0.225 |  | 2 | 0.45
|  | Line 2 / Droper No - 1 |  |  | 1 | 0.525 |  | 2 | 1.05
[5 empty] | 1 | 0.225 |  | 2 | 0.45
Line 3 /Droper No. 1
|  | Duct 1 (900*300) |  |  | 0.2 | 0.925 |  | 2 | 0.37
[5 empty] | 0.2 | 0.325 |  | 2 | 0.13
|  | Duct 2 (900*300) |  |  | 0.5 | 0.925 |  | 2 | 0.925
[5 empty] | 0.5 | 0.325 |  | 2 | 0.325
|  | Duct 3 (900*300) |  |  | 1.5 | 0.925 |  | 2 | 2.775
[5 empty] | 1.5 | 0.325 |  | 2 | 0.975
|  | Duct 4 (900*300) |  |  | 0.6 | 0.925 |  | 2 | 1.11
[5 empty] | 0.6 | 0.325 |  | 2 | 0.39
Line 3 /Droper No. 2
|  | Duct 1 (900*300) |  |  | 0.2 | 0.925 |  | 2 | 0.37
[5 empty] | 0.2 | 0.325 |  | 2 | 0.13
|  | Duct 2 (900*300) |  |  | 0.5 | 0.925 |  | 2 | 0.925
[5 empty] | 0.5 | 0.325 |  | 2 | 0.325
|  | Duct 3 (900*300) |  |  | 1.5 | 0.925 |  | 2 | 2.775
[5 empty] | 1.5 | 0.325 |  | 2 | 0.975
|  | Duct 4 (900*300) |  |  | 0.6 | 0.925 |  | 2 | 1.11
[5 empty] | 0.6 | 0.325 |  | 2 | 0.39
| 4 | 3500 CFM
|  | Duct 1 (650*350) |  |  | 5.4 | 0.675 |  | 2 | 7.29
[5 empty] | 5.4 | 0.375 |  | 2 | 4.05
|  | Duct 2 (650*350) |  |  | 1.4 | 0.675 |  | 2 | 1.89
[5 empty] | 1.4 | 0.375 |  | 2 | 1.05
| 1 | AHU 17 TR 6000 CFM
|  | Line 1 (Duct 1- 450*250) |  |  | 1.5 | 0.475 |  | 2 | 1.425
[5 empty] | 1.5 | 0.275 |  | 2 | 0.825
|  | Line 1 (Duct 2- 450*250) |  |  | 0.5 | 0.475 |  | 2 | 0.475
[5 empty] | 0.5 | 0.275 |  | 2 | 0.275
|  | Line 3 (Duct 1 - 950*400) |  |  | 8 | 0.975 |  | 2 | 15.6
[5 empty] | 8 | 0.425 |  | 2 | 6.8
|  | Line 3 (Duct 2 - 300*400) |  |  | 9 | 0.325 |  | 2 | 5.85
[5 empty] | 9 | 0.425 |  | 2 | 7.65
|  | Line 4 (Duct 1 - 700*400) |  |  | 0.6 | 0.725 |  | 2 | 0.87
[5 empty] | 0.6 | 0.425 |  | 2 | 0.51
|  | Line 4 (Duct 2 - 700*400) |  |  | 1.6 | 0.725 |  | 2 | 2.32
[5 empty] | 1.6 | 0.425 |  | 2 | 1.36
| 2 | AHU 5 TR 2000 CFM
|  | Line 1 (Duct 1- 600*300) |  |  | 0.7 | 0.625 |  | 2 | 0.875
[5 empty] | 0.7 | 0.325 |  | 2 | 0.455
|  | Line 1 (Duct 2- 600*300) |  |  | 2 | 0.625 |  | 2 | 2.5
[5 empty] | 2 | 0.325 |  | 2 | 1.3
|  | Line 1 (Duct 3- 600*300) |  |  | 0.7 | 0.625 |  | 2 | 0.875
[5 empty] | 0.7 | 0.325 |  | 2 | 0.455
| 3 | AHU 7 TR 3000 CFM
|  | Line 1 (Duct 1- 350*300) |  |  | 1.8 | 0.375 |  | 2 | 1.35
[5 empty] | 1.8 | 0.325 |  | 2 | 1.17
|  | Line 1 (Duct 2- 350*300) |  |  | 0.8 | 0.375 |  | 2 | 0.6
[5 empty] | 0.8 | 0.325 |  | 2 | 0.52
|  | Line 2 (Duct 1- 300*250) |  |  | 0.2 | 0.325 |  | 2 | 0.13
[5 empty] | 0.2 | 0.275 |  | 2 | 0.11
|  | Line 2 (Duct 2- 300*250) |  |  | 2.3 | 0.325 |  | 2 | 1.495
[5 empty] | 2.3 | 0.275 |  | 2 | 1.265
|  | Line 3 (Duct 1 - 600*300) |  |  | 0.8 | 0.625 |  | 2 | 1
[5 empty] | 0.8 | 0.325 |  | 2 | 0.52
|  | Line 3 (Duct 2 - 600*300) |  |  | 0.75 | 0.625 |  | 2 | 0.9375
[5 empty] | 0.75 | 0.325 |  | 2 | 0.4875
| 4 | 3500 CFM
|  | Duct 3 (650*350) |  |  | 8.5 | 0.675 |  | 2 | 11.475
[5 empty] | 8.5 | 0.375 |  | 2 | 6.375
| 1 | Plenum AHU 17 TR 6000 CFM (1000*1800*750) |  |  | 0.9 |  | 0.725 | 2 | 1.305
[5 empty] | 1.8 |  | 0.725 | 2 | 2.61
| 2 | Plenum AHU 5 TR 2000 CFM
| 3 | Plenum AHU 7 TR 3000 CFM (1500*1200*750) |  |  | 1.5 |  | 0.725 | 2 | 2.175
[5 empty] | 1.2 |  | 0.725 | 2 | 1.74
|  | Plenum 1 (300*750*400) |  |  | 0.3 |  | 0.775 | 2 | 0.465
[5 empty] | 0.3 |  | 0.425 | 2 | 0.255
|  | Plenum 2 (300*750*400) |  |  | 0.3 |  | 0.775 | 2 | 0.465
[5 empty] | 0.3 |  | 0.425 | 2 | 0.255
[8 empty] | Total | 247.755
80 | 5.2 | Acoustic Lining
81 |  | Supplying and Application of Acoustic lining within the Supply Air duct with 15 mm thick class O open cell nitrile Rubber of density 140-160 kg. Cubm. as per spefications.
82 | 5.2.1 | 15 MM Thick | Sqm | 30
[8 empty] | Total | 0
83 | 6.0 | DUCT ACCESSORIES
84 | 6.1 | Supply, Installation, Testing and Commissioning of GI multiblade volume control duct damper complete with neoprene rubber gaskets, nuts, bolts, screws linkages, flanges etc., as per specifications. | Sqm. | 2
[8 empty] | Total | 0
85 | 6.2 | Supply, Installation, Testing and Commissioning of multiblade Al volume control Collar Grille exhaust Air Opening damper complete with suitable links, lever and quadrants for manual control of airflow and with suitable links , lever and quadrants for manual control of airflow and neoprene rubber gaskets, nuts, bolts, screws, flanges etc., as per specifications. | Sqm. | 3
[8 empty] | Total | 0
86 | 6.3 | Supply, Installation, Testing and Commissioning fixing of powder coated extruded aluminium Supply Exhaust Air Grills as per specifications | Sqm. | 2
[8 empty] | Total | 0
87 | 6.6 | Supply, Installation, Testing and Commissioning fixing of powder coated extruded Aluminium Continuous Grille as per specifications
88 | 6.6.2 | 150 MM Aluminium Continuos Grille | RM | 5
[8 empty] | Total | 0
89 | 6.6.3 | 100 MM Aluminium Continuos Grille | RM | 30
[8 empty] | Total | 0
90 | 7.0 | Motorised Fire and Smoke Dampers
91 |  | Supply, installation, testing commissioning of motorised fire smoke damper (spring return type) of approved make of atleast 90 min fire rating as per UL555, made out of 16 ga GSS and suitable for duct wall mounting with suitable size 18 Ga Sleeve as per the specification detail given earlier in the relevant section. The damper shall have 90 minute fire rating. It shall be complete with electronic temperature sensor and electrically operated actuator. The fire damper shall be located in supply return air duct and at fire rated crossover. These fire damper shall be interlocaked with BMS system for fire detection and shall trip close in case of fire. Controller for Fire and Smoke Damper with necessary step down transformer , fan interlocking, centralize Fire Alarm panel Integration, Smoke Detector Integration, UL Listed Thermal Cut Off (72 deg C) and remote testing unit for routine testing with spring return motorized assembly shall be suitable to control the mentioned sizes of damper.
92 | 7.1 | Fire Dampers with Factory Fabricated TDC flange. | Sqm. | 0
93 | 7.2 | Motorized Actuators and Modbus Compatible Contoller for motorized dampers | Nos. | 0
94 | 7.3 | Interconnectng wiring for fire alarm system. | Lot. | 0
95 | 7.4 | Loop in and loop out | Lot. | 0
96 | 7.5 | Sealing the openings around the sleeve of fire damper with approved fire sealant as per manufacturer recommendation | Lot. | 0
97 | 11.0 | Louvers
98 | 11.1 | Providing and fixing of powder coated extruded aluminium exhaust air louvers fresh air louvers with bird screen and mounting arrangement as per specification and drawings. Free Area shall be more than 60% of gross area.
99 | 11.1.1 | Fresh Air Exhaust Air Louvers with Bird Screen Mesh | Sqm. | 1
[8 empty] | Total | 0
Low side HVAC
100 | 1 | Providing, Laying, Jointing Testing of Pipes for Sprinkler System - G.I Pipe confirming IS Codes Class `C Heavy Pipe with necessary support anchore fastening from slab.
101 | a. | 25 mm dia | Rmt. | 16
|  | Sprinkler point 7 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 8 |  |  | 2 |  |  | 1 | 2
|  | Sprinkler point 31 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 32 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 33 |  |  | 2 |  |  | 1 | 2
|  | Sprinkler point 34 |  |  | 2 |  |  | 1 | 2
|  | Sprinkler point 35 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 36 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 37 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 38 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 20 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 21 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 22 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 23 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 27to 28 |  |  | 2.5 |  |  | 1 | 2.5
|  | Sprinkler point 28to 30 |  |  | 2.5 |  |  | 1 | 2.5
|  | Sprinkler point 29 |  |  | 1.5 |  |  | 1 | 1.5
|  | Less Overrun Qty | [6 empty] | -13
[8 empty] | Total | 16
102 | b. | 32 mm dia | Rmt. | 12
|  | Sprinkler point 1 to 2 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 2 to 31 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 3 to 4 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 3To32 |  |  | 3 |  |  | 1 | 3
[8 empty] | Total | 12
103 | c. | 40 mm dia | Rmt. | 50
|  | Sprinkler point 5 To 6 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 6 To 7 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 7 To 33 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 34 To 8 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 8 to 9 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 9 to 10 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 11 to 12 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 12 to 13 |  |  | 2.5 |  |  | 1 | 2.5
|  | Sprinkler point 13 to 38 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 38 to 35 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 36 to 37 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 37 to 14 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 14 to 15 |  |  | 2.5 |  |  | 1 | 2.5
|  | Sprinkler point 15 to 16 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 17 to18 |  |  | 1.5 |  |  | 1 | 1.5
|  | Sprinkler point 18 to 19 |  |  | 2.5 |  |  | 1 | 2.5
|  | Sprinkler point 19 to 20 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 20 to 21 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 22 to 23 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 23 to 24 |  |  | 3 |  |  | 1 | 3
|  | Sprinkler point 24 to 25 |  |  | 2.5 |  |  | 1 | 2.5
|  | Sprinkler point 25 to 26 |  |  | 1.5 |  |  | 1 | 1.5
|  | Less Overrun Qty | [6 empty] | -8
[8 empty] | Total | 50
104 | d. | 50 mm dia | Rmt. | 10
|  | Main Heder | [5 empty] | 10 | 10
[8 empty] | Total | 10
105 | e. | 65mm dia | Rmt. | 15
|  | Main Heder | [5 empty] | 14 | 14
[8 empty] | Total | 14
106 | f. | 80mm dia | Rmt. | 0
107 | 2 | Synthetic Enamel Paint.
108 | a. | 25 mm dia | Rmt. | 17
[8 empty] | 29 | 29
|  | Less Overrun Qty | [6 empty] | -12
[8 empty] | Total | 17
109 | b. | 32 mm dia | Rmt. | 12
[8 empty] | 12 | 12
[8 empty] | Total | 12
110 | c. | 40 mm dia | Rmt. | 50
[8 empty] | 58 | 58
|  | Less Overrun Qty | [6 empty] | -8
[8 empty] | Total | 50
111 | d. | 50 mm dia | Rmt. | 10
[8 empty] | 10 | 10
[8 empty] | Total | 10
112 | e. | 65mm dia | Rmt. | 15
[8 empty] | 14 | 14
[8 empty] | Total | 14
113 | f. | 80mm dia | Rmt. | 0
114 | 3 | Providing Fixing of Butterfly Valve.
115 | a. | 50 mm dia | No. | 0
116 | b. | 80 mm dia | No. | 1
[8 empty] | Total | 0
117 | 4 | Providing Fixing of Ball Valve.
118 | a. | 25 mm dia | No. | 0
119 | b. | 32 mm dia | No. | 0
120 | c. | 40 mm dia | No. | 0
121 | d. | 50 mm dia | No. | 0
122 | e. | 65 mm dia | No. | 0
123 | f. | 80 mm dia | No. | 1
[8 empty] | Total | 0
124 | 5 | HEADER FITTING.
125 | a. | Flow Switch | No. | 1
[8 empty] | Total | 0
126 | b | Pressure Gauge | No. | 1
[8 empty] | Total | 0
127 | c | Air Release Valve | No. | 1
[8 empty] | Total | 0
128 | d | 80 mm dia NRV | No. | 1
[8 empty] | Total | 0
129 | 6 | Providing Fixing C.P. Brass 68 degree Quartzoid Bulb Sprinklers. Make Tyco viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed EN approved.
130 | a. | Pendant Type | No. | 30
|  | 1 To 30 | [5 empty] | 30 | 30
[8 empty] | Total | 30
131 | b. | UP Right Type | No. | 30
|  | 1 To 30 | [5 empty] | 30 | 30
[8 empty] | Total | 30
132 | 7 | Providing Fixing C.P. Brass 79 degree(QR) Quartzoid Bulb Sprinklers. Make Tyco viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed EN approved for high temperature area in Kitchen temprating shall be 79degre
133 | a. | Pendant Type | No. | 8
|  | 31 To 38 No. | [5 empty] | 8 | 8
[8 empty] | Total | 8
134 | b. | UP Right Type | No. | 8
|  | 31 To 38 No. | [5 empty] | 8 | 8
[8 empty] | Total | 8
135 | 8 | Flexible Sprinkler Drop.
136 | a. | 25mm | No. | 38
[8 empty] | 38 | 38
[8 empty] | Total | 38
137 | b. | 100mm | No. | 0
138 | c. | 150mm | No. | 0
139 | 9 | Drain Valve | No. | 0
PR for Fire Sprinkler LKN Budweiser bar
140 | 1 | R1 (RESPONSE INDICATORS)
141 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Response indicators are connected to automatic fire detectors in order to indicate quickly the source of an alarm signal from detectors which are not easily accessible or visible. They light up as soon as the connected fire detector gives an alarm.(Wiring from switches to panel and stair case pressurization not included) | Nos | 13
[8 empty] | Total | 0
142 | 2 | HD (HEAT DETECTOR) INSTALL NEAR HOOD
143 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) A heat detector is a fire alarm device designed to respond when the convected thermal energy of a fire increases the temperature of a heat sensitive element. The thermal mass and conductivity of the element regulate the rate flow of heat into the element. All heat detectors have this thermal lag (Wiring from switches to panel and stair case pressurization not included) (Edwards Apollo) | Nos | 1
[8 empty] | Total | 0
144 | 3 | CONVENTIONAL FIRE PANEL | Nos | 0
145 | 4 | MCP (MANUAL CALL POINT)
146 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Manual call points are used to initiate an alarm signal, and operate by means of a simple button press or when glass is broken revealing a button. They can form part of a manual alarm system or an automatic alarm system.Model Edwards Apollo and FM approved with GI mounting Box | Nos | 3
[8 empty] | Total | 0
147 | 5 | H (HOOTER)
148 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Fire Alarm Systems. A fire alarm system is a electrical electronic system which is connected with many type of devices such as main panel, smoke heat detectors, mcp, sounder etc.. to detect the fire event by indiacating audio or visualize signal at the main or individual devices.Model Edwards Apollo with GI mounting Box | Nos | 3
[8 empty] | Total | 0
149 | 6 | SD (SMOKE DETECTOR ABOVE CEILING)
150 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay.Model Edwards Apollo. | NOS | 13
[8 empty] | Total | 0
151 | 7 | SD (SMOKE DETECTOR BELOW CEILING)
152 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model Edwards Apollo. | NOS | 13
[8 empty] | Total | 0
153 | 8 | MSD (MULTI SENSOR DETECTOR BELOW CEILING)
154 |  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model Edwards Apollo. | NOS | 0
155 | 9 | FIRE ALARM SYSTEM LOOPING | RMT. | 92
[8 empty] | Total | 0
156 | 10 | MONITOR MODULE
157 |  | Providing and fixing Emonitor module . Model Edwards FMM-1 flash scan type UL listed and FM approved. | NOS | 0
PR for FAS for LKN Budweiser bar