## PI
VART
Infracon Pvt Ltd
229, Neha Ind. Est., Off Duttapada Road,
Opp. Oberoi Sky, Borivali (E), Mumbai - 400066
Contact No :- 022-40233596 / 28700110 Email : info@vartinfra.com
Proforma Invoice
To, | Simolina Kitchen Pvt. Ltd. |  |  | 2024-05-16
Ra-2nd
Kindly Attn.:- Mr. Irfaan ji
Sr. No. | Description | Unit | Previous | Up To Date | This Bill
1 | The Lucknow Seating Interior and finishing work RA-1st | Job | 412312.4571 | 916244.0335 | 503931.5763
| Basic Total |  | 412312.4571 | 916244.0335 | 503931.5763
| Add GST @ 18% |  | 74216.2423 | 164923.926 | 90707.6837
| Grand Total |  | 486528.6994 | 1081167.9595 | 594639.2601
| This Bill Amount |  |  |  | 594639.2601
Work Completion Time Period
Material Delivery 1o days from the Date of PO with advance
Payment terms :
100% Advance with Work order
No Retention
For VART Infracon Pvt. Ltd.
Authorised Signatory

## Summary
Sr.No | Item Description | Boq amount Incl. GST | Previuos Bill Amount | This Bill Amount | Upto Date Bill Amount | Remarks
1 | BOQ for Civil & Interior Work for LKN Dom Seating space D-21a | 1261930 | 374867.8071 | 226351.5763 | 601219.3835
2 | BOQ for Fire Work for LKN Dom Seating space D-21a | 64550 | 37444.65 | 0 | 37444.65
3 | BOQ for HVAC HIgh Side for LKN Dom Seating space D-21a | 115000 |  | 115000 | 115000
4 | BOQ for HVAC Low Side for LKN Dom Seating space D-21a | 291650
5 | BOQ for Electrical Work for LKN Dom Seating space D-21a | 613360 |  | 162580 | 162580
| Total Amount | 2346490 | 412312.4571 | 503931.5763 | 916244.0335
| GST 18% | 433868.2 | 74216.2423 | 90707.6837 | 164923.926
| G.Total | 2780358.2 | 486528.6994 | 594639.2601 | 1081167.9595

## Abstract
Project -The Lucknow Seating D-21 Airport (Lucknow)
Sr No | Item Name | UOM | Boq Qty. | Rate |  | Quantity |  |  | Amount in (Rs.) |  |  |  | Remarks
[5 empty] | Amount | Previous Bill | This Bill | Upto Date | Previous Bill | This Bill | Upto Date | Varation
BOQ for Civil & Interior Work for LKN Dom Seating space D-21a
1 | GENERAL NOTES Please refer to Exhibit A - Basic rate of material for the applicable base rates of materials Items of works shall to be read in conjunction with Drawings, Specifications, Contractual terms and conditions and Trade Preambles to this BOQ as included in the RFP. The quantities mentioned in the BOQ is tentative and may increase or decrease. Payment shall be restricted to the quantum of work executed and measured as per the defined mode of measurement. The Mode of Measurement (in order of priority) is as follows (i) As defined in relevant item in the BOQ (ii) As defined in the specification (iii) As defined in IS-1200 or (latest version) for relevant trade . (iv) if mode is not defined in (i), (ii) and (iii), the standard industry practice shall be adopted. Items of work and trade preambles are essential parts of the bill of quantities and are to be taken as mutually explanatory of one another. Requirement occurring in one is binding as though occurring in both. In resolving conflicts, discrepancies, errors or omissions as regards trade preambles bill of quantities the following order of precedence shall be used but subject to PRIORITY OF DOCUMENTS as included in General Conditions of Contract a. General Notes as included in this bill of quantities. b. Trade Preambles as included in RFP. c. Item Description as included in this bill of quantities.
2 | GENERAL NOTES All MS frame shall be 14 Gauge All MS frame shall be Duco paint at site and consider on the cost
3 | FS-01 Furniture Construction and fabrications Fixed Seating -01 BWP board base framing Supply and install BWP Board (Boiling water proof board) base framing for furniture units as per specifications and drawings. Cut and shape the BWP board frame to match the dimensions specified in the drawings or as directed by the Site engineer. Securely combine the furniture structure using appropriate screws, nails or adhesives as per industry standards. Sand the edges and surfaces of the BWP board furniture structure to ensure smoothness and remove any rough edges splinters.Length - 26 6 width | SqFt | 440 | 150 | 66000 | 299.7263 | 0 | 299.7263 | 44958.9406 | 0 | 44958.9406 | -140.2737
4 | MS framing 25 x 25mm MS hollow pipe seating structure, primer painted and enamel painted. Welding and joining from the floor, complete base structure | RFT | 200 | 180 | 36000 | 200 | 0 | 200 | 36000 | 0 | 36000 | 0
5 | Brick Tile Cladding Providing laying approved shade brick cladding tile of size 50 x 230 mm(thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction)with silicone coating above the tile to provide good finish with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | Sqft | 130 | 270 | 35100 |  | 123.5546 | 123.5546 |  | 33359.735 | 33359.735 | -6.4454
6 | Leatherite Cushioning Seatrest Assembly Providing fixing of approved colour , seats shall have 12mm thk plyboard base finished with wooden finish laminate. Seat foam The Seat s made of PU foam having an additional top layer of PU foam. Seat is upholstered with leatherite. | SqFt | 60 | 2950 | 177000 | [6 empty] | -60 | SqFt (PER SEATING)
7 | MS Hollow pipe Providing fixing MS pipe 14 gauge in specific dia mentioned below - ms hollow pipe metal for the specified fixed seating as per design. Finished with powder coating with specific color as mentioned in BOQ Fabricate the metal base according to the approved design or as per the specifications provided. The design includes specific shapes, dimensions, saeting style, and other design elements. Utilize skilled craftsmanship to ensure precise welding, proper alignment, and secure attachment of the metal base components for structural integrity. 25mm dia | RFT | 30 | 350 | 10500 |  | 24.63 | 24.63 |  | 8620.5 | 8620.5 | -5.37
8 | Stone - Granite top ledge top and table top Providing and fixing 17-18mm thick granite over ledge top and table top | sqft | 20 | 510 | 10200 | [6 empty] | -20
9 | Fixed Seating -02 FS-01 Furniture Construction and fabrications BWP board base framing Supply and install BWP Board (Boiling water proof board) base framing for furniture units as per specifications and drawings. Cut and shape the BWP board frame to match the dimensions specified in the drawings or as directed by the Site engineer. Securely combine the furniture structure using appropriate screws, nails or adhesives as per industry standards. Sand the edges and surfaces of the BWP board furniture structure to ensure smoothness and remove any rough edges splinters. Length -7 -5 -0 Depth - 2 -0 Height -1 -6 | sqft | 35 | 180 | 6300 | 27.3029 | 0 | 27.3029 | 4914.5195 | 0 | 4914.5195 | -7.6971 | SqFt (PER SEATING)
10 | Leatherite Cushioning Seatrest Assembly Providing fixing of approved colour , seats shall have 12mm thk plyboard base finished with wooden finish laminate. Seat foam The Seats made of PU foam having an additional top layer of PU foam. Seat is upholstered with leatherite. | Sqft | 32 | 2950 | 94400 | [6 empty] | -32 | SqFt (PER SEATING)
11 | Brick Tile Cladding Providing laying approved shade brick cladding tile of size 50 x 230 mm(thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction)with silicone coating above the tile to provide good finish with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | Sqft | 50 | 270 | 13500 |  | 50 | 50 |  | 13500 | 13500 | 0
12 | MS Hollow pipe Providing fixing an m 14 gauge 25mm, 10mm,6mm dia ms hollow pipe metal for the specified fixed saeting as per design. Fabricate the metal base according to the approved design or as per the specifications provided. The design includes specific shapes, dimensions, saeting style, and other design elements. Utilize skilled craftsmanship to ensure precise welding, proper alignment, and secure attachment of the metal base components for structural integrity. | RFt | 10 | 350 | 3500 |  | 7.389 | 7.389 |  | 2586.15 | 2586.15 | -2.611 | RFt (PER SEATING)
13 | High table | [10 empty] | 0
14 | BWP board base framing Cut and shape the BWP board to match the design and dimensions specified in the drawings or as directed by the site engineer. Consider factors such as the shape, thickness, and size of the table top. Length -3.35m Depth - 450mm Height - 900mm | SqFt | 20 | 350 | 7000 | 20 | 0 | 20 | 7000 | 0 | 7000 | 0
15 | Granite marble at the table top Providing fixing a 15-17mm thick granite marble at the counter top surface of the table, applied over the BWP board. Ensure the BWP board surface is clean, dry, and free from any dirt, dust, or imperfections that may affect the adhesion of the granite marble. Remove any adhesive residues or smudges from the corian surface, leaving it clean. | SqFt | 30 | 510 | 15300 | [6 empty] | -30
16 | MS Hollow pipe Providing fixing an m 14 gauge 25mm, 10mm,6mm dia ms hollow pipe metal for the specified fixed saeting as per design, powder coated in specific color Fabricate the metal base according to the approved design or as per the specifications provided. The design includes specific shapes, dimensions, saeting style, and other design elements. Utilize skilled craftsmanship to ensure precise welding, proper alignment, and secure attachment of the metal base components for structural integrity. | Ft (PER SEATIN | 18 | 350 | 6300 |  | 17.9963 | 17.9963 |  | 6298.712 | 6298.712 | -0.00368
17 | Flooring | [10 empty] | 0
18 | Tile Flooring Providing laying approved shade vitrified floor tile of size 600 x 600 mm (thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand) including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | Sqft | 360 | 195 | 70200 | 360 | 0 | 360 | 70200 | 0 | 70200 | 0
19 | Brick Tile Flooring (op.a) Providing laying approved shade brick floor tile of size 50 x 230 mm(thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction)with silicone coating above the tile to provide good finish with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | sqft | 280 | 270 | 75600 | [6 empty] | -280
20 | Brick Tile Flooring (op.b) Providing laying approved shade vitrified floor tile of size 600 x 600 mm (thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand) including pointing the joints with cnc grooving of size 50 x 90 mm as schedule for the specified area as per the drawing , in proper line and level in all direction with proper cleaning and covering after completing the job (make mentioned in the flooring schedule) |  | 0 | 0 | 0 | [6 empty] | 0
21 | Wall Tile Cladding -1 Brick TILE ) Providing laying approved shade brick floor tile of size 50 x 230 mm(thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction)with silicone coating above the tile to provide good finish with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | Sqft | 90 | 270 | 24300 |  | 89.9913 | 89.9913 |  | 24297.6633 | 24297.6633 | -0.0086544
22 | Floor Transition S.S. Profile Providing fixing 6mm thick S.S. transition profile strip on junction in flooring as mentioned in the flooring drawing and details. | Rft | 90 | 300 | 27000 |  | 48.7017 | 48.7017 |  | 14610.516 | 14610.516 | -41.2983
23 | False Ceiling | [10 empty] | 0
24 | Gypsum false ceiling (Measurement shall be taken of the plan area only nothing extra for cove or verticle designs upto 3 -8 height) Suspending system and frame work shall match to compliment the layout of A.C. Ducts grills, electrical fire protection wiring fixtures, Return Air grills etc. Rate to include provision of extra frame work needed due to layout refered above and fixtures etc. Rates to include necessary scaffolding. Providing fixing Gypsum Board False ceiling with Saint Gobain ULTRA Main ceiling sections at 1200 c c Cross members at 450 c c. The grid work to be suspended from ceiling with Hangers at every 1200 c c both directions. The Frame work to be as per manufacturer s specifications. False ceiling is finished with 12.5 mm thk. gypsum board for (Saint gobain make) to be screwerd to the frame. The board is finished with fillign the tapered edges of the board with jointing compound and finishing with PAPER tape of INDIA GYPSUM. The ceiling is finished with a top coat as per approved manufacturer. The item includes all necessary cut outs for electrical air conditioning grills and necessary frame work for them. Item includes Cove and curve designs. (Only Plan area is considered for area calculations) Make- Gyproc - Gyp serra | Sqft | 355 | 185 | 65675 | 355 | 0 | 355 | 65675 | 0 | 65675 | 0
25 | HDHMR false ceiling HDHMR board ceiling as per drawing and detail supported from existing ceiling with MS framing of 38x38mm hollow pipe with complete fabrication and carpentry | sqft | 500 | 400 | 200000 | 194.4786 | 236.9156 | 431.3942 | 77791.428 | 94766.256 | 172557.684 | -68.6058
26 | Ceiling paint with acrlic emulsion paint | Sqft | 310 | 38 | 11780 | [6 empty] | -310
27 | Ceiling bottom surface finished with mirror finish acrylic sheets | Sqft | 170 | 270 | 45900 | [6 empty] | -170
28 | , with 25mm flat PVD profile and | rft | 130 | 220 | 28600 | [6 empty] | -130
29 | aluminum LED profile | rft | 70 | 35 | 2450 | [6 empty] | -70
30 | Finishing | [10 empty] | 0
31 | Ceiling paint Providing applying double (02) coats of approved paint on ceiling including scraping, primer, filling with putty, etc. complete with the final coat with no brush mark to be visible after painting color shade as specified. | Sqft | 530 | 38 | 20140 | [6 empty] | -530
32 | WALLPAPER Providing and fixing of custom printed wallpaper base with proper oil based paint and putty | Sqft | 65 | 45 | 2925 | [6 empty] | -65
33 | Wooden Paneling | [10 empty] | 0
34 | BWP plyboard panelling Providing and fixing of BWP plyboard paneling with necessary wooden battens with complete hardware and fixing from wall and floor | Sqft | 60 | 210 | 12600 | 60 | 0 | 60 | 12600 | 0 | 12600 | 0
35 | Plyboard partition Providing and fixing of BWP plyboard boxing partition with necessary wooden battens and fixing from the floor and ceiling | Sqft | 130 | 450 | 58500 | 123.8398 | 0 | 123.8398 | 55727.919 | 0 | 55727.919 | -6.1602
36 | Solid teak wood battens with clear polish- 25 x 50mm size of teak wood | RFT | 140 | 180 | 25200 |  | 105.2194 | 105.2194 |  | 18939.4848 | 18939.4848 | -34.7806
37 | 6mm thick mirror to be finished and pasted over plybaord | Sqft | 64 | 190 | 12160 |  | 49.3293 | 49.3293 |  | 9372.5592 | 9372.5592 | -14.6707
38 | Misc. | [10 empty] | 0
39 | Signage Providing and fixing of acrylic signage with side lit in multi color acrylic - Lucknow | LS | 1 | 15000 | 15000 | [6 empty] | -1
40 | Neon Signage Providing and fixing of Neon signage - Hello | LS | 1 | 11000 | 11000 | [6 empty] | -1
41 | Signage Providing and fixing of Neon Signage on graphic wall | LS | 3 | 4500 | 13500 | [6 empty] | -3
42 | WATERPROOFING | [10 empty] | 0
43 | Providing and laying a proprietary chemical waterproofing system consisting of polymer-modified acrylic base coating in two coats in form of a slurry (total consumption of 1.5 Kg Sqm) as approved by the PM and as directed by the approved manufacturer of waterproofing coating, with sandwiched fiber mesh and protective screed. The work shall include cleaning the surface, grouting porous surfaces making ‘V’ grooves at junctions , cracks with nonshrink crystalline base cementitious grout, etc. Further including horizontal and vertical surfaces protected with 20mm screeding in 1 4 mortar (1 cement 4 sand), finished in ready to receive Architectural finish, in the correct line, level, and plumb, curing, grouting, testing, etc. all complete to the entire satisfaction of the PM. FLOOR | Sqft | 530 | 110 | 58300 | [6 empty] | -530
Total Civil And Interior |  |  |  |  | 1261930 |  |  |  | 374867.8071 | 226351.5763 | 601219.3835
BOQ for Fire Work for LKN Dom Seating space D-21a
44 | Supply, laying, testing Commissioning of C class heavy duty MS pipe conforming to IS 3589 1239 for hydrent and sprinkler applications including fittings like elbows, tees, flanges, tapers, nuts bolts, gaskets etc. fixing the pipe on the wall ceiling with suitable clamps, U bolt and including painting of two coats of Red Oxide , painting with two or more coats of synthetic enamel paint of Post office red shade complete as required .The installation includes all civil openings , breakages and making good the same. ( Final Quantity Measure as per site after working )
45 | 25 mm dia | Mtr. | 14 | 790 | 11060 | 11.255 | 0 | 11.255 | 8891.45 | 0 | 8891.45 | -2.745
46 | 32 mm dia | Mtr. | 6 | 840 | 5040 | 5.48 | 0 | 5.48 | 4603.2 | 0 | 4603.2 | -0.52
47 | 40 mm dia | Mtr. | 3 | 970 | 2910 | 3 | 0 | 3 | 2910 | 0 | 2910 | 0
48 | 50 mm dia | Mtr. | 3 | 1080 | 3240 | 3 | 0 | 3 | 3240 | 0 | 3240 | 0
49 | Supply, installation, testing and commissioning of Brass ball valves of following sizes as required. 50 mm dia | Each | 1 | 7000 | 7000 | 1 | 0 | 1 | 7000 | 0 | 7000 | 0
50 | Supply, fixing, testing commissioning of 15 mm dia size ,quartzoid bulb sprinkler heads suitable for 68 degree centigrade rating of the following type Pendant type | Each | 8 | 1350 | 10800 | 8 | 0 | 8 | 10800 | 0 | 10800 | 0
51 | Supply Fixing ISI marked ( IS 15683 ) Portable Fire Exitnguisher, ABC type,finished externally with red enamel paint, complete in all respects including initial fill and wall suspension of following capacity. 6 kg | Each | 1 | 6500 | 6500 | [6 empty] | -1
52 | Supply Fixing ISI marked ( IS 15683 ) Portable fire Extinguisher, Carbon-dioxide type flat base including valve, discharge hose of not less than 10 mm dia. min. 600 mm long complete in all respects including initial fill with C02 gas confirming to IS 307-1966 filled to a filling ratio of not more than 0.667and wall suspension bracket. Capacity 5 Kg. | Each | 1 | 8500 | 8500 | [6 empty] | -1
53 | Supply Fixing ISI marked ( IS 15683 ) Portable fire Extinguisher, k type flat base including valve, discharge hose of not less than 10 mm dia. min. 600 mm long complete in all respects including initial fill. Capacity 6kg | Each | 1 | 9500 | 9500 | [6 empty] | -1
Total Fire Fighting Work |  |  |  |  | 64550 |  |  |  | 37444.65 | 0 | 37444.65
BOQ for HVAC HIgh Side for LKN Dom Seating space D-21a
54 | Ceiling Suspended AHU Supplying, installing, testing and commissioning of double skin construction draw thru type Ceiling Suspended AIR HANDLING UNITS as per specification, each complete with ESP Filter (94% down to 3 microns), pre-filter section (90% down to 10 microns), min 6 Row Deep Chilled water coil of copper tube aluminium fins construction, squirrel cage induction motor, airfoil centrifugal fan belt drive and vibration isolators, coil size shall be selected for a maximum face velocity of 500 feet minute and static pressure shall be as indicated. The motor selected shall be energy efficient having efficiency (IE2) at full load ranging between 82.5% to 92% in accordance with motor rating as per specification. Motor shall be suitable for 415±10% volts, 50 cycles, 3 phase AC supply. Fan motor assembly (as whole) shall be statically and dynamically balanced to grade G 6.3 as per ISO-1940 AMCA 204-3.All units shall be complete with opposed blade volume control dampers at oulet. Duct flexible connector (fire proof) shall be provided at outlets of AHU. ( Temporary bypass arrangement in Chilled Water Line with related accessories to be considered to facilitate flushing during precommissioning and commissioning of the System). AHU Tag. Description AHU CFM TR ESP Motor HP AHU-01 Sitting area 2500 cfm 5 15 mm 2 | No. | 1 | 115000 | 115000 |  | 1 | 1 |  | 115000 | 115000 | 0
Total HVAC High Side |  |  |  |  | 115000 |  |  |  | 0 | 115000 | 115000
BOQ for HVAC Low Side for LKN Dom Seating space D-21a
55 | (FOR FACTORY FABRICATED DUCTS AS PER “SMACNA” STANDARDS SPECIFICTIONS) |  | Qty
56 | Supply, Fabrication, installation and testing of factory fabricated sheet metal ducts with sleeve joints and supports complete with the approved shop drawings and as required by the specifications and hanging of the ducts to be done by thread wire on metal cushion with gripple support.
57 | 24G sheet | sq.m | 40 | 1350 | 54000 | [6 empty] | -40
58 | 26G sheet | sq.m | 5 | 1150 | 5750 | [6 empty] | -5
59 | Supplying and erecting GI sheet of fabricated at site and mentioned guage to be used for fabrication of ducting complete with neoprene rubber garkets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required 24G sheet | sq.m | 5 | 1350 | 6750 | [6 empty] | -5
60 | Supply, installation, testing and balancing of powder coated Extruded Aluminium Supply air Grilles with volume control dampers in accordance with the approved shop drawings and specifications. (Minimum Chargable area would be 0.1 Sqm Per Pc) | SQMT | 1 | 6800 | 6800 | [6 empty] | -1
61 | Supplying fixing of opposed blade volume control dampers in supply air duct collars as per approved drawings and specifications. Volume control damper shall be provided at the junction of each branch duct with main duct. Dampers shall be 2 gauge heavier than the gauge of large duct but should not be less than 20 gauge, and shall be rigid in construction so as not to flutter with the passage of air. | SQMT | 1 | 5800 | 5800 | [6 empty] | -1
62 | Supply, fabrication, installation and testing the flexible connections constructed of fire resistance flexible double canvas sleeve as per the approved shop drawings. | Nos. | 1 | 4450 | 4450 | [6 empty] | -1
63 | Supply, installation, testing and balancing of powder coated Extruded Aluminium Return air Grilles without volume control dampers in accordance with the approved shop drawings and specifications. (Minimum Chargable area would be 0.1 Sqm Per Pc) | sq.m | 2 | 6800 | 13600 | [6 empty] | -2
64 | Supply, installation and testing of Acoustic lining with Open cell nitrile rubber with in supply and return air ducts of specified thickness as per the specifications. All ducts shown cross hatched on the approved shop drawings shall be provided with acoustic lining as perthe specifications 15 mm thick | sq.m | 10 | 800 | 8000 | [6 empty] | -10
65 | Supplying and fixing of following thickness duly laminated aluminum foil of mat finish closed cell Nitrile rubber(Class“O”) insulation on existing duct after applying suitable adhesive for Nitrile rubber. The joints shall be sealed with 50mm wide and 3mm thick self adhesive nitrile rubber tape insulation complete as per specifications and as required. 19mm thick | sq.m | 40 | 890 | 35600 | [6 empty] | -40
66 | Supplying, installing and testing of UPVC pipe ( heavy duty) with 6 mm thick nitrile rubber insulation with protective coating on condensing water piping and fitting like bends, elbow, tee and union, etc. as per the approved shop drawings and specifications. 25mm Dia | Rmt | 5 | 440 | 2200 | [6 empty] | -5
67 | Supply ,Installation ,Testing and commissioning of ERW heavy duty C Class MS pipes as per IS-1239 upto 6 dia. and as per IS-3589 above 6 dia. cut to required lengths and installed with all welded joints, complete with necessary pipe hot dip galvanized MS supports, GI hangers with rubber lined universal clamps and hangers , fittings like bends, elbows, tees, reducers, matching flanges, neoprene 6 mm thick gaskets, hot dipped galvanized nut blots washers ,PUF gutti with U clamp, socket and fittings for instruments and sensors connections etc. ERW pipes shall be with two coats of Zinc Chromate paint for anti-rust including all fittings like valves, flanges and unions, etc. Note Pipe Measurement are in Pair (Supply + Return) . Quoted rates shall be inclusive of the cost of piping Insulation of Class O rated thermal insulations with one sided factory laminated glass clothed Nitrile Rubber insulation with density 45-60 kg m3 with covered with two coats of UL Listed lag coating (Low VOC) Anti-fungal, Anti-microbial vapour barrier for line item sealed with acrylic based food grade sealant. 32 mm dia MS Pipe with 25 mm thick Insulation | Rmt | 10 | 650 | 6500 | [6 empty] | -10
68 | Providing and fixing in position following ball valves 32 mm dia valves | Nos. | 2 | 4950 | 9900 | [6 empty] | -2
69 | Providing and fixing in position the following ‘Y’ Strainers 32 mm dia strainers | Nos. | 1 | 6250 | 6250 | [6 empty] | -1
70 | Supplying, installation, testing and commissioning of Auto air vents . 25 mm dia pipes | Nos. | 1 | 2250 | 2250 | [6 empty] | -1
71 | Providing and fixing in position SS 304 the industrial dial type pressure gauges with gun metal valves. | Nos. | 2 | 6500 | 13000 | [6 empty] | -2
72 | Providing and fixing in position SS 304 the mercury-in- glass industrial dial type thermometers. | Nos. | 2 | 1950 | 3900 | [6 empty] | -2
73 | Supply, installation, testing and commissioning of THERMOSTAT for cooling. The thermostat shall be electronic room temperature controller with digital display fan speed control, capable of providing individual space temperature control for cooling application. The controller shall produce a dual output to cooling coils in response to load change in rooms. The controller shall be designed to modulate two control devices such as 2 way motorized valves for chilled water duty . (minimum of 5 Deg F dead band ) | No. | 1 | 1900 | 1900 | [6 empty] | -1
74 | Supply, installation, testing and commissioning of Electronic Self Balancing Valve pressure independent with independent type dynamic balancing valve for AHUs with integrated 2 way modulating control valves in a single body. The actuator shall be capable of accepting 2-10 VDC 4-20 mA electric signal and shall provide similar transduced feedback output signal to control system for flow measurement. The minimum close off pressure actuator must be 1.5 times shut off head of pump 5 bars whichever is maximum. The valves shall be suitable for following pipe sizes 32 mm dia | No. | 1 | 21500 | 21500 | [6 empty] | -1
75 | Supply, Installation, Testing and Commissioning of BMS compatible ultrasonic BTU Meter complete with flanged type water flow meter (pressure drop across water meter not exceeding 0.1 bar at the specified nominal flow rate), temperature sensors, LCD display panel, inbuilt Lithium battery backup with minimum six years life. The units shall be capable to calculate and store maximum values, display flow rates and temperature difference across supply and return. The quoted price shall be inclusive of necessary wiring, conduiting between the flow meter and the display panel. The unit shall be housed in a totally tamper proof box. The size of the BTU meter is as under 32 mm dia BTU Meter | No. | 1 | 59000 | 59000 | [6 empty] | -1
76 | CONTROL PANEL FOR AHU (WITH DOL SD STARTER) Design, manufacture, supply, installation, testing and commissioning of the following cubicle type, dead front, sheet steel, wall mounted control panels including anchoring into the wall, wiring, incoming, earthing terminating into MCCB in each panel shall be provided by the electrical contractor. All internal wiring power cabling and copper earthing of air handling unit motors from the panel shall be included. All outgoing shall be provided with Stop Manual Auto selector switch to facilitate operation through BAS. All starters shall be provided with potential free Contact for Connections to Building Automation System. The panel shall include the following components and accessories. a)MCCB as per the ratings given below, suitable for motor duty and able to withstand fault level of 20 KA. b)DOL SD starter as per HP ratings c) Terminal block for power distribution. d) Contactor, over load relay with built in single phasing protection. e) Phase indicating lights and indicating light for ON status. f) Digital voltmeter and digital ammeter with selector switches. g) Time delay relay for delayed automatic restart of air handling unit motor. h) For on off remote and local operation , 3 pole single throw switch shall be provided in each AHU panel to facilitate override of the automatic operation. i) All starters shall be provided with suitable potential free contract for connections to the Building Automation System . The number of AHU FAN control panels shall be as follows . 2 HP DOL Starter | No. | 1 | 24500 | 24500 | [6 empty] | -1
| Total HVAC Low Side |  |  |  | 291650 |  |  |  | 0 | 0 | 0
BOQ for Electrical Work for LKN Dom Seating space D-21a
77 | DISTRIBUTION BOARDS 6 WAY V-TPN DB - LPDB Incomer 63A, FP, MCB, 10kA 1 Nos Sub Incomer 32A, DP, RCCB, 100mA 3 Nos Outgoings 6 10 16 A SP MCB C Type - 18 Nos. | Nos. | 1 | 34500 | 34500 |  | 1 | 1 |  | 34500 | 34500 | 0
78 | MV CABLES | [10 empty] | 0
79 | POWER CABLING Supply and laying, effecting proper connections, testing commissioning of the following sizes of 1.1 KV XLPE FRLS armoured unarmoured PVC insulated PVC sheathed aluminium copper conductor cables conforming to IS 1554 and IS 694 for Flexible copper cable Part I - 1976 with latest amendments laid over MS supports in existing RCC ducts laid in ground laid on Cable Trays including clamping the cables to supports in an approved manner as required complete with all accessories.All cables shall have thermo setting insulation XLPE and low emission of smoke and corrosive gas when affected by fire . Necessary Markers shall be provided at the intervals as per the specifications. CU Flexible Cables 4C x 6 Sq.mm. | Mtr. | 30 | 630 | 18900 |  | 3 | 3 |  | 1890 | 1890 | -27
80 | CABLE TERMINATION - Making cable and terminations including brass single compression glands and crimping type copper lugs for cable sizes mentioned below for aluminium or copper. | [10 empty] | 0
81 | 3.5C x 70 Sq.mm. AL | Nos. | 2 | 1150 | 2300 | [6 empty] | -2
82 | 4C x 6 Sq.mm. | Nos. | 2 | 680 | 1360 |  | 2 | 2 |  | 1360 | 1360 | 0
83 | POINT WIRING | [10 empty] | 0
84 | Point wiring LENGTH from DB to SB or First Light point control be MCB shall be avg. of 15Mtr. of 3C x 2.5 sq mm FRLS PVC insulated stranded copper conductor wires. For SB to SB the length shall be measured in Mtr. The secondary Loop point length shall be 10Mtr from Light fixture to light fixture. If secondary point shall be operated from MCB then the length shall be 10 Mtr. All sockets to be checked with a Check Plug socket tester for live-neutral reverse, no earth,neutral fault, live earth reverse, neutral earth reverse. The Circuit No. and DB no. label shall be provided on all UPS ,RAW sockets and switchboards with label printer . The Length shall be paid as per the actual measurements as per following manner. Wiring for the following light points with 3 x 2.5 Sq.mm FRLS PVC insulated stranded copper conductor wires in GI conduits in F.ceiling walls ceiling as direc-ted including providing 6 amps flush type switches, 5 sided G.I Boxes for housing switc-hes and earth- ing complete as required from the above switch board. Rates shall exclusive of Switches Switch Box. (FROM SB TO LIGHT) | [10 empty] | 0
85 | First point controlled by one no. 6 amp switch. (upto 10Mtr.) | Nos. | 15 | 2600 | 39000 |  | 11 | 11 |  | 28600 | 28600 | -4
86 | First point controlled by one no. 6 amp switch. For Emergency Light (upto 10Mtr.) | Nos. | 6 | 2550 | 15300 | [6 empty] | -6
87 | Same as item No. 4.2.1 4.2.2 above but LOOP POINT i.e. wiring of point looped from first point with 3C x 2.5 sq. mm FRLS PVC insulated copper conductor wire in concealed exposed GI conduit and earthing | Nos. | 12 | 800 | 9600 |  | 11 | 11 |  | 8800 | 8800 | -1
88 | Same as item No. 4.2.3 4.2.4 above but LOOP POINT i.e. wiring of point looped from first point with 3C x 2.5 sq. mm FRLS PVC insulated copper conductor wire in concealed exposed GI conduit and earthing For Emergency Light | Nos. | 8 | 1420 | 11360 | [6 empty] | -8
89 | First point controlled by existing MCB in D.B. | Nos. | 10 | 3250 | 32500 |  | 10 | 10 |  | 32500 | 32500 | 0
90 | Same as item No.4.5.1 above but LOOP POINT i.e. wiring of point looped from first point with 3C x 2.5 sq. mm FRLS. insulated copper conductor wire in concealed exposed GI conduit and earthing | Nos. | 30 | 1750 | 52500 |  | 11 | 11 |  | 19250 | 19250 | -19
91 | Wiring for UPS Raw plug outlets points with 3C x 4 sqmm FRLS PVC Insulated and PVC sheathed flexible cable with bright annealed electrolytic copper conductor , 1100 volt grade confirming to IS 694-1990 with latest amendments, in existing Channels conduit in ceiling walls floor including all cable termination accessories) (including body earth for GI boxes) | Mtr. | 200 | 420 | 84000 | [6 empty] | -200
92 | Wiring for UPS Raw plug outlets points with 4C x 4 sqmm FRLS PVC Insulated and PVC sheathed flexible cable with bright annealed electrolytic copper conductor , 1100 volt grade confirming to IS 694-1990 with latest amendments, in existing Channels conduit in ceiling walls floor including all cable termination accessories) (including body earth for GI boxes) | Mtr. | 125 | 560 | 70000 | [6 empty] | -125
93 | 20 mm dia GI Conduit | Mtr. | 100 | 155 | 15500 |  | 100 | 100 |  | 15500 | 15500 | 0
94 | MODULAR SWITCHES Supply, installation, testing commissioning of following types of modular switches, cover plates, 5 sided G.I. Boxes for housing the modular switches earthing complete as required. GI Boxes to have earth pin for body earthing. The Circuit No. and DB no. label shall be provided on all UPS ,RAW sockets and switchboards with label printer.(Make- Legrand Aretor Series) |  | 0 | 0 | 0 | [6 empty] | 0
95 | 6A One Way Switch | Nos. | 22 | 190 | 4180 |  | 18 | 18 |  | 3420 | 3420 | -4
96 | 6A 5 pin Socket - 1Nos. 6A Switch - 1Nos. | Nos. | 22 | 620 | 13640 |  | 18 | 18 |  | 11160 | 11160 | -4
97 | GENERAL EARTHING Supplying and erecting bare Copper conductor of following sizes 8 SWG | Mtr. | 30 | 275 | 8250 | [6 empty] | -30
98 | LIGHT FIXTURES INSTALLATION Receiving from Store, Installation, testing commissioning of following light fixtures with complete installation hardwares including Anchor fastner, supporting Hook Rods as per final approval from Architect Client Consultant |  | 0 | 0 | 0 | [6 empty] | 0
99 | DOME LIGHT | Nos. | 13 | 450 | 5850 | [6 empty] | -13
100 | CYLINRICAL SURFACE MOUNT LIGHT | Mtr. | 36 | 350 | 12600 | [6 empty] | -36
101 | MISCELLANEOUS WORKS |  | 0 | 0 | 0 | [6 empty] | 0
102 | Supply fixing in position approved shock treatment chart written in English, Hindi and Local language. These charts shall be framed in wooden frame covered with clear glass. | Nos. | 1 | 650 | 650 | [6 empty] | -1
103 | Supply fixing in position the best quality danger notice boards of approved shape size as reqd. by the local Electrical Inspecting Authority written in English, Hindi local language. | Nos. | 1 | 650 | 650 | [6 empty] | -1
104 | CCTV System |  |  |  | 0 | [6 empty] | 0
105 | 2 Megapixel Fixed Lens Camera IR Dome Type 1 2.8 Progressive Scan CMOS, 1920 × 1080 at 25fps, 2.8mm Fixed lens, 0.028 Lux at F1.2, ICR, ONVIF, support H.265, H.264, MJPEG, 120db WDR, 3D Digital Noise Reduction, Three individually configurable stream, 12 VDC PoE, IR range 40m, Support on-board storage up to 128 GB (SD card not included), IP67, IK10, Edge Anlalytics- Line crossing detection, Intrusion detection, Motion detection, Scene change detection, video tampering, UL, CE, FCC certified. | Nos. | 4 | 7500 | 30000 | [6 empty] | -4
106 | NVR 16 Channel Connect Up to 16 IP Cameras, Dual OS, Up to 8 Megapixels Resolution, HDMI output with 4k output and VGA output with 2MP Output , Support H.265,H.264, MJPEG, Incoming Bandwidth 160 Mbps, 4 SATA Hard Disks, ANR Technology, 2 SATA interfaces for 2 HDDs and capacity of each HDD upto 6TB, 2 USB at least 1 × USB with 3.0, Serial interface 1 RS-485, 1 RS-232, Alarm I O 16 4, 2 RJ-45 10 100 1000 Mbps self-adaptive Ethernet interface, Multiple network monitoring Web viewer, CE, FCC, UL certified. | Nos. | 1 | 19000 | 19000 | [6 empty] | -1
107 | 16 Port Network Switch Gigabit POE 16 × gigabit PoE ports, 1 × gigabit RJ45 port, and 1 × gigabit SFP fiber optical port, IEEE 802.3at af standard | Nos. | 1 | 7000 | 7000 | [6 empty] | -1
108 | CAT 6 Connector | Nos. | 8 | 175 | 1400 | [6 empty] | -8
109 | Hard Disk 6 TB | Nos. | 2 | 17500 | 35000 | [6 empty] | -2
110 | Suplly installation of Computer system as required | Nos. | 1 | 18500 | 18500 | [6 empty] | -1
111 | Installation labour charges | Job | 1 | 6000 | 6000 | [6 empty] | -1
112 | Supply, Drawing and Testing of 4 pair ,100 Ohm, 24 AWG UTP Cat 6 Cable as per latest amendments of TIA EIA 568 B.2 specifications for Data Telephone points in existing MS PVC conduits including making connections to Information outlets and patch panels with ferruling at both ends for identification with necessary tools for punching ,stripping crimping and testing as required | Mtr | 80 | 70 | 5600 |  | 80 | 80 |  | 5600 | 5600 | 0
113 | Supply and laying of HDMI Cabel | Nos. | 1 | 1600 | 1600 | [6 empty] | -1
114 | Supply and Laying of RIGID PVC Medium Duty Conduits ISI marked conduits complete with accessories such as bends, junction boxes, pull boxes etc., in recess or on surface including cutting chases in the walls floors and making good the same complete as required. 25 mm dia | RM | 32 | 160 | 5120 | [6 empty] | -32
115 | Supply , Installation, Testing and Comissioning of Wall mounted Communication rack with glass doors, handles ,lock , Top and Bottom Cable entries, Supports for mounting rack on wall , Cable managers, one Fan, Equipment mounting hardware, power supply box for supplying power to switches, fans etc along with earth continuity kit, Mcb, indicator, moulded power supply cable . 12U(44 mm ) wall mounted | Nos. | 1 | 16000 | 16000 | [6 empty] | -1
116 | UPS System Supply,Installation, testing and commissioning of following type of Online UPS Inverter as per drawings and specifications with all other accessories. Online UPS 1.2.0KVA UPS12V DC 25AH maintenance free batteries for 30 minutes battery backup. Input supply voltage -230-250 Volts Output voltage -220-240V+ -1% Voltage Regulation -Less than or equal to + - 1% Output frequency -50 Hz + - 0.05 Hz Type of cooling -Forced air cooled Invertor Efficiency -Better than 85% Output Power factor -0.8 | Nos. | 1 | 35500 | 35500 | [6 empty] | -1
Total Electrical Work |  |  |  |  | 613360 |  |  |  | 0 | 162580 | 162580

## MB Sheet
MB SHEET RA-02
Project -The Lucknow Seating D-21 Airport (Lucknow)
Sr No | Item Name | UOM | Boq Qty. | No. | Length | Width | Height | Total | Remarks
BOQ for Civil & Interior Work for LKN Dom Seating space D-21a
1 | GENERAL NOTES Please refer to Exhibit A - Basic rate of material for the applicable base rates of materials Items of works shall to be read in conjunction with Drawings, Specifications, Contractual terms and conditions and Trade Preambles to this BOQ as included in the RFP. The quantities mentioned in the BOQ is tentative and may increase or decrease. Payment shall be restricted to the quantum of work executed and measured as per the defined mode of measurement. The Mode of Measurement (in order of priority) is as follows (i) As defined in relevant item in the BOQ (ii) As defined in the specification (iii) As defined in IS-1200 or (latest version) for relevant trade . (iv) if mode is not defined in (i), (ii) and (iii), the standard industry practice shall be adopted. Items of work and trade preambles are essential parts of the bill of quantities and are to be taken as mutually explanatory of one another. Requirement occurring in one is binding as though occurring in both. In resolving conflicts, discrepancies, errors or omissions as regards trade preambles bill of quantities the following order of precedence shall be used but subject to PRIORITY OF DOCUMENTS as included in General Conditions of Contract a. General Notes as included in this bill of quantities. b. Trade Preambles as included in RFP. c. Item Description as included in this bill of quantities.
2 | GENERAL NOTES All MS frame shall be 14 Gauge All MS frame shall be Duco paint at site and consider on the cost
3 | FS-01 Furniture Construction and fabrications Fixed Seating -01 BWP board base framing Supply and install BWP Board (Boiling water proof board) base framing for furniture units as per specifications and drawings. Cut and shape the BWP board frame to match the dimensions specified in the drawings or as directed by the Site engineer. Securely combine the furniture structure using appropriate screws, nails or adhesives as per industry standards. Sand the edges and surfaces of the BWP board furniture structure to ensure smoothness and remove any rough edges splinters.Length - 26 6 width | SqFt | 440
| 75mm Ledge wall | Sqm |  | 2 | 7.99 |  | 1.2 | 19.176
| Seating Top | Sqm |  | 1 | 7 |  | 0.6 | 4.2
| Seating Sides | Sqm |  | 2 | 0.6 |  | 0.45 | 0.54
| Seating facia | Sqm |  | 1 | 7 |  | 0.45 | 3.15
| ledge 75mm Top | Sqm |  | 1 | 7.99 | 0.075 |  | 0.59925
| Sides | Sqm |  | 2 |  | 0.075 | 1.2 | 0.18
| Total Qty in Sqm | [6 empty] | 27.8452
| Total Qty in Sqft | [5 empty] | 10.764 | 299.7263
| Previous bill Qty | [6 empty] | 299.7263
| This Bill Qty | [6 empty] | 0
4 | MS framing 25 x 25mm MS hollow pipe seating structure, primer painted and enamel painted. Welding and joining from the floor, complete base structure | RFT | 200
| Ledge Horizontal member | Rmt |  | 4 | 7.99 |  |  | 31.96
| Ledge Vertical Maber | Rmt |  | 15 | 1.075 |  |  | 16.125
| seating Vertical | Rmt |  | 3 | 7.5 |  |  | 22.5
| Seating Vertical member | Rmt |  | 15 | 0.5 |  |  | 7.5
| Seating Front Vertical | Rmt |  | 15 | 0.4 |  |  | 6
| Fixed seating -02 Ms framing | Rmt |  | 4 | 2.25 |  |  | 9
| Seating Bottam Horizontal | Rmt |  | 6 | 0.54 |  |  | 3.24
| Seating Facia vertical | Rmt |  | 6 | 0.45 |  |  | 2.7
| Total Qty in Rmt | [6 empty] | 99.025
| Total Qty in Eft | [5 empty] | 3.284 | 325.1981
| Restricted boq Qty | [6 empty] | 200
| Previous bill Qty | [6 empty] | 200
| This Bill Qty | [6 empty] | 0
5 | Brick Tile Cladding Providing laying approved shade brick cladding tile of size 50 x 230 mm(thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction)with silicone coating above the tile to provide good finish with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | Sqft | 130
| 75mm Ledge wall | Sqm |  | 1 | 7.99 |  | 1.2 | 9.588
| Seating Sides | Sqm |  | 2 | 0.6 |  | 0.45 | 0.54
| Fixed seating 2 facia | Sqm |  | 1 | 2.25 |  | 0.37 | 0.8325
| Fixed seating 2 sides | Sqm |  | 2 | 0.7 |  | 0.37 | 0.518
| Total Qty in Sqm | [6 empty] | 11.4785
| Total Qty in Sqft | [5 empty] | 10.764 | 123.5546
Previous bill Qty
| This Bill Qty | [6 empty] | 123.5546
6 | Leatherite Cushioning Seatrest Assembly Providing fixing of approved colour , seats shall have 12mm thk plyboard base finished with wooden finish laminate. Seat foam The Seat s made of PU foam having an additional top layer of PU foam. Seat is upholstered with leatherite. | SqFt | 60
7 | MS Hollow pipe Providing fixing MS pipe 14 gauge in specific dia mentioned below - ms hollow pipe metal for the specified fixed seating as per design. Finished with powder coating with specific color as mentioned in BOQ Fabricate the metal base according to the approved design or as per the specifications provided. The design includes specific shapes, dimensions, saeting style, and other design elements. Utilize skilled craftsmanship to ensure precise welding, proper alignment, and secure attachment of the metal base components for structural integrity. 25mm dia | RFT | 30
| Front side | Rmt |  | 1 | 7.5 |  |  | 7.5
| Total Qty in Rmt | [6 empty] | 7.5
| Total Qty in Rft | [5 empty] | 3.284 | 24.63
Previous bill Qty
| This Bill Qty | [6 empty] | 24.63
8 | Stone - Granite top ledge top and table top Providing and fixing 17-18mm thick granite over ledge top and table top | sqft | 20
9 | Fixed Seating -02 FS-01 Furniture Construction and fabrications BWP board base framing Supply and install BWP Board (Boiling water proof board) base framing for furniture units as per specifications and drawings. Cut and shape the BWP board frame to match the dimensions specified in the drawings or as directed by the Site engineer. Securely combine the furniture structure using appropriate screws, nails or adhesives as per industry standards. Sand the edges and surfaces of the BWP board furniture structure to ensure smoothness and remove any rough edges splinters. Length -7 -5 -0 Depth - 2 -0 Height -1 -6 | sqft | 35
| Fixed seation -02 Bottam | Sqm |  | 1 | 2.25 | 0.56 |  | 1.26
| fixed seation -02 front Facia | Sqm |  | 1 | 2.25 | 0.37 |  | 0.8325
| Seating back | Sqm |  | 1 | 2.25 | 0.45
| Sides | Sqm |  | 2 | 0.6 | 0.37 |  | 0.444
| Total Qty in Sqm | [6 empty] | 2.5365
| Total Qty in Sqft | [5 empty] | 10.764 | 27.3029
| Previous bill Qty | [6 empty] | 27.3029
| This Bill Qty | [6 empty] | 0
10 | Leatherite Cushioning Seatrest Assembly Providing fixing of approved colour , seats shall have 12mm thk plyboard base finished with wooden finish laminate. Seat foam The Seats made of PU foam having an additional top layer of PU foam. Seat is upholstered with leatherite. | Sqft | 32
11 | Brick Tile Cladding Providing laying approved shade brick cladding tile of size 50 x 230 mm(thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction)with silicone coating above the tile to provide good finish with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | Sqft | 50
| Seating back | Sqm |  | 1 | 2.25 | 2.95 |  | 6.6375
| Less seating facia | Sqm |  | -1 | 2.25 | 0.37 |  | -0.8325
| Total Qty in Sqm | [6 empty] | 5.805
| Total Qty in Sqft | [5 empty] | 10.764 | 62.485
| Restricted Qty | [6 empty] | 50
Previous bill Qty
| This Bill Qty | [6 empty] | 62.485
12 | MS Hollow pipe Providing fixing an m 14 gauge 25mm, 10mm,6mm dia ms hollow pipe metal for the specified fixed saeting as per design. Fabricate the metal base according to the approved design or as per the specifications provided. The design includes specific shapes, dimensions, saeting style, and other design elements. Utilize skilled craftsmanship to ensure precise welding, proper alignment, and secure attachment of the metal base components for structural integrity. | RFt | 10
| MS hollow pipe | Rmt |  | 1 | 2.25 |  |  | 2.25
| Total Qty in Rmt | [6 empty] | 2.25
| Total Qty in Rft | [5 empty] | 3.284 | 7.389
Previous bill Qty
| This Bill Qty | [6 empty] | 7.389
13 | High table |  | 0
14 | BWP board base framing Cut and shape the BWP board to match the design and dimensions specified in the drawings or as directed by the site engineer. Consider factors such as the shape, thickness, and size of the table top. Length -3.35m Depth - 450mm Height - 900mm | SqFt | 20
| High Table top | Sqm |  | 1 | 2.15 | 0.45 |  | 0.9675
| High Table RHS Mirror Wall | Sqm |  | 1 | 3.53 | 0.45 |  | 1.5885
| Total Qty in Sqm | [6 empty] | 2.556
| Total Qty in Sqft | [5 empty] | 10.764 | 27.5128
| Restricted Qty | [6 empty] | 20
| Previous bill Qty | [6 empty] | 20
| This Bill Qty | [6 empty] | 0
15 | Granite marble at the table top Providing fixing a 15-17mm thick granite marble at the counter top surface of the table, applied over the BWP board. Ensure the BWP board surface is clean, dry, and free from any dirt, dust, or imperfections that may affect the adhesion of the granite marble. Remove any adhesive residues or smudges from the corian surface, leaving it clean. | SqFt | 30
16 | MS Hollow pipe Providing fixing an m 14 gauge 25mm, 10mm,6mm dia ms hollow pipe metal for the specified fixed saeting as per design, powder coated in specific color Fabricate the metal base according to the approved design or as per the specifications provided. The design includes specific shapes, dimensions, saeting style, and other design elements. Utilize skilled craftsmanship to ensure precise welding, proper alignment, and secure attachment of the metal base components for structural integrity. | Ft (PER SEATIN | 18
| High Table-01 hollow pipe | Rmt |  | 1 | 3.35 |  |  | 3.35
| High Table-02 hollow pipe | Rmt |  | 1 | 2.13 |  |  | 2.13
| Total Qty in Rmt | [6 empty] | 5.48
| Total Qty in rft | [5 empty] | 3.284 | 17.9963
Previous bill Qty
| This Bill Qty | [6 empty] | 17.9963
17 | Flooring |  | 0
18 | Tile Flooring Providing laying approved shade vitrified floor tile of size 600 x 600 mm (thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand) including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | Sqft | 360
| Flooring | Sqm |  | 1 | 11.4 | 3.87 |  | 44.118
| Curved area | Sqm |  | 1 | 1.8 | 0.6 |  | 1.08
| Fixed seating -2 area flooring | Sqm |  | 1 | 1.63 | 2.75 |  | 4.4825
| Total Qty in Sqm | [6 empty] | 49.6805
| Total Qty in Sqft | [5 empty] | 10.764 | 534.7609
| Restricted Boq Qty. | [6 empty] | 360
| Previous bill Qty | [6 empty] | 360
| This Bill Qty | [6 empty] | 0
19 | Brick Tile Flooring (op.a) Providing laying approved shade brick floor tile of size 50 x 230 mm(thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction)with silicone coating above the tile to provide good finish with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | sqft | 280
20 | Brick Tile Flooring (op.b) Providing laying approved shade vitrified floor tile of size 600 x 600 mm (thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand) including pointing the joints with cnc grooving of size 50 x 90 mm as schedule for the specified area as per the drawing , in proper line and level in all direction with proper cleaning and covering after completing the job (make mentioned in the flooring schedule) |  | 0
21 | Wall Tile Cladding -1 Brick TILE ) Providing laying approved shade brick floor tile of size 50 x 230 mm(thickness to be mentioned by the manufacturer) of 1st quality laid on 20mm thick cement mortar 1 4 (1 cement 4 coarse sand including pointing the joints with approved epoxy grout as schedule for the specified area as per the drawing , in proper line and level in all direction)with silicone coating above the tile to provide good finish with proper cleaning and covering after completing the job. (make mentioned in the flooring schedule) | Sqft | 90
| 75mm Ledge wall | Sqm |  | 1 | 7.98 |  | 1.18 | 9.4164
| Less trashbin | Sqm |  | -1 | 0.88 |  | 1.2 | -1.056
| Total Qty in Sqm | [6 empty] | 8.3604
| Total Qty in Sqft | [5 empty] | 10.764 | 89.9913
| Previous bill Qty | [6 empty] | 0
| This Bill Qty | [6 empty] | 89.9913
22 | Floor Transition S.S. Profile Providing fixing 6mm thick S.S. transition profile strip on junction in flooring as mentioned in the flooring drawing and details. | Rft | 90
| Floor transition profile | rmt |  | 1 | 14.83 |  |  | 14.83
| Total Qty in rmt | [6 empty] | 14.83
| Total Qty in rft | [5 empty] | 3.284 | 48.7017
| Previous bill Qty | [6 empty] | 0
| This Bill Qty | [6 empty] | 48.7017
23 | False Ceiling |  | 0
24 | Gypsum false ceiling (Measurement shall be taken of the plan area only nothing extra for cove or verticle designs upto 3 -8 height) Suspending system and frame work shall match to compliment the layout of A.C. Ducts grills, electrical fire protection wiring fixtures, Return Air grills etc. Rate to include provision of extra frame work needed due to layout refered above and fixtures etc. Rates to include necessary scaffolding. Providing fixing Gypsum Board False ceiling with Saint Gobain ULTRA Main ceiling sections at 1200 c c Cross members at 450 c c. The grid work to be suspended from ceiling with Hangers at every 1200 c c both directions. The Frame work to be as per manufacturer s specifications. False ceiling is finished with 12.5 mm thk. gypsum board for (Saint gobain make) to be screwerd to the frame. The board is finished with fillign the tapered edges of the board with jointing compound and finishing with PAPER tape of INDIA GYPSUM. The ceiling is finished with a top coat as per approved manufacturer. The item includes all necessary cut outs for electrical air conditioning grills and necessary frame work for them. Item includes Cove and curve designs. (Only Plan area is considered for area calculations) Make- Gyproc - Gyp serra | Sqft | 355
| Flat Area | Sqm |  | 1 | 11.4 | 3.87 |  | 44.118
| Less wooden ceiling | Sqm |  | -1 | 7.525 | 1.9 |  | -14.2975
| Curved area | Sqm |  | 1 | 1.8 | 0.6 |  | 1.08
| Fixed seating -2 area Ceiling | Sqm |  | 1 | 1.63 | 2.75 |  | 4.4825
| vertical Patta level 3100 to 2950 | Sqm |  | 1 | 2.305 | 0.15 |  | 0.34575
| vertical Patta level 3100 to 2790 | Sqm |  | 1 | 2.15 | 0.31 |  | 0.6665
| vertical Patta level 3100 to 2790 | Sqm |  | 1 | 1.15 | 0.31 |  | 0.3565
| Total Qty in Sqm | [6 empty] | 36.7518
| Total Qty in Sqft | [5 empty] | 10.764 | 395.5958
| Restricted Qty. | [6 empty] | 355
| Previous bill Qty | [6 empty] | 355
| This Bill Qty | [6 empty] | 0
25 | HDHMR false ceiling HDHMR board ceiling as per drawing and detail supported from existing ceiling with MS framing of 38x38mm hollow pipe with complete fabrication and carpentry | sqft | 500
| wooden ceiling flat | Sqm |  | 1 | 7.525 | 1.9 |  | 14.2975
| Side Vertical | Sqm |  | 2 | 7.525 | 0.2 |  | 3.01
| Side Vertical | Sqm |  | 2 | 1.9 | 0.2 |  | 0.76
| Center vertical | Sqm |  | 2 | 7.525 | 0.2 |  | 3.01
| Center horizontal | Sqm |  | 12 | 1.9 | 0.2 |  | 4.56
| Top | Sqm |  | 1 | 7.6 | 1.9 |  | 14.44
| Total Qty in Sqm | [6 empty] | 40.0775
| Total Qty in Sqft | [5 empty] | 10.764 | 431.3942
| Previous bill Qty | [6 empty] | 194.4786
| This Bill Qty | [6 empty] | 236.9156
26 | Ceiling paint with acrlic emulsion paint | Sqft | 310
27 | Ceiling bottom surface finished with mirror finish acrylic sheets | Sqft | 170
28 | , with 25mm flat PVD profile and | rft | 130
29 | aluminum LED profile | rft | 70
30 | Finishing |  | 0
31 | Ceiling paint Providing applying double (02) coats of approved paint on ceiling including scraping, primer, filling with putty, etc. complete with the final coat with no brush mark to be visible after painting color shade as specified. | Sqft | 530
32 | WALLPAPER Providing and fixing of custom printed wallpaper base with proper oil based paint and putty | Sqft | 65
33 | Wooden Paneling |  | 0
34 | BWP plyboard panelling Providing and fixing of BWP plyboard paneling with necessary wooden battens with complete hardware and fixing from wall and floor | Sqft | 60
| Mirror Wall | Sqm |  | 1 | 3.51 | 3.1 |  | 10.881
| Total Qty in Sqm | [6 empty] | 10.881
| Total Qty in Sqft | [5 empty] | 10.764 | 117.1231
| Restricted Qty | [6 empty] | 60
| Previous bill Qty | [6 empty] | 60
| This Bill Qty | [6 empty] | 0
35 | Plyboard partition Providing and fixing of BWP plyboard boxing partition with necessary wooden battens and fixing from the floor and ceiling | Sqft | 130
| DB wall | Sqm |  | 1 | 1.65 | 2.95 |  | 4.8675
| LHS wall | Sqm |  | 1 | 2.25 | 2.95 |  | 6.6375
| Total Qty in Sqm | [6 empty] | 11.505
| Total Qty in Sqft | [5 empty] | 10.764 | 123.8398
| Previous bill Qty | [6 empty] | 123.8398
| This Bill Qty | [6 empty] | 0
36 | Solid teak wood battens with clear polish- 25 x 50mm size of teak wood | RFT | 140
| Vertical Member | Rmt |  | 8 | 2.01 |  |  | 16.08
| Horizontzl | Rmt |  | 7 | 2.28 |  |  | 15.96
| Total Qty in Sqm | [6 empty] | 32.04
| Total Qty in Sqft | [5 empty] | 3.284 | 105.2194
Previous bill Qty
| This Bill Qty | [6 empty] | 105.2194
37 | 6mm thick mirror to be finished and pasted over plybaord | Sqft | 64
| Mirror in pasted wall | Sqm |  | 1 | 2.01 | 2.28 |  | 4.5828
| Total Qty in Sqm | [6 empty] | 4.5828
| Total Qty in Sqft | [5 empty] | 10.764 | 49.3293
Previous bill Qty
| This Bill Qty | [6 empty] | 49.3293
38 | Misc.
39 | Signage Providing and fixing of acrylic signage with side lit in multi color acrylic - Lucknow | LS | 1
40 | Neon Signage Providing and fixing of Neon signage - Hello | LS | 1
41 | Signage Providing and fixing of Neon Signage on graphic wall | LS | 3
42 | WATERPROOFING |  | 0
43 | Providing and laying a proprietary chemical waterproofing system consisting of polymer-modified acrylic base coating in two coats in form of a slurry (total consumption of 1.5 Kg Sqm) as approved by the PM and as directed by the approved manufacturer of waterproofing coating, with sandwiched fiber mesh and protective screed. The work shall include cleaning the surface, grouting porous surfaces making ‘V’ grooves at junctions , cracks with nonshrink crystalline base cementitious grout, etc. Further including horizontal and vertical surfaces protected with 20mm screeding in 1 4 mortar (1 cement 4 sand), finished in ready to receive Architectural finish, in the correct line, level, and plumb, curing, grouting, testing, etc. all complete to the entire satisfaction of the PM. FLOOR | Sqft | 530
Total Civil And Interior
BOQ for Fire Work for LKN Dom Seating space D-21a
44 | Supply, laying, testing Commissioning of C class heavy duty MS pipe conforming to IS 3589 1239 for hydrent and sprinkler applications including fittings like elbows, tees, flanges, tapers, nuts bolts, gaskets etc. fixing the pipe on the wall ceiling with suitable clamps, U bolt and including painting of two coats of Red Oxide , painting with two or more coats of synthetic enamel paint of Post office red shade complete as required .The installation includes all civil openings , breakages and making good the same. ( Final Quantity Measure as per site after working )
45 | 25 mm dia | Mtr. | 14
| Branches | Rmt |  | 3 | 0.545 |  |  | 1.635
|  | Rmt |  | 1 | 5.52 |  |  | 5.52
|  | Rmt |  | 1 | 4.1 |  |  | 4.1
| Total Qty in Rmt | [6 empty] | 11.255
| Previous bill Qty | [6 empty] | 11.255
| This Bill Qty | [6 empty] | 0
46 | 32 mm dia | Mtr. | 6
|  | Rmt |  | 1 | 1.4 |  |  | 1.4
|  | Rmt |  | 1 | 4.08 |  |  | 4.08
| Total Qty in Rmt | [6 empty] | 5.48
| Previous bill Qty | [6 empty] | 5.48
| This Bill Qty | [6 empty] | 0
47 | 40 mm dia | Mtr. | 3
|  | Rmt |  | 1 | 3 |  |  | 3
| Total Qty in Rmt | [6 empty] | 3
| Previous bill Qty | [6 empty] | 3
| This Bill Qty | [6 empty] | 0
48 | 50 mm dia | Mtr. | 3
|  | Rmt |  | 1 | 5 |  |  | 5
| Main Header Connection | Rmt |  | 1 | 2.5 |  |  | 2.5
| Total Qty in Rmt | [6 empty] | 7.5
| Restricted qty | [6 empty] | 3
| Previous bill Qty | [6 empty] | 3
| This Bill Qty | [6 empty] | 0
49 | Supply, installation, testing and commissioning of Brass ball valves of following sizes as required. 50 mm dia | Each | 1
| ball valve | Nos |  | 1 |  |  |  | 1
| Total Qty in Rmt | [6 empty] | 1
| Previous bill Qty | [6 empty] | 1
| This Bill Qty | [6 empty] | 0
50 | Supply, fixing, testing commissioning of 15 mm dia size ,quartzoid bulb sprinkler heads suitable for 68 degree centigrade rating of the following type Pendant type | Each | 8
| Sprinklar | Nos |  | 8 |  |  |  | 8
| Total Qty in Rmt | [6 empty] | 8
| Previous bill Qty | [6 empty] | 8
| This Bill Qty | [6 empty] | 0
51 | Supply Fixing ISI marked ( IS 15683 ) Portable Fire Exitnguisher, ABC type,finished externally with red enamel paint, complete in all respects including initial fill and wall suspension of following capacity. 6 kg | Each | 1
52 | Supply Fixing ISI marked ( IS 15683 ) Portable fire Extinguisher, Carbon-dioxide type flat base including valve, discharge hose of not less than 10 mm dia. min. 600 mm long complete in all respects including initial fill with C02 gas confirming to IS 307-1966 filled to a filling ratio of not more than 0.667and wall suspension bracket. Capacity 5 Kg. | Each | 1
53 | Supply Fixing ISI marked ( IS 15683 ) Portable fire Extinguisher, k type flat base including valve, discharge hose of not less than 10 mm dia. min. 600 mm long complete in all respects including initial fill. Capacity 6kg | Each | 1
Total Fire Fighting Work
BOQ for HVAC HIgh Side for LKN Dom Seating space D-21a
54 | Ceiling Suspended AHU Supplying, installing, testing and commissioning of double skin construction draw thru type Ceiling Suspended AIR HANDLING UNITS as per specification, each complete with ESP Filter (94% down to 3 microns), pre-filter section (90% down to 10 microns), min 6 Row Deep Chilled water coil of copper tube aluminium fins construction, squirrel cage induction motor, airfoil centrifugal fan belt drive and vibration isolators, coil size shall be selected for a maximum face velocity of 500 feet minute and static pressure shall be as indicated. The motor selected shall be energy efficient having efficiency (IE2) at full load ranging between 82.5% to 92% in accordance with motor rating as per specification. Motor shall be suitable for 415±10% volts, 50 cycles, 3 phase AC supply. Fan motor assembly (as whole) shall be statically and dynamically balanced to grade G 6.3 as per ISO-1940 AMCA 204-3.All units shall be complete with opposed blade volume control dampers at oulet. Duct flexible connector (fire proof) shall be provided at outlets of AHU. ( Temporary bypass arrangement in Chilled Water Line with related accessories to be considered to facilitate flushing during precommissioning and commissioning of the System). AHU Tag. Description AHU CFM TR ESP Motor HP AHU-01 Sitting area 2500 cfm 5 15 mm 2 | No. | 1
| AHU | Nos |  | 1 |  |  |  | 1
| Total Qty in Rmt | [6 empty] | 1
Previous bill Qty
| This Bill Qty | [6 empty] | 1
Total HVAC High Side
BOQ for HVAC Low Side for LKN Dom Seating space D-21a
55 | (FOR FACTORY FABRICATED DUCTS AS PER “SMACNA” STANDARDS SPECIFICTIONS) |  | 0
56 | Supply, Fabrication, installation and testing of factory fabricated sheet metal ducts with sleeve joints and supports complete with the approved shop drawings and as required by the specifications and hanging of the ducts to be done by thread wire on metal cushion with gripple support. |  | 0
57 | 24G sheet | sq.m | 40
58 | 26G sheet | sq.m | 5
59 | Supplying and erecting GI sheet of fabricated at site and mentioned guage to be used for fabrication of ducting complete with neoprene rubber garkets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required 24G sheet | sq.m | 5
60 | Supply, installation, testing and balancing of powder coated Extruded Aluminium Supply air Grilles with volume control dampers in accordance with the approved shop drawings and specifications. (Minimum Chargable area would be 0.1 Sqm Per Pc) | SQMT | 1
61 | Supplying fixing of opposed blade volume control dampers in supply air duct collars as per approved drawings and specifications. Volume control damper shall be provided at the junction of each branch duct with main duct. Dampers shall be 2 gauge heavier than the gauge of large duct but should not be less than 20 gauge, and shall be rigid in construction so as not to flutter with the passage of air. | SQMT | 1
62 | Supply, fabrication, installation and testing the flexible connections constructed of fire resistance flexible double canvas sleeve as per the approved shop drawings. | Nos. | 1
63 | Supply, installation, testing and balancing of powder coated Extruded Aluminium Return air Grilles without volume control dampers in accordance with the approved shop drawings and specifications. (Minimum Chargable area would be 0.1 Sqm Per Pc) | sq.m | 2
64 | Supply, installation and testing of Acoustic lining with Open cell nitrile rubber with in supply and return air ducts of specified thickness as per the specifications. All ducts shown cross hatched on the approved shop drawings shall be provided with acoustic lining as perthe specifications 15 mm thick | sq.m | 10
65 | Supplying and fixing of following thickness duly laminated aluminum foil of mat finish closed cell Nitrile rubber(Class“O”) insulation on existing duct after applying suitable adhesive for Nitrile rubber. The joints shall be sealed with 50mm wide and 3mm thick self adhesive nitrile rubber tape insulation complete as per specifications and as required. 19mm thick | sq.m | 40
66 | Supplying, installing and testing of UPVC pipe ( heavy duty) with 6 mm thick nitrile rubber insulation with protective coating on condensing water piping and fitting like bends, elbow, tee and union, etc. as per the approved shop drawings and specifications. 25mm Dia | Rmt | 5
67 | Supply ,Installation ,Testing and commissioning of ERW heavy duty C Class MS pipes as per IS-1239 upto 6 dia. and as per IS-3589 above 6 dia. cut to required lengths and installed with all welded joints, complete with necessary pipe hot dip galvanized MS supports, GI hangers with rubber lined universal clamps and hangers , fittings like bends, elbows, tees, reducers, matching flanges, neoprene 6 mm thick gaskets, hot dipped galvanized nut blots washers ,PUF gutti with U clamp, socket and fittings for instruments and sensors connections etc. ERW pipes shall be with two coats of Zinc Chromate paint for anti-rust including all fittings like valves, flanges and unions, etc. Note Pipe Measurement are in Pair (Supply + Return) . Quoted rates shall be inclusive of the cost of piping Insulation of Class O rated thermal insulations with one sided factory laminated glass clothed Nitrile Rubber insulation with density 45-60 kg m3 with covered with two coats of UL Listed lag coating (Low VOC) Anti-fungal, Anti-microbial vapour barrier for line item sealed with acrylic based food grade sealant. 32 mm dia MS Pipe with 25 mm thick Insulation | Rmt | 10
68 | Providing and fixing in position following ball valves 32 mm dia valves | Nos. | 2
69 | Providing and fixing in position the following ‘Y’ Strainers 32 mm dia strainers | Nos. | 1
70 | Supplying, installation, testing and commissioning of Auto air vents . 25 mm dia pipes | Nos. | 1
71 | Providing and fixing in position SS 304 the industrial dial type pressure gauges with gun metal valves. | Nos. | 2
72 | Providing and fixing in position SS 304 the mercury-in- glass industrial dial type thermometers. | Nos. | 2
73 | Supply, installation, testing and commissioning of THERMOSTAT for cooling. The thermostat shall be electronic room temperature controller with digital display fan speed control, capable of providing individual space temperature control for cooling application. The controller shall produce a dual output to cooling coils in response to load change in rooms. The controller shall be designed to modulate two control devices such as 2 way motorized valves for chilled water duty . (minimum of 5 Deg F dead band ) | No. | 1
74 | Supply, installation, testing and commissioning of Electronic Self Balancing Valve pressure independent with independent type dynamic balancing valve for AHUs with integrated 2 way modulating control valves in a single body. The actuator shall be capable of accepting 2-10 VDC 4-20 mA electric signal and shall provide similar transduced feedback output signal to control system for flow measurement. The minimum close off pressure actuator must be 1.5 times shut off head of pump 5 bars whichever is maximum. The valves shall be suitable for following pipe sizes 32 mm dia | No. | 1
75 | Supply, Installation, Testing and Commissioning of BMS compatible ultrasonic BTU Meter complete with flanged type water flow meter (pressure drop across water meter not exceeding 0.1 bar at the specified nominal flow rate), temperature sensors, LCD display panel, inbuilt Lithium battery backup with minimum six years life. The units shall be capable to calculate and store maximum values, display flow rates and temperature difference across supply and return. The quoted price shall be inclusive of necessary wiring, conduiting between the flow meter and the display panel. The unit shall be housed in a totally tamper proof box. The size of the BTU meter is as under 32 mm dia BTU Meter | No. | 1
76 | CONTROL PANEL FOR AHU (WITH DOL SD STARTER) Design, manufacture, supply, installation, testing and commissioning of the following cubicle type, dead front, sheet steel, wall mounted control panels including anchoring into the wall, wiring, incoming, earthing terminating into MCCB in each panel shall be provided by the electrical contractor. All internal wiring power cabling and copper earthing of air handling unit motors from the panel shall be included. All outgoing shall be provided with Stop Manual Auto selector switch to facilitate operation through BAS. All starters shall be provided with potential free Contact for Connections to Building Automation System. The panel shall include the following components and accessories. a)MCCB as per the ratings given below, suitable for motor duty and able to withstand fault level of 20 KA. b)DOL SD starter as per HP ratings c) Terminal block for power distribution. d) Contactor, over load relay with built in single phasing protection. e) Phase indicating lights and indicating light for ON status. f) Digital voltmeter and digital ammeter with selector switches. g) Time delay relay for delayed automatic restart of air handling unit motor. h) For on off remote and local operation , 3 pole single throw switch shall be provided in each AHU panel to facilitate override of the automatic operation. i) All starters shall be provided with suitable potential free contract for connections to the Building Automation System . The number of AHU FAN control panels shall be as follows . 2 HP DOL Starter | No. | 1
Total HVAC Low Side
BOQ for Electrical Work for LKN Dom Seating space D-21a
77 | DISTRIBUTION BOARDS 6 WAY V-TPN DB - LPDB Incomer 63A, FP, MCB, 10kA 1 Nos Sub Incomer 32A, DP, RCCB, 100mA 3 Nos Outgoings 6 10 16 A SP MCB C Type - 18 Nos. | Nos. | 1
| Distribution board |  |  | 1 |  |  |  | 1
| Total qty in nos | [6 empty] | 1
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 1
78 | MV CABLES
79 | POWER CABLING Supply and laying, effecting proper connections, testing commissioning of the following sizes of 1.1 KV XLPE FRLS armoured unarmoured PVC insulated PVC sheathed aluminium copper conductor cables conforming to IS 1554 and IS 694 for Flexible copper cable Part I - 1976 with latest amendments laid over MS supports in existing RCC ducts laid in ground laid on Cable Trays including clamping the cables to supports in an approved manner as required complete with all accessories.All cables shall have thermo setting insulation XLPE and low emission of smoke and corrosive gas when affected by fire . Necessary Markers shall be provided at the intervals as per the specifications. CU Flexible Cables 4C x 6 Sq.mm. | Mtr. | 30
| 10mm Power Cable DB To electric Metre | Rmt |  | 3 |  |  |  | 3
| Total qty in Rmt | [6 empty] | 3
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 3
80 | CABLE TERMINATION - Making cable and terminations including brass single compression glands and crimping type copper lugs for cable sizes mentioned below for aluminium or copper. |  | 0
81 | 3.5C x 70 Sq.mm. AL | Nos. | 2
82 | 4C x 6 Sq.mm. | Nos. | 2
| Distribution board |  |  | 2 |  |  |  | 2
| Total qty in nos | [6 empty] | 2
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 2
83 | POINT WIRING
84 | Point wiring LENGTH from DB to SB or First Light point control be MCB shall be avg. of 15Mtr. of 3C x 2.5 sq mm FRLS PVC insulated stranded copper conductor wires. For SB to SB the length shall be measured in Mtr. The secondary Loop point length shall be 10Mtr from Light fixture to light fixture. If secondary point shall be operated from MCB then the length shall be 10 Mtr. All sockets to be checked with a Check Plug socket tester for live-neutral reverse, no earth,neutral fault, live earth reverse, neutral earth reverse. The Circuit No. and DB no. label shall be provided on all UPS ,RAW sockets and switchboards with label printer . The Length shall be paid as per the actual measurements as per following manner. Wiring for the following light points with 3 x 2.5 Sq.mm FRLS PVC insulated stranded copper conductor wires in GI conduits in F.ceiling walls ceiling as direc-ted including providing 6 amps flush type switches, 5 sided G.I Boxes for housing switc-hes and earth- ing complete as required from the above switch board. Rates shall exclusive of Switches Switch Box. (FROM SB TO LIGHT)
85 | First point controlled by one no. 6 amp switch. (upto 10Mtr.) | Nos. | 15
| Distribution board to SB |  |  | 11 |  |  |  | 11
| Total qty in nos | [6 empty] | 11
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 11
86 | First point controlled by one no. 6 amp switch. For Emergency Light (upto 10Mtr.) | Nos. | 6
87 | Same as item No. 4.2.1 4.2.2 above but LOOP POINT i.e. wiring of point looped from first point with 3C x 2.5 sq. mm FRLS PVC insulated copper conductor wire in concealed exposed GI conduit and earthing | Nos. | 12
| Main SB to Looping |  |  | 11 |  |  |  | 11
| Total qty in nos | [6 empty] | 11
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 11
88 | Same as item No. 4.2.3 4.2.4 above but LOOP POINT i.e. wiring of point looped from first point with 3C x 2.5 sq. mm FRLS PVC insulated copper conductor wire in concealed exposed GI conduit and earthing For Emergency Light | Nos. | 8
89 | First point controlled by existing MCB in D.B. | Nos. | 10
| MCB to DB |  |  | 10 |  |  |  | 10
| Total qty in nos | [6 empty] | 10
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 10
90 | Same as item No.4.5.1 above but LOOP POINT i.e. wiring of point looped from first point with 3C x 2.5 sq. mm FRLS. insulated copper conductor wire in concealed exposed GI conduit and earthing | Nos. | 30
| Looping |  |  | 11 |  |  |  | 11
| Total qty in nos | [6 empty] | 11
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 11
91 | Wiring for UPS Raw plug outlets points with 3C x 4 sqmm FRLS PVC Insulated and PVC sheathed flexible cable with bright annealed electrolytic copper conductor , 1100 volt grade confirming to IS 694-1990 with latest amendments, in existing Channels conduit in ceiling walls floor including all cable termination accessories) (including body earth for GI boxes) | Mtr. | 200
92 | Wiring for UPS Raw plug outlets points with 4C x 4 sqmm FRLS PVC Insulated and PVC sheathed flexible cable with bright annealed electrolytic copper conductor , 1100 volt grade confirming to IS 694-1990 with latest amendments, in existing Channels conduit in ceiling walls floor including all cable termination accessories) (including body earth for GI boxes) | Mtr. | 125
93 | 20 mm dia GI Conduit | Mtr. | 100
| In ceiling |  |  | 27 |  |  |  | 27
|  |  |  | 18 |  |  |  | 18
| floor |  |  | 17 |  |  |  | 17
|  |  |  | 18 |  |  |  | 18
|  |  |  | 15 |  |  |  | 15
|  |  |  | 5 |  |  |  | 5
| Total qty in Rmt | [6 empty] | 100
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 100
94 | MODULAR SWITCHES Supply, installation, testing commissioning of following types of modular switches, cover plates, 5 sided G.I. Boxes for housing the modular switches earthing complete as required. GI Boxes to have earth pin for body earthing. The Circuit No. and DB no. label shall be provided on all UPS ,RAW sockets and switchboards with label printer.(Make- Legrand Aretor Series) |  | 0
95 | 6A One Way Switch | Nos. | 22
| One way switch |  |  | 18 |  |  |  | 18
| Total qty in Rmt | [6 empty] | 18
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 18
96 | 6A 5 pin Socket - 1Nos. 6A Switch - 1Nos. | Nos. | 22
| 6a switch socket |  |  | 18 |  |  |  | 18
| Total qty in Rmt | [6 empty] | 18
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 18
97 | GENERAL EARTHING Supplying and erecting bare Copper conductor of following sizes 8 SWG | Mtr. | 30
98 | LIGHT FIXTURES INSTALLATION Receiving from Store, Installation, testing commissioning of following light fixtures with complete installation hardwares including Anchor fastner, supporting Hook Rods as per final approval from Architect Client Consultant |  | 0
99 | DOME LIGHT | Nos. | 13
100 | CYLINRICAL SURFACE MOUNT LIGHT | Mtr. | 36
101 | MISCELLANEOUS WORKS |  | 0
102 | Supply fixing in position approved shock treatment chart written in English, Hindi and Local language. These charts shall be framed in wooden frame covered with clear glass. | Nos. | 1
103 | Supply fixing in position the best quality danger notice boards of approved shape size as reqd. by the local Electrical Inspecting Authority written in English, Hindi local language. | Nos. | 1
104 | CCTV System
105 | 2 Megapixel Fixed Lens Camera IR Dome Type 1 2.8 Progressive Scan CMOS, 1920 × 1080 at 25fps, 2.8mm Fixed lens, 0.028 Lux at F1.2, ICR, ONVIF, support H.265, H.264, MJPEG, 120db WDR, 3D Digital Noise Reduction, Three individually configurable stream, 12 VDC PoE, IR range 40m, Support on-board storage up to 128 GB (SD card not included), IP67, IK10, Edge Anlalytics- Line crossing detection, Intrusion detection, Motion detection, Scene change detection, video tampering, UL, CE, FCC certified. | Nos. | 4
106 | NVR 16 Channel Connect Up to 16 IP Cameras, Dual OS, Up to 8 Megapixels Resolution, HDMI output with 4k output and VGA output with 2MP Output , Support H.265,H.264, MJPEG, Incoming Bandwidth 160 Mbps, 4 SATA Hard Disks, ANR Technology, 2 SATA interfaces for 2 HDDs and capacity of each HDD upto 6TB, 2 USB at least 1 × USB with 3.0, Serial interface 1 RS-485, 1 RS-232, Alarm I O 16 4, 2 RJ-45 10 100 1000 Mbps self-adaptive Ethernet interface, Multiple network monitoring Web viewer, CE, FCC, UL certified. | Nos. | 1
107 | 16 Port Network Switch Gigabit POE 16 × gigabit PoE ports, 1 × gigabit RJ45 port, and 1 × gigabit SFP fiber optical port, IEEE 802.3at af standard | Nos. | 1
108 | CAT 6 Connector | Nos. | 8
109 | Hard Disk 6 TB | Nos. | 2
110 | Suplly installation of Computer system as required | Nos. | 1
111 | Installation labour charges | Job | 1
112 | Supply, Drawing and Testing of 4 pair ,100 Ohm, 24 AWG UTP Cat 6 Cable as per latest amendments of TIA EIA 568 B.2 specifications for Data Telephone points in existing MS PVC conduits including making connections to Information outlets and patch panels with ferruling at both ends for identification with necessary tools for punching ,stripping crimping and testing as required | Mtr | 80
| Cat 6 Wire for CCTV -1 | Rmt |  | 1 | 25 |  |  | 25
| Cat 6 Wire for CCTV -2 |  |  | 1 | 22 |  |  | 22
| Cat 6 Wire for CCTV -3 |  |  | 1 | 20 |  |  | 20
| Cat 6 Wire for CCTV -4 |  |  | 1 | 26 |  |  | 26
| Total qty in Rmt | [6 empty] | 93
| Restricted qty | [6 empty] | 80
| previous qty | [6 empty] | 0
| This Bill qty | [6 empty] | 93
113 | Supply and laying of HDMI Cabel | Nos. | 1
114 | Supply and Laying of RIGID PVC Medium Duty Conduits ISI marked conduits complete with accessories such as bends, junction boxes, pull boxes etc., in recess or on surface including cutting chases in the walls floors and making good the same complete as required. 25 mm dia | RM | 32
115 | Supply , Installation, Testing and Comissioning of Wall mounted Communication rack with glass doors, handles ,lock , Top and Bottom Cable entries, Supports for mounting rack on wall , Cable managers, one Fan, Equipment mounting hardware, power supply box for supplying power to switches, fans etc along with earth continuity kit, Mcb, indicator, moulded power supply cable . 12U(44 mm ) wall mounted | Nos. | 1
116 | UPS System Supply,Installation, testing and commissioning of following type of Online UPS Inverter as per drawings and specifications with all other accessories. Online UPS 1.2.0KVA UPS12V DC 25AH maintenance free batteries for 30 minutes battery backup. Input supply voltage -230-250 Volts Output voltage -220-240V+ -1% Voltage Regulation -Less than or equal to + - 1% Output frequency -50 Hz + - 0.05 Hz Type of cooling -Forced air cooled Invertor Efficiency -Better than 85% Output Power factor -0.8 | Nos.
Total Electrical Work