## Summary Sheet
Summary Sheet KFC T1 @ Foodcourt
Semolina Project Pvt Ltd.
Vendor Name : Pikture Perfect Design Studio Pvt. Ltd.
PO No: Semolina/PO/24-25/000588
Sr no | Description | PO value | Previous Bill Amount | Present Bill Amount | Cumulative Amount | Variance Amount
1 | Plumbing Work | 737075 | 0 | 373992.5 | 373992.5 | 363082.5
2 | Electric Work | 1692951 | 0 | 1233983 | 1233983 | 458968
3 | Fire Sprinkler System | 258450 | 0 | 48300 | 48300 | 210150
4 | Fire Detection | 186600 | 0 | 122275 | 122275 | 64325
5 | Civil Interior | 1603495.2 | 0 | 544952.2186 | 544952.2186 | 1058542.9814
6 | HVAC High Side | 343400 | 0 | 343400 | 343400 | 0
7 | Hvac Low Side | 953350 | 0 | 805055 | 805055 | 148295
8 | Lighting | 52450 | 0 | 0 | 0 | 52450
9 | CCTV | 113400 | 0 | 21000 | 21000 | 92400
| Total | 5941171.2 |  | 3492957.7186 | 3492957.7186 | 2448213.4814
| GST 18 % | 1007598.816 |  | 566920.3893 | 566920.3893 | 440678.4267
| GST 28% | 96152 |  | 96152 | 96152 | 0
| Gross Total | 7044922.016 |  | 4156030.108 | 4156030.108 | 2888891.908

## Measurement Sheet
Sr. No. | 1 |  | Name of site In charge : | [6 empty] | Ashish Nagar
PO No.: | Semolina/PO/24-25/000588 |  | Agency Name : |  | Document No.: MIAL/EN-CL/FMT/01 Issue No. : 01 Issue Date: 22-Apr-15 Revision No. : 00 Revision Date: Nil |  |  |  |  | TFS
PO Date : | 2024-07-09 |  | Date : 12-09-2024
PO Validity : |  |  | Name of Work: MUM T1 KFC T1C FC
Measurement Sheet No. of this PO: | 1 |  | Period of work Executed : Sept'24
PLUMBING WORK | [8 empty] | Total Qty
SR. NO. | MATERIAL | DESCRIPTION | UNIT | QTY. | No. | Length | Breadth | Height |  | Claimable % | Claimable Qty
1 |  | WATER SUPPLY PIPES
| CPVC Pipes | Supply, laying, testing & commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia, jointing with CPVC solvent cement of medium body IPS brand or equivalent conform. (Make – SUPREME / KASTA)
1.01 |  | 15mm dia | R.M. | 20 |  | 19.5 |  |  | 19.5 | 97.5% | 19.5
1.02 |  | 20mm dia | R.M. | 45 |  | 44 |  |  | 44 | 97.78% | 44
2 |  | WATER DRAIN PIPES
| PVC WASTE PIPE | PVC Plastic Pipe for Drainage (Make – SUPREME / KASTA)
2.01 |  | 100mm dia | R.M. | 0 |  |  |  |  | 0
2.02 |  | 50mm dia | R.M. | 0 |  |  |  |  | 0
3 |  | CHAMBER & GRATING
3.01 | INSPECTION CHAMBER | Supply, Laying, Testing & Commissioning of Approved SS Inspection Chamber along of Size- 300mmx300mm with SS Cover & SS Grating over it. Make Jaquar / Ozone. | Nos. | 7 | 4 |  |  |  | 4 | 57.14% | 4
4 |  | FLOOR TRAP | [6 empty] | 0
4.01 | FLOOR TRAP | Supply, Laying, Testing & Commissioning of 100x100mm Floor Trap with Approved Make heavy duty round or Square. | Nos. | 8 | 8 |  |  |  | 8 | 100% | 8
5 |  | VALVE AND TAP
5.01 | ANGLE VALVE | Providing & Fixing Angle Valve. | Nos. | 20 |  |  |  |  | 0 | 0% | 0
5.02 | LONG BODY TAP | Providing & Fixing Sink Cock. (Make – JAQUAR / OZONE) | Nos. | 12 |  |  |  |  | 0 | 0% | 0
5.03 | TAP | Providing & Fixing Sink Cock. (Make – JAQUAR / OZONE) | Nos. | 0 |  |  |  |  | 0
5.04 | Gate Valves | Providing & Fixing CPVC Ball Valve ISI mark. (For Inlet) (Make – KITZ / ZOLOTO / AUDCO) 20mm Dia | Nos. | 2 |  |  |  |  | 0 | 0% | 0
5.05 | Single Lever Mixer | Providing and fixing 15mm C.P. Single lever wall mixer for 3 Bowl Sink. (Jaguar-Continental make.) | Nos. | 1 |  |  |  |  | 0 | 0% | 0
6 |  | ACCESSORIES | [6 empty] | 0
6.01 | Grease Trap | Providing & Fixing of portable grease trap NGT-8,14,50 from Nugreen | Nos. | 5 | 2.5 |  |  |  | 2.5 | 50% | 2.5
6.02 | SS Sink | Providing & Fixing 304 Grade SS Sink of Size as per detailed drawing | Nos. | 0 |  |  |  |  | 0
6.03 | Bottle Trap | Providing & fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR / OZONE) | Nos. | 2 | 0 |  |  |  | 0 | 0% | 0
6.04 | S.S. GRATING | Providing & Fixingof S.S. triple layer grating for the drain as per drawings. | Nos. | 3 | 3 |  |  |  | 3
6.05 | Waste Coupling | Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. (Make – JAQUAR / OZONE) | Nos. | 1 | 0 |  |  |  | 0 | 0% | 0
6.06 | GEYSER STORAGE | Geyser(Providing & fixing)RECOLD MAKE
|  | 35 LTR | each | 1 | 1 |  |  |  | 1 | 100% | 1
|  | 15 LTR | each
|  | 6LTR (INSTANT GEYSER) | each | 2 | 1 |  |  |  | 1 | 50% | 1
6.07 | PVC WATER TANK | Providing & Fixing of PVC water, vertical type storage tanks of the approved quality Make Sintex, including making solid supported flat base as per instruction but in masonary work, and doing all connections as required. Item also inculding the lockable system require for food safety. | [6 empty] | 0
|  | 5000 LTR. | Each
|  | 2000 LTR. | Each
|  | 1000 LTR | each | 1 | 0 |  |  |  | 0 | 0% | 0
|  | 500 LTR | each
|  | 200 ltr | each | [5 empty] | 0
SUB TOTAL OF WATER SUPPLY
6.08 | WATER MOTOR | P/f of 1HP water motor. | No | 1 |  |  |  |  | 0 | 0% | 0
6.09 | 03 BOWL SINK CONNECTION | Providing and fixing 3-Bowl Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 |  |  |  |  | 0 | 0% | 0
6.1 | SINK CONNECTION | Fixing Hand Wash Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 |  |  |  |  | 0
6.11 | SINK CONNECTION | Providing and fixing Veg. Prep. Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 |  |  |  |  | 0 | 0%
6.12 | FRESH AIR MACHINE CONNECTION | Connection of fresh air overflow. Complete in all respects. | No | 1 | 1 |  |  |  | 1 | 100% | 1
6.13 | MAIN CONNECTION with airport drain line | Making connection to existing sewer/storm water drains including excavation,cutting of manhole walls and making good the same,modifying drain channels etc.complete in all respects. A)150 to 300 mm dia connection. | No | 1 | 1 |  |  |  | 1 | 100% | 1
6.14 | PVC 50MM DIA PIPE | Providing, laying and jointing 50mm dia. PVC pipes complete (PRINCE) with PVC fittings and clamps, including cutting and making good the walls and floors, wherever necessary etc., complete. | Rm | 10 | 10 |  |  |  | 10 | 100% | 10
6.15 | CORNER WASH BASIN | Providing and fixing corner China Counter top - Bowl type wash basin of size as/dwg for over the counter mounting, 32mm dia C.P. waste, C.P. chain and rubber plug, 32mm C.P. cast brass bottle trap and pipe to waste pipe. Rubbic (CAT NO-91041) Hindware make | Nos | 0
6.16 | Pressure Pump | 0.5 HP Crompton Make Pressure Pump | Nos | 1 | 0.5 |  |  |  | 0.5 | 50% | 0.5
6.17 | Ro Plant |  | Nos | 1 |  |  |  |  | 0
6.18 | Rodding of Existing drain Line | Rodding and clearing of existing drain line | Job | 1 | 1 |  |  |  | 1 | 100% | 1
6.19 | Changing of main drain line | Removing of existing main drain line from core cut to main line. ( GI to SMR UPVC) | Job | 1 | 1 |  |  |  | 1 | 100% | 1
Electrical Works
| S. No. | Description | Unit | Qty. | [5 empty] | Claimable % | Claimable Qty
Design, fabrication, assembling, wiring , supply , Erection , Installation , testing and commissioning of MDB Panels fabricated out of 2mm thick for structural members (Load bearing members) and 1.6mm thick for door and covers (Non load bearing members) CRCA painted sheet steel in cubicle formation with reinforcement of suitable size angle iron, channels, T irons, flats wherever necessary for large meter boards. Cable gland plates shall be provided at top and bottom both and windows for meter reading, locking arrangement (pad-lock & seal) with wiring upto KWH meter & meter to MCB shall be done by using adequately rated flexible single core copper wire. The boards shall be treated with all anticorrosive process before painting as per standards with final approved shade of powder coated as approved, 2 nos. earthing terminals shall be provided for all panels. The boards shall be suitable for 415 V, 3 phase, 4 wire, 50 Hz supply system. Boards shall be fabricated in length, height, depth etc to match with site conditions.
|  | An approval shall be taken for each panel before manufacturing. Galvanised hardwares with zinc passivation shall be used in fabrication of boards. | [6 empty] | 0
0
Note: The following provisions shall be required to be made in the switchboard detailed below
|  | The Switchboard shall have provision for entry of all PVCA cables from the top/bottom as required. | [6 empty] | 0
0
All live accessible parts shall be shrouded and all equipment shall be finger touch proof. The busbar insulation shall be with heat shrinkable sleeves. SMC/DMC shrouds and busbar supports shall be used.
Suitable tinned copper extension links for incoming/outgoing cables shall be provided wherever required
Control circuits includes breaker control switch, auto manual selector switch, anti pumping relay, spring charging trip indication, TIMER, control wiring, Auxiliary contactors MCB’s as required at site.
Positive isolation of all breakers.
All fault level breaking capacity indicates shall be ICS value at 415 volts (ICS = ICU = ICW = 100%).
Space Heater/ light/air filter shall be provided for each vertical compartment
0
|  | Link and drops from MCCB shall be designed for full rated current of MCCB ratings at same current density as of Main Bus Bar | [6 empty] | 0
2 nos. GI earth strip throughout the panel.
| 1 | Main Panel
| A | Incoming | [6 empty] | 0
|  | 1 No. 250 amps 16 kA 440 volt FP MCCB with Thermal Magnetic overcurrent and short circuit and with following | [6 empty] | 0
0
| B | Metering, Indication & Protection: | [6 empty] | 0
| a | 1 Nos. 6 Parameter Multi Function Mater with 3 Nos. Cast Resin CTs and MCBs
| b | Breaker ON OFF indication Lamps
| c | R-Y-B indication lamps with MCBs
| d | ELR with CBCT | [6 empty] | 0
| C | Bus Bar:
300 A, TPN Al. Bus Bar of suitable length having Current density 1Amp/sq.mm & having high conductivity electrical grade suitable to withstand symmetrical fault level of 25 kA. Neutral busbar shall be of 100% capacity.
| D | Outgoings: | [6 empty] | 0
0
| a | 9 No. 63 amps 4P MCB ( Type C)
| b | 2 No. 40 amps 4P MCB ( Type C)
| c | 4 No. 25 amps 4P MCB ( Type C) | [6 empty] | 0
| d | 3 No. 25 amps 4P MCB ( Type C) | [6 empty] | 0
0
| e | 1 No. 40 amps 2P MCB ( Type C) | [6 empty] | 0
| f | 5 No. 32 amps 2P MCB ( Type C)
| g | 2 No. 25 amps 2P MCB ( Type C)
|  | Main MDB as described above (Repairinf and replacing of damaged material in existing panel and re painting) | 1 | Set | 0.8 |  |  |  | 0.8 | 80% | 0.8
| 1.1 | DISTRIBUTION BOARDS
Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof double door type distribution boards constructed from 16 SWG sheet steel IP 42 construction, finished with rust proof duly powder coated in approved shade with hinged gasketed door and housing the following complete with P.V.C. insulated copper busbars rated 200 amp with interconnections, neutral and earth bar assembly per phase, earthing terminals complete as approved by Architects.
Note : All MCBs in distribuition board for power circuits shall be of C curve
| i | Type A | [6 empty] | 0
0
|  | 1-63 amp FP MCB with 3 single phase banks each comprising of 63A DP RCCB(100 mA) and 6 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 2 | Set | 1.5 |  |  |  | 1.5 | 75% | 1.5
| ii | Type B
|  | 1-40 amp DP MCB + DP RCCB ( 100mA) and 8 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 0.75 |  |  |  | 0.75 | 75% | 0.75
| iii | Type C
|  | 1-32 amp DP MCB + DP RCCB ( 100mA) and 12 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 0.75 |  |  |  | 0.75 | 75% | 0.75
| iv | Type D
|  | 1-32 amp DP MCB + DP RCCB ( 100mA) and 8 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 0.75 |  |  |  | 0.75 | 75% | 0.75
| v | Type E
|  | 1-25 amp DP MCB + DP RCCB ( 100mA) and 6 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | RO | Set |  |  |  |  | 0
| 2 | Supply installation testing and commisioning 3.0 kVA online ( 1ph input and 1ph output) UPS with 15 Min power back up complete with in buit Static by pass switch , Mannual external maintenance by pass switch , Rectifiers , Sealed MF batteries etc as required | 2 | No. | 0 |  |  |  | 0 | 0% | 0
| 3 | Supply, laying, testing & commissioning of following sizes of Al/Cu. conductor 1.1 kV grade, armoured, XLPE insulated FRLS LT Cables/ Control Cables including necessary cleats, clamps etc. (Cables shall be partly laid in Pipes, O/H cable tray, on wall as required )
| 3.1 | 3.5C – 150.0 (Al.) FRLS Armoured XLPE Cable * | 50 | Mtrs |  |  |  |  | 0 | 0% | 0
| 3.2 | 4C – 10.0 (Cu.) FRLS Armoured XLPE Cable | 40 | Mtrs | 38 |  |  |  | 38 | 95% | 38
| 3.3 | 4C – 6.0 (Cu.) FRLS Armoured XLPE Cable | 20 | Mtrs | 20 |  |  |  | 20 | 100% | 20
0
| 3.4 | 4C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 60 | Mtrs | 60 |  |  |  | 60 | 100% | 60
| 3.5 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 70 | Mtrs | 70 |  |  |  | 70 | 100% | 70
* Approximate and shall be as per point of supply from Airport Panel/ Isolator
| 4 | Supply, erection, testing & commissioning of following sizes of cable end terminations with Single compression gland for 1.1 kV grade, XLPE insulated, Al/Cu Conductor cable
| 4.1 | 3.5C – 150 (Al.) FRLS Armoured XLPE Cable *(Double Compression) | 2 | Nos. | 2 |  |  |  | 2 | 100% | 2
| 4.2 | 4C – 10.0 (Cu.) FRLS Armoured XLPE Cable | 4 | Nos. | 4 |  |  |  | 4 | 100% | 4
| 4.3 | 4C – 6.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 2 |  |  |  | 2 | 100% | 2
| 4.4 | 4C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 4 | Nos. | 4 |  |  |  | 4 | 100% | 4
| 4.5 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 6 | Nos. | 6 |  |  |  | 6 | 100% | 6
| 5 | Wiring for DB Submains with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in surface/concealed MS surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and making suitable end termination with copper lugs complete as required and as below
| 5.1 | 4 x 16 sq.mm + 2 No. 6.0 Sq. mm in 40 mm dia MS Conduit | 20 | Mtrs | 18 |  |  |  | 18 | 90% | 18
| 5.2 | 4 x 10 sq.mm + 2 No. 4.0 Sq. mm in 32 mm dia MS Conduit | 60 | Mtrs | 57 |  |  |  | 57 | 95% | 57
| 5.3 | 4 x 6 sq.mm + 2 No. 4.0 Sq. mm in 32 mm dia MS Conduit | 15 | Mtrs | 15 |  |  |  | 15 | 100% | 15
0
| 5.4 | 2 x 6 sq.mm + 1 No. 4 Sq. mm in 25 mm dia MS Conduit | 110 | Mtrs | 80 |  |  |  | 80 | 72.73% | 80
| 5.5 | 2 x 4 sq.mm + 1 No. 2.5 Sq. mm in 25 mm dia MS Conduit | 325 | Mtrs | 240 |  |  |  | 240 | 73.85% | 240
| 6 | Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required
| 6.1 | 50X6 mm GI Strip | 15 | Mtrs | 0 |  |  |  | 0 | 0% | 0
| 6.2 | 25X6 mm GI Strip | 20 | Mtrs |  |  |  |  | 0 | 0% | 0
| 6.3 | 25X3 mm GI Strip | 50 | Mtrs | 48 |  |  |  | 48 | 96% | 48
| 6.4 | 8 SWG Copper Wire | 80 | Mtrs |  |  |  |  | 0 | 0% | 0
| 6.5 | 8 SWG GI Wire | 125 | Mtrs |  |  |  |  | 0 | 0% | 0
| 6.6 | 1 Core 6.0 Sq. Mm FRLS Green Wire | 60 | Mtrs | 60 |  |  |  | 60 | 100% | 60
| 7 | Supply, erection, testing & commissioning of prefabricated GI Perforated type cable trays including Tees / Bends / Crossing / Reducers / Couping to be laid in cable trench, overhead on wall or hanged from ceiling complete with all accessories as required including support at every 1500mm as required
| 7.1 | 150 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 50 | Mtrs | 10 |  |  |  | 10 | 20% | 10
| 7.2 | 300 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 30 | Mtrs | 30 |  |  |  | 30 | 100% | 30
| 7.2 | 450 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 10 | Mtrs | 0 |  |  |  | 0 | 0% | 0
| 8 | Wiring for MCB controlled normal primary light points/ Wall Point/ Floor Point with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 5 | Pt | 5 |  |  |  | 5 | 100% | 5
| 9 | Wiring for secondary MCB controlled normal light points/ Wall Point/ Floor Point( Looped from above point) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 15 | Pt | 15 |  |  |  | 15 | 100% | 15
| 10 | Wiring for MCB controlled Emergency primary light points/ Wall Point/ Floor Point with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 2 | Pt | 2 |  |  |  | 2 | 100% | 2
0
| 11 | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 6 | Pt | 6 |  |  |  | 6 | 100% | 6
| 12 | Wiring for switch controlled Normal primary light points with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25 mm 16SWG MS Heavy Duty PVC concealed/surface conduit including cost of cutting and filling chases for recessed conduiting and supports in case of Surface conduit including all bends , saddles , Junction boxes etc. including the cost of running 2.5 sq. mm PVC insulated copper conductor wire for loop earthing etc. and including providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade FRLS wires and including the cost of providing and fixing a 6 amp 240 Volt grid plate mounted switch with moulded cover plate in GI box and complete as required ( Switch shall be as approved by the architect / Client) | 2 | Pt. | 2 |  |  |  | 2 | 100% | 2
| 13 | Wiring for secondary Switch controlled normal light points ( Looped from above point) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16SWG MS concealed/surface conduit including cost of cutting and filling chases for recessed conduiting and supports in case of Surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 1 | Pt. | 1 |  |  |  | 1 | 100% | 1
| 14 | Wiring for switch controlled emergency primary light points with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS concealed/surface conduit including cost of cutting and filling chases for recessed conduiting and supports in case of Surface conduit including all bends , saddles , Junction boxes etc. including the cost of running 2.5 sq. mm PVC insulated copper conductor wire for loop earthing etc. and including providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade FRLS wires and including the cost of providing and fixing a 6 amp 240 Volt grid plate mounted switch with moulded cover plate in GI box and complete as required ( Switch shall be as approved by the architect / Client) | 2 | Pt. | 2 |  |  |  | 2 | 100% | 2
| 15 | Wiring for a 5 pin 240 volt 6 amp single phase and neutral switch socket outlet with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / ceiling including cost of providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade wires and including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and providing and fixing of a combined 5 pin 240 volt 6 amp socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires complete as requied( Switch and socket shall be as approved by the architect / Client) | 8 | Pt. | 8 |  |  |  | 8 | 100% | 8
| 16 | Wiring same as in Item 15 above looped from an adjacent 6 amp switch socket outlet as required and providing and fixing of a modular type 5 pin 240 Volt 6 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole switch in a recessed GI boxes with internal wiring and moulded front plates complete as required. ( Switch and socket shall be as approved by the architect / Client) | 12 | Pt. | 12 |  |  |  | 12 | 100% | 12
| 17 | Same as above but switch and socket provided at separate location including wiring berween switch and socket and complete as required | RO | Pt.
| 18 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 3 | Pt. | 3 |  |  |  | 3 | 100% | 3
| 19 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 4.0 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 7 | Pt. | 7 |  |  |  | 7 | 100% | 7
| 20 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (2 outlets wired on 1 circuit) with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 4.0 sq mm upto the first outlet and 2.5 sq mm from first to the second outlet in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing of two sets of 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switches with moulded cover plate in a recessed GI box including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) | 6 | Pt. | 6 |  |  |  | 6 | 100% | 6
| 21 | Wiring for primary switch board consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A switch with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 2.5 sq FRLS copper wire mm in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing prewired switch board each consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A modular switch , safety shutters in a recessed/surface GI box including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) Note- Conduits shall be 16 SWG MS on surface and FRLS PVC for wall concealed | 4 | Pt. | 4 |  |  |  | 4 | 100% | 4
| 22 | Supply installation testing and fixing 3 pin 16A/20A , 240V , single Phase metal Clad industrial socket outlet with 16A/20A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 18 | Nos. | 18 |  |  |  | 18 | 100% | 18
| 23 | Supply installation testing and fixing 3 pin 25A/32A , 240V , single Phase metal Clad industrial socket outlet with 25A/32A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 4 | Nos. | 4 |  |  |  | 4 | 100% | 4
| 24 | Supply installation testing and fixing 3 pin 40A , 240V , single Phase metal Clad industrial socket outlet with 40A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | RO | Nos.
| 25 | Supply installation testing and fixing 5 pin 32A , 415V , single Phase metal Clad industrial socket outlet with 32A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | 1 | Nos. | 1 |  |  |  | 1 | 100% | 1
| 26 | Supply installation testing and fixing 5 pin 63A , 415V , single Phase metal Clad industrial socket outlet with 63A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | 4 | Nos. | 4 |  |  |  | 4 | 100% | 4
| 27 | Supply and Installation of following in wall mounted MS enclosure
| i | 63A FP RCBO(300 mA) | 1 | Nos | 1 |  |  |  | 1 | 100% | 1
| ii | 32A/25A DP RCBO | 5 | Nos | 5 |  |  |  | 5 | 100% | 5
| 28 | Supply and Installation of 32A FP RCBO in IP 67 Rated polycarbonarte enclosure | 1 | Nos | 1 |  |  |  | 1 | 100% | 1
| 29 | Supply and installation of flush mounted (Enhanced Category 6T 568 A or B) outlets with 2 mm thick GI box complete including cutting, chases, fixing of GI boxes and making good. The plastic shall be high impact, flame-retardant, UL rate thermoplastic. Dust cover / blank shall be provided to protect unused faceplate openings. Termination caps and plastic cover shall be provided to protect jack wiring.
| i | Single outlet face plate with RJ-45 Jack with information outlet | 16 | Nos. | 0 |  |  |  | 0 | 0% | 0
| ii | Duplex outlet face plate with RJ-45 Jack with information outlet | 3 | Nos. | 0 |  |  |  | 0 | 0% | 0
| 30 | Supply,installtion testing and commisioning of Cat-6A UTP cables in existing Conduit complete as required for Telephone and Data System | 325 | Mtrs | 325 |  |  |  | 315 | 96.92% | 315
| 31 | Supplying,installation and commisioning of CAT-6A patch cords 2 mtrs. | 22 | Nos | 0 |  |  |  | 0 | 0% | 0
| 32 | Supplying,installation and commisioning of CAT-6A patch cords 1 mtr. | 22 | Nos | 0 |  |  |  | 0 | 0% | 0
| 33 | Supply , fixing & Laying 16 SWG MS conduits on surface or concealed complete with PVC junction boxes, cover plates, bends, saddles, base and other accessories all made in PVC with GI screws as required to complete the job. .
| i | 25 mm dia 16 SWG MS conduit | 90 | Mtrs | 90 |  |  |  | 80 | 88.89% | 80
| ii | 20 mm dia 16 SWG MS conduit | 120 | Mtrs | 60 |  |  |  | 60 | 50% | 60
| 34 | Supply , fixing & Laying 2.0mm Thick FRLS PVC conduits on surface or concealed complete with PVC junction boxes, cover plates, PVC bends, PVC saddles, base and other accessories all made in PVC with GI screws as required to complete the job. .
| i | 25 mm dia FRLS PVC conduit | RO | Mtrs
| ii | 20 mm dia FRLS PVC conduit | RO | Mtrs
| 35 | Installation of following light fixtures including connections and complete in all respects
| i | 25/15/12Watt Recessed Down Lighter | 15 | No. | 0 |  |  |  | 0 | 0% | 0
| ii | Signage | 2 | No. | 0
| iii | 2X20W FTL LED | 16 | No. | 0 |  |  |  | 0 | 0% | 0
Fire Sprinkler System Work
| SR. NO. | DESCRIPTION | UNIT | QTY. | [5 empty] | Claimable % | Claimable Qty
| 1 | Providing, Laying, Jointing & Testing of Pipes for Sprinkler System - G.I Pipe confirming IS Codes Class `C' Heavy Pipe & with necessary support & anchore fastening from slab.
| a. | 25 mm dia | Rmt. | 14 |  |  |  |  | 0 | 0% | 0
| b. | 32 mm dia | Rmt. | 6 |  |  |  |  | 0 | 0% | 0
| c. | 40 mm dia | Rmt. | 8 |  |  |  |  | 0 | 0% | 0
| d. | 50 mm dia | Rmt. | 12 |  |  |  |  | 0 | 0% | 0
| e. | 65mm dia | Rmt. | 0 |  |  |  |  | 0
| f. | 80mm dia | Rmt. | 0 |  |  |  |  | 0
| 2 | Synthetic Enamel Paint.
| a. | 25 mm dia | Rmt. | 14 |  |  |  |  | 0 | 0% | 0
| b. | 32 mm dia | Rmt. | 6 |  |  |  |  | 0 | 0% | 0
| c. | 40 mm dia | Rmt. | 8 |  |  |  |  | 0 | 0% | 0
| d. | 50 mm dia | Rmt. | 12 |  |  |  |  | 0 | 0% | 0
| e. | 65mm dia | Rmt. | 0 |  |  |  |  | 0
| f. | 80mm dia | Rmt. | 0 |  |  |  |  | 0
| 3 | Providing & Fixing of Butterfly Valve.
| a. | 50 mm dia | No. | 0 |  |  |  |  | 0
| b. | 80 mm dia | No. | 1 |  |  |  |  | 0 | 0% | 0
| 4 | Providing & Fixing of Ball Valve.
| a. | 25 mm dia | No. | 0 |  |  |  |  | 0
| b. | 32 mm dia | No. | 0 |  |  |  |  | 0
| c. | 40 mm dia | No. | 0 |  |  |  |  | 0
| d. | 50 mm dia | No. | 0 |  |  |  |  | 0
| e. | 65 mm dia | No. | 0 |  |  |  |  | 0
| f. | 80 mm dia | No. | 1 | 0 |  |  |  | 0 | 0% | 0
| 5 | HEADER FITTING.
| a. | Flow Switch | No. | 1 |  |  |  |  | 0 | 0%
| b | Pressure Gauge | No. | 1 |  |  |  |  | 0 | 0%
| c | Air Release Valve | No. | 1 |  |  |  |  | 0 | 0%
| d | 80 mm dia NRV | No. | 1 |  |  |  |  | 0 | 0%
| 6 | Providing & Fixing C.P. Brass 68 degree Quartzoid Bulb Sprinklers. Make : Tyco / viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed & EN approved.
| a. | Pendant Type | No. | 16 | 6 |  |  |  | 6 | 37.5% | 6
| b. | UP Right Type | No. | 16 | 6 |  |  |  | 6 | 37.5% | 6
| 7 | Providing & Fixing C.P. Brass 79 degree(QR) Quartzoid Bulb Sprinklers. Make : Tyco / viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed & EN approved for high temperature area in Kitchen temprating shall be 79degree c (QR)
| a. | Pendant Type | No. | 0
| b. | UP Right Type | No. | 0
| 8 | Flexible Sprinkler Drop.
| a. | 25mm | No. | 16 | 6 |  |  |  | 6 | 37.5% | 6
| b. | 100mm | No. | 0
| c. | 150mm | No. | 0
| 9 | Drain Valve | No. | 0
NOTE: KINDLY FOLLOW THE GUIDELINES ISSUED BY MALL AUTHORITY FOR THE DETAILED SPECIFICATIPONS OF DIFFERENT ITEMS MENTIONED IN THIS BOQ. SPRINKLER TAP OFF TO BE TAKEN FROM EXISTING SPRINKLER LINE
Fire Alarm System Work
S. NO. | DIAGRAM | DESCRIPTION | UNIT | QTY. | [5 empty] | Claimable % | Claimable Qty
1 |  | R1 (RESPONSE INDICATORS)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Response indicators are connected to automatic fire detectors in order to indicate quickly the source of an alarm signal from detectors which are not easily accessible or visible. They light up as soon as the connected fire detector gives an alarm.(Wiring from switches to panel and stair case pressurization not included) | Nos | 9 | 3 |  |  |  | 3 | 33.33% | 3
2 |  | HD (HEAT DETECTOR) INSTALL NEAR HOOD
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) A heat detector is a fire alarm device designed to respond when the convected thermal energy of a fire increases the temperature of a heat sensitive element. The thermal mass and conductivity of the element regulate the rate flow of heat into the element. All heat detectors have this thermal lag (Wiring from switches to panel and stair case pressurization not included) (Edwards / Apollo) | Nos | 2 | 2 |  |  |  | 2 | 100% | 2
3 |  | CONVENTIONAL FIRE PANEL | Nos | _
4 |  | MCP (MANUAL CALL POINT)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Manual call points are used to initiate an alarm signal, and operate by means of a simple button press or when glass is broken revealing a button. They can form part of a manual alarm system or an automatic alarm system.Model : Edwards / Apollo and FM approved with GI mounting Box | Nos | 2 | 1 |  |  |  | 1 | 50% | 1
5 |  | H (HOOTER)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Fire Alarm Systems. A fire alarm system is a electrical / electronic system which is connected with many type of devices such as main panel, smoke / heat detectors, mcp, sounder etc.. to detect the fire event by indiacating audio or visualize signal at the main or individual devices.Model : Edwards / Apollo with GI mounting Box | Nos | 2 | 1 |  |  |  | 1 | 50% | 1
6 |  | SD (SMOKE DETECTOR ABOVE CEILING)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay.Model : Edwards / Apollo. | NOS | 9 | 3 |  |  |  | 3 | 33.33% | 3
7 |  | SD (SMOKE DETECTOR BELOW CEILING)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model : Edwards / Apollo. | NOS | 9 | 9 |  |  |  | 9 | 100% | 9
8 |  | MSD (MULTI SENSOR DETECTOR BELOW CEILING)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model : Edwards / Apollo. | NOS | _
9 |  | FIRE ALARM SYSTEM LOOPING | RMT. | 50 | 50 |  |  |  | 45 | 90% | 45
10 |  | Acrylic EXIT Glow Sign Board with LED Lights, Size 10 x 6.5 inch, | NOS | 2 | 2 |  |  |  | 2 | 100% | 2
NOTE: KINDLY FOLLOW THE GUIDELINES ISSUED BY AIRPORT AUTHORITY FOR THE DETAILED SPECIFICATIPONS OF DIFFERENT ITEMS MENTIONED IN THIS BOQ.
Civil & Interior Work
S.NO. | ITEM NAME | ITEM SPECIFICATIONS | UNIT | QUANTITY | [5 empty] | Claimable % | Claimable Qty
1 | DISMENTLING
1.1 | Existing wall and floor Dismantling | Dismantling exisiting brick wall and flooring as per the site | Job | 1 | 1 |  |  |  | 1 | 100% | 1
1.2 | Malwa Dumping | Site scrapping/debris Dumping at nearest Dumping yard as/ airport authority rate shall be including loading unloding etc | Per/Trolly | 4 | 3 |  |  |  | 3 | 75% | 3
2 | ANTI TERMITE
2.1 | Anti Termite Treatment | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect. (Mode of measurement is to be carpet area of floor and not the area of surface treated) | Sq.m | 92 |  | 12.28 | 7.491 |  | 91.9895 | 99.99% | 91.9895
3 | CIVIL WORK
3.1 | 100 MM Thick ACC Siporex block work | Providing and erecting 100 mm thick ACC siporex Block work with Chemical ) in true line, level and plumb for wall compound walls, steps, complete with necessary scaffolding, raking of joints, curing etc., . Rate to include soaking of bricks adequately before construction, complete as directed and specified. (Brick of min strength 100kg./sq.cm.) rate are including all type of scaffolding and required arrangements for making brick wall. | Sq.m | 0 |  |  |  |  | 0
3.1a | 150 MM Thick ACC Siporex block work | Providing and erecting 150 mm thick ACC siporex Block work with Chemical ) in true line, level and plumb for wall compound walls, steps, complete with necessary scaffolding, raking of joints, curing etc., . Rate to include soaking of bricks adequately before construction, complete as directed and specified. (Brick of min strength 100kg./sq.cm.) rate are including all type of scaffolding and required arrangements for making brick wall. | Sq.m | 0
3.2 | RCC Band in brick wall | Providing & laying 60-70 mm thick RCC band with 10mm dia bar in brick wall at every 1200 mm height in brick wall with M25 grade concreete ratio 1:1:2 (1 is cement 1 is sand & 2 is aggregate ) in true line ,level and plumb for wall. | Rm | 0
3.3 | Plaster Work | Providing & Laying:- Of 12-15mm thick plaster in cement mortar 1:4 (1 cement : 4 coarse sand) to ceiling, all types of RCC. work, brick work surfaces at all levels in line, level and plumb including smooth cement finish or roughening of surface to hold tiles and providing necessary grooves at junctions of walls and ceiling, door/window frames inclusive of racking the joints, roughing the RCC. surface, necessary curing scaffolding etc., completed as per details given in drawing or as directed by Architect. | Sq.m | 15 | 2 | 3.25 | 2 |  | 13 | 86.67% | 13
3.4 | PCC Flooring | Providing and laying plain cement concrete of specified grade, 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20 mm and down gauge) as bed concrete in locations as called for laid, consolidated and cured etc. complete upto maximun 75mm thickness as per specification and drawing including the cost of centering and shuttering. | Sq.m | 0 |  |  |  |  | 0 |  | 0
3.5 | Water proofing | Applying and grouting a slurry coat of neat cement using 2.75 kg/sqm. of cement admixed with propeirtary water proofing compound(Davco K10 Polyurethane plus/Dr. Fixit Flexi PU 270-I)conforming to IS : 2645 over the RCC slab including cleaning the surfacebefore treatment cement morter 1:5 (1 cement : 5 coarse sand)admixed with proprietary water proofing compound conforming to IS :2645 over 20 mm thick layer of cement morter of mix 1:5 ( 1 cement : 5coarse sand) admixed with proprietary water proofing compound conforming to IS : 2645 to required slope and treating similary the adjoining walls upto 300 mm height including rounding of junctions of walls and slabs.Finishing the surface with 20 mm thick jointless cement morter of mix1:4 (1 cement : 4 coarse sand) admixed with proprietary water proofing compound conforming to IS : 2645 and finally finishing the surface with trowel with neat cement slurry and making of 300x300 mm square. | Sq.m | 0
TOTAL
4 | TILE / STONE WORK
4.01 | KOTA STONE FLOORING BOH AREA | Providing & laying of 25 thk. 560mmX560mm Kota Stone flooring over a bed of 20mm thk. Cement mortar (1:4) jointed with cement slurry mixed with pigment to match the color of kota stone including hole cutting for traps etc. necessary cutting, rubbing, grinding and mirror polishing completed as per the details are provided in drawings or as directed by Architect/Engineer. | Sq.m | 20 |  | 6.667 | 3 |  | 20.001 | 100% | 20.001
4.02 | KOTA SKIRTING IN BOH AREA | Providing & fixing of 25mm thk. kota stone 4" high over a bed of 20 mm thk. Cement mortar ( 1:4 ) jointed with cement slurry mixed with pigment to match the coloure of KOTA including necessary wastage ,cutting ,grinding & polishing completed as per the details are provided in drawings or as directed by Architect/Engineer. | Rm | 10 |  | 10 |  |  | 10 | 100% | 10
4.03 | Kota polish | Providing and Applyng:- Of dimond polish over kota flooring if required . | Rm | RO
4.04 | Raised floor & Cinder filling | Providing and cinder filing to raised floor as per the drawing and instruction as per site location UPTO 250mm ht. | Sq.m | 0
4.05 | WALL TILES ( BOH AREA ) | P/fixing glazed ceramic (Kajaria /Johnson Make) White- (200x300mm) Wall tiles as approved, UPTO 2100mm from FFLVL. or BOFC whichever is achieveable, in kitchen over a base of 20-25mm thick plaster with cement mortar 1:3 (1 cement: 3 fine sand) as per approved pattern, setting the tiles in cement slurry, joints filled and finished neat with white cement as/spec.(Basic cost of tile Rs.22/- per sft.) | Sq.m | 45 | 2 | 3.25 | 2.5 |  | 44.525 | 98.94% | 44.525
[6 empty] | 4.26 | 2.5
[6 empty] | 2.03 | 2.5
[5 empty] | 3 | 0.8 | 2.5
[6 empty] | 4.05 | 2.5
4.06 | WALL TILES ( MOH AREA ) | Providing & Fixing of100x200mm White Bevelled Tile [JOHNSON ] in MOH Area with 12 thk base plaster cement mortar 1:4 and joined with white cement slurry mixed with pigment to match the shade of tile. The tile to be laid as per approved pattern. Completed as per design & details are provided or as directed by Architect. ( Base Rate 85/- Sq.Ft. ) | Sq.m | 30 |  |  |  |  | 0 | 0% | 0
4.1 | Granite Work | Providing ,cutting ,and laying 18 mm th. granite, laying over a cement motor ,bedding (1:4) as per the detail draing like thresh hold ,ledge wall top and etc Rate are included with required moulding ,shemfring and polish as per the detail drawing. | Sq.m | 6 |  | 6.15 | 0.3 |  | 1.845 | 30.75% | 1.845
5 | MS WORK
5.1 | MS tubular partition | P/F Full Ht partition (75mm above bofc) with single side Framework as per dwg, of MS Box section 50x50mm ,18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame of approved sections fixed to floor/soffit/existing ceiling structure with rust-free treatment & enamel paint of colour as specified ready to recieve ply on top. Rate inclusive of all necessary hardware, wastage, making provision for electrical points and edges with grooves, provision for fixing concealed LED lights, edge finishing as per detailed drawing. Measurement as per elevation | Sq.m | 0
5.2 | MS tubular partition | P/F Full Ht partition with double Framework made to shape as per dwg, of MS Box section 50x50mm ,18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame of approved sections fixed to floor/soffit/existing ceiling structure with rust-free treatment & enamel paint of colour as specified ready to recieve ply on top. Rate inclusive of all necessary hardware, wastage, making provision for electrical points and edges with grooves, provision for fixing concealed LED lights, edge finishing as per detailed drawing. Measurement as per elevation (single side) | Sq.m | 0
5.3 | MS tubular partition | P/F of MS Box section 25x25mm , 18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame of approved sections fixed to floor/soffit/existing ceiling structure with rust-free treatment & enamel paint of colour as specified ready to recieve ply on top. Rate inclusive of all necessary hardware, wastage, making provision for electrical points and edges with grooves, provision for fixing concealed LED lights, edge finishing as per detailed drawing. Measurement as per elevation | Sq.m | 10 |  |  |  |  | 0 | 0%
5.4 | Framing for DMB's | Providing and fixing MS Frame work just below the false ceiling, to hang DMB's in MOH, supported by civil structure with two coats of ms primer etc, complete. | Sq.m | 3 |  |  |  |  | 0 | 0% | 0
6 | WOODEN WORK
6.1 | Bison board cladding | Providing and fixing :- 12mm th. Bison board over existing MS framework, ready to take tile finish on top. Rate inculsive of all necessary hardware wastage etc complete in all respects as per drawings/details. Measurement as per elevation. | Sq.m | 20 |  |  |  |  | 0 | 0% | 0
6.2 | Laminate cladding on wall & partition | Providing and fixing :- 19mm th. FR ply, finished with 1.0mm th. laminate of approved shade and make as/elevation. Rate inculsive of all necessary hardware wastage etc complete in all respects as per drawings/details | Sq.m | 30 |  |  |  |  | 0 | 0% | 0
6.4 | Acrylic sheet cladding on partition | Providing and fixing :- 4mm th. Grey and Red Acrylic sheet, pasted with approved adhesive over 19mm th. FR ply, over existing MS tubular structure, as/elevation. Rate inculsive of all necessary hardware wastage etc complete in all respects as per drawings/details | Sq.m | 13 |  |  |  |  | 0 | 0% | 0
6.6 | Door frame | Providing and fixing :- HARD Wood door frames i.e Sal wood or Equivalent 2.5"X 5"complete with grooves as specified complete polished/painted matching the laminate as specified, with all necessary hardware such as hold fasts etc. completed as per design & details given in drawing/Architect instruction. Door frames to be manufactured with horns minimum 3", 40x12mm rebate size and a temporary wooden strip to retain the shape of the frame etc.including polish of approved shade. | Rm | 0 |  |  |  |  | 0 |  | 0
6.7 | DRY STORE ENTRY | Flush door 38 mm thk ply finished with 1mm thk.laminate on both side & 6" high aluminum powder coated grill at bottom of door. All necessary hardware (i.e. lock, handle, hinges, latch or tower bolt, door stopper, pvc buffer etc ) to be provided. Door held on granite jamb & having open door closer. All to be completed as per the details are provided in drawings or as directed by Architect/Engineer. Door size 3'0" x 7'0" | no | 1 |  |  |  |  | 0 | 0% | 0
6.8 | MANAGER CABIN DOOR (WITH VISION PANEL) | Providing & Making of Flush door (38 mm thk ply) finished with 1mm thk. on both side, having vision panel of size 2'-6" x 6" at eye level. All necessary hardware (i.e. lock, handle, hinges, latch or tower bolt, door stopper, door pvc buffer etc ) to be provided. (Door Size: 3'0"x7'0" Incl. Door Frame), completed as per the details are provided in drawings or as directed by Architect/Engineer. | no | 1 |  |  |  |  | 0 | 0% | 0
6.9 | BOH ENTRY (VISION PANEL DOOR) | Providing & Making of Flush door (38 mm thk ply) finished with 1mm thk. on both side, having vision panel of size 9"x9" at eye level. All necessary hardware (i.e. lock, handle, hinges, latch or tower bolt, door stopper, door pvc buffer etc ) to be provided. (Door Size: 3'0"x7'0" Incl. Door Frame), completed as per the details are provided in drawings or as directed by Architect/Engineer. | no | 1 |  |  |  |  | 0 | 0% | 0
6.11 | Front Counter Portal | Providing and fixing Of front counter portal with 18 mm thick ply finished with 1mm th. Lamiante on all visible faces as per the detail drawings | Sq.m | 10 |  | 4.3 | 0.92 |  | 3.956 | 39.56% | 3.956
6.12 | Main Counter For Order and Picup | Providing & Fixing:- Of 2'-9" deep counter to order & Pick Up made from 19mm thick FR Ply with nosing in front as per detail drawing. Counter top and front fascia to be finished in white corian EM-03 with 150mm wide 3 vertical stripes of Red corian as mentioned, all internal surfaces & under counter storage finished in plain white laminate, niche for KDS, provision for cash till, wire manager etc to completed as per details & design provided or as directed by Architect. Elevation area from MOH side shall be Measured. | Sq.m | 3.5 |  | 3.8 | 0.92 |  | 3.496 | 99.89% | 3.496
6.14 | OVERHEAD STORAGE (MANAGERS ROOM) | P/Fof 450MM deep overhead storage unit made of 19mm thk. Commercial board.Externally Laminated with laminate of approved shade, off white enamel painted inside.Cost is inclusive of handles, foldable 19mm th. comm. board shelves,partitions etc. and polish complete. Measurement as per elevation | Sq.m | 1 |  |  |  |  | 0 | 0% | 0
6.15 | MANAGER -O.T. TABLE-LCMS | P/f Table made out of 3/4" thk.commercial board laminated with (LAM -8844 AGED SUEDE ASH FORMICA MAKE). The table to have one drawer unit and key board tray. Cost would include cost of all hardwares likeTelescopic Channels,"C" shaped brushed steel handles, ball catchers,locks etc complete with polish. Measurement as per plan | Sq.m | 0
6.16 | SOFT BOARD (MANAGERS ROOM , CREW ROOM & DELIVERY TABLE ) | Providing & fixing of Soft board for Managers Cabin with fabric of approved shade, completed as per the details are provided in drawings or as directed by Architect/Engineer. Basic rate of Fabric as Rs. 100/r.mtr. | Sq.m | 0
8 | FALSE CEILING/PAINTING
8.1 | Metal Grid ceiling | Ceiling - Supply and install - 600x600mm Metal grid false ceiling including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications | Sq.m | 86 |  |  |  |  | 0 | 0% | 0
8.3 | Paint in BOH | Providing & applying Of Two or more coats of roller applied premium acrylic emulsion(Asian -0765 MORNING GLORY) paint of interior grade,having VOC (Volatile Organic Compound ) content less than 50 grams/ litre of approved brand and manufacture (Asian Paints applyingTwo coats birla putty to achive smooth surface of BOH area ceiling and one coats primer and two or more coats of paint to achieve even shade and colour as per direction and satisfaction of Architect | Sq.m | 90 |  |  |  |  | 0 | 0%
9 | MISCELLANEOUS ITEMS
9.1 | SS PARTITION | Providing and fixing of 304 grade stainless steel partition made with 20X20mm tube frame and wrapped with stainless steel sheet and completed as per the details are provided in drawings or as directed by Architect/Engineer. Rate include SS sheet and ss frame and all necessary hardware etc. | Sq.m | 0
9.2 | Corner Guard For BOH Area | Providing & fixing of 25mm x 25mm SS (202 Grade) Tile Guard in Stainless Steel ( Brushed surface finished 1mm thk.) complete as per approved specification, completed as per the details are provided in drawings or as directed by Architect/Engineer. | Rm | 75 | 40 |  |  |  | 40 | 53.33% | 40
9.3 | Trap Door in BOH Area | Providing & fixing Trap door to be made of 19mm BWP ply, finished with laminate or approved paint to match the shade of false ceiling. The trapdoor edges to be finished with 8mm thick teak wood lipping painted to match ceiling color. The item is inclusive of all fittings, fixtures and hardware; providing & fixing all necessary SS hinges (concealed), approved locking system, tied with safety chain, any frames, necessary support structure from the ceiling for fixing the trap door shutters, shadow gap, tools and tackles etc. Rate shall include all wastage, necessary cutting,all leads and lifts at all levels, loading and unloading, transportation and all other incidental charges, cost of materials, providing patterns,as per design, labour, etc.,complete as per specification, design & details,as per the instructions of the Architect/Engineer in charge. Refer to detail drawing | Nos | 4 | 0 |  |  |  | 0 | 0% | 0
9.4 | Key box | Providing and making key box as per the design at site | Nos | 1 |  |  |  |  | 0 | 0% | 0
9.6 | KICK PLATE ON DOORS | Providing and fixing stainless steel(20 gauge) kick plate on doors on both sides including all necessary screws, nails etc. complete at the bottom of each door.(8" high) | no | 2 | 0 |  |  |  | 0 | 0% | 0
9.9 | HOUSEKEEPING | Providing services for Daily Site Cleaning & proper House keeping on Handover day | Nos. | 1 | 1 |  |  |  | 1 | 100% | 1
10 | MS Barricade | Providing and fixing of 25x25mm pipe frame for temporary Baricating, to completed as per details & design given in drawing/Architect instruction. | Sq.m | RO
HVAC High Side
| 1 | DX and Ventilation System
| S.No. | Description | Unit | Qty | [5 empty] | Claimable % | Claimable Qty
| Part A | DX EQUIPMENTS (Hi Side Works)
| 1 | Air Cooled Split units (R32)(Inverter Type)
| 1.1 | Supply of Air Cooled Split airconditioners each comprising an outdoor unit consisting of hermetic scroll compressor, air cooled condensing unit, Condenser fan etc. with outer casing and indoor fan coil unit(s) consisting of centrifugal fans, fan motor, DX cooling coil, outer casing, filter, control and power panel with remote control etc. both inter connected with copper refrigerant pipe and drain pipe of required length as given, cabling and wiring, insulation with cross linked polyethelene foam, full charge of refrigerant gas and oil, M.S. base frame, supports etc. complete as per specifications and drawings. The cost shall also include angle iron stands for outdoor units.
| A | HI WALL TYPE
| 1.1.1 | 1.5 TR | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
| B | DUCTABLE TYPE
| 1.1.2 | 11.0 TR | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
HVAC Low Side
| Part B | DX EQUIPMENTS (Low Side Works)
| 1 | Air Cooled Split units (R32)(Inverter Type)
| 1.1 | Installation . Testing and commissioning of Air Cooled Split airconditioners each comprising an outdoor unit consisting of hermetic scroll compressor, air cooled condensing unit, Condenser fan etc. with outer casing and indoor fan coil unit(s) consisting of centrifugal fans, fan motor, DX cooling coil, outer casing, filter, control and power panel with remote control etc. both inter connected with copper refrigerant pipe and drain pipe of required length as given, cabling and wiring, insulation with cross linked polyethelene foam, full charge of refrigerant gas and oil, M.S. base frame, supports etc. complete as per specifications and drawings.
| A | HI WALL TYPE
| 1.1.1 | 1.5 TR | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
| B | DUCTABLE TYPE
| 1.1.2 | 11.0 TR | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
Sub-Total Part-'B' Rs.
| Part C | VENTILATION EQUIPMENTS
| 1 | AHU Fan Section
Supply , Installation, Testing and Commissioning of Double Skin Type AHU Fan section with 0.6 mm preplasticized/precoated GI sheet outside and 0.6 mm plain Galvanized sheet inside with 25mm injected PUF insulation of 42KG/m3 , G.I. blower section, DIDW Blower (Forward Curved) with motors , base , drive arrangement ,Filter, motor drive suitable for Outdoor Application complete as per specifications and drawings .
| 1.1 | 5000 CFM ; SP 30 mm of wg;for Kitchen Exhaust , 2.25 KW Motor | Nos. | 1 | 1 |  |  |  | 1 | 100% | 1
| 2 | Package Type Air Washers
Providing and fixing of Double Skin Packaged Type Air Washer with extruded aluminium section with 0.6 mm preplasticized/precoated GI sheet outside and 0.6 mm plain Galvanized sheet inside, 25 mm thick PUF insulation of 42KG/m3 , G.I. blower section, DIDW Blower (Backward Curved) / Plug Fans with motors , base , drive arrangement ,Filter, cooling pad section, stainless steel sump tank and housing, motor drive, water circulation pump, piping, valves & fittings etc. suitable for Outdoor Application as per specifications and drawings .
| 2.1 | 4200 CFM (with Backward Type DIDW Blowers 3.75 KW Motor ; SP 40 mm of wg;for Kitchen Fresh Air Supply | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
Sub-Total Part D Rs.
| PART-D : | LOW SIDE WORKS
| 1 | Piping
| 1.1 | Refrigerant Piping
| 1.1.1 | Refrigerant Piping (DX System)(R32 Refrigerant)
Providing and fixing copper piping with nitreal rubber with chaseling as per specifications and drawings.
| a. | 1.5 TR Machine (Liquid Line + Gas Line) | Mtrs. | 15 | 15 |  |  |  | 15 | 100% | 15
| b. | 11.0 TR Machine (Liquid Line + Gas Line) | Mtrs. | 10 | 10 |  |  |  | 10 | 100% | 10
(Note : 1RM is equal to 1 RM of gas line and 1 RM of liquid line)
| 1.2 | Drain Piping
| 1.2.1 | 32 mm PVC Pipe with 9 mm insulation | RM | 5 | 5 |  |  |  | 5 | 100% | 5
| 1.2.2 | 25 mm PVC Pipe with 9 mm insulation | RM | RO
| 1.2.3 | 20 mm PVC Pipe with 9 mm insulation | RM | 5 | 5 |  |  |  | 5 | 100% | 5
| 2 | Ducting
| 2.1 | Factory Fabricated Ducting (GSS)
Supply, installation, balancing and commissioning of factory fabricated GSS sheet metal rectangular/round ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
| 2.1.1 | 0.63 MM (24 Gauge) | Sqm. | 100 | 85 |  |  |  | 85 | 85% | 85
| 2.1.2 | 0.8 MM (22 Gauge) | Sqm. | 10 | 10 |  |  |  | 10 | 100% | 10
| 2.1.3 | 1.00 MM (20 Gauge) | Sqm. | 10 | 10 |  |  |  | 10 | 100% | 10
| 2.2 | Site Fabricated Ducting (GSS)
Supply, installation, balancing and commissioning of fabricated at site GSS sheet metal rectangular/round ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
| 2.2.1 | 0.63 MM (24 Gauge) | Sqm. | 10 | 10 |  |  |  | 10 | 100% | 10
| 2.2.2 | 0.8 MM (22 Gauge) | Sqm. | 5 | 5 |  |  |  | 5 | 100% | 5
| 3 | Insulation/ Accoustic Lining
| 3.1 | Duct Acoustic Lining
Supplying and Application of Acoustic lining within the Supply Air duct with 15 mm thick class 'O' open cell nitrile Rubber of density 140-160 kg./Cubm. as per spefications.
| 3.1.1 | 15 MM thick | Sqm | 15 | 15 |  |  |  | 15 | 100% | 15
| 3.2 | Nitrile Rubber Insulation- Class 'O'
Supplying and fixing of closed cell elastomeric insulation of density 55 kg/cu.m.and K valueof not less than 0.037W/mk at 20 deg C as per specifications and drawings (For indoor applications) with factory Laminated 7 mill woven glass cloth
| 3.2.1 | 9 MM Thick (Return Air Duct) | Sqm | RO
| 3.2.2 | 13 MM Thick (Supply Air & Fresh Air Duct) | Sqm | 80 | 70 |  |  |  | 70 | 87.5% | 70
| 3.2.3 | 19 mm Thick (Exhaust Duct) | Sqm | 35 | 30 |  |  |  | 30 | 85.71% | 30
| 4 | Grilles / Diffusers/ Dampers / Louvers
| 4.1 | Supply, Installation, Testing and Commissioning of GI multiblade volume control duct damper complete with neoprene rubber gaskets, nuts, bolts, screws linkages, flanges etc., as per specifications. | Sqm. | 1 |  |  |  |  | 0 | 0% | 0
| 4.2 | Supply, Installation, Testing and Commissioning of multiblade Al volume control Collar / Grille / exhaust Air Opening damper complete with suitable links, lever and quadrants for manual control of airflow and with suitable links , lever and quadrants for manual control of airflow and neoprene rubber gaskets, nuts, bolts, screws, flanges etc., as per specifications. | Sqm. | 0.5 |  |  |  |  | 0 | 0% | 0
| 4.3 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded aluminium Supply / Exhaust Air Grills as per specifications | Sqm. | 1 |  |  |  |  | 0 | 0% | 0
| 4.4 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded Aluminium Continuous Grille as per specifications
| 4.4.1 | 200 MM Aluminium Continuos Grille | RM | 5 |  |  |  |  | 0 | 0% | 0
| 4.4.2 | 150 MM Aluminium Continuos Grille | RM | 25 |  |  |  |  | 0 | 0% | 0
| 4.4.3 | 100 MM Aluminium Continuos Grille | RM | 10 | 0 |  |  |  | 0 | 0% | 0
| 4.5 | Providing and fixing of powder coated extruded aluminium exhaust air louvers/ fresh air louvers with bird screen and mounting arrangement as per specification and drawings. Free Area shall be more than 60% of gross area.
| 4.5.1 | Fresh Air / Exhaust Air Louvers with Bird Screen Mesh | Sqm. | 1 | 0 |  |  |  | 0 | 0% | 0
Sub-Total Part E Rs.
| Part F | ELECTRICAL WORKS
Electrical Work
| 1 | Electrical Control Panel
Supply, installation, testing and commissioning of panel boards made of 2.0 mm thick steel sheet duly powder coated with voltmeter, ammeter, electronic energy meter, indicating lights, Stop/manual /Auto selector switch in each, outgoing current operated single phase preventer. The starters should have potential free contacts for connection to Building Automation System. The panel shall include contactors /over load relay with built in single phase protection / Time delay relay for delayed automatic start of the motor. All panels should have spare NO/ NC Contacts for BMS applications as required.
| 1.1 | Panel-PA10
|  | (1 x 2.25 KW + 1 X 3.75 KW) | Nos | 1 | 1 |  |  |  | 1 | 100% | 1
INCOMER
| -- | 1 No. incoming 40 Amps TP MCB
| -- | 1 No. Digital Type voltmeter with selector switch with control MCB
| -- | 1 No. Digital Type Ammeter 0-63 A with C.T.'s
| -- | 1 Set of RYB indication lamps with control MCB
| -- | 1 No. of 63 Amps Aluminium conductor 25kA bus bar duly sleeved as required.
OUTGOING
2 No. 16 Amps TP MCB for AHU's
1 No. DOL starter for 2.25 KW motor .
1 No. DOL starter for 3.75 KW motor .
2 Nos. of single phase preventor (current based-MPRD2)
2 Nos. direct reading Digital Type Ammeter
|  | Each star-delta/DOL starter consists of current operated MN type over load relay, contactor, push button, ON/OFF indication light | Set | 1 | 0 |  |  |  | 0 | 0% | 0
| 2 | Control & Transmission Wiring
| 2.1 | Providing & fixing control cum transmission wiring of 2 core x 1.5 sqmm copper in MS conduits between indoor and out door unit and between indoor units and their remote sensor/controller. | RM | 25 | 22 |  |  |  | 22 | 88% | 22
| 3 | Power Cabling
| 3.1 | Indoor Units
| 3.1.1 | Providing and fixing flexible power cable of 3 core x 1.5 sqmm copper between Indoor units and their power points | RM | 5 | 5 |  |  |  | 5 | 100% | 5
| 3.1.2 | Providing and fixing flexible power cable of 3 core x 2.5 sqmm copper between Indoor units and their power points | RM | 5 | 5 |  |  |  | 5 | 100% | 5
| 4 | Isolator (Weather Proof)
| 4.1 | Providing & fixing weather proof isolator near each outdoor unit & kitchen ventilation units as per specific control & drawup.
| 4.1.1 | 16 Amp MCB | Nos. | RO
| 4.1.2 | 10 Amp MCP | Nos | RO
| 5 | Cables
Supplying and laying of XLPE insulated aluminium conductor armored cables of 1.1 KV grade of following sizes directly on wall/structural frame/ cable trays or racks using approved type of clamps,End terminations with Double Compression type glands on both ends, double earthing with GI strip/wire of suitable size and hardware as per specifications.
| 5.1 | 3 C x 4 Sq. mm | RM | 40 | 38 |  |  |  | 38 | 95% | 38
| 5.2 | 3 C x 1.5 Sq. mm | RM | RO
| 6 | GI perforated Cable tray
Supply,Installation, Testing and Commissioning following size of perforated painted with powder coating M.S. cable trays with perforation not more than 17.5%, in convenient sections, joined with connectors, suspended from the ceiling with M.S. suspenders including bolts& nuts, painting suspenders etc. as required.
| 6.1 | 150 mm width X 50 mm depth X 1.6 mm thickness | RM | RO
| 6.2 | 300 mm width X 50 mm depth X 1.6 mm thickness | RM | RO
| 6.3 | 450 mm width X 50 mm depth X 2.0 mm thickness | RM | RO
| 7 | Earthing
Supply,Installation, Testing and Commissioning of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required
| 7.1 | 25 mm x 6 mm GI strip | RM | 10 |  |  |  |  | 0 | 0% | 0
| 7.2 | 8 SWG GI Wire | RM | 10 |  |  |  |  | 0 | 0% | 0
Sub-Total Part F Rs.
Total
LIGHTING Work
| S.NO. | DESCRIPTION | UNIT | QTY. | [5 empty] | Claimable % | Claimable Qty
| 1 | Square Ceiling Mounted concealed Fixture 175mmx175mm off white powder coated.Lamp Code: LED lamp integrated 4000K; 22 W.(Counter,Toilet & Change) | NOS | 14 | 0 |  |  |  | 0 | 0% | 0
| 2 | 4'-0" Long 20w Tubelight for BOH 6500k | NOS | 30 | 0 |  |  |  | 0 | 0% | 0
| 3 | Hanging Kit for Tubelight 2pc.= 1 Set | NOS | 15 | 0 |  |  |  | 0 | 0% | 0
CCTV Work
S.No | Items | Specification | Make | Qty | [5 empty] | Claimable % | Claimable Qty
1 | Dome Cameras | Full HD 720p Video Output, Adopt HDTVI Technology, Trud Day & Night, Lens 3.6mm, 12LED, Upto 20M IR Distance | Hikvision | 9 | 0 |  |  |  | 0 | 0% | 0
2 | Hard Disk - SURVEILLANCE | 2TB | Seagate / Toshiba | 1 |  |  |  |  | 0 | 0% | 0
3 | CAT 6 Wire provide and supply |  | AMP/Molex | 130 | 120 |  |  |  | 120 | 92.31% | 120
4 | Screen | 18-19" | Acer/LG/Dell | 1 |  |  |  |  | 0 | 0% | 0
5 | Power Supply | 8 Cameras - 10 amps X 2 | CP-PLUS / ZEBRONICS | 1 |  |  |  |  | 0 | 0% | 0
6 | HDMI Cable | 5 Mtrs | MX | 1 |  |  |  |  | 0 | 0% | 0
7 | Cameras Installation | All Over India | Hikvision | 1 |  |  |  |  | 0 | 0% | 0
Total Amount

## Abstract Sheet
RA-01 - Abstract
WO No :-Semolina/PO/24-25/000588 | [6 empty] | Date:- 30-09-2024
KFC Revamp
BILL OF QUANTITIES FOR PLUMBING WORK PROJECT : PROJECT : KFC BOQ @ MUMBAI AIRPORT | [6 empty] | RA - 1 (Current Bill) |  | Variation |  | Remarks
SR. NO. | MATERIAL | DESCRIPTION | UNIT | QTY. | RATE | AMOUNT | QTY | AMOUNT (Rs) | QTY | AMOUNT (Rs)
1 |  | WATER SUPPLY PIPES
| CPVC Pipes | Supply, laying, testing & commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia, jointing with CPVC solvent cement of medium body IPS brand or equivalent conform. (Make – SUPREME / KASTA)
1.01 |  | 15mm dia | R.M. | 20 | 325 | 6500 | 19.5 | 6337.5 | -0.5 | -162.5 | 98% Claimed in RA Bill 1
1.02 |  | 20mm dia | R.M. | 45 | 395 | 17775 | 44 | 17380 | -1 | -395
2 |  | WATER DRAIN PIPES
| PVC WASTE PIPE | PVC Plastic Pipe for Drainage (Make – SUPREME / KASTA)
2.01 |  | 100mm dia | R.M. | 0 | 1250 | 0
2.02 |  | 50mm dia | R.M. | 0 | 550 | 0
3 |  | CHAMBER & GRATING
3.01 | INSPECTION CHAMBER | Supply, Laying, Testing & Commissioning of Approved SS Inspection Chamber along of Size- 300mmx300mm with SS Cover & SS Grating over it. Make Jaquar / Ozone. | Nos. | 7 | 12500 | 87500 | 4 | 50000 | -3 | -37500 | 57% Claimed in RA Bill 1
4 |  | FLOOR TRAP
4.01 | FLOOR TRAP | Supply, Laying, Testing & Commissioning of 100x100mm Floor Trap with Approved Make heavy duty round or Square. | Nos. | 8 | 1850 | 14800 | 8 | 14800 | 0 | 0 | 100% Claimed in RA Bill 1
5 |  | VALVE AND TAP
5.01 | ANGLE VALVE | Providing & Fixing Angle Valve. | Nos. | 20 | 1850 | 37000 | 0 | 0 | -20 | -37000 | 0% Claimed in RA Bill 1
5.02 | LONG BODY TAP | Providing & Fixing Sink Cock. (Make – JAQUAR / OZONE) | Nos. | 12 | 5500 | 66000 | 0 | 0 | -12 | -66000 | 0% Claimed in RA Bill 1
5.03 | TAP | Providing & Fixing Sink Cock. (Make – JAQUAR / OZONE) | Nos. | 0 |  | 0
5.04 | Gate Valves | Providing & Fixing CPVC Ball Valve ISI mark. (For Inlet) (Make – KITZ / ZOLOTO / AUDCO) 20mm Dia | Nos. | 2 | 950 | 1900 | 0 | 0 | -2 | -1900 | 0% Claimed in RA Bill 1
5.05 | Single Lever Mixer | Providing and fixing 15mm C.P. Single lever wall mixer for 3 Bowl Sink. (Jaguar-Continental make.) | Nos. | 1 | 7500 | 7500 | 0 | 0 | -1 | -7500 | 0% Claimed in RA Bill 1
6 |  | ACCESSORIES
6.01 | Grease Trap | Providing & Fixing of portable grease trap NGT-8,14,50 from Nugreen | Nos. | 5 | 48690 | 243450 | 2.5 | 121725 | -2.5 | -121725 | 50% Claimed in RA Bill 1
6.02 | SS Sink | Providing & Fixing 304 Grade SS Sink of Size as per detailed drawing | Nos. | 0 | 0 | 0
6.03 | Bottle Trap | Providing & fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR / OZONE) | Nos. | 2 | 2250 | 4500 | 0 | 0 | -2 | -4500 | 0% Claimed in RA Bill 1
6.04 | S.S. GRATING | Providing & Fixingof S.S. triple layer grating for the drain as per drawings. | Nos. | 3
6.05 | Waste Coupling | Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. (Make – JAQUAR / OZONE) | Nos. | 1 | 1650 | 1650 | 0 | 0 | -1 | -1650 | 0% Claimed in RA Bill 1
6.06 | GEYSER STORAGE | Geyser(Providing & fixing)RECOLD MAKE |  |  |  | 0
|  | 35 LTR | each | 1 | 23500 | 23500 | 1 | 23500 | 0 | 0 | 50% Claimed in RA Bill 1
|  | 15 LTR | each |  |  | 0
|  | 6LTR (INSTANT GEYSER) | each | 2 | 9500 | 19000 | 1 | 9500 | -1 | -9500 | 50% Claimed in RA Bill 1
6.07 | PVC WATER TANK | Providing & Fixing of PVC water, vertical type storage tanks of the approved quality Make Sintex, including making solid supported flat base as per instruction but in masonary work, and doing all connections as required. Item also inculding the lockable system require for food safety. |  |  |  | 0
|  | 5000 LTR. | Each |  |  | 0
|  | 2000 LTR. | Each |  |  | 0
|  | 1000 LTR | each | 1 | 40000 | 40000 | 0 | 0 | -1 | -40000 | 0% Claimed in RA Bill 1
|  | 500 LTR | each |  |  | 0
|  | 200 ltr | each |  |  | 0
|  | SUB TOTAL OF WATER SUPPLY |  |  |  | 0
6.08 | WATER MOTOR | P/f of 1HP water motor. | No | 1 | 18500 | 18500 | 0 | 0 | -1 | -18500 | 0% Claimed in RA Bill 1
6.09 | 03 BOWL SINK CONNECTION | Providing and fixing 3-Bowl Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 | 4500 | 4500 | 0 | 0 | -1 | -4500 | 0% Claimed in RA Bill 1
6.1 | SINK CONNECTION | Fixing Hand Wash Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 | 1500 | 1500 | 0 | 0 | -1 | -1500 | 0% Claimed in RA Bill 1
6.11 | SINK CONNECTION | Providing and fixing Veg. Prep. Sink Drain outlet connection with valve & Drain pipe complete with all necessary fittings. | No | 1 | 1500 | 1500 | 0 | 0 | -1 | -1500 | 0% Claimed in RA Bill 1
6.12 | FRESH AIR MACHINE CONNECTION | Connection of fresh air overflow. Complete in all respects. | No | 1 | 15000 | 15000 | 1 | 15000 | 0 | 0 | 100% Claimed in RA Bill 1
6.13 | MAIN CONNECTION with airport drain line | Making connection to existing sewer/storm water drains including excavation,cutting of manhole walls and making good the same,modifying drain channels etc.complete in all respects. A)150 to 300 mm dia connection. | No | 1 | 6500 | 6500 | 1 | 6500 | 0 | 0 | 100% Claimed in RA Bill 1
6.14 | PVC 50MM DIA PIPE | Providing, laying and jointing 50mm dia. PVC pipes complete (PRINCE) with PVC fittings and clamps, including cutting and making good the walls and floors, wherever necessary etc., complete. | Rm | 10 | 550 | 5500 | 10 | 5500 | 0 | 0 | 100% Claimed in RA Bill 1
6.15 | CORNER WASH BASIN | Providing and fixing corner China Counter top - Bowl type wash basin of size as/dwg for over the counter mounting, 32mm dia C.P. waste, C.P. chain and rubber plug, 32mm C.P. cast brass bottle trap and pipe to waste pipe. Rubbic (CAT NO-91041) Hindware make | Nos | 0 |  | 0
6.16 | Pressure Pump | 0.5 HP Crompton Make Pressure Pump | Nos | 1 | 18500 | 18500 | 0.5 | 9250 | -0.5 | -9250 | 50% Claimed in RA Bill 1
6.17 | Ro Plant |  | Nos | 1 |  | 0
6.18 | Rodding of Existing drain Line | Rodding and clearing of existing drain line | Job | 1 | 60000 | 60000 | 1 | 60000 | 0 | 0 | 100% Claimed in RA Bill 1
6.19 | Changing of main drain line | Removing of existing main drain line from core cut to main line. ( GI to SMR UPVC) | Job | 1 | 34500 | 34500 | 1 | 34500 | 0 | 0 | 100% Claimed in RA Bill 1
| GRAND TOTAL |  |  |  |  | 737075 |  | 373992.5 |  | -363082.5
KFC Terminal-1 Food Court , Mumbai Airport.
Schedule of Quantities - Electrical Works Dated 05th Feb 2024
The prices are to be quoted in the section mentioned below and shall include the supply, Installation, Testing and commissioning at site of all the equipments, ancillary materials as specified and all such items what so ever required to fulfill the intent and purpose as laid down in the specifications and/or drawings and shall include all taxes and duties on works contract basis.
| S. No. | Description | Unit | Qty. | Rate | Amount
[5 empty] | (Rs.) | (Rs.)
Design, fabrication, assembling, wiring , supply , Erection , Installation , testing and commissioning of MDB Panels fabricated out of 2mm thick for structural members (Load bearing members) and 1.6mm thick for door and covers (Non load bearing members) CRCA painted sheet steel in cubicle formation with reinforcement of suitable size angle iron, channels, T irons, flats wherever necessary for large meter boards. Cable gland plates shall be provided at top and bottom both and windows for meter reading, locking arrangement (pad-lock & seal) with wiring upto KWH meter & meter to MCB shall be done by using adequately rated flexible single core copper wire. The boards shall be treated with all anticorrosive process before painting as per standards with final approved shade of powder coated as approved, 2 nos. earthing terminals shall be provided for all panels. The boards shall be suitable for 415 V, 3 phase, 4 wire, 50 Hz supply system. Boards shall be fabricated in length, height, depth etc to match with site conditions.
An approval shall be taken for each panel before manufacturing. Galvanised hardwares with zinc passivation shall be used in fabrication of boards.
Note: The following provisions shall be required to be made in the switchboard detailed below
The Switchboard shall have provision for entry of all PVCA cables from the top/bottom as required.
All live accessible parts shall be shrouded and all equipment shall be finger touch proof. The busbar insulation shall be with heat shrinkable sleeves. SMC/DMC shrouds and busbar supports shall be used.
Suitable tinned copper extension links for incoming/outgoing cables shall be provided wherever required
Control circuits includes breaker control switch, auto manual selector switch, anti pumping relay, spring charging trip indication, TIMER, control wiring, Auxiliary contactors MCB’s as required at site.
Positive isolation of all breakers.
All fault level breaking capacity indicates shall be ICS value at 415 volts (ICS = ICU = ICW = 100%).
Space Heater/ light/air filter shall be provided for each vertical compartment
Link and drops from MCCB shall be designed for full rated current of MCCB ratings at same current density as of Main Bus Bar
2 nos. GI earth strip throughout the panel.
| 1 | Main Panel
| A | Incoming
1 No. 250 amps 16 kA 440 volt FP MCCB with Thermal Magnetic overcurrent and short circuit and with following
| B | Metering, Indication & Protection:
| a | 1 Nos. 6 Parameter Multi Function Mater with 3 Nos. Cast Resin CTs and MCBs
| b | Breaker ON OFF indication Lamps
| c | R-Y-B indication lamps with MCBs
| d | ELR with CBCT
| C | Bus Bar:
300 A, TPN Al. Bus Bar of suitable length having Current density 1Amp/sq.mm & having high conductivity electrical grade suitable to withstand symmetrical fault level of 25 kA. Neutral busbar shall be of 100% capacity.
| D | Outgoings:
| a | 9 No. 63 amps 4P MCB ( Type C)
| b | 2 No. 40 amps 4P MCB ( Type C)
| c | 4 No. 25 amps 4P MCB ( Type C)
| d | 3 No. 25 amps 4P MCB ( Type C)
| e | 1 No. 40 amps 2P MCB ( Type C)
| f | 5 No. 32 amps 2P MCB ( Type C)
| g | 2 No. 25 amps 2P MCB ( Type C)
|  | Main MDB as described above (Repairinf and replacing of damaged material in existing panel and re painting) | 1 | Set | 285000 | 285000 | 0.8 | 228000 | -0.2 | -57000 | 80% Claimed in RA Bill 1
| 1.1 | DISTRIBUTION BOARDS
Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof double door type distribution boards constructed from 16 SWG sheet steel IP 42 construction, finished with rust proof duly powder coated in approved shade with hinged gasketed door and housing the following complete with P.V.C. insulated copper busbars rated 200 amp with interconnections, neutral and earth bar assembly per phase, earthing terminals complete as approved by Architects.
Note : All MCBs in distribuition board for power circuits shall be of C curve
| i | Type A
|  | 1-63 amp FP MCB with 3 single phase banks each comprising of 63A DP RCCB(100 mA) and 6 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 2 | Set | 25500 | 51000 | 1.5 | 38250 | -0.5 | -12750 | 75% Claimed in RA Bill 1
| ii | Type B
|  | 1-40 amp DP MCB + DP RCCB ( 100mA) and 8 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 13400 | 13400 | 0.75 | 10050 | -0.25 | -3350 | 75% Claimed in RA Bill 1
| iii | Type C
|  | 1-32 amp DP MCB + DP RCCB ( 100mA) and 12 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 11500 | 11500 | 0.75 | 8625 | -0.25 | -2875 | 75% Claimed in RA Bill 1
| iv | Type D
|  | 1-32 amp DP MCB + DP RCCB ( 100mA) and 8 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 15500 | 15500 | 0.75 | 11625 | -0.25 | -3875 | 75% Claimed in RA Bill 1
| v | Type E
|  | 1-25 amp DP MCB + DP RCCB ( 100mA) and 6 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | RO | Set | 16000
| 2 | Supply installation testing and commisioning 3.0 kVA online ( 1ph input and 1ph output) UPS with 15 Min power back up complete with in buit Static by pass switch , Mannual external maintenance by pass switch , Rectifiers , Sealed MF batteries etc as required | 2 | No. | 71000 | 142000 | 0 | 0 | -2 | -142000 | 0% Claimed in RA Bill 1
| 3 | Supply, laying, testing & commissioning of following sizes of Al/Cu. conductor 1.1 kV grade, armoured, XLPE insulated FRLS LT Cables/ Control Cables including necessary cleats, clamps etc. (Cables shall be partly laid in Pipes, O/H cable tray, on wall as required )
| 3.1 | 3.5C – 150.0 (Al.) FRLS Armoured XLPE Cable * | 50 | Mtrs | 1020 | 51000 | 0 | 0 | -50 | -51000 | 0% Claimed in RA Bill 1
| 3.2 | 4C – 10.0 (Cu.) FRLS Armoured XLPE Cable | 40 | Mtrs | 840 | 33600 | 38 | 31920 | -2 | -1680 | 95% Claimed in RA Bill 1
| 3.3 | 4C – 6.0 (Cu.) FRLS Armoured XLPE Cable | 20 | Mtrs | 550 | 11000 | 20 | 11000 | 0 | 0 | 100% Claimed in RA Bill 1
| 3.4 | 4C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 60 | Mtrs | 420 | 25200 | 60 | 25200 | 0 | 0 | 100% Claimed in RA Bill 1
| 3.5 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 70 | Mtrs | 370 | 25900 | 70 | 25900 | 0 | 0 | 100% Claimed in RA Bill 1
* Approximate and shall be as per point of supply from Airport Panel/ Isolator
| 4 | Supply, erection, testing & commissioning of following sizes of cable end terminations with Single compression gland for 1.1 kV grade, XLPE insulated, Al/Cu Conductor cable
| 4.1 | 3.5C – 150 (Al.) FRLS Armoured XLPE Cable *(Double Compression) | 2 | Nos. | 950 | 1900 | 2 | 1900 | 0 | 0 | 100% Claimed in RA Bill 1
| 4.2 | 4C – 10.0 (Cu.) FRLS Armoured XLPE Cable | 4 | Nos. | 520 | 2080 | 4 | 2080 | 0 | 0 | 100% Claimed in RA Bill 1
| 4.3 | 4C – 6.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 450 | 900 | 2 | 900 | 0 | 0 | 100% Claimed in RA Bill 1
| 4.4 | 4C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 4 | Nos. | 450 | 1800 | 4 | 1800 | 0 | 0 | 100% Claimed in RA Bill 1
| 4.5 | 3C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 6 | Nos. | 450 | 2700 | 6 | 2700 | 0 | 0 | 100% Claimed in RA Bill 1
| 5 | Wiring for DB Submains with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in surface/concealed MS surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and making suitable end termination with copper lugs complete as required and as below
| 5.1 | 4 x 16 sq.mm + 2 No. 6.0 Sq. mm in 40 mm dia MS Conduit | 20 | Mtrs | 1450 | 29000 | 18 | 26100 | -2 | -2900 | 90% Claimed in RA Bill 1
| 5.2 | 4 x 10 sq.mm + 2 No. 4.0 Sq. mm in 32 mm dia MS Conduit | 60 | Mtrs | 1300 | 78000 | 57 | 74100 | -3 | -3900 | 95% Claimed in RA Bill 1
| 5.3 | 4 x 6 sq.mm + 2 No. 4.0 Sq. mm in 32 mm dia MS Conduit | 15 | Mtrs | 1140 | 17100 | 15 | 17100 | 0 | 0 | 100% Claimed in RA Bill 1
| 5.4 | 2 x 6 sq.mm + 1 No. 4 Sq. mm in 25 mm dia MS Conduit | 110 | Mtrs | 480 | 52800 | 80 | 38400 | -30 | -14400 | 73% Claimed in RA Bill 1
| 5.5 | 2 x 4 sq.mm + 1 No. 2.5 Sq. mm in 25 mm dia MS Conduit | 325 | Mtrs | 420 | 136500 | 240 | 100800 | -85 | -35700 | 74% Claimed in RA Bill 1
| 6 | Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required
| 6.1 | 50X6 mm GI Strip | 15 | Mtrs | 300 | 4500 | 0 | 0 | -15 | -4500 | 0% Claimed in RA Bill 1
| 6.2 | 25X6 mm GI Strip | 20 | Mtrs | 150 | 3000 | 0 | 0 | -20 | -3000 | 0% Claimed in RA Bill 1
| 6.3 | 25X3 mm GI Strip | 50 | Mtrs | 101 | 5050 | 48 | 4848 | -2 | -202 | 96% Claimed in RA Bill 1
| 6.4 | 8 SWG Copper Wire | 80 | Mtrs | 95 | 7600 | 0 | 0 | -80 | -7600 | 0% Claimed in RA Bill 1
| 6.5 | 8 SWG GI Wire | 125 | Mtrs | 55 | 6875 | 0 | 0 | -125 | -6875 | 0% Claimed in RA Bill 1
| 6.6 | 1 Core 6.0 Sq. Mm FRLS Green Wire | 60 | Mtrs | 102 | 6120 | 60 | 6120 | 0 | 0 | 100% Claimed in RA Bill 1
| 7 | Supply, erection, testing & commissioning of prefabricated GI Perforated type cable trays including Tees / Bends / Crossing / Reducers / Couping to be laid in cable trench, overhead on wall or hanged from ceiling complete with all accessories as required including support at every 1500mm as required
| 7.1 | 150 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 50 | Mtrs | 710 | 35500 | 10 | 7100 | -40 | -28400 | 20% Claimed in RA Bill 1
| 7.2 | 300 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 30 | Mtrs | 1140 | 34200 | 30 | 34200 | 0 | 0 | 100% Claimed in RA Bill 1
| 7.2 | 450 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 10 | Mtrs | 1950 | 19500 | 0 | 0 | -10 | -19500 | 0% Claimed in RA Bill 1
| 8 | Wiring for MCB controlled normal primary light points/ Wall Point/ Floor Point with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 5 | Pt | 3050 | 15250 | 5 | 15250 | 0 | 0 | 100% Claimed in RA Bill 1
| 9 | Wiring for secondary MCB controlled normal light points/ Wall Point/ Floor Point( Looped from above point) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 15 | Pt | 1550 | 23250 | 15 | 23250 | 0 | 0 | 100% Claimed in RA Bill 1
| 10 | Wiring for MCB controlled Emergency primary light points/ Wall Point/ Floor Point with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 2 | Pt | 3250 | 6500 | 2 | 6500 | 0 | 0 | 100% Claimed in RA Bill 1
| 11 | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 6 | Pt | 1550 | 9300 | 6 | 9300 | 0 | 0 | 60% Claimed in RA Bill 1
| 12 | Wiring for switch controlled Normal primary light points with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25 mm 16SWG MS Heavy Duty PVC concealed/surface conduit including cost of cutting and filling chases for recessed conduiting and supports in case of Surface conduit including all bends , saddles , Junction boxes etc. including the cost of running 2.5 sq. mm PVC insulated copper conductor wire for loop earthing etc. and including providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade FRLS wires and including the cost of providing and fixing a 6 amp 240 Volt grid plate mounted switch with moulded cover plate in GI box and complete as required ( Switch shall be as approved by the architect / Client) | 2 | Pt. | 1700 | 3400 | 2 | 3400 | 0 | 0 | 100% Claimed in RA Bill 1
| 13 | Wiring for secondary Switch controlled normal light points ( Looped from above point) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16SWG MS concealed/surface conduit including cost of cutting and filling chases for recessed conduiting and supports in case of Surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 2.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 1 | Pt. | 1250 | 1250 | 1 | 1250 | 0 | 0 | 100% Claimed in RA Bill 1
| 14 | Wiring for switch controlled emergency primary light points with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS concealed/surface conduit including cost of cutting and filling chases for recessed conduiting and supports in case of Surface conduit including all bends , saddles , Junction boxes etc. including the cost of running 2.5 sq. mm PVC insulated copper conductor wire for loop earthing etc. and including providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade FRLS wires and including the cost of providing and fixing a 6 amp 240 Volt grid plate mounted switch with moulded cover plate in GI box and complete as required ( Switch shall be as approved by the architect / Client) | 2 | Pt. | 1250 | 2500 | 2 | 2500 | 0 | 0 | 100% Claimed in RA Bill 1
| 15 | Wiring for a 5 pin 240 volt 6 amp single phase and neutral switch socket outlet with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / ceiling including cost of providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade wires and including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and providing and fixing of a combined 5 pin 240 volt 6 amp socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires complete as requied( Switch and socket shall be as approved by the architect / Client) | 8 | Pt. | 3400 | 27200 | 8 | 27200 | 0 | 0 | 100% Claimed in RA Bill 1
| 16 | Wiring same as in Item 15 above looped from an adjacent 6 amp switch socket outlet as required and providing and fixing of a modular type 5 pin 240 Volt 6 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole switch in a recessed GI boxes with internal wiring and moulded front plates complete as required. ( Switch and socket shall be as approved by the architect / Client) | 12 | Pt. | 3400 | 40800 | 12 | 40800 | 0 | 0 | 100% Claimed in RA Bill 1
| 17 | Same as above but switch and socket provided at separate location including wiring berween switch and socket and complete as required | RO | Pt. | 1815 |  | 0
| 18 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 3 | Pt. | 3900 | 11700 | 3 | 11700 | 0 | 0 | 100% Claimed in RA Bill 1
| 19 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 4.0 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 7 | Pt. | 3900 | 27300 | 7 | 27300 | 0 | 0 | 100% Claimed in RA Bill 1
| 20 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (2 outlets wired on 1 circuit) with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 4.0 sq mm upto the first outlet and 2.5 sq mm from first to the second outlet in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing of two sets of 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switches with moulded cover plate in a recessed GI box including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) | 6 | Pt. | 4500 | 27000 | 6 | 27000 | 0 | 0 | 100% Claimed in RA Bill 1
| 21 | Wiring for primary switch board consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A switch with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 2.5 sq FRLS copper wire mm in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing prewired switch board each consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A modular switch , safety shutters in a recessed/surface GI box including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) Note- Conduits shall be 16 SWG MS on surface and FRLS PVC for wall concealed | 4 | Pt. | 4900 | 19600 | 4 | 19600 | 0 | 0 | 100% Claimed in RA Bill 1
| 22 | Supply installation testing and fixing 3 pin 16A/20A , 240V , single Phase metal Clad industrial socket outlet with 16A/20A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 18 | Nos. | 4500 | 81000 | 18 | 81000 | 0 | 0 | 100% Claimed in RA Bill 1
| 23 | Supply installation testing and fixing 3 pin 25A/32A , 240V , single Phase metal Clad industrial socket outlet with 25A/32A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 4 | Nos. | 5500 | 22000 | 4 | 22000 | 0 | 0 | 100% Claimed in RA Bill 1
| 24 | Supply installation testing and fixing 3 pin 40A , 240V , single Phase metal Clad industrial socket outlet with 40A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | RO | Nos. | 7150
| 25 | Supply installation testing and fixing 5 pin 32A , 415V , single Phase metal Clad industrial socket outlet with 32A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | 1 | Nos. | 13500 | 13500 | 1 | 13500 | 0 | 0 | 100% Claimed in RA Bill 1
| 26 | Supply installation testing and fixing 5 pin 63A , 415V , single Phase metal Clad industrial socket outlet with 63A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | 4 | Nos. | 17800 | 71200 | 4 | 71200 | 0 | 0 | 100% Claimed in RA Bill 1
| 27 | Supply and Installation of following in wall mounted MS enclosure
| i | 63A FP RCBO(300 mA) | 1 | Nos | 10300 | 10300 | 1 | 10300 | 0 | 0 | 100% Claimed in RA Bill 1
| ii | 32A/25A DP RCBO | 5 | Nos | 8100 | 40500 | 5 | 40500 | 0 | 0 | 100% Claimed in RA Bill 1
| 28 | Supply and Installation of 32A FP RCBO in IP 67 Rated polycarbonarte enclosure | 1 | Nos | 10300 | 10300 | 1 | 10300 | 0 | 0 | 100% Claimed in RA Bill 1
| 29 | Supply and installation of flush mounted (Enhanced Category 6T 568 A or B) outlets with 2 mm thick GI box complete including cutting, chases, fixing of GI boxes and making good. The plastic shall be high impact, flame-retardant, UL rate thermoplastic. Dust cover / blank shall be provided to protect unused faceplate openings. Termination caps and plastic cover shall be provided to protect jack wiring.
| i | Single outlet face plate with RJ-45 Jack with information outlet | 16 | Nos. | 595 | 9520 | 0 | 0 | -16 | -9520 | 0% Claimed in RA Bill 1
| ii | Duplex outlet face plate with RJ-45 Jack with information outlet | 3 | Nos. | 920 | 2760 | 0 | 0 | -3 | -2760 | 0% Claimed in RA Bill 1
| 30 | Supply,installtion testing and commisioning of Cat-6A UTP cables in existing Conduit complete as required for Telephone and Data System | 325 | Mtrs | 101 | 32825 | 315 | 31815 | -10 | -1010 | 97% Claimed in RA Bill 1
| 31 | Supplying,installation and commisioning of CAT-6A patch cords 2 mtrs. | 22 | Nos | 396 | 8712 | 0 | 0 | -22 | -8712 | 0% Claimed in RA Bill 1
| 32 | Supplying,installation and commisioning of CAT-6A patch cords 1 mtr. | 22 | Nos | 297 | 6534 | 0 | 0 | -22 | -6534 | 0% Claimed in RA Bill 1
| 33 | Supply , fixing & Laying 16 SWG MS conduits on surface or concealed complete with PVC junction boxes, cover plates, bends, saddles, base and other accessories all made in PVC with GI screws as required to complete the job. .
| i | 25 mm dia 16 SWG MS conduit | 90 | Mtrs | 220 | 19800 | 80 | 17600 | -10 | -2200 | 89% Claimed in RA Bill 1
| ii | 20 mm dia 16 SWG MS conduit | 120 | Mtrs | 200 | 24000 | 60 | 12000 | -60 | -12000 | 50% Claimed in RA Bill 1
| 34 | Supply , fixing & Laying 2.0mm Thick FRLS PVC conduits on surface or concealed complete with PVC junction boxes, cover plates, PVC bends, PVC saddles, base and other accessories all made in PVC with GI screws as required to complete the job. .
| i | 25 mm dia FRLS PVC conduit | RO | Mtrs | 155
| ii | 20 mm dia FRLS PVC conduit | RO | Mtrs | 121
| 35 | Installation of following light fixtures including connections and complete in all respects
| i | 25/15/12Watt Recessed Down Lighter | 15 | No. | 475 | 7125 | 0 | 0 | -15 | -7125 | 0% Claimed in RA Bill 1
| ii | Signage | 2 | No. |  | 0
| iii | 2X20W FTL LED | 16 | No. | 475 | 7600 | 0 | 0 | -16 | -7600 | 0% Claimed in RA Bill 1
| Total For Electrical Works - INR |  |  |  |  | 1692951 |  | 1233983 |  | -458968
| SR. NO. | DESCRIPTION | UNIT | QTY. | RATE | AMOUNT
| 1 | Providing, Laying, Jointing & Testing of Pipes for Sprinkler System - G.I Pipe confirming IS Codes Class `C' Heavy Pipe & with necessary support & anchore fastening from slab.
| a. | 25 mm dia | Rmt. | 14 | 850 | 11900 | 0 | 0 | -14 | -11900 | 0% Claimed in RA Bill 1
| b. | 32 mm dia | Rmt. | 6 | 1050 | 6300 | 0 | 0 | -6 | -6300 | 0% Claimed in RA Bill 1
| c. | 40 mm dia | Rmt. | 8 | 1150 | 9200 | 0 | 0 | -8 | -9200 | 0% Claimed in RA Bill 1
| d. | 50 mm dia | Rmt. | 12 | 1350 | 16200 | 0 | 0 | -12 | -16200 | 0% Claimed in RA Bill 1
| e. | 65mm dia | Rmt. | 0 |  | 0
| f. | 80mm dia | Rmt. | 0 |  | 0
| 2 | Synthetic Enamel Paint.
| a. | 25 mm dia | Rmt. | 14 | 75 | 1050 | 0 | 0 | -14 | -1050 | 0% Claimed in RA Bill 1
| b. | 32 mm dia | Rmt. | 6 | 95 | 570 | 0 | 0 | -6 | -570 | 0% Claimed in RA Bill 1
| c. | 40 mm dia | Rmt. | 8 | 110 | 880 | 0 | 0 | -8 | -880 | 0% Claimed in RA Bill 1
| d. | 50 mm dia | Rmt. | 12 | 125 | 1500 | 0 | 0 | -12 | -1500 | 0% Claimed in RA Bill 1
| e. | 65mm dia | Rmt. | 0 |  | 0
| f. | 80mm dia | Rmt. | 0 |  | 0
| 3 | Providing & Fixing of Butterfly Valve.
| a. | 50 mm dia | No. | 0 |  | 0
| b. | 80 mm dia | No. | 1 | 12500 | 12500 | 0 | 0 | -1 | -12500 | 0% Claimed in RA Bill 1
| 4 | Providing & Fixing of Ball Valve.
| a. | 25 mm dia | No. | 0 |  | 0
| b. | 32 mm dia | No. | 0 |  | 0
| c. | 40 mm dia | No. | 0 |  | 0
| d. | 50 mm dia | No. | 0 |  | 0
| e. | 65 mm dia | No. | 0 |  | 0
| f. | 80 mm dia | No. | 1 | 10500 | 10500 | 0 | 0 | -1 | -10500 | 0% Claimed in RA Bill 1
| 5 | HEADER FITTING.
| a. | Flow Switch | No. | 1 | 25500 | 25500 | 0 | 0 | -1 | -25500 | 0% Claimed in RA Bill 1
| b | Pressure Gauge | No. | 1 | 3550 | 3550 | 0 | 0 | -1 | -3550 | 0% Claimed in RA Bill 1
| c | Air Release Valve | No. | 1 | 17500 | 17500 | 0 | 0 | -1 | -17500 | 0% Claimed in RA Bill 1
| d | 80 mm dia NRV | No. | 1 | 12500 | 12500 | 0 | 0 | -1 | -12500 | 0% Claimed in RA Bill 1
| 6 | Providing & Fixing C.P. Brass 68 degree Quartzoid Bulb Sprinklers. Make : Tyco / viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed & EN approved.
| a. | Pendant Type | No. | 16 | 2550 | 40800 | 6 | 15300 | -10 | -25500 | 38% Claimed in RA Bill 1
| b. | UP Right Type | No. | 16 | 2850 | 45600 | 6 | 17100 | -10 | -28500 | 38% Claimed in RA Bill 1
| 7 | Providing & Fixing C.P. Brass 79 degree(QR) Quartzoid Bulb Sprinklers. Make : Tyco / viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed & EN approved for high temperature area in Kitchen temprating shall be 79degree c (QR)
| a. | Pendant Type | No. | 0 |  | 0
| b. | UP Right Type | No. | 0 |  | 0
| 8 | Flexible Sprinkler Drop.
| a. | 25mm | No. | 16 | 2650 | 42400 | 6 | 15900 | -10 | -26500 | 38% Claimed in RA Bill 1
| b. | 100mm | No. | 0 |  | 0
| c. | 150mm | No. | 0 |  | 0
| 9 | Drain Valve | No. | 0 |  | 0
NOTE: KINDLY FOLLOW THE GUIDELINES ISSUED BY MALL AUTHORITY FOR THE DETAILED SPECIFICATIPONS OF DIFFERENT ITEMS MENTIONED IN THIS BOQ. SPRINKLER TAP OFF TO BE TAKEN FROM EXISTING SPRINKLER LINE
| Total |  |  |  |  | 258450 |  | 48300 |  | -210150
S. NO. | DIAGRAM | DESCRIPTION | UNIT | QTY. | RATE | TOTAL
1 |  | R1 (RESPONSE INDICATORS)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Response indicators are connected to automatic fire detectors in order to indicate quickly the source of an alarm signal from detectors which are not easily accessible or visible. They light up as soon as the connected fire detector gives an alarm.(Wiring from switches to panel and stair case pressurization not included) | Nos | 9 | 1550 | 13950 | 3 | 4650 | -6 | -9300 | 33% Claimed in RA Bill 1
2 |  | HD (HEAT DETECTOR) INSTALL NEAR HOOD
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) A heat detector is a fire alarm device designed to respond when the convected thermal energy of a fire increases the temperature of a heat sensitive element. The thermal mass and conductivity of the element regulate the rate flow of heat into the element. All heat detectors have this thermal lag (Wiring from switches to panel and stair case pressurization not included) (Edwards / Apollo) | Nos | 2 | 9100 | 18200 | 2 | 18200 | 0 | 0 | 100% Claimed in RA Bill 1
3 |  | CONVENTIONAL FIRE PANEL | Nos | _
4 |  | MCP (MANUAL CALL POINT)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Manual call points are used to initiate an alarm signal, and operate by means of a simple button press or when glass is broken revealing a button. They can form part of a manual alarm system or an automatic alarm system.Model : Edwards / Apollo and FM approved with GI mounting Box | Nos | 2 | 8200 | 16400 | 1 | 8200 | -1 | -8200 | 50% Claimed in RA Bill 1
5 |  | H (HOOTER)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Fire Alarm Systems. A fire alarm system is a electrical / electronic system which is connected with many type of devices such as main panel, smoke / heat detectors, mcp, sounder etc.. to detect the fire event by indiacating audio or visualize signal at the main or individual devices.Model : Edwards / Apollo with GI mounting Box | Nos | 2 | 9300 | 18600 | 1 | 9300 | -1 | -9300 | 50% Claimed in RA Bill 1
6 |  | SD (SMOKE DETECTOR ABOVE CEILING)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay.Model : Edwards / Apollo. | NOS | 9 | 6150 | 55350 | 3 | 18450 | -6 | -36900 | 33% Claimed in RA Bill 1
7 |  | SD (SMOKE DETECTOR BELOW CEILING)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model : Edwards / Apollo. | NOS | 9 | 6150 | 55350 | 9 | 55350 | 0 | 0 | 100% Claimed in RA Bill 1
8 |  | MSD (MULTI SENSOR DETECTOR BELOW CEILING)
|  | Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model : Edwards / Apollo. | NOS | _
9 |  | FIRE ALARM SYSTEM LOOPING | RMT. | 50 | 125 | 6250 | 45 | 5625 | -5 | -625 | 90% Claimed in RA Bill 1
10 |  | Acrylic EXIT Glow Sign Board with LED Lights, Size 10 x 6.5 inch, | NOS | 2 | 1250 | 2500 | 2 | 2500 | 0 | 0 | 100% Claimed in RA Bill 1
NOTE: KINDLY FOLLOW THE GUIDELINES ISSUED BY AIRPORT AUTHORITY FOR THE DETAILED SPECIFICATIPONS OF DIFFERENT ITEMS MENTIONED IN THIS BOQ.
|  | TOTAL |  |  |  | 186600 |  | 122275 |  | -64325
S.NO. | ITEM NAME | ITEM SPECIFICATIONS | UNIT | QUANTITY | Rate | Total
1 | DISMENTLING
1.1 | Existing wall and floor Dismantling | Dismantling exisiting brick wall and flooring as per the site | Job | 1 | 30000 | 30000 | 1 | 30000 | 0 | 0 | 100% Claimed in RA Bill 1
1.2 | Malwa Dumping | Site scrapping/debris Dumping at nearest Dumping yard as/ airport authority rate shall be including loading unloding etc | Per/Trolly | 4 | 15500 | 62000 | 3 | 46500 | -1 | -15500 | 75% Claimed in RA Bill 1
[6 empty] | 92000 |  | 76500 |  | -15500
2 | ANTI TERMITE
2.1 | Anti Termite Treatment | Providing & doing anti termite treatment with IMIDACLOPRID (OZIER) for entire area (Pest control) Diluting and injecting chemical emulsion 3" in floor for pre constructional Anti Termite treatment and creating a continuous chemical @ 4' center to center barrier all over as per manufacturer specification and ISI standards. (OR AS APPVD.) including a 1 year guarantee under suitable undertaking on stamp paper etc, complete as directed by Architect. (Mode of measurement is to be carpet area of floor and not the area of surface treated) | Sq.m | 92 | 129.6 | 11923.2 | 91.9895 | 11921.8366 | -0.01052 | -1.3634 | 100% Claimed in RA Bill 1
[6 empty] | 11923.2 |  | 11921.8366 |  | -1.3634
3 | CIVIL WORK
3.1 | 100 MM Thick ACC Siporex block work | Providing and erecting 100 mm thick ACC siporex Block work with Chemical ) in true line, level and plumb for wall compound walls, steps, complete with necessary scaffolding, raking of joints, curing etc., . Rate to include soaking of bricks adequately before construction, complete as directed and specified. (Brick of min strength 100kg./sq.cm.) rate are including all type of scaffolding and required arrangements for making brick wall. | Sq.m | 0 | 1620 | 0 | 0 | 0 | 0 | 0
3.1a | 150 MM Thick ACC Siporex block work | Providing and erecting 150 mm thick ACC siporex Block work with Chemical ) in true line, level and plumb for wall compound walls, steps, complete with necessary scaffolding, raking of joints, curing etc., . Rate to include soaking of bricks adequately before construction, complete as directed and specified. (Brick of min strength 100kg./sq.cm.) rate are including all type of scaffolding and required arrangements for making brick wall. | Sq.m | 0 | 1836 | 0 | 0 | 0 | 0 | 0
3.2 | RCC Band in brick wall | Providing & laying 60-70 mm thick RCC band with 10mm dia bar in brick wall at every 1200 mm height in brick wall with M25 grade concreete ratio 1:1:2 (1 is cement 1 is sand & 2 is aggregate ) in true line ,level and plumb for wall. | Rm | 0 | 700 | 0 | 0 | 0 | 0 | 0
3.3 | Plaster Work | Providing & Laying:- Of 12-15mm thick plaster in cement mortar 1:4 (1 cement : 4 coarse sand) to ceiling, all types of RCC. work, brick work surfaces at all levels in line, level and plumb including smooth cement finish or roughening of surface to hold tiles and providing necessary grooves at junctions of walls and ceiling, door/window frames inclusive of racking the joints, roughing the RCC. surface, necessary curing scaffolding etc., completed as per details given in drawing or as directed by Architect. | Sq.m | 15 | 702 | 10530 | 13 | 9126 | -2 | -1404 | 86.7% Claimed in RA Bill 1
3.4 | PCC Flooring | Providing and laying plain cement concrete of specified grade, 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20 mm and down gauge) as bed concrete in locations as called for laid, consolidated and cured etc. complete upto maximun 75mm thickness as per specification and drawing including the cost of centering and shuttering. | Sq.m | 0 | 864 | 0 | 0 | 0 | 0 | 0
3.5 | Water proofing | Applying and grouting a slurry coat of neat cement using 2.75 kg/sqm. of cement admixed with propeirtary water proofing compound(Davco K10 Polyurethane plus/Dr. Fixit Flexi PU 270-I)conforming to IS : 2645 over the RCC slab including cleaning the surfacebefore treatment cement morter 1:5 (1 cement : 5 coarse sand)admixed with proprietary water proofing compound conforming to IS :2645 over 20 mm thick layer of cement morter of mix 1:5 ( 1 cement : 5coarse sand) admixed with proprietary water proofing compound conforming to IS : 2645 to required slope and treating similary the adjoining walls upto 300 mm height including rounding of junctions of walls and slabs.Finishing the surface with 20 mm thick jointless cement morter of mix1:4 (1 cement : 4 coarse sand) admixed with proprietary water proofing compound conforming to IS : 2645 and finally finishing the surface with trowel with neat cement slurry and making of 300x300 mm square. | Sq.m | 0 | 1850 | 0 | 0 | 0 | 0 | 0
|  | TOTAL |  |  |  | 10530 |  | 9126 |  | -1404
4 | TILE / STONE WORK
4.01 | KOTA STONE FLOORING BOH AREA | Providing & laying of 25 thk. 560mmX560mm Kota Stone flooring over a bed of 20mm thk. Cement mortar (1:4) jointed with cement slurry mixed with pigment to match the color of kota stone including hole cutting for traps etc. necessary cutting, rubbing, grinding and mirror polishing completed as per the details are provided in drawings or as directed by Architect/Engineer. | Sq.m | 20 | 2592 | 51840 | 20.001 | 51842.592 | 0.001 | 2.592 | 100% Claimed in RA Bill 1
4.02 | KOTA SKIRTING IN BOH AREA | Providing & fixing of 25mm thk. kota stone 4" high over a bed of 20 mm thk. Cement mortar ( 1:4 ) jointed with cement slurry mixed with pigment to match the coloure of KOTA including necessary wastage ,cutting ,grinding & polishing completed as per the details are provided in drawings or as directed by Architect/Engineer. | Rm | 10 | 488 | 4880 | 10 | 4880 | 0 | 0 | 100% Claimed in RA Bill 1
4.03 | Kota polish | Providing and Applyng:- Of dimond polish over kota flooring if required . | Rm | RO
4.04 | Raised floor & Cinder filling | Providing and cinder filing to raised floor as per the drawing and instruction as per site location UPTO 250mm ht. | Sq.m | 0 | 2268 | 0 | 0 | 0
4.05 | WALL TILES ( BOH AREA ) | P/fixing glazed ceramic (Kajaria /Johnson Make) White- (200x300mm) Wall tiles as approved, UPTO 2100mm from FFLVL. or BOFC whichever is achieveable, in kitchen over a base of 20-25mm thick plaster with cement mortar 1:3 (1 cement: 3 fine sand) as per approved pattern, setting the tiles in cement slurry, joints filled and finished neat with white cement as/spec.(Basic cost of tile Rs.22/- per sft.) | Sq.m | 45 | 2484 | 111780 | 44.525 | 110600.1 | -0.475 | -1179.9 | 98.9% Claimed in RA Bill 1
4.06 | WALL TILES ( MOH AREA ) | Providing & Fixing of100x200mm White Bevelled Tile [JOHNSON ] in MOH Area with 12 thk base plaster cement mortar 1:4 and joined with white cement slurry mixed with pigment to match the shade of tile. The tile to be laid as per approved pattern. Completed as per design & details are provided or as directed by Architect. ( Base Rate 85/- Sq.Ft. ) | Sq.m | 30 | 3370 | 101100 | 0 | 0 | -30 | -101100 | 0% Claimed in RA Bill 1
4.1 | Granite Work | Providing ,cutting ,and laying 18 mm th. granite, laying over a cement motor ,bedding (1:4) as per the detail draing like thresh hold ,ledge wall top and etc Rate are included with required moulding ,shemfring and polish as per the detail drawing. | Sq.m | 6 | 4850 | 29100 | 1.845 | 8948.25 | -4.155 | -20151.75 | 31% Claimed in RA Bill 1
[6 empty] | 298700 |  | 176270.942 |  | -122429.058
5 | MS WORK
5.1 | MS tubular partition | P/F Full Ht partition (75mm above bofc) with single side Framework as per dwg, of MS Box section 50x50mm ,18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame of approved sections fixed to floor/soffit/existing ceiling structure with rust-free treatment & enamel paint of colour as specified ready to recieve ply on top. Rate inclusive of all necessary hardware, wastage, making provision for electrical points and edges with grooves, provision for fixing concealed LED lights, edge finishing as per detailed drawing. Measurement as per elevation | Sq.m | 0 | 5940 | 0 | 0 | 0 | 0 | 0
5.2 | MS tubular partition | P/F Full Ht partition with double Framework made to shape as per dwg, of MS Box section 50x50mm ,18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame of approved sections fixed to floor/soffit/existing ceiling structure with rust-free treatment & enamel paint of colour as specified ready to recieve ply on top. Rate inclusive of all necessary hardware, wastage, making provision for electrical points and edges with grooves, provision for fixing concealed LED lights, edge finishing as per detailed drawing. Measurement as per elevation (single side) | Sq.m | 0 | 9500 | 0 | 0 | 0 | 0 | 0
5.3 | MS tubular partition | P/F of MS Box section 25x25mm , 18 gauge at a spacing of 600 mm c/c in both direction to achieve rigidity in the frame of approved sections fixed to floor/soffit/existing ceiling structure with rust-free treatment & enamel paint of colour as specified ready to recieve ply on top. Rate inclusive of all necessary hardware, wastage, making provision for electrical points and edges with grooves, provision for fixing concealed LED lights, edge finishing as per detailed drawing. Measurement as per elevation | Sq.m | 10 | 4320 | 43200 | 0 | 0 | -10 | -43200 | 0% Claimed in RA Bill 1
5.4 | Framing for DMB's | Providing and fixing MS Frame work just below the false ceiling, to hang DMB's in MOH, supported by civil structure with two coats of ms primer etc, complete. | Sq.m | 3 | 3240 | 9720 | 0 | 0 | -3 | -9720 | 100% Claimed in RA Bill 1
[6 empty] | 52920 |  | 0 |  | -52920
6 | WOODEN WORK
6.1 | Bison board cladding | Providing and fixing :- 12mm th. Bison board over existing MS framework, ready to take tile finish on top. Rate inculsive of all necessary hardware wastage etc complete in all respects as per drawings/details. Measurement as per elevation. | Sq.m | 20 | 2430 | 48600 | 0 | 0 | -20 | -48600 | 0% Claimed in RA Bill 1
6.2 | Laminate cladding on wall & partition | Providing and fixing :- 19mm th. FR ply, finished with 1.0mm th. laminate of approved shade and make as/elevation. Rate inculsive of all necessary hardware wastage etc complete in all respects as per drawings/details | Sq.m | 30 | 4428 | 132840 | 0 | 0 | -30 | -132840 | 0% Claimed in RA Bill 1
6.4 | Acrylic sheet cladding on partition | Providing and fixing :- 4mm th. Grey and Red Acrylic sheet, pasted with approved adhesive over 19mm th. FR ply, over existing MS tubular structure, as/elevation. Rate inculsive of all necessary hardware wastage etc complete in all respects as per drawings/details | Sq.m | 13 | 5670 | 73710 | 0 | 0 | -13 | -73710 | 0% Claimed in RA Bill 1
6.6 | Door frame | Providing and fixing :- HARD Wood door frames i.e Sal wood or Equivalent 2.5"X 5"complete with grooves as specified complete polished/painted matching the laminate as specified, with all necessary hardware such as hold fasts etc. completed as per design & details given in drawing/Architect instruction. Door frames to be manufactured with horns minimum 3", 40x12mm rebate size and a temporary wooden strip to retain the shape of the frame etc.including polish of approved shade. | Rm | 0 | 1800 | 0 | 0 | 0 | 0 | 0
6.7 | DRY STORE ENTRY | Flush door 38 mm thk ply finished with 1mm thk.laminate on both side & 6" high aluminum powder coated grill at bottom of door. All necessary hardware (i.e. lock, handle, hinges, latch or tower bolt, door stopper, pvc buffer etc ) to be provided. Door held on granite jamb & having open door closer. All to be completed as per the details are provided in drawings or as directed by Architect/Engineer. Door size 3'0" x 7'0" | no | 1 | 35000 | 35000 | 0 | 0 | -1 | -35000 | 0% Claimed in RA Bill 1
6.8 | MANAGER CABIN DOOR (WITH VISION PANEL) | Providing & Making of Flush door (38 mm thk ply) finished with 1mm thk. on both side, having vision panel of size 2'-6" x 6" at eye level. All necessary hardware (i.e. lock, handle, hinges, latch or tower bolt, door stopper, door pvc buffer etc ) to be provided. (Door Size: 3'0"x7'0" Incl. Door Frame), completed as per the details are provided in drawings or as directed by Architect/Engineer. | no | 1 | 35000 | 35000 | 0 | 0 | -1 | -35000 | 0% Claimed in RA Bill 1
6.9 | BOH ENTRY (VISION PANEL DOOR) | Providing & Making of Flush door (38 mm thk ply) finished with 1mm thk. on both side, having vision panel of size 9"x9" at eye level. All necessary hardware (i.e. lock, handle, hinges, latch or tower bolt, door stopper, door pvc buffer etc ) to be provided. (Door Size: 3'0"x7'0" Incl. Door Frame), completed as per the details are provided in drawings or as directed by Architect/Engineer. | no | 1 | 38000 | 38000 | 0 | 0 | -1 | -38000 | 0% Claimed in RA Bill 1
6.11 | Front Counter Portal | Providing and fixing Of front counter portal with 18 mm thick ply finished with 1mm th. Lamiante on all visible faces as per the detail drawings | Sq.m | 10 | 15000 | 150000 | 3.956 | 59340 | -6.044 | -90660 | 40% Claimed in RA Bill 1
6.12 | Main Counter For Order and Picup | Providing & Fixing:- Of 2'-9" deep counter to order & Pick Up made from 19mm thick FR Ply with nosing in front as per detail drawing. Counter top and front fascia to be finished in white corian EM-03 with 150mm wide 3 vertical stripes of Red corian as mentioned, all internal surfaces & under counter storage finished in plain white laminate, niche for KDS, provision for cash till, wire manager etc to completed as per details & design provided or as directed by Architect. Elevation area from MOH side shall be Measured. | Sq.m | 3.5 | 49140 | 171990 | 3.496 | 171793.44 | -0.004 | -196.56 | 100% Claimed in RA Bill 1
6.14 | OVERHEAD STORAGE (MANAGERS ROOM) | P/Fof 450MM deep overhead storage unit made of 19mm thk. Commercial board.Externally Laminated with laminate of approved shade, off white enamel painted inside.Cost is inclusive of handles, foldable 19mm th. comm. board shelves,partitions etc. and polish complete. Measurement as per elevation | Sq.m | 1 | 24300 | 24300 | 0 | 0 | -1 | -24300 | 0% Claimed in RA Bill 1
6.15 | MANAGER -O.T. TABLE-LCMS | P/f Table made out of 3/4" thk.commercial board laminated with (LAM -8844 AGED SUEDE ASH FORMICA MAKE). The table to have one drawer unit and key board tray. Cost would include cost of all hardwares likeTelescopic Channels,"C" shaped brushed steel handles, ball catchers,locks etc complete with polish. Measurement as per plan | Sq.m | 0 | 24300 | 0 | 0 | 0 | 0 | 0
6.16 | SOFT BOARD (MANAGERS ROOM , CREW ROOM & DELIVERY TABLE ) | Providing & fixing of Soft board for Managers Cabin with fabric of approved shade, completed as per the details are provided in drawings or as directed by Architect/Engineer. Basic rate of Fabric as Rs. 100/r.mtr. | Sq.m | 0 | 3200 | 0 | 0 | 0 | 0 | 0
[6 empty] | 709440 |  | 231133.44 |  | -478306.56
8 | FALSE CEILING/PAINTING
8.1 | Metal Grid ceiling | Ceiling - Supply and install - 600x600mm Metal grid false ceiling including all necessary fitting, supports, accessories, consumables, opening,etc.in accordance with the drawings and specifications | Sq.m | 86 | 2592 | 222912 | 0 | 0 | -86 | -222912 | 0% Claimed in RA Bill 1
8.3 | Paint in BOH | Providing & applying Of Two or more coats of roller applied premium acrylic emulsion(Asian -0765 MORNING GLORY) paint of interior grade,having VOC (Volatile Organic Compound ) content less than 50 grams/ litre of approved brand and manufacture (Asian Paints applyingTwo coats birla putty to achive smooth surface of BOH area ceiling and one coats primer and two or more coats of paint to achieve even shade and colour as per direction and satisfaction of Architect | Sq.m | 90 | 648 | 58320 | 0 | 0 | -90 | -58320 | 0% Claimed in RA Bill 1
[6 empty] | 281232 |  | 0 |  | -281232
9 | MISCELLANEOUS ITEMS
9.1 | SS PARTITION | Providing and fixing of 304 grade stainless steel partition made with 20X20mm tube frame and wrapped with stainless steel sheet and completed as per the details are provided in drawings or as directed by Architect/Engineer. Rate include SS sheet and ss frame and all necessary hardware etc. | Sq.m | 0 | 9180 | 0 | 0 | 0 | 0 | 0
9.2 | Corner Guard For BOH Area | Providing & fixing of 25mm x 25mm SS (202 Grade) Tile Guard in Stainless Steel ( Brushed surface finished 1mm thk.) complete as per approved specification, completed as per the details are provided in drawings or as directed by Architect/Engineer. | Rm | 75 | 750 | 56250 | 40 | 30000 | -35 | -26250 | 53% Claimed in RA Bill 1
9.3 | Trap Door in BOH Area | Providing & fixing Trap door to be made of 19mm BWP ply, finished with laminate or approved paint to match the shade of false ceiling. The trapdoor edges to be finished with 8mm thick teak wood lipping painted to match ceiling color. The item is inclusive of all fittings, fixtures and hardware; providing & fixing all necessary SS hinges (concealed), approved locking system, tied with safety chain, any frames, necessary support structure from the ceiling for fixing the trap door shutters, shadow gap, tools and tackles etc. Rate shall include all wastage, necessary cutting,all leads and lifts at all levels, loading and unloading, transportation and all other incidental charges, cost of materials, providing patterns,as per design, labour, etc.,complete as per specification, design & details,as per the instructions of the Architect/Engineer in charge. Refer to detail drawing | Nos | 4 | 18000 | 72000 | 0 | 0 | -4 | -72000 | 0% Claimed in RA Bill 1
9.4 | Key box | Providing and making key box as per the design at site | Nos | 1 | 4500 | 4500 | 0 | 0 | -1 | -4500 | 0% Claimed in RA Bill 1
9.6 | KICK PLATE ON DOORS | Providing and fixing stainless steel(20 gauge) kick plate on doors on both sides including all necessary screws, nails etc. complete at the bottom of each door.(8" high) | no | 2 | 2000 | 4000 | 0 | 0 | -2 | -4000 | 0% Claimed in RA Bill 1
9.9 | HOUSEKEEPING | Providing services for Daily Site Cleaning & proper House keeping on Handover day | Nos. | 1 | 10000 | 10000 | 1 | 10000 | 0 | 0 | 100% Claimed in RA Bill 1
10 | MS Barricade | Providing and fixing of 25x25mm pipe frame for temporary Baricating, to completed as per details & design given in drawing/Architect instruction. | Sq.m | RO
|  | TOTAL |  |  |  | 146750 |  | 40000 |  | -106750
|  | SUB-TOTAL |  |  |  | 1603495.2 |  | 544952.2186 |  | -1058542.9814
| 1 | DX and Ventilation System
| S.No. | Description | Unit | Qty | Rate | Amount
| Part A | DX EQUIPMENTS (Hi Side Works)
| 1 | Air Cooled Split units (R32)(Inverter Type)
| 1.1 | Supply of Air Cooled Split airconditioners each comprising an outdoor unit consisting of hermetic scroll compressor, air cooled condensing unit, Condenser fan etc. with outer casing and indoor fan coil unit(s) consisting of centrifugal fans, fan motor, DX cooling coil, outer casing, filter, control and power panel with remote control etc. both inter connected with copper refrigerant pipe and drain pipe of required length as given, cabling and wiring, insulation with cross linked polyethelene foam, full charge of refrigerant gas and oil, M.S. base frame, supports etc. complete as per specifications and drawings. The cost shall also include angle iron stands for outdoor units.
| A | HI WALL TYPE
| 1.1.1 | 1.5 TR | Nos | 1 | 60900 | 60900 | 1 | 60900 | 0 | 0 | 100% Claimed in RA Bill 1
| B | DUCTABLE TYPE
| 1.1.2 | 11.0 TR | Nos | 1 | 282500 | 282500 | 1 | 282500 | 0 | 0 | 100% Claimed in RA Bill 1
|  | Sub-Total Part-'A' Rs. |  |  |  | 343400 |  | 343400 |  | 0
| Part B | DX EQUIPMENTS (Low Side Works)
| 1 | Air Cooled Split units (R32)(Inverter Type)
| 1.1 | Installation . Testing and commissioning of Air Cooled Split airconditioners each comprising an outdoor unit consisting of hermetic scroll compressor, air cooled condensing unit, Condenser fan etc. with outer casing and indoor fan coil unit(s) consisting of centrifugal fans, fan motor, DX cooling coil, outer casing, filter, control and power panel with remote control etc. both inter connected with copper refrigerant pipe and drain pipe of required length as given, cabling and wiring, insulation with cross linked polyethelene foam, full charge of refrigerant gas and oil, M.S. base frame, supports etc. complete as per specifications and drawings.
| A | HI WALL TYPE
| 1.1.1 | 1.5 TR | Nos | 1 | 2000 | 2000 | 1 | 2000 | 0 | 0 | 100% Claimed in RA Bill 1
| B | DUCTABLE TYPE
| 1.1.2 | 11.0 TR | Nos | 1 | 15000 | 15000 | 1 | 15000 | 0 | 0 | 100% Claimed in RA Bill 1
|  | Sub-Total Part-'B' Rs. |  |  |  | 17000 |  | 17000 |  | 0
| Part C | VENTILATION EQUIPMENTS
| 1 | AHU Fan Section
Supply , Installation, Testing and Commissioning of Double Skin Type AHU Fan section with 0.6 mm preplasticized/precoated GI sheet outside and 0.6 mm plain Galvanized sheet inside with 25mm injected PUF insulation of 42KG/m3 , G.I. blower section, DIDW Blower (Forward Curved) with motors , base , drive arrangement ,Filter, motor drive suitable for Outdoor Application complete as per specifications and drawings .
| 1.1 | 5000 CFM ; SP 30 mm of wg;for Kitchen Exhaust , 2.25 KW Motor | Nos. | 1 | 146000 | 146000 | 1 | 146000 | 0 | 0 | 100% Claimed in RA Bill 1
| 2 | Package Type Air Washers
Providing and fixing of Double Skin Packaged Type Air Washer with extruded aluminium section with 0.6 mm preplasticized/precoated GI sheet outside and 0.6 mm plain Galvanized sheet inside, 25 mm thick PUF insulation of 42KG/m3 , G.I. blower section, DIDW Blower (Backward Curved) / Plug Fans with motors , base , drive arrangement ,Filter, cooling pad section, stainless steel sump tank and housing, motor drive, water circulation pump, piping, valves & fittings etc. suitable for Outdoor Application as per specifications and drawings .
| 2.1 | 4200 CFM (with Backward Type DIDW Blowers 3.75 KW Motor ; SP 40 mm of wg;for Kitchen Fresh Air Supply | Nos | 1 | 220000 | 220000 | 1 | 220000 | 0 | 0 | 100% Claimed in RA Bill 1
|  | Sub-Total Part D Rs. |  |  |  | 366000 |  | 366000 |  | 0
| PART-D : | LOW SIDE WORKS
| 1 | Piping
| 1.1 | Refrigerant Piping
| 1.1.1 | Refrigerant Piping (DX System)(R32 Refrigerant)
Providing and fixing copper piping with nitreal rubber with chaseling as per specifications and drawings.
| a. | 1.5 TR Machine (Liquid Line + Gas Line) | Mtrs. | 15 | 1050 | 15750 | 15 | 15750 | 0 | 0 | 100% Claimed in RA Bill 1
| b. | 11.0 TR Machine (Liquid Line + Gas Line) | Mtrs. | 10 | 1450 | 14500 | 10 | 14500 | 0 | 0 | 100% Claimed in RA Bill 1
(Note : 1RM is equal to 1 RM of gas line and 1 RM of liquid line)
| 1.2 | Drain Piping
| 1.2.1 | 32 mm PVC Pipe with 9 mm insulation | RM | 5 | 175 | 875 | 5 | 875 | 0 | 0 | 100% Claimed in RA Bill 1
| 1.2.2 | 25 mm PVC Pipe with 9 mm insulation | RM | RO
| 1.2.3 | 20 mm PVC Pipe with 9 mm insulation | RM | 5 | 160 | 800 | 5 | 800 | 0 | 0 | 100% Claimed in RA Bill 1
| 2 | Ducting
| 2.1 | Factory Fabricated Ducting (GSS)
Supply, installation, balancing and commissioning of factory fabricated GSS sheet metal rectangular/round ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
| 2.1.1 | 0.63 MM (24 Gauge) | Sqm. | 100 | 1450 | 145000 | 85 | 123250 | -15 | -21750 | 85% Claimed in RA Bill 1
| 2.1.2 | 0.8 MM (22 Gauge) | Sqm. | 10 | 1850 | 18500 | 10 | 18500 | 0 | 0 | 100% Claimed in RA Bill 1
| 2.1.3 | 1.00 MM (20 Gauge) | Sqm. | 10 | 2200 | 22000 | 10 | 22000 | 0 | 0 | 100% Claimed in RA Bill 1
| 2.2 | Site Fabricated Ducting (GSS)
Supply, installation, balancing and commissioning of fabricated at site GSS sheet metal rectangular/round ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
| 2.2.1 | 0.63 MM (24 Gauge) | Sqm. | 10 | 1450 | 14500 | 10 | 14500 | 0 | 0 | 100% Claimed in RA Bill 1
| 2.2.2 | 0.8 MM (22 Gauge) | Sqm. | 5 | 1850 | 9250 | 5 | 9250 | 0 | 0 | 100% Claimed in RA Bill 1
| 3 | Insulation/ Accoustic Lining
| 3.1 | Duct Acoustic Lining
Supplying and Application of Acoustic lining within the Supply Air duct with 15 mm thick class 'O' open cell nitrile Rubber of density 140-160 kg./Cubm. as per spefications.
| 3.1.1 | 15 MM thick | Sqm | 15 | 950 | 14250 | 15 | 14250 | 0 | 0 | 100% Claimed in RA Bill 1
| 3.2 | Nitrile Rubber Insulation- Class 'O'
Supplying and fixing of closed cell elastomeric insulation of density 55 kg/cu.m.and K valueof not less than 0.037W/mk at 20 deg C as per specifications and drawings (For indoor applications) with factory Laminated 7 mill woven glass cloth
| 3.2.1 | 9 MM Thick (Return Air Duct) | Sqm | RO
| 3.2.2 | 13 MM Thick (Supply Air & Fresh Air Duct) | Sqm | 80 | 1350 | 108000 | 70 | 94500 | -10 | -13500 | 88% Claimed in RA Bill 1
| 3.2.3 | 19 mm Thick (Exhaust Duct) | Sqm | 35 | 1650 | 57750 | 30 | 49500 | -5 | -8250 | 86% Claimed in RA Bill 1
| 4 | Grilles / Diffusers/ Dampers / Louvers
| 4.1 | Supply, Installation, Testing and Commissioning of GI multiblade volume control duct damper complete with neoprene rubber gaskets, nuts, bolts, screws linkages, flanges etc., as per specifications. | Sqm. | 1 | 8250 | 8250 | 0 | 0 | -1 | -8250 | 0% Claimed in RA Bill 1
| 4.2 | Supply, Installation, Testing and Commissioning of multiblade Al volume control Collar / Grille / exhaust Air Opening damper complete with suitable links, lever and quadrants for manual control of airflow and with suitable links , lever and quadrants for manual control of airflow and neoprene rubber gaskets, nuts, bolts, screws, flanges etc., as per specifications. | Sqm. | 0.5 | 8250 | 4125 | 0 | 0 | -0.5 | -4125 | 0% Claimed in RA Bill 1
| 4.3 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded aluminium Supply / Exhaust Air Grills as per specifications | Sqm. | 1 | 8850 | 8850 | 0 | 0 | -1 | -8850 | 0% Claimed in RA Bill 1
| 4.4 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded Aluminium Continuous Grille as per specifications | [5 empty] | 0
| 4.4.1 | 200 MM Aluminium Continuos Grille | RM | 5 | 1400 | 7000 | 0 | 0 | -5 | -7000 | 0% Claimed in RA Bill 1
| 4.4.2 | 150 MM Aluminium Continuos Grille | RM | 25 | 1250 | 31250 | 0 | 0 | -25 | -31250 | 0% Claimed in RA Bill 1
| 4.4.3 | 100 MM Aluminium Continuos Grille | RM | 10 | 1050 | 10500 | 0 | 0 | -10 | -10500 | 0% Claimed in RA Bill 1
| 4.5 | Providing and fixing of powder coated extruded aluminium exhaust air louvers/ fresh air louvers with bird screen and mounting arrangement as per specification and drawings. Free Area shall be more than 60% of gross area. | [5 empty] | 0
| 4.5.1 | Fresh Air / Exhaust Air Louvers with Bird Screen Mesh | Sqm. | 1 | 8500 | 8500 | 0 | 0 | -1 | -8500 | 0% Claimed in RA Bill 1
|  | Sub-Total Part E Rs. |  |  |  | 499650 |  | 377675 |  | -121975
| Part F | ELECTRICAL WORKS
Electrical Work
| 1 | Electrical Control Panel
Supply, installation, testing and commissioning of panel boards made of 2.0 mm thick steel sheet duly powder coated with voltmeter, ammeter, electronic energy meter, indicating lights, Stop/manual /Auto selector switch in each, outgoing current operated single phase preventer. The starters should have potential free contacts for connection to Building Automation System. The panel shall include contactors /over load relay with built in single phase protection / Time delay relay for delayed automatic start of the motor. All panels should have spare NO/ NC Contacts for BMS applications as required.
| 1.1 | Panel-PA10
|  | (1 x 2.25 KW + 1 X 3.75 KW) | Nos | 1 | 22500 | 22500 | 1 | 22500 | 0 | 0 | 100% Claimed in RA Bill 1
INCOMER
| -- | 1 No. incoming 40 Amps TP MCB
| -- | 1 No. Digital Type voltmeter with selector switch with control MCB
| -- | 1 No. Digital Type Ammeter 0-63 A with C.T.'s
| -- | 1 Set of RYB indication lamps with control MCB
| -- | 1 No. of 63 Amps Aluminium conductor 25kA bus bar duly sleeved as required.
OUTGOING
2 No. 16 Amps TP MCB for AHU's
1 No. DOL starter for 2.25 KW motor .
1 No. DOL starter for 3.75 KW motor .
2 Nos. of single phase preventor (current based-MPRD2)
2 Nos. direct reading Digital Type Ammeter
|  | Each star-delta/DOL starter consists of current operated MN type over load relay, contactor, push button, ON/OFF indication light | Set | 1 | 12600 | 12600 | 0 | 0 | -1 | -12600 | 0% Claimed in RA Bill 1
| 2 | Control & Transmission Wiring
| 2.1 | Providing & fixing control cum transmission wiring of 2 core x 1.5 sqmm copper in MS conduits between indoor and out door unit and between indoor units and their remote sensor/controller. | RM | 25 | 350 | 8750 | 22 | 7700 | -3 | -1050 | 88% Claimed in RA Bill 1
| 3 | Power Cabling
| 3.1 | Indoor Units
| 3.1.1 | Providing and fixing flexible power cable of 3 core x 1.5 sqmm copper between Indoor units and their power points | RM | 5 | 145 | 725 | 5 | 725 | 0 | 0 | 100% Claimed in RA Bill 1
| 3.1.2 | Providing and fixing flexible power cable of 3 core x 2.5 sqmm copper between Indoor units and their power points | RM | 5 | 145 | 725 | 5 | 725 | 0 | 0 | 100% Claimed in RA Bill 1
| 4 | Isolator (Weather Proof)
| 4.1 | Providing & fixing weather proof isolator near each outdoor unit & kitchen ventilation units as per specific control & drawup.
| 4.1.1 | 16 Amp MCB | Nos. | RO
| 4.1.2 | 10 Amp MCP | Nos | RO
| 5 | Cables
Supplying and laying of XLPE insulated aluminium conductor armored cables of 1.1 KV grade of following sizes directly on wall/structural frame/ cable trays or racks using approved type of clamps,End terminations with Double Compression type glands on both ends, double earthing with GI strip/wire of suitable size and hardware as per specifications.
| 5.1 | 3 C x 4 Sq. mm | RM | 40 | 335 | 13400 | 38 | 12730 | -2 | -670 | 95% Claimed in RA Bill 1
| 5.2 | 3 C x 1.5 Sq. mm | RM | RO
| 6 | GI perforated Cable tray
Supply,Installation, Testing and Commissioning following size of perforated painted with powder coating M.S. cable trays with perforation not more than 17.5%, in convenient sections, joined with connectors, suspended from the ceiling with M.S. suspenders including bolts& nuts, painting suspenders etc. as required.
| 6.1 | 150 mm width X 50 mm depth X 1.6 mm thickness | RM | RO
| 6.2 | 300 mm width X 50 mm depth X 1.6 mm thickness | RM | RO
| 6.3 | 450 mm width X 50 mm depth X 2.0 mm thickness | RM | RO
| 7 | Earthing
Supply,Installation, Testing and Commissioning of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required
| 7.1 | 25 mm x 6 mm GI strip | RM | 10 | 650 | 6500 | 0 | 0 | -10 | -6500 | 0% Claimed in RA Bill 1
| 7.2 | 8 SWG GI Wire | RM | 10 | 550 | 5500 | 0 | 0 | -10 | -5500 | 0% Claimed in RA Bill 1
|  | Sub-Total Part F Rs. |  |  |  | 70700 |  | 44380 |  | -26320
|  | Total |  |  |  | 953350 |  | 805055 |  | -148295
BILL OF QUANTITIES FOR LIGHTING PROJECT : Mumbai T1C_Lighting BOQ Mumbai Airport
| S.NO. | DESCRIPTION | UNIT | QTY. | Pikture Perfect R1 | Amount
| 1 | Square Ceiling Mounted concealed Fixture 175mmx175mm off white powder coated.Lamp Code: LED lamp integrated 4000K; 22 W.(Counter,Toilet & Change) | NOS | 14 | 1550 | 21700 | 0 | 0 | -14 | -21700 | 0% Claimed in RA Bill 1
| 2 | 4'-0" Long 20w Tubelight for BOH 6500k | NOS | 30 | 750 | 22500 | 0 | 0 | -30 | -22500 | 0% Claimed in RA Bill 1
| 3 | Hanging Kit for Tubelight 2pc.= 1 Set | NOS | 15 | 550 | 8250 | 0 | 0 | -15 | -8250 | 0% Claimed in RA Bill 1
|  | TOTAL |  |  |  | 52450 |  | 0 |  | -52450
S.No | Items | Specification | Make | Qty | Rate | Amount
1 | Dome Cameras | Full HD 720p Video Output, Adopt HDTVI Technology, Trud Day & Night, Lens 3.6mm, 12LED, Upto 20M IR Distance | Hikvision | 9 | 6500 | 58500 | 0 | 0 | -9 | -58500 | 0% Claimed in RA Bill 1
2 | Hard Disk - SURVEILLANCE | 2TB | Seagate / Toshiba | 1 | 6550 | 6550 | 0 | 0 | -1 | -6550 | 0% Claimed in RA Bill 1
3 | CAT 6 Wire provide and supply |  | AMP/Molex | 130 | 175 | 22750 | 120 | 21000 | -10 | -1750 | 92% Claimed in RA Bill 1
4 | Screen | 18-19" | Acer/LG/Dell | 1 | 10500 | 10500 | 0 | 0 | -1 | -10500 | 0% Claimed in RA Bill 1
5 | Power Supply | 8 Cameras - 10 amps X 2 | CP-PLUS / ZEBRONICS | 1 | 1850 | 1850 | 0 | 0 | -1 | -1850 | 0% Claimed in RA Bill 1
6 | HDMI Cable | 5 Mtrs | MX | 1 | 6500 | 6500 | 0 | 0 | -1 | -6500 | 0% Claimed in RA Bill 1
7 | Cameras Installation | All Over India | Hikvision | 1 | 6750 | 6750 | 0 | 0 | -1 | -6750 | 0% Claimed in RA Bill 1
Total Amount | [5 empty] | 113400 |  | 21000 |  | -92400

## Sheet1 (hidden)
15nos nhani trap
15nos 75*110 reducer
40ft 160mm pvc pipe
4nos 110mm Y
4nos 110mm shoe bend
70ft. 110mm pvc pipe
4nos 110mm bend
4nos 250gm solution pvc
6nos 110 coupling
1/2“ cpvc 60 ft
3/4” cpvc 50ft
1/2” cpvc elbow 25nos
3/4” cpvc elbow 25nos
1/2” cpvc T 6nos
3/4” cpvc T 6nos
1/2” cpvc 8nos
3/4” cpvc 8nos
3/4*1/2 bushing 5nos
1”*3/4” bushing 5nos
Ro ka ek motar