## Summary
Semolina Project Pvt Ltd.
Vendor Name : ARIHANT INFRACON
PO No: Semolina/PO/24-25/000687
Sr no | Description | PO value | Previous Bill Amount | Present Bill Amount | Cumulative Amount | Total Variation Amount with Extra Qty
1 | Civil & Interior Work | 1700472.8 | 1090165.24 | 609637 | 1699802.24 | 10166.94
2 | Electrical | 1245189.95 | 612900 | 631758.57 | 1244658.57 | 5234.5
3 | Plumbing | 190440 | 95500 | 94940 | 190440 | 2185
4 | HVAC | 651375 | 37500 | 613084.5 | 650584.5 | 19659.5
5 | Furniture | 1904500 | 815000 | 1089500 | 1904500 | 0
6 | Signages | 180500 | 0 | 180500 | 180500
7 | Fire Alarm System | 255100 | 0 | 254714 | 254714 | -386
8 | Fire Sprinkler System | 95040 | 0 | 95040 | 95040 | 1770 | 2806.5592
9 | IT | 44400 | 22200 | 22200 | 44400 | 560
10 | CCTV System | 60500 | 30250 | 30250 | 60500 | 1280
| Total | 6327517.75 | 2703515.24 | 3621624.07 | 6325139.31 | 40469.94
| GST 18 % | 1138953.195 | 486632.7432 | 651892.3326 | 1138525.0758 | 7284.5892
| Gross Total | 7466470.945 | 3190147.9832 | 4273516.4026 | 7463664.3858 | 47754.5292

## Abstract(RA 2)
RA-02 - Abstract
WO No :-Semolina/PO/24-25/000687 | [7 empty] | Date:- 10-10-2024
AJ Kitchen Fit Out
SR.NO. | DESCRIPTION | UNIT | PO QTY | PO RATE (Rs) | PO AMOUNT (Rs) | TOTAL EXECUTED QTY | RA - 1 |  | RA - 2 (Current Bill) |  | VARIATION
[7 empty] | QTY | AMOUNT (Rs) | QTY | AMOUNT (Rs) | QTY | AMOUNT (Rs)
CIVIL & INTERIOR WORKS
1 | Partition walls
1.01 | Supply and installation of fire rated calcium silicate board Partition Wall with the necessory supports, fittings and fixtures (excluding final finishes). Purposed height of kitchen partition wall is 4500 mm and pot wash room is 3150mm, it may be change as per site conditions. Note: Framing and double side board to be installed. Final Finishies price to be quoted in wall finishes section. | SQM | 44.17 | 1700 | 75089 | 44.1712 | 44.1712 | 75091.04 | 0 | 0 | 0.0012 | 2.04
1.02 | Supply and installation of fire rated calcium silicate board cladding on the existing walls in the Kitchen & pot wash area to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures (excluding final finishes). Purposed height is 3150mm, it may be change as per site conditions. Note: Framing and single side board to be installed on existing wall. Final Finishies price to be quoted in wall finishes section. | SQM | 26.91 | 2000 | 53820 | 26.9097 | 26.9097 | 53819.4 | 0 | 0 | -0.0003 | -0.6
1.03 | Supply and installation of 100 mm thick fire rated Gypsum board cladding on the existing walls to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures in the FOH & dining area walls. (excluding final finishes). Purposed height is 3700mm, it may be change as per site conditions. Note: Framing and single side board to be installed on existing wall. Final Finishies price to be quoted in wall finishes section. | SQM | 47.71 | 1800 | 85878 | 47.73 | 47.73 | 85914 | 0 | 0 | 0.02 | 36
1.04 | Supply and installation of 65mm thick fire rated Gypsum board cladding on the existing walls to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures in the FOH & dining area walls. (excluding final finishes). Purposed height is 3700mm, it may be change as per site conditions. Note: Framing and single side board to be installed on existing wall. Final Finishies price to be quoted in wall finishes section. | SQM | 50 | 1800 | 90000 | 68.45 | 68.45 | 123210 | 0 | 0 | 18.45 | 33210
2 | FLOOR FINISHES
2.01 | 150mm thick concrete floor screeding to raise the floor to accomodate the drainage pipes and floor gratings & to receive floor finish in the Kitchen & FOH counter areas; all in accordance with drawings & site conditions. Note: Total height of floor to be raised including floor finishes is 180mm in the kitchen & FOH counter area only | SQM | 32.4 | 5800 | 187920 | 32.4 | 32.4 | 187920 | 0 | 0 | 0 | 0
2.02 | Supply & installation of water proofing with all necessary items; all in accordance with drawings and below mentioned specification. Note: Detailed specifications of the materials to be submitted to client. |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0
2.02a | Wet Areas: 2 Layers of 4mm thick SBS Bituminous membrane with 24-hour water ponding test including the sealing of Cores in the slab/walls (inspected and approved from airports team). | SQM | 44.14 | 1200 | 52968 | 44.14 | 44.14 | 52968 | 0 | 0 | 0 | 0
2.03 | Supply and installation of self levelling with all necessary items; all in accordance with drawings. | SQM | 83.28 | 1585 | 131998.8 | 83.28 | 83.28 | 131998.8 | 0 | 0 | 0 | 0
2.04 | Supply and installation of anti-skid 600 x 600 mm white floor tile in the kitchen & Pot wash area as per the drawings and renders. Note: Material to be approved by Clients team. | SQM | 14.07 | 2500 | 35175 | 14.04 | 14.04 | 35100 | 0 | 0 | -0.03 | -75
2.05 | Supply and installation of Stone Plastic Composite (SPC) flooring in the FOH dining area area; colour & design as per drawings & render. Note: material to be approved by Clients Team | SQM | 47.25 | 2800 | 132300 | 47.25 | 47.25 | 132300 | 0 | 0 | 0 | 0
2.06 | Supply and installation of anti skid 300 x 300 mm designer floor tile in the FOH area; colour & design as per drawings & render. Note: material to be approved by Clients Team | SQM | 23.63 | 2700 | 63801 | 23.63 | 23.63 | 63801 | 0 | 0 | 0 | 0
3 | SKIRTING
3.01 | supply & installation of 100mm wooden skirting matching wall color as per the renders & drawings. Note: material to be approved by Clients Team | RM | 21.67 | 4300 | 93181 | 11.4 | 10.835 | 46590.5 | 0.565 | 2429.5 | -10.27 | -44161
4 | WALL FINISHES
A | Kitchen & Pot Wash areas | [9 empty] | 0 | 0
4.01 | Supply & installation of 300x300 mm White wall tile in the kitchen & Pot wash area as per drawings and renders. Note: material to be approved by Clients Team. Considered Ceiling height in kitchen is 3000mm | SQM | 61.73 | 1600 | 98768 | 65.4 | 0 | 0 | 61.73 | 98768 | 3.67 | 5872
4.02 | Allow sum for the supply and Installation of SS corner beeding on the corners of kitchen wall tiles. | RM | 14.4 | 4300 | 61920 | 14.2 | 0 | 0 | 14.2 | 61060 | -0.2 | -860
B | FOH & Dining areas | [9 empty] | 0 | 0
4.03 | Supply & Painiting of matt finish paint of approved color on the walls of dining & FOH area as per the drawings & renders. Note: Material to be approved by clients Team | SQM | 117.4 | 350 | 41090 | 115.56 |  |  | 117.4 | 41090 | -1.84 | -644
4.04 | Supply & installation of WOODEN MOULDING STRIP finished with paint of approved colour on the walls of Dining & FOH area as per drawings and renders. Note: Material to be approved by clients Team | RM | 168.71 | 500 | 84355 | 194.14 | 84.357 | 42178.5 | 109.783 | 54891.5 | 25.43 | 12715
5 | GYPSUM WORKS
5.01 | Supply & installation of fire rated bulkhead gypsum above the hood in white paint matt finish. Paint shall be included, as per the below hood sizes. Considered Ceiling height in kitchen is 3000mm
5.01A | Hood - Hot Cooking line : 2600 L x 1000 W x 600 H mm | Nos | 1 | 20000 | 20000 | 1 | 0 | 0 | 1 | 20000 | 0 | 0
6 | CEILING WORKS
6.01 | Supply & Installation of 600x600 mm metal tile ceiling in the Kitchen & Pot wash area with necessary support, fixtures & accessories as per drawings & renders Note: Material to be approved by Clients Team. | SQM | 13.94 | 2600 | 36244 | 16.0975 | 0 | 0 | 13.94 | 36244 | 2.1575 | 5609.5
6.02 | Supply and Installation of Metal 3x3cm mesh ceiling with fire rated hanging flowers in the FOH & Dining areas including the final finishes with necessary support, fixtures & accessories as per drawings & renders. Note: Material to be approved by Clients Team. This ceiling will be Mesh type so that flower can be hanged. | SQM | 36.12 | 4100 | 148092 | 35.8 | 0 | 0 | 35.8 | 146780 | -0.32 | -1312
6.03 | Supply and Installation of fire rated Gypsum false ceiling with cove (for cove lights provision) in the the FOH & dining area with paint of approved color with necessary support, fixtures & accessories as per drawings & renders, refer to RCP layout. Including access panel/door as per the MEP services and Cutting & finishing for the AC grill/diffuser and lights. Note: Material to be approved by Clients Team. Running meter of cove has included in total quantity (24.87m+9.32m) | SQM | 67.86 | 1800 | 122148 | 67.86 | 32.93 | 59274 | 34.93 | 62874 | 0 | 0
6.04 | Supply and painting with matt finish paint of approved color on the slab & walls of inside ceiling area of FOH & dinning, including paints on all MEP services & metal ceiling parts. Note: color to be selected/approved by Clients Team. The metioned quantity is the total covered area of the FOH and dining, quote the price accordingly for the paint on the slab and walls above the ceiling level and painting on all the MEP services | SQM | 67.45 | 500 | 33725 | 67 | 0 | 0 | 67 | 33500 | -0.45 | -225
7 | DOORS
7.01 | Supply and installation of heavy duty single leaf both side swing fire rated wooden door (kitchen door flushed to wall invisible type finished with same wall color) with the door frame for kitchen, including all the fittings & accessories as per the drawings and renders. Groove to be provided as per drawing and render. Dim: 2100H x 900W mm Note: Door frame should not be visible from Customer dining area. | Nos | 1 | 32000 | 32000 | 1 | 0 | 0 | 1 | 32000 | 0 | 0
8 | Miscellaneous works
8.01 | Allow sum for the closing of wall opening using foams. | LS | 1 | 10000 | 10000 | 1 | 0 | 0 | 1 | 10000 | 0 | 0
8.02 | Allow sum for the Kitchen equipment equipment unloading and shifting till outlet | LS | 1 | 10000 | 10000 | 1 | 0 | 0 | 1 | 10000 | 0 | 0
CIVIL & INTERIOR WORKS - TOTAL |  |  |  |  | 1700472.8 |  |  | 1090165.24 |  | 609637 |  | 10166.94
FURNITURE
1 | CHAIRS & BANQUETTE SEATING
1.01 | Customer Dining Chair : Supply of Chair, inner side of chair in upholstery designer fabric of approved design and color, outer side of chair in upholstery of approved grey fabric, MS tube legs finished in golden powder coat. Dimensions, color & design as per the drawings and renders. Note: Samples to be submitted by contractor | PCS | 24 | 12500 | 300000 | 24 | 12 | 150000 | 12 | 150000 | 0 | 0
1.02 | Banquett Seating: Supply and installation of BANQUETTE SEATING MADE OF CUSHION FINISHED WITH LEATHER OF APPROVED COLOUR with 18mm THK MR MDF FINISHED LEATHER OF APPROVED COLOUR as per the drawings & renders. Size: L 11280 mm Dimensions, color & design as per the drawings and renders. Note: Samples to be submitted by contractor. | PCS | 1 | 180000 | 180000 | 1 | 0.5 | 90000 | 0.5 | 90000 | 0 | 0
2 | TABLE
2.01 | Customer Dining Table: Supply and Installation of Table made up of 20mm thick Corian tabletop of approved color with 2 mm thick MS tube legs finished in black powder coat and gold power coat, 6mm thick Golden metal embedded in the sides of tabletop, leg base with 6mm thick steel plate in gold powder coat finish as per the drawings and renders. Note: Samples to be submitted by contractor Dimensions, color & design as per the drawings and renders.
| 650L x 650W x 750H mm | PCS | 18 | 28000 | 504000 | 18 | 9 | 252000 | 9 | 252000 | 0 | 0
3 | JOINERY
3.01 | Supply & installation of "FOH counter" made up of 18mm thick MR-MDF structured, with 12mm thick Corian material finish on top; and sides finished by stucco paint of RAL 4008 color and with black metal strips and cove lighting, 20mm wide black metal strips placed on the top of stucco finish with 20mm spacing 12mm thick corian skirting, 30mm dia 75mm high from centre guard rail finished with gold colour, 18mm THK MR MDF Partition wall 1100mm high finished with Oak wood veneer 18mm THK MR MDF swing door finish with oak wood veneer, 18mm THK MR MDF Planter box above counter sides finished with Oak wood Veneer and top with Corian of approved design Adjustable 2 layer open shelf finished with approved white laminate, 3 layer adjustable shelf inner side finished with approved white laminate and outer with Oak wood veneer, Open spaces for display units, All inner sides of the counter are to be finished with white laminate, and all necessary support, fittings, and accessories as per approved drawings and renders. Space/provisions are to be provided to accommodate the equipment inside the counter as shown in the drawings and renders. Note: Actual countertop material sample shall be submitted by the contractor and, required provision for electrical socket as per power layout. The contractor shall refer to the counter details for complete detailings, dimensions & materials etc. | NOS | 1 | 520000 | 520000 | 1 | 0.5 | 260000 | 0.5 | 260000 | 0 | 0
3.02 | Supply and installation of "FOH Back counter" made up of SS metal structure (Kitchen equipment vendor makes SS metal frame structure), Top finished with Corian material of approved design and the sides cladding & doors by 18mm thick MR-MDF finished with oak wood veneer. The contractor shall refer to the FOH back counter detail drawings & renders for complete detailings, dimensions & materials etc. | Nos | 1 | 120000 | 120000 | 1 | 0 | 0 | 1 | 120000 | 0 | 0
3.03 | Supply and installation of "Back Counter for u/c Ice Machine" made up of 18mm THK MRMDF COUNTER WITH OPEN SHELF FOR UNDERCOUNTER ICE CUBE MACHINE, Top finished with Corian material of approved design and the sides cladding by 18mm thick MR-MDF finished with oak wood veneer. The contractor shall refer to the detail drawings & renders for complete detailings, dimensions & materials etc. | Nos | 1 | 68000 | 68000 | 1 | 0 | 0 | 1 | 68000 | 0 | 0
3.04 | Supply and installation of SERVICE COUNTER MADE UP OF 18mm THK MRMDF FINISHED WITH OAK WOOD VENEER ON THE OUTER SIDE, 18mm THK MRMDF DRAWER FOR CUTTLERY, FINISHED IN WHITE MICA IN INNER SIDE, as per the renders and drawings. The contractor shall refer to the service counter detail drawings & renders for complete detailings, dimensions & materials etc. | Nos | 1 | 42000 | 42000 | 1 | 0 | 0 | 1 | 42000 | 0 | 0
3.05 | Supply and installation of Electrical panel unit made up of 18mm THK FRMDF finished with paint of the same wall colour outer side with mouldings and in white mica on the inner side as per the drawings. The contractor shall refer to the service counter detail drawings & renders for complete detailings, dimensions & materials etc. | Nos | 1 | 16500 | 16500 | 1 | 0 | 0 | 1 | 16500 | 0 | 0
4 | PLANTER BOXES & ARTIFICIAL PLANTS
4.01 | Supply & installation of planter box with fire rated artificial plants with the 18mm thick MDF finished with laminate of approved color, 10mm thick wooden moulding, 6mm thick Corian cladding with 4mm grove & naturally looking artificial fire rated plant as per drawings and renders. Size: 600 x 300 x 800 mm Dimensions, color & design as per the drawings and renders. Note: Samples shall be submitted by contractor. | NOS | 2 | 31500 | 63000 | 2 | 2 | 63000 | 0 | 0 | 0 | 0
4.02 | Supply & installation of round shape planter box with fire rated artificial plants with the paint/powder coated finishes as per drawings and renders. Size of planter box: dia. 300mm Note: Samples shall be submitted by contractor. | Nos | 3 | 12000 | 36000 | 3 | 0 | 0 | 3 | 36000 | 0 | 0
4.03 | Supply and Installation of NATURALY LOOKING ARTIFICIAL GRASS AND TREE as per the drawings and renders. To be coordinate with FOH counter drawings. Note: Samples shall be submitted by contractor. Supply and installation of planter box to be quote along with the FOH counter in Joinery section. | Nos | 1 | 55000 | 55000 | 1 | 0 | 0 | 1 | 55000 | 0 | 0
FURNITURE - TOTAL |  |  |  |  | 1904500 |  |  | 815000 |  | 1089500 |  | 0
SIGNAGES & DISPLAY UNIT
0.01 | AJ1881 LOGO AT FRONT ELEVATION: Supply & Installation of AJ1881 front lit aluminium 3D logo, letter made of aluminium channellume 3D letters with font face acrylic illuminated LED with transformer. Including the Vinyle graphic base & structure, to be hunged from the top, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 | 32500 | 32500 | 1 | 0 | 0 | 1 | 32500 | 0 | 0
| Above mentioned logo in the Marathi language with the same material and specification | Nos | 1 | 32500 | 32500 | 1 | 0 | 0 | 1 | 32500 | 0 | 0
0.02 | AJ1881 LOGO IN THE DINING AREA WALL: Supply & Installation of AJ1881 front lit aluminium 3D logo, letter made of aluminium channellume 3D letters with front face acrylic illuminated LED with transformer, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 | 18500 | 18500 | 1 | 0 | 0 | 1 | 18500 | 0 | 0
0.03 | HEART SHAPE LOGO IN THE DINING AREA WALL: Supply & Installation of front lit 3D Logo- Heart Shape, letter made of aluminium channellume 3D letters with front face acrylic illuminated LED with transformer, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 | 11000 | 11000 | 1 | 0 | 0 | 1 | 11000 | 0 | 0
1.04 | Supply and installation of 43" Digital Display unit for the Menu as per the drawings and renders. Note: Sample to be approved by Clients team | Nos | 2 | 43000 | 86000 | 2 | 0 | 0 | 2 | 86000 | 0 | 0
SIGNAGES & DISPLAY UNIT- TOTAL |  |  |  |  | 180500 |  |  | 0 |  | 180500 |  | 0
PLUMBING
A | SANITORY FIXTURES
5 | Supplying, Installing, testing & commissioning of Pantry sink with single bowl with out drain board manufactured from stainless steel, 18G high grade indestructible chrome nickel steel with top quality polish, 1no.40 mm dia CP waste coupling, with 1no. 40mm dia CP bottle trap with extension pipe, CP angle cock, & divertor with Counter mounted type sink tap and necessary wall flanges,angle cock etc., complete. | Nos | 4 | 13500 | 54000 | 4 | 0 | 0 | 4 | 54000 | 0 | 0
[7 empty] | 0 | 0 |  |  | 0 | 0
6 | Supplying, installing, testing and commissioning of 15mm CP angle valve with CP flanges including necessary fixing materials etc.,complete. | Nos | 17 | 520 | 8840 | 17 | 0 | 0 | 17 | 8840 | 0 | 0
[7 empty] | 0 | 0 |  |  | 0 | 0
7 | Supplying, installing, testing and commissioning of 15mm CP bib cock with CP flanges including necessary fixing materials etc.,complete. | Nos | 2 | 3000 | 6000 | 2 | 0 | 0 | 2 | 6000 | 0 | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0
14 | Supply, Fixing, testing and commissioning of approved make vertical/horizontal type Electric 'water heater suitable for pressure rating up to 6Kg/sqcm with heating element with thermostat, 2 Nos. 15mm dia CP angle valve, pressure relief valve, non-return valve with CP copper connecting pipes with wall flanges etc., complete with all inlets, outlets, valves and all other accessories etc., complete. | [9 empty] | 0 | 0
14.1 | Capacity : 15 lts. 1..5 K.W heating element | Nos | 1 | 11000 | 11000 | 1 | 0 | 0 | 1 | 11000 | 0 | 0
14.2 | Capacity : 25 lts. 2 K.W heating element | Nos | 1 | 11500 | 11500 | 1 | 0 | 0 | 1 | 11500 | 0 | 0
B | DRAINAGE
1 | Supplying, fixing, testing and commissioning of PVC Soil, waste and ventilating pipes (SWR) conforming to IS:13592 Type B with rubber ring,yellow seal (conforming to IS : 5382) joints inclusive of all necessary specials like bends, tee, offsets, door bends, junctions, cowls, threaded type cleanout etc., laid under floor / fixed on walls and in pipe shaft with proper pipe support like brackets, hangers, G.I grip bolts etc., complete. The support shall be painted with two coats of enamel paint.The rate shall include the cost of galvanized U clamps, bolts & nuts,painting of supports with 2 coats of zinc chromate primer with 2 coats of enamel paint of total DFT minimum 100 micron. As required at site as per drawings to the satisfaction of the Project Manager. Internal Toilet
1.1 | 75 mm dia | Rm | 30 | 950 | 28500 | 32.3 | 30 | 28500 | 0 | 0 | 2.3 | 2185
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
2 | Supplying, fixing and testing uPVC pressure pipes (6Kg/sqcm) conforming to IS 4985 for waste connection from washbasin, kitchen sink to floor trap, including, threading, cutting, laid under floor / concealed in wall etc. The work shall include wall chase and making good the same in cement mortar etc. complete to the satisfaction of Engineer-in-charge.The rate shall include the cost of galvanized U clamps, bolts & nuts,painting of pipes with 2 coats of zinc chromate primer with 2 coats of enamel paint of total DFT minimum 100 micron |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0
2.1 | 40mm dia | Rm | 10 | 1250 | 12500 | 10 | 10 | 12500 | 0 | 0 | 0 | 0
2.2 | 50 mm dia | Rm | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0
3 | Supplying, installing, testing and commissioning of Upvc floor trap with 110mm dia pipe PVC deep seal 'P' trap with necessary PVC fabricated boss connection with a minimum 2Nos. of 50mm dia inlets & CP floor grating (sealed type) etc... Complete. The cost shall include Cockroach Traps., | Nos | 6 | 600 | 3600 | 6 |  |  | 6 | 3600 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0
4 | Drilling with core cutting in RCC beams, slabs, floors etc.,for laying pipes and rendering the same in RCC 1:2:4, finishing the same to the satisfaction of the Owner or his authorized representative etc.,including nominal reinforcement where ever required, complete. The quoted rate shall also include for providing EPOXY based water proofing compound for sealing the joints around the pipes. Core cut shall be done using rebar detector after getting the approval from the structural consultant.. |  |  |  |  | 0 |  |  | 0 | 0
4.1 | RCC slabs |  |  |  |  | 0 |  |  | 0 | 0
| s | Nos | 0 |  |  | 0 |  |  | 0 | 0
| 50mm dia upto 110 mm | Nos | 0 |  |  | 0 |  |  | 0 | 0
| 125mm dia. upto 160 mm | Nos | 0 |  |  | 0 |  |  | 0 | 0
| 160mm upto 250mm | Nos | 0 |  |  | 0 |  |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0
5 | Supplying and installing MS fabricated drain grating at kitchen area where ever indicated using 50mm nominal bore,MS pipes at 105mm C/C and 8mm thick MS flats welded together and placed on MS angles of size 65mm x 65mm x 6mm, the quoted rates shall include for painting two coats of enamel paint over a coat of primer etc,.Complete. |  |  |  |  | 0 |  |  | 0 | 0
5.1 | 150mm wide Drain Channel | Nos | 0 |  |  | 0 |  |  | 0 | 0
5.2 | 300mm wide Drain Channel | Nos | 3 | 8500 | 25500 | 3 | 3 | 25500 | 0 | 0 | 0 | 0
5.3 | 450mm wide Drain Channel | Nos | 0 |  |  | 0
C | WATER SUPPLY
1 | Supply Installation, testing & commissioning of Chlorinated Polyvinyl Chloride (CPVC) pipes, SDR 11 as per IS 15778: 2007 & fittings as per ASTM D2846 / D2846M - 14 for pipe upt 50mm dia and for pipe 65mm and above use Sch 80 Pipes as per ASTM F - 441 & Sch 80 fittings as per ASTM F439 - 13, both of approved make. both of approved make having thermal stability for hot & cold water supply, including all CPVC plain & brass threaded fittings such as bends, elbows, tees, sockets, unions, plugs etc., including fixing the pipe., including necessary drilling holes, chasing walls and making the same good in as directed by the Engineer in-charge.
Cost shall be inclusive of all hangers, clamps, brackets etc. shall be of galvanized iron unless specified otherwise and then supply of the same shall also be included for rates under this head. Also rates including flusing and chemical cleaning of pipes.Charges for Labelling of pipe as per color schedule over painted surface of the pipes.
All pipes are mentioned here is ID only
Domestic water supply
1.1 | 15 mm nominal dia | Rm | 130 | 200 | 26000 | 130 | 130 | 26000 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0
2 | Supply Installation, testing & commissioning of full way lever operated forged brass ball valve working pressure not less than PN10 with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc. | [7 empty] | 0 | 0
2.1 | 15 mm nominal dia | Nos | 1 | 1100 | 1100 | 1 | 1 | 1100 | 0 | 0 | 0 | 0
2.2 | 20 mm nominal dia | Nos | 1 | 1900 | 1900 | 1 | 1 | 1900 | 0 | 0 | 0 | 0
PLUMBING - TOTAL |  |  |  |  | 190440 |  |  | 95500 |  | 94940 |  | 2185
ELECTRICAL
1 | LT SWITCHGEAR and Distribution Boards
Supply, installation, testing and commissioning of Low voltage switchgear's, free standing, Cubical type, dead front, Frame and Doors:2mm, Internal Partations:1.6mm thick, Gland Plates:3mm Thick, powder coated (Paint Shade: RAL 7032/7035), indoor type with vermin proof hinged lockable doors for each compartment, bus bar interconnections for incoming and outgoing including feeders earthing and painting and as per specifications comprising of ACB,MCCB and MCB horizontal and vertical aluminum bus bar, earth bus bar as per SLD. All meters shall be digital with LED display, whereever mentioned and shall have RS 485 Modbus RTU half duplex communication interface for provision of BMS connectivity and wired accordingly. Provide required NO/NC potential free contacts wires and terminal blocks in the cable alley for BMS operation (Optional).The swtichboards are to be tested as per IS 8623 -1977 specifications. The busbars are of high conductivity Al. alloy E91E IS 5082 specification and cable entries will be from either top or bottom depending on location. LT Switchgear shall be as per technical specification and single line diagram
1.1 | MDB
| MDB shall be as per Single line diagram and technical specifications.(Indoor -IP 42) | Nos | 1 | 87000 | 87000 | 1 | 0 | 0 | 1 | 87000 | 0 | 0
1.2 | ISOLATORS
a | 160A 4P MCCB in metallic enclosure -IP 42 | Nos | 1 | 12500 | 12500 | 1 | 0 | 0 | 1 | 12500 | 0 | 0
b | 63A 4P MCB in metallic enclosure -IP 42 | Nos | RO
c | 40A 4P MCB in metallic enclosure -IP 42 | Nos | RO
d | 25A 4P MCB in metallic enclosure -IP 42 | Nos | RO
e | 40A DP MCB in metallic enclosure -IP 42 | Nos | 2 | 3000 | 6000 | 2 | 0 | 0 | 2 | 6000 | 0 | 0
f | 25A DP MCB in metallic enclosure -IP 42 | Nos | 0
1.3 | STARTERS
a | Supply & Installation of 1.1kW Similat to Motor KW of fan slelected by OEM of unit as per approved TDS DOL/STAR DELTA starter with contactor, MPCB, overload relay, ON-OFF push buttons, Auto/Manual, ON/OFF/Trip indicating lamps, NO/NC Contacts and potential free contacts with required accessories and provied universal sockets as shown in SLD, refere Single line diagram and technical specifications. Starter panel shall be supplied with space provisons with internal wring circuits and sight glass for VFD instlattions. Installation and wiring terminations for VFD will be electrical vendor scope. Supply of VFD in HVAC vendor scope. | Nos | 1 | 4000 | 4000 | 1 | 0 | 0 | 1 | 4000 | 0 | 0
2 | MCB Distribution boards
a | 12 Way TPN MCB Distribution Board -PPI (KDB) | Nos | 1 | 17000 | 17000 | 1 | 0 | 0 | 1 | 17000 | 0 | 0
MCB DB comprising the following
Type of DB - 12 way TPN PPI MCB DB (Double Door)
100A 4P MCB - 1 No. as incomer
63A DP RCCB, 30mA, 2 Module - 3 Nos. as Sub incomer per phase
20A SP MCB, 10 kA - 29 Nos. as outgoings : MCB are of 'C' Curve
32A SP MCB, 10 kA - 1 Nos. as outgoings : MCB are of 'C' Curve
The rate shall include providing Cu. bus barsinterconnection, separate earth bus, separate neutral bus for each phases, Blank Plates and incluuding necessary connected civil works like chipping, rough plastering etc.
b | 8 Way TPN MCB Distribution Board - PPI (LPDB) | Nos | 1 | 10500 | 10500 | 1 | 0 | 0 | 1 | 10500 | 0 | 0
MCB DB comprising the following
Type of DB - 8 way TPN PPI MCB DB (Double Door)
32A 4P MCB - 1 No. as incomer
25A DP RCCB, 30mA, 2 Module - 3 Nos. as Sub incomer per phase
10A SP MCB, 10 kA - 18 Nos. as outgoings : MCB are of 'C' Curve
The rate shall include providing Cu. bus barsinterconnection, separate earth bus, separate neutral bus for each phases, Blank Plates and incluuding necessary connected civil works like chipping, rough plastering etc.
c | 12 Way SPN MCB Distribution Board | Nos | 1 | 10500 | 10500 | 1 | 0 | 0 | 1 | 10500 | 0 | 0
MCB DB comprising the following
Type of DB - 12 way SPN MCB DB (Single Door)
40A DP RCBO,30mA, 2 Module - 1 No. as incomer
6A SP MCB, 10 kA - 4 Nos. as outgoings : MCB are of 'C' Curve
10/16A SP MCB, 10 kA - 10 Nos. as outgoings : MCB are of 'C' Curve
The rate shall include providing Cu. bus barsinterconnection, separate earth bus, separate neutral bus for each phases, Blank Plates and incluuding necessary connected civil works like chipping, rough plastering etc.
3 | LOW VOLTAGE CABLES AND END TERMINATION
3.1 | Low voltage Aluminium conductor cables
Supply and laying of 1100 V grade, XLPE insulated,extruded PVC Inner Sheathed and extruded FRLS-PVC Outer sheatehed , aluminium conductor, Armoured power cable as per specifications. The cable shall be laid in indoor trenches / cable trays as required. The cable shall be clamped at regular intervals to the suppoprts in trench or to cable trays or brick wall using MS clamps and fasteners. Rate shall exclude the cost of cable trays and termination in this item.
NOTE: Cables will not be procured based on BOQ only. True measurements will be taken by Contractor before ordering, based on Drawings/ Site actual requirements ( Applicable to all respect Line items)
a | 3.5CX 50Sqmm Alu.arm Cable | Rmt | 30 | 350 | 10500 | 31.85 | 30 | 10500 | 0 | 0 | 1.85 | 647.5
b | 3.5CX 35Sqmm Alu.arm Cable | Rmt | RO |  |  |  | 0 | 0
c | 3.5CX 25Sqmm Alu.arm Cable | Rmt | RO |  |  |  | 0 | 0
d | 4CX 16Sqmm Alu.arm Cable | Rmt | RO |  |  |  | 0 | 0
e | 4CX 10Sqmm Alu.arm Cable | Rmt | 15 | 250 | 3750 | 16.1 | 15 | 3750 | 0 | 0 | 1.1 | 275
3.2 | Low Voltage Copper Conductor Cables
Supply and laying of 1100 V grade, XLPE insulated,extruded PVC Inner Sheathed and extruded FRLS-PVC Outer sheatehed copper conductor, Armoured/Un armoured power cable as per specifications. The cable shall be laid in indoor trenches / cable trays as required. The cable shall be clamped at regular intervals to the suppoprts in trench or to cable trays or brick wall using MS clamps and fasteners. Rate shall exclude the cost of cable trays and termination in this item.
Armoured Copper Cables :
a | 4Cx 16sqmm Cu Arm Cable | Rmt | 15 | 283.33 | 4249.95 | 15 | 15 | 4249.95 | 0 | 0 | 0 | 0
b | 4Cx 6sqmm Cu Arm Cable | Rmt | 15 | 450 | 6750 | 15 | 15 | 6750 | 0 | 0 | 0 | 0
c | 4Cx 4sqmm Cu Arm Cable | Rmt | 20 | 250 | 5000 | 20 | 20 | 5000 | 0 | 0 | 0 | 0
d | 3Cx 6sqmm Cu Arm. Cable | Rmt | RO |  |  |  | 0 | 0
e | 3Cx 4sqmm Cu Arm. Cable | Rmt | 20 | 180 | 3600 | 22 | 20 | 3600 | 0 | 0 | 2 | 360
3.3 | Copper Flexible Cables :
a | 3Cx6sqmm Cu Flexible Cable | Rmt | 20 | 330 | 6600 | 20 | 20 | 6600 | 0 | 0 | 0 | 0
b | 4Cx6sqmm Cu Flexible Cable | Rmt | RO |  |  |  | 0 | 0
3.4 | LOW VOLTAGE CABLE END TERMINATION:
| Supply and providing LV cable end termination for below listed cable with copper lugs, brass cable glands, tapping, crimping, etc. complete. Single Compression Glands : Cable Size Below 150 Sqmm Double Compression Glands : Cable size above 185sqmm and Single core cables 400sqmm and above | [8 empty] | 0
a | 3.5CX 50 Sqmm Alu.arm Cable | Nos | 2 | 300 | 600 | 2 | 2 | 600 | 0 | 0 | 0 | 0
b | 3.5CX 35Sqmm Alu.arm Cable | Nos | RO |  |  |  | 0 | 0
c | 3.5CX 25Sqmm Alu.arm Cable | Nos | RO |  |  |  | 0 | 0
d | 4CX 16Sqmm Alu.arm Cable | Nos | RO |  |  |  | 0 | 0
e | 4CX 10Sqmm Alu.arm Cable | Nos | 2 | 300 | 600 | 2 | 2 | 600 | 0 |  | 0 | 0
f | 3.5CX 120 Sqmm Alu.arm Cable | Nos | RO |  |  |  | 0 | 0
3.5 | Armoured Copper Cables :
a | 4Cx 16sqmm Cu Arm Cable | Nos | 2 | 300 | 600 | 2 | 2 | 600 | 0 | 0 | 0 | 0
b | 4Cx 6sqmm Cu Arm Cable | Nos | 2 | 300 | 600 | 2 | 2 | 600 | 0 | 0 | 0 | 0
c | 4Cx 4sqmm Cu Arm Cable | Nos | 2 | 300 | 600 | 2 | 2 | 600 | 0 | 0 | 0 | 0
d | 3Cx 6sqmm Cu Arm. Cable | Nos | RO |  |  |  | 0 | 0
e | 3Cx 4sqmm Cu Arm. Cable | Nos | 2 | 300 | 600 | 2 | 2 | 600 | 0 | 0 | 0 | 0
3.6 | Copper Flexible Cables :
a | 3Cx6sqmm Cu Flexible Cable | Nos | 8 | 300 | 2400 | 8 | 8 | 2400 | 0 | 0 | 0 | 0
b | 4Cx6sqmm Cu Flexible Cable | Nos | RO
4 | SWITCHES AND SOCKETS
Supply and install switches and Sockets System as required according to the specification, drawings and design. The installation rate of all the following accessories shall include for the supply of all materials such as passivated metal switchbox,junction boxes, switch plate, switches, conduit accessories, wires, tags, supports, fittings fixings and the like, to form complete elements and shall include for earthing the switchboxes The installation rate shall include for termination of all cables and wires into the devices, testing,commissioning and setting to work as required by the specifications.
NOTE: SWITCHES AND SOCKETS will not be procured based on BOQ only. True measurements will be taken by Contractor before ordering, based on Drawings/ Site actual requirements ( Applicable to all respect Line items)
Power Receptacles with Box
4.1 | Supply, installation, testing and Commissioning of 1 x 6/16A, Universal 5 pin round/flat socket controlled with 1 x 16A Switch with Indication lamp including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories.Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | 40 | 1150 | 46000 | 44 | 0 | 0 | 40 | 46000 | 4 | 4600
4.2 | Supply, installation, testing and Commissioning of 1 x 6A, universal socket controlled with 1 x 6A Switch including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories.Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | 3 | 600 | 1800 | 3 | 0 | 0 | 3 | 1800 | 0 | 0
4.3 | Supply, installation, testing and Commissioning of 2 x 6/16A,, universal socket controlled with 2 x 16A Switch including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories.Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | RO |  |  |  | 0 | 0 | 0
4.4 | Supply, installation, testing and Commissioning of 3 x 6A, universal socket controlled with 1 x 16A Switch including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories. Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | RO |  |  |  | 0 | 0 | 0
4.5 | Supply, installation, testing and Commissioning of 2 x 6A, universal socket controlled with 2 x 6A Switch including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories. Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | RO |  |  |  | 0 | 0 | 0
4.6 | Supply, installation, testing and Commissioning of 1 x 20A, universal socket controlled with 1 x 20A Switch floor mounted pop up box including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories.Rate shall include the cost for fixing of back box with plastering and rough finish (MK Type Floor Box) | Nos | RO |  |  |  | 0 | 0 | 0
0
| Power Receptacles without Box | [7 empty] | 0
4.7 | Supply, Installation testing and commissioning of 3 nos. of 6/16 A, multi Pin Universal socket controlled by 1 no. 16 A common switch along with face plate, raceway/Table mounted and other necessary accessories to complete the installation. | Nos | 2 | 2100 | 4200 | 2 | 0 | 0 | 2 | 4200 | 0 | 0
4.7 | Supply, Installation testing and commissioning of 6/16 A, multi Pin Universal socket controlled by 1 no. 16 A common switch along with face plate, raceway/Table mounted and other necessary accessories to complete the installation. | Nos | RO |  |  |  |  | 0 | 0
| Industrial Sockets : | [7 empty] | 0
4.8 | Supply, installation, testing and Commissioning of 16A, 1 phase Industrial Plug & Socket controlled with 16A DP MCB in a enclosure with all accessories. (IP65) | Nos | 6 | 7500 | 45000 | 6 | 0 | 0 | 6 | 45000 | 0 | 0
4.9 | Supply, installation, testing and Commissioning of 20A, 1 phase Industrial Plug & Socket controlled with 20A DP MCB in a enclosure with all accessories. (IP65) | Nos | 10 | 8500 | 85000 | 10 | 0 | 0 | 10 | 85000 | 0 | 0
4.10 | Supply, installation, testing and Commissioning of 25A, 1 phase Industrial Plug & Socket controlled with 25A DP MCB in enclosure with all accessories.(IP65) | Nos | RO |  |  |  | 0 | 0 | 0
4.11 | Supply, installation, testing and Commissioning of 32A, 1 phase Industrial Plug & Socket controlled with 25A DP MCB in enclosure with all accessories.(IP65) | Nos | RO |  |  |  | 0 | 0 | 0
4.12 | Supply, installation, testing and Commissioning of 32A, 3 phase Industrial Plug & Socket controlled with 32A 4P MCB in enclosure with all accessories.(IP65) | Nos | 1 | 2000 | 2000 | 1 | 0 | 0 | 1 | 2000 | 0 | 0
4.13 | Supply and installation of 3 Module Metal Boxes | Nos | RO |  |  |  | 0 | 0 | 0
4.14 | Supply and installation of 4 Module Metal Boxes | Nos | RO |  |  |  | 0 | 0 | 0
4.15 | Supply and installation of 6 Module Metal Boxes | Nos | RO |  |  |  | 0 | 0 | 0
4.16 | Supply and fixing of Blankplates | Nos | 2 | 120 | 240 | 2 | 0 | 0 | 2 | 240 | 0 | 0
4.17 | Supply and fixing of 3 Pin Plug top suitable for 16/20A | Nos | 2 | 450 | 900 | 2 | 0 | 0 | 2 | 900 | 0 | 0
5 | CIRCUIT MAINS
CIRCUIT MAIN FOR LIGHTING/POWER :
Supply and drawing of 1100V grade, multi strand FRLS insulated copper conductor wire. drawn into existing raceways/cable trays with necessary fixing accessories.
5.1 | 3 core 1.5 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduits. Rate shall exclude the cost of Raceway/Conduit in this items. | Rmtrs | 35 | 165 | 5775 | 35 | 35 | 5775 | 0 | 0 | 0 | 0
5.2 | 3 core 2.5 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduits. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | 75 | 185 | 13875 | 75 | 75 | 13875 | 0 | 0 | 0 | 0
5.3 | 3 core 4 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduit. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | 150 | 225 | 33750 | 150 | 150 | 33750 | 0 | 0 | 0 | 0
5.4 | 3 core 6 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduit. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | RO
5.5 | 2R x 2.5 sq.mm. + 1R 1.5 sq mm FRLS, MSCC wires drawn in 25mm Dia GI conduit with all accessories for general lighting.The rate shall include the cost of conduits and its accessories . | Rmtrs | RO
5.6 | 2R x 4sqmm and 1RX2.5Sqmm FRLS MSCC wires drawn in 25mm dia GI conduit with all accessories for general purpose power sockets.The rate shall include the cost of conduits and its accessories. | Rmtrs | RO
5.7 | 1 core 4 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduits. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | 1750 | 175 | 306250 | 1750 | 1750 | 306250 | 0 | 0 | 0 | 0
5.8 | 1 core 6 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduits. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | 50 | 225 | 11250 | 50 | 50 | 11250 | 0 | 0 | 0 | 0
6 | POINT WIRING
Point wiring of light, using 1100 volt grade, 3Rx1.5Sqmm multi strand FRLS insulated copper conductor flexible cable, drawn in existing raceways/Conduit. The rate shall include providing mounting boxes with tapped holes for lights switches, moulded front plates with brass screws earthing of all points using third core of the cable, For MCB Controlled Lights -DB to 1st light will be measured as circuit wiring.The point wiring shall be as per specification.Rate shall exclude the cost of MCB,Rceways in this item.(CONDUIT - GI)
6.1 | PRIMARY LIGHT POINT (Switch Control)
| Primary light point means wiring from first switch control to the first light outlet. The switch and all necessary accessories would be part of primary point.'. Not to include the incoming lighting circuit from MCB-DB to switch.' But to include the sub-circuit if it is drawn from adjacent switch box. Ceiling flexible conduit shall be included at the drop of light fixture. | Nos | 10 | 2800 | 28000 | 10 | 10 | 28000 | 0 | 0 | 0 | 0
6.2 | SECONDARY LIGHT POINT (Switch Control)
| Secondary light point means extention of light outlet from existing primary point. Same to be controlled by the existing switch of primary point. Ceiling flexible conduit shall be included at the drop of light fixture. | Nos | 25 | 2800 | 70000 | 25 | 25 | 70000 | 0 | 0 | 0 | 0
6.3 | SECONDARY LIGHT POINT (MCB Control)
| Secondary light point means extention of light outlet from existing primary point. Same to be controlled by the existing MCB of primary point. Ceiling flexible conduit shall be included at the drop of light fixture. The Wiring from DB to First Light point will be measured under circuit mains. | Nos | RO |  |  |  | 0 | 0
6.4 | Ceiling fan point controlled by 6/10 A flush type SP switch. The rate shall include MS fan hook boxes. The rate shall also include cost of 300 W electronic fan speed controller in this item only.Rate shall exclude the cost of ceiling fan in this item. | Nos | RO |  |  |  | 0 | 0
7 | CABLE TRAY/RACEWAYS
7.1 | Ladder Type
Supply and providing Ladder cable trays factory fabricated out of 2mm thick pre galvanized sheet steel, channel size 75 x 15 mm and rung size 30 x 6 mm, spaced at 250 mm interval, supporting angle frame at every 1.8 m, bottom angle fasteners, anchor grip bolts, synthetic enamelled painting, etc. The tray shall be suspended from ceiling using anchor bolt and angle iron supports or mounted from wall. The rate shall include all accessories like bends, elbows, tees, coupler plates, etc., which will be measured as linear measurement and fixing accessories.The rate shall include the cost of Supports
a | 150 mm wide 50 mm height | Rmtrs | RO |  |  |  | 0 | 0 |  |  |  | 0
b | 300 mm wide 75 mm height | Rmtrs | RO |  |  |  | 0 | 0 |  |  |  | 0
c | 450 mm wide 75 mm height | Rmtrs | RO |  |  |  | 0 | 0 |  |  |  | 0
7.2 | Perforated Type
Supply and providing MS Perforated cable trays factory fabricated out of 2mm thick pre galvanized sheet steel, channel size 50 mm supporting angle frame at every 1.8 m, bottom angle fasteners, anchor grip bolts, synthetic enamelled painting, etc. The tray shall be suspended from ceiling using anchor bolt and angle iron supports or mounted from wall. The rate shall include all accessories like bends, elbows, tees, coupler plates, etc., which will be measured as linear measurement and fixing accessories.The rate shall include the cost of Supports
a) | 50 mm wide 50 mm height | Rmtrs | RO
b) | 100 mm wide 50 mm height | Rmtrs | RO
c) | 150 mm wide 50 mm height | Rmtrs | RO
d) | 200 mm wide 50 mm height | Rmtrs | 25 | 830 | 20750 | 25 | 25 | 20750 | 0 | 0 | 0 | 0
e) | 300 mm wide 50 mm height | Rmtrs | RO
7.7 | POWDER COATED FRAME FOR MCB DB's
a | Supply and Installation of DB Frame with wire ways shall be made out of 1.6mm thick CRCA sheet steel and powder coating colour shall match the colour of MCB DB's with hinged type door. 100mm x 100mm 1.6mm thick, wire ways / Raceway with 2mm thick screwed / press to fit cover with hinged type door for making Frame for MCB DB's. Complete required including installation accessories. | Rmtrs | 15 | 900 | 13500 | 15 | 15 | 13500 | 0 | 0 | 0 | 0
8 | EARTHING
8.1 | Supply and Installation of earthing station as per IS3043 complete with 600x600x3.15mm Copper plate earthing with salt, charcoal, 2 nos. of 25x3mm Copper strip up to test link,19mm dia GI watering pipe with funnel, test link earthing chamber 450x450mm CI cover etc with required civil works complete. The CI Frame and cover shall be of heavy duty type. | Nos | RO |  |  |  | 0 | 0 |  |  |  | 0
8.2 | Supply and Installation of earthing station as per IS 3043 complete with GI pipe earthing with salt, charcoal, 2 nos. of 50x6mm GI strip up to test link ,40mm dia GI watering pipe with funnel,test link, earthing chamber of 450x450mm CI cover etc with required civil works complete.The CI Frame and cover shall be of heavy duty type. . | Nos | RO |  |  |  | 0 | 0 |  |  |  | 0
8.3 | Supply and running of below listed sizes of electrolytic copper / GI earth conductor tapes / wires and laid along with cable or clamped to brick wall, etc., as required. | [9 empty] | 0 | 0
a | 8 SWG GI wire for Earthing | Rmtrs | 40 | 240 | 9600 | 40 | 40 | 9600 | 0 | 0 | 0 | 0
b | 25x3mm GI Flat | Rmtrs | 25 | 190 | 4750 | 25 | 25 | 4750 | 0 | 0 | 0 | 0
c | 25x6mm GI Flat | Rmtrs | RO |  |  |  | 0 | 0
d | 1Cx6sqmm Cu Flexible Cable Earthing (Green) | Rmtrs | 75 | 100 | 7500 | 75 | 75 | 7500 | 0 | 0 | 0 | 0
e | 1Cx4sqmm Cu Flexible Cable Earthing (Green) | Rmtrs | 50 | 95 | 4750 | 50 | 50 | 4750 | 0 | 0 | 0 | 0
8.4 | Supply and installation of Earth pads made out of copper/GI busbars installed on 1100 V insulators including hardware and other minor civil works.associated works.
a | Busbar of 0.5 Mtr length made out of 25 x 3 mm Cu. strip with drill holes of M8 at 25mm interval mounted on insulators and acrylic cover to be provided. | Nos | RO
b | Busbar of 0.5 Mtr length made out of 25 x 6 mm Cu. strip with drill holes of M8 at 25mm interval mounted on insulators and acrylic cover to be provided. | Nos | RO
c | Busbar of 0.5 Mtr length made out of 45 x 6 mm GI strip with drill holes of M8 at 25mm interval mounted on insulators. | Nos | 1 | 2000 | 2000 | 1 | 1 | 2000 | 0 | 0 | 0 | 0
9 | PVC pipes (Electrical/IT/AV/CCTV/ACS)
9.1 | Supply and laying of 2 mm thick rigid FRLS PVC conduits in concealed conduit system using conduit accessories like junction boxes, collars, bends, elbows, binding wires, etc.
a | 32 mm dia conduit | Rmtrs | RO |  |  |  | 0 | 0 |  |  |  | 0
b | 25 mm dia conduit | Rmtrs | RO |  |  |  | 0 | 0 |  |  |  | 0
c | 20 mm dia conduit | Rmtrs | RO |  |  |  | 0 | 0 |  |  |  | 0
GI pipes (Electrical/IT/AV/CCTV/ACS)
9.2 | Supply and laying of 2 mm thick rigid MS conduits in concealed/Open conduit system using conduit accessories like junction boxes, collars, bends, elbows, binding wires, etc.
[11 empty] | 0 | 0
a | 32 mm dia conduit | Rmtrs | 10 | 250 | 2500 | 10 | 9.0013 | 2250.32 | 0.99872 | 249.68 | 0 | 0
b | 25 mm dia conduit | Rmtrs | 125 | 220 | 27500 | 125 | 96.59 | 21249.8 | 28.9375 | 6366.25 | 0 | 0
c | 20 mm dia conduit | Rmtrs | 80 | 190 | 15200 | 80 | 58.947 | 11199.93 | 21.056 | 4000.64 | 0 | 0
10 | STRUCTURAL WORKS
10.1 | Supply, cutting, welding, grouting, fastening, cleaning and painting of MS Channels, angles, plate, supporting brackets/structures , etc complete with necessary hardwares. | Kgs | RO |  |  |  | 0 | 0 |  |  |  | 0
10.2 | Supply of 6mm thick MS chequred plates duly painted. Plates to be cut size as per site requirement. | Kgs | RO |  |  |  | 0 | 0 |  |  |  | 0
11 | MISCELLANEOUS ITEMS
11.1 | Supply and fixing of danger boards of appropriate voltage grade, size and style as required by Electrical Inspectorate. | Nos | 1 | 850 | 850 | 1 |  |  | 1 | 850 | 0 | 0
11.2 | Supply of Rubber checkered mat of size 2000 x 1000 x 10mm thick, 11000 V grade. | Nos | 0
11.3 | Supply of Rubber checkered mat of size 2000 x 1000 x 3mm thick, 11000 V grade. | Nos | 1 | 2000 | 2000 | 1 |  |  | 1 | 2000 | 0 | 0
11.4 | Supply of Standard First aid box complete with all accessories. | Nos | 1 | 1850 | 1850 | 1 |  |  | 1 | 1850 | 0 | 0
11.5 | Supply of Wooden framed glass fronted shock treatment chart as per IE rules fixed to wall. | Nos | 1 | 1050 | 1050 | 1 |  |  | 1 | 1050 | 0 | 0
11.6 | SITC of Hand held Fire Extinguisher - ABC Powder - 6 Kg with floor mount accessories | Nos | 1 | 6500 | 6500 | 1 |  |  | 1 | 6500 | 0 | 0
11.7 | Temporary Works
a | For temporary Lighting in the construction area with necessary light fixtures ,cabling & Power Distribution control panel for construction works.The cost shall include necessary industrial sockets, cables, distribution boards, earthing,Light fixtures and all safety accessories as required. | LS | RO
b | Professional charges towards filing application, preparation of drawings in necessary formats for approval, follow up and arranging approval of drawings, scheme by Local electricity authority Electrical Inspectorate, obtaining clearance from electricity authority / Electrical Inspectorate. | LS | RO
c | Preparation and Submission of as built drawings of total work executed (2 Sets hard and soft copy) | Nos | 1 | 2500 | 2500 | 1 |  |  | 1 | 2500 | 0 | 0
0
12 | LIGHT FIXTURES
12.1 | Supply Installation of LED 2x2 Grid Light (Type-1) | Nos | 2 | 2800 | 5600 | 2 | 0 | 0 | 2 | 5600 | 0 | 0
12.2 | Supply Installation of LED Surface Mounted Type Light Fixtures (Type-2) | Nos | 2 | 1400 | 2800 | 2 | 0 | 0 | 2 | 2800 | 0 | 0
12.3 | Supply Installation of LED Round pendenat-1 Type Light Fixtures (Type-3) | Nos | 6 | 8500 | 51000 | 6 | 0 | 0 | 6 | 51000 | 0 | 0
12.3 | Supply Installation of LED Round pendenat-2 Type Light Fixtures (Type-4) | Nos | 11 | 2000 | 22000 | 11 | 0 | 0 | 11 | 22000 | 0 | 0
12.2 | Supply Installation of LED Recessed COB Type Light Fixtures (Type-5) | Nos | 5 | 4700 | 23500 | 5 | 0 | 0 | 5 | 23500 | 0 | 0
12.2 | Supply Installation of LED Decorative Wall Light Fixtures (Type-6) | Nos | 5 | 6700 | 33500 | 5 | 0 | 0 | 5 | 33500 | 0 | 0
12.2 | Supply Installation of LED Strip Light (Type-7) | Mtrs | 35 | 600 | 21000 | 33.92 | 0 | 0 | 33.92 | 20352 | -1.08 | -648
13 | UPS
a | Supply, Installation, Testing & Comissioning of: 5 KVA 1 Phase input/1 phase output UPS with 90 mins. Backup Battery Type: SMF with racks & enclouser (Output Power Factor Unity ) | Nos | 1 | 115000 | 115000 | 1 | 0 | 0 | 1 | 115000 | 0 | 0
ELECTRICAL - TOTAL |  |  |  |  | 1245189.95 |  |  | 612900 |  | 631758.57 |  | 5234.5
IT
1 | IT/NETWORKING :
1.1 | 4-pair, Cat 6 UTP FRLS Cable | Mtrs | 175 | 80 | 14000 | 182 | 87.5 | 7000 | 87.5 | 7000 | 7 | 560
1.2 | Cat 6 UTP Information Outlet for Workstation end | Nos | 8 | 300 | 2400 | 8 | 4 | 1200 | 4 | 1200 | 0 | 0
1.3 | Cat 6 RJ45-RJ45 UTP Patch Cords, color matched, Yellow - Workstation end, 7 ft | Nos | 8 | 550 | 4400 | 8 | 4 | 2200 | 4 | 2200 | 0 | 0
1.5 | Dual Face Plates | Nos | 0 | 700 |  |  | 0 |  |  |  | 0 | 0
1.4 | Single Face Plates | Nos | 8 | 500 | 4000 | 8 | 4 | 2000 | 4 | 2000 | 0 | 0
1.6 | Supply and fixing of Metal box suitable information outlet , flush/surface type in position .The rate shall exclude the cost of faceplate and Information Outlet. | Nos | 8 | 1200 | 9600 | 8 | 4 | 4800 | 4 | 4800 | 0 | 0
1.7 | Supply, installation, testing and Commissioning of RJ11 Telephone Point. The Telephone Socket shall be with face plate, GI BOX with accessories. | Nos | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.8 | Cat 6 24 Port Angled Discrete Jack panel - fully loaded (1U).The rate shall include the cost of Patch Panel, Information Outlets with all the required supporting accessories. | Nos | 1 | 3000 | 3000 | 1 | 0.5 | 1500 | 0.5 | 1500 | 0 | 0
9 | 06 U wall mount rack with required mounting accessories, Rate shall include required accessories, tools etc., complete as required. | No | 1 | 7000 | 7000 | 1 | 0.5 | 3500 | 0.5 | 3500 | 0 | 0
IT - TOTAL |  |  |  |  | 44400 |  |  | 22200 |  | 22200 |  | 560
CCTV
1 | Supply, installation, testing and Commissioning of UL approved, IP based Dome Indoor type 5MP,HD Dome camera | Nos | 5 | 3500 | 17500 | 5 | 2.5 | 8750 | 2.5 | 8750 | 0 | 0
2 | Supply, installation, testing and Commissioning of UL approved, Outdoor type 2MP Camera | Nos | RO |  |  | 0 | 0 | 0 | 0 | 0
3 | Supply, installation, testing and Commissioning of 8 Channel NVR Ultra 4 K resolution and recording software with Storage capacity of 30Days .with all required accessories | No | 1 | 16000 | 16000 | 1 | 0.5 | 8000 | 0.5 | 8000 | 0 | 0
4 | CAT 6 PoE Cable, as per the survey done, Rate shall include required accessories, tools etc., complete as required. | Mtr | 100 | 80 | 8000 | 116 | 50 | 4000 | 50 | 4000 | 16 | 1280
5 | Cat 6 Sngle Information Outlets including faceplates and backbox accessories. | Nos | 5 | 300 | 1500 | 5 | 2.5 | 750 | 2.5 | 750 | 0 | 0
6 | Cat 6 12 Port Angled Discrete Jack panel - fully loaded (1U).The rate shall include the cost of Patch Panel, Information Outlets with all the required supporting accessories.(CCTV) | Nos | RO |  |  | 0 | 0 | 0 | 0 | 0
7 | Cat 6, PoE 7ft Gigabit Snagless Molded Patch Cable (RJ-45 Male) with factory crimping, these patch cords will suffice for connecting between Data Outlet & CCTV | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Cat 6, PoE 4ft Gigabit Snagless Molded Patch Cable (RJ-45 Male) with factory crimping, these patch cords will suffice for connecting between Data Outlet & CCTV (100%) | No | 5 | 3500 | 17500 | 5 | 2.5 | 8750 | 2.5 | 8750 | 0 | 0
9 | 05 U wall mount rack with required mounting accessories, Rate shall include required accessories, tools etc., complete as required. | No | RO |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0
10 | PVC pipes |  |  |  |  | 0 |  |  | 0 | 0
| Supply and laying of 2 mm thick rigid FRLS PVC conduits in concealed conduit system using conduit accessories like junction boxes, collars, bends, elbows, binding wires, etc. |  |  |  |  | 0 |  |  | 0 | 0
a | 32 mm dia conduit | Mtrs | RO |  |  | 0 | 0 | 0 | 0 | 0
b | 25 mm dia conduit | Mtrs | RO |  |  | 0 | 0 | 0 | 0 | 0
c | 19 mm dia conduit | Mtrs | RO |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0
11 | GI pipes |  |  |  |  | 0 |  |  | 0 | 0
| Supply and laying of 2 mm thick rigid GI conduits in concealed/Open conduit system using conduit accessories like junction boxes, collars, bends, elbows, binding wires, etc. |  |  |  |  | 0 |  |  | 0 | 0
a | 32 mm dia conduit | Mtrs | 0 |  |  |  | 0 | 0
b | 25 mm dia conduit | Mtrs | 30 |  |  | 36 | 0 | 0 | 36 | 0 | 6 | 0
c | 19 mm dia conduit | Mtrs | 35 |  |  | 40 | 0 | 0 | 40 | 0 | 5 | 0
[6 empty] | 0 |  | 0 | 0 | 0
12 | 1.5 meter length, Powder coated MS 25 mm dia Conduit supports for CCTV cameras with required supporting /mounting accessories complete. | No | RO |  |  | 0 | 0 | 0 | 0 | 0
13 | Supervision, Programming, Testing & Commissioning, Documentation, Training. | LS | 1 |  |  | 1 | 0 | 0 | 1 | 0
CCTV - TOTAL |  |  |  |  | 60500 |  |  | 30250 |  | 30250 |  | 1280
HVAC
1 | CHILLED WATER TYPE DOUBLE SKIN AIR HANDLING UNITS - CEILING SUSPENDED TYPE
Supply,Installation, Testing & Commissioning of Double skin type Ceiling suspended units complete with double skin (43±3 mm) insulated with CFC free polyurethane foam (PUF) panels of 40 +/- 2 Kg/cum density. The outer and inner panel thickness shall be 0.8 mm and 0.63 mm GI respectively. Outer skin shall be precoated/Powder Coated G.I. sheet and internal skin shall be Plain G.I. sheet suitable for chilled water application. The unit shall be provided with DIDW Fan, Motor, minimum 4 row cooling coil and drain pan with 15mm thick nitrile rubber insulation, inlet filter section with with 50mm thick panel type pre-filter of MERV-8 as part of CSU, drive set & guard, spring isolator to avoid transmission of vibration,etc. The noise of the unit shall not exceed more than 55-60 dBA at 1m distance from the unit and at maximum operating speed.The height of the unit shall not exceed 650mm. Additional FRP drain tray shall be considered for this units. Cooling Coil should be certified by AHRI 410
The unit shall be provided with belt driven backward curved Multi fans for achive the unit hight as not Exceed 650mm, IE3 Motor, drive package, vibration isolating rubber bush to fans and motor to avoid transmission of vibration. All CSU motor pulleys shall be of adjustable type only. Cost shall be inclusive of non-cloth type canvas connection made of self extinguishing, moisture resistant flexible fabric to be provided between CSU outlet flange and the supply duct / plenum.Spring isolators shall be used in the installation of the Ceiling suspended Units to ensure there is no transmission of vibration from the equipment to the building structure.
a | Supply. Installation,Testing & Commissioning of Double Skin CSU- Capacity-5 TR capacity, 1750 Dcfm with 0.325 sqm cooling cooling coil face area, 30 mmwg fan external static, 4/6 row cooling coil, 0.75/1.1 Kw fan motor, filter section with Pre Filter (EU-3)-MERV-8 supplied by the builder -Serving area: AJ Kitchen - Fine Dine | Set | 1 | 65000 | 65000 | 1 | 0 | 0 | 1 | 65000 | 0 | 0
b | Supply, Installation, Testing & commissioning of Limit switch wiring ,lighting & motor interlock to be provided with 3 core 2.5sqmm cable in 19mm dia GI conduit | Rmt | 20 | 2200 | 44000 | 24.5 | 0 | 0 | 20 | 44000 | 4.5 | 9900
2 | CHILLED WATER PIPING WITH INSULATION
| Supply, Installation, Testing & commissioning of MS 'C' Class pipes insulated with Closed cell elastomeric insulation of specified thickness & Insulation to be covered with Aluminium cladding 26G , 0.5mm thick as per technical specification. All Bolts / Nuts used in the chilled water piping should be of GI & not MS. The cost shall be inclusive of pipe suppoorts with MS Channels. The piping flange connection bolts, washers and nuts should be hot dipped galvanised.The pipes should be supported with MS Channels, angle frame with neoprene rubber / PUF saddles. Fitting accessories for installation of pressure gauges, thermometers, BMS sensors, drain ports to be provided by the HVAC lowside contractor. Flourscent Plastic Sticker/ paint shall be applied to indicate Water flow directions. Only End flanges to be used for capping of pipes. "Table E" of BS code for flange thickness to be adhered. The Piping material & network should be selected to operate at PN 16 Rating | [5 empty] | 0
Pipe dia below 150 mm shall be C Class confirming to IS:1239 (part 1) 2004,Pipe size between 200 mm to 350 mm dia shall be 6.35 mm & pipe dia above 350 mm shall be 8.0 mm confirming to IS:3589 Gr330
Opening and closing for all the chilled pipe entries in civil / gypsum / any type of partition shall be under scope of HVAC vendor and inclusive of cost. Routing diagram can be checked in drawing prior for quoting.
a | 40 mm dia | Rmt | R.only
b | 32 mm dia | Rmt | 20 | 2700 | 54000 | 21.4 | 0 | 0 | 20 | 54000 | 1.4 | 3780
3 | BUTTERFLY VALVE WITH INSULATION
Supply, Installation, Testing & commissioning of Wafer type Butterfly valve which shall be of Slim seal wafer type with long stem of PN 16 rating, companion flanges shall also be of PN20 rating. Butterfly valves installed for the chilled water pipelines shall be insulated with nitrile rubber insulation and the insulation thickness shall be similar to that of the pipe dimensions. (valve sizes above 200mm shall be wheel operated type instead of handles). All bolts, washers and nuts shall be hot dipped galvanized only.The MOC of body shall be cast iron & disk shall be epoxy coated ductile iron.
a | 40 mm dia | Nos | R.only
b | 32 mm dia | Nos | 5 | 10000 | 50000 | 5 | 0 | 0 | 5 | 50000 | 0 | 0
4 | PRESSURE INDEPENDENT TYPE DYNAMIC BALANCING CUM FLOW CONTROL VALVE.
Valve selection to be submitted in the technical submittal for approval before procurement.
Supply, Installation, Testing & commissioning of Pressure Independent dynamic balancing cum equal percentage type modulating flow control valve - PN16 rating fitted with high torque actuator with Non spring return type to ensure the valve closes automatically in the event of power disconnect to actuator. Actuator enclosure shall be rated for IP 54 protection. Step down transformer if required shall be part of valve supply, matching flanges, hot dipped galvanized bolts and nuts. Valve body to be insulated with closed cell elastomeric insulation. Supply , Installtion, testing & commissioning of thermostat along with control/ power cabling to be part of scope.The MOC of body shall be cast iron & membrane shall be EPDM, SS spring.
Actuator should be provided with position feed back switch and also actuator should have BMS interfacing card and shall be suitable for accepting signals from temperature sensors supplied by BMS vendor. Actuator should also have facility to set the required flow rate as per site requirements through dip switch adjustments. Valve body to be rated for PN 16. The valve design flow rate should be factory calibrated with +/- 5% flow accuracy. THe scope shall include the cost supply of thermostat/ return air temperature and required control cabling
Valve shall have necessary measuring ports, drain port, flanges etc., The balancing to be done through microprocessor based hand held terminal / POT and the same results shall be furnished in the water balancing report as part of commissioning report and handing over manual.
a | 40 mm dia | Nos | R.only
b | 32 mm dia | Nos | 1 | 13500 | 13500 | 1 | 0 | 0 | 1 | 13500 | 0 | 0
5 | 2 WAY FLOW CONTROL VALVE.
Valve selection to be submitted in the technical submittal for approval before procurement.
Supply, Installation, Testing & commissioning of 2 Way- modulating flow control valve - PN16 rating fitted with high torque actuator with Non spring return type to ensure the valve closes automatically in the event of power disconnect to actuator. Actuator enclosure shall be rated for IP 54 protection. Step down transformer if required shall be part of valve supply, matching flanges, hot dipped galvanized bolts and nuts. Valve body to be insulated with closed cell elastomeric insulation. Supply , Installtion, testing & commissioning of thermostat along with control/ power cabling to be part of scope.The MOC of body shall be cast iron & membrane shall be EPDM, SS spring.
Actuator should be provided with position feed back switch and also actuator should have BMS interfacing card and shall be suitable for accepting signals from temperature sensors supplied by BMS vendor. Actuator should also have facility to set the required flow rate as per site requirements through dip switch adjustments. Valve body to be rated for PN 16. The valve design flow rate should be factory calibrated with +/- 5% flow accuracy. THe scope shall include the cost supply of thermostat/ return air temperature and required control cabling
Valve shall have necessary measuring ports, drain port, flanges etc., The balancing to be done through microprocessor based hand held terminal / POT and the same results shall be furnished in the water balancing report as part of commissioning report and handing over manual.
a | 40 mm dia | Nos | R.only
b | 32 mm dia | Nos | R.only
6 | TEMPERATURE SENSORS
| Supply, Installation, Testing & commissioning of Duct type/ space type temperature sensor for measuring the Return air temperature at the Chilled water type CSU Units (Range 45-150 deg. F).A Temperature sensor shall be provided in the return air path of CSU to control the 2 way modulating valve. The scope shall include the cost of Control Cabling with conduit between temperature sensor and actuator of 2 Way modulating flow control valve | Nos | 1 | 4500 | 4500 | 1 | 0 | 0 | 1 | 4500 | 0 | 0
7 | Y'-STRAINER WITH INSULATION
Supply, Installation, Testing & commissioning of Y-strainer -PN 16 rating body construction shall be with Mild steel and strainer shall be of SS screen with permanent magnet and drain port. The MOC of body shall be cast iron & SS-304 filter with 3 mm perforation with flanged connection, gaskets, permanent magnet. Note, the insulation quantity will be measured in running meters and the valve in numbers.
a | 40 mm dia | Nos | R.only
b | 32 mm dia | Nos | 1 | 4500 | 4500 | 1 | 0 | 0 | 1 | 4500 | 0 | 0
8 | BALANCING VALVE WITH INSULATION
SITC of BALANCING VALVE (Manual Type) - PN16 Rating. Balancing valves installed for the chilled water pipelines shall be insulated with 25mm thick nitrile rubber insulation The valve should be with factory calibrated with +/- 5% flow accuracy. Provided with necessary measuring port, drain port, flanges hot dipped galvanized bolts, washers and nuts etc., The balancing to be done by portable hand held device and same result should be furnished in the handing over manual.The MOC of body shall be cast iron & the seat shall be EPDM, brass / SS cone.
a | 40 mm dia | Nos | R.only
b | 32 mm dia | Nos | R.only
9 | TEMPERATURE GUAGES
a | Supply, Installation, Testing & commissioning of Thermometer which shall be of Dial type (100mm) Range 0⁰ to 50⁰C, with stainless steel body - IP 55 protection, with necessary theromowells. | Nos | 2 | 6500 | 13000 | 2 | 0 | 0 | 2 | 13000 | 0 | 0
10 | PRESSURE GAUGE (GLYCERINE FILLED)
a | Supply, Installation, Testing & commissioning of Pressure Gauge which shall be of Bourdon tube Dial type (100mm) Range 0 to 10 kg/cm², with stainless steel body - IP55 protection with necessary pipe fitting and needle valve etc., | Nos | 2 | 8200 | 16400 | 2 | 0 | 0 | 2 | 16400 | 0 | 0
11 | INSULATED RIGID PVC PIPING FOR CONDENSATE DRAIN
Supply, Installation, Testing and Commissioning of Rigid PVC piping with pressure rating of 6 Kg /CM2 duly insulated with 9 mm thick factory laminated aluminium foil faced closed cell elastomeric nitrile rubber insulation with class 'O' fire retardant properties in tubing form & all fittings, elbows, tees reducers, supports and clamps up to 50 mm dia. including drilling, wall chipping etc. and conceal the wall opening. Pipes shall be of following sizes :
a | 65mm. Dia. | Rmt | 30 | 600 | 18000 | 31.5 | 0 | 0 | 30 | 18000 | 1.5 | 900
b | 50mm. Dia. | Rmt | 15 | 500 | 7500 | 14.5 | 0 | 0 | 15 | 7500 | -0.5 | -250
c | 40mm. Dia. | Rmt | 20 | 400 | 8000 | 20 | 0 | 0 | 20 | 8000 | 0 | 0
d | 32mm. Dia. | Rmt | R.only
d | 25mm. Dia. | Rmt | R.only
12 | AUTOMATIC AIR VENTS
a | Supply, Installation, Testing & commissioning of Automatic air vents to be provided at all high location of piping. The air vent to be provided with necessary ball valve. | Nos | R.only |  |  |  | 0
13 | DRAIN VALVES
| Supply, Installation, Testing & commissioning of Ball/Drain valves with handles and extended stem , threaded joints shall be of PN16 class and insulated with nitrile rubber.The MOC of body shall be forged brass, SS ball, SS 410 stem. The end connections shall be threaded. | [5 empty] | 0
a | 25 mm dia | Nos | 2 | 2200 | 4400 | 2 | 0 | 0 | 2 | 4400 | 0 | 0
0
14 | GSS DUCT WORKS
FACTORY FABRICATED DUCTING - TDF /TDC FLANGES - RECTANGULAR DUCTWORKS
Supply, Installation, Testing & Commissioning of factory fabricated GSS Ducting with TDF /TDC flange with GI bolt & nuts (the cleat into the flange Used for C and G together with Bolt) and necessary supporting arrangement using GI full threaded rods and slotted rail- Unistrut channel supports of size 41mm x 41mm for rectangular ducts to be used
Ducting shall include guide vanes etc., Ducting shall be designed for 500pa ESP as per the specifications, GSS Ducting:- Galvanized steel sheet shall be of Class VIII – light coating of zinc, nominal 120 gm /sqm as per IS-277.All ducts 900 mm to 1100mm shall have Stiffener bracket made of GI 1.25mm thick sheet and 1101mm above shall have Stiffener bracket made of GI 1.6mm thick sheet with special profile for strength and rigidity fixed throughout the duct perimeter Intermediate between flanges with Fastener screws 2 nos for every interval of 150mm.
Spacing between duct supports should not exceed 2m i.e GI rods with GI "C" channels. In case of duct sizes above 1800mm, MS angles duly painted with black enamel paint should be used along with neoprene pad in between the duct & MS angle. All duct support to be provided with check nuts (lock nuts).
While selecting the duct supports vendor shall ensure vibration free installation. Quoted price shall be inclusive of light testing with complete arragement & accessories for leakages. Quoted price shall be inclusive of necessary scaffolding charges towards installation of supply/exhaust air ducts outside or within building wherever required. Quoted price should also include necessary charges towards duct supports including MS angle/channel arrangement as required for ducts being installed outside or within building wherever required.
All duct construction and installation shall be in accordance with SMACNA standards. In addition ducts shall be factory fabricated utilizing the following machines to provide the requisite quality of ducts.
a | 24 G-GSS-0.63MM ( 1MM TO 250MM) - C & SS | Sqm | R.only
b | 24 G-GSS-0.63MM ( 251MM TO 1000MM) - TDF Flanges | Sqm | 105 | 1800 | 189000 | 108.4 | 0 | 0 | 105 | 189000 | 3.4 | 6120
c | 22 G-GSS-0.80MM ( 1001MM TO 1200MM) - TDF Flanges, Guide Vanes & Stiffeners Rods | Sqm | 2 | 2000 | 4000 | 2 | 0 | 0 | 2 | 4000 | 0 | 0
d | 20 G-GSS-1.00MM ( 1201MM TO 1300MM) - TDF Flanges, Guide Vanes & Stiffeners Rods | Sqm | R.only
e | 18 G-GSS-1.25MM ( 1301MM TO Above) - TDF Flanges, Guide Vanes & Stiffeners Rods | Sqm | R.only
15 | DUCT INSULATION MATERIALS
15.1 | THERMAL INSULATION FOR DUCTWORKS
Supply, Installation, Testing & Commissioning of Thermal insulation closed cell elastromeric nitrile rubber insulation manafactured as per ASTM E 84 test with density between 40-60 kg / m³(External and internal) for spiral duct, Material shall be FM GLOBAL approved, food grade material with antimicrobial properties, Class 'O'. Insulation material should meet NFPA 90A supplementary materials for air distribution system which should not absorbs less 0.2% water by volume (ASTM c 209), should not support microbial growth (ASTM C1071, G21, G22) and should emit objectionable odors (ASTM C 665) and should have thermal conductivity of 0.27 ( R - 2.78 in 3.4" thickness) and water vapor permeance of 0.10. Scope shall include the cost for aluminium foil which to be laid over the thermal insulation. Aluminium foil shall provide protection against scratches.
Insulation material shall be bonded with the ducts using metal screw and washers to facilitate grip to the GI sheet.Insulation materials brought on site should be installed following the manufacturer recommended methodology and using the appropriately suitable manufacturer recommended cutting, measuring, pasting tools & tackles. It is advised to use the manufacturer’s tool box for installation of insulation materials on site.
a | 9mm thick | Sqm | R.only |  |  |  | 0
b | 13mm thick | Sqm | 65 | 105 | 6825 | 62.4 | 0 | 0 | 62.4 | 6552 | -2.6 | -273
15.2 | ACOUSTIC INSULATION FOR DUCTWORKS
SITC of internal acoustic lining within air ducts plenum with open cell 10mm thick Elastromeric nitrile rubber insulation manafactured as per ASTM E 84 test with density140- 180 kg / m³, Material shall be FM rated as per the approved shop drawings / specifications. Insulation material should meet NFPA 90A supplementary materials for air distribution system which should not absorbs less 0.2% water by volume (ASTM c 209), should not support microbial growth (ASTM C1071, G21, G22) and should emit objectionable odors (ASTM C 665) and should have thermal conductivity of 0.27 ( R - 2.78 in 3.4" thickness) and water vapor permeance of 0.10. - Class "1" Material.
Insulation sheets should have self-adhesive backing for faster installation and better quality. The adhesive used in self-adhesive backing should be Fire Retardant, LEED compliant and zero VOC.
Insulation material shall be bonded with the ducts using metal screw and washers to facilitate grip to the GI sheet.Insulation materials brought on site should be installed following the manufacturer recommended methodology and using the appropriately suitable manufacturer recommended cutting, measuring, pasting tools & tackles. It is advised to use the manufacturer’s tool box for installation of insulation materials on site.
a | 10mm thick-acoustic insulation for main duct outlets as per HVAC drawings | Sqm | 7 | 3450 | 24150 | 6.85 | 0 | 0 | 6.85 | 23632.5 | -0.15 | -517.5
b | 20mm thick-acoustic insulation for main duct outlets as per HVAC drawings | Sqm | R.only |  |  |  | 0
16 | AIR DISTRIBUTION DEVICES
16.1 | MANUAL TYPE VOLUME CONTROL DAMPERS
a | Supply, Installation, Testing & Commissioning of Volume Control Dampers made out of 100 x 40 x 1.55 mm thick galavanised steel frame and blades of 1.55 mm galavanised sheet steel. | Sqm | 0.7 | 4500 | 3150 | 0.7 | 0 | 0 | 0.7 | 3150 | 0 | 0
16.2 | ALLUMINIUM COLLAR DAMPERS
a | Supply, Installation, Testing & Commissioning of Collar Dampers or neck damper of opposed blade type made out of Aluminium alloy extrusion with anodised matt black finish (AL.blade thickness 1.0mm, Border thickness-1.3 MM). Qty is for Supply air grilles | Sqm | 1.7 | 4500 | 7650 | 1.7 | 0 | 0 | 1.7 | 7650 | 0 | 0
16.3 | CONTINUOUS LINEAR GRILLE
Supply, Installation , Testing & Commissioning of Extruded Al. powder coated continuous, discrete grilles for supply & return air distribution of 100 to 600 mm wide with 0 / 15 / 30 / 45 deg (AL.frame thickness 1.2MM, Louver thickness-3 MM). Deflection as specified In the approved shop drawings. Grilles complete with integral flanges on both sides & ends as required complete with corner pieces.( colour for the grill to be conifremed by Arch/ PMC team before placing the order)
a | 150mm wide | Nos | 21 | 1100 | 23100 | 21 | 0 | 0 | 21 | 23100 | 0 | 0
16.4 | POWDER COATED ALUMINIUM GRILLES- FOR EXHAUST AIR & FRESH AIR APPLICATION
Supply, Installation , Testing & Commissioning of Extruded Al. powder coated grilles for exhuast air & Fresh air application with 0 degree deflection. AL.frame thickness 1.2MM, Louver thickness-1MM/ 3 MM ( colour for the grill to be conifimed by Arch/ PMC team before placing the order). The sizes of the grilles shall be as mentioned below
a | 600mm x 600mm | Nos | 3 | 2900 | 8700 | 3 | 0 | 0 | 3 | 8700 | 0 | 0
b | 200mm x 200 mm | Nos | 2 | 2500 | 5000 | 2 | 0 | 0 | 2 | 5000 | 0 | 0
16.5 | 4 WAY SUPPLY AIR DIFFUSERS- SQUARE TYPE
Supply, Installation , Testing & Commissioning of Powder coated, extruded aluminium, removable center core type, supply air diffusers with Collar Dampers or neck damper of the following neck sizes.
(All are of 595 x 595 MM Outer to Outer Size)
b | 300 x 300 MM (Neck Size) | Nos | 1 | 2000 | 2000 | 1 | 0 | 0 | 1 | 2000 | 0 | 0
17 | ELECTROSTATIC DRY SCRUBBER FOR KITCHEN EXHAUST OF 3600 CFM.
Supply, installation, testing & Commissioning of Electro- Static DRY scrubber for the above exhaust rating of 3600 CFM. The vendor shall include the Pressure drop to be 20mm Wg, works with necessary valve arrangement. The scope of supply should include complete system for Electrostatic Dry scrubber operation. It shall also include the carbon filters for residual carbon content removal.The Electrostatic Air Cleaners shall be supplied as a one-piece factory joined assembly of individual section(s) selected to treat oil mist, smoke, fume, grease & dust/ powder problems.
Housing shall be constructed with minimum 1.6mm thick steel sheet with reinforced structure & powder coated to protect against rust and corrosion. It shall have a hinged door for cell access, located one side of the unit. The door shall be gasketed to prevent air leakage. There shall be a safety interlock switch to cut off primary supply when the access door is opened.The external finish shall be a durable industrial grade semi-gloss epoxy-polyester coating suitable for outdoor installations.
Ionizing-Collecting cell(s) shall be of one-piece construction 13.38” (340mm) deep in direction of airflow. The dimension of the collection cell shall be 18.89” (480mm) H x 19.76” (502mm)W Max. All support framing, end plates and ionizer ground electrodes shall be 0.080 inch (2mm) thick aluminum. Both repelling and collector plates shall be 0.032 inch (0.8mm) thick aluminum alloy material rigidly retained in place with tubular spacers and tie rods. Each plate shall be corrugated, perpendicular to airflow direction. Spacing between plates shall be no less than 0.318 inch (8mm). Each cell shall weigh at least 17 kg with at least 8 stainless steel spiked blade ionizers. Tungsten wire ionizers will not be accepted
Ionizing spiked blade shall be made of Stainless steel 304 material, rigidly supported both vertically and laterally. Spiked ionizer to ground electrode spacing shall be 1.0" (25mm). High voltage support insulators shall be of Teflon material for dielectric strength.
Equipment should be selected on the basis of required Air handling capacity so as to achieve 90-95% particulate matter removal efficiency according to DOP Test or EN779 European standard (Equivalent to ASHRAE 52.1). Vendor should submit the Test report from the Lab having Test facility according to ASHRAE 52.2 or EN779. In the absence of Test report Vendor should demonstrate the efficiency claim at their manufacturing facility at their expenses.
Power supplies shall be 100% solid state, operate on 230 VAC, 50 Hz, 1 Phase input and provide a dual high voltage output of 12-13 KVDC for the ionizer and 6.0-6.5 KVDC for the collector in normal operation conditions. Current output at the high tension shall be 12mA. A maximum power output for the solid state power supply shall be 120 watts to maintain the specified collection efficiency. Integrally mounted Electrical interlocks shall be provided to prevent access to the high voltage components without first interrupting the primary input power. The power supply shall operate over a temperature range of -32 degrees F to 140 degrees F, be overloaded self-protecting and accommodate an LED lights indicating the performance status of the ionizing/collecting cell. High voltage output components in the power supply shall be sealed with epoxy for moisture resistance.
The power pack shall incorporate a short circuit arc protection with automatic power restoration system to prevent overload.
There shall be 2 LED lights (Green & Red) installed on the access door of the unit to indicate the status of the air cleaning system
BMS (Building Management System) interface: The power supply (pack) shall have a 2 wire dry contacts (NO/NC) for remote link to Building Management System. This is for performance indication of the air cleaning system
| Supply , Installation , Testing & Commissioning of Electro-static Dry Scrubber unit complete with all sections as listed above & detailed in tender drawings | LS | 1 | 75000 | 75000 | 1 | 0.5 | 37500 | 0.5 | 37500 | 0 | 0
HVAC - TOTAL |  |  |  |  | 651375 |  |  | 37500 |  | 613084.5 |  | 19659.5
FIRE ALARM SYSTEM
1 | FIRE Alarm System Works
1.1 | Supply installation testing and commissioning of addressable type smoke detectors with LED indication lamp, MS Back box, detector base braket, along with complete fixing accessories.(Above false ceiling) | Nos | RO
1.2 | Supply installation testing and commissioning of addressable type smoke detectors with LED indication lamp, MS Back box, detector base braket, along with complete fixing accessories.(Below false ceiling) | Nos | 4 | 3800 | 15200 | 4 | 0 | 0 | 4 | 15200 | 0 | 0
1.2a | Supply installation testing and commissioning of addressable type Multi Sensor Heat detectors with LED indication lamp, MS Back box, detector base braket, along with complete fixing accessories. | Nos | 3 | 3000 | 9000 | 3 | 0 | 0 | 3 | 9000 | 0 | 0
1.3 | Supply installation testing and commissioning of Response indicators with complete fixing accessories for the detectors placed above false ceiling and below false flooring | Nos | RO |  |  |  |  | 0 | 0 | 0
1.4 | Supply installation testing and commissioning of addressable Hooter cum STROBE along with its control modules complete with all fixing materials. | Nos | 1 | 4500 | 4500 | 1 | 0 | 0 | 1 | 4500 | 0 | 0
1.5 | Supply and installation of analogue addressable type Manual call points with Glass and hammer and monitor module with complete fixing accessories also with self illuminated signage. | Nos | 1 | 4100 | 4100 | 1 | 0 | 0 | 1 | 4100 | 0 | 0
1.6 | Supply and installation of Short circuit Fault Isolators @ 20 detectors with complete fixing accessories | Nos | RO |  |  |  |  | 0
1.7 | Supply and installation of Monitor Module with complete fixing accessories | Nos | 1 | 6000 | 6000 | 1 | 0 | 0 | 1 | 6000 | 0 | 0
1.8 | Supply and installation of Control Relay Module with complete fixing accessories | Nos | 1 | 4800 | 4800 | 1 | 0 | 0 | 1 | 4800 | 0 | 0
1.9 | Supply and laying of PVC insulated,2C x 1.5sq.mm shielded armored FRLS copper cable (RED COLUR) including cable glands and all fixing accessories where ever required complete with end terminations at both sides. The colour of the cable shall be RED only.( Shall be on actuals ). | Rmtrs | 50 | 70 | 3500 | 48.3 | 0 | 0 | 48.3 | 3381 | -1.7 | -119
1.10 | Supply, installation, testing and commissioning of Addressable fire alarm Panel which consists of display board which will have 160 Character Display with Touch key pad, Mother board which will have ARM CORTEX M3 32 Bit Processor, Inbuilt RS-485 Networking Circuit for peer to peer networking, Inbuilt USB 2.0 Port for upload and download the Configuration tools, Two inbuilt programmable inputs, Two inbuilt NAC's, and Three Programmable Relays, and 4 Loop Card circuits. power Supply, Installation and Commissioning Board which will have SMPS fully protected board, which its operates on 120 to 220V AC ± 10% with 50/60 Hz, battery backup 24V DC with built-in charger. the panel have IP-50 rating Optional: for BMS integration thru MODBUS converter, Graphical Software, Software for TCP/IP Module, provision for GSM based Auto dialler, provision for printer thru compatible module, fire alarm panel with battery backup for 6 hours operation, with battery charger, alarm bell, test buttons etc. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a | 2 loop panel | Nos | 1 | 47500 | 47500 | 1 | 0 | 0 | 1 | 47500 | 0 | 0
b | 4 loop panel | Nos | RO |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.11 | SITC of Hand held Fire Extinguisher - ABC Powder - 6 Kg with floor mount accessories | Nos | 2 | 7000 | 14000 | 2 | 0 | 0 | 2 | 14000 | 0 | 0
1.12 | SITC of Hand held Fire Extinguisher - CO2 - 4.5 Kg with floor mount accessories | Nos | 2 | 12000 | 24000 | 2 | 0 | 0 | 2 | 24000 | 0 | 0
1.13 | Supply installation testing and commissioning of Emergency Exit -LED Battery Backup(180Min) | Nos | 0 | 0 | 0 | 0 | 0 | 0
1.14 | Supply installation testing and commissioning of Fire Exit - LED Battery Backup (180Min) | Nos | 3 | 3000 | 9000 | 3 | 0 | 0 | 3 | 9000 | 0 | 0
1.15 | Supply installation testing and commissioning of Exit - LED Battery Backup (180Min) | Nos | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0
2 | PA System Works | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Supply and installation testing and commissioning of 6 Watt 180mm dia Surface mounted white colour speakers along with all fixing accessories. | Nos | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Supply and installation testing and commissioning of 6 Watt Recesse Mounted Ceiling speakers along with all fixing accessories . | Nos | 4 | 6400 | 25600 | 4 | 0 | 0 | 4 | 25600 | 0 | 0
2.3 | Supply and laying of shielded twin twisted pair 1.0 sqmm cable in existing conduit ( Shall be on actuals ). | Rmtrs | 50 | 90 | 4500 | 48.9 | 0 | 0 | 48.9 | 4401 | -1.1 | -99
2.4 | Supply and fixing of 20mm dia heavy guage GI conduit concealed in wall/ above false ceiling for taking copper wires including all accessories such as Conduit junction boxes, bends etc as required ( Shall be on actuals ). | Rmtrs | 40 | 210 | 8400 | 39.2 | 0 | 0 | 39.2 | 8232 | -0.8 | -168
2.5 | Mixer Amplfier -240W with Pre recorded Message ,Music Ssytem etc complete in a PA rack (The rate to include the Cost of rack and other required acessories ) | Nos | RO |  |  |  |  | 0 | 0 | 0
2.6 | Mixer Amplfier -120W with Pre recorded Message ,Music Ssytem etc complete in a PA rack (The rate to include the Cost of rack and other required acessories ) | Nos | 1 | 75000 | 75000 | 1 | 0 | 0 | 1 | 75000 | 0 | 0
FIRE ALARM SYSTEM - TOTAL |  |  |  |  | 255100 |  |  | 0 |  | 254714 |  | -386
FIRE SPRINKLER SYSTEM
3.1 | Supply, installation, testing and commissioning of G.I Heavy grade piping as per IS: 1239/3589 GI Forged Threaded GI forged socket welded & 65mm and above Seamless schedule 40) with necessary fittings such as tees, elbows,union,flanges, bends, rubber gaskets, reducers, GI nut bolt, washer etc. The pipes being suspended from ceilings by using support with clamps, hangers using anchor fastners upto 65 mm & above 80 mm pipe should be support with galvanized channel supports complete Rate quoted shall include painting with one coat of zinc cromet primer & 2 coats of synthetic enamel PO red paint and for painting of pipe & brackets and clamps as per IS-5 for above ground piping as per the NBC / IS standards and local fire service department requirement complete including supply and installation of G.I. Rods, clamps and , fasteners etc. All supports shall be hot dip galvanized in the range of DFT of micron 80 to 90 micron with 7 tank process, hot dip galvanizing shall be confirming to IS:2629/2633/4759/6745. Anchor fastners to be used of chemical type only where pipe supports to be taken from brick/block work.
a | 150mm nominal dia | Rmtrs | 0
b | 100mm nominal dia | Rmtrs | 0
c | 80mm nominal dia | Rmtrs | 0
d | 65mm nominal dia | Rmtrs | 0
e | 50mm nominal dia | Rmtrs | 0
f | 40mm nominal dia | Rmtrs | 0
g | 32mm nominal dia | Rmtrs | 3 | 600 | 1800 | 4.2 | 0 | 0 | 3 | 1800 | 1.2 | 720
h | 25mm nominal dia | Rmtrs | 30 | 500 | 15000 | 32.1 | 0 | 0 | 30 | 15000 | 2.1 | 1050
3.2 | Supplying, installing, testing and commissioning conventional Standard Response Sprinkler quartzoid bulb type with 15mm screwed end connection of 68 deg. C. temperature rating, K-Factor =5.6 GPM/psi½ (80.6 LPM/bar½) and orifice shall not be less than 6mm. Sprinklers shall be UL Listed / BIS approved with Chrome finished. |  |  |  | 0 |  | 0 | 0
a | Pendent Sprinkler | Nos | RO |  |  |  | 0 | 0
b | Upright Sprinkler | Nos | RO |  |  |  | 0 | 0
b | Concealed Sprinkler | Nos | 16 | 3000 | 48000 | 16 | 0 | 0 | 16 | 48000 | 0 | 0
3.3 | Stainless steel corrugated flexible pipe(hose) for dropping sprinklers below false ceiling, pipe shall be 16 bar pressure rating and 1500 mm long, 25 mm dia with union / reducer collar, clamps etc. as required. | Nos | 16 | 1800 | 28800 | 16 | 0 | 0 | 16 | 28800 | 0 | 0
3.4 | Supply & fixing of approved type rosette plates (Recessed type, in two piece) for Sprinklers below false ceiling area. | Nos | 16 | 90 | 1440 | 16 | 0 | 0 | 16 | 1440 | 0 | 0
3.5 | Supply and Installation, Testing and Commissioning of CI butterfly valves (body conforming to IS 210 GR FG 200) slim seal standard lever operated type conforming to IS13039/BS5155 with required flanges, nuts, bolts etc complete with supervisory tamper switch for monitoring. The valves shall be suitable for 150 psi pressure rating. Tamper Switch equipped with 2 Nos. of NO-NC contacts for monitoring
a | 100 mm dia | Nos | RO
b | 80 mm dia | Nos | RO
c | 65 mm dia | Nos | RO
3.6 | Fire Sprinkler Pipe Modifictaion Works (Extending the branch pipe as per proposed Interior layout wherever required and removal of existing rigid dropers) | Lot | RO
FIRE SPRINKLER SYSTEM - TOTAL |  |  |  |  | 95040 |  |  | 0 |  | 95040 |  | 1770

## Measurements
| Mumbai International Airport Pvt. Ltd. Measurement Sheet (Civil) |  | Document No.: MIAL/EN-CL/FMT/01 Issue No. : 01 Issue Date: 22-Apr-15 Revision No. : 00 Revision Date: Nil
Sr. No. | 1 |  | Name of site In charge : |  |  |  | Ashish Nagar
PO No.: | Semolina/PO/24-25/000687 |  | Agency Name : |  |  |  | TFS / Samolina Kitchen Pvt. Ltd.
PO Date : | 2024-07-29 |  | Date : 10-10-2024
PO Validity : |  |  | Name of Work: AJ Kitchen Fit Out
Measurement Sheet No. of this PO: | 1 |  | Period of work Executed : Sep '24
Sr.No | Details of Work | Measurements |  |  |  |  | Total Qty | Claimable % | Claimabl Qty | Claimable % | Claimabl Qty
|  | Unit | No. | Length | Breadth | Height
[8 empty] | RA-1 |  | RA-2 (Current Bill)
CIVIL & INTERIOR WORKS
1 | Partition walls
1.01 | Supply and installation of fire rated calcium silicate board Partition Wall with the necessory supports, fittings and fixtures (excluding final finishes). Purposed height of kitchen partition wall is 4500 mm and pot wash room is 3150mm, it may be change as per site conditions. Note: Framing and double side board to be installed. Final Finishies price to be quoted in wall finishes section. | SQM | 1 | 11.624 |  | 3.8 | 44.1712 | 100% | 44.1712 | 0% | 0
1.02 | Supply and installation of fire rated calcium silicate board cladding on the existing walls in the Kitchen & pot wash area to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures (excluding final finishes). Purposed height is 3150mm, it may be change as per site conditions. Note: Framing and single side board to be installed on existing wall. Final Finishies price to be quoted in wall finishes section. | SQM | 1 | 7.0815 |  | 3.8 | 26.9097 | 100% | 26.9097 | 0% | 0
1.03 | Supply and installation of 100 mm thick fire rated Gypsum board cladding on the existing walls to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures in the FOH & dining area walls. (excluding final finishes). Purposed height is 3700mm, it may be change as per site conditions. Note: Framing and single side board to be installed on existing wall. Final Finishies price to be quoted in wall finishes section. | SQM | 1 | 12.9 |  | 3.7 | 47.73 | 100% | 47.73 | 0% | 0
1.04 | Supply and installation of 65mm thick fire rated Gypsum board cladding on the existing walls to pass the MEP services & to receive the final finishes with the necessory supports, fittings and fixtures in the FOH & dining area walls. (excluding final finishes). Purposed height is 3700mm, it may be change as per site conditions. Note: Framing and single side board to be installed on existing wall. Final Finishies price to be quoted in wall finishes section. | SQM | 1 | 18.5 |  | 3.7 | 68.45 | 100% | 68.45 | 0% | 0
2 | FLOOR FINISHES
2.01 | 150mm thick concrete floor screeding to raise the floor to accomodate the drainage pipes and floor gratings & to receive floor finish in the Kitchen & FOH counter areas; all in accordance with drawings & site conditions. Note: Total height of floor to be raised including floor finishes is 180mm in the kitchen & FOH counter area only | SQM | 1 | 32.4 |  |  | 32.4 | 100% | 32.4 | 0% | 0
2.02 | Supply & installation of water proofing with all necessary items; all in accordance with drawings and below mentioned specification. Note: Detailed specifications of the materials to be submitted to client. | [9 empty] | 0
2.02a | Wet Areas: 2 Layers of 4mm thick SBS Bituminous membrane with 24-hour water ponding test including the sealing of Cores in the slab/walls (inspected and approved from airports team). | SQM | 1 | 44.14 |  |  | 44.14 | 100% | 44.14 | 0% | 0
2.03 | Supply and installation of self levelling with all necessary items; all in accordance with drawings. | SQM | 1 | 83.28 |  |  | 83.28 | 100% | 83.28 | 0% | 0
2.04 | Supply and installation of anti-skid 600 x 600 mm white floor tile in the kitchen & Pot wash area as per the drawings and renders. Note: Material to be approved by Clients team. | SQM | 1 | 5.2 | 2.7 |  | 14.04 | 100% | 14.04 | 0% | 0
2.05 | Supply and installation of Stone Plastic Composite (SPC) flooring in the FOH dining area area; colour & design as per drawings & render. Note: material to be approved by Clients Team | SQM | 1 | 47.25 |  |  | 47.25 | 100% | 47.25 | 0% | 0
2.06 | Supply and installation of anti skid 300 x 300 mm designer floor tile in the FOH area; colour & design as per drawings & render. Note: material to be approved by Clients Team | SQM | 1 | 23.63 |  |  | 23.63 | 100% | 23.63 | 0% | 0
3 | SKIRTING
3.01 | supply & installation of 100mm wooden skirting matching wall color as per the renders & drawings. Note: material to be approved by Clients Team | RM | 1 | 11.4 |  |  | 11.4 | 50% | 10.835 | Balance Qty | 0.565
4 | WALL FINISHES
A | Kitchen & Pot Wash areas
4.01 | Supply & installation of 300x300 mm White wall tile in the kitchen & Pot wash area as per drawings and renders. Note: material to be approved by Clients Team. Considered Ceiling height in kitchen is 3000mm | SQM | 1 | 21.8 |  | 3 | 65.4 | 0% | 0 | PO Qty | 61.73
4.02 | Allow sum for the supply and Installation of SS corner beeding on the corners of kitchen wall tiles. | RM | 1 | 14.2 |  |  | 14.2 | 0% | 0 | 100% | 14.2
B | FOH & Dining areas
4.03 | Supply & Painiting of matt finish paint of approved color on the walls of dining & FOH area as per the drawings & renders. Note: Material to be approved by clients Team | SQM | 1 | 32.1 |  | 3.6 | 115.56 | 0% | 0 | PO QTY | 117.4
4.04 | Supply & installation of WOODEN MOULDING STRIP finished with paint of approved colour on the walls of Dining & FOH area as per drawings and renders. Note: Material to be approved by clients Team | RM | 1 | 194.14 |  |  | 194.14 | 50% | 84.357 | Balance PO Qty | 109.783
5 | GYPSUM WORKS
5.01 | Supply & installation of fire rated bulkhead gypsum above the hood in white paint matt finish. Paint shall be included, as per the below hood sizes. Considered Ceiling height in kitchen is 3000mm
5.01A | Hood - Hot Cooking line : 2600 L x 1000 W x 600 H mm | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
6 | CEILING WORKS
6.01 | Supply & Installation of 600x600 mm metal tile ceiling in the Kitchen & Pot wash area with necessary support, fixtures & accessories as per drawings & renders Note: Material to be approved by Clients Team. | SQM | 1 | 2.74 | 5.875 |  | 16.0975 | 0% | 0 | PO QTY | 13.94
6.02 | Supply and Installation of Metal 3x3cm mesh ceiling with fire rated hanging flowers in the FOH & Dining areas including the final finishes with necessary support, fixtures & accessories as per drawings & renders. Note: Material to be approved by Clients Team. This ceiling will be Mesh type so that flower can be hanged. | SQM | 1 | 35.8 |  |  | 35.8 | 0% | 0 | 100% | 35.8
6.03 | Supply and Installation of fire rated Gypsum false ceiling with cove (for cove lights provision) in the the FOH & dining area with paint of approved color with necessary support, fixtures & accessories as per drawings & renders, refer to RCP layout. Including access panel/door as per the MEP services and Cutting & finishing for the AC grill/diffuser and lights. Note: Material to be approved by Clients Team. Running meter of cove has included in total quantity (24.87m+9.32m) | SQM | 1 | 65.86 |  |  | 67.86 | 50% | 32.93 | BALANCE QTY | 34.93
6.04 | Supply and painting with matt finish paint of approved color on the slab & walls of inside ceiling area of FOH & dinning, including paints on all MEP services & metal ceiling parts. Note: color to be selected/approved by Clients Team. The metioned quantity is the total covered area of the FOH and dining, quote the price accordingly for the paint on the slab and walls above the ceiling level and painting on all the MEP services | SQM | 1 | 67 |  |  | 67 | 0% | 0 | 100% | 67
7 | DOORS
7.01 | Supply and installation of heavy duty single leaf both side swing fire rated wooden door (kitchen door flushed to wall invisible type finished with same wall color) with the door frame for kitchen, including all the fittings & accessories as per the drawings and renders. Groove to be provided as per drawing and render. Dim: 2100H x 900W mm Note: Door frame should not be visible from Customer dining area. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
8 | Miscellaneous works
8.01 | Allow sum for the closing of wall opening using foams. | LS | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
8.02 | Allow sum for the Kitchen equipment equipment unloading and shifting till outlet | LS | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
FURNITURE
1 | CHAIRS & BANQUETTE SEATING
1.01 | Customer Dining Chair : Supply of Chair, inner side of chair in upholstery designer fabric of approved design and color, outer side of chair in upholstery of approved grey fabric, MS tube legs finished in golden powder coat. Dimensions, color & design as per the drawings and renders. Note: Samples to be submitted by contractor | PCS | 24 |  |  |  | 24 | 50% | 12 | 50% | 12
1.02 | Banquett Seating: Supply and installation of BANQUETTE SEATING MADE OF CUSHION FINISHED WITH LEATHER OF APPROVED COLOUR with 18mm THK MR MDF FINISHED LEATHER OF APPROVED COLOUR as per the drawings & renders. Size: L 11280 mm Dimensions, color & design as per the drawings and renders. Note: Samples to be submitted by contractor. | PCS | 1 |  |  |  | 1 | 50% | 0.5 | 50% | 0.5
2 | TABLE
2.01 | Customer Dining Table: Supply and Installation of Table made up of 20mm thick Corian tabletop of approved color with 2 mm thick MS tube legs finished in black powder coat and gold power coat, 6mm thick Golden metal embedded in the sides of tabletop, leg base with 6mm thick steel plate in gold powder coat finish as per the drawings and renders. Note: Samples to be submitted by contractor Dimensions, color & design as per the drawings and renders.
| 650L x 650W x 750H mm | PCS | 18 |  |  |  | 18 | 50% | 9 | 50% | 9
3 | JOINERY
3.01 | Supply & installation of "FOH counter" made up of 18mm thick MR-MDF structured, with 12mm thick Corian material finish on top; and sides finished by stucco paint of RAL 4008 color and with black metal strips and cove lighting, 20mm wide black metal strips placed on the top of stucco finish with 20mm spacing 12mm thick corian skirting, 30mm dia 75mm high from centre guard rail finished with gold colour, 18mm THK MR MDF Partition wall 1100mm high finished with Oak wood veneer 18mm THK MR MDF swing door finish with oak wood veneer, 18mm THK MR MDF Planter box above counter sides finished with Oak wood Veneer and top with Corian of approved design Adjustable 2 layer open shelf finished with approved white laminate, 3 layer adjustable shelf inner side finished with approved white laminate and outer with Oak wood veneer, Open spaces for display units, All inner sides of the counter are to be finished with white laminate, and all necessary support, fittings, and accessories as per approved drawings and renders. Space/provisions are to be provided to accommodate the equipment inside the counter as shown in the drawings and renders. Note: Actual countertop material sample shall be submitted by the contractor and, required provision for electrical socket as per power layout. The contractor shall refer to the counter details for complete detailings, dimensions & materials etc. | Nos | 1 |  |  |  | 1 | 50% | 0.5 | 50% | 0.5
3.02 | Supply and installation of "FOH Back counter" made up of SS metal structure (Kitchen equipment vendor makes SS metal frame structure), Top finished with Corian material of approved design and the sides cladding & doors by 18mm thick MR-MDF finished with oak wood veneer. The contractor shall refer to the FOH back counter detail drawings & renders for complete detailings, dimensions & materials etc. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
3.03 | Supply and installation of "Back Counter for u/c Ice Machine" made up of 18mm THK MRMDF COUNTER WITH OPEN SHELF FOR UNDERCOUNTER ICE CUBE MACHINE, Top finished with Corian material of approved design and the sides cladding by 18mm thick MR-MDF finished with oak wood veneer. The contractor shall refer to the detail drawings & renders for complete detailings, dimensions & materials etc. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
3.04 | Supply and installation of SERVICE COUNTER MADE UP OF 18mm THK MRMDF FINISHED WITH OAK WOOD VENEER ON THE OUTER SIDE, 18mm THK MRMDF DRAWER FOR CUTTLERY, FINISHED IN WHITE MICA IN INNER SIDE, as per the renders and drawings. The contractor shall refer to the service counter detail drawings & renders for complete detailings, dimensions & materials etc. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
3.05 | Supply and installation of Electrical panel unit made up of 18mm THK FRMDF finished with paint of the same wall colour outer side with mouldings and in white mica on the inner side as per the drawings. The contractor shall refer to the service counter detail drawings & renders for complete detailings, dimensions & materials etc. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
4 | PLANTER BOXES & ARTIFICIAL PLANTS
4.01 | Supply & installation of planter box with fire rated artificial plants with the 18mm thick MDF finished with laminate of approved color, 10mm thick wooden moulding, 6mm thick Corian cladding with 4mm grove & naturally looking artificial fire rated plant as per drawings and renders. Size: 600 x 300 x 800 mm Dimensions, color & design as per the drawings and renders. Note: Samples shall be submitted by contractor. |  | 2 |  |  |  | 2 | 100% | 2 | 0% | 0
4.02 | Supply & installation of round shape planter box with fire rated artificial plants with the paint/powder coated finishes as per drawings and renders. Size of planter box: dia. 300mm Note: Samples shall be submitted by contractor. | Nos | 3 |  |  |  | 3 | 0% | 0 | 100% | 3
4.03 | Supply and Installation of NATURALY LOOKING ARTIFICIAL GRASS AND TREE as per the drawings and renders. To be coordinate with FOH counter drawings. Note: Samples shall be submitted by contractor. Supply and installation of planter box to be quote along with the FOH counter in Joinery section. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
SIGNAGES & DISPLAY UNIT
0.01 | AJ1881 LOGO AT FRONT ELEVATION: Supply & Installation of AJ1881 front lit aluminium 3D logo, letter made of aluminium channellume 3D letters with font face acrylic illuminated LED with transformer. Including the Vinyle graphic base & structure, to be hunged from the top, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
| Above mentioned logo in the Marathi language with the same material and specification | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
0.02 | AJ1881 LOGO IN THE DINING AREA WALL: Supply & Installation of AJ1881 front lit aluminium 3D logo, letter made of aluminium channellume 3D letters with front face acrylic illuminated LED with transformer, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
0.03 | HEART SHAPE LOGO IN THE DINING AREA WALL: Supply & Installation of front lit 3D Logo- Heart Shape, letter made of aluminium channellume 3D letters with front face acrylic illuminated LED with transformer, as per the drawings & renders. Supply and fixing of LED controller for adjusting LED brightnes. Note: Material to be approved by Clients Team. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
1.04 | Supply and installation of 43" Digital Display unit for the Menu as per the drawings and renders. Note: Sample to be approved by Clients team | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
PLUMBING
A | SANITORY FIXTURES
5 | Supplying, Installing, testing & commissioning of Pantry sink with single bowl with out drain board manufactured from stainless steel, 18G high grade indestructible chrome nickel steel with top quality polish, 1no.40 mm dia CP waste coupling, with 1no. 40mm dia CP bottle trap with extension pipe, CP angle cock, & divertor with Counter mounted type sink tap and necessary wall flanges,angle cock etc., complete. | Nos | 4 |  |  |  | 4 | 0% | 0 | 100% | 4
6 | Supplying, installing, testing and commissioning of 15mm CP angle valve with CP flanges including necessary fixing materials etc.,complete. | Nos | 17 |  |  |  | 17 | 0% | 0 | 100% | 17
7 | Supplying, installing, testing and commissioning of 15mm CP bib cock with CP flanges including necessary fixing materials etc.,complete. | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
14 | Supply, Fixing, testing and commissioning of approved make vertical/horizontal type Electric 'water heater suitable for pressure rating up to 6Kg/sqcm with heating element with thermostat, 2 Nos. 15mm dia CP angle valve, pressure relief valve, non-return valve with CP copper connecting pipes with wall flanges etc., complete with all inlets, outlets, valves and all other accessories etc., complete.
14.1 | Capacity : 15 lts. 1..5 K.W heating element | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
14.2 | Capacity : 25 lts. 2 K.W heating element | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
B | DRAINAGE
1 | Supplying, fixing, testing and commissioning of PVC Soil, waste and ventilating pipes (SWR) conforming to IS:13592 Type B with rubber ring,yellow seal (conforming to IS : 5382) joints inclusive of all necessary specials like bends, tee, offsets, door bends, junctions, cowls, threaded type cleanout etc., laid under floor / fixed on walls and in pipe shaft with proper pipe support like brackets, hangers, G.I grip bolts etc., complete. The support shall be painted with two coats of enamel paint.The rate shall include the cost of galvanized U clamps, bolts & nuts,painting of supports with 2 coats of zinc chromate primer with 2 coats of enamel paint of total DFT minimum 100 micron. As required at site as per drawings to the satisfaction of the Project Manager. Internal Toilet
1.1 | 75 mm dia |  | 32.3 |  |  |  | 32.3 | 100% | 30 | 0% | 0
2 | Supplying, fixing and testing uPVC pressure pipes (6Kg/sqcm) conforming to IS 4985 for waste connection from washbasin, kitchen sink to floor trap, including, threading, cutting, laid under floor / concealed in wall etc. The work shall include wall chase and making good the same in cement mortar etc. complete to the satisfaction of Engineer-in-charge.The rate shall include the cost of galvanized U clamps, bolts & nuts,painting of pipes with 2 coats of zinc chromate primer with 2 coats of enamel paint of total DFT minimum 100 micron
2.1 | 40mm dia | Rm | 10 |  |  |  | 10 | 100% | 10 | 0% | 0
2.2 | 50 mm dia | Rm | 0 |  |  |  |  | 0% | 0
3 | Supplying, installing, testing and commissioning of Upvc floor trap with 110mm dia pipe PVC deep seal 'P' trap with necessary PVC fabricated boss connection with a minimum 2Nos. of 50mm dia inlets & CP floor grating (sealed type) etc... Complete. The cost shall include Cockroach Traps., | Nos | 6 |  |  |  | 6 | 0% | 0 | 100% | 6
4 | Drilling with core cutting in RCC beams, slabs, floors etc.,for laying pipes and rendering the same in RCC 1:2:4, finishing the same to the satisfaction of the Owner or his authorized representative etc.,including nominal reinforcement where ever required, complete. The quoted rate shall also include for providing EPOXY based water proofing compound for sealing the joints around the pipes. Core cut shall be done using rebar detector after getting the approval from the structural consultant..
4.1 | RCC slabs
| s | Nos | 0 |  |  |  |  | 0% | 0
| 50mm dia upto 110 mm | Nos | 0 |  |  |  |  | 0% | 0
| 125mm dia. upto 160 mm | Nos | 0 |  |  |  |  | 0% | 0
| 160mm upto 250mm | Nos | 0 |  |  |  |  | 0% | 0
5 | Supplying and installing MS fabricated drain grating at kitchen area where ever indicated using 50mm nominal bore,MS pipes at 105mm C/C and 8mm thick MS flats welded together and placed on MS angles of size 65mm x 65mm x 6mm, the quoted rates shall include for painting two coats of enamel paint over a coat of primer etc,.Complete. |  | 0
5.1 | 150mm wide Drain Channel | Nos | 0 |  |  |  |  | 0% | 0
5.2 | 300mm wide Drain Channel | Nos | 3 |  |  |  | 3 | 100% | 3 | 0% | 0
5.3 | 450mm wide Drain Channel | Nos | 0 |  |  |  |  | 0% | 0
C | WATER SUPPLY
1 | Supply Installation, testing & commissioning of Chlorinated Polyvinyl Chloride (CPVC) pipes, SDR 11 as per IS 15778: 2007 & fittings as per ASTM D2846 / D2846M - 14 for pipe upt 50mm dia and for pipe 65mm and above use Sch 80 Pipes as per ASTM F - 441 & Sch 80 fittings as per ASTM F439 - 13, both of approved make. both of approved make having thermal stability for hot & cold water supply, including all CPVC plain & brass threaded fittings such as bends, elbows, tees, sockets, unions, plugs etc., including fixing the pipe., including necessary drilling holes, chasing walls and making the same good in as directed by the Engineer in-charge.
Cost shall be inclusive of all hangers, clamps, brackets etc. shall be of galvanized iron unless specified otherwise and then supply of the same shall also be included for rates under this head. Also rates including flusing and chemical cleaning of pipes.Charges for Labelling of pipe as per color schedule over painted surface of the pipes.
All pipes are mentioned here is ID only
Domestic water supply
1.1 | 15 mm nominal dia |  | 130 |  |  |  | 130 | 100% | 130 | 0% | 0
2 | Supply Installation, testing & commissioning of full way lever operated forged brass ball valve working pressure not less than PN10 with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc.
2.1 | 15 mm nominal dia |  | 1 |  |  |  | 1 | 100% | 1 | 0% | 0
2.2 | 20 mm nominal dia |  | 1 |  |  |  | 1 | 100% | 1 | 0% | 0
ELECTRICAL
1 | LT SWITCHGEAR and Distribution Boards
Supply, installation, testing and commissioning of Low voltage switchgear's, free standing, Cubical type, dead front, Frame and Doors:2mm, Internal Partations:1.6mm thick, Gland Plates:3mm Thick, powder coated (Paint Shade: RAL 7032/7035), indoor type with vermin proof hinged lockable doors for each compartment, bus bar interconnections for incoming and outgoing including feeders earthing and painting and as per specifications comprising of ACB,MCCB and MCB horizontal and vertical aluminum bus bar, earth bus bar as per SLD. All meters shall be digital with LED display, whereever mentioned and shall have RS 485 Modbus RTU half duplex communication interface for provision of BMS connectivity and wired accordingly. Provide required NO/NC potential free contacts wires and terminal blocks in the cable alley for BMS operation (Optional).The swtichboards are to be tested as per IS 8623 -1977 specifications. The busbars are of high conductivity Al. alloy E91E IS 5082 specification and cable entries will be from either top or bottom depending on location. LT Switchgear shall be as per technical specification and single line diagram
1.1 | MDB
| MDB shall be as per Single line diagram and technical specifications.(Indoor -IP 42) | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
1.2 | ISOLATORS
a | 160A 4P MCCB in metallic enclosure -IP 42 | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
b | 63A 4P MCB in metallic enclosure -IP 42 | Nos | RO
c | 40A 4P MCB in metallic enclosure -IP 42 | Nos | RO
d | 25A 4P MCB in metallic enclosure -IP 42 | Nos | RO
e | 40A DP MCB in metallic enclosure -IP 42 | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
f | 25A DP MCB in metallic enclosure -IP 42 | Nos | 0
1.3 | STARTERS
a | Supply & Installation of 1.1kW Similat to Motor KW of fan slelected by OEM of unit as per approved TDS DOL/STAR DELTA starter with contactor, MPCB, overload relay, ON-OFF push buttons, Auto/Manual, ON/OFF/Trip indicating lamps, NO/NC Contacts and potential free contacts with required accessories and provied universal sockets as shown in SLD, refere Single line diagram and technical specifications. Starter panel shall be supplied with space provisons with internal wring circuits and sight glass for VFD instlattions. Installation and wiring terminations for VFD will be electrical vendor scope. Supply of VFD in HVAC vendor scope. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
2 | MCB Distribution boards
a | 12 Way TPN MCB Distribution Board -PPI (KDB) | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
MCB DB comprising the following
Type of DB - 12 way TPN PPI MCB DB (Double Door)
100A 4P MCB - 1 No. as incomer
63A DP RCCB, 30mA, 2 Module - 3 Nos. as Sub incomer per phase
20A SP MCB, 10 kA - 29 Nos. as outgoings : MCB are of 'C' Curve
32A SP MCB, 10 kA - 1 Nos. as outgoings : MCB are of 'C' Curve
The rate shall include providing Cu. bus barsinterconnection, separate earth bus, separate neutral bus for each phases, Blank Plates and incluuding necessary connected civil works like chipping, rough plastering etc.
b | 8 Way TPN MCB Distribution Board - PPI (LPDB) | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
MCB DB comprising the following
Type of DB - 8 way TPN PPI MCB DB (Double Door)
32A 4P MCB - 1 No. as incomer
25A DP RCCB, 30mA, 2 Module - 3 Nos. as Sub incomer per phase
10A SP MCB, 10 kA - 18 Nos. as outgoings : MCB are of 'C' Curve
The rate shall include providing Cu. bus barsinterconnection, separate earth bus, separate neutral bus for each phases, Blank Plates and incluuding necessary connected civil works like chipping, rough plastering etc.
c | 12 Way SPN MCB Distribution Board | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
MCB DB comprising the following
Type of DB - 12 way SPN MCB DB (Single Door)
40A DP RCBO,30mA, 2 Module - 1 No. as incomer
6A SP MCB, 10 kA - 4 Nos. as outgoings : MCB are of 'C' Curve
10/16A SP MCB, 10 kA - 10 Nos. as outgoings : MCB are of 'C' Curve
The rate shall include providing Cu. bus barsinterconnection, separate earth bus, separate neutral bus for each phases, Blank Plates and incluuding necessary connected civil works like chipping, rough plastering etc.
3 | LOW VOLTAGE CABLES AND END TERMINATION
3.1 | Low voltage Aluminium conductor cables
Supply and laying of 1100 V grade, XLPE insulated,extruded PVC Inner Sheathed and extruded FRLS-PVC Outer sheatehed , aluminium conductor, Armoured power cable as per specifications. The cable shall be laid in indoor trenches / cable trays as required. The cable shall be clamped at regular intervals to the suppoprts in trench or to cable trays or brick wall using MS clamps and fasteners. Rate shall exclude the cost of cable trays and termination in this item.
NOTE: Cables will not be procured based on BOQ only. True measurements will be taken by Contractor before ordering, based on Drawings/ Site actual requirements ( Applicable to all respect Line items)
a | 3.5CX 50Sqmm Alu.arm Cable | Rmt | 1 | 31.85 |  |  | 31.85 | 100% | 30 | 0% | 0
b | 3.5CX 35Sqmm Alu.arm Cable | Rmt | 0 | RO |  |  |  | 0% | 0
c | 3.5CX 25Sqmm Alu.arm Cable | Rmt | 0 | RO |  |  |  | 0% | 0
d | 4CX 16Sqmm Alu.arm Cable | Rmt | 0 | RO |  |  |  | 0% | 0
e | 4CX 10Sqmm Alu.arm Cable | Rmt | 1 | 16.1 |  |  | 16.1 | 100% | 15 | 0% | 0
f | 3.5CX 120 Sqmm Alu.arm Cable | Rmt | 0
3.2 | Low Voltage Copper Conductor Cables
Supply and laying of 1100 V grade, XLPE insulated,extruded PVC Inner Sheathed and extruded FRLS-PVC Outer sheatehed copper conductor, Armoured/Un armoured power cable as per specifications. The cable shall be laid in indoor trenches / cable trays as required. The cable shall be clamped at regular intervals to the suppoprts in trench or to cable trays or brick wall using MS clamps and fasteners. Rate shall exclude the cost of cable trays and termination in this item.
Armoured Copper Cables :
a | 4Cx 16sqmm Cu Arm Cable | Rmt | 1 | 15 |  |  | 15 | 100% | 15 | 0% | 0
b | 4Cx 6sqmm Cu Arm Cable | Rmt | 1 | 15 |  |  | 15 | 100% | 15 | 0% | 0
c | 4Cx 4sqmm Cu Arm Cable | Rmt | 1 | 20 |  |  | 20 | 100% | 20 | 0% | 0
d | 3Cx 6sqmm Cu Arm. Cable | Rmt | 0 | RO
e | 3Cx 4sqmm Cu Arm. Cable | Rmt | 1 | 22 |  |  | 22 | 100% | 20 | 0% | 0
3.3 | Copper Flexible Cables :
a | 3Cx6sqmm Cu Flexible Cable | Rmt | 1 | 20 |  |  | 20 | 100% | 20 | 0% | 0
b | 4Cx6sqmm Cu Flexible Cable | Rmt |  | RO
3.4 | LOW VOLTAGE CABLE END TERMINATION:
Supply and providing LV cable end termination for below listed cable with copper lugs, brass cable glands, tapping, crimping, etc. complete. Single Compression Glands : Cable Size Below 150 Sqmm Double Compression Glands : Cable size above 185sqmm and Single core cables 400sqmm and above
a | 3.5CX 50 Sqmm Alu.arm Cable | Nos | 2 | 2 |  |  | 2 | 100% | 2 | 0% | 0
b | 3.5CX 35Sqmm Alu.arm Cable | Nos | 0 | RO
c | 3.5CX 25Sqmm Alu.arm Cable | Nos | 0 | RO
d | 4CX 16Sqmm Alu.arm Cable | Nos | 0 | RO
e | 4CX 10Sqmm Alu.arm Cable | Nos | 2 | 2 |  |  | 2 | 100% | 2 | 0% | 0
f | 3.5CX 120 Sqmm Alu.arm Cable | Nos | 0 | RO
3.5 | Armoured Copper Cables :
a | 4Cx 16sqmm Cu Arm Cable | Nos | 2 | 2 |  |  | 2 | 100% | 2 | 0% | 0
b | 4Cx 6sqmm Cu Arm Cable | Nos | 2 | 2 |  |  | 2 | 100% | 2 | 0% | 0
c | 4Cx 4sqmm Cu Arm Cable | Nos | 2 | 2 |  |  | 2 | 100% | 2 | 0% | 0
d | 3Cx 6sqmm Cu Arm. Cable | Nos |  | RO
e | 3Cx 4sqmm Cu Arm. Cable | Nos | 2 | 2 |  |  | 2 | 100% | 2 | 0% | 0
3.6 | Copper Flexible Cables :
a | 3Cx6sqmm Cu Flexible Cable | Nos | 8 | 8 |  |  | 8 | 100% | 8 | 0% | 0
b | 4Cx6sqmm Cu Flexible Cable | Nos |  | RO
4 | SWITCHES AND SOCKETS
Supply and install switches and Sockets System as required according to the specification, drawings and design. The installation rate of all the following accessories shall include for the supply of all materials such as passivated metal switchbox,junction boxes, switch plate, switches, conduit accessories, wires, tags, supports, fittings fixings and the like, to form complete elements and shall include for earthing the switchboxes The installation rate shall include for termination of all cables and wires into the devices, testing,commissioning and setting to work as required by the specifications.
NOTE: SWITCHES AND SOCKETS will not be procured based on BOQ only. True measurements will be taken by Contractor before ordering, based on Drawings/ Site actual requirements ( Applicable to all respect Line items)
Power Receptacles with Box
4.1 | Supply, installation, testing and Commissioning of 1 x 6/16A, Universal 5 pin round/flat socket controlled with 1 x 16A Switch with Indication lamp including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories.Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | 44 |  |  |  | 44 | 0% | 0 | PO Qty | 40
4.2 | Supply, installation, testing and Commissioning of 1 x 6A, universal socket controlled with 1 x 6A Switch including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories.Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | 3 |  |  |  | 3 | 0% | 0 | 100% | 3
4.3 | Supply, installation, testing and Commissioning of 2 x 6/16A,, universal socket controlled with 2 x 16A Switch including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories.Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | RO | [5 empty] | 0
4.4 | Supply, installation, testing and Commissioning of 3 x 6A, universal socket controlled with 1 x 16A Switch including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories. Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | RO | [5 empty] | 0
4.5 | Supply, installation, testing and Commissioning of 2 x 6A, universal socket controlled with 2 x 6A Switch including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories. Rate shall include the cost for fixing of back box with plastering and rough finish | Nos | RO | [5 empty] | 0
4.6 | Supply, installation, testing and Commissioning of 1 x 20A, universal socket controlled with 1 x 20A Switch floor mounted pop up box including interconnection etc., complete.The sockets shall be with face plate, GI BOX with accessories.Rate shall include the cost for fixing of back box with plastering and rough finish (MK Type Floor Box) | Nos | RO | [5 empty] | 0
0
| Power Receptacles without Box | [7 empty] | 0
4.7 | Supply, Installation testing and commissioning of 3 nos. of 6/16 A, multi Pin Universal socket controlled by 1 no. 16 A common switch along with face plate, raceway/Table mounted and other necessary accessories to complete the installation. | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
4.7 | Supply, Installation testing and commissioning of 6/16 A, multi Pin Universal socket controlled by 1 no. 16 A common switch along with face plate, raceway/Table mounted and other necessary accessories to complete the installation. | Nos | RO | [5 empty] | 0
Industrial Sockets :
4.8 | Supply, installation, testing and Commissioning of 16A, 1 phase Industrial Plug & Socket controlled with 16A DP MCB in a enclosure with all accessories. (IP65) | Nos | 6 |  |  |  | 6 | 0% | 0 | 100% | 6
4.9 | Supply, installation, testing and Commissioning of 20A, 1 phase Industrial Plug & Socket controlled with 20A DP MCB in a enclosure with all accessories. (IP65) | Nos | 10 |  |  |  | 10 | 0% | 0 | 100% | 10
4.10 | Supply, installation, testing and Commissioning of 25A, 1 phase Industrial Plug & Socket controlled with 25A DP MCB in enclosure with all accessories.(IP65) | Nos | RO | [5 empty] | 0
4.11 | Supply, installation, testing and Commissioning of 32A, 1 phase Industrial Plug & Socket controlled with 25A DP MCB in enclosure with all accessories.(IP65) | Nos | RO | [5 empty] | 0
4.12 | Supply, installation, testing and Commissioning of 32A, 3 phase Industrial Plug & Socket controlled with 32A 4P MCB in enclosure with all accessories.(IP65) | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
4.13 | Supply and installation of 3 Module Metal Boxes | Nos | RO | [5 empty] | 0
4.14 | Supply and installation of 4 Module Metal Boxes | Nos | RO | [5 empty] | 0
4.15 | Supply and installation of 6 Module Metal Boxes | Nos | RO | [5 empty] | 0
4.16 | Supply and fixing of Blankplates | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
4.17 | Supply and fixing of 3 Pin Plug top suitable for 16/20A | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
5 | CIRCUIT MAINS
CIRCUIT MAIN FOR LIGHTING/POWER :
Supply and drawing of 1100V grade, multi strand FRLS insulated copper conductor wire. drawn into existing raceways/cable trays with necessary fixing accessories.
5.1 | 3 core 1.5 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduits. Rate shall exclude the cost of Raceway/Conduit in this items. | Rmtrs | 35 |  |  |  | 35 | 100% | 35 | 0% | 0
5.2 | 3 core 2.5 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduits. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | 75 |  |  |  | 75 | 100% | 75 | 0% | 0
5.3 | 3 core 4 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduit. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | 150 |  |  |  | 150 | 100% | 150 | 0% | 0
5.4 | 3 core 6 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduit. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | 0 |  |  |  |  | 0% | 0
5.5 | 2R x 2.5 sq.mm. + 1R 1.5 sq mm FRLS, MSCC wires drawn in 25mm Dia GI conduit with all accessories for general lighting.The rate shall include the cost of conduits and its accessories . | Rmtrs | 0 |  |  |  |  | 0% | 0
5.6 | 2R x 4sqmm and 1RX2.5Sqmm FRLS MSCC wires drawn in 25mm dia GI conduit with all accessories for general purpose power sockets.The rate shall include the cost of conduits and its accessories. | Rmtrs | 0 |  |  |  |  | 0% | 0
5.7 | 1 core 4 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduits. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | 1750 |  |  |  | 1750 | 100% | 1750 | 0% | 0
5.8 | 1 core 6 sqmm Double Insulated Copper copper conductor flexible cable with FRLS Sheathing in the existing raceways/conduits. Rate shall exclude the cost of Raceway/conduit in this items. | Rmtrs | 50 |  |  |  | 50 | 100% | 50 | 0% | 0
6 | POINT WIRING
Point wiring of light, using 1100 volt grade, 3Rx1.5Sqmm multi strand FRLS insulated copper conductor flexible cable, drawn in existing raceways/Conduit. The rate shall include providing mounting boxes with tapped holes for lights switches, moulded front plates with brass screws earthing of all points using third core of the cable, For MCB Controlled Lights -DB to 1st light will be measured as circuit wiring.The point wiring shall be as per specification.Rate shall exclude the cost of MCB,Rceways in this item.(CONDUIT - GI)
6.1 | PRIMARY LIGHT POINT (Switch Control)
| Primary light point means wiring from first switch control to the first light outlet. The switch and all necessary accessories would be part of primary point.'. Not to include the incoming lighting circuit from MCB-DB to switch.' But to include the sub-circuit if it is drawn from adjacent switch box. Ceiling flexible conduit shall be included at the drop of light fixture. | Nos | 10 |  |  |  | 10 | 100% | 10 | 0% | 0
6.2 | SECONDARY LIGHT POINT (Switch Control)
| Secondary light point means extention of light outlet from existing primary point. Same to be controlled by the existing switch of primary point. Ceiling flexible conduit shall be included at the drop of light fixture. | Nos | 25 |  |  |  | 25 | 100% | 25 | 0% | 0
6.3 | SECONDARY LIGHT POINT (MCB Control)
| Secondary light point means extention of light outlet from existing primary point. Same to be controlled by the existing MCB of primary point. Ceiling flexible conduit shall be included at the drop of light fixture. The Wiring from DB to First Light point will be measured under circuit mains. | Nos | RO |  |  |  |  | 0% | 0
6.4 | Ceiling fan point controlled by 6/10 A flush type SP switch. The rate shall include MS fan hook boxes. The rate shall also include cost of 300 W electronic fan speed controller in this item only.Rate shall exclude the cost of ceiling fan in this item. | Nos | RO |  |  |  |  | 0% | 0
7 | CABLE TRAY/RACEWAYS
7.1 | Ladder Type
Supply and providing Ladder cable trays factory fabricated out of 2mm thick pre galvanized sheet steel, channel size 75 x 15 mm and rung size 30 x 6 mm, spaced at 250 mm interval, supporting angle frame at every 1.8 m, bottom angle fasteners, anchor grip bolts, synthetic enamelled painting, etc. The tray shall be suspended from ceiling using anchor bolt and angle iron supports or mounted from wall. The rate shall include all accessories like bends, elbows, tees, coupler plates, etc., which will be measured as linear measurement and fixing accessories.The rate shall include the cost of Supports
a | 150 mm wide 50 mm height | Rmtrs | 0 |  |  |  |  | 100% | 0
b | 300 mm wide 75 mm height | Rmtrs | 0 |  |  |  |  | 100% | 0
c | 450 mm wide 75 mm height | Rmtrs | 0 |  |  |  |  | 100% | 0
7.2 | Perforated Type
Supply and providing MS Perforated cable trays factory fabricated out of 2mm thick pre galvanized sheet steel, channel size 50 mm supporting angle frame at every 1.8 m, bottom angle fasteners, anchor grip bolts, synthetic enamelled painting, etc. The tray shall be suspended from ceiling using anchor bolt and angle iron supports or mounted from wall. The rate shall include all accessories like bends, elbows, tees, coupler plates, etc., which will be measured as linear measurement and fixing accessories.The rate shall include the cost of Supports
a) | 50 mm wide 50 mm height | Rmtrs | 0 |  |  |  |  | 100% | 0
b) | 100 mm wide 50 mm height | Rmtrs | 0 |  |  |  |  | 100% | 0
c) | 150 mm wide 50 mm height | Rmtrs | 0 |  |  |  |  | 100% | 0
d) | 200 mm wide 50 mm height | Rmtrs | 25 |  |  |  | 25 | 100% | 25 | 0% | 0
e) | 300 mm wide 50 mm height | Rmtrs | 0 | [5 empty] | 0
7.7 | POWDER COATED FRAME FOR MCB DB's
a | Supply and Installation of DB Frame with wire ways shall be made out of 1.6mm thick CRCA sheet steel and powder coating colour shall match the colour of MCB DB's with hinged type door. 100mm x 100mm 1.6mm thick, wire ways / Raceway with 2mm thick screwed / press to fit cover with hinged type door for making Frame for MCB DB's. Complete required including installation accessories. | Rmtrs | 15 |  |  |  | 15 | 100% | 15 | 0% | 0
8 | EARTHING
8.1 | Supply and Installation of earthing station as per IS3043 complete with 600x600x3.15mm Copper plate earthing with salt, charcoal, 2 nos. of 25x3mm Copper strip up to test link,19mm dia GI watering pipe with funnel, test link earthing chamber 450x450mm CI cover etc with required civil works complete. The CI Frame and cover shall be of heavy duty type. | Nos | 0 | [5 empty] | 0
8.2 | Supply and Installation of earthing station as per IS 3043 complete with GI pipe earthing with salt, charcoal, 2 nos. of 50x6mm GI strip up to test link ,40mm dia GI watering pipe with funnel,test link, earthing chamber of 450x450mm CI cover etc with required civil works complete.The CI Frame and cover shall be of heavy duty type. . | Nos | 0 | [5 empty] | 0
8.3 | Supply and running of below listed sizes of electrolytic copper / GI earth conductor tapes / wires and laid along with cable or clamped to brick wall, etc., as required.
a | 8 SWG GI wire for Earthing | Rmtrs | 40 |  |  |  | 40 | 100% | 40 | 0% | 0
b | 25x3mm GI Flat | Rmtrs | 25 |  |  |  | 25 | 100% | 25 | 0% | 0
c | 25x6mm GI Flat | Rmtrs | 0 |  |  |  |  | 100% | 0
d | 1Cx6sqmm Cu Flexible Cable Earthing (Green) | Rmtrs | 75 |  |  |  | 75 | 100% | 75 | 0% | 0
e | 1Cx4sqmm Cu Flexible Cable Earthing (Green) | Rmtrs | 50 |  |  |  | 50 | 100% | 50 | 0% | 0
8.4 | Supply and installation of Earth pads made out of copper/GI busbars installed on 1100 V insulators including hardware and other minor civil works.associated works.
a | Busbar of 0.5 Mtr length made out of 25 x 3 mm Cu. strip with drill holes of M8 at 25mm interval mounted on insulators and acrylic cover to be provided. | Nos | 0
b | Busbar of 0.5 Mtr length made out of 25 x 6 mm Cu. strip with drill holes of M8 at 25mm interval mounted on insulators and acrylic cover to be provided. | Nos | 0
c | Busbar of 0.5 Mtr length made out of 45 x 6 mm GI strip with drill holes of M8 at 25mm interval mounted on insulators. | Nos | 1 |  |  |  | 1 | 100% | 1 | 0% | 0
9 | PVC pipes (Electrical/IT/AV/CCTV/ACS)
9.1 | Supply and laying of 2 mm thick rigid FRLS PVC conduits in concealed conduit system using conduit accessories like junction boxes, collars, bends, elbows, binding wires, etc.
a | 32 mm dia conduit | Rmtrs | 0 |  |  |  |  | 100% | 0
b | 25 mm dia conduit | Rmtrs | 0 |  |  |  |  | 100% | 0
c | 20 mm dia conduit | Rmtrs | 0 |  |  |  |  | 100% | 0
GI pipes (Electrical/IT/AV/CCTV/ACS)
9.2 | Supply and laying of 2 mm thick rigid MS conduits in concealed/Open conduit system using conduit accessories like junction boxes, collars, bends, elbows, binding wires, etc.
a | 32 mm dia conduit | Rmtrs | 10 |  |  |  | 10 | 90.01% | 9.0013 | 9.987% | 0.99872
b | 25 mm dia conduit | Rmtrs | 125 |  |  |  | 125 | 76.85% | 96.59 | 23.15% | 28.9375
c | 20 mm dia conduit | Rmtrs | 80 |  |  |  | 80 | 73.68% | 58.947 | 26.32% | 21.056
10 | STRUCTURAL WORKS
10.1 | Supply, cutting, welding, grouting, fastening, cleaning and painting of MS Channels, angles, plate, supporting brackets/structures , etc complete with necessary hardwares. | Kgs | 0 |  |  |  |  | 100% | 0
10.2 | Supply of 6mm thick MS chequred plates duly painted. Plates to be cut size as per site requirement. | Kgs | 0 |  |  |  |  | 100% | 0
11 | MISCELLANEOUS ITEMS
11.1 | Supply and fixing of danger boards of appropriate voltage grade, size and style as required by Electrical Inspectorate. | Nos | 1 |  |  |  | 1 |  |  | 100% | 1
11.2 | Supply of Rubber checkered mat of size 2000 x 1000 x 10mm thick, 11000 V grade. | Nos | 0 |  |  |  | 0 |  |  |  | 0
11.3 | Supply of Rubber checkered mat of size 2000 x 1000 x 3mm thick, 11000 V grade. | Nos | 1 |  |  |  | 1 |  |  | 100% | 1
11.4 | Supply of Standard First aid box complete with all accessories. | Nos | 1 |  |  |  | 1 |  |  | 100% | 1
11.5 | Supply of Wooden framed glass fronted shock treatment chart as per IE rules fixed to wall. | Nos | 1 |  |  |  | 1 |  |  | 100% | 1
11.6 | SITC of Hand held Fire Extinguisher - ABC Powder - 6 Kg with floor mount accessories | Nos | 1 |  |  |  | 1 |  |  | 100% | 1
11.7 | Temporary Works | [9 empty] | 0
a | For temporary Lighting in the construction area with necessary light fixtures ,cabling & Power Distribution control panel for construction works.The cost shall include necessary industrial sockets, cables, distribution boards, earthing,Light fixtures and all safety accessories as required. | LS | RO |  |  |  | RO
b | Professional charges towards filing application, preparation of drawings in necessary formats for approval, follow up and arranging approval of drawings, scheme by Local electricity authority Electrical Inspectorate, obtaining clearance from electricity authority / Electrical Inspectorate. | LS | RO |  |  |  | RO
c | Preparation and Submission of as built drawings of total work executed (2 Sets hard and soft copy) | Nos | 1 |  |  |  | 1 |  |  | 100% | 1
12 | LIGHT FIXTURES
12.1 | Supply Installation of LED 2x2 Grid Light (Type-1) | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
12.2 | Supply Installation of LED Surface Mounted Type Light Fixtures (Type-2) | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
12.3 | Supply Installation of LED Round pendenat-1 Type Light Fixtures (Type-3) | Nos | 6 |  |  |  | 6 | 0% | 0 | 100% | 6
12.3 | Supply Installation of LED Round pendenat-2 Type Light Fixtures (Type-4) | Nos | 11 |  |  |  | 11 | 0% | 0 | 100% | 11
12.2 | Supply Installation of LED Recessed COB Type Light Fixtures (Type-5) | Nos | 5 |  |  |  | 5 | 0% | 0 | 100% | 5
12.2 | Supply Installation of LED Decorative Wall Light Fixtures (Type-6) | Nos | 5 |  |  |  | 5 | 0% | 0 | 100% | 5
12.2 | Supply Installation of LED Strip Light (Type-7) | Mtrs | 33.92 |  |  |  | 33.92 | 0% | 0 | 100% | 33.92
13 | UPS
a | Supply, Installation, Testing & Comissioning of: 5 KVA 1 Phase input/1 phase output UPS with 90 mins. Backup Battery Type: SMF with racks & enclouser (Output Power Factor Unity ) | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
IT
1.1 | 4-pair, Cat 6 UTP FRLS Cable | Mtrs | 182 |  |  |  | 182 | 50% | 87.5 | Balance PO Qty | 87.5
1.2 | Cat 6 UTP Information Outlet for Workstation end | Nos | 8 |  |  |  | 8 | 50% | 4 | 50% | 4
1.3 | Cat 6 RJ45-RJ45 UTP Patch Cords, color matched, Yellow - Workstation end, 7 ft | Nos | 8 |  |  |  | 8 | 50% | 4 | 50% | 4
1.4 | Single Face Plates | Nos | 0 |  |  |  | 0
1.5 | Dual Face Plates | Nos | 8 |  |  |  | 8 | 50% | 4 | 50% | 4
1.6 | Supply and fixing of Metal box suitable information outlet , flush/surface type in position .The rate shall exclude the cost of faceplate and Information Outlet. | Nos | 8 |  |  |  | 8 | 50% | 4 | 50% | 4
1.7 | Supply, installation, testing and Commissioning of RJ11 Telephone Point. The Telephone Socket shall be with face plate, GI BOX with accessories. | Nos | 0 |  |  |  | 0
1.8 | Cat 6 24 Port Angled Discrete Jack panel - fully loaded (1U).The rate shall include the cost of Patch Panel, Information Outlets with all the required supporting accessories. | Nos | 1 |  |  |  | 1 | 50% | 0.5 | 50% | 0.5
9 | 06 U wall mount rack with required mounting accessories, Rate shall include required accessories, tools etc., complete as required. | No | 1 |  |  |  | 1 | 50% | 0.5 | 50% | 0.5
CCTV
1 | Supply, installation, testing and Commissioning of UL approved, IP based Dome Indoor type 5MP,HD Dome camera | Nos | 5 |  |  |  | 5 | 50% | 2.5 | 50% | 2.5
2 | Supply, installation, testing and Commissioning of UL approved, Outdoor type 2MP Camera | Nos | RO
3 | Supply, installation, testing and Commissioning of 8 Channel NVR Ultra 4 K resolution and recording software with Storage capacity of 30Days .with all required accessories | No | 1 |  |  |  | 1 | 50% | 0.5 | 50% | 0.5
4 | CAT 6 PoE Cable, as per the survey done, Rate shall include required accessories, tools etc., complete as required. | Mtr | 116 |  |  |  | 116 | 50% | 50 | Balance PO Qty | 50
5 | Cat 6 Sngle Information Outlets including faceplates and backbox accessories. | Nos | 5 |  |  |  | 5 | 50% | 2.5 | 50% | 2.5
6 | Cat 6 12 Port Angled Discrete Jack panel - fully loaded (1U).The rate shall include the cost of Patch Panel, Information Outlets with all the required supporting accessories.(CCTV) | Nos | RO
7 | Cat 6, PoE 7ft Gigabit Snagless Molded Patch Cable (RJ-45 Male) with factory crimping, these patch cords will suffice for connecting between Data Outlet & CCTV | No | 0
8 | Cat 6, PoE 4ft Gigabit Snagless Molded Patch Cable (RJ-45 Male) with factory crimping, these patch cords will suffice for connecting between Data Outlet & CCTV (100%) | No | 5 |  |  |  | 5 | 50% | 2.5 | 50% | 2.5
9 | 05 U wall mount rack with required mounting accessories, Rate shall include required accessories, tools etc., complete as required. | No | RO
10 | PVC pipes
Supply and laying of 2 mm thick rigid FRLS PVC conduits in concealed conduit system using conduit accessories like junction boxes, collars, bends, elbows, binding wires, etc.
a | 32 mm dia conduit | Mtrs | RO
b | 25 mm dia conduit | Mtrs | RO
c | 19 mm dia conduit | Mtrs | RO
11 | GI pipes
Supply and laying of 2 mm thick rigid GI conduits in concealed/Open conduit system using conduit accessories like junction boxes, collars, bends, elbows, binding wires, etc.
a | 32 mm dia conduit | Mtrs | 0
b | 25 mm dia conduit | Mtrs | 36 |  |  |  | 36 | 0% | 0 | 100% | 36
c | 19 mm dia conduit | Mtrs | 40 |  |  |  | 40 | 0% | 0 | 100% | 40
12 | 1.5 meter length, Powder coated MS 25 mm dia Conduit supports for CCTV cameras with required supporting /mounting accessories complete. | No | RO
13 | Supervision, Programming, Testing & Commissioning, Documentation, Training. | LS | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
HVAC
1 | CHILLED WATER TYPE DOUBLE SKIN AIR HANDLING UNITS - CEILING SUSPENDED TYPE
Supply,Installation, Testing & Commissioning of Double skin type Ceiling suspended units complete with double skin (43±3 mm) insulated with CFC free polyurethane foam (PUF) panels of 40 +/- 2 Kg/cum density. The outer and inner panel thickness shall be 0.8 mm and 0.63 mm GI respectively. Outer skin shall be precoated/Powder Coated G.I. sheet and internal skin shall be Plain G.I. sheet suitable for chilled water application. The unit shall be provided with DIDW Fan, Motor, minimum 4 row cooling coil and drain pan with 15mm thick nitrile rubber insulation, inlet filter section with with 50mm thick panel type pre-filter of MERV-8 as part of CSU, drive set & guard, spring isolator to avoid transmission of vibration,etc. The noise of the unit shall not exceed more than 55-60 dBA at 1m distance from the unit and at maximum operating speed.The height of the unit shall not exceed 650mm. Additional FRP drain tray shall be considered for this units. Cooling Coil should be certified by AHRI 410
The unit shall be provided with belt driven backward curved Multi fans for achive the unit hight as not Exceed 650mm, IE3 Motor, drive package, vibration isolating rubber bush to fans and motor to avoid transmission of vibration. All CSU motor pulleys shall be of adjustable type only. Cost shall be inclusive of non-cloth type canvas connection made of self extinguishing, moisture resistant flexible fabric to be provided between CSU outlet flange and the supply duct / plenum.Spring isolators shall be used in the installation of the Ceiling suspended Units to ensure there is no transmission of vibration from the equipment to the building structure.
a | Supply. Installation,Testing & Commissioning of Double Skin CSU- Capacity-5 TR capacity, 1750 Dcfm with 0.325 sqm cooling cooling coil face area, 30 mmwg fan external static, 4/6 row cooling coil, 0.75/1.1 Kw fan motor, filter section with Pre Filter (EU-3)-MERV-8 supplied by the builder -Serving area: AJ Kitchen - Fine Dine | Set | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
b | Supply, Installation, Testing & commissioning of Limit switch wiring ,lighting & motor interlock to be provided with 3 core 2.5sqmm cable in 19mm dia GI conduit | Rmt | 24.5 |  |  |  | 24.5 | 0% | 0 | PO Qty | 20
2 | CHILLED WATER PIPING WITH INSULATION
Supply, Installation, Testing & commissioning of MS 'C' Class pipes insulated with Closed cell elastomeric insulation of specified thickness & Insulation to be covered with Aluminium cladding 26G , 0.5mm thick as per technical specification. All Bolts / Nuts used in the chilled water piping should be of GI & not MS. The cost shall be inclusive of pipe suppoorts with MS Channels. The piping flange connection bolts, washers and nuts should be hot dipped galvanised.The pipes should be supported with MS Channels, angle frame with neoprene rubber / PUF saddles. Fitting accessories for installation of pressure gauges, thermometers, BMS sensors, drain ports to be provided by the HVAC lowside contractor. Flourscent Plastic Sticker/ paint shall be applied to indicate Water flow directions. Only End flanges to be used for capping of pipes. "Table E" of BS code for flange thickness to be adhered. The Piping material & network should be selected to operate at PN 16 Rating
Pipe dia below 150 mm shall be C Class confirming to IS:1239 (part 1) 2004,Pipe size between 200 mm to 350 mm dia shall be 6.35 mm & pipe dia above 350 mm shall be 8.0 mm confirming to IS:3589 Gr330
Opening and closing for all the chilled pipe entries in civil / gypsum / any type of partition shall be under scope of HVAC vendor and inclusive of cost. Routing diagram can be checked in drawing prior for quoting.
a | 40 mm dia | Rmt | 0 |  |  |  | 0 | 0% | 0 |  | 0
b | 32 mm dia | Rmt | 21.4 |  |  |  | 21.4 | 0% | 0 | PO Qty | 20
3 | BUTTERFLY VALVE WITH INSULATION
Supply, Installation, Testing & commissioning of Wafer type Butterfly valve which shall be of Slim seal wafer type with long stem of PN 16 rating, companion flanges shall also be of PN20 rating. Butterfly valves installed for the chilled water pipelines shall be insulated with nitrile rubber insulation and the insulation thickness shall be similar to that of the pipe dimensions. (valve sizes above 200mm shall be wheel operated type instead of handles). All bolts, washers and nuts shall be hot dipped galvanized only.The MOC of body shall be cast iron & disk shall be epoxy coated ductile iron.
a | 40 mm dia | Nos | R.only |  |  |  |  | 0% | 0
b | 32 mm dia | Nos | 5 |  |  |  | 5 | 0% | 0 | 100% | 5
4 | PRESSURE INDEPENDENT TYPE DYNAMIC BALANCING CUM FLOW CONTROL VALVE.
Valve selection to be submitted in the technical submittal for approval before procurement.
Supply, Installation, Testing & commissioning of Pressure Independent dynamic balancing cum equal percentage type modulating flow control valve - PN16 rating fitted with high torque actuator with Non spring return type to ensure the valve closes automatically in the event of power disconnect to actuator. Actuator enclosure shall be rated for IP 54 protection. Step down transformer if required shall be part of valve supply, matching flanges, hot dipped galvanized bolts and nuts. Valve body to be insulated with closed cell elastomeric insulation. Supply , Installtion, testing & commissioning of thermostat along with control/ power cabling to be part of scope.The MOC of body shall be cast iron & membrane shall be EPDM, SS spring.
Actuator should be provided with position feed back switch and also actuator should have BMS interfacing card and shall be suitable for accepting signals from temperature sensors supplied by BMS vendor. Actuator should also have facility to set the required flow rate as per site requirements through dip switch adjustments. Valve body to be rated for PN 16. The valve design flow rate should be factory calibrated with +/- 5% flow accuracy. THe scope shall include the cost supply of thermostat/ return air temperature and required control cabling
Valve shall have necessary measuring ports, drain port, flanges etc., The balancing to be done through microprocessor based hand held terminal / POT and the same results shall be furnished in the water balancing report as part of commissioning report and handing over manual.
a | 40 mm dia | Nos | R.only |  |  |  |  | 0% | 0
b | 32 mm dia | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
5 | 2 WAY FLOW CONTROL VALVE.
Valve selection to be submitted in the technical submittal for approval before procurement.
Supply, Installation, Testing & commissioning of 2 Way- modulating flow control valve - PN16 rating fitted with high torque actuator with Non spring return type to ensure the valve closes automatically in the event of power disconnect to actuator. Actuator enclosure shall be rated for IP 54 protection. Step down transformer if required shall be part of valve supply, matching flanges, hot dipped galvanized bolts and nuts. Valve body to be insulated with closed cell elastomeric insulation. Supply , Installtion, testing & commissioning of thermostat along with control/ power cabling to be part of scope.The MOC of body shall be cast iron & membrane shall be EPDM, SS spring.
Actuator should be provided with position feed back switch and also actuator should have BMS interfacing card and shall be suitable for accepting signals from temperature sensors supplied by BMS vendor. Actuator should also have facility to set the required flow rate as per site requirements through dip switch adjustments. Valve body to be rated for PN 16. The valve design flow rate should be factory calibrated with +/- 5% flow accuracy. THe scope shall include the cost supply of thermostat/ return air temperature and required control cabling
Valve shall have necessary measuring ports, drain port, flanges etc., The balancing to be done through microprocessor based hand held terminal / POT and the same results shall be furnished in the water balancing report as part of commissioning report and handing over manual.
a | 40 mm dia | Nos | R.only |  |  |  |  | 0% | 0
b | 32 mm dia | Nos | R.only |  |  |  |  | 0% | 0
6 | TEMPERATURE SENSORS
| Supply, Installation, Testing & commissioning of Duct type/ space type temperature sensor for measuring the Return air temperature at the Chilled water type CSU Units (Range 45-150 deg. F).A Temperature sensor shall be provided in the return air path of CSU to control the 2 way modulating valve. The scope shall include the cost of Control Cabling with conduit between temperature sensor and actuator of 2 Way modulating flow control valve | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
7 | Y'-STRAINER WITH INSULATION
Supply, Installation, Testing & commissioning of Y-strainer -PN 16 rating body construction shall be with Mild steel and strainer shall be of SS screen with permanent magnet and drain port. The MOC of body shall be cast iron & SS-304 filter with 3 mm perforation with flanged connection, gaskets, permanent magnet. Note, the insulation quantity will be measured in running meters and the valve in numbers.
a | 40 mm dia | Nos | R.only |  |  |  |  | 0% | 0
b | 32 mm dia | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
8 | BALANCING VALVE WITH INSULATION
SITC of BALANCING VALVE (Manual Type) - PN16 Rating. Balancing valves installed for the chilled water pipelines shall be insulated with 25mm thick nitrile rubber insulation The valve should be with factory calibrated with +/- 5% flow accuracy. Provided with necessary measuring port, drain port, flanges hot dipped galvanized bolts, washers and nuts etc., The balancing to be done by portable hand held device and same result should be furnished in the handing over manual.The MOC of body shall be cast iron & the seat shall be EPDM, brass / SS cone.
a | 40 mm dia | Nos | R.only |  |  |  |  | 0% | 0
b | 32 mm dia | Nos | R.only |  |  |  |  | 0% | 0
9 | TEMPERATURE GUAGES
a | Supply, Installation, Testing & commissioning of Thermometer which shall be of Dial type (100mm) Range 0⁰ to 50⁰C, with stainless steel body - IP 55 protection, with necessary theromowells. | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
10 | PRESSURE GAUGE (GLYCERINE FILLED)
a | Supply, Installation, Testing & commissioning of Pressure Gauge which shall be of Bourdon tube Dial type (100mm) Range 0 to 10 kg/cm², with stainless steel body - IP55 protection with necessary pipe fitting and needle valve etc., | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
11 | INSULATED RIGID PVC PIPING FOR CONDENSATE DRAIN
Supply, Installation, Testing and Commissioning of Rigid PVC piping with pressure rating of 6 Kg /CM2 duly insulated with 9 mm thick factory laminated aluminium foil faced closed cell elastomeric nitrile rubber insulation with class 'O' fire retardant properties in tubing form & all fittings, elbows, tees reducers, supports and clamps up to 50 mm dia. including drilling, wall chipping etc. and conceal the wall opening. Pipes shall be of following sizes :
a | 65mm. Dia. | Rmt | 31.5 |  |  |  | 31.5 | 0% | 0 | PO Qty | 30
b | 50mm. Dia. | Rmt | 14.5 |  |  |  | 14.5 | 0% | 0 | PO Qty | 15
c | 40mm. Dia. | Rmt | 20 |  |  |  | 20 | 0% | 0 | 100% | 20
d | 32mm. Dia. | Rmt | 0 |  |  |  |  | 0% | 0
d | 25mm. Dia. | Rmt | 0 |  |  |  |  | 0% | 0
12 | AUTOMATIC AIR VENTS
a | Supply, Installation, Testing & commissioning of Automatic air vents to be provided at all high location of piping. The air vent to be provided with necessary ball valve. | Nos | 0 |  |  |  |  | 0% | 0
13 | DRAIN VALVES
Supply, Installation, Testing & commissioning of Ball/Drain valves with handles and extended stem , threaded joints shall be of PN16 class and insulated with nitrile rubber.The MOC of body shall be forged brass, SS ball, SS 410 stem. The end connections shall be threaded.
a | 25 mm dia | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
14 | GSS DUCT WORKS
FACTORY FABRICATED DUCTING - TDF /TDC FLANGES - RECTANGULAR DUCTWORKS
Supply, Installation, Testing & Commissioning of factory fabricated GSS Ducting with TDF /TDC flange with GI bolt & nuts (the cleat into the flange Used for C and G together with Bolt) and necessary supporting arrangement using GI full threaded rods and slotted rail- Unistrut channel supports of size 41mm x 41mm for rectangular ducts to be used
Ducting shall include guide vanes etc., Ducting shall be designed for 500pa ESP as per the specifications, GSS Ducting:- Galvanized steel sheet shall be of Class VIII – light coating of zinc, nominal 120 gm /sqm as per IS-277.All ducts 900 mm to 1100mm shall have Stiffener bracket made of GI 1.25mm thick sheet and 1101mm above shall have Stiffener bracket made of GI 1.6mm thick sheet with special profile for strength and rigidity fixed throughout the duct perimeter Intermediate between flanges with Fastener screws 2 nos for every interval of 150mm.
Spacing between duct supports should not exceed 2m i.e GI rods with GI "C" channels. In case of duct sizes above 1800mm, MS angles duly painted with black enamel paint should be used along with neoprene pad in between the duct & MS angle. All duct support to be provided with check nuts (lock nuts).
While selecting the duct supports vendor shall ensure vibration free installation. Quoted price shall be inclusive of light testing with complete arragement & accessories for leakages. Quoted price shall be inclusive of necessary scaffolding charges towards installation of supply/exhaust air ducts outside or within building wherever required. Quoted price should also include necessary charges towards duct supports including MS angle/channel arrangement as required for ducts being installed outside or within building wherever required.
All duct construction and installation shall be in accordance with SMACNA standards. In addition ducts shall be factory fabricated utilizing the following machines to provide the requisite quality of ducts.
a | 24 G-GSS-0.63MM ( 1MM TO 250MM) - C & SS | Sqm | 0 |  |  |  |  | 0% | 0
b | 24 G-GSS-0.63MM ( 251MM TO 1000MM) - TDF Flanges | Sqm | 108.4 |  |  |  | 108.4 | 0% | 0 | PO Qty | 105
c | 22 G-GSS-0.80MM ( 1001MM TO 1200MM) - TDF Flanges, Guide Vanes & Stiffeners Rods | Sqm | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
d | 20 G-GSS-1.00MM ( 1201MM TO 1300MM) - TDF Flanges, Guide Vanes & Stiffeners Rods | Sqm | 0 |  |  |  |  | 0% | 0
e | 18 G-GSS-1.25MM ( 1301MM TO Above) - TDF Flanges, Guide Vanes & Stiffeners Rods | Sqm | 0 |  |  |  |  | 0% | 0
15 | DUCT INSULATION MATERIALS
15.1 | THERMAL INSULATION FOR DUCTWORKS
Supply, Installation, Testing & Commissioning of Thermal insulation closed cell elastromeric nitrile rubber insulation manafactured as per ASTM E 84 test with density between 40-60 kg / m³(External and internal) for spiral duct, Material shall be FM GLOBAL approved, food grade material with antimicrobial properties, Class 'O'. Insulation material should meet NFPA 90A supplementary materials for air distribution system which should not absorbs less 0.2% water by volume (ASTM c 209), should not support microbial growth (ASTM C1071, G21, G22) and should emit objectionable odors (ASTM C 665) and should have thermal conductivity of 0.27 ( R - 2.78 in 3.4" thickness) and water vapor permeance of 0.10. Scope shall include the cost for aluminium foil which to be laid over the thermal insulation. Aluminium foil shall provide protection against scratches.
Insulation material shall be bonded with the ducts using metal screw and washers to facilitate grip to the GI sheet.Insulation materials brought on site should be installed following the manufacturer recommended methodology and using the appropriately suitable manufacturer recommended cutting, measuring, pasting tools & tackles. It is advised to use the manufacturer’s tool box for installation of insulation materials on site.
a | 9mm thick | Sqm | 0 |  |  |  |  | 0% | 0
b | 13mm thick | Sqm | 62.4 |  |  |  | 62.4 | 0% | 0 | 100% | 62.4
15.2 | ACOUSTIC INSULATION FOR DUCTWORKS
SITC of internal acoustic lining within air ducts plenum with open cell 10mm thick Elastromeric nitrile rubber insulation manafactured as per ASTM E 84 test with density140- 180 kg / m³, Material shall be FM rated as per the approved shop drawings / specifications. Insulation material should meet NFPA 90A supplementary materials for air distribution system which should not absorbs less 0.2% water by volume (ASTM c 209), should not support microbial growth (ASTM C1071, G21, G22) and should emit objectionable odors (ASTM C 665) and should have thermal conductivity of 0.27 ( R - 2.78 in 3.4" thickness) and water vapor permeance of 0.10. - Class "1" Material.
Insulation sheets should have self-adhesive backing for faster installation and better quality. The adhesive used in self-adhesive backing should be Fire Retardant, LEED compliant and zero VOC.
Insulation material shall be bonded with the ducts using metal screw and washers to facilitate grip to the GI sheet.Insulation materials brought on site should be installed following the manufacturer recommended methodology and using the appropriately suitable manufacturer recommended cutting, measuring, pasting tools & tackles. It is advised to use the manufacturer’s tool box for installation of insulation materials on site.
a | 10mm thick-acoustic insulation for main duct outlets as per HVAC drawings | Sqm | 6.85 |  |  |  | 6.85 | 0% | 0 | 100% | 6.85
b | 20mm thick-acoustic insulation for main duct outlets as per HVAC drawings | Sqm | 0 |  |  |  |  | 0% | 0
16 | AIR DISTRIBUTION DEVICES
16.1 | MANUAL TYPE VOLUME CONTROL DAMPERS
a | Supply, Installation, Testing & Commissioning of Volume Control Dampers made out of 100 x 40 x 1.55 mm thick galavanised steel frame and blades of 1.55 mm galavanised sheet steel. | Sqm | 0.7 |  |  |  | 0.7 | 0% | 0 | 100% | 0.7
16.2 | ALLUMINIUM COLLAR DAMPERS
a | Supply, Installation, Testing & Commissioning of Collar Dampers or neck damper of opposed blade type made out of Aluminium alloy extrusion with anodised matt black finish (AL.blade thickness 1.0mm, Border thickness-1.3 MM). Qty is for Supply air grilles | Sqm | 1.7 |  |  |  | 1.7 | 0% | 0 | 100% | 1.7
16.3 | CONTINUOUS LINEAR GRILLE
Supply, Installation , Testing & Commissioning of Extruded Al. powder coated continuous, discrete grilles for supply & return air distribution of 100 to 600 mm wide with 0 / 15 / 30 / 45 deg (AL.frame thickness 1.2MM, Louver thickness-3 MM). Deflection as specified In the approved shop drawings. Grilles complete with integral flanges on both sides & ends as required complete with corner pieces.( colour for the grill to be conifremed by Arch/ PMC team before placing the order)
a | 150mm wide | Nos | 21 |  |  |  | 21 | 0% | 0 | 100% | 21
16.4 | POWDER COATED ALUMINIUM GRILLES- FOR EXHAUST AIR & FRESH AIR APPLICATION
Supply, Installation , Testing & Commissioning of Extruded Al. powder coated grilles for exhuast air & Fresh air application with 0 degree deflection. AL.frame thickness 1.2MM, Louver thickness-1MM/ 3 MM ( colour for the grill to be conifimed by Arch/ PMC team before placing the order). The sizes of the grilles shall be as mentioned below
a | 600mm x 600mm | Nos | 3 |  |  |  | 3 | 0% | 0 | 100% | 3
b | 200mm x 200 mm | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
16.5 | 4 WAY SUPPLY AIR DIFFUSERS- SQUARE TYPE
Supply, Installation , Testing & Commissioning of Powder coated, extruded aluminium, removable center core type, supply air diffusers with Collar Dampers or neck damper of the following neck sizes.
(All are of 595 x 595 MM Outer to Outer Size)
b | 300 x 300 MM (Neck Size) | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
17 | ELECTROSTATIC DRY SCRUBBER FOR KITCHEN EXHAUST OF 3600 CFM.
Supply, installation, testing & Commissioning of Electro- Static DRY scrubber for the above exhaust rating of 3600 CFM. The vendor shall include the Pressure drop to be 20mm Wg, works with necessary valve arrangement. The scope of supply should include complete system for Electrostatic Dry scrubber operation. It shall also include the carbon filters for residual carbon content removal.The Electrostatic Air Cleaners shall be supplied as a one-piece factory joined assembly of individual section(s) selected to treat oil mist, smoke, fume, grease & dust/ powder problems.
Housing shall be constructed with minimum 1.6mm thick steel sheet with reinforced structure & powder coated to protect against rust and corrosion. It shall have a hinged door for cell access, located one side of the unit. The door shall be gasketed to prevent air leakage. There shall be a safety interlock switch to cut off primary supply when the access door is opened.The external finish shall be a durable industrial grade semi-gloss epoxy-polyester coating suitable for outdoor installations.
Ionizing-Collecting cell(s) shall be of one-piece construction 13.38” (340mm) deep in direction of airflow. The dimension of the collection cell shall be 18.89” (480mm) H x 19.76” (502mm)W Max. All support framing, end plates and ionizer ground electrodes shall be 0.080 inch (2mm) thick aluminum. Both repelling and collector plates shall be 0.032 inch (0.8mm) thick aluminum alloy material rigidly retained in place with tubular spacers and tie rods. Each plate shall be corrugated, perpendicular to airflow direction. Spacing between plates shall be no less than 0.318 inch (8mm). Each cell shall weigh at least 17 kg with at least 8 stainless steel spiked blade ionizers. Tungsten wire ionizers will not be accepted
Ionizing spiked blade shall be made of Stainless steel 304 material, rigidly supported both vertically and laterally. Spiked ionizer to ground electrode spacing shall be 1.0" (25mm). High voltage support insulators shall be of Teflon material for dielectric strength.
Equipment should be selected on the basis of required Air handling capacity so as to achieve 90-95% particulate matter removal efficiency according to DOP Test or EN779 European standard (Equivalent to ASHRAE 52.1). Vendor should submit the Test report from the Lab having Test facility according to ASHRAE 52.2 or EN779. In the absence of Test report Vendor should demonstrate the efficiency claim at their manufacturing facility at their expenses.
Power supplies shall be 100% solid state, operate on 230 VAC, 50 Hz, 1 Phase input and provide a dual high voltage output of 12-13 KVDC for the ionizer and 6.0-6.5 KVDC for the collector in normal operation conditions. Current output at the high tension shall be 12mA. A maximum power output for the solid state power supply shall be 120 watts to maintain the specified collection efficiency. Integrally mounted Electrical interlocks shall be provided to prevent access to the high voltage components without first interrupting the primary input power. The power supply shall operate over a temperature range of -32 degrees F to 140 degrees F, be overloaded self-protecting and accommodate an LED lights indicating the performance status of the ionizing/collecting cell. High voltage output components in the power supply shall be sealed with epoxy for moisture resistance.
The power pack shall incorporate a short circuit arc protection with automatic power restoration system to prevent overload.
There shall be 2 LED lights (Green & Red) installed on the access door of the unit to indicate the status of the air cleaning system
BMS (Building Management System) interface: The power supply (pack) shall have a 2 wire dry contacts (NO/NC) for remote link to Building Management System. This is for performance indication of the air cleaning system
| Supply , Installation , Testing & Commissioning of Electro-static Dry Scrubber unit complete with all sections as listed above & detailed in tender drawings | Nos | 1 |  |  |  | 1 | 50% | 0.5 | 50% | 0.5
FIRE ALARM SYSTEM
1 | FIRE Alarm System Works
1.1 | Supply installation testing and commissioning of addressable type smoke detectors with LED indication lamp, MS Back box, detector base braket, along with complete fixing accessories.(Above false ceiling) | Nos | RO |  |  |  | RO
1.2 | Supply installation testing and commissioning of addressable type smoke detectors with LED indication lamp, MS Back box, detector base braket, along with complete fixing accessories.(Below false ceiling) | Nos | 4 |  |  |  | 4 | 0% | 0 | 100% | 4
1.2a | Supply installation testing and commissioning of addressable type Multi Sensor Heat detectors with LED indication lamp, MS Back box, detector base braket, along with complete fixing accessories. | Nos | 3 |  |  |  | 3 | 0% | 0 | 100% | 3
1.3 | Supply installation testing and commissioning of Response indicators with complete fixing accessories for the detectors placed above false ceiling and below false flooring | Nos | RO |  |  |  | RO
1.4 | Supply installation testing and commissioning of addressable Hooter cum STROBE along with its control modules complete with all fixing materials. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
1.5 | Supply and installation of analogue addressable type Manual call points with Glass and hammer and monitor module with complete fixing accessories also with self illuminated signage. | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
1.6 | Supply and installation of Short circuit Fault Isolators @ 20 detectors with complete fixing accessories | Nos | RO |  |  |  | RO
1.7 | Supply and installation of Monitor Module with complete fixing accessories | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
1.8 | Supply and installation of Control Relay Module with complete fixing accessories | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
1.9 | Supply and laying of PVC insulated,2C x 1.5sq.mm shielded armored FRLS copper cable (RED COLUR) including cable glands and all fixing accessories where ever required complete with end terminations at both sides. The colour of the cable shall be RED only.( Shall be on actuals ). | Rmtrs | 48.3 |  |  |  | 48.3 | 0% | 0 | 100% | 48.3
1.10 | Supply, installation, testing and commissioning of Addressable fire alarm Panel which consists of display board which will have 160 Character Display with Touch key pad, Mother board which will have ARM CORTEX M3 32 Bit Processor, Inbuilt RS-485 Networking Circuit for peer to peer networking, Inbuilt USB 2.0 Port for upload and download the Configuration tools, Two inbuilt programmable inputs, Two inbuilt NAC's, and Three Programmable Relays, and 4 Loop Card circuits. power Supply, Installation and Commissioning Board which will have SMPS fully protected board, which its operates on 120 to 220V AC ± 10% with 50/60 Hz, battery backup 24V DC with built-in charger. the panel have IP-50 rating Optional: for BMS integration thru MODBUS converter, Graphical Software, Software for TCP/IP Module, provision for GSM based Auto dialler, provision for printer thru compatible module, fire alarm panel with battery backup for 6 hours operation, with battery charger, alarm bell, test buttons etc. | [5 empty] | 0 | 0% | 0 | 100% | 0
a | 2 loop panel | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
b | 4 loop panel | Nos | RO |  |  |  | RO
1.11 | SITC of Hand held Fire Extinguisher - ABC Powder - 6 Kg with floor mount accessories | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
1.12 | SITC of Hand held Fire Extinguisher - CO2 - 4.5 Kg with floor mount accessories | Nos | 2 |  |  |  | 2 | 0% | 0 | 100% | 2
1.13 | Supply installation testing and commissioning of Emergency Exit -LED Battery Backup(180Min) | Nos | 0 |  |  |  | 0 | 0% | 0 | 100% | 0
1.14 | Supply installation testing and commissioning of Fire Exit - LED Battery Backup (180Min) | Nos | 3 |  |  |  | 3 | 0% | 0 | 100% | 3
1.15 | Supply installation testing and commissioning of Exit - LED Battery Backup (180Min) | Nos | 0 |  |  |  | 0 | 0% | 0 | 100% | 0
2 | PA System Works
2.1 | Supply and installation testing and commissioning of 6 Watt 180mm dia Surface mounted white colour speakers along with all fixing accessories. | Nos | 0
2.2 | Supply and installation testing and commissioning of 6 Watt Recesse Mounted Ceiling speakers along with all fixing accessories . | Nos | 4 |  |  |  | 4 | 0% | 0 | 100% | 4
2.3 | Supply and laying of shielded twin twisted pair 1.0 sqmm cable in existing conduit ( Shall be on actuals ). | Rmtrs | 48.9 |  |  |  | 48.9 | 0% | 0 | 100% | 48.9
2.4 | Supply and fixing of 20mm dia heavy guage GI conduit concealed in wall/ above false ceiling for taking copper wires including all accessories such as Conduit junction boxes, bends etc as required ( Shall be on actuals ). | Rmtrs | 39.2 |  |  |  | 39.2 | 0% | 0 | 100% | 39.2
2.5 | Mixer Amplfier -240W with Pre recorded Message ,Music Ssytem etc complete in a PA rack (The rate to include the Cost of rack and other required acessories ) | Nos | RO |  |  |  | RO
2.6 | Mixer Amplfier -120W with Pre recorded Message ,Music Ssytem etc complete in a PA rack (The rate to include the Cost of rack and other required acessories ) | Nos | 1 |  |  |  | 1 | 0% | 0 | 100% | 1
FIRE SPRINKLER SYSTEM
3.1 | Supply, installation, testing and commissioning of G.I Heavy grade piping as per IS: 1239/3589 GI Forged Threaded GI forged socket welded & 65mm and above Seamless schedule 40) with necessary fittings such as tees, elbows,union,flanges, bends, rubber gaskets, reducers, GI nut bolt, washer etc. The pipes being suspended from ceilings by using support with clamps, hangers using anchor fastners upto 65 mm & above 80 mm pipe should be support with galvanized channel supports complete Rate quoted shall include painting with one coat of zinc cromet primer & 2 coats of synthetic enamel PO red paint and for painting of pipe & brackets and clamps as per IS-5 for above ground piping as per the NBC / IS standards and local fire service department requirement complete including supply and installation of G.I. Rods, clamps and , fasteners etc. All supports shall be hot dip galvanized in the range of DFT of micron 80 to 90 micron with 7 tank process, hot dip galvanizing shall be confirming to IS:2629/2633/4759/6745. Anchor fastners to be used of chemical type only where pipe supports to be taken from brick/block work.
a | 150mm nominal dia | Rmtrs | 0 |  |  |  |  | 0% | 0
b | 100mm nominal dia | Rmtrs | 0 |  |  |  |  | 0% | 0
c | 80mm nominal dia | Rmtrs | 0 |  |  |  |  | 0% | 0
d | 65mm nominal dia | Rmtrs | 0 |  |  |  |  | 0% | 0
e | 50mm nominal dia | Rmtrs | 0 |  |  |  |  | 0% | 0
f | 40mm nominal dia | Rmtrs | 0 |  |  |  |  | 0% | 0
g | 32mm nominal dia | Rmtrs | 4.2 |  |  |  | 4.2 | 0% | 0 | PO Qty | 3
h | 25mm nominal dia | Rmtrs | 32.1 |  |  |  | 32.1 | 0% | 0 | PO Qty | 30
3.2 | Supplying, installing, testing and commissioning conventional Standard Response Sprinkler quartzoid bulb type with 15mm screwed end connection of 68 deg. C. temperature rating, K-Factor =5.6 GPM/psi½ (80.6 LPM/bar½) and orifice shall not be less than 6mm. Sprinklers shall be UL Listed / BIS approved with Chrome finished.
a | Pendent Sprinkler | Nos | RO |  |  |  |  | 0% | 0
b | Upright Sprinkler | Nos | RO |  |  |  |  | 0% | 0
b | Concealed Sprinkler | Nos | 16 |  |  |  | 16 | 0% | 0 | 100% | 16
3.3 | Stainless steel corrugated flexible pipe(hose) for dropping sprinklers below false ceiling, pipe shall be 16 bar pressure rating and 1500 mm long, 25 mm dia with union / reducer collar, clamps etc. as required. | Nos | 16 |  |  |  | 16 | 0% | 0 | 100% | 16
3.4 | Supply & fixing of approved type rosette plates (Recessed type, in two piece) for Sprinklers below false ceiling area. | Nos | 16 |  |  |  | 16 | 0% | 0 | 100% | 16
3.5 | Supply and Installation, Testing and Commissioning of CI butterfly valves (body conforming to IS 210 GR FG 200) slim seal standard lever operated type conforming to IS13039/BS5155 with required flanges, nuts, bolts etc complete with supervisory tamper switch for monitoring. The valves shall be suitable for 150 psi pressure rating. Tamper Switch equipped with 2 Nos. of NO-NC contacts for monitoring
a | 100 mm dia | Nos | 0 |  |  |  |  | 0% | 0
b | 80 mm dia | Nos | 0 |  |  |  |  | 0% | 0
c | 65 mm dia | Nos | 0 |  |  |  |  | 0% | 0
3.6 | Fire Sprinkler Pipe Modifictaion Works (Extending the branch pipe as per proposed Interior layout wherever required and removal of existing rigid dropers) | Lot | 0 |  |  |  |  | 0% | 0
| Measurement Taken By |  |  | Measurement Certified By
| Name & Sign of Vendor |  | Name & Sign of Site In Charge

## Abstract - Costing Diff. (hidden)
ANNEXURE -1
WO No :-5700338947 | [9 empty] | Date:- 30-04-2024
CAR No :-01
Civil & Interior work for Office 1 , 2 & Briefing Room at JCC Office at Level 3 at T2
SECTION: A
SR.NO. | SERVICE CODE | DESCRIPTION | UNIT | PO QTY | PO RATE (Rs) | PO AMOUNT (Rs) | REV QTY | CLAIMABLE QTY | RATE (Rs) | CLAIMABLE AMOUNT (Rs) | NEW RATE | RATE DIFFERENCE | AMOUNT DIFFERENCE | REMARKS
RA - 1 (Current Bill)
2 | 99992504 | Dismantling Dry cladding/Finishes cladding and stacking of serviceable material at MLCP level P2 as directed by engineer incharge | sqm | 250 | 400 | 100000 | #NAME? | #NAME? | 400 | #NAME?
3 | 120021037 | Demolishing brick work/block work including stacking of serviceable material and disposal of unserviceable material within 500 metres lead:a) In cement mortar | cum | 40 | 2000 | 80000 | #NAME? | #NAME? | 2000 | #NAME?
4 | 99992505 | Dismantling aluminium/Gypsum partitions/ply/double skinned bison board with frame, doors,windows, fixed glazing and false ceiling including disposal of unserviceable surplus material and stacking of serviceable material within 500 metres lead as directed by Engineer-in- charge. | sqm | 170 | 750 | 127500 | #NAME? | #NAME? | 750 | #NAME?
5 | 99992135 | Removing metal and wooden door with all its hardware and stacking the same in T2 MLCP as directed by engineer in charge | no | 4 | 2500 | 10000 | #NAME? | #NAME? | 2500 | #NAME?
7 | 120020484 | Demolishing RCC structure /slab,beam,lintel column etc including taking away the reinforcement Rate to offset for credit of steel | cum | 10 | 2800 | 28000 | #NAME? | #NAME? | 2800 | #NAME?
9 | 170002645 | Disposal of building rubbish/malba from building premises from airside,inside building and city side by mechanical transport including loading,unloading etc. and disposal outside the airport premises. | cum | 120 | 1500 | 180000 | #NAME? | #NAME? | 1500 | #NAME?
10 | 120014430 | Providing and constructing Brick/Solid Block for 150MM thick walls till R.C.C slab lvl using in cement mortar 1:4, using 2 nos. with 1:6 CM 12mm thk plastered and finished to match the existing wall. The junction of existing & new wall or brick wall and RCC surface to be plastered after placing wiremesh 6" wide on either side. The block should be of minimum compressive strength of 35 Kg/ sqcm. Rate to be inclusive of filling of voids created by chasing of walls for water supply and electrical works with appropriate material as directed, etc. complete. | cum | 52 | 10000 | 520000 | #NAME? | #NAME? | 10000 | #NAME?
14 | 120020788 | cutting the groove upto 50 mm wide in wall and floor for cable conduits and refiliing it with cement mortar 1:3 and finishing etc complete as directed by engineer incharge | m | 50 | 500 | 25000 | #NAME? | #NAME? | 500 | #NAME?
18 | 90130834 | Providing and fixing 100mm thk gypboard partition from India gypsum with 50mm x 50mm aluminium frame @ 600mm distance vertically & horizontally center to center. The frame shall be rigidly fixed between floor and ceiling. The same shall be filled with 50mm thk. rock wool 48KG/m3 density (1000GSM) for sound insulation and covered with black color kora cloth & shall be finished with double layer 12mm thk gypsum board on both sides. shall be finished with proper grooves, skirting etc,. see detail drawing. not to be painted in the areas above the false ceiling & below false floor. | sqm | 215 | 2300 | 494500 | #NAME? | #NAME? | 2300 | #NAME?
20 | 90132182 | Providing and fixing of Fluted acoustic panel cladding with 12mm thk fluted acoustic panel from Vividha or equivalent with 12mm thk ply backing. A 6x6mm groove shall be made between acoustic panel and gypboard in the gypboard and finished with 6x6mm aluminium c-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the acoustic panel shall not have any gypboard. Panel shall have 0.5 NRC. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing | sqm | 17 | 4200 | 71400 | #NAME? | #NAME? | 4200 | #NAME? | 4800 | 600 | #NAME? | 0.9 NRC USED INSTEAD OF 0.5 NRC
21 | 90100402 | Providing & fixing of 6mm thk white lacquered glass with 6mm thk ply backing to be fitted directly on the framework of the gypsum partition so that the glass is in flush lvl with the gypboard. A 6x6mm groove shall be made between glass and gypboard in the gypboard and finished with 6x6mm aluminium C/T-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the glass shall not have any gypboard. | sqm | 31 | 6200 | 192200 | #NAME? | #NAME? | 6200 | #NAME? | 6800 | 600 | #NAME? | 12MM PLY USED INSTEAD OF 6MM
22 | 170002758 | Providing and fixing 12mm thk soft board to be fitted above 6mm ply with rounded edge on all sides to stretch the fabric properly. soft board shall be fitted above table skirting upto same ht as writing board. there shall be a 6mm groove fitted with aluminium channel between softboard and skirting and shall run all round the softboard. .Color of the fabric to be selected. samples to be shown. skirting shall be made of 19mm thk ply and finished with laminate same as table top. softboard shall be in flush level with gypboard partition. see detail in typical details sheet. | sqm | 33 | 1800 | 59400 | #NAME? | #NAME? | 1800 | #NAME? | 2400 | 600 | #NAME? | 12MM PLY USED INSTEAD OF 6MM
25 | 99992398 | Providing and fixing 600x600mm ceramic tile dado of KAJARIA make or equivalent for wall above pantry counter upto 600mm ht as per the drawing. Shall be provided with suitable white cement backing on existing surface, with colour cement finishing including dilute acid. Epoxy joint filler to be used in the joint between tiles.(See Toilet details) | sqm | 2.5 | 2400 | 6000 | #NAME? | #NAME? | 2400 | #NAME?
26 | 90132182 | Providing and fixing of acoustic panel cladding with 12mm thk acoustic panel from Vividha or equivalent with 12mm thk ply backing. A 6x6mm groove shall be made between acoustic panel and gypboard in the gypboard and finished with 6x6mm aluminium c-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the acoustic panel shall not have any gypboard. Panel shall have 0.5 NRC. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing | sqm | 18 | 4200 | 75600 | #NAME? | #NAME? | 4200 | #NAME? | 4800 | 600 | #NAME? | 0.9 NRC USED INSTEAD OF 0.5 NRC
28 | 170002757 | Base cabinet shall be made of 19mm BWP ply with 2400MM x 600mm depth and 825mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. counter top shall be finished with 19mm thk granite as per selection with 19mm thk BWP ply base. Kitchen sink of Franke or equivalent. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, 75mm high & 75mm recessed skirting, etc. refer detail drawing. | sqm | 2.4 | 15000 | 36000 | #NAME? | #NAME? | 15000 | #NAME?
29 | 170002757 | Overhead cabinet shall be made of 19mm BWP ply with 2400MM x 300mm depth and 750mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, etc. refer detail drawing. | sqm | 2 | 15000 | 30000 | #NAME? | #NAME? | 15000 | #NAME?
48 | 90131332 | SILHOUETTE GRID CEILING :Providing and fixing in true horizontal level false ceiling grid of SILHOUTTE GRID 15mm using hot dipped galvonized steel section, Exposed surface chemically cleaned capping prefinished in baked polyster paint, main Tee of size 15 x 44 x 0.3 at every 1200 mm C/C max and rotary stiched Croos Tee of size 15 x 44 x 0.3 mm at every 1200 mm centrally between the 1200mm cross tees and 18 x 18 x 0.5 mm Wall angles all round the the wall to form a grid of size 600 mm x 600mm and suspended the grid using suitable rigid hangers at every 1200 mm intervals at the Main ' T ' and laying tile with edge CONSTILATION TILE of size 600 x 600 x 15 mm over the formed grid., Tile Specs; NRC of the tile to 0.9 ,Class 1 FIRE PERFORMANCE AND HUMIDITY RESISTANCE RH 99 %.The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. | sqm | 2 | 3500 | 7000 | #NAME? | #NAME? | 3500 | #NAME?
49 | 90132107 | Providing and fixing Linear metal ceiling tiles of size 1200,1500 & 1800mm x 150mm, thickness of 15mm with galvanised steel grid system, as per vendor detail and specification. From Armstrong/Tranquil or equivalent. | sqm | 45 | 3500 | 157500 | #NAME? | #NAME? | 3500 | #NAME?
50 | 90132185 | AOUSTIC BAFFLE CEILING - Providing and fixing in true horizontal level false ceiling using 50X100MM Extruded aluminium sections arranged at100mmc/c. The sections to be wrapped with acoustic panles and finished as per architects approval. The cost shall include all necessary hardwares as per vendor specifications | sqm | 34 | 6600 | 224400 | #NAME? | #NAME? | 6600 | #NAME? | 6200 | -400 | #NAME? | USED EXISTING SUPPORT
55 | 99992174 | FALSE FLOORING - Providing & Fixing of UNITILE OR EQUIVALENT CEMENTATIOUS INFILL TILE raised flooring system with necessary metal framework (GI/Epoxy coated) as per site requirements. The understructure shall be capable of level adjustment of ±50mm. The flooring to also include thermal insulation (15mm Armaduct Insulation) | sqm | 3 | 8500 | 25500 | #NAME? | #NAME? | 8500 | #NAME?
57 | 99992385 | To prepare & finish 3 coats of tractor emulsion paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of tractor emulsion paint, touching up with putty & applying two final roller coats of tractor emulsion paint, to internal wall/ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. | sqm | 455 | 360 | 163800 | #NAME? | #NAME? | 360 | #NAME?
94 | 99992409 | Fire line GYPBOARD FALSE CEILING- Providing and fixing MF suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. Metal expanded rawl plugs shall be bolted to the beam/deck slab and suspenders of the required length shall be provided using GI hangers. Metal expanded rawl plugs and suspenders are to be positiioned at such spacing so that the runner when connected shall have support not exceeding 4' intervals. Main runners coonsisting of GI intermediate channels shall be provided at not exceeding 4' centre in one direction and connected to the suspenders with GI bolts and nuts. GI ceiling channels shall be placed in the opposite direction to the Intermediate channel at not exceeding 2' centres and connected to the intermediate channel using special connecting clips. Gi perimeter channel shall be fixed along the periphery walls, columns, etc. and the ceiling channel shall be inserted and screwed to this perimeter channel. | sqm | 121 | 2400 | 290400 | #NAME? | #NAME? | 2400 | #NAME? | 2150 | -250 | #NAME? | EXISTING MAIN SUPPORT FOR BRIEFING ROOM & OFFICE 1 CABIN
96 | 90132185 | ACOUSTIC CEILING - Providing and fixing acoustic suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. ceiling shall be finished with 12mm thk acoustic panel with 0.9 NRC rating with 12mm thk ply backing. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. | sqm | 25 | 6500 | 162500 | #NAME? | #NAME? | 6500 | #NAME? | 6100 | -400 | #NAME?
[8 empty] | TOTAL |  | #NAME? |  |  | #NAME?
[8 empty] | 18% GST |  | #NAME?
[8 empty] | GROSS TOTAL |  | #NAME?

## DIS (hidden)
ANNEXURE -1
WO No :-5700338947 | [8 empty] | Date:- 30-04-2024
CAR No :-01
Civil & Interior work for Office 1 , 2 & Briefing Room at JCC Office at Level 3 at T2
SECTION: A (DEVIATED ITEMS)
SR.NO. | SERVICE CODE | DESCRIPTION | UNIT | PO QTY | PO RATE (Rs) | PO AMOUNT (Rs) | REV QTY | REV RATE (Rs) | REV AMOUNT (Rs) | VARIATION{(+)/(-)} |  | REMARKS
[10 empty] | QTY. | AMOUNT (Rs)
1 | 230002422 | Providing and fixing temporary site barricading, with wooden runners of size 50mm x50mmas a basic framework and cladding with 6mm plywood.The barricades shall be pasted with printed artwork vinyl on outside.The material will be contractors property after its usage as a barricade.Cost to include dismantalling also. upto a height of 4.5. m | sqm | 84 | 1800 | 151200 | #NAME? | 1800 | #NAME? | #NAME? | #NAME?
2 | 99992504 | Dismantling Dry cladding/Finishes cladding and stacking of serviceable material at MLCP level P2 as directed by engineer incharge | sqm | 250 | 400 | 100000 | #NAME? | 400 | #NAME? | #NAME? | #NAME?
3 | 120021037 | Demolishing brick work/block work including stacking of serviceable material and disposal of unserviceable material within 500 metres lead:a) In cement mortar | cum | 40 | 2000 | 80000 | #NAME? | 2000 | #NAME? | #NAME? | #NAME?
4 | 99992505 | Dismantling aluminium/Gypsum partitions/ply/double skinned bison board with frame, doors,windows, fixed glazing and false ceiling including disposal of unserviceable surplus material and stacking of serviceable material within 500 metres lead as directed by Engineer-in- charge. | sqm | 170 | 750 | 127500 | #NAME? | 750 | #NAME? | #NAME? | #NAME?
5 | 99992135 | Removing metal and wooden door with all its hardware and stacking the same in T2 MLCP as directed by engineer in charge | no | 4 | 2500 | 10000 | #NAME? | 2500 | #NAME? | #NAME? | #NAME?
6 | 99992504 | Dismantling existing SS skirting | rmt | 90 | 110 | 9900 | #NAME? | 110 | #NAME? | #NAME? | #NAME?
7 | 120020484 | Demolishing RCC structure /slab,beam,lintel column etc including taking away the reinforcement Rate to offset for credit of steel | cum | 10 | 2800 | 28000 | #NAME? | 2800 | #NAME? | #NAME? | #NAME?
8 | 99992262 | Demolishing of flooring tile with mortar | sqm | 170 | 650 | 110500 | #NAME? | 650 | #NAME? | #NAME? | #NAME?
9 | 170002645 | Disposal of building rubbish/malba from building premises from airside,inside building and city side by mechanical transport including loading,unloading etc. and disposal outside the airport premises. | cum | 120 | 1500 | 180000 | #NAME? | 1500 | #NAME? | #NAME? | #NAME?
10 | 120014430 | Providing and constructing Brick/Solid Block for 150MM thick walls till R.C.C slab lvl using in cement mortar 1:4, using 2 nos. with 1:6 CM 12mm thk plastered and finished to match the existing wall. The junction of existing & new wall or brick wall and RCC surface to be plastered after placing wiremesh 6" wide on either side. The block should be of minimum compressive strength of 35 Kg/ sqcm. Rate to be inclusive of filling of voids created by chasing of walls for water supply and electrical works with appropriate material as directed, etc. complete. | cum | 52 | 10000 | 520000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
11 | 120008655 | Lintels shall be precast and it should be casted at ground level. Lintel shall be lifted by crane at relevant location, Rate shall include above all activities including lift, lead, casting, shuttering, leaving dowels for chajja etc. | no | 10 | 17000 | 170000 | #NAME? | 17000 | #NAME? | #NAME? | #NAME?
12 | 120020797 | Supplying, fabrication and erection of strucutre steel including plate cutting, assembling hoisting and fixing for helipad, etc in position to alignments and levels and painting / other protection of steelwork for structures including fixtures, fittings, temporary works and supports, and ancillaries. Including fabricated out of rolled steel sections , plates, hollow sections, pipes, cast steel, forgings etc and may involve any or combination of two or more of these in sizes, quantity and quality as specified in the drawings or as directed by the Employer’s Representative . steelwork consist of all types such as columns, beams, trusses, wall beams, girders, brackets, base-plates, floorings, anchors, any other kind as shown in the drawings. | kg | 1000 | 160 | 160000 | #NAME? | 160 | #NAME? | #NAME? | #NAME?
13 | 220013144 | Supply and installation of 16 mm dia and 200mm long Hilti bolts with RE500V4 chemical | NO.S | 50 | 1250 | 62500 | #NAME? | 1250 | #NAME? | #NAME? | #NAME?
14 | 120020788 | cutting the groove upto 50 mm wide in wall and floor for cable conduits and refiliing it with cement mortar 1:3 and finishing etc complete as directed by engineer incharge | m | 50 | 500 | 25000 | #NAME? | 500 | #NAME? | #NAME? | #NAME?
15 | 93011022 | Supply and installation of fully straight single glazed door using 10mm thick toughened glass and fixed with proprietary anodised aluminium WIDE LINE sections of size 100mm x 25mm as per architects approval. Rate to include required accessories as per the manufacturers specifications and shall be inclusive of all accessories like rubber gasket etc.,. Glass panels to be of maximum sizes and it should be executed strictly as per detailed drawings / elevations and as per architects approval. Partition with more number of glass pieces are not advised. Rate to include providing & fixing of necessary G.I./wooden/MS frame supports for the above doors, fixtures & additional suspenders etc., complete as per architects / PM's instruction or approval. Tested in an accredited laboratory as per ASTM/ISO standards. Partition to floor/ceiling junctions shall be sealed with acoustic sealant. To have 12mm thk MDF finished with paint of approved shade to be provided all around on junctions of modular door frames & partitions (All around horizontally and vertically)Height of 2400mm. Size 1050x2400mm.Glass shall have 50% area under frosting. Cost to include frosting. Cost shall include all hinges, handles, hardware and accesories.Vendor to share shop drawings for architect approval. | NO.S | 4 | 25000 | 100000 | #NAME? | 25000 | #NAME? | #NAME? | #NAME?
16 | 93011022 | Supply and installation of fully straight single glazed door using 10mm thick toughened glass and fixed with proprietary anodised aluminium WIDE LINE sections of size 100mm x 25mm as per architects approval. Rate to include required accessories as per the manufacturers specifications and shall be inclusive of all accessories like rubber gasket etc.,. Glass panels to be of maximum sizes and it should be executed strictly as per detailed drawings / elevations and as per architects approval. Partition with more number of glass pieces are not advised. Rate to include providing & fixing of necessary G.I./wooden/MS frame supports for the above doors, fixtures & additional suspenders etc., complete as per architects / PM's instruction or approval. Tested in an accredited laboratory as per ASTM/ISO standards. Partition to floor/ceiling junctions shall be sealed with acoustic sealant. To have 12mm thk MDF finished with paint of approved shade to be provided all around on junctions of modular door frames & partitions (All around horizontally and vertically)Height of 2400mm. Size 900x2400mm.Glass shall have 50% area under frosting. Cost to include frosting. Cost shall include all hinges, handles, hardware and accesories.Vendor to share shop drawings for architect approval. | NO.S | 3 | 24000 | 72000 | #NAME? | 24000 | #NAME? | #NAME? | #NAME?
17 | 93011022 | Supply and installation of fully straight single glazed door using 10mm thick toughened glass and fixed with proprietary anodised aluminium WIDE LINE sections of size 100mm x 25mm as per architects approval. Rate to include required accessories as per the manufacturers specifications and shall be inclusive of all accessories like rubber gasket etc.,. Glass panels to be of maximum sizes and it should be executed strictly as per detailed drawings / elevations and as per architects approval. Partition with more number of glass pieces are not advised. Rate to include providing & fixing of necessary G.I./wooden/MS frame supports for the above doors, fixtures & additional suspenders etc., complete as per architects / PM's instruction or approval. Tested in an accredited laboratory as per ASTM/ISO standards. Partition to floor/ceiling junctions shall be sealed with acoustic sealant. To have 12mm thk MDF finished with paint of approved shade to be provided all around on junctions of modular door frames & partitions (All around horizontally and vertically)Height of 2400mm. Size 900x2400mm.Glass shall have 50% area under frosting. Cost to include frosting. Cost shall include all hinges, handles, hardware and accesories.Vendor to share shop drawings for architect approval. | NO.S | 1 | 24000 | 24000 | #NAME? | 24000 | #NAME? | #NAME? | #NAME?
18 | 90130834 | Providing and fixing 100mm thk gypboard partition from India gypsum with 50mm x 50mm aluminium frame @ 600mm distance vertically & horizontally center to center. The frame shall be rigidly fixed between floor and ceiling. The same shall be filled with 50mm thk. rock wool 48KG/m3 density (1000GSM) for sound insulation and covered with black color kora cloth & shall be finished with double layer 12mm thk gypsum board on both sides. shall be finished with proper grooves, skirting etc,. see detail drawing. not to be painted in the areas above the false ceiling & below false floor. | sqm | 215 | 2300 | 494500 | #NAME? | 2300 | #NAME? | #NAME? | #NAME?
19 | 90130704 | Supply and installation of fully straight single glazed partition using 10mm thick toughened glass and fixed with proprietary anodised aluminium WIDE LINE sections of size 100mm x 25mm as per architects approval. Rate to include required accessories as per the manufacturers specifications and shall be inclusive of all accessories like rubber gasket etc.,. Glass panels to be of maximum sizes and it should be executed strictly as per detailed drawings / elevations and as per architects approval. Partition with more number of glass pieces are not advised. RATE NOT TO INCLUDE DOOR FRAMES. Rate to include 'I' section, 'L' section, 'T' section & capping at the junction of gypsum partitions & glazed partitions. The glass to glass joints to be bonded with " I section" and 3M VHB double side tape with room temperature and dust free. Rate to include providing & fixing of necessary G.I./wooden/MS frame supports for the above doors, fixtures & additional suspenders etc., complete as per architects / PM's instruction or approval. Tested in an accredited laboratory as per ASTM/ISO standards. Partition to floor/ceiling junctions shall be sealed with acoustic sealant. To have 12mm thk MDF finished with paint of approved shade to be provided all around on junctions of modular door frames & partitions (All around horizontally and vertically)Height of 2400mm. 50% of glass shall be under frosting. Cost shall include frosting. Vendor to share shop drawings for architect approval. | sqm | 54 | 6800 | 367200 | #NAME? | 6800 | #NAME? | #NAME? | #NAME?
20 | 90132182 | Providing and fixing of Fluted acoustic panel cladding with 12mm thk fluted acoustic panel from Vividha or equivalent with 12mm thk ply backing. A 6x6mm groove shall be made between acoustic panel and gypboard in the gypboard and finished with 6x6mm aluminium c-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the acoustic panel shall not have any gypboard. Panel shall have 0.5 NRC. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing | sqm | 17 | 4200 | 71400 | #NAME? | 4200 | #NAME? | #NAME? | #NAME?
21 | 90100402 | Providing & fixing of 6mm thk white lacquered glass with 6mm thk ply backing to be fitted directly on the framework of the gypsum partition so that the glass is in flush lvl with the gypboard. A 6x6mm groove shall be made between glass and gypboard in the gypboard and finished with 6x6mm aluminium C/T-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the glass shall not have any gypboard. | sqm | 31 | 6200 | 192200 | #NAME? | 6200 | #NAME? | #NAME? | #NAME? | Ply backing is 12mm istead of 6mm
22 | 170002758 | Providing and fixing 12mm thk soft board to be fitted above 6mm ply with rounded edge on all sides to stretch the fabric properly. soft board shall be fitted above table skirting upto same ht as writing board. there shall be a 6mm groove fitted with aluminium channel between softboard and skirting and shall run all round the softboard. .Color of the fabric to be selected. samples to be shown. skirting shall be made of 19mm thk ply and finished with laminate same as table top. softboard shall be in flush level with gypboard partition. see detail in typical details sheet. | sqm | 33 | 1800 | 59400 | #NAME? | 1800 | #NAME? | #NAME? | #NAME? | Ply backing is 19mm istead of 6mm
23 | 90130832 | Providing and fixing wallpaper as per architect approval. Wall to be leveled properly to recieve the wallpaper. Installation will be contractors responsibility. care shall be taken for air bubbles not to form and joints shall not be visible. measurement will be given only on the laid area. Basic rate: 90rs/sft | sqm | 41 | 140 | 5740 | #NAME? | 140 | #NAME? | #NAME? | #NAME?
24 | 100000391 | Providing and fixing vinyl stickering as per architect approval. installation will be contractors responsibility. care shall be taken for air bubbles not to form and joints shall not be visible. measurement will be given only on the laid area. | sqm | 12 | 2500 | 30000 | #NAME? | 2500 | #NAME? | #NAME? | #NAME?
25 | 99992398 | Providing and fixing 600x600mm ceramic tile dado of KAJARIA make or equivalent for wall above pantry counter upto 600mm ht as per the drawing. Shall be provided with suitable white cement backing on existing surface, with colour cement finishing including dilute acid. Epoxy joint filler to be used in the joint between tiles.(See Toilet details) | sqm | 2.5 | 2400 | 6000 | #NAME? | 2400 | #NAME? | #NAME? | #NAME?
26 | 90132182 | Providing and fixing of acoustic panel cladding with 12mm thk acoustic panel from Vividha or equivalent with 12mm thk ply backing. A 6x6mm groove shall be made between acoustic panel and gypboard in the gypboard and finished with 6x6mm aluminium c-channel from bottom line or equivalent. see detail drawing.Note: area of the partition covered by the acoustic panel shall not have any gypboard. Panel shall have 0.5 NRC. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing | sqm | 18 | 4200 | 75600 | #NAME? | 4200 | #NAME? | #NAME? | #NAME?
27 | 90131175 | CABIN DESK - 1500mmx 675mm x750mm Ht- Table top - 25mm thick Pre-laminate particle board finished with 2mm edge lipping on the other two sides Supports – MS powder coated 50mm Square MS perform series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top | NOS | 3 | 8500 | 25500 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
28 | 170002757 | Base cabinet shall be made of 19mm BWP ply with 2400MM x 600mm depth and 825mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. counter top shall be finished with 19mm thk granite as per selection with 19mm thk BWP ply base. Kitchen sink of Franke or equivalent. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, 75mm high & 75mm recessed skirting, etc. refer detail drawing. | sqm | 2.4 | 15000 | 36000 | #NAME? | 15000 | #NAME? | #NAME? | #NAME?
29 | 170002757 | Overhead cabinet shall be made of 19mm BWP ply with 2400MM x 300mm depth and 750mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, etc. refer detail drawing. | sqm | 2 | 15000 | 30000 | #NAME? | 15000 | #NAME? | #NAME? | #NAME?
30 | 90131175 | Linear Workstation Size : 1650 x 1650x 1200 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping on the other two sides Screen : 30mm split screen ( fabric magnetic & glass marker ) , 30mm thick with aluminum anodised trim ( 1500 x 300ht ) fabric on longer side and glass marker on shorter side. Supports – MS powder coated 50mm Perform Series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top CPU trolley on castors for the above | NOS | 5 | 18000 | 90000 | #NAME? | 18000 | #NAME? | #NAME? | #NAME?
31 | 99992776 | Pedestal ( 2D + 1 F ) - with Cushion top Size : 450 x 450 x 600ht Top: 18mm Thk pre laminated particle board Back: 9mm Thk pre laminated particle board with 2mm PVC edge lipping Shutters: 18mm Thk pre laminated particle board Edge: All exposed area with 2mm thick PVC edge lipping Handle: Finger groove handles Lock: Regular lock | NOS | 5 | 5000 | 25000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
32 | 90131175 | Linear Workstation Size : 3200 x 600x 750 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping on the other two sides Screen : 30mm split screen ( fabric magnetic & glass marker ) , 30mm thick with aluminum anodised trim ( 1500 x 300ht ) fabric on longer side and glass marker on shorter side. Supports – MS powder coated 50mm Perform Series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top PVC Keyboard tray with a mouse pad CPU trolley on castors for the above | NOS | 1 | 22500 | 22500 | #NAME? | 22500 | #NAME? | #NAME? | #NAME?
33 | 99992776 | Pedestal ( 2D + 1 F ) - with Cushion top Size : 400 x 450 x 600ht Top: 18mm Thk pre laminated particle board Back: 9mm Thk pre laminated particle board with 2mm PVC edge lipping Shutters: 18mm Thk pre laminated particle board Edge: All exposed area with 2mm thick PVC edge lipping Handle: Finger groove handles Lock: Regular lock | NOS | 3 | 5000 | 15000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
34 | 90131175 | Linear Workstation Size : 1200 x 600x 750 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping on the other two sides Screen : 30mm split screen ( fabric magnetic & glass marker ) , 30mm thick with aluminum anodised trim ( 1500 x 300ht ) fabric on longer side and glass marker on shorter side. Supports – MS powder coated 50mm Perform Series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top CPU trolley on castors for the above PVC Keyboard tray with a mouse pad | NOS | 10 | 7100 | 71000 | #NAME? | 7100 | #NAME? | #NAME? | #NAME?
35 | 99992776 | Pedestal ( 2D + 1 F ) - with Cushion top Size : 400 x 450 x 600ht Top: 18mm Thk pre laminated particle board Back: 9mm Thk pre laminated particle board with 2mm PVC edge lipping Shutters: 18mm Thk pre laminated particle board Edge: All exposed area with 2mm thick PVC edge lipping Handle: Finger groove handles Lock: Regular lock | NOS | 10 | 5000 | 50000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
36 | 90131175 | POUFF SEATING - 600X600X450MM To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 2 | 4500 | 9000 | #NAME? | 4500 | #NAME? | #NAME? | #NAME?
37 | 90131175 | CABIN DESK - 1200mmx 675mm x750mm Ht- Table top - 25mm thick Pre-laminate particle board finished with 2mm edge lipping on the other two sides Supports – MS powder coated 50mm Square MS perform series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top | NOS | 1 | 8500 | 8500 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
38 | 90131175 | Meeting table Size : 1050DIA x 750 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping Supports – MS powder coated 50mm perform MS powdercoated leg understructure, with necessary supports Wire Management -450mm flip open with ABS cable tray without switches and sockets | NOS | 1 | 8000 | 8000 | #NAME? | 8000 | #NAME? | #NAME? | #NAME?
39 | 99992487 | Medium Back Chairs (FEATHERLITE) - Nylon Back With Nylon Mesh Up/Down Adjustable Arms ( 1-D ) Nylon Base With Nylon Wheels Single Locking Position Synchro Tilt Mechansim Class IV Gas Lift. | Nos | 30 | 5000 | 150000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
40 | 99992487 | High Back Chairs (FEATHERLITE) - Nylon Back With Nylon Mesh Up/Down Adjustable Arms ( 1-D ) Nylon Base With Nylon Wheels Single Locking Position Synchro Tilt Mechansim Class IV Gas Lift. | Nos | 4 | 6000 | 24000 | #NAME? | 6000 | #NAME? | #NAME? | #NAME?
41 | 99992487 | HIGH CHAIR - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 8 | 4500 | 36000 | #NAME? | 4500 | #NAME? | #NAME? | #NAME?
42 | 90131175 | HIGH TABLE - 600 x 1200 x 1050 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 7800 | 7800 | #NAME? | 7800 | #NAME? | #NAME? | #NAME?
43 | 90131175 | HIGH TABLE - 1100DIA x 1050 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 8500 | 8500 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
44 | 99992487 | CHAIRS - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 2 | 4500 | 9000 | #NAME? | 4500 | #NAME? | #NAME? | #NAME?
45 | 90131175 | 600DIA x 450 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 5300 | 5300 | #NAME? | 5300 | #NAME? | #NAME? | #NAME?
46 | 99992409 | Fire line GYPBOARD FALSE CEILING- Providing and fixing MF suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. Metal expanded rawl plugs shall be bolted to the beam/deck slab and suspenders of the required length shall be provided using GI hangers. Metal expanded rawl plugs and suspenders are to be positiioned at such spacing so that the runner when connected shall have support not exceeding 4' intervals. Main runners coonsisting of GI intermediate channels shall be provided at not exceeding 4' centre in one direction and connected to the suspenders with GI bolts and nuts. GI ceiling channels shall be placed in the opposite direction to the Intermediate channel at not exceeding 2' centres and connected to the intermediate channel using special connecting clips. Gi perimeter channel shall be fixed along the periphery walls, columns, etc. and the ceiling channel shall be inserted and screwed to this perimeter channel. | sqm | 102 | 2200 | 224400 | #NAME? | 2200 | #NAME? | #NAME? | #NAME?
47 | 99992321 | Providing and fixing carpet flooring of imported loopile carpet of Divine/unitex/armstrong make of approved shade and colour. complete in all respect including fixing of 5 mm thick poly urethene foam rolls below the carpet. Rates quoted should include cost of adhesives, fixing , cutting welding of carpet etc complete in all respects.. Laid on site including wastage. (basic rate: 110rs/sft) | sqm | 145 | 2800 | 406000 | #NAME? | 2800 | #NAME? | #NAME? | #NAME?
48 | 90131332 | SILHOUETTE GRID CEILING :Providing and fixing in true horizontal level false ceiling grid of SILHOUTTE GRID 15mm using hot dipped galvonized steel section, Exposed surface chemically cleaned capping prefinished in baked polyster paint, main Tee of size 15 x 44 x 0.3 at every 1200 mm C/C max and rotary stiched Croos Tee of size 15 x 44 x 0.3 mm at every 1200 mm centrally between the 1200mm cross tees and 18 x 18 x 0.5 mm Wall angles all round the the wall to form a grid of size 600 mm x 600mm and suspended the grid using suitable rigid hangers at every 1200 mm intervals at the Main ' T ' and laying tile with edge CONSTILATION TILE of size 600 x 600 x 15 mm over the formed grid., Tile Specs; NRC of the tile to 0.9 ,Class 1 FIRE PERFORMANCE AND HUMIDITY RESISTANCE RH 99 %.The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. | sqm | 2 | 3500 | 7000 | #NAME? | 3500 | #NAME? | #NAME? | #NAME?
49 | 90132107 | Providing and fixing Linear metal ceiling tiles of size 1200,1500 & 1800mm x 150mm, thickness of 15mm with galvanised steel grid system, as per vendor detail and specification. From Armstrong/Tranquil or equivalent. | sqm | 45 | 3500 | 157500 | #NAME? | 3500 | #NAME? | #NAME? | #NAME?
50 | 90132185 | AOUSTIC BAFFLE CEILING - Providing and fixing in true horizontal level false ceiling using 50X100MM Extruded aluminium sections arranged at100mmc/c. The sections to be wrapped with acoustic panles and finished as per architects approval. The cost shall include all necessary hardwares as per vendor specifications | sqm | 34 | 6600 | 224400 | #NAME? | 6600 | #NAME? | #NAME? | #NAME?
51 | 90131163 | Providing and fixing trap doors for access to the areas above false ceiling. The trap door shall have an external frame made using 2" x 2" teakwood frame on which the shutter is hinged. Shutter shall be made using 19mm thk ply. The exposed side shall be finished with 12mm thk gypboard from India Gypsum painted in approved quality and colour. Heavy duty brass hinges shall be used to mount the shutters and locking shall be provided with panel locks. The shutter shall be moulded in level with the false ceiling forming a groove all around. further 6x6mm grooves shall be made on the shutter as per design. Sufficient number of hinges and locks shall be provided to avoid sagging of the shutter. Key also shall be supplied. (No extra rate shall be provided for suspenders or frame work all around for linking the trap door to gypboard false) | sqm | 12 | 11800 | 141600 | #NAME? | 11800 | #NAME? | #NAME? | #NAME?
52 | 90132171 | Providing & fixing alluminium skirting profile of 75mm height. Cost inclusive of adhesive. | rmt | 130 | 150 | 19500 | #NAME? | 150 | #NAME? | #NAME? | #NAME?
53 | 120020840 | Providing & fixing aluminium floor transition profiles from inside spaes or equivalent. | rmt | 11 | 1500 | 16500 | #NAME? | 1500 | #NAME? | #NAME? | #NAME?
54 | 90132171 | Providing & fixing VINYL skirting profile of 75mm height. Cost inclusive of adhesive. | rmt | 20 | 250 | 5000 | #NAME? | 250 | #NAME? | #NAME? | #NAME?
55 | 99992174 | FALSE FLOORING - Providing & Fixing of UNITILE OR EQUIVALENT CEMENTATIOUS INFILL TILE raised flooring system with necessary metal framework (GI/Epoxy coated) as per site requirements. The understructure shall be capable of level adjustment of ±50mm. The flooring to also include thermal insulation (15mm Armaduct Insulation) | sqm | 3 | 8500 | 25500 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
56 | 90111172 | Supply and laying of Cementitious Self Leveling Underlay Material. The surface to be prepared and should be clean , sound and free from loose material and contamination such as plaster ,oil, paint and grease. Thereafter applying one coat of Primer and after the primer application gets dried , the self levelling compound to be applied as per the manufacturers specifications... PRODUCT : ARDEX ENDURA , PRIMER : ARDEX P51 , SELF LEVELLING UNDERLAY : ARDEX CL11 , THICKNESS TO BE 6mm | sqm | 55 | 570 | 31350 | #NAME? | 570 | #NAME? | #NAME? | #NAME?
57 | 99992385 | To prepare & finish 3 coats of tractor emulsion paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of tractor emulsion paint, touching up with putty & applying two final roller coats of tractor emulsion paint, to internal wall/ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. | sqm | 455 | 360 | 163800 | #NAME? | 360 | #NAME? | #NAME? | #NAME?
58 | 90130762 | To prepare & finish 3 coats of asian texture paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of asian texture paint, touching up with putty & applying two final roller coats of texture paint. The application shall be carried out using spray gun and the sprayed surface shall be trowelled for a head cut finish. | sqm | 10 | 500 | 5000 | #NAME? | 500 | #NAME? | #NAME? | #NAME?
59 | 99993108 | Providing and fixing of RUGS | NO.S | 2 | 8000 | 16000 | #NAME? | 8000 | #NAME? | #NAME? | #NAME?
60 | 240001910 | ARTWORK -Providing & fixing of artwork as per selection. | NO.S | 10 | 20000 | 200000 | #NAME? | 20000 | #NAME? | #NAME? | #NAME?
61 | 250003450 | providing and fixing of PLANTERS | NO.S | 20 | 8500 | 170000 | #NAME? | 8500 | #NAME? | #NAME? | #NAME?
62 | 230002422 | Providing and fixing temporary site barricading, with wooden runners of size 50mm x50mmas a basic framework and cladding with 6mm plywood.The barricades shall be fixed with printed artwork vinyl on outside.The material will be contractors property after its usage as a barricade.Cost to include dismantalling also. upto a height of 4.5. m | sqm | 72 | 1800 | 129600 | #NAME? | 1800 | #NAME? | #NAME? | #NAME?
63 | 99992504 | Dismantling Dry cladding/Finishes cladding and stacking of serviceable material at MLCP level P2 as directed by engineer incharge | sqm | 225 | 400 | 90000 | #NAME? | 400 | #NAME? | #NAME? | #NAME?
64 | 99992505 | Dismantling aluminium/Gypsum partitions/ply/double skinned bison board with frame, doors,windows, fixed glazing and false ceiling including disposal of unserviceable surplus material and stacking of serviceable material within 500 metres lead as directed by Engineer-in- charge. | sqm | 150 | 750 | 112500 | #NAME? | 750 | #NAME? | #NAME? | #NAME?
65 | 99992135 | Removing metal and wooden door with all its hardware and stacking the same in T2 MLCP as directed by engineer in charge | NO.s | 1 | 2500 | 2500 | #NAME? | 2500 | #NAME? | #NAME? | #NAME?
66 | 99992504 | Dismantling existing SS skirting | rmt | 80 |  | 0 | #NAME? | 0 | #NAME? | #NAME? | #NAME?
67 | 99992262 | Demolishing of flooring tile with mortar | sqm | 150 | 650 | 97500 | #NAME? | 650 | #NAME? | #NAME? | #NAME?
68 | 170002645 | Disposal of building rubbish/malba from building premises from airside,inside building and city side by mechanical transport including loading,unloading etc. and disposal outside the airport premises. | cum | 50 | 1500 | 75000 | #NAME? | 1500 | #NAME? | #NAME? | #NAME?
69 | 120008655 | Providing & plastering to internal block masonry wall/concrete surface 12mm tk in CM1:6,including providing & removing scaffolding,rounding off all corners wherever required,smooth lime rendering(hydrating the lime 24hrs before starting of the work),curing, hacking etc.,complete.With all lead & lift as directed by engineer incharge. | sqm | 7 | 425 | 2975 | #NAME? | 425 | #NAME? | #NAME? | #NAME?
70 | 99992734 | Lintels shall be precast and it should be casted at ground level. Lintel shall be lifted by crane at relevant location, Rate shall include above all activities including lift, lead, casting, shuttering, leaving dowels for chajja etc. | no | 10 | 17000 | 170000 | #NAME? | 17000 | #NAME? | #NAME? | #NAME?
71 | 120014430 | Providing and constructing Brick/Solid Block for 150MM thick walls till R.C.C slab lvl using in cement mortar 1:4, using 2 nos. with 1:6 CM 12mm thk plastered and finished to match the existing wall. The junction of existing & new wall or brick wall and RCC surface to be plastered after placing wiremesh 6" wide on either side. The block should be of minimum compressive strength of 35 Kg/ sqcm. Rate to be inclusive of filling of voids created by chasing of walls for water supply and electrical works with appropriate material as directed, etc. complete. | cum | 0.8 | 10000 | 8000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
72 | 99992441 | Providing and fixing of 35 mm thk flush door as per detail design. Item to be finished with laminates with all necessary joints, grooves, hardware such as hinges, door handle, door closer, door stopper, mortice lock, lock cover plate etc. The door frame shall be 2.5"X5" made out of second grade teak wood with provision of bottom louvers for wshrooms (Pls refer detail drawing) Size: 1000x2100mm | NO.S | 3 | 26000 | 78000 | #NAME? | 26000 | #NAME? | #NAME? | #NAME?
73 | 90130832 | Providing and fixing wallpaper as per architect approval. Wall to be leveled properly to recieve the wallpaper. Installation will be contractors responsibility. care shall be taken for air bubbles not to form and joints shall not be visible. measurement will be given only on the laid area. Basic rate: 90rs/sft | sqm | 117 | 140 | 16380 | #NAME? | 140 | #NAME? | #NAME? | #NAME?
74 | 99992398 | PANTRY TILE DADO - Providing and fixing 600x600mm ceramic tile dado of KAJARIA make or equivalent for wall above pantry counter upto 600mm ht as per the drawing. Shall be provided with suitable white cement backing on existing surface, with colour cement finishing including dilute acid. Epoxy joint filler to be used in the joint between tiles.(See Toilet details) | sqm | 2 | 2450 | 4900 | #NAME? | 2450 | #NAME? | #NAME? | #NAME?
75 | 90131592 | Wall to be fitted with 12mm thk ply and finished with 12mm thk wooden fluted panel as per selection. Panel to be finished with melamine polish.shall be finished with proper grooves,skirting, etc,. | SQM | 47 | 4200 | 197400 | #NAME? | 4200 | #NAME? | #NAME? | #NAME?
76 | 90131592 | Providing and fixing of laminate paneling with 19mm thk ply finished with laminate as per selection. Item to be finished with proper grooves & skirtings, etc,. as per detail drawing. | sqm | 56 | 3400 | 190400 | #NAME? | 3400 | #NAME? | #NAME? | #NAME?
77 | 90131592 | Providing and fixing ply boxing made with 12mm thk ply with proper salwood or GI framework at the back and finished with 12mm thk wooden fluted panel. Boxing to be done to flush the around the column as shown in drawing. To be fixed from floor to false ceiling with proper skirting,etc. to be painted as per selection. wooden fluted panel already considered in wall & surace finishes.item no.05. | sqm | 11 | 9000 | 99000 | #NAME? | 9000 | #NAME? | #NAME? | #NAME?
78 | 170002757 | Providing & fixing of full height storage with shutters made out of 12mm thk ply and finished with approved 12mm thick wooden fluted panel with necessary hardware such as soft close hinges, push-to-open mechanism,locks etc. from HAFELE / or equivalent. internally the cabinets shall be vertically divided equally into with shelves made of 12mm thk ply. all internal areas shall be finished with a 0.8mm laminate as per selection. The item shall be provided with proper grooves, skirting etc,. as per drawing. wooden fluted panel already considered in wall & surace finishes.item no.05. | sqm | 11 | 10500 | 115500 | #NAME? | 10500 | #NAME? | #NAME? | #NAME?
79 | 170002757 | PLY BOXING FOR TV NICHE - Providing and fixing ply boxing made with 19mm thk ply with proper salwood or GI framework at the back and finished with 4mm thk veneer panel. To be fixed from floor to false ceiling with proper skirting,etc. to be painted as per selection. niche to be made in the boxing as required to fit the led screens as required. AV vendor shop drawing is required. veneer panel already considered in wall & surace finishes.item no.05. | sqm | 45 | 7800 | 351000 | #NAME? | 7800 | #NAME? | #NAME? | #NAME?
80 | 170002757 | PANTRY BOTTOM COUNTER - Base cabinet shall be made of 19mm BWP ply with 2200MM x 600mm depth and 825mm ht . Shutters to be finished with 1mm thk laminate as per selection. all internal surfaces to be finished with 0.8mm laminate as per selection. counter top shall be finished with 19mm thk granite as per selection with 19mm thk BWP ply base. Kitchen sink of Franke or equivalent. item to be fitted with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent and finished with required grooves, 75mm high & 75mm recessed skirting, etc. refer detail drawing. | sqm | 2.2 | 15000 | 33000 | #NAME? | 15000 | #NAME? | #NAME? | #NAME?
81 | 99992487 | Medium Back Chairs (FEATHERLITE) - Nylon Back With Nylon Mesh Up/Down Adjustable Arms ( 1-D ) Nylon Base With Nylon Wheels Single Locking Position Synchro Tilt Mechansim Class IV Gas Lift. | Nos | 9 | 5000 | 45000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
82 | 170002757 | Providing and fixing shutters made with 19mm thk ply finished with 4mm thk veneer as per selection with a 50x50mm wooden framework as per drawing. Shutters shall have 19mm slits at every 25mm gaps done by CNC machine. Item shall have all necassry hardware such as hinges, locks, handles, etc. shall have a 75mm high skirting depressed in by 75mm made with 19mm thk ply finished with same laminate as shutter. shutter shall be upto 2400mm ht from ffl. the remaining area upto false ceiling will be a fixed panel. item to be finished with proper grooves, skirting, etc. see detailed drawing. | sqm | 10 | 10000 | 100000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
83 | 90131175 | L-SHAPE Workstation Size : 600,1200 x 600x 750 ht Table top - 25mm thick Pre-laminate particle board finished with d 2mm edge lipping on the other two sides Screen : 30mm split screen ( fabric magnetic & glass marker ) , 30mm thick with aluminum anodised trim ( 1500 x 300ht ) fabric on longer side and glass marker on shorter side. Supports – MS powder coated 50mm Perform Series leg understructure, with necessary supports Wire Management - 65mm wire manager, with MS powder coated race way with laminate facia , below the table top CPU trolley on castors for the above PVC Keyboard tray with a mouse pad | NOS | 1 | 10500 | 10500 | #NAME? | 10500 | #NAME? | #NAME? | #NAME?
84 | 99992776 | Pedestal ( 2D + 1 F ) - with Cushion top Size : 450 x 450 x 600ht Top: 18mm Thk pre laminated particle board Back: 9mm Thk pre laminated particle board with 2mm PVC edge lipping Shutters: 18mm Thk pre laminated particle board Edge: All exposed area with 2mm thick PVC edge lipping Handle: Finger groove handles Lock: Regular lock | NOS | 1 | 5500 | 5500 | #NAME? | 5500 | #NAME? | #NAME? | #NAME?
85 | 90131175 | Meeting table Size : 4800 x 1500 x 750 ht Table top - 12mm thk corian top with double layer 19mm thk ply base Supports – MS powder coated 50mm perform MS powdercoated leg understructure, with necessary supports Wire Management -450mm flip open with ABS cable tray without switches and sockets | NOS | 1 | 165000 | 165000 | #NAME? | 165000 | #NAME? | #NAME? | #NAME?
86 | 99992487 | High Back Chairs (FEATHERLITE) - Nylon Back With Nylon Mesh Up/Down Adjustable Arms ( 1-D ) Nylon Base With Nylon Wheels Single Locking Position Synchro Tilt Mechansim Class IV Gas Lift. | Nos | 1 | 6500 | 6500 | #NAME? | 6500 | #NAME? | #NAME? | #NAME?
87 | 99992696 | SINGLE SEATER SOFA - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 2 | 10000 | 20000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
88 | 90131758 | 3- SEATER SOFA - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 1 | 28000 | 28000 | #NAME? | 28000 | #NAME? | #NAME? | #NAME?
89 | 99992696 | SINGLE SEATER SOFA - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 2 | 10000 | 20000 | #NAME? | 10000 | #NAME? | #NAME? | #NAME?
90 | 90131175 | 600DIA x 450 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 5500 | 5500 | #NAME? | 5500 | #NAME? | #NAME? | #NAME?
91 | 90131175 | 600 x 900 x 450 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 6500 | 6500 | #NAME? | 6500 | #NAME? | #NAME? | #NAME?
92 | 90131175 | 1100dia x 750 ht. This is of MS frame of POWDER COATED BLACK color in matt finish inish with laminated top as per selection . | Nos | 1 | 9800 | 9800 | #NAME? | 9800 | #NAME? | #NAME? | #NAME?
93 | 99992487 | CHAIRS - To be finished with Fabric - Samples to be shown. This is of SAL WOOD understructure material with HIGH DENSITY FOAM - 40 - D with ELASTIC/SPRINGS & Adhesives etc. With dark wooden legs for the bottom legs. | Nos | 4 | 5000 | 20000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
94 | 99992409 | Fire line GYPBOARD FALSE CEILING- Providing and fixing MF suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. Metal expanded rawl plugs shall be bolted to the beam/deck slab and suspenders of the required length shall be provided using GI hangers. Metal expanded rawl plugs and suspenders are to be positiioned at such spacing so that the runner when connected shall have support not exceeding 4' intervals. Main runners coonsisting of GI intermediate channels shall be provided at not exceeding 4' centre in one direction and connected to the suspenders with GI bolts and nuts. GI ceiling channels shall be placed in the opposite direction to the Intermediate channel at not exceeding 2' centres and connected to the intermediate channel using special connecting clips. Gi perimeter channel shall be fixed along the periphery walls, columns, etc. and the ceiling channel shall be inserted and screwed to this perimeter channel. | sqm | 121 | 2400 | 290400 | #NAME? | 2400 | #NAME? | #NAME? | #NAME?
95 | 90131332 | 600X600MM WOODEN GRID CEILING - Providing and fixing Wooden ceiling, fabricate and install 12 mm thk. plywood ceiling with appropriate reinforcement with suitable 2" x 2" frame supports at every 2' x 2' c/c supported from the slab with cut outs for light fixtures, ac grilles etc. The ply is to be finished with 1mm thk laminate over 4mm thk ply to form 4mm x 4mm grooves as per design. The wooden ceiling will have drops or coves as per design from adjacent ceiling by 150mm , and hence facia of 150mm is visible. Area / quantity indicated is surface area, including vertical facia of 150mm . . Coves as per design to be provided of 200mm width and 100mm heght ALL VERTICALS UPTO 150MM WILL NOT BE PAYABALE AND SHOUDL BE PART OF RATE QUOTED, | sqm | 35 | 5000 | 175000 | #NAME? | 5000 | #NAME? | #NAME? | #NAME?
96 | 90132185 | ACOUSTIC CEILING - Providing and fixing acoustic suspended False ceiling consisting of the following using India Gypsum's Standard GI metal section. ceiling shall be finished with 12mm thk acoustic panel with 0.9 NRC rating with 12mm thk ply backing. The work shall include making necessary cutout for spotlights,light fixtures also providing necessary supporting system for these cutouts. | sqm | 25 | 6500 | 162500 | #NAME? | 6500 | #NAME? | #NAME? | #NAME?
97 | 99992321 | Providing and fixing carpet flooring of imported loopile carpet of Divine/unitex/armstrong make of approved shade and colour. complete in all respect including fixing of 5 mm thick poly urethene foam rolls below the carpet. Rates quoted should include cost of adhesives, fixing , cutting welding of carpet etc complete in all respects.. Laid on site including wastage. (basic rate: 110rs/sft) | sqm | 165 | 3000 | 495000 | #NAME? | 3000 | #NAME? | #NAME? | #NAME?
98 | 90132171 | Providing & fixing alluminium skirting profile of 75mm height. Cost inclusive of adhesive. | rmt | 120 | 1200 | 144000 | #NAME? | 1200 | #NAME? | #NAME? | #NAME?
99 | 99992385 | To prepare & finish 3 coats of tractor emulsion paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of tractor emulsion paint, touching up with putty & applying two final roller coats of tractor emulsion paint, to internal wall/ceilings masonry concrete surfaces incl. preparing the surface by cleaning scrapping, smooth filling crevices, scaffolding etc. | sqm | 3080 | 360 | 1108800 | #NAME? | 360 | #NAME? | #NAME? | #NAME?
100 | 90130762 | To prepare & finish 3 coats of asian texture paint of approved quality & shade by sand papering the surface, applying one coat of primer, prepare the surface with two coats of full putty, sand papering again, repeating a coat of primer, applying one coat of asian texture paint, touching up with putty & applying two final roller coats of texture paint. The application shall be carried out using spray gun and the sprayed surface shall be trowelled for a head cut finish. | sqm | 616 | 500 | 308000 | #NAME? | 500 | #NAME? | #NAME? | #NAME?
101 | 170002764 | Providing & fixing of Shelf made out of 19mm thk ply and finished with approved 4mm thick Veneer as per selection,melamine polish with necessary hardware from HAFELE / or equivalent. the bookshelf shall be divided into equal parts with shelves made of 12mm thk ply. all internal areas shall be finished with 4mm veneer as per selection. The item shall be provided with proper grooves, 75mm high & 75mm recessed skirting etc,. as per drawing. 1700X250X3000MM | Nos. | 1 | 125000 | 125000 | #NAME? | 125000 | #NAME? | #NAME? | #NAME?
102 | 170002764 | SIDE RETURN TABLE - 900mmx450mmx750mm Ht | NOS | 1 | 15000 | 15000 | #NAME? | 15000 | #NAME? | #NAME? | #NAME?
103 | 90131975 | Plaster of paris or gypboard moulded as per the design and detail of the architect shall be fixed to the GI frame work for indirect lighting. The mould shall be properly finished and levelled. For indirect lighting | rmt | 42 | 225 | 9450 | #NAME? | 225 | #NAME? | #NAME? | #NAME?
104 | 170002764 | SEATER WITH STORAGE - Providing & fixing of 600mm deep, 4500mm length & 450mm height seating with storage. item carcass to bemade with 19mm thk ply finished with 4mm thk veneer as per drawing with shutters made out of 19mm thk ply and finished with approved 4mm thick veneer with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent. internal area to be divided finished with laminate as per selection the top shall be made with ply covered with a seating made with 100mm foam filling and wrapped around with a fabric as per selection. The item shall be provided with proper grooves, skirting etc,. as per drawing. | Nos. | 2 | 75000 | 150000 | #NAME? | 75000 | #NAME? | #NAME? | #NAME?
105 | 170002764 | Providing & fixing of storage with shutters made out of 19mm thk ply and finished with approved 1mm thick laminate with necessary hardware such as hinges, handles,locks etc. from HAFELE / or equivalent. internally the cabinets shall be vertically divided into 2 equal parts with shelves made of 12mm thk ply. all internal areas shall be finished with a 0.8mm laminate as per selection. Top of the storage shall be made with 19mm thk ply and finished with laminate postformed with matching edge banding. Overhead storage shutters to be finished with 1mm thk laminate matt finish as per selection, all internal surfaces to be finished with 0.8mm laminate as per selection. The item shall be provided with proper grooves, 75mm high & 75mm recessed skirting etc,. as per drawing. 2100X450X450MM | no | 1 | 40000 | 40000 | #NAME? | 40000 | #NAME? | #NAME? | #NAME?
106 | 90131975 | Plaster of paris or gypboard moulded as per the design and detail of the architect shall be fixed to the GI frame work for indirect lighting. The mould shall be properly finished and levelled. For indirect lighting | rmt | 120 | 250 | 30000 | #NAME? | 250 | #NAME? | #NAME? | #NAME?
107 | 120019346 | Providing & plastering to internal block masonry wall/concrete surface 12mm tk in CM1:6,including providing & removing scaffolding,rounding off all corners wherever required,smooth lime rendering(hydrating the lime 24hrs before starting of the work),curing, hacking etc.,complete.With all lead & lift as directed by engineer incharge. | sqm | 30 | 425 | 12750 | #NAME? | 425 | #NAME? | #NAME? | #NAME?
|  |  |  | SUB TOTAL |  | 10959145 |  |  | #NAME?
|  |  |  | SGST @ 9% |  | 986323.05 |  |  | #NAME?
|  |  |  | CGST @ 9% |  | 986323.05 |  |  | #NAME?
|  |  |  | GRAND TOTAL |  | 12931791.1 |  |  | #NAME?