## Summary
PROJECT: CONSTRUCTION OF BLR-T1-080 LOUNGE PH-2
CIVIL,INTERIOR & PLUMBING WORK
INTERCARE ENTERPRISES Work Order No : : BLR/PO/24-25/000129
Sr. No. | Item Description | BOQ | RA-1 | RA-2 | RA-3
1 | Boq & Ex Items | 57913844.49 | 25503537.4147 | 29458092.1878 | 35241772.0601
2 | Plumbing | 2444934 | 893649.6 | 1369097.496 | 1391357.496
3 | Extra Item |  |  | 2684679.362 | 5967953.041
TOTAL AMOUNT |  | 60358778.49 | 26397187.0147 | 33511869.0458 | 42601082.5971
| GST | 10864580.1282 | 4751493.6627 | 6032136.4282 | 7668194.8675
| TOTAL WITH GST | 71223358.6182 | 31148680.6774 | 39544005.474 | 50269277.4646
Less: Certified in RA -2 |  |  |  |  | 39544005.474
PAYABLE IN RA-3 WITH GST |  |  |  |  | 10725271.9906
(Rupees One Crore Seven Lakh Twenty-Five Thousand Two Hundred Seventy-Two Rupees Only.)
| CERTIFIED BY |  |  |  | ACCEPTED BY
| RANJANDAS SHETTY |  |  |  | INTERCARE ENTERPRISES

## RA 3
|  | BLR-T1-080 LOUNGE PH-2 |  |  |  | INTER CARE ENTERPRISES
[6 empty] | Contact Name : ATTAHAR ALI SHAIKH | Contact Name : ATTAHAR ALI SHAIKH
Po. No.BLR/PR/24-25/000129 | PR Number : BLR-2425-00050,BLR-2425-00068 | PR Number : BLR-2425-00050,BLR-2425-00068 | PR Number : BLR-2425-00050,BLR-2425-00068 | PR Number : BLR-2425-00050,BLR-2425-00068 | PR Number : BLR-2425-00050,BLR-2425-00068 | Email : info.intercareenterprises@gmail.com | Email : info.intercareenterprises@gmail.com
Package / RFQ Name : Civil, Interior & PLB for Bangalore Lounge | Package / RFQ Name : Civil, Interior & PLB for IFH Bangalore | Package / RFQ Name : Civil, Interior & PLB for IFH Bangalore | Package / RFQ Name : Civil, Interior & PLB for IFH Bangalore | Package / RFQ Name : Civil, Interior & PLB for IFH Bangalore | Package / RFQ Name : Civil, Interior & PLB for IFH Bangalore
BLR-T1-080 LOUNGE PH-2
Sr No. | Sr.No | Item Name | UOM | Qty | Minimum Amount | Unit Price | Amount | RA-1 |  |  | RA-2 |  |  |  | RA-3 |  |  |  | Remarks
1 |  | Civil Interior | NOS | 1 |  |  | 57913844.49 | Qty | % | Amount | Qty | % | Amount | RA-2 Actual Amout | Qty | % | Amount | RA-3 Actual Amout
1 | 1.1 | 18 mm thick Italian Marble flooring | Smt | 190 | 1615000 | 10795 | 2051050 | 190 | 40% | 820420 | 201.458 | 85% | 1848528.6105 | 1028108.6105 | 201.458 | 95% | 2066002.5647 | 217473.9542
2 |  | Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including approved sealer to be applied on all sides, with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft | [10 empty] | 0 |  |  |  | 0 | 0
3 | 1.2 | 18 mm thick Italian Marble Dado on Lift wall including Jamb line | Smt | 41.04 | 352944 | 11050 | 453492 | 41.04 | 40% | 181396.8 | 0 |  | 0 | -181396.8 | 0 |  | 0 | 0
4 |  | At least 18 mm thk polished marble fixed to Plastered masonry, Marble shall be cut from slabs of even thickness, Marble shall be installed with white cement paste, Include all finished marble niches, with V groove edge polish etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, All visible edges of Marble shall be mirror polished, including approved sealer to be applied on all sides , Basic cost of marble Rs 450 sft | [10 empty] | 0 |  |  |  | 0 | 0
5 | 1.3 | Designer Texture Tile Cladding | Smt | 25.2 | 169470 | 7450 | 187740 | 25.2 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
6 |  | Clean existing wall surface before fixing Texture designer tile Before starting, carefully read the suppliers laying plan and instructions.DecorativeTexture tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of Texture tiles at Rs.400 sft without tax | [10 empty] | 0 |  |  |  | 0 | 0
7 | 1.4 | Marble Jamb line | rmt | 22.5 | 66937.5 | 3414 | 76815 | 22.5 | 40% | 30726 | 0 |  | 0 | -30726 | 0 |  | 0 | 0
8 |  | All around the Opening Up to 250 mm Wide ,polished Italian marble fixed to existing masonry Plastered wall, Marble shall be installed with white cement paste, if installed on masonry work, with edge Moulding etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, All visible edges of Marble shall be mirror polished, including approved sealer to be applied on all sides , Special care to be taken to fix marble on horizontal surface. Shall rest over ply at one end and vertical marble on the other, ( Basic cost of marble Rs 450 sft ) | [10 empty] | 0 |  |  |  | 0 | 0
9 | 1.5 | Marble Skirting Boxing -Openable | rmt | 60 | 127620 | 2127 | 127620 | 60 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
10 |  | up to 150 mm high x 200 mm wide ,Skirting Boxing to be made out of 18 mm thick Marine ply, Ply to be covered with 18 MM thick Italian Marble including Edge Moulding, etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, All visible edges of Marble shall be mirror polished, approved sealer to be applied on all sides ( Basic cost of marble Rs 450 sft ) | [10 empty] | 0 |  |  |  | 0 | 0
11 | II | FRENCH PLASTER WORK | [10 empty] | 0 |  |  |  | 0 | 0
12 | 2.1 | Fire line Gypsum board ceiling | Smt | 20 | 40680 | 2034 | 40680 | 20 | 40% | 16272 |  |  | 0 | -16272 |  |  | 0 | 0
13 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobin Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibber tape reinforcement, Include finished cutouts for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceiling height is 4300 mm ) | [10 empty] | 0 |  |  |  | 0 | 0
14 | 2.2 | Bulk Head in Profile- In Flat Water cut Paint finish | rmt | 30 | 318000 | 30080 | 902400 | 30 | 50% | 451200 |  |  | 0 | -451200 |  |  | 0 | 0
15 |  | As per drawing -Size up to 600 mm wide x 1850 mm high, Using 50mm x 36 mm, 16 SWG aluminium framework at 600 mm c c Fixed on existing Structural Framework, Frame to be covered with 18 mm thick marine ply, For Curve surface use 6+6+6 mm flexi ply, 12 mm thick HDF to be fixed on Ply, For Curve surface use 6+6 mm flexi HDF, All joints shall be filled with suitable fillers and reinforcement tape, 50 mm wide x 25 mm thick HDF fluting to be fixed on HDF surface with 25 mm gap, Base and HDF moulding surface shall be finished n Water cut enamel Paint finish, as approved by Architect, include 450 mm wide x 100 mm thick veneer finish Band at bottom, Veneer to be finished in Approved Melamine polish . Including 2 layers of light Pelmet with Led strip light provision. (Basic cost of veneer up to Rs. 125 -sft ) | [10 empty] | 0 |  |  |  | 0 | 0
16 |  | refer Drawing no- B01-TFS-DOM02-ID-00-13 | [10 empty] | 0 |  |  |  | 0 | 0
17 | 2.3 | POP plaster punning | Smt | 50 | 24250 | 615 | 30750 | 50 | 80% | 24600 | 112.5488 | 100% | 69217.512 | 44617.512 | 112.5488 | 100% | 69217.512 | 0
18 |  | Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bull marks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work | [10 empty] | 0 | 0 |  |  | 0 | 0
19 | III | CARPENTRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
20 | 3.1 | FRP Ply Panelling | [10 empty] | 0 | 0 |  |  | 0 | 0
21 |  | providing and fixing Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at centre of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material | [10 empty] | 0 | 0 |  |  | 0 | 0
22 |  | 12 mm thk Fire rated plywood | Smt | 10 | 16140 | 2160 | 21600 | 10 | 60% | 12960 |  |  | 0 | -12960 |  |  | 0 | 0
23 |  | 15 mm thk Fire rated plywood | Smt | 10 | 21000 | 2740 | 27400 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
24 |  | 18 mm thk Fire rated plywood | Smt | 10 | 23000 | 3280 | 32800 | 10 | 60% | 19680 |  |  | 0 | -19680 |  |  | 0 | 0
25 |  | 6 mm thk Flexi Fire rated plywood | Smt | 10 | 12800 | 1650 | 16500 | 10 | 60% | 9900 |  |  | 0 | -9900 |  |  | 0 | 0
26 | 3.2 | Veneer skin | Smt | 10 | 43040 | 6133 | 61330 | 10 | 60% | 36798 |  |  | 0 | -36798 |  |  | 0 | 0
27 |  | Using 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, pressed over backing plywood including matching wood beading as per approved design, with 3 mm x 3mm finish groove as per design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be finished in Approved Water base PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
28 |  | (Basic cost of veneer up to Rs. 125 -sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
29 |  | refer Drawing no- B01-TFS-DOM02-ID-00-13 | [10 empty] | 0 | 0 |  |  | 0 | 0
30 | 3.3 | SS Satin Bronze finish Floor Insert in Curved Profile | Rmt | 150 | 172200 | 1175 | 176250 | 150 | 40% | 70500 |  |  | 0 | -70500 | 83.634 | 95% | 93356.4525 | 93356.4525
31 |  | up to 18 mm wide, 4 mm thick 304 grade Insert in Two Floorings , Fixed with epoxy adhesive | [10 empty] | 0 | 0 |  |  | 0 | 0
32 | 3.4 | SS Bronze Satin finish skirting 50mm high | Rmt | 10 | 9500 | 1500 | 15000 | 10 | 40% | 6000 |  |  | 0 | -6000 | 9.9 | 95% | 14107.5 | 14107.5
33 |  | 16 SWG, 304 Grade SS skirting over existing ply, Fixed with epoxy adhesive | [10 empty] | 0 | 0 |  |  | 0 | 0
34 |  | refer Drawing no- B01-TFS-DOM02-ID-00-13 | [10 empty] | 0 | 0 |  |  | 0 | 0
35 | 3.5 | View Cutter Panelling up to 2500 mm high above Deck Slab | sqmt | 90 | 382500 | 13698 | 1232820 | 90 | 40% | 493128 |  |  | 0 | -493128 |  |  | 0 | 0
36 |  | Providing and fixing using 36 x36 mm MS partition frame work with cross bracing, Frame Anchor to Deck slab, Exposed side of frame to be covered with 12 mm thick HDF base ,additional 6 mm HDF to be fixed on 12 mm thick base with 12 mm Groove pattern, Finish in approved Lustre paint | [10 empty] | 0 | 0 |  |  | 0 | 0
37 | IV | MISCELLANOUS WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
38 | 4.1 | Art paintings artefacts | LS | 1 | 0 | 0 | 0 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
39 | 4.2 | Signages | LS | 1 | 0 | 0 | 0 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
40 | 4.3 | Attendance for MEPF works | LS | 1 | 0 | 0 | 0 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
41 |  | On Electrical Lighting allied Works | [10 empty] | 0 | 0 |  |  | 0 | 0
42 |  | On IT Works | [10 empty] | 0 | 0 |  |  | 0 | 0
43 |  | On Fire Protection System Works | [10 empty] | 0 | 0 |  |  | 0 | 0
44 |  | On HVAC Works | [10 empty] | 0 | 0 |  |  | 0 | 0
45 |  | On Plumbing Works | [10 empty] | 0 | 0 |  |  | 0 | 0
46 |  | On Kitchen Works | [10 empty] | 0 | 0 |  |  | 0 | 0
47 |  | Including all Other services | [10 empty] | 0 | 0 |  |  | 0 | 0
48 | V | PAINTING WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
49 | 5.1 | Highlight Painting to walls | smt | 50 | 24600 | 650 | 32500 | 50 | 40% | 13000 |  |  | 0 | -13000 |  |  | 0 | 0
50 |  | Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of lustre paint. Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
51 | 5.2 | Duco Paint to Walls Partition | smt | 50 | 113750 | 3287 | 164350 | 50 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
52 |  | Sanding and preparing surface for receiving paint, Final coats of Duco paint. Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
53 | 5.3 | Painting to ceiling in acrylic emulsion paint | smt | 50 | 24000 | 650 | 32500 | 50 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
54 |  | Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base. Two coats of putty ,Three coats of acrylic emulsion paint, Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
55 | 5.4 | Concrete texture finish Paint | smt | 50 | 187500 | 5474 | 273700 | 50 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
56 |  | Paint By Evolve-Mumbai ( basic cost of Pati Rs 250 sqft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
57 |  | Dismantling work | [5 empty] | 0 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 |  |  | 0 | 0 |  |  | 0 | 0
|  | OVERALL EXTRA ITEAM | [10 empty] | 0 | 0 |  |  | 0 | 0
| 1 | P F of metalized grid ceiling with selected approved Armstrong or eqv. make metal sheet (suspended lay-in square Armstrong metal ceiling, standard plain square tiles of 600mm x 600mm in off white colour, exposed grid white Armstrong metal false ceiling, thickness 0.5 mm, surface treatment in galvanized, off white colour coated, features -water proof, corrosion resistant - basic cost INR. 1345.00 SM) and section (as per approved sample) with grid section framework, frame work should be hanged from the existing slab as per manufacture s instruction, including scaffolding, all necessary hardware fittings etc., making provision for lighting, including opening for ventilation grills, duct, etc. as required on site. Complete as per architectural detail drawing site engineer s instruction. It is for kitchen area. | Smt |  |  | 2231.19 |  |  |  |  | 79.8087 | 50% | 89034.2201 | 89034.2201 | 79.8087 | 100% | 178068.4403 | 89034.2201
| 2 | 18 mm thick Italian Marble flooring (Both side railing below marble Patta) | Smt |  |  | 10795 |  |  |  |  | 28.8 | 70% | 217627.2 | 217627.2 | 28.8 | 95% | 295351.2 | 77724
|  | Marble strip size up to 50 to 225 mm wide in various length, Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides , with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
| 3 | Vitrified tile Flooring for janitor room | smt |  | 32500 | 3690 |  |  |  |  | 11.652 | 60% | 25797.528 | 25797.528 | 11.652 | 100% | 42995.88 | 17198.352
|  | Clean existing sub floor thoroughly before fixing Vitrified tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.150 sft without tax | [10 empty] | 0 | 0 |  |  | 0 | 0
| 4 | Lustre Painting to walls | smt | 160 | 78720 | 650 | 104000 | [5 empty] | 0 | 0 | 127.9602 | 90% | 74856.717 | 74856.717
|  | Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of lustre paint. Complete as per manufacturer s specifications (BOH AREA) | [10 empty] | 0 | 0 |  |  | 0 | 0
[13 empty] | 0 | 0 |  |  | 0 | 0
[13 empty] | 0 | 0 |  |  | 0 | 0
|  | Welcome zone | [10 empty] | 0 | 0 |  |  | 0 | 0
|  | DEMOLITION WORK | PS | 2 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0
58 | II | MASONRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
59 | 2.1 | P C of 150mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patil to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level. | Sq. Mtr. | 87.2 | 178324 | 2740 | 238928 | 87.2 | 60% | 143356.8 |  |  | 0 | -143356.8 |  |  | 0 | 0
60 | 2.2 | P C of 100mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level. | Sq. Mtr. | 41.12 | 70808.64 | 2300 | 94576 | 41.12 | 80% | 75660.8 | 26.3023 | 100% | 60495.175 | -15165.625 | 26.3023 | 100% | 60495.175 | 0
61 | 2.3 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr. | 240.79 | 161329.3 | 767 | 184685.93 | 240.79 | 70% | 129280.151 | 341.0412 | 90% | 235420.7058 | 106140.5548 | 341.0412 | 100% | 261578.5621 | 26157.8562
62 | 2.4 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr. | 444.3 | 340778.1 | 767 | 340778.1 | 444.3 | 70% | 238544.67 | 84.7311 | 100% | 64988.7537 | -173555.9163 | 84.7311 | 100% | 64988.7537 | 0
63 | 2.5 | P C of 50mm 75mm thick screed in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Laying the same in proper line level on the seating area s floor to maintain the floor leveling to get the smooth surface to lay the finishing floor materials on the said surface. Complete as per architectural detail drawings instruction by the site engineer. | Sq. Mtr. | 131 | 116590 | 898 | 117638 | 131 | 80% | 94110.4 | 9.3 | 100% | 8351.4 | -85759 | 9.3 | 100% | 8351.4 | 0
64 | III | CIVIL WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
65 | 3.1 | 18 mm thick Italian Marble flooring - Dark | Smt | 100 | 850000 | 10795 | 1079500 | 100 | 50% | 539750 |  |  | 0 | -539750 |  |  | 0 | 0
66 |  | Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides , with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
67 | 3.2 | Kota Stone Flooring for Corridor | Smt | 25 | 62500 | 3040 | 76000 | 25 | 90% | 68400 | 25.0051 | 100% | 76015.58 | 7615.58 | 25.0051 | 100% | 76015.58 | 0
68 |  | P F of 19mm thick Kota Stone flooring (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, Kotah to be laid with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for service area. | [10 empty] | 0 | 0 |  |  | 0 | 0
69 | 3.3 | 18 mm thick Italian Marble Dado on Lift wall including Jambline | Smt | 61.6 | 529760 | 10995 | 677292 | 61.6 | 50% | 338646 | 3.0412 | 90% | 30094.6894 | -308551.3106 | 3.0412 | 100% | 33438.5437 | 3343.8544
70 |  | At least 18 mm thk polished marble fixed to Plastered masonry, Marble shall be cut from slabs of even thickness, Marble shall be installed with white cement paste, Include all finished marble niches, with V groove edge polish etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, including Approved sealer to be applied on all sides, All visible edges of Marble shall be mirror polished, Basic cost of marble Rs 450 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
71 | 3.4 | 18 mm thick Exotic Italian Marble Cladding on signage wall | Smt | 26.2 | 360250 | 19660 | 515092 | 26.2 | 40% | 206036.8 | 19.155 | 90% | 338928.57 | 132891.77 | 19.155 | 100% | 376587.3 | 37658.73
72 |  | At least 18 mm thk polished marble fixed to Plastered masonry, Marble shall be cut from slabs of even thickness, Marble shall be installed with white cement paste, Include all finished marble niches, with V groove edge polish etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, including Approved sealer to be applied on all sides, All visible edges of Marble shall be mirror polished, Basic cost of marble Rs 1000 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
73 | 3.5 | Marble finish Planter Box | nos | 2 | 188500 | 105000 | 210000 | 2 | 40% | 84000 | 2 | 90% | 189000 | 105000 | 2 | 100% | 210000 | 21000
74 |  | As per Drawing- Size up to 1800 mm in length x 600 mm wide 600 mm high, Planter box Frame to be made 50 mm x 38 mm MS box Frame, Planter Skirting Base to be Covered with 12 mm thick FRP Ply and 50 mm high 16g 304 grade SS satin Bronze finish Skirting, Frame Vertical surfaces to be covered with At least 18 mm thk Onyx marble fixed to MS box frame with SS clamps pins and Adhesive from outside , and From in side Base to be finish in ordinary marble and Vertical Surfaces to be covered with 12 mm thick FRP Ply and Laminate with Mirror Screw ( openable Panel ), Including 6 mm thick 304 grade SS satin Bronze finish top Trim, etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, including Approved sealer to be applied on all sides, All visible edges of Marble shall be mirror polished, Basic cost of marble Rs 1500 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
75 | 3.6 | Kota Stone Skirting 150 mm high | Rmt | 40 | 19800 | 637 | 25480 | 40 | 80% | 20384 | 18.33 | 100% | 11676.21 | -8707.79 | 18.33 | 100% | 11676.21 | 0
76 |  | P F of 19mm thick Kota Stone Skirting (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, Fix as detailed in drawing, fix with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for service area. | [10 empty] | 0 | 0 |  |  | 0 | 0
77 | IV | FRENCH PLASTER WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
78 | 4.1 | Fire line Gypsum board ceiling | Smt | 128 | 260352 | 2034 | 260352 | 128 | 0% | 0 | 65.6822 | 90% | 120237.9067 | 120237.9067 | 65.6822 | 100% | 133597.6741 | 13359.7674
79 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobain Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fiber tape reinforcement, Include finished cutouts for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceilling height is 4300 mm ) | [10 empty] | 0 | 0 |  |  | 0 | 0
80 | 4.2 | Curved Feature ceiling with facia in Water cut Enamal Paint finish | Smt | 5 | 28750 | 6120 | 30600 | 5 | 0% | 0 | 4.42 | 90% | 24345.36 | 24345.36 | 4.42 | 100% | 27050.4 | 2705.04
81 |  | All MS framework for ceiling to be used, 50mm x 50 mm, MS Box framework at 600 mm c c fixed to Existing MS framework Wall and Partition frame work with proper welding bolting , Including anti rust paint ,ceiling frame to be covered with 12 mm thick ply from all side and 6+6 mm thick Flexi ply for curved profile, Ply to be covered with 12mm thk MDF board to be used to Received Water cut Enamal PaintFinish Including 6+6 mm thick for curved profile, All joints to be filled with jointing compound , Include finished cutouts for light fixtures, AC grills . | [10 empty] | 0 | 0 |  |  | 0 | 0
82 | 4.3 | FR Gypsum board Cove for indirect light | [10 empty] | 0 | 0 |  |  | 0 | 0
83 |  | In L shape with 150 mm deep up to 300mm high and 50 mm wide fascia, All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobain Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fiber tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum | [10 empty] | 0 | 0 |  |  | 0 | 0
84 |  | *in Straight Profile | Rmt | 32 | 10400 | 645 | 20640 | 32 | 0% | 0 | 19.315 | 90% | 11212.3575 | 11212.3575 | 19.315 | 100% | 12458.175 | 1245.8175
85 |  | *In Curved Profile | Rmt | 30 | 10800 | 1050 | 31500 | 30 | 0% | 0 | 10.132 | 90% | 9574.74 | 9574.74 | 10.132 | 100% | 10638.6 | 1063.86
86 | 4.4 | POP plaster punning | Smt | 191.9 | 93071.5 | 615 | 118018.5 | 191.9 | 80% | 94414.8 | 139.2821 | 90% | 77092.6424 | -17322.1576 | 139.2821 | 100% | 85658.4915 | 8565.8491
87 |  | Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bull marks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work | [10 empty] | 0 | 0 |  |  | 0 | 0
88 | V | CARPENTRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
89 | 5.1 | Aluminum frame work In Profile for Art work | Smt | 49.56 | 148680 | 3835 | 190062.6 | 49.56 | 60% | 114037.56 |  |  | 0 | -114037.56 |  |  | 0 | 0
90 |  | 36mm x 36 mm, 16 SWG aluminum framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminum angle to be used for assembling paneling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment, including provision for Electrical Conduit and slot for Digital screen as shown in drawing | [10 empty] | 0 | 0 |  |  | 0 | 0
91 | 5.2 | Aluminum frame work For Paneling | Smt | 41.25 | 123750 | 3835 | 158193.75 | 41.25 | 60% | 94916.25 | 27.72 | 100% | 106306.2 | 11389.95 | 27.72 | 100% | 106306.2 | 0
92 |  | 36mm x 36 mm, 16 SWG aluminum framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminum angle to be used for assembling paneling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment, including provision for Electrical Conduit and slot for Digital screen as shown in drawing | [10 empty] | 0 | 0 |  |  | 0 | 0
93 | 5.3 | FRP Ply Paneling | [10 empty] | 0 | 0 |  |  | 0 | 0
94 |  | providing and fixing Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at center of aluminum framework. Edges to be tightly screwed to aluminum framework at 300 mm c c. Edges to be planed properly to receive finish material | [10 empty] | 0 | 0 |  |  | 0 | 0
95 | a | 12 mm thk Fire rated plywood | Smt | 111 | 179154 | 2160 | 239760 | 111 | 60% | 143856 | 150.8806 | 100% | 325902.1975 | 182046.1975 | 150.8806 | 100% | 325902.1975 | 0
96 | b | 15 mm thk Fire rated plywood | Smt | 10 | 21000 | 2740 | 27400 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
97 | c | 18 mm thk Fire rated plywood | Smt | 10 | 23000 | 3280 | 32800 | 10 | 60% | 19680 |  |  | 0 | -19680 |  |  | 0 | 0
98 | d | 6 mm thk Flexi Fire rated plywood | Smt | 10 | 12500 | 1650 | 16500 | 10 | 60% | 9900 |  |  | 0 | -9900 |  |  | 0 | 0
99 | 5.4 | HDF Paneling | [10 empty] | 0 | 0 |  |  | 0 | 0
100 |  | providing and fixing HDF Panel to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of HDF to end at center of framework. Edges to be tightly screwed to framework at 300 mm c c. Edges to be planed properly to receive finish material | [10 empty] | 0 | 0 |  |  | 0 | 0
101 |  | 12 mm thk HDF | Smt | 69.8 | 122359.4 | 1753 | 122359.4 | 69.8 | 60% | 73415.64 |  |  | 0 | -73415.64 |  |  | 0 | 0
102 |  | 6 mm thk Flexi HDF | Smt | 10 | 8710 | 1315 | 13150 | 10 | 60% | 7890 |  |  | 0 | -7890 |  |  | 0 | 0
103 | 5.5 | Fluted Wall paneling in Metallic Duco paint finish | smt | 69.8 | 453700 | 9750 | 680550 | 69.8 | 60% | 408330 | 98.3824 | 90% | 863305.9724 | 454975.9724 | 98.3824 | 100% | 959228.8583 | 95922.8858
104 |  | Using 12 mm thk HDF to be fixed on Existing ply as base , All joints shall be planed and smoothened before installing fluting mouldings.All joints shall be filled with suitable fillers and reinforcement tape, if required. HDF Moldings to be fixed as per drawing ( min 25 mm wide deep ), shall be installed on HDF back surface in perfect plumb, line and level. base and HDF moulding surface shall be finished in metallic duco paint, as approved by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
105 | 5.6 | Backlit Feature Wall Paneling in SS Gold Finish | smt | 13 | 139750 | 19500 | 253500 | 13 | 60% | 152100 | 13.7616 | 75% | 201263.4 | 49163.4 | 13.7616 | 100% | 268351.2 | 67087.8
106 |  | As per Drawing - Size up to 3600 mm wide x 3600 mm high, Feature wall frame work to be made out of 50mm x 100 mm MS Box framework , fixed to Floor slab wall with adequate anchor bolts and plates, Including anti rust paint , Frame to be covered 6 mm thick FRP Flexi Ply, 6+6 mm thick FRP Flexi ply bttens to be made and fix on 6 mm thick base ply with 30 mm Gap,Batten to be covered with 16G, 304 grade SS sheet in C shape Profile ( as per approved design ) sheet in Gold Finish , 30 mm x 40 mm SS Gold finish box insert in Perforated sheet as per drawing, including Vertical provision for Led strip light and Electrical Conduit. Include SS sheet insert in Groove | [10 empty] | 0 | 0 |  |  | 0 | 0
107 | 5.7 | Concrete Finish Fins- in Profile | SQmt | 25.2 | 163800 | 12100 | 304920 | 25.2 | 50% | 152460 | 13.176 | 85% | 135515.16 | -16944.84 | 13.176 | 100% | 159429.6 | 23914.44
108 |  | As per Drawing - Size upto 650 mm wide x 3600 mm high, Fins frame work to be made out of 38mm x 38 mm MS Box framework , fixed to Floor slab wall with adequate anchor bolts and plates, Including anti rust paint , Frame to be covered with 12 mm thick Marin Ply , 4 mm thick HDF to be Fix on ply to received Concrete finish Coating, including Vertical Light Pelmet provision for Led strip light and Electrical Conduit. Include 16 SWG, 304 Grade SS skirting. ( basic cost of Pait Rs 250 sqft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
109 | 5.8 | SS Bronze Satin finish skirting 50mm high | Rmt | 24.2 | 29959.6 | 1500 | 36300 | 24.2 | 40% | 14520 |  |  | 0 | -14520 | 17.675 | 95% | 25186.875 | 25186.875
110 |  | 16 SWG, 304 Grade SS skirting over existing ply, Fixed with epoxy adhesive | [10 empty] | 0 | 0 |  |  | 0 | 0
111 | 5.9 | 400 mm wide Veneer SS finish Portal | Smt | 14.1 | 63450 | 8100 | 114210 | 14.1 | 40% | 45684 |  |  | 0 | -45684 |  |  | 0 | 0
112 |  | Providing and fixing 4 mm thick Venner and 16 G SS 304 cladding as portal, finish in PU and PVD coating | [10 empty] | 0 | 0 |  |  | 0 | 0
113 | 5.1 | TINTED Mirror PANELING | Smt | 42.2 | 158925.2 | 7600 | 320720 | 42.2 | 40% | 128288 | 40.305 | 60% | 183790.8 | 55502.8 | 40.305 | 100% | 306318 | 122527.2
114 |  | Providing and fixing 8 mm thick Tinted Mirror on exisitng ply , Fixed with Approved adhesive | [10 empty] | 0 | 0 |  |  | 0 | 0
115 | 5.11 | Reception Desk - Lecturn for Main Enterance | Nos | 1 | 135000 | 135000 | 135000 | 1 | 40% | 54000 | 1 | 90% | 121500 | 67500 | 1 | 100% | 135000 | 13500
116 |  | Providing and fixing 1000 mm wide x 2000 mm length Reception (Lectrun )desk , finish in Marble SS Veneer. As per detail drawings | [10 empty] | 0 | 0 |  |  | 0 | 0
117 | 5.12 | Reception Desk - Lecturn for Service lift Entry | Nos | 1 | 67500 | 67500 | 67500 | 1 | 40% | 27000 | 1 | 90% | 60750 | 33750 | 1 | 100% | 67500 | 6750
118 |  | Providing and fixing 1000 mm wide x 1000 mm length Reception (Lectrun )desk , finish in Marble SS Veneer. As per detail drawings | [10 empty] | 0 | 0 |  |  | 0 | 0
119 | 5.13 | Service room Spa room Door in Fluted design matching to fluted paneling in metallic Paint Finish | No | 2 | 150000 | 75000 | 150000 | 2 | 40% | 60000 | 2 | 85% | 127500 | 67500 | 2 | 100% | 150000 | 22500
120 |  | Size 1000mm x 2250mm | [10 empty] | 0 | 0 |  |  | 0 | 0
121 |  | Door Frame | [10 empty] | 0 | 0 |  |  | 0 | 0
122 |  | Overall finish size 250mm x 50 mm thk without rebate,Door frame to be Made up Using 18 mm thick FRP ply as rough ground, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 4 mm thk HDF, Rebate to be separately put in CP wood, including , Wood to be treated with anti-termite medicine, Frame to be finish in Approved Metallic Duco paint finish | [10 empty] | 0 | 0 |  |  | 0 | 0
123 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
124 |  | Overall size 900 mm wide x 2250 mm ht. x 1 leaf, up to 67 mm thk. Using 38 mm thick readymade fireproof shutter covered with 12 mm thick FRP ply on both sides. The shutter shall be clad with 4 mm thick mdf on one side Laminate on other side including NBTW beading all around. including 25x25mm HDF strip press on HDF side on shutter as per drawings, Shutter and MDF strip be finish in Approved Metallic duco paint finish | [10 empty] | 0 | 0 |  |  | 0 | 0
125 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
126 |  | 125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, Dead lock with suitable cover plate, Concealed door closer by Hafele Dorma as per required capacity, 1 set of handle as approved by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
127 | 5.14 | Fire Hose reel Double leaf Glass Door | nos | 1 | 25650 | 48750 | 48750 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
128 |  | Shutter-Size 1200mm x 2250mm | [10 empty] | 0 | 0 |  |  | 0 | 0
129 |  | As per drawing, Using 6 mm toughened glass Door with Powder coated Aluminum frame , all edges CNC machine polished | [10 empty] | 0 | 0 |  |  | 0 | 0
130 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
131 |  | The shutter shall be mounted on min. 3 nos. bearing SS copper finished hinges with proprietary screws, made by Hafele Dorma or equivalent approved by Architect. handle with locking arrangement, by Hafele or equivalent approved, | [10 empty] | 0 | 0 |  |  | 0 | 0
132 | 5.15 | Service Door_Dining Area | No | 1 | 90000 | 105000 | 105000 | 1 | 50% | 52500 | 1 | 85% | 89250 | 36750 | 1 | 100% | 105000 | 15750
133 |  | Size 1500mm x 2250mm Double Leaf | [10 empty] | 0 | 0 |  |  | 0 | 0
134 |  | Door Frame | [10 empty] | 0 | 0 |  |  | 0 | 0
135 |  | Overall finish size 250mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick FRP ply as rough ground, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk New burma teak wood, Rebate to be separately put in rough ground frame, Wood to be treated with anti-termite medicine, Frame to be finish in Approved Melamine polish | [10 empty] | 0 | 0 |  |  | 0 | 0
136 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
137 |  | Overall size 750 mm wide x 2250 mm ht. x 2 leaf, up to 67 mm thk. Using 38 mm thick readymade fireproof shutter covered with 12 mm thick FRP ply on both sides. The shutter shall be clad with 4 mm thick Veneer from lounge side and other side 1 mm thick approved Laminate, including NBTW beading all around. Shutter to be finish in Approved Melamine polish , Including Vision panel as per drawing. | [10 empty] | 0 | 0 |  |  | 0 | 0
138 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
139 |  | Heavy duty floor Spring by Hafle or Dorma, Dead lock with suitable cover plate, including 300 mm wide SS kick plate from both side of shutter, 1 set of handle as approved by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
140 |  | PAINTING WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
141 | 6.1 | Duco Paint to Walls Partition | smt | 20 | 45500 | 3287 | 65740 | 20 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
142 |  | Sanding and preparing surface for receiving paint, Final coats of Duco paint. Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
143 | 6.2 | Concrete texture finish Coating | smt | 15 | 56250 | 4000 | 60000 | 15 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
144 |  | Paint By Evolve-mumbai ( basic cost of Pait Rs 250 sqft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
145 | 6.3 | Artificial Silver Gold leafing on ceiling | smt | 36 | 149400 | 4150 | 149400 | 36 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
146 |  | Surface to be ready with putty and primer, to receive metal leaf, Metal leafing to be applied over surface by skilled labour, Metal leaf to be installed as per approved sample, Stain coating to be applied as per approved sample, 2 coats of protective coating in matt glossy finish, as instructed by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
147 | 6.4 | Luster Painting to walls | smt | 160 | 78720 | 650 | 104000 | 160 |  | 0 |  |  | 0 | 0 | 189.0874 | 90% | 110616.1407 | 110616.1407
148 |  | Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of luster paint. Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
149 | 6.5 | Painting to ceiling in acrylic emulsion paint | smt | 180 | 86400 | 650 | 117000 | 180 |  | 0 |  |  | 0 | 0 | 49.3579 | 90% | 28874.3715 | 28874.3715
150 |  | Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base. Two coats of putty ,Three coats of acrylic emulsion paint, Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
151 | 6.6 | Black matt paint to walls, beams structural frame and ceiling above false ceiling | smt | 60 | 18000 | 735 | 44100 | 60 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
152 |  | Sanding and preparing surface for receiving paint, Oil based, black matt paint to be applied in two coats, Clean surface before applying | [10 empty] | 0 | 0 |  |  | 0 | 0
153 | I | CIVIL WORK - fine dine live kitchen | [10 empty] | 0 | 0 |  |  | 0 | 0
154 | 1.1a | 18 mm thick Italian Marble flooring in Various Marble shade and in strip form Pattern - for Dining | Smt | 121 | 1107150 | 13450 | 1627450 | 121 | 60% | 976470 | 104.0446 | 90% | 1259459.3988 | 282989.3988 | 104.0446 | 100% | 1399399.332 | 139939.9332
155 |  | Marble strip size up to 50 to 225 mm wide in various length, Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides , with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
156 | 1.1b | Kotah tile Flooring for Live Kitchen | smt | 20 | 39000 | 3040 | 60800 | 20 | 90% | 54720 | 17.193 | 100% | 52266.72 | -2453.28 | 17.193 | 100% | 52266.72 | 0
157 |  | P F of 19mm thick Kota Stone flooring (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, Kotah to be laid with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for kitchen service area. | [10 empty] | 0 | 0 |  |  | 0 | 0
158 | 1.1c | 18 mm thick Italian Marble flooring black and white tile form- for Dining | Smt | 60 | 555000 | 12260 | 735600 | 60 | 50% | 367800 | 39 | 90% | 430326 | 62526 | 39 | 100% | 478140 | 47814
159 |  | Marble tile size up to 600 mm x 600 mm- Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealent, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides, with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 550 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
160 | 1.2 | Joint less ceramic tiles cladding ( behind Buffet counter ) | smt | 10 | 19200 | 1920 | 19200 | 10 | 40% | 7680 |  |  | 0 | -7680 |  |  | 0 | 0
161 |  | Cladding shall comprise of ceramic tile of 300 mm x 300 mm, Tiles to be fixed in ordinary Portland cement only, Tiles to be put with Spacer required with Leticrete grout in joints in plumb, Joints to be filled with matching grout.(Basic cost of ceramic tiles at Rs.30 sft) make Johnson Somany Kajaria Nitco | [10 empty] | 0 | 0 |  |  | 0 | 0
162 | 1.3 | Vitrified tile For Live Kitchen | smt | 47.6 | 157080 | 3690 | 175644 | 47.6 | 80% | 140515.2 | 36.189 | 100% | 133537.41 | -6977.79 | 36.189 | 100% | 133537.41 | 0
163 |  | Clean existing wall surface before fixing tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, Tiles to be put with Spacer required with Leticrete grout in joints in plumb, Joints to be filled with matching grout. preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.150 sft without tax | [10 empty] | 0 | 0 |  |  | 0 | 0
164 | 1.4 | Italian Marble Wall Cladding | smt | 18.78 | 161508 | 11050 | 207519 | 18.78 | 50% | 103759.5 | 25.035 | 90% | 248973.075 | 145213.575 | 25.035 | 100% | 276636.75 | 27663.675
165 |  | Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to fire rated plywood panelling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
166 | 1.5 | Italian Marble Finish Band | rmt | 7 | 40250 | 6550 | 45850 | 7 | 50% | 22925 | 14.9 | 90% | 87835.5 | 64910.5 | 14.9 | 100% | 97595 | 9759.5
167 |  | Size up to 400 Mm high, Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to Fire rated plywood panelling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
168 | 1.6 | Marble Portal Architrave ( 50 mm wide 400 mm deep ) | rmt | 12 | 49200 | 6550 | 78600 | 12 | 50% | 39300 | 5.382 | 90% | 31726.89 | -7573.11 | 5.382 | 100% | 35252.1 | 3525.21
169 |  | All around in C profile Pasted over existing ply surface with epoxy adhesive brass pins, Ply surface shall be cleaned before installing marble, At least 18mm thk marble to be fixed, Marble shall be cut as per size laid with tight hairline joints, Edge of marble shall be polished before installation, Joints to be filled with Tim-X or equivalent joint filler, Special care to be taken to fix marble on horizontal surface. Shall rest over ply at one end and vertical marble on the other, The vertical marble over 50 mm shall be fixed using brass pins . including Approved sealer to be applied on all sides (Basic cost of Marble at Rs.450 sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
170 | 1.7 | Marble Skirting | rmt | 10 | 13260 | 2830 | 28300 | 10 | 40% | 11320 | 14.8 | 90% | 37695.6 | 26375.6 | 14.8 | 100% | 41884 | 4188.4
171 |  | up to 150 mm high Skirting with 18 MM thick Italian Marble including Edge Moulding, etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, All visible edges of Marble shall be mirror polished, including Approved sealer to be applied on all sides ( Basic cost of marble Rs 450 sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
172 | II | FRENCH PLASTER WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
173 | 2.1 | Fire line Gypsum board ceiling | Smt | 20 | 40680 | 2034 | 40680 | 20 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
174 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobain Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cut-outs for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceiling height is 4300 mm ) | [10 empty] | 0 | 0 |  |  | 0 | 0
175 | 2.4 | POP plaster punning | Smt | 39 | 18915 | 615 | 23985 | 39 | 80% | 19188 | 46.5836 | 100% | 28648.914 | 9460.914 | 46.5836 | 100% | 28648.914 | 0
176 |  | Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bull marks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work | [10 empty] | 0 | 0 |  |  | 0 | 0
177 | III | CARPENTRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
178 | 3.1 | Aluminium framework for panelling | Smt | 75 | 228750 | 3835 | 287625 | 75 | 50% | 143812.5 |  |  | 0 | -143812.5 |  |  | 0 | 0
179 |  | 50mm x 25 mm, 16 SWG aluminium framework at 600 mm c c fixed to wall, 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable packing to be provided behind framework for correct alignment, | [10 empty] | 0 | 0 |  |  | 0 | 0
180 | 3.2 | Veneer finish Panelling in batten form - Vertical and Horizontal | Smt | 39.14 | 273980 | 13600 | 532304 | 39.14 | 40% | 212921.6 | 33.8206 | 90% | 413964.144 | 201042.544 | 33.8206 | 100% | 459960.16 | 45996.016
181 |  | Providing and fixing 150 mm wide batten form, Using 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, pressed over 12 mm thick backing Fire rated plywood including matching wood beading as per approved design, with 12 mm x 12mm finish groove as per design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be Finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
182 | 3.3 | Free standing low height Partition in Curved Profile- 1350 mm High | Smt | 9.72 | 99630 | 13600 | 132192 | 9.72 | 50% | 66096 | 12.501 | 80% | 136010.88 | 69914.88 | 12.501 | 95% | 161512.92 | 25502.04
183 |  | 50mm x 50 mm, MS Box framework at 600 mm c c fixed to Floor slab with adequate anchor bolts and plates, 25 mm x 25mm, 4 mm thick MS angle to be used for assembling Partition framework, with proper welding , Framework to be fixed to Floor in perfect plum, line and level, Including anti rust paint, Frame to be covered with 6+6 mm thick ply for Curved Profile , Ply to be covered with 4 mm thick veneer, 232 mm high x 38 mm thick Veneer finish Fins to be fixed on veneer surface with 50 mm gap, including 50 mm high SS bronze satin finish Band in L C shape as per drawings, Veneer to be Finished in Approved Melamine Polish, including 18 mm thick 125 mm wide Italian Marble top band to be fixed on the Ply with edge moulding and polishing. Provision to be made for fixing partition bracket light (Basic cost of veneer at Rs.125 sft) (Basic cost of Marble at Rs. 550 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
184 | 3.4 | Free standing low height Partition in straight Profile-1350 mm high | Smt | 12.45 | 146287.5 | 13600 | 169320 | 12.45 | 50% | 84660 | 21.3 | 80% | 231744 | 147084 | 21.3 | 95% | 275196 | 43452
185 |  | 50mm x 50 mm, MS Box framework at 600 mm c c fixed to Floor slab with adequate anchor bolts and plates, 25 mm x 25mm, 4 mm thick MS angle to be used for assembling Partition framework, with proper welding , Framework to be fixed to Floor in perfect plum, line and level, Including anti rust paint, Frame to be covered with 12 mm thick Fire rated plywood , Ply to be covered with 4 mm thick veneer, 232 mm high x 38 mm thick Veneer finish Fins to be fixed on veneer surface with 50 mm gap, including 50 mm high SS bronze satin finish Band in L C shape as per drawings, Veneer to be Finished in Approved Melamine Polish, including 18 mm thick 125 mm wide Italian Marble top band to be fixed on the Ply with edge moulding and polishing. Provision to be made for fixing partition bracket light (Basic cost of veneer at Rs.125 sft) (Basic cost of Marble at Rs. 550 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
186 | 3.5 | Fluted glass screen with SS Flat trim- 300 mm high | Rmt | 3 | 8610 | 3150 | 9450 | 3 | 40% | 3780 | 5.4 |  | 0 | -3780 | 5.4 | 60% | 10206 | 10206
187 |  | 10 mm thick Fluted Glass panel with 6 mm thick SS flat band around the glass , SS in bronze satin finish, Fixed to marble top Trim , as shown in drawing, including fluted glass film | [10 empty] | 0 | 0 |  |  | 0 | 0
188 | 3.6 | Buffet serving counter - in U shape | Nos | 1 | 497250 | 565000 | 565000 | 1 | 40% | 226000 | 1 | 80% | 452000 | 226000 | 1 | 95% | 536750 | 84750
189 |  | Size 11500mm length x 800mm depth x 950mm ht. | [10 empty] | 0 | 0 |  |  | 0 | 0
190 |  | As per drawing, Serving counter structure constructed out of 18 mm thk Fire rated plywood, At least 18 mm thk approved Marble fixed to top with fascia in profile shown in drawing - including Mirror polish. Marble to be tightly placed together and shall have mitre joints on edges including moulding as approved by Architect. All joints to be filled with matching colour TIM-X or equivalent grout filler. Ventilation space to be created within carcass as per drawing and all internal non visible surfaces shall be in Black matt paint. Carcass to be covered with 12mm thk DuPont Corian fluted panel on all exposed surfaces including Led strip light provision,150 mm high skirting boxing to be made in 18 mm thick ply covered with Italian marble. Ventilation space fascia to be covered with 8 mm thick SS jali. SS jali in Bronze Satin finish, as per approved design. Including all cut-outs for electrical points, induction plates and temperature devices. (Basic cost of Marble at Rs. 450 sft ) (Basic cost of Corian at Rs. 850 sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
191 | 3.7 | Coffee Station | [10 empty] | 0 | 0 |  |  | 0 | 0
192 |  | Size 1800mm length x 750mm depth x 950mm ht. | nos | 1 | 0 | 87500 | 87500 | 1 | 60% | 52500 | 1 | 80% | 70000 | 17500 | 1 | 100% | 87500 | 17500
193 |  | As per drawing, counter structure constructed out of 18 mm thk Fire rated plywood, At least 18 mm thk approved marble fixed to TOP with 50 mm high fascia, At least 18 mm thk approved marble fixed to skirting up to 200 mm high, Marble pieces to be tightly placed together and shall have mitre joints on edges, All joints to be filled with matching colour TIM-X or equivalent joint filler, 30 mm thick shelf to made, shelf to be covered with 4 mm thk veneer from top bottom with 0.40 mm thk wooden face pressed on front side, All Internal Surface to be covered with 4 mm thick veneer, Veneer Wood to be Finished in Approved Melamine Polish, 200 mm high skirting boxing to be made in 18 mm thick marine ply covered with marble, with openable panel, Provision to be made in counter for water inlet point drain outlet, Including all cut-outs for electrical points. (Basic cost of veneer at Rs.125sft) (Basic cost of Marble at Rs. 450 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
194 | 3.8 | SS Screen in Satin Bronze finish | smt | 5 | 78000 | 27500 | 137500 | 5 | 60% | 82500 | 4.62 | 70% | 88935 | 6435 | 4.62 | 80% | 101640 | 12705
195 |  | Overall size- 4500 mm wide x 1000 mm height, 304 grade SS screen to be made out of 3 mm thick Sheet ( cris-cross pattern ), SS frame in Satin Bronze finish as approved by Architect, frame fixed to Wall and above ceiling Bulkhead, | [10 empty] | 0 | 0 |  |  | 0 | 0
196 | 3.9 | TV FIDS surround frame | nos | 3 | 29250 | 15750 | 47250 | 3 | 60% | 28350 | 1 | 90% | 14175 | -14175 | 1 | 100% | 15750 | 1575
197 |  | Size up to ( 1200 mm x 1350 mm ), Using 3 4 thick ply carcass as TV surround, like a picture frame including 50 to 75 mm wide surround finished in 4 mm thick veneer to receive polycot paint, Rear portion of TV surround covered with 1 mm thick laminate, To be fixed on wall panelling with adequate supports | [10 empty] | 0 | 0 |  |  | 0 | 0
198 | 3.1 | 18 mm thick Glass Shelf | nos | 4 | 16800 | 4500 | 18000 | 4 | 40% | 7200 |  |  | 0 | -7200 |  |  | 0 | 0
199 |  | size - 1500MMX350MM- using 18 mm thick toughen glass shelf including SS Patch fittings ( Haffle or Dorma ) | [10 empty] | 0 | 0 |  |  | 0 | 0
200 | 3.11 | Glass Display BOX with SS pipe in Satin Bronze - 300 mm ht. | nos | 1 | 20750 | 24750 | 24750 | 1 | 40% | 9900 | 1 | 0% | 0 | -9900 | 1 | 80% | 19800 | 19800
201 |  | size - 300MM X4500MM- Made of Box frame using 25 x25 x2.5 mm thick SS box pipe in Satin bronze finish, and frame to be covered with 12 mm thick toughen Glass as per detail drawing | [10 empty] | 0 | 0 |  |  | 0 | 0
202 | 3.12 | Glass Display BOX with SS pipe in Satin Bronze - 200 mm ht. | nos | 1 | 17750 | 21750 | 21750 | 1 | 40% | 8700 | 1 | 0% | 0 | -8700 | 1 | 80% | 17400 | 17400
203 |  | size - 200MM X4500MM- Made of Box frame using 25 x25 x2.5 mm thick SS box pipe in Satin bronze finish, and frame to be covered with 12 mm thick toughen Glass as per detail drawing | [10 empty] | 0 | 0 |  |  | 0 | 0
204 | 3.13 | Service door-Veneer laminate finish including top fixed panel | No | 1 | 55000 | 75500 | 75500 | 1 | 50% | 37750 | 1 | 90% | 67950 | 30200 | 1 | 100% | 75500 | 7550
205 |  | Size 900mm x 2250mm | [10 empty] | 0 | 0 |  |  | 0 | 0
206 |  | Door Frame | [10 empty] | 0 | 0 |  |  | 0 | 0
207 |  | Overall finish size 200mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick marine ply as rough ground,, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk marine ply 4 mm thick Approved Veneer, Rebate to be separately put in wood, Wood to be treated with anti-termite medicine, Frame to be finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
208 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
209 |  | Overall size 800 mm wide x 2250 mm ht. x 1 leaf, up to 40 mm thk. Using 35 mm thick readymade fireproof shutter covered with 4 mm thick approved veneer from Lounge side and other side 1 mm thick approved Laminate, (basic cost of veneer up to Rs. 125 sft) (basic cost of laminate Rs 1600 sheet) | [10 empty] | 0 | 0 |  |  | 0 | 0
210 |  | Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
211 |  | Frame entire door to be to be Finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
212 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
213 |  | 125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, Dead lock with suitable cover plate , and Magnetic latch, 1 set of handle as approved by architect | [10 empty] | 0 | 0 |  |  | 0 | 0
214 | 3.14 | Wooden finish Capital for Column | Rmt | 10 | 48500 | 6750 | 67500 | 10 | 40% | 27000 | 6.8 | 90% | 41310 | 14310 | 6.8 | 100% | 45900 | 4590
215 |  | size up to 300 mm Deep- Providing and fixing 75 mm thick Veneer finish Capital including adequate MS frame and 12 mm thick Fire rated plywood, ply to be covered with 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, including matching wood beading as per approved design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be Finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
216 | 3.15 | Bulk Head in Profile- In Flat Water cut Paint finish | rmt | 22 | 233200 | 31800 | 699600 | 22 | 50% | 349800 | 29.35 | 95% | 886663.5 | 536863.5 | 29.35 | 100% | 933330 | 46666.5
217 |  | As per drawing -Size up to 600 mm wide x 1850 mm high, Using 50mm x 36 mm, 16 SWG aluminium framework at 600 mm c c Fixed on existing Structural Framework, Frame to be covered with 18 mm thick marine ply, For Curve surface use 6+6+6 mm flexi ply, 12 mm thick HDF to be fixed on Ply, For Curve surface use 6+6 mm flexi HDF, All joints shall be filled with suitable fillers and reinforcement tape, 50 mm wide x 25 mm thick HDF fluting to be fixed on HDF surface with 25 mm gap, Base and HDF moulding surface shall be finished n Water cut enamal Paint finish, as approved by Architect, include 450 mm wide x 100 mm thick veneer finish Band at bottom, Veneer to be finished in Approved Melamine polish . Including 2 layers of light Pelmet with Led strip light provision. (Basic cost of veneer up to Rs. 125 -sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
218 | 3.16 | Veneer finish Ceiling | Sqmt | 10 | 96840 | 10200 | 102000 | 10 | 50% | 51000 | 8.93 | 95% | 86531.7 | 35531.7 | 8.93 | 100% | 91086 | 4554.3
219 |  | As per drawing - Using 50mm x 36 mm, 16 SWG aluminium framework at 600 mm c c Fixed on existing Structural Framework, Frame to be covered with 18 mm thick marine ply, ply to be covered with 4 mm thick approved Veneer, Veneer to be Finished in Approved waterbase PU polish . (Basic cost of veneer up to Rs. 125 -sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
220 | 3.17 | Corian finish fluted panelling | rmt | 6 | 51600 | 10980 | 65880 | 6 | 50% | 32940 | 4.55 | 60% | 29975.4 | -2964.6 | 4.55 | 95% | 47461.05 | 17485.65
221 |  | Providing and fixing up to 50 mm wide x 600 umm high Corian batten form, Using 12 mm thk approved Corian sheet , pressed over 12 mm thick backing Fire rated plywood as per approved design, with 12 mm x 6 mm finish groove as per design, Pressing shall be free of defects, Basic cost of Corian at Rs.900 sft without tax | [10 empty] | 0 | 0 |  |  | 0 | 0
222 | 3.18 | Brick Cladding on Existing taper column | smt | 18 | 50940 | 3570 | 64260 | 18 | 40% | 25704 | 23.8748 | 95% | 80971.3842 | 55267.3842 | 23.8748 | 100% | 85233.036 | 4261.6518
223 |  | Clean existing wall Ply surface before fixing brick tile cladding Before starting, carefully read the suppliers laying plan and instructions. Decorative Brick tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.120 sft without tax | [10 empty] | 0 | 0 |  |  | 0 | 0
224 | 3.19 | Built In seating In Profile- for Dining Area ( Part of Phase-1 ) | [10 empty] | 0 | 0 |  |  | 0 | 0
225 |  | Partition in Curved Profile | [10 empty] | 0 | 0 |  |  | 0 | 0
226 |  | 50mm x 50 mm, MS Box framework at 600 mm c c fixed to Floor slab with adequate anchor bolts and plates, 25 mm x 25mm, 4 mm thick MS angle to be used for assembling Partition framework, with proper welding , Framework to be fixed to Floor in perfect plum, line and level, Including anti rust paint, Frame to be covered with 12 mm thick plywood and 6+6 mm thick ply for Curved Profile , Ply to be covered with 4 mm thick veneer, 232 mm high x 38 mm thick Veneer finish Fins to be fixed on veneer surface with 50 mm gap, including 50 mm high SS bronze satin finish Band in L C shape as per drawings, Veneer to be Finished in Approved Melamine Polish, including 18 mm thick 125 mm wide Italian Marble top band to be fixed on the Ply with edge moulding and polishing. Provision to be made for fixing partition barcket light (Basic cost of veneer at Rs.125 sft) (Basic cost of Marble at Rs. 2000 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
227 |  | Built-in seating -Seat | [10 empty] | 0 | 0 |  |  | 0 | 0
228 |  | up to 100 mm thk foam rubber seat pasted to 18 mm thk ply base , 25 mm thk., 32 density PU foam to cover rubber seat, PU foam to be covered with 6 mm thk. sheet before finishing seat in white cloth,Final finished in approved fabric leatherite (Basic cost of fabric at Rs.2500 rmt) | [10 empty] | 0 | 0 |  |  | 0 | 0
229 |  | Built-in seating- Back | [10 empty] | 0 | 0 |  |  | 0 | 0
230 |  | Back rest to be fixed to rear partition .Up to 25mm thk. Foam rubber pasted to back rest, in Fluted profile, 25 mm thk., 32 density PU foam to cover rubber sheet, PU foam to be covered with 6 mm thk sheet before finishing in white cloth,Final finished in approved fabric leatherite (Basic cost of fabric at Rs.2500 rmt) | [10 empty] | 0 | 0 |  |  | 0 | 0
231 | a | Fixed Seating Sofa - Size - 9650 mm length x860 mm deep x 1200 mm height | nos | 1 | 225000 | 225000 | 225000 | 1 | 50% | 112500 | 1 | 70% | 157500 | 45000 | 1 | 90% | 202500 | 45000
232 | b | Fixed Seating Sofa - Size -7200 mm length x860 mm deep x 1200 mm height | nos | 2 | 336000 | 168000 | 336000 | 2 | 50% | 168000 | 2 | 70% | 235200 | 67200 | 2 | 90% | 302400 | 67200
233 | 3.2 | Standy Tall Table - In profile | Nos | 12 | 0 | 42750 | 513000 | 12 | 40% | 205200 | 8 | 70% | 239400 | 34200 | 8 | 90% | 307800 | 68400
234 |  | Size 65 mm thick 1050mm length x 450 deep x1140 mm ht. | [10 empty] | 0 | 0 |  |  | 0 | 0
235 |  | Using 35mmx25mm Aluminium frame, 400x400 mm c c both ways, Frame to be covered with 8 mm thick ply, Top ply including 200 mm drop to be covered with 12 mm thick corian, Bottom ply to be covered with 1 mm thick laminate with balance vertical ply to be covered with 4 mm thick veneer with additional 12 mm ply backing to match the thickness, Provision to be made to pass conduit for electrical points, including boxing to receive pop up box and SS finish Foot rail, Veneer to be Finished in Approved Melamine Polish , including 50 mm wide 6 mm thick 304 grade SS Base in Satin Bronze finish (Basic cost veneer Rs.125 sft) (Basic cost of corian Rs.850 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
236 | IV | PAINTING WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
237 | 4.1 | Luster Painting to walls | smt | 10 | 4920 | 650 | 6500 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
238 |  | Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of luster paint. Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
239 | 4.2 | Painting to ceiling in acrylic emulsion paint | smt | 20 | 9600 | 650 | 13000 | 20 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
240 |  | Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base. Two coats of putty ,Three coats of acrylic emulsion paint, Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
241 | 4.3 | Black matt paint to walls, beams structural frame and ceiling above false ceiling | smt | 10 | 3000 | 715 | 7150 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
242 |  | Sanding and preparing surface for receiving paint, Oil based, black matt paint to be applied in two coats, Clean surface before applying | [10 empty] | 0 | 0 |  |  | 0 | 0
243 |  | Tea Lounge | [5 empty] | 0 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
| 1.1 | 10 mm thick Terrazo Flooring in Pattern | Smt | 110 | 759000 | 10686 | 1175460 | 110 | 30% | 352638 | 105.073 | 90% | 1010529.0029 | 657891.0029 | 105.073 | 90% | 1010529.0029 | 0
244 |  | Supply and application of 10mm thick Epoxy Resin Terrazzo flooring system (12 mm laid grinded to 10 mm) Flexural strength = 25MPa as per ASTM D790,Tensile strength = 14 MPa as per ASTM D638. The product must have elongation = 5%, when tested as per ASTM D638. Hardness of the floor must be = 75, when tested as per Shore D hardness test. Co-efficient of linear thermal expansion of the product will be approximately 13.3x10-6. This product should have flammability of not more than 0.025inch minute when tested as per ASTM D 635. IGBC certified product.Typical properties of the resin needs to be achieved in laboratory tests at 50% Relative Humidity. Fire Resistance BS476-7 Spread of Flame Class 2Slip Resistance TRRL Pendulum Slip Test Dry > 40 low slip potential.Temperature Resistance Tolerant up to 60 C .Water Permeability Nil – Karsten Test(Impermeable) Abrasion Resistance Taber Abrader - 50 mg loss per 1000 cycles(1kg load using CS17 wheels). Compressive Strength > 55 N mm2 (BS6319), Bond Strength Greater than cohesive strength of 25 N mm2 concrete. >1.5 MPa. Toxicity (when cured) Taint Free to sensitive foodstuffs. Epoxy terrazzo layer to be applied over Epoxy high build primer and needs to be properly finished, grinded and polished with suitable transparent abrasion resistant material. The complete system of Epoxy Resin Terrazzo flooring needs to be executed by an authorized applicator of the manufacturer and as per the approved method statement of the manufacturer. Providing and application of Divider termination Trim of 2mm- 2.5mm thick L SS , Providing and application of Momex Joint , Providing and application of PU Sealant at terminations | [10 empty] | 0 | 0 |  |  | 0 | 0
245 |  | COUNTER AND LEDGES | [10 empty] | 0 | 0 |  |  | 0 | 0
246 | 1.2 | Tea Bar counter in Curved Profile | nos | 1 | 575000 | 575000 | 575000 | 1 | 30% | 172500 | 1 | 70% | 402500 | 230000 | 1 | 95% | 546250 | 143750
247 |  | Size 9000mm length x 650 mm depth x 1100mm ht. | [10 empty] | 0 | 0 |  |  | 0 | 0
248 |  | Apron partition | [10 empty] | 0 | 0 |  |  | 0 | 0
249 |  | 38 mm x 38 Aluminum Box framework made up thickness up to 100 mm wide, frame to be covered with 6+6 mm thick flexi Fire rated plywood on both sides for curved profile, At least 12 mm thk Corean fixed to apron In Approved design pattern and in profile, Corean to be tightly placed together and shall have seamless joints on edges, Bartender side of Apron partition shall have 1.5 mm thk approved laminate below counter top, Including 200 mm high 16G 304 grade SS satin Bronze finish Skirting . Including provision for Food Display unit (Basic cost of Corean at Rs.800 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
250 |  | Preparation counter | [10 empty] | 0 | 0 |  |  | 0 | 0
251 |  | Size up to 600 mm wide Preparation counter structure constructed out of 18 mm thk Fire rated plywood In laminate finish, 18 mm thick Veneer finish Shutter Including matching wood beading on all exposed plywood edges, Venner Beading to be finish in approved Duco paint, 16 mm thk Terrazo counter tops with 50 mm thk top edge on all sides, (Basic cost of Terrazo at Rs.750 sft) (Basic cost Veneer at Rs.100 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
252 |  | Serving counter top in profile | [10 empty] | 0 | 0 |  |  | 0 | 0
253 |  | Upto 350 mm wide Serving Counter top,75 mm facia Including provision for Led strip profile light, comprising of 38x38 mm Aluminium framework covered with Fire rated plywood , At least 16 mm thk approved Terrazo stone fixed to on counter Ply top, Bottom ply of serving top shall have 1.5 mm thk approved laminate on bottom side, Exclude electrical point wiring light source within counter top, (Basic cost of Terrazo at Rs.750 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
254 | 1.3 | Terrazo finish Bar Back unit | [10 empty] | 0 | 0 |  |  | 0 | 0
255 |  | Size 6500mm length x 600mm depth x 900 mm ht. | nos | 1 | 178000 | 305000 | 305000 | 1 | 50% | 152500 | 1 | 90% | 274500 | 122000 | 1 | 95% | 289750 | 15250
256 |  | Back unit structure constructed out of 18 mm thk Fire rated plywood with vertical support in the center, Plywood to be covered with 18 mm thick Terrazo top and back wall, with 50 mm thick Terrazo Facia, with mitre joints , Marble pieces to be tightly placed together and shall have mitre joints on edges, All joints to be filled with matching colour joint filler, All edges of stone to be polished. including 18 mm thick duco paint finish Shutter (Basic cost of Terrazo at Rs.750 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
257 | II | CARPENTRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
258 | 2.1 | Low height Curved Partition ( 1500 mm high ) Attached to Built in Seating | rmt | 15 | 277500 | 20530 | 307950 | 15 | 60% | 184770 | 14.2 | 80% | 233220.8 | 48450.8 | 14.2 | 90% | 262373.4 | 29152.6
259 |  | As per drawing, overall thichness up to 100 mm, using 50mm x 50 mm MS box framework, 6+6 mm thk Flexi Fire rated plywood fixed to framework from all side, Ply to be covered with 4 mm thick approved veneer finish with Approved waterbase PU polish from outer side ( corridor side ), and approved duco paint finish from in side ( tea lounge side ), 10 mm thick x 250 high Curved rib Glass to be fix in the partition including 6 mm thick 304 grade SS bronze satin finish Top trim including 50 mm wide vertical support as shown in drawing, all veneer to be Finished in Approved waterbase PU polish, including provision for pole light (Basic cost of veneer at Rs.150 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
260 | 2.2 | Low height Curved Partition ( 1500 mm high ) with moulding panel behind counter | rmt | 10 | 185000 | 24750 | 247500 | 10 | 60% | 148500 | 8.3 | 80% | 164340 | 15840 | 8.3 | 90% | 184882.5 | 20542.5
261 |  | As per drawing, overall thichness up to 100 mm, using 50mm x 50 mm MS box framework, 6+6 mm thk Flexi Fire rated plywood fixed to framework from all side, Ply to be covered with 4 mm thick approved veneer finish with Approved waterbase PU polish from outer side ( corridor side ), and approved duco paint finish from in side including half round moulding panel ( tea lounge side ), 10 mm thick x 250 high Curved rib Glass to be fix in the partition including 6 mm thick 304 grade SS bronze satin finish Top trim including 50 mm wide vertical support as shown in drawing, all veneer to be Finished in Approved waterbase PU polish, including provision for pole light (Basic cost of veneer at Rs.150 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
262 | 2.3 | Low height Curved Partition ( 600 mm high ) for Planter | rmt | 4 | 30000 | 9750 | 39000 | 4 | 60% | 23400 |  |  | 0 | -23400 |  |  | 0 | 0
263 |  | As per drawing, overall thichness up to 100 mm, using 50mm x 50 mm MS box framework, 6+6 mm thk Flexi Fire rated plywood fixed to framework from all side, Ply to be covered with 4 mm thick approved veneer finish with Approved waterbase PU polish from outer side ( corridor side ), and approved Marble cladding from in side , including 6 mm thick 304 grade SS bronze satin finish Top trim as shown in drawing, all veneer to be Finished in Approved waterbase PU polish, (Basic cost of veneer at Rs.150 sft) (Basic cost of marble at Rs.450 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
264 | 2.4 | SS Foot Rail | rmt | 12 | 27000 | 4600 | 55200 | 12 | 40% | 22080 |  |  | 0 | -22080 |  |  | 0 | 0
265 |  | up to 200 mm high -Providing and fixing in position 304 grade S.S Satin Bronze finish foot rail of 38mm diameter with horizontal vertical members, Grouting in concrete, etc. complete, as specified and as directed by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
266 | 2.5 | Built-in seating -Seat | rmt | 15 | 203430 | 32750 | 491250 | 15 | 60% | 294750 | 14.2 | 70% | 325535 | 30785 | 14.2 | 90% | 418545 | 93010
267 |  | Carcus to be made out of 38mm x 38 mm Aluminium framework and 18 mm thk plywood , up to 100 mm thk foam rubber seat pasted to 18 mm thk ply base , 25 mm thk., 32 density PU foam to cover rubber seat, PU foam to be covered with 6 mm thk. sheet before finishing seat in white cloth, Final fabric leather shall be nailed on bottom side of plywood base, Including reccesed SS Skirting ,(Basic cost of fabric at Rs.2500 rmt) | [10 empty] | 0 | 0 |  |  | 0 | 0
268 | 2.6 | Tea Garden Tree with Roof in Oval Profile | rmt | 1 | 345750 | 1175000 | 1175000 | 1 | 40% | 470000 | 1 | 80% | 940000 | 470000 | 1 | 95% | 1116250 | 176250
269 |  | Size 6300mm dia x 1800mm wide x 3600mm ht. | [10 empty] | 0 | 0 |  |  | 0 | 0
270 |  | Main Tree Base | [10 empty] | 0 | 0 |  |  | 0 | 0
271 |  | Using 50 mm x 50 MS Box framework , frame to be covered with 6+6 mm thick flexi HDF for curved profile, ply to be covered with 50 mm wide x 150 mm deep Vertical fins in profile as shown in drawings, 50 mm wide horizontal band to be provide at every 500 mm as shown in drawing , All expose surface of Metal and HDF to be finish in Approve Duco paint, Including providion for Electrcial wire manger and light and light handing system | [10 empty] | 0 | 0 |  |  | 0 | 0
272 |  | Roof | [10 empty] | 0 | 0 |  |  | 0 | 0
273 |  | Roof to be made Using 50 mm x 50 MS Box framework as per drawing, frame all side to be covered with 6 mm thick HDF in profile, use 10 mm thick rib glass roof panel as shown in drawing , All expose surface of Metal and HDF to be finish in Approve Duco paint, | [10 empty] | 0 | 0 |  |  | 0 | 0
274 |  | Capical ring | [10 empty] | 0 | 0 |  |  | 0 | 0
275 |  | On existing roof frame Upto 300 mm high Roof top band to be made using 6mm thick HDF, HDF to be coverd with Bronze finish SS as aproved by architect | [10 empty] | 0 | 0 |  |  | 0 | 0
276 |  | Civil Interior work for sports relax lounge | [10 empty] | 0 | 0 |  |  | 0 | 0
277 | 1.1 | 18 mm thick Italian Marble flooring | Smt | 40 | 340000 | 10795 | 431800 | 40 | 70% | 302260 | 26.2393 | 90% | 254928.2981 | -47331.7019 | 26.2393 | 100% | 283253.6645 | 28325.3665
278 |  | Marble strip size up to 50 to 225 mm wide in various length, Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides , with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
279 | 1.2 | 18 mm thick Italian Marble flooring in Various Marble shade and in Pattern - for Sports Bar | Smt | 252 | 2142000 | 13450 | 3389400 | 252 | 70% | 2372580 | 153.3542 | 90% | 1856352.9057 | -516227.0943 | 153.3542 | 100% | 2062614.3397 | 206261.434
280 |  | Marble strip size up to 50 to 225 mm wide in various length, Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides, with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
281 | 1.3 | Vitrified tile Flooring for Bar Store room | smt | 30 | 97500 | 3690 | 110700 | 30 | 80% | 88560 | 17.86 | 100% | 65903.4 | -22656.6 | 17.86 | 100% | 65903.4 | 0
282 |  | SUPPLYING AND LAYING VITRIFIED FLOOR TILES OF 600 X 600 MM SIZE OF FIRST QUALITY,CONFIRMING TO IS 13006 PL-LBE OF RAK CERAMICS EURO NITCO KAJARIA OR EQUIVALENT,DESIGN AND SHADE AS APPROVED, FIXED OVER 30 MM AVERAGE THICK BASE OF CEMENT MARTOR 1 4 (1 CEMENT 4 COARSE SAND)LAID WITH CEMENT SLURRY,INCLUDING PREPAIRING THE BASE,FILLING WITH WHITE CEMENT PASTE OF APPROVED MATCHING COLOUR AND SHADE ETC.CLEANING ALL COMPLETE AS PER DIRECTION OF ENGINEER-IN- CHARGE. basic cost of tile Rs.150 sft without tax | [10 empty] | 0 | 0 |  |  | 0 | 0
283 | 1.4 | Joint less ceramic tiles cladding ( behind Display screen and store room) | smt | 100.8 | 199584 | 2360 | 237888 | 100.8 | 40% | 95155.2 |  |  | 0 | -95155.2 |  |  | 0 | 0
284 |  | Cladding shall comprise of ceramic tile of 300 mm x 600 mm, Tiles to be fixed in ordinary Portland cement only, Tiles to be put with Spacer required with Leticrete grout in joints , in plumb, Joints to be filled with matching grout . (Basic cost of ceramic tiles at Rs.60 sft) make Johnson Somany Kajaria Nitco | [10 empty] | 0 | 0 |  |  | 0 | 0
285 | 1.5 | Vitrified tile Cladding for Inside Bar wall | smt | 12 | 24960 | 2360 | 28320 | 12 | 40% | 11328 | 10.535 | 90% | 22376.34 | 11048.34 | 10.535 | 100% | 24862.6 | 2486.26
286 |  | Cladding shall comprise of vitrified tile of 600 mm x 600 mm, Tiles to be fixed in ordinary Portland cement only, Tiles to be put with Spacer required with Leticrete grout in joints in plumb, Joints to be filled with matching grout . (Basic cost of vitrified tiles at Rs.60 sft) make Johnson Somany Kajaria Nitco | [10 empty] | 0 | 0 |  |  | 0 | 0
287 | 1.6 | Italian Marble Wall Cladding | smt | 7 | 60200 | 11050 | 77350 | 7 | 40% | 30940 |  |  | 0 | -30940 |  |  | 0 | 0
288 |  | Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to Fire rated plywood panelling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, including Approved sealer to be applied on all sides, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
289 |  | COUNTER AND LEDGES | [10 empty] | 0 | 0 |  |  | 0 | 0
290 | 1.7 | Sports Bar counter in Profile | nos | 1 | 597500 | 597500 | 597500 | 1 | 50% | 298750 | 1 | 90% | 537750 | 239000 | 1 | 100% | 597500 | 59750
291 |  | Size 11500mm length x 1050mm depth x 1150mm ht. | [10 empty] | 0 | 0 |  |  | 0 | 0
292 |  | Apron partition | [10 empty] | 0 | 0 |  |  | 0 | 0
293 |  | 50 mm x 50 Aluminum Box framework made up thickness up to 150 mm wide, frame to be covered with 18 mm thk Fire rated plywood on both sides on straight surfaces including 6+6 mm thick flexi FRP ply for curved profile,18 mm thk plywood boxing fixed over partition with FRP plywood frame grid at regular intervals, At least 18 mm thk Flutted Marble fixed to apron In Approved design pattern and in profile, Marble to be tightly placed together and shall have seamless joints on edges, including sealer coat of all side, Marble joint should not be visible, Bartender side of Apron partition shall have 12 mm thick Corian fixed above preparation counter and 1.5 mm thk approved laminate below counter top, Including 200 mm high 16G 304 grade SS satin Bronze finish Skirting (Basic cost of solid surface (Corian) at Rs.850 sft) (Basic cost of Marble at Rs.1000 Sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
294 |  | Preparation counter | [10 empty] | 0 | 0 |  |  | 0 | 0
295 |  | Size up to 650 mm wide Preparation counter structure constructed out of 18 mm thk Fire rated plywood In laminate finish, Include matching wood beading on all exposed plywood edges, Beading to be polished and coated with 1 coat sealer and 2 coats of PU finish in approved matt glossy ratio, 12 mm thk Corian counter tops with 32 mm thk top edge on all sides, (Basic cost of solid surface (Corian) at Rs.850 sft) (Basic cost of laminate at Rs.1500 sheet) | [10 empty] | 0 | 0 |  |  | 0 | 0
296 |  | Serving counter top in profile | [10 empty] | 0 | 0 |  |  | 0 | 0
297 |  | Upto 450 mm wide Serving Counter top, 100 mm facia Including provision for Led strip light, comprising of 1st quality CP teakwood framework with Fire rated plywood on bottom side, At least 18 mm thk approved Onyx stone fixed to on counter Ply top, Bottom ply of serving top shall have 1.5 mm thk approved laminate on bottom side, Include 100 mm x 10 mm thk SS Satin Bronze edges Facia fixed to serving top edges on both sides (with one side openable for maintaining LEd strip Light ), with suitable adhesive, Exclude electrical point wiring light source within counter top, (Basic cost of Onyx Rs 1500 sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
298 | 1.8 | Marble finish Bar Back unit | [10 empty] | 0 | 0 |  |  | 0 | 0
299 |  | Size 3500mm length x 750mm depth x 975 mm ht. | nos | 1 | 85000 | 175000 | 175000 | 1 | 50% | 87500 | 1 | 80% | 140000 | 52500 | 1 | 100% | 175000 | 35000
300 |  | Back unit structure constructed out of 18 mm thk Fire rated plywood with vertical support in the center, Plywood to be covered with 18 mm thick Marble top and back wall, with 50 mm thick marble Facia, with mitre joints , Marble pieces to be tightly placed together and shall have mitre joints on edges, All joints to be filled with matching colour TIM-X or equivalent joint filler, All edges of stone to be mirror edge polished. including 75x75 mm SS Satin Bronz finish Architrave as per detail drawing, Side panel to be finish with 4 mm thick veneer with 12 mm thick back ply Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be Finished in Approved waterbase PU Polish, 8 mm thick tinted mirro paneling with 12 mm thick FRP back ply and including 12 mm thick Glass shelve as per disign including 1 mm thick laminate finish paneling behind TV back (Basic cost of veneer at Rs.150 sft) (Basic cost of marble Rs 450 sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
301 | II | CARPENTRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
302 | 2.1 | Aluminum frame work ( for Paneling Cladding ) | Smt | 40 | 122000 | 3950 | 158000 | 40 | 50% | 79000 | 38.688 | 100% | 152817.6 | 73817.6 | 38.688 | 100% | 152817.6 | 0
303 |  | 50mm x 36 mm, 16 SWG aluminum framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminum angle to be used for assembling paneling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plumb, line and level, Suitable bracket to be provided behind framework for correct alignment, | [10 empty] | 0 | 0 |  |  | 0 | 0
304 |  | REFER DRAWING-00B01-TFS-DOM02-ID-07-03 11 12 | [10 empty] | 0 | 0 |  |  | 0 | 0
305 | 2.2 | Ply Paneling | [10 empty] | 0 | 0 |  |  | 0 | 0
306 |  | providing and fixing Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at center of aluminum framework. Edges to be tightly screwed to aluminum framework at 300 mm c c. Edges to be planed properly to receive finish material | [10 empty] | 0 | 0 |  |  | 0 | 0
307 | a | 12 mm thk Fire rated plywood | Smt | 113.5 | 183189 | 2160 | 245160 | 113.5 | 60% | 147096 | 41.299 | 100% | 89205.84 | -57890.16 | 41.299 | 100% | 89205.84 | 0
308 | b | 15 mm thk Fire rated plywood | Smt | 10 | 21000 | 2740 | 27400 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
309 | c | 18 mm thk Fire rated plywood | Smt | 10 | 23000 | 3280 | 32800 | 10 | 60% | 19680 |  |  | 0 | -19680 |  |  | 0 | 0
310 | d | 6 mm thk Flexi Fire rated plywood | Smt | 10 | 12800 | 1650 | 16500 | 10 | 80% | 13200 | 21.708 | 100% | 35818.2 | 22618.2 | 21.708 | 100% | 35818.2 | 0
311 | 2.3 | Veneer skin for Straight curved surfaces | Smt | 53.6 | 317204.8 | 6133 | 328728.8 | 53.6 | 40% | 131491.52 |  |  | 0 | -131491.52 |  |  | 0 | 0
312 |  | Using 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, pressed over backing plywood including matching wood beading as per approved design, with 3 mm x 3mm finish groove as per design including on column surface, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be Finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
313 |  | (Basic cost of veneer upto Rs. 150 -sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
314 | 2.4 | Wooden finish Capital for Column | Rmt | 10 | 48500 | 6500 | 65000 | 10 | 60% | 39000 |  |  | 0 | -39000 |  |  | 0 | 0
315 |  | size up to 300 mm Deep- Providing and fixing 75 mm thick Veneer finish Capital including adequate MS frame and 12 mm thick Fire rated plywood, ply to be covered with 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, including matching wood beading as per approved design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
316 | 2.5 | Veneer finish Panelling in batten form - Vertical and Horizontal | Smt | 49.44 | 358440 | 7950 | 393048 | 49.44 | 40% | 157219.2 | 40.2596 | 85% | 272054.247 | 114835.047 | 40.2596 | 100% | 320063.82 | 48009.573
317 |  | Providing and fixing 50 to 100 mm wide batten form, Using 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, pressed over 12 mm thick backing fire rated plywood including matching wood beading as per approved design, with 12 mm x 12mm finish groove as per design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
318 | 2.6 | Low height Curved Partition ( 1100 mm high ) | rmt | 33 | 461340 | 15250 | 503250 | 33 | 40% | 201300 | 30.52 | 90% | 418887 | 217587 | 30.52 | 90% | 418887 | 0
319 |  | As per drawing, 50mm x 50 mm MS framework, 6+6 mm thk Flexi Fire rated plywood fixed to Aluminum framework from all side, Ply to be covered with 4 mm thick veneer finish with Approved waterbase PU polish, 10 mm thick x 250 high Curved rib Glass to be fix in the partition including 6 mm thick 304 grade SS bronze satin finish Top trim including 50 mm wide vertical support, veneer to beFinished in Approved waterbase PU polish, (Basic cost of veneer at Rs.125 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
320 | 2.7 | Community table ( 1600 mm long x 650 mm wide) | nos | 6 | 51000 | 39750 | 238500 | 6 | 40% | 95400 | 6 | 50% | 119250 | 23850 | 6 | 80% | 190800 | 71550
321 |  | as per drawing Using 50 x 50 mm SS Base Frame in satin bronze finish, Frame top to be covered with 18 mm thick sleeper wooden plank, to beFinished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
322 | 2.8 | SS Bronze Satin finish 50 mm high skirting | rmt | 17 | 17850 | 1500 | 25500 | 17 | 40% | 10200 |  |  | 0 | -10200 | 1.83 | 90% | 2470.5 | 2470.5
323 |  | 16 SWG, 304 Grade SS skirting over existing ply, Fixed with epoxy adhesive | [10 empty] | 0 | 0 |  |  | 0 | 0
324 | 2.9 | SS Foot Rail | rmt | 17 | 38250 | 3900 | 66300 | 17 | 40% | 26520 |  |  | 0 | -26520 | 12 | 80% | 37440 | 37440
325 |  | up to 200 mm high -Providing and fixing in position 304 grade S.S Satin Bronze finish foot rail of 38mm diameter with horizontal vertical members, Grouting in concrete, etc. complete, as specified and as directed by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
326 | 2.1 | TV FIDS surround frame | nos | 4 | 39000 | 14750 | 59000 | 4 | 50% | 29500 | 3 | 100% | 44250 | 14750 | 3 | 100% | 44250 | 0
327 |  | Size up to ( 1200 mm x 1350 mm ), Using 3 4 thick ply carcass as TV surround, like a picture frame including 50 to 75 mm wide surround finished in 4 mm thick veneer to receive polycot paint, Rear portion of TV surround covered with 1 mm thick laminate, To be fixed on wall panelling with adequate supports | [10 empty] | 0 | 0 |  |  | 0 | 0
328 | 2.11 | Brick Cladding on Existing taper column | smt | 60 | 168000 | 3620 | 217200 | 60 | 40% | 86880 | 44.3697 | 100% | 160618.4588 | 73738.4588 | 44.3697 | 100% | 160618.4588 | 0
329 |  | Clean existing wall Ply surface before fixing brick tile cladding Before starting, carefully read the suppliers laying plan and instructions. Decorative Brick tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of tiles at Rs.120 sft without tax | [10 empty] | 0 | 0 |  |  | 0 | 0
330 | 2.12 | Corian finish Wicked door | nos | 1 | 26582 | 32750 | 32750 | 1 | 40% | 13100 | 1 | 60% | 19650 | 6550 | 1 | 90% | 29475 | 9825
331 |  | Door size 950mm wide x 1150 height, 50 mm x 50 Aluminum framework for shutter, frame to be covered with 12 mm thk Fire rated plywood from all sides , At least 12 mm thk Corian fixed In Approved design pattern ( mixed of 2 Corian finishes )From guest side and in side plain, Corian to be tightly placed together and shall have seamless joints on edges, Corian joint should not be visible, Including 200 mm high 16G 304 grade SS satin Bronze finish band at door bottom matching to bar counter skirting . (Basic cost of solid surface (Corian) at Rs.850 sft) | [10 empty] | 0 | 0 |  |  | 0 | 0
332 | 2.13 | Service door-Veneer laminate finish including top fixed panel | No | 1 | 62750 | 79450 | 79450 | 1 | 50% | 39725 | 1 | 80% | 63560 | 23835 | 1 | 95% | 75477.5 | 11917.5
333 |  | Size 950mm x 2250mm | [10 empty] | 0 | 0 |  |  | 0 | 0
334 |  | Door Frame | [10 empty] | 0 | 0 |  |  | 0 | 0
335 |  | Overall finish size 200mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick FRP ply as rough ground,, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk FRP ply 4 mm thick Approved Veneer, Rebate to be separately put in wood, Wood to be treated with anti-termite medicine, Frame to be finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
336 |  | Shutter Overall size 850 mm wide x 2250 mm ht. x 1 leaf, up to 40 mm thk. Using 35 mm thick readymade fireproof shutter covered with 4 mm thick approved veneer from Lounge side and Above veener fix 50 mm wide wooden batten as per drawing and store room side 1 mm thick approved Laminate, Veneer and wood to be finish in approved waterbase PU polish (basic cost of veneer up to Rs. 150 sft) (basic cost of laminate Rs 1600 sheet) | [10 empty] | 0 | 0 |  |  | 0 | 0
337 |  | Polish Frame entire door to be to be finish in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
338 |  | Hardware 125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, Dead lock with suitable cover plate , and Magnetic latch, 1 set of handle as approved by architect ( Make Dorma Hafle ) | [10 empty] | 0 | 0 |  |  | 0 | 0
339 | III | PAINTING WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
340 | 3.1 | Luster Painting to walls | smt | 26 | 12792 | 650 | 16900 | 26 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
341 |  | Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of luster paint. Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
342 | 3.2 | Painting to ceiling in acrylic emulsion paint | smt | 10 | 4800 | 650 | 6500 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
343 |  | Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base. Two coats of putty ,Three coats of acrylic emulsion paint, Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
344 |  | SPA Area | [10 empty] | 0 | 0 |  |  | 0 | 0
345 | I | DEMOLITION WORK | LS | 1 | 0 | 0 | 0 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
346 | II | MASONRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
347 | 2.1 | P C of 200mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level. | Sq. Mtr. | 17.2 | 35260 | 3346.79 | 57564.79 | 17.2 | 80% | 46051.8304 | 173.8639 | 100% | 581885.7945 | 535833.9641 | 173.8639 | 100% | 581885.7945 | 0
348 | 2.2 | P C of 100mm solid concrete block masonry made of solid concrete blocks conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All divider walls up to 4300mm ht of internal divider walls at toilet area. | Sq. Mtr. | 4 | 6888 | 2342.75 | 9371 | 4 |  | 0 | 27.6737 | 100% | 64832.6778 | 64832.6778 | 27.6737 | 100% | 64832.6778 | 0
349 | 2.3 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr. | 38.4 | 24960 | 777.2 | 29844.48 | 38.4 | 80% | 23875.584 | 165.379 | 100% | 128532.5588 | 104656.9748 | 165.379 | 100% | 128532.5588 | 0
350 | 2.4 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr. | 111.8 | 50980.8 | 777.2 | 86890.96 | 111.8 | 80% | 69512.768 | 55.8219 | 100% | 43384.7807 | -26127.9873 | 55.8219 | 100% | 43384.7807 | 0
351 | 2.5 | P C of 150mm thick screed with 100mm thick broken AAC (Siporex) Block, broken siporex block to be laid on the waterproofing treated floor in proper levelling, after laying of the siporex block, void area to be filled up with Siporex or equivalent light weight materials including making of 50mm thick IPS flooring in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Complete as per instruction by the site engineer. | Sq. Mtr. | 5 | 9000 | 2677.43 | 13387.15 | 5 | 80% | 10709.72 | 35.6463 | 100% | 95440.473 | 84730.753 | 35.6463 | 100% | 95440.473 | 0
352 | 2.6 | P C of 50mm 75mm thick screed in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Laying the same in proper line level on the seating area s floor to maintain the floor levelling to get the smooth surface to lay the finishing floor materials on the said surface. Complete as per architectural detail drawings instruction by the site engineer. | Sq. Mtr. | 65 | 57850 | 892.48 | 58011.2 | 65 | 80% | 46408.96 |  |  | 0 | -46408.96 |  |  | 0 | 0
353 | III | CIVIL FINISHES WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
354 |  | FLOORING | [10 empty] | 0 | 0 |  |  | 0 | 0
355 | 3.1 | Italian Marble Flooring | smt | 5 | 42500 | 10795 | 53975 | 5 | 40% | 21590 | 3.0753 | 90% | 29877.5914 | 8287.5914 | 3.0753 | 100% | 33197.3238 | 3319.7324
356 |  | Clean existing sub floor thoroughly. Flooring shall consist of Marble as per drawing, Up to 50 mm thick bedding mortar as per tech specs. Marble slabs shall be minimum 18 mm thick, laid as per tech specs, Marble to be cut as per size and laid with tight hairline joints. Joint filling and finishing as per tech specs.(On site cost of Italian marble @ Rs.450 sft without tax) including Approved sealer to be applied on all sides, Including sealer coat , Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover | [10 empty] | 0 | 0 |  |  | 0 | 0
357 | 3.2 | 10 mm thick Terrazzo Flooring | Smt | 60 | 414000 | 10350.26 | 621015.6 | 60 | 40% | 248406.24 | 55.5756 | 90% | 517699.7187 | 269293.4787 | 55.5756 | 100% | 575221.9097 | 57522.191
358 |  | Supply and application of 10mm thick Epoxy Resin Terrazzo flooring system (12 mm laid grinded to 10 mm) Flexural strength = 25MPa as per ASTM D790,Tensile strength = 14 MPa as per ASTM D638. The product must have elongation = 5%, when tested as per ASTM D638. Hardness of the floor must be = 75, when tested as per Shore D hardness test. Co-efficient of linear thermal expansion of the product will be approximately 13.3x10-6. This product should have flammability of not more than 0.025inch minute when tested as per ASTM D 635. IGBC certified product. Typical properties of the resin needs to be achieved in laboratory tests at 50% Relative Humidity. Fire Resistance BS476-7 Spread of Flame Class 2Slip Resistance TRRL Pendulum Slip Test Dry > 40 low slip potential. Temperature Resistance Tolerant up to 60 C .Water Permeability Nil – Karsten Test(Impermeable) Abrasion Resistance Taber Abrader - 50 mg loss per 1000 cycles(1kg load using CS17 wheels). Compressive Strength > 55 N mm2 (BS6319), Bond Strength Greater than cohesive strength of 25 N mm2 concrete. >1.5 MPa. Toxicity (when cured) Taint Free to sensitive foodstuffs. Epoxy terrazzo layer to be applied over Epoxy high build primer and needs to be properly finished, grinded and polished with suitable transparent abrasion resistant material. The complete system of Epoxy Resin Terrazzo flooring needs to be executed by an authorized applicator of the manufacturer and as per the approved method statement of the manufacturer. Providing and application of Divider termination Trim of 2mm- 2.5mm thick L SS , Providing and application of Momex Joint , Providing and application of PU Sealant at terminations | [10 empty] | 0 | 0 |  |  | 0 | 0
359 |  | CLADDING | [10 empty] | 0 | 0 |  |  | 0 | 0
360 | 3.3 | Synthetic Marble Wall Cladding with Grooves | smt | 21 | 112560 | 8397.96 | 176357.16 | 21 | 60% | 105814.296 | 21.4 | 85% | 152758.8924 | 46944.5964 | 21.4 | 100% | 179716.344 | 26957.4516
361 |  | Clean existing wall surface before fixing wall cladding. Slabs shall be min. 18 mm thick fixed to plastered siporex block work, Slabs shall be installed as per tech specs on plastered wall siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Synthetic marble @ Rs.275 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
362 | 3.4 | Italian Marble Wall Cladding | smt | 3 | 25500 | 11217.95 | 33653.85 | 3 | 60% | 20192.31 |  |  | 0 | -20192.31 |  |  | 0 | 0
363 |  | Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to Fire rated plywood panelling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves chamfer edge moulding, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
364 | 3.5 | Synthetic Marble Jamb lining for common Toilet Door Openings | rmt | 7 | 11200 | 2559.97 | 17919.79 | 7 | 60% | 10751.874 |  |  | 0 | -10751.874 |  |  | 0 | 0
365 |  | Marble jamb lining for EWC doors including rebate, up to 230 mm wide, up to 2250 mm ht all around, At least 18 mm thk per-polished slabs to be used, Slabs to be cut as per approved size drawings, Include mitre joints at all junctions as per Architects instructions, Including V groove to match wall cladding, Marble to be fitted with white cement only, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides (Basic cost of Synthetic Marble at Rs.275 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
366 | 3.6 | Italian Marble Finish Wash Basin Counter for toilet | rmt | 1 | 13966 | 30776.37 | 30776.37 | 1 | 60% | 18465.822 |  |  | 0 | -18465.822 |  |  | 0 | 0
367 |  | The counter shall be supported on 38mm x 38mm x 5mm thk MS angle fixed to block work. Brackets shall be inserted within wall by at least 125mm, MS brackets shall be coated with 2 coats of anti-corrosive paint and 3 coats of synthetic enamel paint, 18mm thk ordinary Indian marble placed within bracket and screwed through bracket, At least 20mm thk cement mortar bedding in 1 4 ratio, Pre-finished and pre-polished marble slabs shall be fixed as per tech specs. Counter shall have up to 300 mm wide fascia marble with mitre joints All top edges of counter shall have chamfer moulding. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides. Including all plumbing cutout as shown in drawing | [10 empty] | 0 | 0 |  |  | 0 | 0
368 |  | (Basic cost of marble at Rs.450 sft including fibre filling polish) | [10 empty] | 0 | 0 |  |  | 0 | 0
369 | 3.7 | Sink counter including under counter shutter | rmt | 1.8 | 48600 | 37577.78 | 67640 | 1.8 | 50% | 33820.002 | 1.7 | 85% | 54299.8921 | 20479.8901 | 1.7 | 100% | 63882.226 | 9582.3339
370 |  | Size 1800mm length x 450mm depth x 850mm ht. | [10 empty] | 0 | 0 |  |  | 0 | 0
371 |  | As per drawing, Sink counter structure constructed out of 18 mm thk plywood, At least 16 mm thk approved Terrazzo Stone fixed to top with 50 mm thick front fascia and back flash in profile shown in drawing - including polish. stone to be tightly placed together and shall have mitre joints on edges including moulding as approved by Architect. All joints to be filled with matching colour TIM-X or equivalent grout filler. Carcass internal surface to be covered with 1mm thk approved laminate , all exposed surfaces including shutter to be finished in approved veneer, Veneer to be Finished in Approved water base PU polish, including 50 mm high SS skirting , as per approved design. Including all cutouts for electrical points, (Basic cost of Terrazzo at Rs. 750 sft ) (Basic cost of Veneer at Rs. 150 sft ) excluding sink | [10 empty] | 0 | 0 |  |  | 0 | 0
372 | 3.8 | Synthetic Marble Portal 450 mm wide | rmt | 15.5 | 34100 | 6801.41 | 105421.86 | 15.5 |  | 0 | 10.5 | 60% | 42848.883 | 42848.883 | 10.5 | 100% | 71414.805 | 28565.922
373 |  | Using 16mm thick marble Pasted over existing ply surface with epoxy adhesive brass pins, Ply surface shall be cleaned before installing marble, At least 16mm thk marble to be fixed, Marble shall be cut as per size laid with tight hairline joints, Edge of marble shall be polished before installation, Joints to be filled with Tim-X or equivalent joint filler, Including 2 high Marble fascia, Approved sealer to be applied on all sides. Special care to be taken to fix marble on horizontal surface. Shall rest over ply at one end and vertical marble on the other, The vertical marble over 50 mm shall be fixed using brass pins | [10 empty] | 0 | 0 |  |  | 0 | 0
374 |  | (Basic cost of Synthetic Marble at Rs.275 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
375 | IV | FRENCH PLASTER WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
376 | 4.1 | Fire line Gypsum board ceiling | smt | 65 | 130524.55 | 2008.07 | 130524.55 | 65 | 40% | 52209.82 | 58.4556 | 100% | 117382.9367 | 65173.1167 | 58.4556 | 100% | 117382.9367 | 0
377 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobain Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceiling height is 4300 mm ) | [10 empty] | 0 | 0 |  |  | 0 | 0
378 | 4.2 | Fire line Gypsum board Facia Band 50 mm TO 100 mm | rmt | 25 | 11250 | 651.8 | 16295 | 25 |  | 0 | 0 |  | 0 | 0 | 3.4 | 100% | 2216.12 | 2216.12
379 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum | [10 empty] | 0 | 0 |  |  | 0 | 0
380 | 4.3 | Indirect Light Coves in Ceiling | rmt | 5 | 2000 | 769.88 | 3849.4 | 5 |  | 0 | 6.4 | 100% | 4927.232 | 4927.232 | 6.4 | 100% | 4927.232 | 0
381 |  | In L shape with 100 mm deep up to 300mm high and 50 mm wide fascia, All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum | [10 empty] | 0 | 0 |  |  | 0 | 0
382 | 4.4 | Fire line Gypsum board slit 100 mm TO 150 mm wide | rmt | 10 | 4000 | 878.52 | 8785.2 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
383 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum | [10 empty] | 0 | 0 |  |  | 0 | 0
384 | 4.5 | Fire line Gypsum board slit 50 mm wide for curtain | rmt | 20 | 8000 | 1095.78 | 21915.6 | 20 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
385 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum | [10 empty] | 0 | 0 |  |  | 0 | 0
386 | 4.6 | Universal plaster punning on wall | smt | 134.4 | 63840 | 557.8 | 74968.32 | 134.4 | 80% | 59974.656 | 56.0731 | 100% | 31277.5752 | -28697.0808 | 56.0731 | 100% | 31277.5752 | 0
387 |  | Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bullmarks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work. | [10 empty] | 0 | 0 |  |  | 0 | 0
388 | V | CARPENTRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
389 | 5.1 | Aluminium frame work for Partition | smt | 10.75 | 28917.5 | 3904.59 | 41974.34 | 10.75 | 60% | 25184.6055 | 8.7606 | 100% | 34206.5512 | 9021.9457 | 8.7606 | 100% | 34206.5512 | 0
390 |  | 50mm x 36 mm, 16 SWG aluminium framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment. | [10 empty] | 0 | 0 |  |  | 0 | 0
391 | 5.2 | Aluminium frame work For Panelling boxing | Smt | 31.5 | 96075 | 3904.59 | 122994.58 | 31.5 | 60% | 73796.751 | 81.6864 | 100% | 318951.7444 | 245154.9934 | 81.6864 | 100% | 318951.7444 | 0
392 |  | 36mm x 36 mm, 16 SWG aluminium framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment, including provision for Electrical Conduit and slot for Digital screen as shown in drawing | [10 empty] | 0 | 0 |  |  | 0 | 0
393 | 5.3 | Ply Panelling | [10 empty] | 0 | 0 |  |  | 0 | 0
394 |  | providing and fixing marine plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at center of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material | [10 empty] | 0 | 0 |  |  | 0 | 0
395 | a | 12 mm thk plywood | Smt | 68.2 | 110074.8 | 2231.19 | 152167.16 | 68.2 | 60% | 91300.2948 | 93.147 | 100% | 207828.5657 | 116528.2709 | 93.147 | 100% | 207828.5657 | 0
396 | b | 15 mm thk plywood | Smt | 5 | 10500 | 2788.99 | 13944.95 | 5 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
397 | c | 18 mm thk plywood | Smt | 5 | 11500 | 3346.79 | 16733.95 | 5 | 60% | 10040.37 |  |  | 0 | -10040.37 |  |  | 0 | 0
398 | d | 6 mm thk Flexi plywood | Smt | 5 | 6400 | 1673.4 | 8367 | 5 | 60% | 5020.2 |  |  | 0 | -5020.2 |  |  | 0 | 0
399 | 5.4 | SS Jali in Satin Bronze finish with fixed glass partition | smt | 8 | 185200 | 27889.92 | 223119.36 | 8 | 60% | 133871.616 | 6.6 | 60% | 110444.0832 | -23427.5328 | 6.6 | 90% | 165666.1248 | 55222.0416
400 |  | Overall size- 1200 mm wide x 3000 mm height, Outer frame in SS hollow frame of 38 mm x50mm x 2.5 mm thickness all around each jali panel, all welded and polished joints, SS frame in Satin Bronze finish as approved by Architect, Outer frame fixed to floor and above false ceiling, using 8 mm thick MS plate with anchor bolt. including 10 mm thk 304 grade SS pipe jali as per approved design and in Satin Bronze finish, | [10 empty] | 0 | 0 |  |  | 0 | 0
401 |  | providing and fixing 10 mm thick toughen fix glass panel with 12 mm wide SS Beading around glass | [10 empty] | 0 | 0 |  |  | 0 | 0
402 | 5.5 | Decorative Toilet Vanity Mirrors | smt | 1.5 | 13350 | 23427.53 | 35141.3 | 1.5 | 40% | 14056.518 | 3.9396 | 50% | 46147.5486 | 32091.0306 | 3.9396 | 90% | 83065.5875 | 36918.0389
403 |  | The mirrors shall be mounted on a backing of marine ply of overall 20 to 25 mm thickness, which shall be fixed to the wall. Including provision for LED strip light. Mirror shall be 8 mm thick to receive bevelling and shall be laminated at the back for protection, and backed with felt lining. All Mirrors shall have 18-25 mm bevelling on all edges. All edges of mirror shall have CNC edge polish, Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect. exclude cost of LED strip lighting | [10 empty] | 0 | 0 |  |  | 0 | 0
404 | 5.6 | Plain mirror panelling | smt | 6 | 45000 | 13387.16 | 80322.96 | 6 |  | 0 | 5.22 | 50% | 34940.4876 | 34940.4876 | 5.22 | 90% | 62892.8777 | 27952.3901
405 |  | The mirrors shall be mounted on a backing of marine ply of overall 18 mm thickness, which shall be fixed to the wall. Including L shape SS finish Angle profile covering on All around the mirror. Mirror shall be 8 mm thick to receive bevelling and shall be laminated at the back for protection, and backed with felt lining. All Mirrors shall have 18-25 mm bevelling on all edges. All edges of mirror shall have CNC edge polish. Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect. | [10 empty] | 0 | 0 |  |  | 0 | 0
406 | 5.7 | Tinted mirror panelling | smt | 6 | 45000 | 14502.76 | 87016.56 | 6 | 50% | 43508.28 | 8.2324 | 50% | 59696.1882 | 16187.9082 | 8.2324 | 95% | 113422.7576 | 53726.5694
407 |  | The mirrors shall be mounted on a backing of marine ply of overall 12 mm thickness, which shall be fixed to the wall. Including SS inserts as per drawings, including 50 mm wide C shape profile covering on All around the mirror. Mirror shall be 8 mm thick and shall be laminated at the back for protection, and backed with felt lining. All edges of mirror shall have CNC edge polish. Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect. | [10 empty] | 0 | 0 |  |  | 0 | 0
408 | 5.8 | Fluted Wall panelling in Duco paint finish | smt | 45 | 292500 | 13944.96 | 627523.2 | 45 | 50% | 313761.6 |  |  | 0 | -313761.6 |  |  | 0 | 0
409 |  | Using 12 mm thk HDF to be fixed on 12 mm thick HDF ply base , All joints shall be planed and smoothened before installing fluting mouldings.All joints shall be filled with suitable fillers and reinforcement tape, if required. HDF Moldings to be fixed as per drawing ( min 25 mm wide 12 mm deep ), shall be installed on HDF back surface in perfect plumb, line and level. base and HDF moulding surface shall be finished in duco paint, as approved by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
410 | 5.9 | Wooden strip panelling | smt | 3.42 | 10260 | 16733.95 | 57230.11 | 3.42 | 50% | 28615.0545 | 36.9855 | 85% | 526076.4816 | 497461.4271 | 36.9855 | 100% | 618913.5077 | 92837.0262
411 |  | Providing and fixing 25 mm wide x 12mm thick NBTW wooden strip as shown in drawing, Fixing shall be free of defects, Wooden strip to be Finished in Approved Melamine Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
412 | 5.1 | Veneer finish Retail Display Behind reception table ( 2600 L x450 D x3000 H) | smt | 7.8 | 163800 | 40161.48 | 313259.54 | 7.8 | 50% | 156629.772 | 7.7775 | 80% | 249884.7286 | 93254.9566 | 7.7775 | 95% | 296738.1152 | 46853.3866
413 |  | As per drawing, 12 mm thick plywood fixed to wall, Ply to be covered with 4 mm thick HDF , 36 mm thick Shelf ( 18 +12mm ply + 6 mm thick Corian ) with provision for Led strip lights, Storage unit at bottom, carcus to be made in 18 mm thick ply, internal surface covered with 1mm thick approved laminate, including veneer finish shutter and drawers, including 50 mm high 16G 304 grade SS bronze satin finish Skirting, Veneer to be Finished in Approved Melamine Polish (Basic cost of veneer upto Rs. 125 -sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
414 | 5.11 | Duco paint finish Salon unit ( 3200 L x400 D x3000 H) | smt | 9.6 | 240000 | 44623.87 | 428389.15 | 9.6 | 50% | 214194.576 | 9.394 | 80% | 335357.3078 | 121162.7318 | 9.394 | 100% | 419196.6348 | 83839.327
415 |  | As per drawing, Carcase to be made out of 18 mm thick ply, Ply to be covered with 6 mm thick HDF , 36 mm thick HDF made-up Shelf with provision for Led strip lights as shown in drawings, Drawer unit at mirror bottom, internal surface covered with 1mm thick approved laminate, 50 mm wide half round duco finish moulding in arch shaped as per drawings, including 50 mm high 16G 304 grade SS bronze satin finish Skirting, | [10 empty] | 0 | 0 |  |  | 0 | 0
416 | 5.12 | Duco paint finish Salon unit ( 2800 L x150 D x3000 H) | smt | 8.4 | 189546 | 26774.32 | 224904.29 | 8.4 | 50% | 112452.144 | 8.3875 | 80% | 179655.6872 | 67203.5432 | 8.3875 | 100% | 224569.609 | 44913.9218
417 |  | As per drawing, Carcase to be made out of 12 mm thick ply, Ply to be covered with 6 mm thick HDF , 36 mm thick HDF made-up Shelf with provision for Led strip lights as shown in drawings, 50 mm wide half round duco finish moulding in arch shaped as per drawings, including 50 mm high 16G 304 grade SS bronze satin finish Skirting, | [10 empty] | 0 | 0 |  |  | 0 | 0
418 | 5.13 | SS Bronze finish niche for Nail bar ( 1600 L x100 D x500 H) | Nos | 1 | 12000 | 24989.37 | 24989.37 | 1 | 50% | 12494.685 | 8.3875 | 80% | 167678.6727 | 155183.9877 | 8.3875 | 90% | 188638.5068 | 20959.8341
419 |  | As per drawing, Carcase to be made out of 12 mm thick ply, Ply to be covered with 16g SS bronze finish with 50 mm wide cover border in SS bronze finish as shown in drawings, | [10 empty] | 0 | 0 |  |  | 0 | 0
420 | 5.14 | Nail Bar counter in profile ( 1250 L x400 D x750 H) | Nos | 1 | 30000 | 37651.39 | 37651.39 | 1 | 50% | 18825.695 | 1 | 60% | 22590.834 | 3765.139 | 1 | 90% | 33886.251 | 11295.417
421 |  | Providing and fixing Nail Bar counter desk in profile , up to 100 mm thick Top finish in Terrazzo , with SS bronze finish base As per detail drawings. | [10 empty] | 0 | 0 |  |  | 0 | 0
422 | 5.15 | Spa reception table in profile ( 2500 L x 600 D x1100 H) | Nos | 1 | 42500 | 122715.65 | 122715.65 | 1 | 50% | 61357.825 | 1 | 80% | 98172.52 | 36814.695 | 1 | 90% | 110444.085 | 12271.565
423 |  | Providing and fixing Reception counter desk in profile , SS bronze finish top , with Fluted Apron finish in Duco paint, including drawer and storage As per detail drawings. | [10 empty] | 0 | 0 |  |  | 0 | 0
424 | 5.16 | SS Bronze Satin finish skirting 50mm high | Rmt | 40 | 42000 | 1530.32 | 61212.8 | 40 | 40% | 24485.12 | 0 |  | 0 | -24485.12 | 24.935 | 90% | 34342.6763 | 34342.6763
425 |  | 16 SWG, 304 Grade SS skirting over existing ply, Fixed with epoxy adhesive | [10 empty] | 0 | 0 |  |  | 0 | 0
426 | 5.17 | 30 mm thick x 400 mm deep Corian finish ledge, | Rmt | 5 | 23780 | 18514.94 | 92574.7 | 5 | 40% | 37029.88 | 4.36 | 60% | 48435.083 | 11405.203 | 4.36 | 100% | 80725.1384 | 32290.0554
427 |  | Using 18 mm thick marine ply covered with 6 mm thick approved Corian on both side with 30 mm wide Facia. | [10 empty] | 0 | 0 |  |  | 0 | 0
428 | 5.18 | 1000 mm dia Circular Picture frame in duco paint | Nos | 4 | 19000 | 11155.97 | 44623.88 | 4 | 50% | 22311.94 | 4 | 80% | 35699.104 | 13387.164 | 4 | 100% | 44623.88 | 8924.776
429 |  | DOORS | [10 empty] | 0 | 0 |  |  | 0 | 0
430 | 5.19 | Main Ent door -Wooden strip fluted panel door in Polish and Duco paint | nos | 1 | 62750 | 77645.54 | 77645.54 | 1 | 50% | 38822.77 | 1 | 80% | 62116.432 | 23293.662 | 1 | 100% | 77645.54 | 15529.108
431 |  | Size 1000mm x 2400mm | [10 empty] | 0 | 0 |  |  | 0 | 0
432 |  | Door Frame | [10 empty] | 0 | 0 |  |  | 0 | 0
433 |  | Overall finish size 100mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick marine ply as rough ground, fixed to masonry wall in perfect plumb, line and level using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk NBTW wood, Rebate to be separately put in NBTW wood, Wood to be treated with anti-termite medicine, Frame to be Finished in Approved Melamine Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
434 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
435 |  | Overall size 900 mm wide x 2400 mm ht. x 1 leaf, up to 82 mm thk. Using 38 mm thick readymade fireproof shutter covered with 8 mm thick marine ply on both sides , The shutter shall be clad with 4 mm thick approved veneer , including NBTW beading all around, 25 mm x 12 mm thick wooden strip to be fix on Veneer surface from inside and 25 mm x 12 mm thick HDF strip from lounge side with in duco paint as shown in drawings. basic cost of veneer up to Rs. 125 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
436 |  | Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
437 |  | Frame entire door to be Finished in Approved Melamine Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
438 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
439 |  | 125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, with lock, Concealed door closer by Hafele as per required capacity, 1 set of handle as approved by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
440 | 5.2 | Toilet door Wooden strip | nos | 1 | 62750 | 66935.81 | 66935.81 | 1 | 50% | 33467.905 | 1 | 80% | 53548.648 | 20080.743 | 1 | 100% | 66935.81 | 13387.162
441 |  | Size 1000mm x 2400mm | [10 empty] | 0 | 0 |  |  | 0 | 0
442 |  | Door Frame | [10 empty] | 0 | 0 |  |  | 0 | 0
443 |  | Overall finish size 250mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick marine ply as rough ground, fixed to masonry wall in perfect plumb, line and level using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk NBTW wood, Rebate to be separately put in NBTW wood, Wood to be treated with anti-termite medicine, Frame to be Finished in Approved Melamine Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
444 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
445 |  | Overall size 800 mm wide x 2400 mm ht. x 1 leaf, up to 82 mm thk. Using 38 mm thick readymade fireproof shutter covered with 8 mm thick marine ply on both sides , The shutter shall be clad with 4 mm thick approved veneer from both side , including NBTW beading all around, 25 mm x 12 mm thick wooden strip from out side, to be fix on Veneer surface as shown in drawings. basic cost of veneer up to Rs. 125 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
446 |  | Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
447 |  | Frame entire door to be Finished in Approved Melamine Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
448 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
449 |  | 125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, with lock, Concealed door closer by Hafele as per required capacity, 1 set of handle as approved by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
450 | 5.21 | Sliding Glass door with SS Jali in Satin Bronze finish | nos | 1 | 52750 | 66935.81 | 66935.81 | 1 | 50% | 33467.905 | 1 | 60% | 40161.486 | 6693.581 | 1 | 80% | 53548.648 | 13387.162
451 |  | Overall size- 1200 mm wide x 3000 mm height, Outer frame in SS hollow frame of 38 mm x50mm x 2.5 mm thickness all around with top hung Sliding channel , SS frame in Satin Bronze finish as approved by Architect, Sliding channel fixed to false ceiling frame, using 8 mm thick MS plate with anchor bolt. including 10 mm thk 304 grade SS pipe jali door panel as per approved design and in Satin Bronze finish, | [10 empty] | 0 | 0 |  |  | 0 | 0
452 |  | providing and fixing 10 mm thick toughen fix glass panel with 12 mm wide SS Beading around glass | [10 empty] | 0 | 0 |  |  | 0 | 0
453 | 5.22 | Built-in seating -Seat | Rmt | 2 | 32000 | 33696 | 67392 | 2 | 50% | 33696 | 1.371 | 70% | 32338.0512 | -1357.9488 | 1.371 | 90% | 41577.4944 | 9239.4432
454 |  | Carcus to be made out of 38mm x 38 mm Aluminium framework and 18 mm thk plywood , up to 100 mm thk foam rubber seat pasted to 18 mm thk ply base , 25 mm thk., 32 density PU foam to cover rubber seat, PU foam to be covered with 6 mm thk. sheet before finishing seat in white cloth, Final fabric leather shall be nailed on bottom side of plywood base, Including Wooden finish band, Wood to be Finished in Approved Melamine Polish,(Basic cost of fabric at Rs.2500 rmt) | [10 empty] | 0 | 0 |  |  | 0 | 0
455 | VI | SANITARY CP FITTINGS - ONLY FIXING | [10 empty] | 0 | 0 |  |  | 0 | 0
456 |  | COMMON LADIES AND GENTS TOILET | [10 empty] | 0 | 0 |  |  | 0 | 0
457 | 6.1 | WC for toilet | nos | 1 | 0 | 5000 | 5000 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
458 | 6.2 | Flush tank | nos | 1 | 0 | 3125 | 3125 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
459 | 6.3 | Flush plate | nos | 1 | 0 | 1562.5 | 1562.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
460 | 6.4 | Wash basin | nos | 1 | 0 | 3125 | 3125 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
461 | 6.6 | health faucet for WC | nos | 1 | 0 | 1562.5 | 1562.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
462 | 6.7 | wash basin faucet | nos | 1 | 0 | 1562.5 | 1562.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
463 | 6.8 | toilet paper holder | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
464 | 6.9 | hand dryer | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
465 | 6.1 | tissue paper holder | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
466 | 6.11 | Soap dispenser | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
467 | 6.12 | Robe hook | nos | 1 | 0 | 187.5 | 187.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
468 | 6.13 | Dust bin | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
469 | VII | PAINTING WORKS | [10 empty] | 0 | 0 |  |  | 0 | 0
470 | 7.1 | Painting to walls in pearl luster | smt | 80 | 39360 | 650 | 52000 | 80 |  | 0 |  |  | 0 | 0 | 2.884 | 90% | 1687.14 | 1687.14
471 |  | Sanding and preparing surface for receiving primer, One coat of cement primer in solvent base, Two coats of putty in water synthetic enamel base, Three coats of luster paint in approved shed, Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
472 | 7.2 | Painting to ceiling in acrylic emulsion paint | smt | 100 | 48000 | 650 | 65000 | 100 |  | 0 |  |  | 0 | 0 | 53.3111 | 90% | 31187.0228 | 31187.0228
473 |  | Sanding and preparing surface for receiving primer, One coat of cement primer in solvent base, Two coats of putty in water synthetic enamel, Three coats of acrylic emulsion paint in approved shed, Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
474 | 7.3 | Surface preparation for wall paper | smt | 70 | 15050 | 420 | 29400 | 70 |  | 0 |  |  | 0 | 0 | 44.7777 | 100% | 18806.6445 | 18806.6445
475 |  | Include cement primer, 2 coats of putty, touch up putty and primer with water base, Surface to be made ready to receive wall paper | [10 empty] | 0 | 0 |  |  | 0 | 0
476 | 7.4 | Hand painted Customised Wall paper | Smt | 70 | 44100 | 5639.96 | 394797.2 | 70 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
477 |  | Providing and fixing approved wall paper by -Marshal Ego wall paper, as approved by architect, Include protection till handover, (Basic cost of wall paper @ Rs.350 sft ) | [10 empty] | 0 | 0 |  |  | 0 | 0
478 | 7.5 | Duco Paint to Walls Partition | Smt | 25 | 56875 | 3098.88 | 77472 | 25 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
479 |  | Sanding and preparing surface for receiving paint, Final coats of Duco paint. Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
480 |  | Water Lounge Area | [10 empty] | 0 | 0 |  |  | 0 | 0
481 | I | DEMOLITION WORK | LS | 1 | 0 | 0 | 0 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
482 | II | MASONRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
483 | 2.1 | P C of 200mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level. | Sq. Mtr. | 231.77 | 475128.5 | 3340 | 774111.8 | 231.77 | 40% | 309644.72 | 241.207 | 100% | 805631.38 | 495986.66 | 241.207 | 100% | 805631.38 | 0
484 | 2.2 | P C of 150mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level. | Sq. Mtr. | 49.1 | 90835 | 2740 | 134534 | 49.1 | 60% | 80720.4 | 30.7854 | 90% | 75916.6731 | -4803.7269 | 30.7854 | 100% | 84351.859 | 8435.1859
485 | 2.3 | P C of 100mm solid concrete block masonry made of solid concrete blocks conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All divider walls up to 4300mm ht of internal divider walls at toilet area. | Sq. Mtr. | 73.69 | 126894.18 | 2300 | 169487 | 73.69 |  | 0 | 70.0318 | 90% | 144965.826 | 144965.826 | 70.0318 | 100% | 161073.14 | 16107.314
486 | 2.4 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr. | 709.12 | 460928 | 767 | 543895.04 | 709.12 | 90% | 489505.536 | 506.2165 | 90% | 349441.25 | -140064.286 | 506.2165 | 100% | 388268.0555 | 38826.8055
487 | 2.5 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr. | 106.21 | 69036.5 | 767 | 81463.07 | 106.21 | 90% | 73316.763 | 168.3845 | 90% | 116235.8204 | 42919.0574 | 168.3845 | 100% | 129150.9115 | 12915.0911
488 | 2.6 | Ramp flooring- Gradient of slope in 1 to 12 ratio, Floor surface to be cleaned of any dust particles, Surface to be watered well before laying blocks,OPC Only 43 grade cement to be used ( make- ACC Bharthi Ultratech Grasim Industries Coromandel ),Cement mortar in 1 4 ratio, minimum 12mm thk, Ramp block shall start from slab level height shall increase gradually match raised flooring height, Blocks shall be laid with alternate joints, Cured for at least 3 days, | [10 empty] | 0 | 0 |  |  | 0 | 0
489 |  | 0 to 300 mm thick | Sq. Mtr. | 10 | 22000 | 2750 | 27500 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
490 | 2.7 | P C of 150mm thick screed with 100mm thick broken AAC (Siporex) Block, broken siporex block to be laid on the waterproofing treated floor in proper leveling, after laying of the siporex block, void area to be filled up with Siporex or equivalent light weight materials including making of 50mm thick IPS flooring in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Complete as per instruction by the site engineer. | Sq. Mtr. | 7 | 12950 | 2750 | 19250 | 7 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
491 | 2.8 | P C of 300mm thick screed with 100 200 250mm thick broken AAC (Siporex) Block, broken siporex block to be laid on the waterproofing treated floor in proper leveling, after laying of the siporex block, void area to be filled up with Siporex or equivalent light weight materials including making of 50mm thick IPS flooring in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Laying the same in proper line level on the seating area s floor to maintain the floor leveling to get the smooth surface to lay the finishing floor materials on the said surface. Complete as per architectural detail drawings instruction by the site engineer. | Sq. Mtr. | 90 | 202500 | 2475 | 222750 | 90 | 60% | 133650 | 83.125 | 90% | 185160.9375 | 51510.9375 | 83.125 | 100% | 205734.375 | 20573.4375
492 | 2.9 | P C of 50mm 75mm thick screed in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Laying the same in proper line level on the seating area s floor to maintain the floor leveling to get the smooth surface to lay the finishing floor materials on the said surface. Complete as per architectural detail drawings instruction by the site engineer. | Sq. Mtr. | 12 | 10680 | 898 | 10776 | 12 | 60% | 6465.6 |  |  | 0 | -6465.6 |  |  | 0 | 0
493 | III | CIVIL FINISHES WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
494 |  | FLOORING | [10 empty] | 0 | 0 |  |  | 0 | 0
495 | 3.1 | Italian Marble Flooring | smt | 88 | 399168 | 10795 | 949960 | 88 | 50% | 474980 | 76.9306 | 90% | 747419.7301 | 272439.7301 | 76.9306 | 95% | 788943.0484 | 41523.3183
496 |  | Clean existing sub floor thoroughly. Flooring shall consist of Marble as per drawing, Up to 50 mm thick bedding mortar as per tech specs. Marble slabs shall be minimum 18 mm thick, laid as per tech specs, Marble to be cut as per size and laid with tight hairline joints. Joint filling and finishing as per tech specs.(On site cost of Italian marble @ Rs.450 sft without tax) including Approved sealer to be applied on all sides, Including sealer coat , Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover | [10 empty] | 0 | 0 |  |  | 0 | 0
497 | 3.2 | Italian Marble Flooring on Ramp in Strip Form | smt | 5 | 45750 | 12450 | 62250 | 5 | 40% | 24900 |  |  | 0 | -24900 |  |  | 0 | 0
498 |  | Clean existing sub floor thoroughly. Flooring shall consist of Marble in strips form as per drawing, At least 50 mm thk bedding mortar as per tech specs. Marble slabs shall be minimum 18 mm thick, laid as per tech specs. Marble to be cut as per size and laid with tight hairline joints. Joint filling and finishing and mirror polishing as per tech specs. Including 4mm thick x12 mm wide SS satin copper finish strip inserts in the flooring at 75 100 mm c c ,(On site cost of Italian marble @ Rs.450 sft without tax) including Approved sealer to be applied on all sides, Including sealer coat, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover | [10 empty] | 0 | 0 |  |  | 0 | 0
499 | 3.2 | Vitrified tile Flooring for staff toilet | smt | 10 | 32500 | 3690 | 36900 | 10 | 40% | 14760 |  |  | 0 | -14760 |  |  | 0 | 0
500 |  | Clean existing sub floor thoroughly before fixing Vitrified tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.150 sft without tax | [10 empty] | 0 | 0 |  |  | 0 | 0
501 | 3.4 | Kota Stone Flooring for Corridor service Area | smt | 80 | 156000 | 3040 | 243200 | 80 | 40% | 97280 |  |  | 0 | -97280 |  |  | 0 | 0
502 |  | P F of 19mm thick Kota Stone flooring (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, Kotah to be laid with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for kitchen service area. | [10 empty] | 0 | 0 |  |  | 0 | 0
503 | 3.5 | Granite Stone Ramp Flooring for Service corridor | smt | 5 | 30250 | 6250 | 31250 | 5 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
504 |  | P F of 18mm thick leather finished jet black granite flooring on the ramp with 100mm wide (selected approved make, basic cost INR. 2690.00 SM) in stroke pattern to get the desired grip. Stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, cleaning, etc. to required line, level, etc. all complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, chamfer of edges, etc. Complete in proper line level as per site engineer s instruction. It is for the back kitchen entrance area | [10 empty] | 0 | 0 |  |  | 0 | 0
505 |  | CLADDING | [10 empty] | 0 | 0 |  |  | 0 | 0
506 | 3.6 | Synthetic Marble Wall Cladding with Grooves | smt | 161.5 | 1086087.5 | 6860 | 1107890 | 161.5 | 40% | 443156 | 159.2625 | 90% | 983286.675 | 540130.675 | 159.2625 | 100% | 1092540.75 | 109254.075
507 |  | Clean existing wall surface before fixing wall cladding. Slabs shall be min. 18 mm thick fixed to plastered siporex block work, Slabs shall be installed as per tech specs on plastered wall siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Synthetic marble @ Rs.275 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
508 | 3.7 | Italian Marble Wall Cladding for in strip format | smt | 100 | 860000 | 11050 | 1105000 | 100 | 40% | 442000 | 68.4148 | 70% | 529188.478 | 87188.478 | 93.8002 | 100% | 1036492.21 | 507303.732
509 |  | Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to Fire rated plywood paneling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves chamfer edge moulding, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
510 | 3.8 | Jointless ceramic tiles cladding ( for staff toilet Service Corridor ) | smt | 140 | 273000 | 2275 | 318500 | 140 | 50% | 159250 | 14.005 | 100% | 31861.375 | -127388.625 | 14.005 | 100% | 31861.375 | 0
511 |  | Cladding shall comprise of ceramic tile of 600 mm x 300 mm, Tiles to be fixed in ordinary Portland cement only, Tiles to be put with Spacer required with Leticrete grout in joints in plumb, including levelling coat if any , Joints to be filled with matching groute.(Basic cost of ceramic tiles at Rs.60 sft) make Johnson Somany Kajaria Nitco | [10 empty] | 0 | 0 |  |  | 0 | 0
512 | 3.9 | Decorative Glass Mosaic Tiles In General Toilets ( customize design ) | smt | 30 | 516480 | 20750 | 622500 | 30 | 50% | 311250 | 26.175 | 60% | 325878.75 | 14628.75 | 26.175 | 95% | 515974.6875 | 190095.9375
513 |  | Clean existing wall surface before fixing Glass Mosaic tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.1200 sft without tax | [10 empty] | 0 | 0 |  |  | 0 | 0
514 | 3.1 | Plain Glass Mosaic Tile Wall Cladding | smt | 109 | 937400 | 9100 | 991900 | 109 | 30% | 297570 | 46.784 | 90% | 383160.96 | 85590.96 | 53.909 | 95% | 466043.305 | 82882.345
515 |  | Clean existing wall surface before fixing Glass Mosaic tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. (Basic cost of mosaic tiles at Rs.450 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
516 | 3.11 | Synthetic Marble Jamb lining for common Toilet Door Openings | rmt | 42 | 48300 | 3060 | 128520 | 42 | 30% | 38556 | 54 | 85% | 140454 | 101898 | 54 | 100% | 165240 | 24786
517 |  | Marble jamb lining for EWC doors including rebate, up to 230 mm wide, up to 2250 mm ht all around, At least 18 mm thk per-polished slabs to be used, Slabs to be cut as per approved size drawings, Include mitre joints at all junctions as per Architects instructions, Including V groove to match wall cladding, Marble to be fitted with white cement only, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides (Basic cost of Synthetic Marble at Rs.275 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
518 | 3.12 | Granite jamb lining Door Openings | rmt | 42 | 44100 | 2100 | 88200 | 42 | 50% | 44100 |  |  | 0 | -44100 |  |  | 0 | 0
519 |  | Granite for kitchen doors including rebate, up to 250 mm wide, up to 2250 mm ht all around, At least 18 mm thk per-polished Granite to be used. Granite to be cut as per approved size drawings. Include mitre joints at all junctions as per Architects instructions, Granite shall be installed as per tech specs on plastered siporex block work, Moulding to Granite edge as approved including polish, Joint filling and finishing and mirror polishing as per tech specs. (Basic cost of Granite at Rs.200 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
520 | 3.13 | Granite Architrave for Door Openings | rmt | 84 | 88200 | 2100 | 176400 | 84 | 50% | 88200 |  |  | 0 | -88200 |  |  | 0 | 0
521 |  | 50 mm wide Granite Architrave for kitchen back office doors , At least 18 mm thk per-polished Granite to be used. Include mitre joints at all junctions as per Architects instructions, Granite shall be installed as per tech specs on plastered siporex block work, Moulding to Granite edge as approved including polish, Joint filling and finishing and mirror polishing as per tech specs. (Basic cost of Granite at Rs.200 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
522 | 3.13a | 150 mm high Kotah Finish Skirting | rmt | 75 | 26250 | 637 | 47775 | 75 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
523 |  | P F of 19mm thick Kota Stone Skirting , stone to be machine cut, machine polished, fixed with cement paste including cleaning and preparing the surface of wall, Kotah to be fixed with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. as per site engineer s instruction. It is considered for service area. | [10 empty] | 0 | 0 |  |  | 0 | 0
524 |  | COUNTER AND LEDGES | [10 empty] | 0 | 0 |  |  | 0 | 0
525 | 3.14 | Italian Marble Finish Wash Basin Counter for Common toilet | rmt | 10 | 91500 | 27500 | 275000 | 10 | 40% | 110000 | 8.23 | 70% | 158427.5 | 48427.5 | 8.23 | 100% | 226325 | 67897.5
526 |  | The counter shall be supported on 38mm x 38mm x 5mm thk MS angle fixed to block work. Brackets shall be inserted within wall by at least 125mm, MS brackets shall be coated with 2 coats of anti-corrosive paint and 3 coats of synthetic enamel paint, 18mm thk ordinary Indian marble placed within bracket and screwed through bracket, At least 20mm thk cement mortar bedding in 1 4 ratio, Pre-finished and pre-polished marble slabs shall be fixed as per tech specs. Counter shall have up to 300 mm wide fascia marble with mitre joints All top edges of counter shall have chamfer moulding. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides. Including all plumbing cutout as shown in drawing | [10 empty] | 0 | 0 |  |  | 0 | 0
527 |  | (Basic cost of marble at Rs.450 sft including fiber filling polish) | [10 empty] | 0 | 0 |  |  | 0 | 0
528 | 3.15 | Synthetic Marble Ledges for all WC | rmt | 11 | 35200 | 4100 | 45100 | 11 |  | 0 | 12.16 | 80% | 39884.8 | 39884.8 | 12.16 | 100% | 49856 | 9971.2
529 |  | Using 18mm thick marble top, Including 2 high Marble fascia, Pre-polished finish marble shall be installed as per tech specs. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides. | [10 empty] | 0 | 0 |  |  | 0 | 0
530 |  | (Basic cost of Synthetic Marble at Rs.275 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
531 | 3.16 | Synthetic Marble Dressing Vanity Ledge in Common Ladies toilet | rmt | 2.5 | 8000 | 4100 | 10250 | 2.5 | 40% | 4100 |  |  | 0 | -4100 |  |  | 0 | 0
532 |  | Using 18 mm thick marble top, including 2 high Marble fascia, Pre-polished finish marble shall be installed as per tech specs. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides | [10 empty] | 0 | 0 |  |  | 0 | 0
533 |  | (Basic cost of Synthetic Marble at Rs.275 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
534 | 3.17 | Urinal Divider for Gents Toilet | nos | 5 | 30000 | 21750 | 108750 | 5 | 40% | 43500 | 4 | 60% | 52200 | 8700 | 5 | 80% | 87000 | 34800
535 |  | Overall size 2000 mm x 400 mm, in approved profile. Frame in 25mmx25mm SS finish pipe in glossy matt copper finish in profile to be approved by Architects, Insert of 18 mm synthetic marble slabs pre-polished on both sides including Approved sealer to be applied on all sides (Basic cost of Marble at Rs.275 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
536 | 3.16 | Granite Ledge in Janitor room | rmt | 4 | 11200 | 4500 | 18000 | 4 | 40% | 7200 |  |  | 0 | -7200 |  |  | 0 | 0
537 |  | Using 18 mm thick marble top, including 2 high Marble fascia, Pre-polished finish marble shall be installed as per tech specs. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides | [10 empty] | 0 | 0 |  |  | 0 | 0
538 |  | (Basic cost of Synthetic Marble at Rs.200 sft without tax) | [10 empty] | 0 | 0 |  |  | 0 | 0
539 | IV | FRENCH PLASTER WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
540 | 4.1 | Fire line Gypsum board ceiling | smt | 200 | 406800 | 2034 | 406800 | 200 |  | 0 | 77.3912 | 60% | 94448.2815 | 94448.2815 | 96.1022 | 95% | 185698.2231 | 91249.9416
541 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobain Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fiber tape reinforcement, Include finished cutouts for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceiling height is 4300 mm ) | [10 empty] | 0 | 0 |  |  | 0 | 0
542 | 4.2 | Fire line Gypsum board Facia Band 50 mm | rmt | 40 | 14400 | 630 | 25200 | 40 |  | 0 |  |  | 0 | 0 | 38.03 | 95% | 22760.955 | 22760.955
543 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fiber tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum | [10 empty] | 0 | 0 |  |  | 0 | 0
544 | 4.3 | Indirect Light Coves in Ceiling | rmt | 40 | 16000 | 800 | 32000 | 40 |  | 0 |  |  | 0 | 0 | 44.19 | 95% | 33584.4 | 33584.4
545 |  | In L shape with 100 mm deep up to 300mm high and 50 mm wide fascia, All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fiber tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum | [10 empty] | 0 | 0 |  |  | 0 | 0
546 | 4.4 | Shadow groove in ceiling | rmt | 54 | 12150 | 875 | 47250 | 54 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
547 |  | providing and Fixing ready made powder coated aluminium profile up to 18 mm x 18 mm as approved by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
548 | 4.5 | Universal plaster punning on wall | smt | 192 | 93120 | 615 | 118080 | 192 |  | 0 | 104.3853 | 90% | 57777.2636 | 57777.2636 | 104.3853 | 100% | 64196.9595 | 6419.6959
549 |  | Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bullmarks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work. | [10 empty] | 0 | 0 |  |  | 0 | 0
550 | V | CARPENTRY WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
551 | 5.1 | P F of 304 grade 3mm thick SS Corner guard (30mm x 30mm, hairline matt finished as per approved sample) fixing with SS full thread screws on each corner of the kitchen s wall after cladding of tiles, so that the corner may be protected from the damages, including cleaning, etc. Complete in proper line level as per site engineer s instruction. It is for the back kitchen area. | rmt | 14.4 | 6912 | 1400 | 20160 | 14.4 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
552 | 5.2 | Frosted Glass Screen with satin Glossy Copper Finish SS Frame in Toilets | smt | 6.98 | 63169 | 10784 | 75272.32 | 6.98 |  | 0 |  |  | 0 | 0 | 5.06 | 90% | 49110.336 | 49110.336
553 |  | Frosted, textured, toughened and laminated glass overall 10 mm thick, as per samples approved by Architect. All glass edges to be fine cut and polished and sealed. The glass shall be fitted into a rebate of special fabricated 16G 304 grade SS copper finish frame of 50mmx50mm, as approved by Architect. The entire assembly shall be fitted on wall and floor with proper accessories and protected till handover. | [10 empty] | 0 | 0 |  |  | 0 | 0
554 | 5.3 | SS satin Glossy Copper Finish Band in Toilets | rmt | 73 | 91250 | 4600 | 335800 | 73 |  | 0 |  |  | 0 | 0 | 64.445 | 90% | 266802.3 | 266802.3
555 |  | SS satin Glossy Copper finish sheet 304 grade, minimum 16 gauge thk. cladding on the ply with joints as required by Architect. The C shape SS band shall be 50 mm wide with turned in sides up to 25 mm and shall be fixed on 12 mm marine ply band fixed to wall and jambs. SS sheets fixed with recommended adhesive including protection film till handover | [10 empty] | 0 | 0 |  |  | 0 | 0
556 | 5.4 | Decorative Toilet Vanity Mirrors in Oval Circular Rectangular Shapes | smt | 9 | 121500 | 23400 | 210600 | 9 |  | 0 |  |  | 0 | 0 | 4.36 | 90% | 91821.6 | 91821.6
557 |  | The mirrors shall be mounted on a backing of aluminium framework and marine ply of overall 30 to 40 mm thickness, which shall be fixed to the wall. Including provision for LED strip light. Mirror shall be 8 mm thick to receive beveling and shall be laminated at the back for protection, and backed with felt lining. All Mirrors shall have 18-25 mm beveling on all edges. All edges of mirror shall have CNC edge polish, Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect. exclude cost of LED strip lighting | [10 empty] | 0 | 0 |  |  | 0 | 0
558 | 5.5 | Plain mirror paneling ( dressing room ) | smt | 5 | 37500 | 13250 | 66250 | 5 |  | 0 |  |  | 0 | 0 | 1.7 | 90% | 20272.5 | 20272.5
559 |  | The mirrors shall be mounted on a backing of marine ply of overall 18 mm thickness, which shall be fixed to the wall. Including L shape SS finish Angle profile covering on All around the mirror. Mirror shall be 8 mm thick to receive beveling and shall be laminated at the back for protection, and backed with felt lining. All Mirrors shall have 18-25 mm beveling on all edges. All edges of mirror shall have CNC edge polish. Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect. | [10 empty] | 0 | 0 |  |  | 0 | 0
560 |  | DOORS | [10 empty] | 0 | 0 |  |  | 0 | 0
561 | 5.6 | Toilet Main Doors in Timber and Veneer Finish- D1 | nos | 2 | 120000 | 77500 | 155000 | 2 | 50% | 77500 | 2 | 80% | 124000 | 46500 | 2 | 100% | 155000 | 31000
562 |  | Overall size 1000 mm x 2250 mm ht 900 mm x 2250 mm ht | [10 empty] | 0 | 0 |  |  | 0 | 0
563 |  | Door frame | [10 empty] | 0 | 0 |  |  | 0 | 0
564 |  | Overall size 275 mm wide x 50 mm thick x 2250 ht Door frame to be Made up Using 18 mm thick marine ply as rough ground, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk NBTW wood, Rebate to be separately put in NBTW wood, Wood to be treated with anti-termite medicine, | [10 empty] | 0 | 0 |  |  | 0 | 0
565 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
566 |  | Overall size 900 mm wide x 2200 mm ht. x 1 leaf, up to 59 mm thk, Using 35 mm thick readymade fireproof shutter covered with 8 mm thick marine ply on both sides , The shutter shall be clad with 4 mm thick approved veneer on both sides including NBTW beading all around. basic cost of veneer up to Rs. 125 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
567 |  | Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
568 |  | Frame entire door to be Finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
569 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
570 |  | The shutter shall be mounted on min. 3 nos. bearing SS finished hinges with proprietary screws, made by Hafele Dorma or equivalent approved by Architect. The shutter shall have a “Dorma” concealed door closer. Include a set of lock and approved handle,( basic cost of handle Rs. 8,000 pair ) | [10 empty] | 0 | 0 |  |  | 0 | 0
571 | 5.7 | Disabled Toilet Entrance Door (Sliding) D-3 ( electronic operated ) | nos | 1 | 64750 | 64750 | 64750 | 1 | 50% | 32375 | 1 | 80% | 51800 | 19425 | 1 | 100% | 64750 | 12950
572 |  | Size 1050mm x 2250mm | [10 empty] | 0 | 0 |  |  | 0 | 0
573 |  | Door frame | [10 empty] | 0 | 0 |  |  | 0 | 0
574 |  | Overall size 275 mm wide x 50 mm thick x 2250 ht Using Door frame to be Made up Using 18 mm thick marine ply as rough ground, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk NBTW wood, Rebate to be separately put in NBTW wood, Wood to be treated with anti-termite medicine, | [10 empty] | 0 | 0 |  |  | 0 | 0
575 |  | Openable Pelmet | [10 empty] | 0 | 0 |  |  | 0 | 0
576 |  | Pelmet to be made out of Using 18 mm thick ply with Pelmet to be covered with 4 mm thk approved veneer with 0.50 mm thk wooden face pressed on outside and approved 1 mm thk laminate pressed inside, including matching | [10 empty] | 0 | 0 |  |  | 0 | 0
577 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
578 |  | Overall size 950 mm wide x 2250 mm ht. x 1 leaf, up to 59 mm thk. Using 35 mm thick readymade fireproof shutter covered with 8 mm thick marine ply on both sides , The shutter shall be clad with 4 mm thick approved veneer on both sides including NBTW beading all around. basic cost of veneer up to Rs. 125 sft | [10 empty] | 0 | 0 |  |  | 0 | 0
579 |  | Polish | [10 empty] | 0 | 0 |  |  | 0 | 0
580 |  | Frame , All wood Veneer to be Veneer to be Finished in Approved waterbase PU polish | [10 empty] | 0 | 0 |  |  | 0 | 0
581 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
582 |  | Sliding channel system by HAWA hafle dorma with bottom guide concealed within sliding shutter (Note No guide shall be fixed on floor), Concealed handle for sliding shutter, as approved, Concealed sliding lock with knob on inside, (Basic cost of concealed sliding handle at Rs.2500 - per set), | [10 empty] | 0 | 0 |  |  | 0 | 0
583 | 5.8 | WC Cubicle Shutter in Laminate Finish in Toilets D-2 | nos | 7 | 79800 | 28750 | 201250 | 7 | 50% | 100625 | 7 | 80% | 161000 | 60375 | 7 | 95% | 191187.5 | 30187.5
584 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
585 |  | Overall size 700 mm wide x 2250 mm ht.x 53 mm thick, Using 35 mm thick readymade fireproof shutter to be covered with 8 mm thick ply from both side including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side ( basci cost of laminate sheet Rs 1600 sheet ) | [10 empty] | 0 | 0 |  |  | 0 | 0
586 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
587 |  | Min. 3nos. SS hinges, and lock, handle and indicator set with 1 double robe hook, by Hafele Dorma or equivalent approved, | [10 empty] | 0 | 0 |  |  | 0 | 0
588 | 5.9 | WC Cubicle Shutter in Laminate Finish in Toilets D-2a | nos | 2 | 23940 | 28750 | 57500 | 2 | 50% | 28750 | 2 | 80% | 46000 | 17250 | 2 | 100% | 57500 | 11500
589 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
590 |  | Overall size 800 mm wide x 2250 mm ht.x 53 mm thick, Using 35 mm thick readymade fireproof shutter to be covered with 8 mm thick ply from both side including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side ( basci cost of laminate sheet Rs 1600 sheet ) | [10 empty] | 0 | 0 |  |  | 0 | 0
591 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
592 |  | Min. 3nos. SS hinges, and lock, handle and indicator set with 1 double robe hook, by Hafele Dorma or equivalent approved, | [10 empty] | 0 | 0 |  |  | 0 | 0
593 | 5.1 | 2 Way Double Door in Laminate Finish with Vision Panel D-7 ( for Kitchen toilet Corridor ) | nos | 1 | 52750 | 65000 | 65000 | 1 | 50% | 32500 | 1 | 80% | 52000 | 19500 | 1 | 100% | 65000 | 13000
594 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
595 |  | Overall size 1500 mm wide x 2250 mm ht.x 53 mm thick, Using 35 mm thick readymade fireproof shutter to be covered with 8 mm thick ply from both side including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side. ( basci cost of laminate sheet Rs 1600 sheet ) | [10 empty] | 0 | 0 |  |  | 0 | 0
596 |  | Vision panel | [10 empty] | 0 | 0 |  |  | 0 | 0
597 |  | 400 mm dia, 8 mm thk toughened glass vision panel including 16SWG 304 grade SS finish Profile as approved by architect | [10 empty] | 0 | 0 |  |  | 0 | 0
598 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
599 |  | 300 mm x 200 mm x 2 nos Handle push plate. hafle dorma Heavy duty floor spring. 300 mm high, 16 G 304 grade SS Kick plate fixed to door on both side with suitable adhesive Including locks, etc. complete | [10 empty] | 0 | 0 |  |  | 0 | 0
600 | 5.11 | Door in Laminate Finish with Vision Panel ( for Garbage Janitor room ) | nos | 2 | 91500 | 49750 | 99500 | 2 | 50% | 49750 | 3 | 80% | 119400 | 69650 | 3 | 100% | 149250 | 29850
601 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
602 |  | Overall size 900 mm wide x 2250 mm ht.x 53 mm thick, Using 35 mm thick readymade fireproof shutter to be covered with 8 mm thick ply from both side including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side. ( basci cost of laminate sheet Rs 1600 sheet ) | [10 empty] | 0 | 0 |  |  | 0 | 0
603 |  | Vision panel | [10 empty] | 0 | 0 |  |  | 0 | 0
604 |  | 400 mm dia, 8 mm thk toughened glass vision panel including 16SWG 304 grade SS finish Profile as approved by architect | [10 empty] | 0 | 0 |  |  | 0 | 0
605 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
606 |  | 300 mm x 200 mm x 2 nos Handle push plate. hafle dorma Heavy duty floor spring. 300 mm high, 16 G 304 grade SS Kick plate fixed to door on both side with suitable adhesive Including locks, etc. complete | [10 empty] | 0 | 0 |  |  | 0 | 0
607 | 5.12 | Lockers | sqmt | 7.2 | 75600 | 26750 | 192600 | 7.2 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
608 |  | OVERALL SIZE 2100 MM HIGH X 350 M DEEP | [10 empty] | 0 | 0 |  |  | 0 | 0
609 |  | size 400x400 mm division - CARCASS SHUTTER 18 MM thk. Prelaminated PB board with PVC Edge band With openable Shutter including handle as approved by architect, lock etc. completed . BACK 12 MM thk. Prelaminated PB board with PVC Edge band. | [10 empty] | 0 | 0 |  |  | 0 | 0
610 | 5.13 | Shaft Door | nos | 3 | 32385 | 24000 | 72000 | 3 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
611 |  | Shutter | [10 empty] | 0 | 0 |  |  | 0 | 0
612 |  | Overall size 600 mm wide x 1800 mm ht.x 37 mm thick, Using 35 mm thick readymade fireproof shutter to be used including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side ( basci cost of laminate sheet Rs 1600 sheet ) | [10 empty] | 0 | 0 |  |  | 0 | 0
613 |  | Hardware | [10 empty] | 0 | 0 |  |  | 0 | 0
614 |  | Min. 3nos. SS hinges, and lock, handle | [10 empty] | 0 | 0 |  |  | 0 | 0
615 | VI | SANITARY CP FITTINGS - ONLY FIXING | [10 empty] | 0 | 0 |  |  | 0 | 0
616 |  | COMMON LADIES AND GENTS TOILET | [10 empty] | 0 | 0 |  |  | 0 | 0
617 | 6.1 | WC for common toilet | nos | 8 | 0 | 5000 | 40000 | 8 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
618 | 6.2 | Flush tank | nos | 8 | 0 | 3125 | 25000 | 8 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
619 | 6.3 | Flush plate | nos | 8 | 0 | 1562.5 | 12500 | 8 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
620 | 6.4 | Wash basin - Gents | nos | 4 | 0 | 3125 | 12500 | 4 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
621 | 6.5 | Wash basin - Ladies | nos | 4 | 0 | 3125 | 12500 | 4 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
622 | 6.6 | health faucet for WC | nos | 8 | 0 | 1562.5 | 12500 | 8 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
623 | 6.7 | wash basin faucet | nos | 8 | 0 | 1562.5 | 12500 | 8 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
624 | 6.8 | toilet paper holder | nos | 8 | 0 | 312.5 | 2500 | 8 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
625 | 6.9 | hand dryer | nos | 2 | 0 | 312.5 | 625 | 2 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
626 | 6.1 | tissue paper holder | nos | 2 | 0 | 312.5 | 625 | 2 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
627 | 6.11 | Napi change ledge | nos | 2 | 0 | 312.5 | 625 | 2 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
628 | 6.12 | Urinals | nos | 5 | 0 | 3125 | 15625 | 5 |  | 0 |  |  | 0 | 0 | 5 | 90% | 14062.5 | 14062.5
629 | 6.13 | Urinals censor plates | nos | 5 | 0 | 3125 | 15625 | 5 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
630 | 6.14 | Soap dispenser | nos | 8 | 0 | 312.5 | 2500 | 8 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
631 | 6.15 | Robe hook | nos | 8 | 0 | 312.5 | 2500 | 8 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
632 | 6.16 | Dust bin | nos | 13 | 0 | 312.5 | 4062.5 | 13 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
633 | 6.17 | Flush tank | nos | 1 | 0 | 3125 | 3125 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
634 | 6.18 | Flush plate | nos | 1 | 0 | 1562.5 | 1562.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
635 | 6.19 | handicap WC | nos | 1 | 0 | 4375 | 4375 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
636 | 6.2 | Wash basin - Handicap | nos | 1 | 0 | 3125 | 3125 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
637 | 6.21 | wash basin faucet for handicap | nos | 1 | 0 | 1562.5 | 1562.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
638 | 6.22 | toilet paper holder | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
639 | 6.23 | hand dryer | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
640 | 6.24 | tissue paper holder | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
641 | 6.25 | Grab bar for handicap toilet | nos | 4 | 0 | 312.5 | 1250 | 4 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
642 | 6.26 | Soap dispenser | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
643 | 6.27 | Robe hook | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
644 | 6.28 | Dust bin | nos | 1 | 0 | 312.5 | 312.5 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
645 | VII | PAINTING WORKS | [10 empty] | 0 | 0 |  |  | 0 | 0
646 | 7.1 | Painting to walls in pearl luster | smt | 80 | 39360 | 975 | 78000 | 80 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
647 |  | Sanding and preparing surface for receiving primer, One coat of cement primer in solvent base, Two coats of putty in water synthetic enamel base, Three coats of luster paint in approved shed, Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
648 | 7.2 | Painting to ceiling in acrylic emulsion paint | smt | 195 | 78000 | 650 | 126750 | 195 |  | 0 |  |  | 0 | 0 | 68.9511 | 90% | 40336.3935 | 40336.3935
649 |  | Sanding and preparing surface for receiving primer, One coat of cement primer in solvent base, Two coats of putty in water synthetic enamel, Three coats of acrylic emulsion paint in approved shed, Complete as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
650 |  | CIVIL-WET WORK | [10 empty] | 0 | 0 |  |  | 0 | 0
651 | 1.1 | 200 mm thick solid concrete block work | SQM | 40.55 | 85155 | 3346.79 | 135712.33 | 40.55 | 30% | 40713.7003 |  |  | 0 | -40713.7003 |  |  | 0 | 0
652 |  | Walls to start from floor slab up to 4300 mm height | [10 empty] | 0 | 0 |  |  | 0 | 0
653 |  | Include 100 mm high RCC lintel at 1.5m, 3.0m with 6nos x 8 mm MS twisted bars and 6 mm MS rod rings at 150 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel ) | [10 empty] | 0 | 0 |  |  | 0 | 0
654 |  | 8 mm MS bar grade FE 500 | [10 empty] | 0 | 0 |  |  | 0 | 0
655 |  | Only 43 or 53 grade Cement Adhesive to be used | [10 empty] | 0 | 0 |  |  | 0 | 0
656 |  | Cement mortar in 1 4 ratio, minimum 12mm thk | [10 empty] | 0 | 0 |  |  | 0 | 0
657 |  | Constructed In perfect plum, line and level | [10 empty] | 0 | 0 |  |  | 0 | 0
658 |  | Wall to be cured for atleast 3 days | [10 empty] | 0 | 0 |  |  | 0 | 0
659 |  | including scaffolding and staging etc. complete. | [10 empty] | 0 | 0 |  |  | 0 | 0
660 |  | 25 mm gap between block wall and slab shall be filled with expandable foam | [10 empty] | 0 | 0 |  |  | 0 | 0
661 |  | B00B01-TFS-I_ID-DOM-0A-DWG-0001 | [10 empty] | 0 | 0 |  |  | 0 | 0
662 | 1.2 | 200 mm thick Aerocon block wall | SQM | 364.91 | 842942.1 | 3346.79 | 1221277.14 | 364.91 | 20% | 244255.4278 |  |  | 0 | -244255.4278 |  |  | 0 | 0
663 |  | Walls to start from floor slab up to 4300 mm height | [10 empty] | 0 | 0 |  |  | 0 | 0
664 |  | Include 200 mm high RCC Patli to be after every 5 layers above doors with 6nos x 8 mm MS twisted bars and 6 mm MS rod rings at 150 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel ) | [10 empty] | 0 | 0 |  |  | 0 | 0
665 |  | 8 mm MS bar grade FE 500 | [10 empty] | 0 | 0 |  |  | 0 | 0
666 |  | Only 43 or 53 grade cement Adhesive to be used | [10 empty] | 0 | 0 |  |  | 0 | 0
667 |  | Cement mortar in 1 4 ratio, minimum 12mm thk | [10 empty] | 0 | 0 |  |  | 0 | 0
668 |  | Constructed In perfect plum, line and level | [10 empty] | 0 | 0 |  |  | 0 | 0
669 |  | Wall to be cured for atleast 3 days | [10 empty] | 0 | 0 |  |  | 0 | 0
670 |  | including scaffolding and staging etc. complete. | [10 empty] | 0 | 0 |  |  | 0 | 0
671 |  | 25 mm gap between block wall and slab shall be filled with expandable foam | [10 empty] | 0 | 0 |  |  | 0 | 0
672 |  | B00B01-TFS-I_ID-DOM-0A-DWG-0001 | [10 empty] | 0 | 0 |  |  | 0 | 0
673 | 1.3 | 150 mm thick solid concrete block work | SQM | 13.85 | 27700 | 2788.99 | 38627.51 | 13.85 | 40% | 15451.0046 |  |  | 0 | -15451.0046 |  |  | 0 | 0
674 |  | Include 150 mm high RCC lintel at 1.8m, 3.6m above doors with 4nos x 8 mm MS twisted bars and 6 mm MS rod rings at 150 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel ) | [10 empty] | 0 | 0 |  |  | 0 | 0
675 |  | 8 mm MS bar grade FE 500 | [10 empty] | 0 | 0 |  |  | 0 | 0
676 |  | Only 43 or 53 grade Cement Adhesive to be used | [10 empty] | 0 | 0 |  |  | 0 | 0
677 |  | Cement mortar in 1 4 ratio, minimum 12mm thk | [10 empty] | 0 | 0 |  |  | 0 | 0
678 |  | Constructed In perfect plum, line and level | [10 empty] | 0 | 0 |  |  | 0 | 0
679 |  | Wall to be cured for atleast 3 days | [10 empty] | 0 | 0 |  |  | 0 | 0
680 |  | including scaffolding and staging etc. complete. | [10 empty] | 0 | 0 |  |  | 0 | 0
681 |  | 25 mm gap between block wall and slab shall be filled with expandable foam | [10 empty] | 0 | 0 |  |  | 0 | 0
682 |  | B00B01-TFS-I_ID-DOM-0A-DWG-0001 | [10 empty] | 0 | 0 |  |  | 0 | 0
683 | 1.4 | 150 mm thick solid Aerocon block wall |  | 124.65 | 236835 | 2788.99 | 347647.6 | 124.65 | 80% | 278118.0828 |  |  | 0 | -278118.0828 |  |  | 0 | 0
684 |  | Walls to start from floor slab up to 4300 mm height | [10 empty] | 0 | 0 |  |  | 0 | 0
685 |  | Include 150 mm high RCC Patli to be after every 5 layers above doors with 4nos x 8 mm MS twisted bars and 6 mm MS rod rings at 100 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel ) | [10 empty] | 0 | 0 |  |  | 0 | 0
686 |  | 8 mm MS bar grade FE 500 | [10 empty] | 0 | 0 |  |  | 0 | 0
687 |  | Only 43 or 53 grade Cement Adhesive to be used | [10 empty] | 0 | 0 |  |  | 0 | 0
688 |  | Cement mortar in 1 4 ratio, minimum 12mm thk | [10 empty] | 0 | 0 |  |  | 0 | 0
689 |  | Constructed In perfect plum, line and level | [10 empty] | 0 | 0 |  |  | 0 | 0
690 |  | Wall to be cured for atleast 3 days | [10 empty] | 0 | 0 |  |  | 0 | 0
691 |  | including scaffolding and staging etc. complete. | [10 empty] | 0 | 0 |  |  | 0 | 0
692 |  | 25 mm gap between block wall and slab shall be filled with expandable foam | [10 empty] | 0 | 0 |  |  | 0 | 0
693 |  | B00B01-TFS-I_ID-DOM-0A-DWG-0001 | [10 empty] | 0 | 0 |  |  | 0 | 0
694 | 1.5 | Building 100 mm thk. Aerocon block wall | smt | 193.32 | 332897.04 | 2342.75 | 452900.43 | 193.32 | 80% | 362320.344 |  |  | 0 | -362320.344 |  |  | 0 | 0
695 |  | Walls to start from floor slab up to 4300 mm height | [10 empty] | 0 | 0 |  |  | 0 | 0
696 |  | Include 100 mm high RCC Patli to be after every 5 layers above doors with 4nos x 8 mm MS twisted bars and 6 mm MS rod rings at 150 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel ) | [10 empty] | 0 | 0 |  |  | 0 | 0
697 |  | 8 mm MS bar grade FE 500 | [10 empty] | 0 | 0 |  |  | 0 | 0
698 |  | Only 43 or 53 grade Cement Adhesive to be used | [10 empty] | 0 | 0 |  |  | 0 | 0
699 |  | Cement mortar in 1 4 ratio, minimum 12mm thk | [10 empty] | 0 | 0 |  |  | 0 | 0
700 |  | Constructed In perfect plum, line and level | [10 empty] | 0 | 0 |  |  | 0 | 0
701 |  | Wall to be cured for atleast 3 days | [10 empty] | 0 | 0 |  |  | 0 | 0
702 |  | including scaffolding and staging etc. complete. | [10 empty] | 0 | 0 |  |  | 0 | 0
703 |  | 25 mm gap between block wall and slab shall be filled with expandable foam | [10 empty] | 0 | 0 |  |  | 0 | 0
704 |  | B00B01-TFS-I_ID-DOM-0A-DWG-0001 | [10 empty] | 0 | 0 |  |  | 0 | 0
705 | 1.6 | Raised flooring in Brick bat Coba | [10 empty] | 0 | 0 |  |  | 0 | 0
706 |  | Providing waterproofing treatment to Slab (India water proofing or alike) Light weight block filling with cement mortar. Top to be finished with 60-70mm 1 2 4 screed, mixed with water proofing compound etc. | [10 empty] | 0 | 0 |  |  | 0 | 0
707 |  | Floor surface to be cleaned of any dust particles | [10 empty] | 0 | 0 |  |  | 0 | 0
708 |  | Surface to be watered well before laying blocks | [10 empty] | 0 | 0 |  |  | 0 | 0
709 |  | Only 43 or 53 grade cement to be used | [10 empty] | 0 | 0 |  |  | 0 | 0
710 |  | Cement mortar in 1 4 ratio, minimum 12mm thk | [10 empty] | 0 | 0 |  |  | 0 | 0
711 |  | Blocks shall be laid with alternate joints | [10 empty] | 0 | 0 |  |  | 0 | 0
712 |  | Cured for atleast 3 days | [10 empty] | 0 | 0 |  |  | 0 | 0
713 |  | Slope to be maintined as per drawing | [10 empty] | 0 | 0 |  |  | 0 | 0
714 |  | B00B01-TFS-I_ID-DOM-0A-DWG-0001 | [10 empty] | 0 | 0 |  |  | 0 | 0
715 |  | 150 mm thick | smt | 55 | 101750 | 2677.43 | 147258.65 | 55 | 60% | 88355.19 |  |  | 0 | -88355.19 |  |  | 0 | 0
716 |  | 250 mm thick | smt | 5 | 11250 | 3346.79 | 16733.95 | 5 | 60% | 10040.37 |  |  | 0 | -10040.37 |  |  | 0 | 0
717 |  | 300 mm thick | smt | 110 | 272250 | 3904.59 | 429504.9 | 110 | 40% | 171801.96 |  |  | 0 | -171801.96 |  |  | 0 | 0
718 | 1.7 | Construction of ramp using Aerocon block | [10 empty] | 0 | 0 |  |  | 0 | 0
719 |  | Floor surface to be cleaned of any dust particles | [10 empty] | 0 | 0 |  |  | 0 | 0
720 |  | Surface to be watered well before laying blocks | [10 empty] | 0 | 0 |  |  | 0 | 0
721 |  | Only 43 or 53 grade cement to be used | [10 empty] | 0 | 0 |  |  | 0 | 0
722 |  | Cement mortar in 1 4 ratio, minimum 12mm thk | [10 empty] | 0 | 0 |  |  | 0 | 0
723 |  | Ramp block shall start from slab level height shall increase gradually match raised flooring height | [10 empty] | 0 | 0 |  |  | 0 | 0
724 |  | Blocks shall be laid with alternate joints | [10 empty] | 0 | 0 |  |  | 0 | 0
725 |  | Cured for atleast 3 days | [10 empty] | 0 | 0 |  |  | 0 | 0
726 |  | B00B01-TFS-I_ID-DOM-0A-DWG-0001 | [10 empty] | 0 | 0 |  |  | 0 | 0
727 |  | 0 to 150 mm thick | smt | 5 | 7250 | 2231.19 | 11155.95 | 5 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
728 |  | 0 to 250 mm thick | smt | 5 | 9250 | 2677.43 | 13387.15 | 5 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
729 |  | 0 to 300 mm thick | smt | 10 | 20750 | 3346.79 | 33467.9 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
730 | 1.8 | Applying cement plaster to NEW wall | smt | 1500 | 1104435 | 736.29 | 1104435 | 1500 | 40% | 441774 |  |  | 0 | -441774 |  |  | 0 | 0
731 |  | Wall surface to be free from any loose particles before plastering | [10 empty] | 0 | 0 |  |  | 0 | 0
732 |  | Surface to be watered well before plastering | [10 empty] | 0 | 0 |  |  | 0 | 0
733 |  | Only river sand to be used free of minerals salts | [10 empty] | 0 | 0 |  |  | 0 | 0
734 |  | Sand shall be fine fibreed before using | [10 empty] | 0 | 0 |  |  | 0 | 0
735 |  | Only 43 or 53 grade cement to be used | [10 empty] | 0 | 0 |  |  | 0 | 0
736 |  | Cement mortar in 1 4 ratio, upto 20mm thk. | [10 empty] | 0 | 0 |  |  | 0 | 0
737 |  | Include 600 m wide PVC chicken mesh on junctions of RCC and brick siporex wall | [10 empty] | 0 | 0 |  |  | 0 | 0
738 |  | In perfect plum, line and level | [10 empty] | 0 | 0 |  |  | 0 | 0
739 |  | Smooth lined surface as instructed | [10 empty] | 0 | 0 |  |  | 0 | 0
740 |  | Plaster to be cured for at least 3 days | [10 empty] | 0 | 0 |  |  | 0 | 0
741 |  | Applying cement plaster to EXISTING wall | smt | 350 | 234500 | 892.48 | 312368 | 350 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
742 | 1.9 | PCC screed on slab ( grade M15 ) | smt | 1120 | 1355200 | 1338.72 | 1499366.4 | 1120 | 40% | 599746.56 |  |  | 0 | -599746.56 |  |  | 0 | 0
743 |  | Clean slab surface before laying mortar | [10 empty] | 0 | 0 |  |  | 0 | 0
744 |  | Aggregate of 0 and 1 no. size to be used | [10 empty] | 0 | 0 |  |  | 0 | 0
745 |  | Atleast average 75 mm thk (min. 50 mm ) mortar in 1 2 4 ratio | [10 empty] | 0 | 0 |  |  | 0 | 0
746 |  | Coba shall not cover raceway junction box | [10 empty] | 0 | 0 |  |  | 0 | 0
747 |  | Coba to be cured for atleast 3 days | [10 empty] | 0 | 0 |  |  | 0 | 0
748 | 1.1 | Chemical waterproofing over walls | [10 empty] | 0 | 0 |  |  | 0 | 0
749 |  | Providing and laying proprietary chemical water proofing system consisting of polymer modified acrylic base coating in two coats in form of slurry (total consumption of 1.5 Kg Sqm) as approved by the PM and as directed by the approved manufacturer of waterproofing coating, with sandwiched fibre mesh and protective screed. The work shall include cleaning of surface, grouting porous surfaces including making ‘V’ grooves at junctions, cracks with non shrink crystalline base cementitious grout etc. Further including horizontal and vertical surfaces protected with 20mm screeding in 1 4 mortar (1 cement 4 sand), finished in ready to receive Architectural finish, in correct line, level and plumb, curing, grouting, testing, etc. all complete to entire satisfaction of the PM, contractor to provide guarantee for 10 years Rs.100 - stamp paper in approved proforma. MAKE WPM 002-AROEX ENDURA. CONTRCTING HAS TO FOLLOW THE DETAILED METHODOLOGY OF THE MANUFCATURERS INSTRUCTION. ONLY FOR WET AREA. | [10 empty] | 0 | 0 |  |  | 0 | 0
750 |  | Waterproofing to wrap up on the walls upto 900 mm height | [10 empty] | 0 | 0 |  |  | 0 | 0
751 |  | Vendor to submit brand specifications for approval | [10 empty] | 0 | 0 |  |  | 0 | 0
752 |  | Waterproofing shall be done within plumbing chases before installing pipes and after filling chases with cement plaster | [10 empty] | 0 | 0 |  |  | 0 | 0
753 |  | For Toilet and Kitchen | smt | 296 | 490176 | 1896.51 | 561366.96 | 296 | 60% | 336820.176 | 161.9923 | 90% | 276498.0152 | -60322.1608 | 174.9986 | 100% | 331886.6278 | 55388.6126
754 | 1.11 | Membrane waterproofing on floor walls in Kitchen toilets | smt | 200 | 430000 | 2231.19 | 446238 | 200 | 60% | 267742.8 |  |  | 0 | -267742.8 |  |  | 0 | 0
755 |  | Upto 3mm thk. membrane sheet, manufactured by reputed brand | [10 empty] | 0 | 0 |  |  | 0 | 0
756 |  | Slab to be dust free before starting process | [10 empty] | 0 | 0 |  |  | 0 | 0
757 |  | 1 4 ratio cement mortar with waterproofing compound | [10 empty] | 0 | 0 |  |  | 0 | 0
758 |  | Membrane to be installed by bonafide approved installer | [10 empty] | 0 | 0 |  |  | 0 | 0
759 |  | Installation to be carried strictly as per manufacturer s specifications | [10 empty] | 0 | 0 |  |  | 0 | 0
760 |  | Waterproofing to wrap up on the wall, upto 900 mm ht | [10 empty] | 0 | 0 |  |  | 0 | 0
761 |  | Waterproofing shall be warranted for 10 years on Rs.100 - stamp paper | [10 empty] | 0 | 0 |  |  | 0 | 0
762 | 1.12 | Jointless ceramic tiles cladding ( for Garbage station ) | smt | 50.02 | 82533 | 2206.4 | 110364.13 | 50.02 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
763 |  | Cladding shall comprise of ceramic tile of 600 mm x 300 mm,Tiles to be fixed in ordinary Portland cement only, Spacer required with Leticrete grout in joints. in plumb,including levelling coat if any , Joints to be filled with matching groute.(Basic cost of ceramic tiles at Rs.60 sft) make Johnson Somany Kajaria Nitco | [10 empty] | 0 | 0 |  |  | 0 | 0
764 | 1.13 | P F of 19mm thick Kota Stone flooring (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, Kotah to be laid with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for kitchen service area. | smt | 100 | 175000 | 2516.29 | 251629 | 100 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
765 |  | B00B01-TFS-I_ID-DOM2-0A-DWG-0004 | [10 empty] | 0 | 0 |  |  | 0 | 0
766 | 1.14 | P F of 304 grade 3mm thick SS Corner guard (50x50x2mmthick SS angles) fixing with SS full thread screws on each corner of the kitchen s wall after cladding of tiles, so that the corner may be protected from the damages, including cleaning, etc. Complete in proper line level as per site engineer s instruction. It is for the back kitchen area. | rmt | 24 | 11400 | 2300 | 55200 | 24 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
767 | II | CEILING AND POP | [10 empty] | 0 | 0 |  |  | 0 | 0
768 | 2.1 | Fire line Gypsum Board ceiling | smt | 100 | 200807 | 2008.07 | 200807 | 100 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
769 |  | All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c | [10 empty] | 0 | 0 |  |  | 0 | 0
770 |  | 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only | [10 empty] | 0 | 0 |  |  | 0 | 0
771 |  | Gypsum Board sheets shall be fitted finished as per manufacturer s specification | [10 empty] | 0 | 0 |  |  | 0 | 0
772 |  | All joints to be fillled with jointing compound including fibre tape reinforcement | [10 empty] | 0 | 0 |  |  | 0 | 0
773 |  | Include finished cutouts for light fixtures, AC grills including necessary framework ply support | [10 empty] | 0 | 0 |  |  | 0 | 0
774 |  | Include 3 mm thk gyp veneer coat on gypsum board (3 mm thk jointing compound filled like punning on wall) | [10 empty] | 0 | 0 |  |  | 0 | 0
775 |  | Include horizontal structural member to span below HVAC ducting for ceiling suspenders | [10 empty] | 0 | 0 |  |  | 0 | 0
776 |  | Exclude painting | [10 empty] | 0 | 0 |  |  | 0 | 0
777 |  | Only fire line Gypsum | [10 empty] | 0 | 0 |  |  | 0 | 0
778 |  | B00B01-TFS-I_ID-DOM-0A-DWG-0006 | [10 empty] | 0 | 0 |  |  | 0 | 0
779 | 2.2 | Universal plaster punning on wall | smt | 2000 | 970000 | 557.8 | 1115600 | 2000 | 60% | 669360 |  |  | 0 | -669360 |  |  | 0 | 0
780 |  | Average 12 mm thk Universal plaster punning by Gyproc Stucco | [10 empty] | 0 | 0 |  |  | 0 | 0
781 |  | Tile bullmarks to be used for channel gliding tracks | [10 empty] | 0 | 0 |  |  | 0 | 0
782 |  | Bull marks to be removed before apply punning | [10 empty] | 0 | 0 |  |  | 0 | 0
783 |  | Surface to be in perfect plum, line and level | [10 empty] | 0 | 0 |  |  | 0 | 0
784 |  | Include pencil rounding to wall corners as instructed | [10 empty] | 0 | 0 |  |  | 0 | 0
785 |  | Smooth finished to receive finishing coating | [10 empty] | 0 | 0 |  |  | 0 | 0
786 |  | Exclude painting work | [10 empty] | 0 | 0 |  |  | 0 | 0
787 | 2.3 | P F of metalized grid ceiling with selected approved Armstrong or eqv. make metal sheet (suspended lay-in square Armstrong metal ceiling, standard plain square tiles of 600mm x 600mm in off white colour, exposed grid white Armstrong metal false ceiling, thickness 0.5 mm, surface treatment in galvanized, off white color coated, features -water proof, corrosion resistant - basic cost INR. 1345.00 SM) and section (as per approved sample) with grid section framework, frame work should be hanged from the existing slab as per manufacture s instruction, including scaffolding, all necessary hardware fittings etc., making provision for lighting, including opening for ventilation grills, duct, etc. as required on site. Complete as per architectural detail drawing site engineer s instruction. It is for kitchen area. | smt | 10 | 21500 | 2231.19 | 22311.9 | 10 |  | 0 | 5.5312 | 60% | 7404.7618 | 7404.7618 | 5.5312 | 95% | 11724.2062 | 4319.4444
788 | 2.4 | SS Foot Rail | rmt | 80 | 180000 | 4100 | 328000 | 80 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
789 |  | up to 200 mm high -Providing and fixing in position 304 grade S.S Satin Bronze finish foot rail of 38mm diameter with horizontal vertical members, Grouting in concrete, etc. complete, as specified and as directed by Architect | [10 empty] | 0 | 0 |  |  | 0 | 0
790 |  | TOTAL OF CIVIL & ID |  |  |  |  | 58017843.09 |  |  | 25503537.4147 |  |  | 29458092.1878 | 3954554.7731 |  |  | 35241772.0601 | 5783679.8724
2 |  | PLUMBING | [5 empty] | 0 |  | 0 | [6 empty] | 0
| A | WATER SUPPLY PIPING | [14 empty] | 0
791 | 1 | Providing fixing PPR-C ( 3 layer pipes-SDR-7.4) confirming to DIN 8078, 8077 - for Domestic, RO, flushing and Hot water, including cutting the pipes to correct length, Fusion welded jointing as per manufacturer, fixing with ms clamps, including necessary fitings like elbows ,tees,unions reducers,coupling, pipe nipples etc.complete, with testing, painting.The work shall also include chasing the walls with machine wherever required for concealed piping require sleeve in walls and making good of chased surface (Pipe shall be tested with 1.5 times working pressure as covered in specifications) | [14 empty] | 0
792 | 1.1 | 20 mm Dia | R.mt | 20 | 10640 | 638.4 | 12768 | 20 | 40% | 5107.2 | 142.45 | 100% | 90940.08 | 85832.88 | 142.45 | 100% | 90940.08 | 0 | 90940.08 | 0
793 | 1.2 | 25 mm Dia | R.mt | 150 | 85800 | 686.4 | 102960 | 150 | 40% | 41184 | 99.59 | 100% | 68358.576 | 27174.576 | 99.59 | 100% | 68358.576 | 0 | 68358.576 | 0
794 | 1.3 | 32mm Dia | R.mt | 60 | 45000 | 900 | 54000 | 60 | 40% | 21600 | 17.8 | 100% | 16020 | -5580 | 17.8 | 100% | 16020 | 0 | 16020 | 0
795 | 1.4 | 40mm Dia | R.mt | 20 | 20680 | 1240.8 | 24816 | 20 | 40% | 9926.4 |  |  | 0 | -9926.4 |  |  | 0 | 0 | 0 | 0
796 | 3 | Providing Fixing of gun metal heavy Ball Valves (approved makes as covered in specification) screwed type for water system of the following diameters(15Kg Sq.cm). Valve shall have with unions. | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
797 | 3.1 | 20mm Dia | Nos. | 8 | 12500 | 2700 | 21600 | 8 | 40% | 8640 |  |  | 0 | -8640 |  |  | 0 | 0 | 0 | 0
798 | 3.2 | 25mm Dia | Nos. | 2 | 4575 | 3360 | 6720 | 2 | 40% | 2688 |  |  | 0 | -2688 |  |  | 0 | 0 | 0 | 0
799 | 3.3 | 32mm Dia | Nos. | 2 | 5125 | 3720 | 7440 | 2 | 40% | 2976 |  |  | 0 | -2976 |  |  | 0 | 0 | 0 | 0
800 | 3.4 | 40mm Dia | Nos. | 2 | 7375 | 4890 | 9780 | 2 | 40% | 3912 |  |  | 0 | -3912 |  |  | 0 | 0 | 0 | 0
801 | 4 | Providing ,fixing, testing and commissioning Electromagnetic flow meter-flow (30 GPM-1.89 LPS) including providing fixing matching with required accessories 16Kgs Sq.cm). - Contractor to check existing make in BIAL airport and provide that. | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
802 | 4.2 | 32 mm Dia incoming line | Nos. | 1 | 14375 | 126000 | 126000 | 1 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
803 | 4.3 | 40 mm Dia incoming line | Nos. | 4 | 62500 | 150000 | 600000 | 4 | 40% | 240000 | 4 | 100% | 600000 | 360000 | 4 | 100% | 600000 | 0 | 600000 | 0
804 | 5 | Supply, installation,testing commissioning of Storage Type Electric Hot Water Generator of mentioned capacity, suitable for 3 KG cm2 pressure, Wall Mounted Floor standing type, with Auto Shut-off Thermostat, along with isoltion Valves, Air Release valve, SS flexible connections andall other std accessories ( Prior to proceed check with client for instant geyser requirement if any) |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
805 | 4.2 | 20 L Capacity | Nos. | 2 | 10500 | 22500 | 45000 | 2 | 40% | 18000 | 2 | 100% | 45000 | 27000 | 2 | 100% | 45000 | 0 | 45000 | 0
806 | B | RO PLANT-PRIOR TO PROCEED LOCATION TO BE FINALISED | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
807 | 1 | Supply , installations, testing and comminissioning of Package RO plant 200 Lit Hr including required internal pumps , all assesories, valves and membrance cleaning system, ultra-violet sterilizer, internal piping within the whole pacakge suitable to connect the inlet and outlet to plumbing contractor work including presure gages etc. | Nos | 2 | 0 | 35700 | 71400 | 2 | 40% | 28560 |  |  | 0 | -28560 |  |  | 0 | 0 | 0 | 0
808 | 2 | Sintex storage tank -300 lit (RO water) | Nos | 2 | 0 | 38100 | 76200 | 2 | 40% | 30480 |  |  | 0 | -30480 |  |  | 0 | 0 | 0 | 0
809 | 3 | Horizntal, pressure booster pumps with motors mounted on a single base frame, complete with all accessories, suction discharge butterfly valves, suction strainers, discharge non-return valves, pressure gauges and of the following capacities | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
810 |  | a)For RO water supply | Nos | 4 | 0 | 23700 | 94800 | 4 | 40% | 37920 |  |  | 0 | -37920 |  |  | 0 | 0 | 0 | 0
811 |  | 50 lpm @ 2.0 kg cm2 discharge pressure. | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
812 | C | DRAINAGE | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
813 | 1 | Providing Fixing spun C.I.hubless Pipes as per IS 3989 1729 (As perISO 6594 As per IS 15905) to correct grade length and alignment including cutting pipes to correct lengths joining as specified by manufacturere including required h M.S.brackets, clamps, testing, painting the pipes with three coats of bitumatic paint complete as per specifications for the following diameters including fittings such as tees. bends, single junction, double junction etc. | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
814 | 1.1 | 75mm Dia | R.mt | 30 | 41880 | 3420 | 102600 | 30 | 40% | 41040 | 52.157 | 100% | 178376.94 | 137336.94 | 52.157 | 100% | 178376.94 | 0 | 178376.94 | 0
815 | 1.2 | 100 mm Dia | R.mt | 65 | 125580 | 3660 | 237900 | 65 | 40% | 95160 | 27.22 | 100% | 99625.2 | 4465.2 | 27.22 | 100% | 99625.2 | 0 | 99625.2 | 0
816 | 1.3 | 150 mm Dia | R.mt | 0 | 0 | 4260 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
817 | 2 | UPVC Type B pipe confirming to IS 13592 (6 Kg CM2) for Soil, Waste upto 65mm dia. confirming to IS 13592 in correct grade,length alingment in Solvent Cement joints including cutting the pipes to correct length, jointing with solvent cement joints,fixing with M.S heavy brackets clamps testing, including cutting holes in R.C.C walls floors making good the same etc all complete including plain fittings such as bends, tees etc. of the following diameters ( basin Sink to FT in toilet internal) | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
818 | 1.1 | 40mm Dia | R.mt | 50 | 29000 | 1770 | 88500 | 50 | 40% | 35400 | 30.45 | 100% | 53896.5 | 18496.5 | 30.45 | 100% | 53896.5 | 0 | 53896.5 | 0
819 | 1.2 | 50mm Dia | R.mt | 40 | 27200 | 2010 | 80400 | 40 | 40% | 32160 | 8.02 | 100% | 16120.2 | -16039.8 | 8.02 | 100% | 16120.2 | 0 | 16120.2 | 0
820 | 1.3 | 65mm Dia | R.mt | 15 | 11250 | 2142 | 32130 | 15 | 40% | 12852 |  |  | 0 | -12852 |  |  | 0 | 0 | 0 | 0
821 | 1.4 | 75mm Dia | R.mt | 20 | 18000 | 2268 | 45360 | 20 | 40% | 18144 |  |  | 0 | -18144 |  |  | 0 | 0 | 0 | 0
822 | 3 | Supply, Install PVAC multiTraps including fixing with lead caulked joints and rings, c w Circular SS 304 Grating, ( in bar and live kitchen) | Nos. | 6 | 10800 | 2700 | 16200 | 6 | 40% | 6480 |  |  | 0 | -6480 |  |  | 0 | 0 | 0 | 0
823 | 4 | Supply, Install CI multiTraps including fixing with lead caulked joints and rings, c w Circular SS 304 Grating, ( Subject to site requirement) | Nos. | 8 | 20000 | 3420 | 27360 | 8 | 40% | 10944 |  |  | 0 | -10944 |  |  | 0 | 0 | 0 | 0
824 | 5 | Supply, Install CI floor Traps including fixing with lead caulked joints and rings, c w Circular SS 304 Grating, | Nos. | 6 | 14400 | 2940 | 17640 | 6 | 40% | 7056 |  |  | 0 | -7056 |  |  | 0 | 0 | 0 | 0
825 | 6 | Supply, Install CI urinal Traps including fixing with necessary consumables with Circular SS Grating with anti cockroach jali Suitable for 75mm Dia outlet | Nos. | 1 | 1500 | 3570 | 3570 | 1 | 40% | 1428 |  |  | 0 | -1428 |  |  | 0 | 0 | 0 | 0
826 | 8 | Supply, Install CI custom made clean out plungs with brass cap including fixing with necessary consumables.(Optional if required at site) | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
827 | 8.2 | 75 mm Dia | Nos. | 2 | 1900 | 1140 | 2280 | 2 | 40% | 912 |  |  | 0 | -912 |  |  | 0 | 0 | 0 | 0
828 | 8.3 | 100 mm Dia | Nos. | 5 | 6250 | 1500 | 7500 | 5 | 40% | 3000 |  |  | 0 | -3000 |  |  | 0 | 0 | 0 | 0
829 | 9 | Supply, Install GREASE TRAP-MODEL LIPUMOBIL-S | Nos. | 2 | 16250 | 111300 | 222600 | 2 | 80% | 178080 | 2 | 80% | 178080 | 0 | 2 | 90% | 200340 | 22260 | 178080 | 0
830 | 10 | Only Installation of S.S. grating of 300x300mm shown in the layout (Note- supply of SS gratings will be by kitchen consultant or TFS) | Nos. | 1 | 900 | 12600 | 12600 | 1 |  | 0 | 2 | 90% | 22680 | 22680 | 2 | 90% | 22680 | 0 | 22680 | 0
831 | D | CORE CUTS | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
832 | 1 | Providing core cuts as per following size with backfilling water proofing core cuts to be sealed as required standared as required by project manager | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
833 | 1.3 | 150 mm Dia | Nos. | 4 | 8000 | 3000 | 12000 | 4 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
834 | D | CORE CUTS | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
835 | E | SANITARY AND C. P. FITTINGS FIXTURES | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
836 |  | Only installation, testing and commissioning of sanitary and C.P. fittings | [10 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
837 | 1.1 | EWC with seat cover | Nos | 10 | 35000 | 5400 | 54000 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
838 | 1.2 | Concealed flush tank | Nos | 10 | 25000 | 4560 | 45600 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
839 | 1.4 | Health Faucet | Nos | 10 | 4360 | 1260 | 12600 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
840 | 1.5 | 2 Way Bib-Cock with connection for Health Faucet | Nos | 10 | 6760 | 1500 | 15000 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
841 | 1.7 | Under Counter Wash Basin including waste Coupling | Nos | 11 | 32725 | 3570 | 39270 | 11 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
842 | 1.8 | Wash Basin Cock | Nos | 11 | 8965 | 1260 | 13860 | 11 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
843 | 1.11 | Under Counter Sink including waste Coupling | Nos | 3 | 2550 | 1020 | 3060 | 3 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
844 | 1.12 | Sink Pillar Cock | Nos | 3 | 1875 | 1260 | 3780 | 3 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
845 | 1.13 | Bottle Trap for WHB sink and urinal with all connecting pipes | Nos | 18 | 15750 | 1500 | 27000 | 18 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
846 | 1.14 | Angle Cock with PVC pipe connection upto WHB sink Geyser connection | Nos | 29 | 15254 | 900 | 26100 | 29 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
847 | 1.15 | Urinal | Nos | 4 | 13500 | 4560 | 18240 | 4 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
848 | 1.16 | Auto Flush Valve Sensor with connecting piping spreader for urinal(DC) | Nos | 4 | 0 | 4500 | 18000 | 4 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
849 | 1.17 | Soap Dispenser | Nos | 11 | 2750 | 300 | 3300 | 11 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
850 | 1.18 | Paper Holder | Nos | 10 | 2500 | 300 | 3000 | 10 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
851 |  | TOTAL OF PLUMBING |  |  |  |  | 2444934 |  |  | 893649.6 |  |  | 1369097.496 | 475447.896 |  |  | 1391357.496 | 22260
|  | TOTAL OF CIVIL,ID & PLUMBING |  |  |  |  | 60462777.09 |  |  | 0 |  |  |  |  | 0
|  | TOTAL OF CIVIL,ID & PLUMBING |  |  |  |  | 60462777.09 |  |  | 0
0
0
0
0

## RA3 ms
Sr.no | Item Name | Qty | Length | Height | Total Qty
OVERALL
I | CIVIL WORK
1.1 | 18 mm thick Italian Marble flooring | Smt
Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including approved sealer to be applied on all sides, with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft
a | Overall passage Between low height partitions (Welcome zone to water lounge ) as per Autocad | 1 |  |  | 201.458
1.2 | 18 mm thick Italian Marble Dado on Lift wall including Jamb line
At least 18 mm thk polished marble fixed to Plastered masonry, Marble shall be cut from slabs of even thickness, Marble shall be installed with white cement paste, Include all finished marble niches, with V groove edge polish etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, All visible edges of Marble shall be mirror polished, including approved sealer to be applied on all sides , Basic cost of marble Rs 450 sft
1.3 | Designer Texture Tile Cladding
Clean existing wall surface before fixing Texture designer tile Before starting, carefully read the suppliers laying plan and instructions.DecorativeTexture tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of Texture tiles at Rs.400 sft without tax
1.4 | Marble Jamb line
All around the Opening Up to 250 mm Wide ,polished Italian marble fixed to existing masonry Plastered wall, Marble shall be installed with white cement paste, if installed on masonry work, with edge Moulding etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, All visible edges of Marble shall be mirror polished, including approved sealer to be applied on all sides , Special care to be taken to fix marble on horizontal surface. Shall rest over ply at one end and vertical marble on the other, ( Basic cost of marble Rs 450 sft )
1.5 | Marble Skirting Boxing -Openable
up to 150 mm high x 200 mm wide ,Skirting Boxing to be made out of 18 mm thick Marine ply, Ply to be covered with 18 MM thick Italian Marble including Edge Moulding, etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, All visible edges of Marble shall be mirror polished, approved sealer to be applied on all sides ( Basic cost of marble Rs 450 sft )
II | FRENCH PLASTER WORK
2.1 | Fire line Gypsum board ceiling
All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobin Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibber tape reinforcement, Include finished cutouts for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceiling height is 4300 mm )
2.2 | Bulk Head in Profile- In Flat Water cut Paint finish
As per drawing -Size up to 600 mm wide x 1850 mm high, Using 50mm x 36 mm, 16 SWG aluminium framework at 600 mm c c Fixed on existing Structural Framework, Frame to be covered with 18 mm thick marine ply, For Curve surface use 6+6+6 mm flexi ply, 12 mm thick HDF to be fixed on Ply, For Curve surface use 6+6 mm flexi HDF, All joints shall be filled with suitable fillers and reinforcement tape, 50 mm wide x 25 mm thick HDF fluting to be fixed on HDF surface with 25 mm gap, Base and HDF moulding surface shall be finished n Water cut enamel Paint finish, as approved by Architect, include 450 mm wide x 100 mm thick veneer finish Band at bottom, Veneer to be finished in Approved Melamine polish . Including 2 layers of light Pelmet with Led strip light provision. (Basic cost of veneer up to Rs. 125 -sft )
refer Drawing no- B01-TFS-DOM02-ID-00-13
a | As per AutoCAD sport bar in front curved flooring | Rmt |  |  | 25.82
2.3 | POP plaster punning
| Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bull marks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work | Sqm
Bar store room area
a | Bar storage front wall (N) | 1 | 9.37 | 2.8 | 26.236
b | Bar storage right-side wall (O) | 1 | 3.42 | 2.8 | 9.576
c | Bar storage left side wall (Q) | 1 | 1.7 | 2.8 | 4.76
d | Bar storage backside wall (P) | 1 | 16.356 | 2.8 | 45.7968
e | Bar back side wall | 1 | 7.7 | 3.4 | 26.18 | 86.37
112.5488
0
0
III | CARPENTRY WORK |  |  |  | 0
3.1 | FRP Ply Panelling
providing and fixing Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at centre of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material
12 mm thk Fire rated plywood
15 mm thk Fire rated plywood
18 mm thk Fire rated plywood
6 mm thk Flexi Fire rated plywood
3.2 | Veneer skin
Using 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, pressed over backing plywood including matching wood beading as per approved design, with 3 mm x 3mm finish groove as per design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be finished in Approved Water base PU polish
(Basic cost of veneer up to Rs. 125 -sft )
refer Drawing no- B01-TFS-DOM02-ID-00-13
3.3 | SS Satin Bronze finish Floor Insert in Curved Profile
up to 18 mm wide, 4 mm thick 304 grade Insert in Two Floorings , Fixed with epoxy adhesive
Spa
| Strat door entrance side | 1 | 1.136 |  | 1.136
|  | 1 | 1.683 |  | 1.683
|  | 1 | 5.266 |  | 5.266
|  | 1 | 4.004 |  | 4.004
|  | 1 | 4.906 |  | 4.906
|  | 1 | 3.334 |  | 3.334
Sports bar
| passage between wooden partition to wall panelling | 1 | 6.41 |  | 6.41
| Before bar counter, additional strip to be installed. | 1 | 10.7 |  | 10.7
| Between wooden partition and opposite tapper column. | 1 | 1.53 |  | 1.53
Relax zone
| Between wooden curved partition and opposite tea lounge | 1 | 2.025 |  | 2.025
| T- profile separating wooden floor | 1 | 10.64 |  | 10.64
Living Dining
| Between curved wooden partition & opposite tapper column | 1 | 6.77 |  | 6.77
| Between end of curved partition and end of buffet counter. | 1 | 1.65 |  | 1.65
Fine Dining
| Between tips of two long sofas wooden partition. Incomplete | 1 | 4.37 |  | 4.37
Tea garden
| Left side passage | 1 | 1.51 |  | 1.51
| Right side passage | 1 | 1.5 |  | 1.5
| Round pink terrazzo | 1 | 3 |  | 3
| Round pink terrazzo | 1 | 4.4 |  | 4.4
| Round pink terrazzo | 1 | 4.4 |  | 4.4
| Round pink terrazzo | 1 | 4.4 |  | 4.4
83.634
3.4 | SS Bronze Satin finish skirting 50mm high
16 SWG, 304 Grade SS skirting over existing ply, Fixed with epoxy adhesive
refer Drawing no- B01-TFS-DOM02-ID-00-13
| Sports bar teppar coloumn | 1 | 9.9 |  | 9.9
3.5 | View Cutter Panelling up to 2500 mm high above Deck Slab
Providing and fixing using 36 x36 mm MS partition frame work with cross bracing, Frame Anchor to Deck slab, Exposed side of frame to be covered with 12 mm thick HDF base ,additional 6 mm HDF to be fixed on 12 mm thick base with 12 mm Groove pattern, Finish in approved Lustur paint
IV | MISCELLANOUS WORK
4.1 | Art paintings atrifacts
4.2 | Signages
4.3 | Attendance for MEPF works
On Electrical Lighting allied Works
On IT Works
On Fire Protection System Works
On HVAC Works
On Plumbing Works
On Kitchen Works
Including all Other services
V | PAINTING WORK
5.1 | Highlight Painting to walls
Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of luster paint. Complete as per manufacturer s specifications
5.2 | Duco Paint to Walls Partition
Sanding and preparing surface for receiving paint, Final coats of Duco paint. Complete as per manufacturer s specifications
5.3 | Painting to ceiling in acrylic emulsion paint
Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base. Two coats of putty ,Three coats of acrylic emulsion paint, Complete as per manufacturer s specifications
5.4 | Concrete texture finish Paint
Paint By Evolve-Mumbai ( basic cost of Pait Rs 250 sqft )
OVERALL EXTRA ITEAM
1 | P F of metalized grid ceiling with selected approved Armstrong or eqv. make metal sheet (suspended lay-in square Armstrong metal ceiling, standard plain square tiles of 600mm x 600mm in off white colour, exposed grid white Armstrong metal false ceiling, thickness 0.5 mm, surface treatment in galvanized, off white colour coated, features -water proof, corrosion resistant - basic cost INR. 1345.00 SM) and section (as per approved sample) with grid section framework, frame work should be hanged from the existing slab as per manufacture s instruction, including scaffolding, all necessary hardware fittings etc., making provision for lighting, including opening for ventilation grills, duct, etc. as required on site. Complete as per architectural detail drawing site engineer s instruction. It is for kitchen area.
| BOH service corridor passage | 1 | 14.65 | 2.05 | 30.0325
| BOH Area Duct wall passage (middle) | 1 | 3.11 | 1.875 | 5.8312
| BOH Area Back Passage | 1 | 4.275 | 1.95 | 8.3362
| Staff toilet Left & right | 2 | 2.43 | 1.242 | 6.0361
| Electrical room | 1 | 1.29 | 1.84 | 2.3736
| Janitor room | 1 | 1.45 | 1.2 | 1.74
| Service corridor welcome zone | 1 | 8.603 | 1.2 | 10.3236
| Electrical room (near it room) | 1 | 1.822 | 1.04 | 1.8949
| Bar storage room inside Ceiling | 1 | 9.293 | 1.69 | 15.7052
| Less Bar Bottle display(-) | -1 | 3.851 | 0.64 | -2.4646
79.8087
2 | 18 mm thick Italian Marble flooring
Marble strip size up to 50 to 225 mm wide in various length, Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides , with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft
a | Straight Railing bellow (left side ) | 1 | 42 | 0.3 | 12.6
b | Curved Railing bellow (Right side ) | 1 | 54 | 0.3 | 16.2
28.8
3 | Vitrified tile Flooring for janitor room
Clean existing sub floor thoroughly before fixing Vitrified tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.150 sft without tax
| Left & right side wall | 2 | 1.29 | 2.4 | 6.192
| Front & back wall | 2 | 1.45 | 2.4 | 6.96
| Less door(-) | -1 | 0.75 | 2 | -1.5
11.652
4 | Luster Painting to walls
Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of luster paint. Complete as per manufacturer s specifications
BOH Live kitchen corridor
| Luster paint | 1 | 4.7 | 0.9 | 4.23
| Luster paint | 1 | 6.54 | 0.9 | 5.886
| Luster paint | 1 | 6.39 | 0.9 | 5.751
| Luster paint | 1 | 1.94 | 0.7 | 1.358
| Luster paint | 1 | 7.9 | 3.28 | 25.912
| Luster paint | 1 | 5.8 | 1.03 | 5.974
| Luster paint | 1 | 2.6 | 2.34 | 6.084
| Luster paint | 1 | 1.92 | 2.6 | 4.992
| Luster paint | 1 | 4.51 | 0.9 | 4.059
| Luster paint | 1 | 5.3 | 0.9 | 4.77
| Luster paint | 1 | 1.55 | 0.47 | 0.7285
| Luster paint | 1 | 2.38 | 1.045 | 2.4871
| Luster paint | 1 | 0.3 | 2.1 | 0.63
| Luster paint | 1 | 8.93 | 0.9 | 8.037
| Luster paint | 1 | 1.2 | 2.05 | 2.46
| Luster paint | 1 | 2.05 | 0.9 | 1.845
| Deduction | 2 | 0.76 | 0.83 | 1.2616
| Deduction | 1 | 0.885 | 0.56 | 0.4956
| Deduction | 1 | 0.43 | 0.11 | 0.0473
| Deduction | 1 | 1.56 | 0.42 | 0.6552
| Deduction | 1 | 0.91 | 0.4 | 0.364
| Deduction | 1 | 1.49 | 0.42 | 0.6258
|  | 1 | 5.8 | 2.6 | 15.08
0
| Lobby Electric room | 1 | 2.75 | 2.6 | 7.15
|  | 1 | 2.75 | 2.6 | 7.15
|  | 1 | 1.3 | 2.6 | 3.38
|  | 1 | 1.3 | 2.6 | 3.38
| Deduction | 1 | 1.53 | 2.07 | 3.1671
127.9602
WELCOME LOUNGE
I | DEMOLITION WORK
II | MASONRY WORK
2.1 | P C of 150mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level.
Added in SPA area as thickness is 200mm
2.2 | P C of 100mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level. | Sq. Mtr.
a | IT room above entry". | 1 | 1.975 | 3.8 | 7.505
b | Less door opening (-) | -1 | 0.77 | 2.075 | -1.5978
c | Electric room entry wall "C" | 1 | 2.65 | 3.2 | 8.48
d | Less door (-) | -1 | 0.9 | 2.05 | -1.845
e | Hvac entry wall right side"E" | 1 | 2.15 | 0.4 | 0.86
| Sport bar counter area storage |  |  |  | 0
f | Sports bar counter curved wall "A". | 1 | 10.75 | 1.2 | 12.9
26.3023
2.3 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr.
a | Welcome zone fire room wall "A". Deduct door area. | 2 | 5.8 | 4.2 | 48.72
b | Less door (-) | -2 | 1.1 | 2.1 | -4.62
c | Welcome zone fire room wall "A". Deduct door area. | 2 | 0.4 | 4.2 | 3.36
d | Less door (-) | -2 | 0.97 | 2.27 | -4.4038
e | Electric room right side wall"D" | 2 | 2 | 3.2 | 12.8
f | IT room above entry". | 1 | 1.975 | 3.8 | 7.505
g | Less door opening (-) | -1 | 0.77 | 2.075 | -1.5978
h | Electric room entry wall "C" | 1 | 2.65 | 3.2 | 8.48
i | Less door (-) | -1 | 0.9 | 2.05 | -1.845
j | Hvac entry wall right side"E" | 1 | 2.15 | 0.4 | 0.86
k | Welcome zone fire room wall "A". Deduct door area. | 2 | 5.8 | 4.2 | 48.72
l | Less door (-) | -2 | 1.1 | 2.1 | -4.62
m | Welcome zone fire room wall "A". Deduct door area. | 2 | 0.4 | 4.2 | 3.36
n | Less door (-) | -2 | 0.97 | 2.27 | -4.4038
o | Electric room right side wall"D" | 2 | 2 | 3.2 | 12.8
p | IT room above entry". | 2 | 1.975 | 3.8 | 15.01
q | Less door opening (-) | -2 | 0.77 | 2.075 | -3.1955
r | Electric room entry wall "C" | 2 | 2.65 | 3.2 | 16.96
s | Less door (-) | -2 | 0.9 | 2.05 | -3.69
t | Hvac entry wall right side "E" | 2 | 2.15 | 0.4 | 1.72
u | Passage entry above (welcome zone) | 2 | 1 | 4.2 | 8.4
v | Welcome zone fire panel wall (A) | 1 | 4.8 | 4.2 | 20.16
w | Less panel (-) | -1 | 1.1 | 2.1 | -2.31
x | Sport bar counter area storage |  |  |  | 0
y | Sports bar counter curved wall "A". both side plaster. | 2 | 10.75 | 1.2 | 25.8
z | Sports bar front wall "B" | 2 | 8.25 | 4.8 | 79.2
aa | Sports bar front wall "C" | 2 | 5.02 | 4.8 | 48.192
ab | Less door (-) | -2 | 0.9 | 2.4 | -4.32
ac | Bar storage left side wall"D" | 2 | 1.75 | 4 | 14
341.0412
2.4 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc.
a | Service passage left side wall "F" | 1 | 6.42 | 3.05 | 19.581
b | Above IT room's entry "G" | 1 | 1.6 | 1.67 | 2.672
c | Electric panel front side wall "H" | 1 | 3.9 | 3.3 | 12.87
d | Passage entry above welcome zone(double). | 1 | 1 | 4.2 | 4.2
e | Less door | -1 | 0.97 | 2.27 | -2.2019
f | Welcome zone fire panel wall "A". Deduct panel area ie,1100x2100 | 1 | 4.8 | 4.2 | 20.16
g | Less panel area | -1 | 1.1 | 2.1 | -2.31
h | Sport bar counter area storage |  |  |  | 0
i | Bar storage front wall"E" | 1 | 9.3 | 3.2 | 29.76
84.7311
2.5 | P C of 50mm 75mm thick screed in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Laying the same in proper line level on the seating area s floor to maintain the floor levelling to get the smooth surface to lay the finishing floor materials on the said surface. Complete as per architectural detail drawings instruction by the site engineer.
| Lift lobby | 1 | 3 | 3.1 | 9.3
III | CIVIL WORK
3.1 | 18 mm thick Italian Marble flooring - Dark
Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides , with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft
3.2 | Kota Stone Flooring for Corridor | Smt
P F of 19mm thick Kota Stone flooring (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, Kotah to be laid with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for service area.
a | AHU service corridor | 1 | 8.63 | 1.2 | 10.356
b | IT room entry | 1 | 1.7 | 0.55 | 0.935
c | Less IT room wall (-) | -1 | 0.25 | 0.63 | -0.1575
d | Electric room | 1 | 1.05 | 0.55 | 0.5775
e | Bar storage room flooring | 1 | 9.273 | 1.695 | 15.7177
f | Less column (-) | -1 | 3.847 | 0.63 | -2.4236
25.0051
3.3 | 18 mm thick Italian Marble Dado on Lift wall including Jamb line | Smt
At least 18 mm thk polished marble fixed to Plastered masonry, Marble shall be cut from slabs of even thickness, Marble shall be installed with white cement paste, Include all finished marble niches, with V groove edge polish etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, including Approved sealer to be applied on all sides, All visible edges of Marble shall be mirror polished, Basic cost of marble Rs 450 sft
a | Lift wall | 1 | 3.05 | 3 | 9.15
b | Less lift door (-) | -1 | 2.25 | 2.715 | -6.1087
3.0412
3.4 | 18 mm thick Exotic Italian Marble Cladding on signage wall | Sqm
At least 18 mm thk polished marble fixed to Plastered masonry, Marble shall be cut from slabs of even thickness, Marble shall be installed with white cement paste, Include all finished marble niches, with V groove edge polish etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, including Approved sealer to be applied on all sides, All visible edges of Marble shall be mirror polished, Basic cost of marble Rs 1000 sft
| exotic marble Welcome zone | 1 | 1.985 | 3 | 5.955
| Lift 2 | 1 | 4.4 | 3 | 13.2
19.155
3.5 | Marble finish Planter Box | Nos
As per Drawing- Size up to 1800 mm in length x 600 mm wide 600 mm high, Planter box Frame to be made 50 mm x 38 mm MS box Frame, Planter Skirting Base to be Covered with 12 mm thick FRP Ply and 50 mm high 16g 304 grade SS satin Bronze finish Skirting, Frame Vertical surfaces to be covered with At least 18 mm thk Onyx marble fixed to MS box frame with SS clamps pins and Adhesive from outside , and From in side Base to be finish in ordinary marble and Vertical Surfaces to be covered with 12 mm thick FRP Ply and Laminate with Mirror Screw ( openable Panel ), Including 6 mm thick 304 grade SS satin Bronze finish top Trim, etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, including Approved sealer to be applied on all sides, All visible edges of Marble shall be mirror polished, Basic cost of marble Rs 1500 sft
|  | 2 |  |  | 2
3.6 | Kota Stone Skirting 150 mm high | Rmt
P F of 19mm thick Kota Stone Skirting (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, Fix as detailed in drawing, fix with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for service area.
a | AHU service passage | 2 | 8.63 |  | 17.26
b | Less door IT | 1 | 1.07 |  | 1.07
18.33
IV | FRENCH PLASTER WORK
4.1 | Fire line Gypsum board ceiling
All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobin Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibber tape reinforcement, Include finished cutouts for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceiling height is 4300 mm )
a | Lift lobby 1 | 1 | 3 | 3.1 | 9.3
b | Rest as per auto cad | 1 |  |  | 39.4222
c | Lift lobby 2 Ceiling | 1 | 6.65 | 2.4 | 15.96
d | Offset | 1 | 2 | 0.5 | 1
65.6822
4.2 | Curved Feature ceiling with facia in Water cut Enamel Paint finish
All MS framework for ceiling to be used, 50mm x 50 mm, MS Box framework at 600 mm c c fixed to Existing MS framework Wall and Partition frame work with proper welding bolting , Including anti rust paint ,ceiling frame to be covered with 12 mm thick ply from all side and 6+6 mm thick Flexi ply for curved profile, Ply to be covered with 12mm thk MDF board to be used to Received Water cut Enamel Paint Finish Including 6+6 mm thick for curved profile, All joints to be filled with jointing compound , Include finished cutouts for light fixtures, AC grills .
a | Oval shape | 1 | 2.6 | 1.7 | 4.42
4.3 | FR Gypsum board Cove for indirect light
In L shape with 150 mm deep up to 300mm high and 50 mm wide fascia, All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobin Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibber tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum
*in Straight Profile
a | Lift lobby cove | 4 | 2.2 |  | 8.8
b | Welcome zone ceiling drop | 1 | 9.079 |  | 9.079
c | Welcome zone sides | 1 | 1.436 |  | 1.436
19.315
*In Curved Profile
a |  | 1 | 10.132 |  | 10.132
4.4 | POP plaster punning
Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bull marks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work
a | Lift lobby "A" opposite to lift | 1 | 2.8 | 3.45 | 9.66
b | Welcome zone opposite to reception "B" | 1 | 11.48 | 3.65 | 41.902
c | Welcome zone fire hose wall | 1 | 4.8 | 4.2 | 20.16
d | Less fire hose area | -1 | 1.1 | 2.1 | -2.31
e | Welcome zone AHU passage entry above "D" both sides | 2 | 1 | 3.5 | 7
f | Less passage entry door | -1 | 0.97 | 2.27 | -2.2019
g | AHU ,IT, electric room |  |  |  | 0
h | Service passage left side wall "E" | 1 | 8.56 | 2.6 | 22.256
i | Service passage right-side wall "F" | 1 | 1.05 | 2 | 2.1
j | AHU room entry above "G" | 1 | 1.2 | 2.6 | 3.12
k | Less door | -1 | 1 | 2 | -2
l | Electric room entry wall above "H" | 1 | 1.8 | 2.6 | 4.68
m | Less door | -1 | 0.58 | 2 | -1.16
n | Electric room panel opposite wall "J" | 1 | 5 | 2.6 | 13
o | Electric room panel right-side wall "K" | 1 | 1.98 | 2.6 | 5.148
p | Electric room panel backside wall "L" | 1 | 3.15 | 2.6 | 8.19
q | IT room above entry "M" | 1 | 3.15 | 2.6 | 8.19
r | "Z" | 1 | 1.68 | 0.6 | 1.008
s | "Y" | 1 | 0.9 | 0.6 | 0.54
139.2821
V | CARPENTRY WORK
5.1 | Aluminium frame work In Profile for Art work
36mm x 36 mm, 16 SWG aluminium framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment, including provision for Electrical Conduit and slot for Digital screen as shown in drawing
5.2 | Aluminium frame work For Panelling | Smt
36mm x 36 mm, 16 SWG aluminium framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment, including provision for Electrical Conduit and slot for Digital screen as shown in drawing
a | Lift lobby portal framing (verticals) | 4 | 0.7 | 2.45 | 6.86
b | Fire house vertical portal | 2 | 0.7 | 3.1 | 4.34
c | Portal horizontal beams (lift lobby) | 2 | 2 | 3.2 | 12.8
d | Fire house portal horizontal (U) | 1 | 3.1 | 1.2 | 3.72
27.72
5.3 | FRP Ply Panelling
providing and fixing Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at centre of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material
A | 12 mm thk Fire rated plywood | Smt
a | A Lift opposite | 1 | 3.057 | 3.2 | 9.7824
b | B Art wall | 1 | 9.13 | 3.66 | 33.4158
c | C column boxing (logo) | 1 | 1.345 | 3.66 | 4.9227
d | D Whole MS column | 1 | 2.44 | 3.66 | 8.9304
e | E SPA entry wall | 1 | 2.53 | 3.66 | 9.2598
f | F portal vertical | 1 | 0.74 | 2.424 | 1.7938
g | G Portal horizontal | 1 | 2.77 | 1.98 | 5.4846
h | H Lift lobby portal | 1 | 3.51 | 4.404 | 15.458
i | J fire hose wall | 1 | 1.98 | 2.353 | 4.6589
j | K Fire hose wall | 1 | 5.321 | 3.66 | 19.4749
k | L vertical portal | 1 | 0.11 | 3.934 | 0.43274
l | M vertical portal | 1 | 0.82 | 30.9 | 25.338
m | Less SPA door | -1 | 1.017 | 2.275 | -2.3137
n | Fire hose edges | 2 | 0.55 | 2 | 2.2
o | top | 1 | 1.074 | 0.444 | 0.47686
p | Less AHU Passage door | 1 | 0.991 | 2.286 | 2.2654
q | Extra ply celling in lift lobby | 1 | 3 | 3.1 | 9.3
150.8806
B | 15 mm thk Fire rated plywood | Smt
C | 18 mm thk Fire rated plywood | Smt
D | 6 mm thk Flexi Fire rated plywood | Smt
5.4 | HDF Panelling
providing and fixing HDF Panel to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of HDF to end at centre of framework. Edges to be tightly screwed to framework at 300 mm c c. Edges to be planed properly to receive finish material
| 12 mm thk HDF | Smt
| 6 mm thk Flexi HDF | Smt
5.5 | Fluted Wall panelling in Metallic Duco paint finish | smt
Using 12 mm thk HDF to be fixed on Existing ply as base , All joints shall be planed and smoothened before installing fluting mouldings. All joints shall be filled with suitable fillers and reinforcement tape, if required. HDF Mouldings to be fixed as per drawing ( min 25 mm wide deep ), shall be installed on HDF back surface in perfect plumb, line and level. base and HDF moulding surface shall be finished in metallic Duco paint, as approved by Architect
a | C column boxing (logo) | 1 | 1.345 | 3.66 | 4.9227
b | D Whole MS column | 1 | 2.44 | 3.66 | 8.9304
c | E SPA entry wall | 1 | 2.53 | 3.66 | 9.2598
d | F portal vertical | 1 | 0.74 | 2.424 | 1.7938
e | G Portal horizontal | 1 | 2.77 | 1.98 | 5.4846
f | H Lift lobby portal | 1 | 3.51 | 4.404 | 15.458
g | J fire hose wall | 1 | 1.98 | 2.353 | 4.6589
h | K Fire hose wall | 1 | 5.321 | 3.66 | 19.4749
i | L vertical portal | 1 | 0.11 | 3.934 | 0.43274
j | M vertical portal | 1 | 0.82 | 30.9 | 25.338
k | Less SPA door (-) | -1 | 1.017 | 2.275 | -2.3137
l | Fire hose edges | 2 | 0.55 | 2 | 2.2
m | top | 1 | 1.074 | 0.444 | 0.47686
n | Less AHU Passage door | 1 | 0.991 | 2.286 | 2.2654
98.3824
5.6 | Backlit Feature Wall Panelling in SS Gold Finish | smt
As per Drawing - Size up to 3600 mm wide x 3600 mm high, Feature wall frame work to be made out of 50mm x 100 mm MS Box framework , fixed to Floor slab wall with adequate anchor bolts and plates, Including anti rust paint , Frame to be covered 6 mm thick FRP Flexi Ply, 6+6 mm thick FRP Flexi ply battens to be made and fix on 6 mm thick base ply with 30 mm Gap, Batten to be covered with 16G, 304 grade SS sheet in C shape Profile ( as per approved design ) sheet in Gold Finish , 30 mm x 40 mm SS Gold finish box insert in Perforated sheet as per drawing, including Vertical provision for Led strip light and Electrical Conduit. Include SS sheet insert in Groove
a | Reception back panelling wall | 1 | 3.76 | 3.66 | 13.7616
5.7 | Concrete Finish Fins- in Profile | SQmt
As per Drawing - Size up to 650 mm wide x 3600 mm high, Fins frame work to be made out of 38mm x 38 mm MS Box framework , fixed to Floor slab wall with adequate anchor bolts and plates, Including anti rust paint , Frame to be covered with 12 mm thick Marin Ply , 4 mm thick HDF to be Fix on ply to received Concrete finish Coating, including Vertical Light Pelmet provision for Led strip light and Electrical Conduit. Include 16 SWG, 304 Grade SS skirting. ( basic cost of Pait Rs 250 sqft )
a | Reception area both side | 4 | 0.9 | 3.66 | 13.176
5.8 | SS Bronze Satin finish skirting 50mm high | Rmt
16 SWG, 304 Grade SS skirting over existing ply, Fixed with epoxy adhesive
| Entrance portal | 2 | 0.57 |  | 1.14
| Lift side wall till door | 1 | 1.97 |  | 1.97
| Spa door to backlit panel | 1 | 2.205 |  | 2.205
| Backlit to corrodor | 1 | 2.63 |  | 2.63
| Corrodor to brick cladding | 1 | 6.05 |  | 6.05
| Right side lift opp mirror to exotic marble | 1 | 2.37 |  | 2.37
| Portal | 1 | 1.31 |  | 1.31
0
17.675
5.9 | 400 mm wide Veneer SS finish Portal | Smt
Providing and fixing 4 mm thick Veneer and 16 G SS 304 cladding as portal, finish in PU and PVD coating
5.10 | TINTED Mirror PANELING | Smt
Providing and fixing 8 mm thick Tinted Mirror on existing ply , Fixed with Approved adhesive
| Lift Lobby opposite | 1 | 3.06 | 3 | 9.18
| Fire Hose Opposite wall art wall 1 | 1 | 4.75 | 3 | 14.25
| Fire Hose Opposite wall art wall 2 | 1 | 3.6 | 3 | 10.8
| lift2 | 1 | 2.025 | 3 | 6.075
40.305
5.11 | Reception Desk - Lecturn for Main Entrance | Nos
Providing and fixing 1000 mm wide x 2000 mm length Reception (Lectrun )desk , finish in Marble SS Veneer. As per detail drawings
a |  | 1 |  |  | 1
5.12 | Reception Desk - Lecturn for Service lift Entry | Nos
Providing and fixing 1000 mm wide x 1000 mm length Reception (Lectrun )desk , finish in Marble SS Veneer. As per detail drawings
a |  | 1 |  |  | 1
5.13 | Service room Spa room Door in Fluted design matching to fluted panelling in metallic Paint Finish | No
Size 1000mm x 2250mm
Door Frame
Overall finish size 250mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick FRP ply as rough ground, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 4 mm thk HDF, Rebate to be separately put in CP wood, including , Wood to be treated with anti-termite medicine, Frame to be finish in Approved Metallic Duco paint finish
Shutter
Overall size 900 mm wide x 2250 mm ht. x 1 leaf, up to 67 mm thk. Using 38 mm thick readymade fireproof shutter covered with 12 mm thick FRP ply on both sides. The shutter shall be clad with 4 mm thick mdf on one side Laminate on other side including NBTW beading all around. including 25x25mm HDF strip press on HDF side on shutter as per drawings, Shutter and MDF strip be finish in Approved Metallic Duco paint finish
Hardware
125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, Dead lock with suitable cover plate, Concealed door closer by Hafele Dorma as per required capacity, 1 set of handle as approved by Architect
a |  | 2 |  |  | 2
5.14 | Fire Hose reel Double leaf Glass Door | nos
Shutter-Size 1200mm x 2250mm
As per drawing, Using 6 mm toughened glass Door with Powder coated Aluminium frame , all edges CNC machine polished
Hardware
The shutter shall be mounted on min. 3 nos. bearing SS copper finished hinges with proprietary screws, made by Hafele Dorma or equivalent approved by Architect. handle with locking arrangement, by Hafele or equivalent approved,
a
5.15 | Service Door_Dining Area | No
Size 1500mm x 2250mm Double Leaf
Door Frame
Overall finish size 250mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick FRP ply as rough ground, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk New Burma teak wood, Rebate to be separately put in rough ground frame, Wood to be treated with anti-termite medicine, Frame to be finish in Approved Melamine polish
Shutter
Overall size 750 mm wide x 2250 mm ht. x 2 leaf, up to 67 mm thk. Using 38 mm thick readymade fireproof shutter covered with 12 mm thick FRP ply on both sides. The shutter shall be clad with 4 mm thick Veneer from lounge side and other side 1 mm thick approved Laminate, including NBTW beading all around. Shutter to be finish in Approved Melamine polish , Including Vision panel as per drawing.
Hardware
Heavy duty floor Spring by Hafle or Dorma, Dead lock with suitable cover plate, including 300 mm wide SS kick plate from both side of shutter, 1 set of handle as approved by Architect
a | D-6 , | 1 |  |  | 1
PAINTING WORK
6.1 | Duco Paint to Walls Partition | smt
Sanding and preparing surface for receiving paint, Final coats of Duco paint. Complete as per manufacturer s specifications
6.2 | Concrete texture finish Coating | smt
Paint By Evolve-Mumbai ( basic cost of Pait Rs 250 sqft )
6.3 | Artificial Silver Gold leafing on ceiling | smt
Surface to be ready with putty and primer, to receive metal leaf, Metal leafing to be applied over surface by skilled labour, Metal leaf to be installed as per approved sample, Stain coating to be applied as per approved sample, 2 coats of protective coating in matt glossy finish, as instructed by Architect
6.4 | Luster Painting to walls | smt
Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of luster paint. Complete as per manufacturer s specifications
| Service corridor wall | 1 | 8.58 | 2.335 | 20.0343
|  | 1 | 8.335 | 2.335 | 19.4622
| door area deduction | -1 | 1.07 | 2 | 17.3222
|  | 1 | 0.2 | 1.07 | 0.214
|  | 0 | 1.2 | 0.33 | 0
|  | 2 | 0.15 | 2 | 0.6
|  | 1 | -1 | 1 | -1
| Elecrical panel room | 2 | 10.885 | 2.425 | 52.7922
| door area deduction | -1 | 0.885 | 2.08 | 50.9514
| Left side entry wall | 2 | 1.8 | 2.14 | 7.704
|  | 2 | 2.9 | 2 | 11.6
| door area deduction | -1 | 0.885 | 2.478 | 9.407
189.0874
6.5 | Painting to ceiling in acrylic emulsion paint | smt
Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base. Two coats of putty ,Three coats of acrylic emulsion paint, Complete as per manufacturer s specifications
| Ceiling | 1 | 1.15 | 1.56 | 1.794
|  | 1 |  |  | 0
| Ceiling near elevator (A) | 1 | 6.34 | 2.02 | 12.8068
|  | 1 | 0.48 | 2.03 | 0.9744
|  | 1 |  |  | 0
| Ceiling near elevator | 1 | 3.05 | 3.09 | 9.4245
| ceiling above reception counter | 1 | 3.55 | 1.72 | 6.106
|  | 1 | 5.26 | 3.47 | 18.2522
49.3579
6.6 | Black matt paint to walls, beams structural frame and ceiling above false ceiling | smt
Sanding and preparing surface for receiving paint, Oil based, black matt paint to be applied in two coats, Clean surface before applying
FINE DINING & LIVE KITCHEN
I | CIVIL WORK - fine dine live kitchen
1.1a | 18 mm thick Italian Marble flooring in Various Marble shade and in strip form Pattern - for Dining | Smt
Marble strip size up to 50 to 225 mm wide in various length, Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides , with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft
a | As per AutoCAD | 1 |  |  | 104.0446
104.0446
1.1b | Kotah tile Flooring for Live Kitchen | smt
P F of 19mm thick Kota Stone flooring (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, Kotah to be laid with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for kitchen service area.
a | Live kitchen flooring | 1 | 4.4 | 2.67 | 11.748
b | Electric room flooring | 1 | 1.3 | 2.85 | 3.705
c | Janitor room flooring | 1 | 1.45 | 1.2 | 1.74
17.193
1.1c | 18 mm thick Italian Marble flooring black and white tile form- for Dining | Smt
Marble tile size up to 600 mm x 600 mm- Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides, with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 550 sft
| FL-03-04 black and white marble flooring(as per AutoCAD) (500 x 500x 78x 2) | 1 |  |  | 39
1.2 | Joint less ceramic tiles cladding ( behind Buffet counter ) | smt
Cladding shall comprise of ceramic tile of 300 mm x 300 mm, Tiles to be fixed in ordinary Portland cement only, Tiles to be put with Spacer required with Leticrete grout in joints in plumb, Joints to be filled with matching grout.(Basic cost of ceramic tiles at Rs.30 sft) make Johnson Somany Kajaria Nitco
1.3 | Vitrified tile For Live Kitchen | smt
Clean existing wall surface before fixing tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, Tiles to be put with Spacer required with Leticrete grout in joints in plumb, Joints to be filled with matching grout. preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.150 sft without tax
a | Wall 1 | 1 | 4.4 | 2.7 | 11.88
b | wall 2 | 1 | 2.67 | 2.7 | 7.209
c | wall 3 | 1 | 4.4 | 2.7 | 11.88
d | wall 4 | 1 | 2.67 | 2.7 | 7.209
e | Less door (-) | -1 | 0.9 | 2.21 | -1.989
36.189
1.4 | Italian Marble Wall Cladding | smt
Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to fire rated plywood panelling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax)
a | Passage beside live kitchen 1 | 1 | 3.136 | 3.4 | 10.6624
b | Less entry | -1 | 2.02 | 3.4 | -6.868
c | Passage beside live kitchen 2 | 1 | 2.9 | 3.4 | 9.86
d | Passage beside live kitchen 3 | 1 | 2.026 | 3.4 | 6.8884
e | Less entry (-) | -1 | 1.3 | 2.246 | -2.9198
f | Live kitchen counter right side wall | 1 | 2.18 | 3.4 | 7.412
25.035
1.5 | Italian Marble Finish Band | rmt
Size up to 400 Mm high, Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to Fire rated plywood panelling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax)
a | Live kitchen counter top,sides,base | 1 | 10.6 |  | 10.6
b | Counter front facia | 1 | 4.3 |  | 4.3
14.9
1.6 | Marble Portal Architrave ( 50 mm wide 400 mm deep ) | rmt
All around in C profile Pasted over existing ply surface with epoxy adhesive brass pins, Ply surface shall be cleaned before installing marble, At least 18mm thk marble to be fixed, Marble shall be cut as per size laid with tight hairline joints, Edge of marble shall be polished before installation, Joints to be filled with Tim-X or equivalent joint filler, Special care to be taken to fix marble on horizontal surface. Shall rest over ply at one end and vertical marble on the other, The vertical marble over 50 mm shall be fixed using brass pins . including Approved sealer to be applied on all sides (Basic cost of Marble at Rs.450 sft )
a | Passage entry vertical | 1 | 3.136 |  | 3.136
b | Passage entry door top | 1 | 2.246 |  | 2.246
5.382
1.7 | Marble Skirting | rmt
up to 150 mm high Skirting with 18 MM thick Italian Marble including Edge Moulding, etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, All visible edges of Marble shall be mirror polished, including Approved sealer to be applied on all sides ( Basic cost of marble Rs 450 sft )
a | Buffet counter 1 | 1 | 8.8 |  | 8.8
b | Buffet counter 2 | 1 | 1.7 |  | 1.7
c | Live kitchen counter skirting | 1 | 4.3 |  | 4.3
14.8
II | FRENCH PLASTER WORK
2.1 | Fire line Gypsum board ceiling | Smt
All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobin Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cut-outs for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceiling height is 4300 mm )
2.4 | POP plaster punning | Smt
Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bull marks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work
Passage Lift area
a | Electric room and janitor room divider wall | 2 | 1.4 | 2.6 | 7.28
b | Electric room panel backside wall (B) | 1 | 2.85 | 2.6 | 7.41
c | Electric room left side wall "C" | 1 | 1.4 | 2.6 | 3.64
d | Electric entry wall from inside "D" | 1 | 1.4 | 2.6 | 3.64
e | Less door | -1 | 1.45 | 2.05 | -2.9725
f | Fire panel backside and right-side wall "E" | 1 | 1.9 | 2.119 | 4.0261
| Buffet counter area | 1 | 3.8 | 3.8 | 14.44
|  | 1 | 2.4 | 3.8 | 9.12
46.5836
III | CARPENTRY WORK
3.1 | Aluminium framework for panelling | Smt
50mm x 25 mm, 16 SWG aluminium framework at 600 mm c c fixed to wall, 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable packing to be provided behind framework for correct alignment,
3.2 | Veneer finish Panelling in batten form - Vertical and Horizontal | Smt
Providing and fixing 150 mm wide batten form, Using 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, pressed over 12 mm thick backing Fire rated plywood including matching wood beading as per approved design, with 12 mm x 12mm finish groove as per design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be Finished in Approved water base PU polish
a | Buffet counter 1 | 1 | 3.83 | 2.1 | 8.043
b | Buffet counter 2 | 1 | 3.1 | 2.1 | 6.51
c | Taper column | 4 | 1.45 | 3.322 | 19.2676
33.8206
3.3 | Free standing low height Partition in Curved Profile- 1350 mm High | Smt
50mm x 50 mm, MS Box framework at 600 mm c c fixed to Floor slab with adequate anchor bolts and plates, 25 mm x 25mm, 4 mm thick MS angle to be used for assembling Partition framework, with proper welding , Framework to be fixed to Floor in perfect plum, line and level, Including anti rust paint, Frame to be covered with 6+6 mm thick ply for Curved Profile , Ply to be covered with 4 mm thick veneer, 232 mm high x 38 mm thick Veneer finish Fins to be fixed on veneer surface with 50 mm gap, including 50 mm high SS bronze satin finish Band in L C shape as per drawings, Veneer to be Finished in Approved Melamine Polish, including 18 mm thick 125 mm wide Italian Marble top band to be fixed on the Ply with edge moulding and polishing. Provision to be made for fixing partition bracket light (Basic cost of veneer at Rs.125 sft) (Basic cost of Marble at Rs. 550 sft)
a | curved partition buffet counter | 2 | 1.06 | 1.35 | 2.862
b | Corridor side | 2 | 1.19 | 1.35 | 3.213
c | Phase 1 side | 4 | 1.19 | 1.35 | 6.426
12.501
3.4 | Free standing low height Partition in straight Profile-1350 mm high | Smt
50mm x 50 mm, MS Box framework at 600 mm c c fixed to Floor slab with adequate anchor bolts and plates, 25 mm x 25mm, 4 mm thick MS angle to be used for assembling Partition framework, with proper welding , Framework to be fixed to Floor in perfect plum, line and level, Including anti rust paint, Frame to be covered with 12 mm thick Fire rated plywood , Ply to be covered with 4 mm thick veneer, 232 mm high x 38 mm thick Veneer finish Fins to be fixed on veneer surface with 50 mm gap, including 50 mm high SS bronze satin finish Band in L C shape as per drawings, Veneer to be Finished in Approved Melamine Polish, including 18 mm thick 125 mm wide Italian Marble top band to be fixed on the Ply with edge moulding and polishing. Provision to be made for fixing partition bracket light (Basic cost of veneer at Rs.125 sft) (Basic cost of Marble at Rs. 550 sft)
a | Partition 1 Near Live kitchen | 1 | 1.8 |  | 1.8
b | Partition 2 Buffet counter | 1 | 6.1 |  | 6.1
c | Partition 3 Corridor side | 1 | 7.75 |  | 7.75
d | Partition 4 Phase 1 side | 1 | 5.65 |  | 5.65
21.3
3.5 | Fluted glass screen with SS Flat trim- 300 mm high | Rmt
10 mm thick Fluted Glass panel with 6 mm thick SS flat band around the glass , SS in bronze satin finish, Fixed to marble top Trim , as shown in drawing, including fluted glass film
a | Above curved partition | 1 | 5.4 |  | 5.4
3.6 | Buffet serving counter - in U shape | Nos
Size 11500mm length x 800mm depth x 950mm ht.
As per drawing, Serving counter structure constructed out of 18 mm thk Fire rated plywood, At least 18 mm thk approved Marble fixed to top with fascia in profile shown in drawing - including Mirror polish. Marble to be tightly placed together and shall have mitre joints on edges including moulding as approved by Architect. All joints to be filled with matching colour TIM-X or equivalent grout filler. Ventilation space to be created within carcass as per drawing and all internal non visible surfaces shall be in Black matt paint. Carcass to be covered with 12mm thk DuPont Corian fluted panel on all exposed surfaces including Led strip light provision,150 mm high skirting boxing to be made in 18 mm thick ply covered with Italian marble. Ventilation space fascia to be covered with 8 mm thick SS jali. SS jali in Bronze Satin finish, as per approved design. Including all cut-outs for electrical points, induction plates and temperature devices. (Basic cost of Marble at Rs. 450 sft ) (Basic cost of Corian at Rs. 850 sft )
a |  | 1 |  |  | 1
3.7 | Coffee Station
| Size 1800mm length x 750mm depth x 950mm ht. | nos
As per drawing, counter structure constructed out of 18 mm thk Fire rated plywood, At least 18 mm thk approved marble fixed to TOP with 50 mm high fascia, At least 18 mm thk approved marble fixed to skirting up to 200 mm high, Marble pieces to be tightly placed together and shall have mitre joints on edges, All joints to be filled with matching colour TIM-X or equivalent joint filler, 30 mm thick shelf to made, shelf to be covered with 4 mm thk veneer from top bottom with 0.40 mm thk wooden face pressed on front side, All Internal Surface to be covered with 4 mm thick veneer, Veneer Wood to be Finished in Approved Melamine Polish, 200 mm high skirting boxing to be made in 18 mm thick marine ply covered with marble, with openable panel, Provision to be made in counter for water inlet point drain outlet, Including all cut-outs for electrical points. (Basic cost of veneer at Rs.125sft) (Basic cost of Marble at Rs. 450 sft)
a | coffee station in buffet area | 1 |  |  | 1
3.8 | SS Screen in Satin Bronze finish | smt
Overall size- 4500 mm wide x 1000 mm height, 304 grade SS screen to be made out of 3 mm thick Sheet ( cris-cross pattern ), SS frame in Satin Bronze finish as approved by Architect, frame fixed to Wall and above ceiling Bulkhead,
a | Live kitchen bulkhead Jali | 1 | 4.4 | 1.05 | 4.62
3.9 | TV FIDS surround frame | nos
Size up to ( 1200 mm x 1350 mm ), Using 3 4 thick ply carcass as TV surround, like a picture frame including 50 to 75 mm wide surround finished in 4 mm thick veneer to receive polycot paint, Rear portion of TV surround covered with 1 mm thick laminate, To be fixed on wall panelling with adequate supports
a | TV FIDS in buffet counter | 1 |  |  | 1
3.10 | 18 mm thick Glass Shelf | nos
size - 1500MMX350MM- using 18 mm thick toughen glass shelf including SS Patch fittings ( Haffle or Dorma )
a | Glass display live kitchen area
3.11 | Glass Display BOX with SS pipe in Satin Bronze - 300 mm ht. | nos
size - 300MM X4500MM- Made of Box frame using 25 x25 x2.5 mm thick SS box pipe in Satin bronze finish, and frame to be covered with 12 mm thick toughen Glass as per detail drawing
a | Glass display live kitchen area Upper side | 1 |  |  | 1
3.12 | Glass Display BOX with SS pipe in Satin Bronze - 200 mm ht. | nos
size - 200MM X4500MM- Made of Box frame using 25 x25 x2.5 mm thick SS box pipe in Satin bronze finish, and frame to be covered with 12 mm thick toughen Glass as per detail drawing
a | Glass display live kitchen area bottom side | 1 |  |  | 1
3.13 | Service door-Veneer laminate finish including top fixed panel | No
Size 900mm x 2250mm
Door Frame
Overall finish size 200mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick marine ply as rough ground,, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk marine ply 4 mm thick Approved Veneer, Rebate to be separately put in wood, Wood to be treated with anti-termite medicine, Frame to be finished in Approved water base PU polish
Shutter
Overall size 800 mm wide x 2250 mm ht. x 1 leaf, up to 40 mm thk. Using 35 mm thick readymade fireproof shutter covered with 4 mm thick approved veneer from Lounge side and other side 1 mm thick approved Laminate, (basic cost of veneer up to Rs. 125 sft) (basic cost of laminate Rs 1600 sheet)
Polish
Frame entire door to be to be Finished in Approved water base PU polish
Hardware
125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, Dead lock with suitable cover plate , and Magnetic latch, 1 set of handle as approved by architect
a | Live kitchen door D-5 | 1 |  |  | 1
3.14 | Wooden finish Capital for Column | Rmt
size up to 300 mm Deep- Providing and fixing 75 mm thick Veneer finish Capital including adequate MS frame and 12 mm thick Fire rated plywood, ply to be covered with 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, including matching wood beading as per approved design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be Finished in Approved water base PU polish
| Wooden round finish column | 2 | 3.4 |  | 6.8
3.15 | Bulk Head in Profile- In Flat Water cut Paint finish | rmt
As per drawing -Size up to 600 mm wide x 1850 mm high, Using 50mm x 36 mm, 16 SWG aluminium framework at 600 mm c c Fixed on existing Structural Framework, Frame to be covered with 18 mm thick marine ply, For Curve surface use 6+6+6 mm flexi ply, 12 mm thick HDF to be fixed on Ply, For Curve surface use 6+6 mm flexi HDF, All joints shall be filled with suitable fillers and reinforcement tape, 50 mm wide x 25 mm thick HDF fluting to be fixed on HDF surface with 25 mm gap, Base and HDF moulding surface shall be finished n Water cut enamel Paint finish, as approved by Architect, include 450 mm wide x 100 mm thick veneer finish Band at bottom, Veneer to be finished in Approved Melamine polish . Including 2 layers of light Pelmet with Led strip light provision. (Basic cost of veneer up to Rs. 125 -sft )
| Bulkhead main Live kitchen above |  |  |  | 29.35
3.16 | Veneer finish Ceiling | Sqmt
As per drawing - Using 50mm x 36 mm, 16 SWG aluminium framework at 600 mm c c Fixed on existing Structural Framework, Frame to be covered with 18 mm thick marine ply, ply to be covered with 4 mm thick approved Veneer, Veneer to be Finished in Approved water base PU polish . (Basic cost of veneer up to Rs. 125 -sft )
a | Live kitchen counter ceiling | 1 | 4.7 | 1.9 | 8.93
3.17 | Corian finish fluted panelling | rmt
Providing and fixing up to 50 mm wide x 600 umm high Corian batten form, Using 12 mm thk approved Corian sheet , pressed over 12 mm thick backing Fire rated plywood as per approved design, with 12 mm x 6 mm finish groove as per design, Pressing shall be free of defects, Basic cost of Corian at Rs.900 sft without tax
| live kitchen counter facia | 1 | 4.55 |  | 4.55
3.18 | Brick Cladding on Existing taper column | smt
Clean existing wall Ply surface before fixing brick tile cladding Before starting, carefully read the suppliers laying plan and instructions. Decorative Brick tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.120 sft without tax
| Cladding beside passage (Relax zone) | 1 | 3.7 | 3.4 | 12.58
| Taper column 2 | 2 | 2.6 | 3.322 | 17.2744
| Less (-) | -2 | 1.45 | 3.322 | -9.6338
| Taper column 2 | 2 | 2 | 3.322 | 13.288
| Less (-) | -2 | 1.45 | 3.322 | -9.6338
23.8748
3.19 | Built In seating In Profile- for Dining Area ( Part of Phase-1 )
Partition in Curved Profile
50mm x 50 mm, MS Box framework at 600 mm c c fixed to Floor slab with adequate anchor bolts and plates, 25 mm x 25mm, 4 mm thick MS angle to be used for assembling Partition framework, with proper welding , Framework to be fixed to Floor in perfect plum, line and level, Including anti rust paint, Frame to be covered with 12 mm thick plywood and 6+6 mm thick ply for Curved Profile , Ply to be covered with 4 mm thick veneer, 232 mm high x 38 mm thick Veneer finish Fins to be fixed on veneer surface with 50 mm gap, including 50 mm high SS bronze satin finish Band in L C shape as per drawings, Veneer to be Finished in Approved Melamine Polish, including 18 mm thick 125 mm wide Italian Marble top band to be fixed on the Ply with edge moulding and polishing. Provision to be made for fixing partition bracket light (Basic cost of veneer at Rs.125 sft) (Basic cost of Marble at Rs. 2000 sft)
Built-in seating -Seat
up to 100 mm thk foam rubber seat pasted to 18 mm thk ply base , 25 mm thk., 32 density PU foam to cover rubber seat, PU foam to be covered with 6 mm thk. sheet before finishing seat in white cloth, Final finished in approved fabric leatherite (Basic cost of fabric at Rs.2500 rmt)
Built-in seating- Back
Back rest to be fixed to rear partition .Up to 25mm thk. Foam rubber pasted to back rest, in Fluted profile, 25 mm thk., 32 density PU foam to cover rubber sheet, PU foam to be covered with 6 mm thk sheet before finishing in white cloth, Final finished in approved fabric leatherite (Basic cost of fabric at Rs.2500 rmt)
A | Fixed Seating Sofa - Size - 9650 mm length x860 mm deep x 1200 mm height | nos
B | Fixed Seating Sofa - Size -7200 mm length x860 mm deep x 1200 mm height | nos
| Seating sofa 1(9650) | 1 |  |  | 1
| Seating sofa 2(7200) | 2 |  |  | 2
3.20 | Standy Tall Table - In profile | Nos
Size 65 mm thick 1050mm length x 450 deep x1140 mm ht.
Using 35mmx25mm Aluminium frame, 400x400 mm c c both ways, Frame to be covered with 8 mm thick ply, Top ply including 200 mm drop to be covered with 12 mm thick Corian, Bottom ply to be covered with 1 mm thick laminate with balance vertical ply to be covered with 4 mm thick veneer with additional 12 mm ply backing to match the thickness, Provision to be made to pass conduit for electrical points, including boxing to receive pop up box and SS finish Foot rail, Veneer to be Finished in Approved Melamine Polish , including 50 mm wide 6 mm thick 304 grade SS Base in Satin Bronze finish (Basic cost veneer Rs.125 sft) (Basic cost of Corian Rs.850 sft)
|  | 8 |  |  | 8
IV | PAINTING WORK
4.1 | Luster Painting to walls | smt
Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of luster paint. Complete as per manufacturer s specifications
4.2 | Painting to ceiling in acrylic emulsion paint | smt
Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base. Two coats of putty ,Three coats of acrylic emulsion paint, Complete as per manufacturer s specifications
4.3 | Black matt paint to walls, beams structural frame and ceiling above false ceiling | smt
Sanding and preparing surface for receiving paint, Oil based, black matt paint to be applied in two coats, Clean surface before applying
TEA LOUNGE
1.1 | 10 mm thick Terrazzo Flooring in Pattern | Smt
Supply and application of 10mm thick Epoxy Resin Terrazzo flooring system (12 mm laid grinded to 10 mm) Flexural strength = 25MPa as per ASTM D790,Tensile strength = 14 MPa as per ASTM D638. The product must have elongation = 5%, when tested as per ASTM D638. Hardness of the floor must be = 75, when tested as per Shore D hardness test. Co-efficient of linear thermal expansion of the product will be approximately 13.3x10-6. This product should have flammability of not more than 0.025inch minute when tested as per ASTM D 635. IGBC certified product. Typical properties of the resin needs to be achieved in laboratory tests at 50% Relative Humidity. Fire Resistance BS476-7 Spread of Flame Class 2Slip Resistance TRRL Pendulum Slip Test Dry > 40 low slip potential. Temperature Resistance Tolerant up to 60 C .Water Permeability Nil – Karsten Test(Impermeable) Abrasion Resistance Taber Abrader - 50 mg loss per 1000 cycles(1kg load using CS17 wheels). Compressive Strength > 55 N mm2 (BS6319), Bond Strength Greater than cohesive strength of 25 N mm2 concrete. >1.5 MPa. Toxicity (when cured) Taint Free to sensitive foodstuffs. Epoxy terrazzo layer to be applied over Epoxy high build primer and needs to be properly finished, grinded and polished with suitable transparent abrasion resistant material. The complete system of Epoxy Resin Terrazzo flooring needs to be executed by an authorized applicator of the manufacturer and as per the approved method statement of the manufacturer. Providing and application of Divider termination Trim of 2mm- 2.5mm thick L SS , Providing and application of Momex Joint , Providing and application of PU Sealant at terminations
a | As per AutoCAD | 1 |  |  | 105.073
COUNTER AND LEDGES
1.2 | Tea Bar counter in Curved Profile | nos
Size 9000mm length x 650 mm depth x 1100mm ht.
Apron partition
38 mm x 38 Aluminium Box framework made up thickness up to 100 mm wide, frame to be covered with 6+6 mm thick flexi Fire rated plywood on both sides for curved profile, At least 12 mm thk Corean fixed to apron In Approved design pattern and in profile, Corean to be tightly placed together and shall have seamless joints on edges, Bartender side of Apron partition shall have 1.5 mm thk approved laminate below counter top, Including 200 mm high 16G 304 grade SS satin Bronze finish Skirting . Including provision for Food Display unit (Basic cost of Corean at Rs.800 sft)
Preparation counter
Size up to 600 mm wide Preparation counter structure constructed out of 18 mm thk Fire rated plywood In laminate finish, 18 mm thick Veneer finish Shutter Including matching wood beading on all exposed plywood edges, Veneer Beading to be finish in approved Duco paint, 16 mm thk Terrazzo counter tops with 50 mm thk top edge on all sides, (Basic cost of Terrazzo at Rs.750 sft) (Basic cost Veneer at Rs.100 sft)
Serving counter top in profile
Up to 350 mm wide Serving Counter top,75 mm facia Including provision for Led strip profile light, comprising of 38x38 mm Aluminium framework covered with Fire rated plywood , At least 16 mm thk approved Terrazzo stone fixed to on counter Ply top, Bottom ply of serving top shall have 1.5 mm thk approved laminate on bottom side, Exclude electrical point wiring light source within counter top, (Basic cost of Terrazzo at Rs.750 sft)
| Tea bar counter | 1 |  |  | 1
1.3 | Terrazzo finish Bar Back unit
| Size 6500mm length x 600mm depth x 900 mm ht. | nos
Back unit structure constructed out of 18 mm thk Fire rated plywood with vertical support in the centre, Plywood to be covered with 18 mm thick Terrazzo top and back wall, with 50 mm thick Terrazzo Facia, with mitre joints , Marble pieces to be tightly placed together and shall have mitre joints on edges, All joints to be filled with matching colour joint filler, All edges of stone to be polished. including 18 mm thick Duco paint finish Shutter (Basic cost of Terrazzo at Rs.750 sft)
|  | 1 |  |  | 1
II | CARPENTRY WORK
2.1 | Low height Curved Partition ( 1500 mm high ) Attached to Built in Seating | rmt
As per drawing, overall thickness up to 100 mm, using 50mm x 50 mm MS box framework, 6+6 mm thk Flexi Fire rated plywood fixed to framework from all side, Ply to be covered with 4 mm thick approved veneer finish with Approved water base PU polish from outer side ( corridor side ), and approved Duco paint finish from in side ( tea lounge side ), 10 mm thick x 250 high Curved rib Glass to be fix in the partition including 6 mm thick 304 grade SS bronze satin finish Top trim including 50 mm wide vertical support as shown in drawing, all veneer to be Finished in Approved water base PU polish, including provision for pole light (Basic cost of veneer at Rs.150 sft)
a | Seating partition 1 | 1 | 5 |  | 5
b | Seating partition 2 | 1 | 9.2 |  | 9.2
14.2
2.2 | Low height Curved Partition ( 1500 mm high ) with moulding panel behind counter | rmt
As per drawing, overall thickness up to 100 mm, using 50mm x 50 mm MS box framework, 6+6 mm thk Flexi Fire rated plywood fixed to framework from all side, Ply to be covered with 4 mm thick approved veneer finish with Approved water base PU polish from outer side ( corridor side ), and approved Duco paint finish from in side including half round moulding panel ( tea lounge side ), 10 mm thick x 250 high Curved rib Glass to be fix in the partition including 6 mm thick 304 grade SS bronze satin finish Top trim including 50 mm wide vertical support as shown in drawing, all veneer to be Finished in Approved water base PU polish, including provision for pole light (Basic cost of veneer at Rs.150 sft)
a | 1 | 1 | 3.95 |  | 3.95
b | 2 | 1 | 4.35 |  | 4.35
8.3
2.3 | Low height Curved Partition ( 600 mm high ) for Planter | rmt
As per drawing, overall thickness up to 100 mm, using 50mm x 50 mm MS box framework, 6+6 mm thk Flexi Fire rated plywood fixed to framework from all side, Ply to be covered with 4 mm thick approved veneer finish with Approved water base PU polish from outer side ( corridor side ), and approved Marble cladding from in side , including 6 mm thick 304 grade SS bronze satin finish Top trim as shown in drawing, all veneer to be Finished in Approved water base PU polish, (Basic cost of veneer at Rs.150 sft) (Basic cost of marble at Rs.450 sft)
2.4 | SS Foot Rail | rmt
up to 200 mm high -Providing and fixing in position 304 grade S.S Satin Bronze finish foot rail of 38mm diameter with horizontal vertical members, Grouting in concrete, etc. complete, as specified and as directed by Architect
2.5 | Built-in seating -Seat | rmt
Carcus to be made out of 38mm x 38 mm Aluminium framework and 18 mm thk plywood , up to 100 mm thk foam rubber seat pasted to 18 mm thk ply base , 25 mm thk., 32 density PU foam to cover rubber seat, PU foam to be covered with 6 mm thk. sheet before finishing seat in white cloth, Final fabric leather shall be nailed on bottom side of plywood base, Including recessed SS Skirting ,(Basic cost of fabric at Rs.2500 rmt)
a | 1 | 1 | 5 |  | 5
b | 2 | 1 | 9.2 |  | 9.2
14.2
2.6 | Tea Garden Tree with Roof in Oval Profile | rmt
Size 6300mm dia x 1800mm wide x 3600mm ht.
Main Tree Base
Using 50 mm x 50 MS Box framework , frame to be covered with 6+6 mm thick flexi HDF for curved profile, ply to be covered with 50 mm wide x 150 mm deep Vertical fins in profile as shown in drawings, 50 mm wide horizontal band to be provide at every 500 mm as shown in drawing , All expose surface of Metal and HDF to be finish in Approve Duco paint, Including provision for Electrical wire manger and light and light handing system
Roof
Roof to be made Using 50 mm x 50 MS Box framework as per drawing, frame all side to be covered with 6 mm thick HDF in profile, use 10 mm thick rib glass roof panel as shown in drawing , All expose surface of Metal and HDF to be finish in Approve Duco paint,
Capital ring
On existing roof frame Up to 300 mm high Roof top band to be made using 6mm thick HDF, HDF to be covered with Bronze finish SS as approved by architect
Civil Interior work for sports relax lounge
|  | 1 |  |  | 1
SPORTS & RELAX LOUNGE
1.1 | 18 mm thick Italian Marble flooring | Smt
Marble strip size up to 50 to 225 mm wide in various length, Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides , with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft
| As per AutoCAD Bar counter front | 1 |  |  | 26.2393
1.2 | 18 mm thick Italian Marble flooring in Various Marble shade and in Pattern - for Sports Bar | Smt
Marble strip size up to 50 to 225 mm wide in various length, Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including Approved sealer to be applied on all sides, with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft
| herringbone pattern (As per AutoCAD) Fl-07 Fl-08 |  |  |  | 153.3542
1.3 | Vitrified tile Flooring for Bar Store room | smt
SUPPLYING AND LAYING VITRIFIED FLOOR TILES OF 600 X 600 MM SIZE OF FIRST QUALITY,CONFIRMING TO IS 13006 PL-LBE OF RAK CERAMICS EURO NITCO KAJARIA OR EQUIVALENT,DESIGN AND SHADE AS APPROVED, FIXED OVER 30 MM AVERAGE THICK BASE OF CEMENT MARTOR 1 4 (1 CEMENT 4 COARSE SAND)LAID WITH CEMENT SLURRY,INCLUDING PREPAIRING THE BASE,FILLING WITH WHITE CEMENT PASTE OF APPROVED MATCHING COLOUR AND SHADE ETC.CLEANING ALL COMPLETE AS PER DIRECTION OF ENGINEER-IN- CHARGE. basic cost of tile Rs.150 sft without tax
Kotah flooring of bar storage is added in overall.
| Bar flooring As per Auto cad | 1 |  |  | 17.86
1.4 | Joint less ceramic tiles cladding ( behind Display screen and store room) | smt
Cladding shall comprise of ceramic tile of 300 mm x 600 mm, Tiles to be fixed in ordinary Portland cement only, Tiles to be put with Spacer required with Leticrete grout in joints , in plumb, Joints to be filled with matching grout . (Basic cost of ceramic tiles at Rs.60 sft) make Johnson Somany Kajaria Nitco
1.5 | Vitrified tile Cladding for Inside Bar wall | smt
Cladding shall comprise of vitrified tile of 600 mm x 600 mm, Tiles to be fixed in ordinary Portland cement only, Tiles to be put with Spacer required with Leticrete grout in joints in plumb, Joints to be filled with matching grout . (Basic cost of vitrified tiles at Rs.60 sft) make Johnson Somany Kajaria Nitco
| Tile on curved wall from inside | 1 | 10.75 | 0.98 | 10.535
1.6 | Italian Marble Wall Cladding | smt
Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to Fire rated plywood panelling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, including Approved sealer to be applied on all sides, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax)
COUNTER AND LEDGES
1.7 | Sports Bar counter in Profile | nos
Size 11500mm length x 1050mm depth x 1150mm ht.
Apron partition
50 mm x 50 Aluminium Box framework made up thickness up to 150 mm wide, frame to be covered with 18 mm thk Fire rated plywood on both sides on straight surfaces including 6+6 mm thick flexi FRP ply for curved profile,18 mm thk plywood boxing fixed over partition with FRP plywood frame grid at regular intervals, At least 18 mm thk Fluted Marble fixed to apron In Approved design pattern and in profile, Marble to be tightly placed together and shall have seamless joints on edges, including sealer coat of all side, Marble joint should not be visible, Bartender side of Apron partition shall have 12 mm thick Corian fixed above preparation counter and 1.5 mm thk approved laminate below counter top, Including 200 mm high 16G 304 grade SS satin Bronze finish Skirting (Basic cost of solid surface (Corian) at Rs.850 sft) (Basic cost of Marble at Rs.1000 Sft)
Preparation counter
Size up to 650 mm wide Preparation counter structure constructed out of 18 mm thk Fire rated plywood In laminate finish, Include matching wood beading on all exposed plywood edges, Beading to be polished and coated with 1 coat sealer and 2 coats of PU finish in approved matt glossy ratio, 12 mm thk Corian counter tops with 32 mm thk top edge on all sides, (Basic cost of solid surface (Corian) at Rs.850 sft) (Basic cost of laminate at Rs.1500 sheet)
Serving counter top in profile
Up to 450 mm wide Serving Counter top, 100 mm facia Including provision for Led strip light, comprising of 1st quality CP teakwood framework with Fire rated plywood on bottom side, At least 18 mm thk approved Onyx stone fixed to on counter Ply top, Bottom ply of serving top shall have 1.5 mm thk approved laminate on bottom side, Include 100 mm x 10 mm thk SS Satin Bronze edges Facia fixed to serving top edges on both sides (with one side openable for maintaining Led strip Light ), with suitable adhesive, Exclude electrical point wiring light source within counter top, (Basic cost of Onyx Rs 1500 sft )
| Bar counter (everything included) | 1 |  |  | 1
1.8 | Marble finish Bar Back unit
| Size 3500mm length x 750mm depth x 975 mm ht. | nos
Back unit structure constructed out of 18 mm thk Fire rated plywood with vertical support in the centre, Plywood to be covered with 18 mm thick Marble top and back wall, with 50 mm thick marble Facia, with mitre joints , Marble pieces to be tightly placed together and shall have mitre joints on edges, All joints to be filled with matching colour TIM-X or equivalent joint filler, All edges of stone to be mirror edge polished. including 75x75 mm SS Satin Bronz finish Architrave as per detail drawing, Side panel to be finish with 4 mm thick veneer with 12 mm thick back ply Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be Finished in Approved water base PU Polish, 8 mm thick tinted mirror panelling with 12 mm thick FRP back ply and including 12 mm thick Glass shelve as per design including 1 mm thick laminate finish panelling behind TV back (Basic cost of veneer at Rs.150 sft) (Basic cost of marble Rs 450 sft )
|  | 1 |  |  | 1
II | CARPENTRY WORK
2.1 | Aluminium frame work ( for Panelling Cladding ) | Smt
50mm x 36 mm, 16 SWG aluminium framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plumb, line and level, Suitable bracket to be provided behind framework for correct alignment,
REFER DRAWING-00B01-TFS-DOM02-ID-07-03 11 12
| Bar storage and bar area divider wall i.e. behind sports bar. | 1 | 6.26 | 3 | 18.78
| less door | -1 | 0.8 | 2.25 | -1.8
| Bulk head framing | 1 | 12.06 | 1.8 | 21.708
38.688
2.2 | Ply Panelling
providing and fixing Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at centre of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material
A | 12 mm thk Fire rated plywood | Smt
a | A Left side Vertical | 1 | 1.37 | 3.7 | 5.069
b | B Bar back counter left side vertical | 1 | 0.65 | 3.7 | 2.405
c | C Screen wall | 1 | 3.35 | 3.7 | 12.395
d | D Bar back counter Right side vertical | 1 | 0.65 | 3.7 | 2.405
e | E Store room door side | 1 | 1.35 | 3.7 | 4.995
f | F Bulkhead ceiling bottom | 1 |  |  | 14.03
41.299
B | 15 mm thk Fire rated plywood | Smt
C | 18 mm thk Fire rated plywood | Smt
D | 6 mm thk Flexi Fire rated plywood | Smt
a | Bulkhead of sports bar | 2 | 12.06 | 0.9 | 21.708
2.3 | Veneer skin for Straight curved surfaces | Smt
Using 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, pressed over backing plywood including matching wood beading as per approved design, with 3 mm x 3mm finish groove as per design including on column surface, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be Finished in Approved water base PU polish
(Basic cost of veneer up to Rs. 150 -sft )
0
2.4 | Wooden finish Capital for Column | Rmt
size up to 300 mm Deep- Providing and fixing 75 mm thick Veneer finish Capital including adequate MS frame and 12 mm thick Fire rated plywood, ply to be covered with 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, including matching wood beading as per approved design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be finished in Approved water base PU polish
2.5 | Veneer finish Panelling in batten form - Vertical and Horizontal | Smt
Providing and fixing 50 to 100 mm wide batten form, Using 4 mm thk approved veneer sheet with 0.4 mm thick wooden face, pressed over 12 mm thick backing fire rated plywood including matching wood beading as per approved design, with 12 mm x 12mm finish groove as per design, Figure of veneer to be matched as per design, Pressing shall be free of defects, Veneer to be finished in Approved water base PU polish
| Sports bar backside | 2 | 1.37 | 3.7 | 10.138
| Bulkhead front side | 1 | 12.06 | 0.9 | 10.854
| Taper column | 4 | 1.45 | 3.322 | 19.2676
40.2596
2.6 | Low height Curved Partition ( 1100 mm high ) | rmt
As per drawing, 50mm x 50 mm MS framework, 6+6 mm thk Flexi Fire rated plywood fixed to Aluminium framework from all side, Ply to be covered with 4 mm thick veneer finish with Approved water base PU polish, 10 mm thick x 250 high Curved rib Glass to be fix in the partition including 6 mm thick 304 grade SS bronze satin finish Top trim including 50 mm wide vertical support, veneer to be Finished in Approved water base PU polish, (Basic cost of veneer at Rs.125 sft)
| Near Sport bar taper column | 1 | 10 |  | 10
| FL-07 Between FL-08 | 1 | 9.52 |  | 9.52
| Relax zone Area | 1 | 5.6 |  | 5.6
| Dining area | 1 | 5.4 |  | 5.4
30.52
2.7 | Community table ( 1600 mm long x 650 mm wide) | nos
as per drawing Using 50 x 50 mm SS Base Frame in satin bronze finish, Frame top to be covered with 18 mm thick sleeper wooden plank, to be Finished in Approved water base PU polish
|  | 6 |  |  | 6
2.8 | SS Bronze Satin finish 50 mm high skirting | rmt
16 SWG, 304 Grade SS skirting over existing ply, Fixed with epoxy adhesive
| Wicked door side | 1 | 1.3 |  | 1.3
| Store door side | 2 | 0.265 |  | 0.53
1.83
2.9 | SS Foot Rail | rmt
up to 200 mm high -Providing and fixing in position 304 grade S.S Satin Bronze finish foot rail of 38mm diameter with horizontal vertical members, Grouting in concrete, etc. complete, as specified and as directed by Architect
| Fronmt side | 1 | 12 |  | 12 | Rate difference steel & brass
2.10 | TV FIDS surround frame | nos
Size up to ( 1200 mm x 1350 mm ), Using 3 4 thick ply carcass as TV surround, like a picture frame including 50 to 75 mm wide surround finished in 4 mm thick veneer to receive polycot paint, Rear portion of TV surround covered with 1 mm thick laminate, To be fixed on wall panelling with adequate supports
a |  | 3 |  |  | 3
2.11 | Brick Cladding on Existing taper column | smt
Clean existing wall Ply surface before fixing brick tile cladding Before starting, carefully read the suppliers laying plan and instructions. Decorative Brick tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of tiles at Rs.120 sft without tax
| Sports bar front wall | 1 | 1.725 | 3.88 | 6.693
|  | 1 | 3.615 | 3.88 | 14.0262
|  | 1 | 1.943 | 3.88 | 7.5388
| Taper column 1 | 2 | 2.6 | 3.322 | 17.2744
| less | -2 | 1.45 | 3.322 | -9.6338
| 3 | 1 | 2 | 3.322 | 6.644
| less | -1 | 1.45 | 3.322 | -4.8169
| 4 | 1 | 2 | 3.322 | 6.644
44.3697
2.12 | Corian finish Wicked door | nos
Door size 950mm wide x 1150 height, 50 mm x 50 Aluminium framework for shutter, frame to be covered with 12 mm thk Fire rated plywood from all sides , At least 12 mm thk Corian fixed In Approved design pattern ( mixed of 2 Corian finishes )From guest side and in side plain, Corian to be tightly placed together and shall have seamless joints on edges, Corian joint should not be visible, Including 200 mm high 16G 304 grade SS satin Bronze finish band at door bottom matching to bar counter skirting . (Basic cost of solid surface (Corian) at Rs.850 sft)
|  | 1 |  |  | 1
2.13 | Service door-Veneer laminate finish including top fixed panel | No
Size 950mm x 2250mm
Door Frame
Overall finish size 200mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick FRP ply as rough ground,, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk FRP ply 4 mm thick Approved Veneer, Rebate to be separately put in wood, Wood to be treated with anti-termite medicine, Frame to be finished in Approved water base PU polish
Shutter Overall size 850 mm wide x 2250 mm ht. x 1 leaf, up to 40 mm thk. Using 35 mm thick readymade fireproof shutter covered with 4 mm thick approved veneer from Lounge side and Above veneer fix 50 mm wide wooden batten as per drawing and store room side 1 mm thick approved Laminate, Veneer and wood to be finish in approved water base PU polish (basic cost of veneer up to Rs. 150 sft) (basic cost of laminate Rs 1600 sheet)
Polish Frame entire door to be to be finish in Approved water base PU polish
Hardware 125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, Dead lock with suitable cover plate , and Magnetic latch, 1 set of handle as approved by architect ( Make Dorma Hafle )
| Bar store room door | 1 |  |  | 1
III | PAINTING WORK
3.1 | Luster Painting to walls | smt
Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base, Two coats of putty in oil synthetic enamel base, Three coats of luster paint. Complete as per manufacturer s specifications
3.2 | Painting to ceiling in acrylic emulsion paint | smt
Sanding and preparing surface for receiving paint, One coat of cement primer in solvent base. Two coats of putty ,Three coats of acrylic emulsion paint, Complete as per manufacturer s specifications
SPA
SPA Area
I | DEMOLITION WORK | LS
II | MASONRY WORK
2.1 | P C of 200mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level. | Sq. Mtr.
a | SPA bathroom left wall (A) | 1 | 2.79 | 4.325 | 12.0668
b | SPA bathroom door wall (B) | 1 | 1.2 | 2.5 | 3
c | Less door (-) | -1 | 0.79 | 2.5 | -1.975
d | Corridor and SPA divider wall © | 1 | 8.93 | 4.225 | 37.7292
e | SPA entry wall above (D ) | 1 | 1.25 | 1.775 | 2.2188
f | Welcome zone fire room wall "A". Deduct door area. | 2 | 5.8 | 4.2 | 48.72
g | Less door (-) | -1 | 1.1 | 2.1 | -2.31
h | Welcome zone fire room wall "A". Deduct door area. | 1 | 0.4 | 4.2 | 1.68
i | Less door (-) | -1 | 0.97 | 2.27 | -2.2019
j | Electric room right side wall"D" | 1 | 2 | 3.2 | 6.4
k | Sport bar counter area storage |  |  |  | 0
l | Sports bar front wall "B" | 1 | 8.25 | 4.8 | 39.6
m | Sports bar front wall "C" | 1 | 5.02 | 4.8 | 24.096
n | Less door (-) | -1 | 0.9 | 2.4 | -2.16
o | Bar storage left side wall"D" | 1 | 1.75 | 4 | 7
173.8639
2.2 | P C of 100mm solid concrete block masonry made of solid concrete blocks conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All divider walls up to 4300mm ht of internal divider walls at toilet area. | Sq. Mtr.
| Curve wall ( E) | 1 | 6.55 | 4.225 | 27.6737
2.3 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr.
a | Bathroom left side wall Both side plaster | 2 | 2.79 | 4.325 | 24.1335
b | Bathroom wall entry above | 2 | 1.2 | 4.325 | 10.38
c | Less door (-) | -1 | 0.79 | 2.5 | -1.975
d | Door edges (Bathroom) | 1 | 3.3 | 0.25 | 0.825
e | Corridor and SPA divider wall | 2 | 8.93 | 3.3 | 58.938
f | Curve wall | 2 | 6.55 | 3.3 | 43.23
g | SPA entry wall above | 2 | 1.25 | 1.775 | 4.4375
|  | 1 | 7.7 | 3.3 | 25.41
165.379
2.4 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr.
a | SPA bathroom right-side wall (F) | 1 | 2.55 | 3.2 | 8.16
b | Salon area front wall (G) | 1 | 3.5 | 3.3 | 11.55
c | Salon area left side wall (H) | 1 | 3.6 | 3.3 | 11.88
d | Wall outside bathroom (Basin wall) | 1 | 1.8 | 3.3 | 5.94
e | Duct wall (J) | 1 | 5.543 | 3.3 | 18.2919
55.8219
2.5 | P C of 150mm thick screed with 100mm thick broken AAC (Siporex) Block, broken siporex block to be laid on the waterproofing treated floor in proper levelling, after laying of the siporex block, void area to be filled up with Siporex or equivalent light weight materials including making of 50mm thick IPS flooring in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Complete as per instruction by the site engineer. | Sq. Mtr.
a | SPA bathroom | 1 | 4.584 | 1.2 | 5.5008
b | SPA Salon below flooring | 1 | 3.915 | 7.7 | 30.1455
35.6463
2.6 | P C of 50mm 75mm thick screed in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Laying the same in proper line level on the seating area s floor to maintain the floor levelling to get the smooth surface to lay the finishing floor materials on the said surface. Complete as per architectural detail drawings instruction by the site engineer. | Sq. Mtr.
III | CIVIL FINISHES WORK
FLOORING
3.1 | Italian Marble Flooring | smt
Clean existing sub floor thoroughly. Flooring shall consist of Marble as per drawing, Up to 50 mm thick bedding mortar as per tech specs. Marble slabs shall be minimum 18 mm thick, laid as per tech specs, Marble to be cut as per size and laid with tight hairline joints. Joint filling and finishing as per tech specs.(On site cost of Italian marble @ Rs.450 sft without tax) including Approved sealer to be applied on all sides, Including sealer coat , Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover
| SPA bathroom flooring | 1 | 2.4 | 1.2 | 2.88
| Door edge | 1 | 0.275 | 0.71 | 0.19525
3.0753
3.2 | 10 mm thick Terrazzo Flooring | Smt
Supply and application of 10mm thick Epoxy Resin Terrazzo flooring system (12 mm laid grinded to 10 mm) Flexural strength = 25MPa as per ASTM D790,Tensile strength = 14 MPa as per ASTM D638. The product must have elongation = 5%, when tested as per ASTM D638. Hardness of the floor must be = 75, when tested as per Shore D hardness test. Co-efficient of linear thermal expansion of the product will be approximately 13.3x10-6. This product should have flammability of not more than 0.025inch minute when tested as per ASTM D 635. IGBC certified product. Typical properties of the resin needs to be achieved in laboratory tests at 50% Relative Humidity. Fire Resistance BS476-7 Spread of Flame Class 2Slip Resistance TRRL Pendulum Slip Test Dry > 40 low slip potential. Temperature Resistance Tolerant up to 60 C .Water Permeability Nil – Karsten Test(Impermeable) Abrasion Resistance Taber Abrader - 50 mg loss per 1000 cycles(1kg load using CS17 wheels). Compressive Strength > 55 N mm2 (BS6319), Bond Strength Greater than cohesive strength of 25 N mm2 concrete. >1.5 MPa. Toxicity (when cured) Taint Free to sensitive foodstuffs. Epoxy terrazzo layer to be applied over Epoxy high build primer and needs to be properly finished, grinded and polished with suitable transparent abrasion resistant material. The complete system of Epoxy Resin Terrazzo flooring needs to be executed by an authorized applicator of the manufacturer and as per the approved method statement of the manufacturer. Providing and application of Divider termination Trim of 2mm- 2.5mm thick L SS , Providing and application of Momex Joint , Providing and application of PU Sealant at terminations
a | SPA reception area | 1 | 4.46 | 5 | 22.3
b | SPA entry passage | 1 | 3.25 | 1.25 | 4.0625
c | SPA salon area | 1 | 7.5 | 3.7 | 27.75
d | Deduct (4) furniture (-) | -1 | 0.45 | 2.57 | -1.1565
e | Washbasin area floor | 1 | 1.48 | 1.77 | 2.6196
55.5756
CLADDING
3.3 | Synthetic Marble Wall Cladding with Grooves | smt
Clean existing wall surface before fixing wall cladding. Slabs shall be min. 18 mm thick fixed to plastered siporex block work, Slabs shall be installed as per tech specs on plastered wall siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Synthetic marble @ Rs.275 sft without tax)
a | SPA bathroom Left wall | 1 | 2.53 | 2.8 | 7.084
b | Spa bathroom back and entry wall | 2 | 1.2 | 2.8 | 6.72
c | Less door | -1 | 0.75 | 2.4 | -1.8
d | SPA bathroom right wall | 1 | 1.2 | 2.4 | 2.88
e | Spa wall cladding half height | 1 | 7.24 | 0.9 | 6.516
21.4
3.4 | Italian Marble Wall Cladding | smt
Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to Fire rated plywood panelling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves chamfer edge moulding, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax)
3.5 | Synthetic Marble Jamb lining for common Toilet Door Openings | rmt
Marble jamb lining for EWC doors including rebate, up to 230 mm wide, up to 2250 mm ht all around, At least 18 mm thk per-polished slabs to be used, Slabs to be cut as per approved size drawings, Include mitre joints at all junctions as per Architects instructions, Including V groove to match wall cladding, Marble to be fitted with white cement only, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides (Basic cost of Synthetic Marble at Rs.275 sft without tax)
3.6 | Italian Marble Finish Wash Basin Counter for toilet | rmt
The counter shall be supported on 38mm x 38mm x 5mm thk MS angle fixed to block work. Brackets shall be inserted within wall by at least 125mm, MS brackets shall be coated with 2 coats of anti-corrosive paint and 3 coats of synthetic enamel paint, 18mm thk ordinary Indian marble placed within bracket and screwed through bracket, At least 20mm thk cement mortar bedding in 1 4 ratio, Pre-finished and pre-polished marble slabs shall be fixed as per tech specs. Counter shall have up to 300 mm wide fascia marble with mitre joints All top edges of counter shall have chamfer moulding. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides. Including all plumbing cutout as shown in drawing
(Basic cost of marble at Rs.450 sft including fibre filling polish)
3.7 | Sink counter including under counter shutter | rmt
Size 1800mm length x 450mm depth x 850mm ht.
As per drawing, Sink counter structure constructed out of 18 mm thk plywood, At least 16 mm thk approved Terrazzo Stone fixed to top with 50 mm thick front fascia and back flash in profile shown in drawing - including polish. stone to be tightly placed together and shall have mitre joints on edges including moulding as approved by Architect. All joints to be filled with matching colour TIM-X or equivalent grout filler. Carcass internal surface to be covered with 1mm thk approved laminate , all exposed surfaces including shutter to be finished in approved veneer, Veneer to be Finished in Approved water base PU polish, including 50 mm high SS skirting , as per approved design. Including all cutouts for electrical points, (Basic cost of Terrazzo at Rs. 750 sft ) (Basic cost of Veneer at Rs. 150 sft ) excluding sink
|  | 1 | 1.7 |  | 1.7
3.80 | Synthetic Marble Portal 450 mm wide | rmt
Using 16mm thick marble Pasted over existing ply surface with epoxy adhesive brass pins, Ply surface shall be cleaned before installing marble, At least 16mm thk marble to be fixed, Marble shall be cut as per size laid with tight hairline joints, Edge of marble shall be polished before installation, Joints to be filled with Tim-X or equivalent joint filler, Including 2 high Marble fascia, Approved sealer to be applied on all sides. Special care to be taken to fix marble on horizontal surface. Shall rest over ply at one end and vertical marble on the other, The vertical marble over 50 mm shall be fixed using brass pins
(Basic cost of Synthetic Marble at Rs.275 sft without tax)
a | vertical Seating | 3 | 3.05 |  | 9.15
b | horizontal (top) | 1 | 1.35 |  | 1.35
10.5
IV | FRENCH PLASTER WORK
4.1 | Fire line Gypsum board ceiling | smt
All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobin Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceiling height is 4300 mm )
a | SPA reception area | 1 | 4.46 | 5 | 22.3
b | SPA entry passage | 1 | 3.25 | 1.25 | 4.0625
c | SPA salon area | 1 | 7.5 | 3.7 | 27.75
d | Deduct (4) furniture | -1 | 0.45 | 2.57 | -1.1565
e | Washbasin area | 1 | 1.48 | 1.77 | 2.6196
f | Bathroom ceiling | 1 | 1.2 | 2.4 | 2.88
58.4556
4.2 | Fire line Gypsum board Facia Band 50 mm TO 100 mm | rmt
| All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum (Round wall side ) | 1 | 3.4 |  | 3.4
4.3 | Indirect Light Coves in Ceiling | rmt
In L shape with 100 mm deep up to 300mm high and 50 mm wide fascia, All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum
a | Above curve wall | 1 | 6.4 |  | 6.4
4.4 | Fire line Gypsum board slit 100 mm TO 150 mm wide | rmt
All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum
4.5 | Fire line Gypsum board slit 50 mm wide for curtain | rmt
All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibre tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum
a | For curtains in SPA
4.6 | Universal plaster punning on wall | smt
Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bull marks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work.
a | SPA basin L wall "R" | 1 | 3.03 | 2.97 | 8.9991
b | Curve wall SPA (S) | 1 | 6.55 | 3.13 | 20.5015
c | SPA entry above door from inside | 1 | 1.25 | 0.93 | 1.1625
|  | 1 | 7.7 | 3.3 | 25.41
56.0731
V | CARPENTRY WORK
5.1 | Aluminium frame work for Partition | smt
50mm x 36 mm, 16 SWG aluminium framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment.
a | SPA reception partition | 1 | 1.7 | 3.14 | 5.338
b | Boxing for sliding in SPA (more thick) | 2 | 0.545 | 3.14 | 3.4226
8.7606
5.2 | Aluminium frame work For Panelling boxing | Smt
36mm x 36 mm, 16 SWG aluminium framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment, including provision for Electrical Conduit and slot for Digital screen as shown in drawing
a | SPA entry right-side wall (B) | 1 | 7.646 | 3.22 | 24.6201
b | SPA room left side wall © | 1 | 7.244 | 3.24 | 23.4706
c | Hair salon right wall | 1 | 2.788 | 3.14 | 8.7543
d | hair salon front wall | 1 | 2.924 | 3.14 | 9.1814
e | Hair salon left wall | 1 | 3.08 | 3 | 9.24
f | Duct wall | 1 | 3 | 2.14 | 6.42
81.6864
5.3 | Ply Panelling
providing and fixing marine plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at centre of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material
A | 12 mm thk plywood | Smt
a | SPA reception partition | 1 | 1.7 | 3.14 | 5.338
b | Boxing for sliding in SPA (more thick) | 2 | 0.545 | 3.14 | 3.4226
c | SPA entry right-side wall (B) | 1 | 7.646 | 3.22 | 24.6201
d | SPA room left side wall © | 1 | 7.244 | 3.24 | 23.4706
e | Hair salon right wall | 1 | 2.788 | 3.14 | 8.7543
f | hair salon front wall | 1 | 2.924 | 3.14 | 9.1814
g | Hair salon left wall | 1 | 3.08 | 3 | 9.24
h | Duct wall | 1 | 3 | 2.14 | 6.42
i | SPA entry right-side wall extra | 1 | 0.9 | 3 | 2.7
93.147
B | 15 mm thk plywood | Smt
C | 18 mm thk plywood | Smt
D | 6 mm thk Flexi plywood | Smt
5.4 | SS Jali in Satin Bronze finish with fixed glass partition | smt
Overall size- 1200 mm wide x 3000 mm height, Outer frame in SS hollow frame of 38 mm x50mm x 2.5 mm thickness all around each jali panel, all welded and polished joints, SS frame in Satin Bronze finish as approved by Architect, Outer frame fixed to floor and above false ceiling, using 8 mm thick MS plate with anchor bolt. including 10 mm thk 304 grade SS pipe jali as per approved design and in Satin Bronze finish,
providing and fixing 10 mm thick toughen fix glass panel with 12 mm wide SS Beading around glass
a | Fix glass | 2 | 1.1 | 3 | 6.6
5.5 | Decorative Toilet Vanity Mirrors | smt
The mirrors shall be mounted on a backing of marine ply of overall 20 to 25 mm thickness, which shall be fixed to the wall. Including provision for LED strip light. Mirror shall be 8 mm thick to receive bevelling and shall be laminated at the back for protection, and backed with felt lining. All Mirrors shall have 18-25 mm bevelling on all edges. All edges of mirror shall have CNC edge polish, Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect. exclude cost of LED strip lighting
| Bathroom inside | 1 | 1.68 | 2.345 | 3.9396
5.6 | Plain mirror panelling | smt
The mirrors shall be mounted on a backing of marine ply of overall 18 mm thickness, which shall be fixed to the wall. Including L shape SS finish Angle profile covering on All around the mirror. Mirror shall be 8 mm thick to receive bevelling and shall be laminated at the back for protection, and backed with felt lining. All Mirrors shall have 18-25 mm bevelling on all edges. All edges of mirror shall have CNC edge polish. Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect.
| Spa Left & right side Arch mirror | 4 | 0.9 | 1.45 | 5.22
5.7 | Tinted mirror panelling | smt
The mirrors shall be mounted on a backing of marine ply of overall 12 mm thickness, which shall be fixed to the wall. Including SS inserts as per drawings, including 50 mm wide C shape profile covering on All around the mirror. Mirror shall be 8 mm thick and shall be laminated at the back for protection, and backed with felt lining. All edges of mirror shall have CNC edge polish. Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect.
| Spa Hair wash back side | 3 | 0.943 | 2.91 | 8.2324
5.8 | Fluted Wall panelling in Duco paint finish | smt
Using 12 mm thk HDF to be fixed on 12 mm thick HDF ply base , All joints shall be planed and smoothened before installing fluting mouldings. All joints shall be filled with suitable fillers and reinforcement tape, if required. HDF Mouldings to be fixed as per drawing ( min 25 mm wide 12 mm deep ), shall be installed on HDF back surface in perfect plumb, line and level. base and HDF moulding surface shall be finished in Duco paint, as approved by Architect
5.9 | Wooden strip panelling | smt
Providing and fixing 25 mm wide x 12mm thick NBTW wooden strip as shown in drawing, Fixing shall be free of defects, Wooden strip to be Finished in Approved Melamine Polish
a | Duct wall "E" and partition | 1 | 1.7 | 3 | 5.1
b | SPA room left side wall (F) | 1 | 7.235 | 2.1 | 15.1935
c | SPA room right-side wall (G,H,I) | 3 | 0.9 | 2.96 | 7.992
d | Spa duct Wall fluted | 1 | 2.9 | 3 | 8.7
36.9855
5.10 | Veneer finish Retail Display Behind reception table ( 2600 L x450 D x3000 H) | smt
As per drawing, 12 mm thick plywood fixed to wall, Ply to be covered with 4 mm thick HDF , 36 mm thick Shelf ( 18 +12mm ply + 6 mm thick Corian ) with provision for Led strip lights, Storage unit at bottom, carcus to be made in 18 mm thick ply, internal surface covered with 1mm thick approved laminate, including veneer finish shutter and drawers, including 50 mm high 16G 304 grade SS bronze satin finish Skirting, Veneer to be Finished in Approved Melamine Polish (Basic cost of veneer up to Rs. 125 -sft )
| Display table | 1 | 2.55 | 3.05 | 7.7775
5.11 | Duco paint finish Salon unit ( 3200 L x400 D x3000 H) | smt
As per drawing, Carcase to be made out of 18 mm thick ply, Ply to be covered with 6 mm thick HDF , 36 mm thick HDF made-up Shelf with provision for Led strip lights as shown in drawings, Drawer unit at mirror bottom, internal surface covered with 1mm thick approved laminate, 50 mm wide half round Duco finish moulding in arch shaped as per drawings, including 50 mm high 16G 304 grade SS bronze satin finish Skirting,
|  | 1 | 3.08 | 3.05 | 9.394
5.12 | Duco paint finish Salon unit ( 2800 L x150 D x3000 H) | smt
As per drawing, Carcase to be made out of 12 mm thick ply, Ply to be covered with 6 mm thick HDF , 36 mm thick HDF made-up Shelf with provision for Led strip lights as shown in drawings, 50 mm wide half round Duco finish moulding in arch shaped as per drawings, including 50 mm high 16G 304 grade SS bronze satin finish Skirting,
|  | 1 | 2.75 | 3.05 | 8.3875
5.13 | SS Bronze finish niche for Nail bar ( 1600 L x100 D x500 H) | Nos
|  | 1 |  |  | 1
As per drawing, Carcase to be made out of 12 mm thick ply, Ply to be covered with 16g SS bronze finish with 50 mm wide cover border in SS bronze finish as shown in drawings,
5.14 | Nail Bar counter in profile ( 1250 L x400 D x750 H) | Nos
Providing and fixing Nail Bar counter desk in profile , up to 100 mm thick Top finish in Terrazzo , with SS bronze finish base As per detail drawings.
a |  | 1 |  |  | 1
5.15 | Spa reception table in profile ( 2500 L x 600 D x1100 H) | Nos
Providing and fixing Reception counter desk in profile , SS bronze finish top , with Fluted Apron finish in Duco paint, including drawer and storage As per detail drawings.
1 |  | 1 |  |  | 1
5.16 | SS Bronze Satin finish skirting 50mm high | Rmt
16 SWG, 304 Grade SS skirting over existing ply, Fixed with epoxy adhesive
| Spa Left side round wall | 1 | 6.27 |  | 6.27
| Right side door Wooden fluted Panel | 3 | 1.245 |  | 3.735
| Right side Wall paper wall | 3 | 0.8 |  | 2.4
| Near storage side wall right side | 1 | 1.41 |  | 1.41
| Storage below | 1 | 2.35 |  | 2.35
| Nail bar side | 1 | 4.575 |  | 4.575
| Counter side wall | 1 | 0.91 |  | 0.91
| Counter below | 1 | 1.635 |  | 1.635
| bath door | 1 | 0.32 |  | 0.32
| Sofa below | 1 | 1.33 |  | 1.33
24.935
5.17 | 30 mm thick x 400 mm deep Corian finish ledge, | Rmt
Using 18 mm thick marine ply covered with 6 mm thick approved Corian on both side with 30 mm wide Facia.
| Pantry above | 2 | 1.65 |  | 3.3
| Seating | 1 | 1.06 |  | 1.06
4.36
5.18 | 1000 mm dia Circular Picture frame in Duco paint | Nos
|  | 4 |  |  | 4
DOORS
5.19 | Main Ent door -Wooden strip fluted panel door in Polish and Duco paint | nos
Size 1000mm x 2400mm
Door Frame
Overall finish size 100mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick marine ply as rough ground, fixed to masonry wall in perfect plumb, line and level using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk NBTW wood, Rebate to be separately put in NBTW wood, Wood to be treated with anti-termite medicine, Frame to be Finished in Approved Melamine Polish
Shutter
Overall size 900 mm wide x 2400 mm ht. x 1 leaf, up to 82 mm thk. Using 38 mm thick readymade fireproof shutter covered with 8 mm thick marine ply on both sides , The shutter shall be clad with 4 mm thick approved veneer , including NBTW beading all around, 25 mm x 12 mm thick wooden strip to be fix on Veneer surface from inside and 25 mm x 12 mm thick HDF strip from lounge side with in Duco paint as shown in drawings. basic cost of veneer up to Rs. 125 sft
Polish
Frame entire door to be Finished in Approved Melamine Polish
Hardware
125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, with lock, Concealed door closer by Hafele as per required capacity, 1 set of handle as approved by Architect
|  | 1 |  |  | 1
5.20 | Toilet door Wooden strip | nos
Size 1000mm x 2400mm
Door Frame
Overall finish size 250mm x 50 mm thk without rebate, Door frame to be Made up Using 18 mm thick marine ply as rough ground, fixed to masonry wall in perfect plumb, line and level using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk NBTW wood, Rebate to be separately put in NBTW wood, Wood to be treated with anti-termite medicine, Frame to be Finished in Approved Melamine Polish
Shutter
Overall size 800 mm wide x 2400 mm ht. x 1 leaf, up to 82 mm thk. Using 38 mm thick readymade fireproof shutter covered with 8 mm thick marine ply on both sides , The shutter shall be clad with 4 mm thick approved veneer from both side , including NBTW beading all around, 25 mm x 12 mm thick wooden strip from out side, to be fix on Veneer surface as shown in drawings. basic cost of veneer up to Rs. 125 sft
Polish
Frame entire door to be Finished in Approved Melamine Polish
Hardware
125 mm x 50 mm x 4 mm thk bearing type SS hinges fixed between frame and shutter with SS screws. At least 4 nos. hinges per shutter, with lock, Concealed door closer by Hafele as per required capacity, 1 set of handle as approved by Architect
|  | 1 |  |  | 1
5.21 | Sliding Glass door with SS Jali in Satin Bronze finish | nos
Overall size- 1200 mm wide x 3000 mm height, Outer frame in SS hollow frame of 38 mm x50mm x 2.5 mm thickness all around with top hung Sliding channel , SS frame in Satin Bronze finish as approved by Architect, Sliding channel fixed to false ceiling frame, using 8 mm thick MS plate with anchor bolt. including 10 mm thk 304 grade SS pipe jali door panel as per approved design and in Satin Bronze finish,
providing and fixing 10 mm thick toughen fix glass panel with 12 mm wide SS Beading around glass
|  | 1 |  |  | 1
5.22 | Built-in seating -Seat | Rmt
Carcus to be made out of 38mm x 38 mm Aluminium framework and 18 mm thk plywood , up to 100 mm thk foam rubber seat pasted to 18 mm thk ply base , 25 mm thk., 32 density PU foam to cover rubber seat, PU foam to be covered with 6 mm thk. sheet before finishing seat in white cloth, Final fabric leather shall be nailed on bottom side of plywood base, Including Wooden finish band, Wood to be Finished in Approved Melamine Polish,(Basic cost of fabric at Rs.2500 rmt)
a |  | 1 | 1.371 |  | 1.371
VI | SANITARY CP FITTINGS - ONLY FIXING
COMMON LADIES AND GENTS TOILET
6.1 | WC for toilet | nos
6.2 | Flush tank | nos
6.3 | Flush plate | nos
6.4 | Wash basin | nos
6.6 | health faucet for WC | nos
6.7 | wash basin faucet | nos
6.8 | toilet paper holder | nos
6.9 | hand dryer | nos
6.10 | tissue paper holder | nos
6.11 | Soap dispenser | nos
6.12 | Robe hook | nos
6.13 | Dust bin | nos
VII | PAINTING WORKS
7.1 | Painting to walls in pearl luster | smt
Sanding and preparing surface for receiving primer, One coat of cement primer in solvent base, Two coats of putty in water synthetic enamel base, Three coats of luster paint in approved shed, Complete as per manufacturer s specifications
| Right side wall of basin counter | 1 | 1.03 | 2.8 | 2.884
7.2 | Painting to ceiling in acrylic emulsion paint | smt
Sanding and preparing surface for receiving primer, One coat of cement primer in solvent base, Two coats of putty in water synthetic enamel, Three coats of acrylic emulsion paint in approved shed, Complete as per manufacturer s specifications
| Spa bathroom ceiling | 1 | 2.325 | 1.15 | 2.6738
| Spa ceiling | 1 | 2.92 | 4.65 | 13.578
|  | 1 | 1.75 | 1.07 | 1.8725
|  | 1 | 3.67 | 2.87 | 10.5329
|  | 1 | 4.15 | 5 | 20.75
|  | 1 | 3.2 | 1.22 | 3.904
53.3111
7.3 | Surface preparation for wall paper | smt
Include cement primer, 2 coats of putty, touch up putty and primer with water base, Surface to be made ready to receive wall paper
| Spa base coat | 1 | 1.4 | 2.95 | 4.13
|  | 1 | 1.22 | 2.95 | 3.599
|  | 1 | 1.22 | 2.95 | 3.599
|  | 1 | 1.13 | 2.95 | 3.3335
| Spa left side round wall | 1 | 6.245 | 3.045 | 19.016
| Spa counter backside wall | 1 | 1.98 | 2.34 | 4.6332
| spa basin counter wall | 1 | 1.63 | 1.7 | 2.771
| sofa wall | 1 | 1.32 | 2.8 | 3.696
44.7777
7.4 | Hand painted Customised Wall paper | Smt
Providing and fixing approved wall paper by -Marshal Ego wall paper, as approved by architect, Include protection till handover, (Basic cost of wall paper @ Rs.350 sft )
7.5 | Duco Paint to Walls Partition | Smt
Sanding and preparing surface for receiving paint, Final coats of Duco paint. Complete as per manufacturer s specifications
WATER LOUNGE
Water Lounge Area
I | DEMOLITION WORK | LS
II | MASONRY WORK
2.1 | P C of 200mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level. | Sq. Mtr.
a | Staff toilet entry wall (A) | 1 | 2.41 | 3.8 | 9.158
b | Less door | -1 | 0.78 | 2.525 | -1.9695
c | Staff toilet and ladies toilet divider wall (B) | 1 | 5.09 | 3.8 | 19.342
d | Staff toilet divider wall © | 1 | 1.455 | 3.8 | 5.529
e | Less wall (D) above | 1 |  |  | 0
f | Handicap toilet L shape entry wall (G) | 1 | 3.8 | 4.25 | 16.15
g | Less door | -1 | 1 | 2.37 | -2.37
h | Wall beside handicap entry (H) | 1 | 0.6 | 2.55 | 1.53
i | Corridor and Men's toilet divider wall (I) | 1 | 6.76 | 3.8 | 25.688
j | Less door | -1 | 0.95 | 2.55 | -2.4225
k | Ladies toilet and corridor divider wall (E ) | 1 | 4.3 | 3.8 | 16.34
l | Less door | -1 | 0.98 | 2.525 | -2.4745
m | Ramp side passage and men's toilet divider wall (F) | 1 | 4.85 | 4.25 | 20.6125
n | Men's toilet washbasin area left side wall (J) | 1 | 3.06 | 3.8 | 11.628
o | Ladies toilet and electric room divider wall (Y) | 1 | 4.18 | 4.25 | 17.765
p | Live kitchen and fine dine |  |  |  | 0
q | Live kitchen counter wall | 1 | 0.95 | 4.45 | 4.2275
r | Live kitchen existing fire duct "B" | 1 | 1.3 | 1.52 | 1.976
s | Live kitchen fine dining divider wall "C" | 1 | 2.93 | 4 | 11.72
| Corridor wall | 1 | 19.95 | 4.45 | 88.7775
241.207
2.2 | P C of 150mm thick block masonry conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All external divider walls up to 4300mm ht up to mother slab level. | Sq. Mtr.
| Phase 1 passage and ladies toilet divider wall above existing wall (K) | 1 | 6.45 | 1.06 | 6.837
0
| Live kitchen Corridor |  |  |  | 0
| Electric room and janitor room's divider wall (A) | 1 | 1.4 | 4.25 | 5.95
| Electric room entry wall(B) | 1 | 2.84 | 2.05 | 5.822
| Less door | -1 | 1.51 | 2.05 | -3.0955
| Corridor entry wall © | 1 | 2.05 | 4.25 | 8.7125
| Less door | -1 | 1.525 | 2.35 | -3.5837
| Existing door in corridor area which has been closed (D) | 1 | 1.7 | 2.32 | 3.944
| Live kitchen above door ( E) | 1 | 2.05 | 1.06 | 2.173
| Fire panel backside wall (F) | 1 | 1.9 | 2.119 | 4.0261
30.7854
2.3 | P C of 100mm solid concrete block masonry made of solid concrete blocks conforming to IS 2185 (Part-I), walls to start from floor slab up to true ceiling, suitably anchored to back existing wall existing columns in cement mortar in 1 4 ratio, minimum 12 15mm thick, only 43 or 53 grade cement Adhesive to be used. Constructed in perfect plum, line and level. Wall to be cured for at least 3 days. Rate inclusive of required scaffolding, ranking out the joints, cutting, providing fixing of including providing RCC Patli to be after every 5 layers and lintel work for the doors windows curved windows opening of 100mm x 100mm at every 1.00m C C with 2 nos. 8mm dia Tor bars and 6mm dia links at 300 c c in cement concrete of mix M 20, required formwork complete with raking out joints, curing, doing independent double legged scaffolding as per specifications etc. at all heights, depths and leads as directed, exclude cement plaster. Complete as per site engineer s instruction and Architectural detail drawings. All divider walls up to 4300mm ht of internal divider walls at toilet area. | Sq. Mtr.
1 | Ladies toilet WC partition wall ( 1) (L) | 1 | 2.2 | 2.55 | 5.61
2 | Ladies toilet WC partition wall ( 2) (M) | 1 | 2.2 | 2.55 | 5.61
3 | Ladies toilet WC partition wall ( 3) (N) | 1 | 2.42 | 2.55 | 6.171
3 | Ladies toilet WC partition wall ( 3) (N) | 1 | 0.5 | 2.55 | 1.275
4 | Ladies toilet WC partition wall ( 1) (O) | 1 | 1.791 | 2.55 | 4.567
5 | Ladies toilet basin partition (2) (P) | 1 | 0.739 | 2.55 | 1.8844
6 | Men's toilet WC partition wall (1) (Q) | 1 | 0.503 | 2.55 | 1.2826
7 | Men's toilet WC partition wall (1) (R) | 1 | 2.2 | 2.5 | 5.5
8 | Men's toilet WC partition wall (1) (S) | 1 | 1.568 | 2.55 | 3.9984
9 | Men's toilet WC partition wall (1) (T) | 1 | 2.175 | 2.55 | 5.5462
10 | Men's toilet basin partition (U) | 1 | 0.9 | 2.55 | 2.295
11 | Men's WC ledge wall all (456) | 3 | 1.235 | 1.2 | 4.446
12 | Ladies WC ledge wall all (123) | 3 | 1.235 | 1.2 | 4.446
13 | Handicap WC ledge wall | 1 | 2.18 | 1.2 | 2.616
14 | Staff toilet ledge wall | 2 | 1.285 | 1.2 | 3.084
0
| Live kitchen and fine dine |  |  |  | 0
| Buffet counter front wall (buffet counter) "D" | 1 | 2.925 | 4 | 11.7
70.0318
2.4 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr.
a | Staff toilet entry wall (A) | 2 | 2.41 | 3.8 | 18.316
b | Less door | -2 | 0.78 | 2.525 | -3.939
c | Staff toilet and ladies toilet divider wall (B) | 2 | 5.09 | 3.8 | 38.684
d | Staff toilet divider wall © | 2 | 1.455 | 3.8 | 11.058
e | Handicap toilet L shape entry wall (G) | 2 | 3.8 | 4.25 | 32.3
f | Less door | -2 | 1 | 2.37 | -4.74
g | Wall beside handicap entry (H) | 2 | 0.6 | 2.55 | 3.06
h | Corridor and Men's toilet divider wall (I) | 2 | 6.76 | 3.8 | 51.376
i | Less door | -2 | 0.95 | 2.55 | -4.845
j | Ladies toilet and corridor divider wall (E ) | 2 | 4.3 | 3.8 | 32.68
k | Less door | -2 | 0.98 | 2.525 | -4.949
l | Ramp side passage and men's toilet divider wall (F) | 2 | 4.85 | 4.25 | 41.225
m | Men's toilet washbasin area left side wall (J) | 2 | 3.06 | 3.8 | 23.256
n | Ladies toilet and electric room divider wall (Y) | 2 | 4.18 | 4.25 | 35.53
o | Ladies toilet WC partition wall ( 1) (L) | 2 | 2.2 | 2.55 | 11.22
p | Ladies toilet WC partition wall ( 2) (M) | 2 | 2.2 | 2.55 | 11.22
q | Ladies toilet WC partition wall ( 3) (N) | 2 | 2.42 | 2.55 | 12.342
r | Ladies toilet WC partition wall ( 3) (N) | 2 | 0.5 | 2.55 | 2.55
s | Ladies toilet WC partition wall ( 1) (O) | 2 | 1.791 | 2.55 | 9.1341
t | Ladies toilet basin partition (2) (P) | 2 | 0.739 | 2.55 | 3.7689
u | Men's toilet WC partition wall (1) (Q) | 2 | 0.503 | 2.55 | 2.5653
v | Men's toilet WC partition wall (1) (R) | 2 | 2.2 | 2.5 | 11
w | Men's toilet WC partition wall (1) (S) | 2 | 1.568 | 2.55 | 7.9968
x | Men's toilet WC partition wall (1) (T) | 2 | 2.175 | 2.55 | 11.0925
y | Men's toilet basin partition (U) | 2 | 0.9 | 2.55 | 4.59
z | Men's WC ledge wall all (4) | 1 | 1.235 | 1.2 | 1.482
aa | Men's WC ledge wall all (5) | 1 | 1.235 | 1.2 | 1.482
ab | Men's WC ledge wall all (6) | 1 | 1.235 | 1.2 | 1.482
ac | Ladies WC ledge wall all (1) | 1 | 1.235 | 1.2 | 1.482
ad | Ladies WC ledge wall all (2) | 1 | 1.235 | 1.2 | 1.482
ae | Ladies WC ledge wall all (3) | 1 | 1.235 | 1.2 | 1.482
af | Handicap WC ledge wall | 1 | 2.18 | 1.2 | 2.616
ag | Staff toilet ledge wall | 1 | 1.285 | 1.2 | 1.542
ah | Staff toilet ledge wall | 1 | 1.285 | 1.2 | 1.542
ai |  |  |  |  | 0
aj | Passage extra |  |  |  | 0
ak | Janitor room entry wall to beam (G) | 1 | 1.66 | 2.15 | 3.569
al | Less door | -1 | 0.84 | 2.06 | -1.7304
am | Electric room entry to corridor entry wall (H) | 1 | 5.6 | 2.8 | 15.68
an | Less electric room door | -1 | 1.48 | 2.4 | -3.552
ao | Less live kitchen door | -1 | 0.9 | 2.4 | -2.16
ap | Less fire panel door | -1 | 1.1 | 1.53 | -1.683
aq | Fire panel backside and right-side (F) wall | 1 | 1.9 | 2.119 | 4.0261
ar | Fire panel left side wall | 1 | 0.8 | 2.119 | 1.6952
ar | Corridor wall © both sides | 2 | 0.6 | 2.8 | 3.36
as | Corridor and live kitchen divider wall (I) | 1 | 2.9 | 3.3 | 9.57
at | Corridor live kitchen entry opposite wall "J" | 1 | 3.5 | 2.6 | 9.1
au | Lift corridor frontside wall (K) both sides | 2 | 4.3 | 3.5 | 30.1
av | Relax zone entry above "L" | 2 | 2.05 | 1 | 4.1
aw | Live kitchen and fine dine |  |  |  | 0
ax | Live kitchen counter wall both sides) "A" | 2 | 0.95 | 4.5 | 8.55
ay | Live kitchen fine dine/buffet divider wall"C" | 2 | 2.93 | 4 | 23.44
az | Buffet front wall "D" (twice) | 2 | 2.925 | 4 | 23.4
ba | Garbage area front wall "F" | 1 | 1.4 | 3.5 | 4.9
bb | Live kitchen column plaster"J" | 1 | 0.8 | 3.46 | 2.768
bc |  |  |  |  | 506.2165
2.5 | P A of single coat backing plaster of 12 15 mm thick in CM 1 4 proportion to the walls others concrete masonry surfaces including raking out joints, hacking concrete surfaces and applying approved chemical bonding agent for receiving cement finished dash coat plaster and applying a scratch coat over concrete surfaces by bonding adhesive chemical coat as directed by approved manufacturer to create a key, cleaning grooving deep junctions of concrete masonry, grouting then back by mortar mixed with non shrinking compound along with packing of clean, fresh square cut aggregate; also providing and fixing approved metal mesh (18 gauge) @ 150 200mm wide to junctions of concrete and masonry, preparing jambs, sills, grooves, pattas, wattas, rounding of corners, all complete as per architectural drawings, specifications and finished smooth with wooden rundha or rough to take specified cladding or as specified, depth and lifts, doing independent double-legged scaffolding, cleaning of surfaces, curing. complete as per specification and to the approval of the PM scaffolding, curing the joints, seven days water treatment as anti crack of plaster, etc.. Complete as per site engineer s instruction. These are for all the both surfaces of new constructed masonry walls rcc wall columns beams etc. | Sq. Mtr.
| Phase 1 passage and ladies toilet divider wall (K) | 1 | 6.45 | 4.25 | 27.4125
| Ladies toilet WC wall (V) | 1 | 4.6 | 3.5 | 16.1
| Handicap toilet WC wall (W) | 1 | 1.5 | 3.1 | 4.65
| Handicap toilet basin wall (X) | 1 | 2.67 | 3.1 | 8.277
| Men's toilet WC wall (K) | 1 | 3.85 | 3.5 | 13.475
| Live kitchen and fine dine |  |  |  | 0
| Live kitchen backside wall(existing wall). Add in existing wall | 1 | 4.53 | 4 | 18.12
| Live kitchen right side wall"H". (Existing wall) | 1 | 3.4 | 4 | 13.6
| corridor wall | 1 | 21.1905 | 3.15 | 66.75
168.3845
2.6 | Ramp flooring- Gradient of slope in 1 to 12 ratio, Floor surface to be cleaned of any dust particles, Surface to be watered well before laying blocks,OPC Only 43 grade cement to be used ( make- ACC Bharthi Ultratech Grasim Industries Coromandel ),Cement mortar in 1 4 ratio, minimum 12mm thk, Ramp block shall start from slab level height shall increase gradually match raised flooring height, Blocks shall be laid with alternate joints, Cured for at least 3 days,
| 0 to 300 mm thick | Sq. Mtr.
2.7 | P C of 150mm thick screed with 100mm thick broken AAC (Siporex) Block, broken siporex block to be laid on the waterproofing treated floor in proper levelling, after laying of the siporex block, void area to be filled up with Siporex or equivalent light weight materials including making of 50mm thick IPS flooring in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Complete as per instruction by the site engineer. | Sq. Mtr.
2.8 | P C of 300mm thick screed with 100 200 250mm thick broken AAC (Siporex) Block, broken siporex block to be laid on the waterproofing treated floor in proper levelling, after laying of the siporex block, void area to be filled up with Siporex or equivalent light weight materials including making of 50mm thick IPS flooring in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Laying the same in proper line level on the seating area s floor to maintain the floor levelling to get the smooth surface to lay the finishing floor materials on the said surface. Complete as per architectural detail drawings instruction by the site engineer. | Sq. Mtr.
a | D x E | 1 | 13.475 | 6.8 | 91.63
b | less F | -1 | 6.075 | 1.4 | -8.505
83.125
2.9 | P C of 50mm 75mm thick screed in cement concrete mix of 1 2 4 (1 cement 2 sand 4 aggregate 20mm) well vibrated, compacted, fixed to correct level and finished smooth and cured by keeping surfaces well- covered and protected against excesses of any type, all complete at all heights and leads to the satisfaction. Laying the same in proper line level on the seating area s floor to maintain the floor levelling to get the smooth surface to lay the finishing floor materials on the said surface. Complete as per architectural detail drawings instruction by the site engineer. | Sq. Mtr.
III | CIVIL FINISHES WORK
FLOORING
3.1 | Italian Marble Flooring | smt
Clean existing sub floor thoroughly. Flooring shall consist of Marble as per drawing, Up to 50 mm thick bedding mortar as per tech specs. Marble slabs shall be minimum 18 mm thick, laid as per tech specs, Marble to be cut as per size and laid with tight hairline joints. Joint filling and finishing as per tech specs.(On site cost of Italian marble @ Rs.450 sft without tax) including Approved sealer to be applied on all sides, Including sealer coat , Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover
a | Ladies toilet flooring | 1 | 5.77 | 4.9 | 28.273
b | Less duct area | -1 | 0.83 | 1.75 | -1.4525
c | Handicap Bathroom | 1 | 2.5 | 2.2 | 5.5
d | Gents toilet | 1 | 4.15 | 7.77 | 32.2455
e | less WC ledge | -3 | 1.235 | 0.15 | -0.55575
f | Common Bathroom Passage | 1 | 4.38 | 1.58 | 6.9204
g | Staff bathroom floor | 2 | 1.25 | 2.4 | 6
76.9306
3.2 | Italian Marble Flooring on Ramp in Strip Form | smt
Clean existing sub floor thoroughly. Flooring shall consist of Marble in strips form as per drawing, At least 50 mm thk bedding mortar as per tech specs. Marble slabs shall be minimum 18 mm thick, laid as per tech specs. Marble to be cut as per size and laid with tight hairline joints. Joint filling and finishing and mirror polishing as per tech specs. Including 4mm thick x12 mm wide SS satin copper finish strip inserts in the flooring at 75 100 mm c c ,(On site cost of Italian marble @ Rs.450 sft without tax) including Approved sealer to be applied on all sides, Including sealer coat, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover
3.2 | Vitrified tile Flooring for staff toilet | smt
Clean existing sub floor thoroughly before fixing Vitrified tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.150 sft without tax
3.4 | Kota Stone Flooring for Corridor service Area | smt
P F of 19mm thick Kota Stone flooring (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, Kotah to be laid with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for kitchen service area.
3.5 | Granite Stone Ramp Flooring for Service corridor | smt
P F of 18mm thick leather finished jet black granite flooring on the ramp with 100mm wide (selected approved make, basic cost INR. 2690.00 SM) in stroke pattern to get the desired grip. Stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, cleaning, etc. to required line, level, etc. all complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, chamfer of edges, etc. Complete in proper line level as per site engineer s instruction. It is for the back kitchen entrance area
CLADDING
3.6 | Synthetic Marble Wall Cladding with Grooves | smt
Clean existing wall surface before fixing wall cladding. Slabs shall be min. 18 mm thick fixed to plastered siporex block work, Slabs shall be installed as per tech specs on plastered wall siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3mm V grooves, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Synthetic marble @ Rs.275 sft without tax)
a | Ladies WC Front wall "A" | 1 | 3.97 | 2.25 | 8.9325
b | Less doors of bathroom (-) | -3 | 0.72 | 2.25 | -4.86
c | WC Inside 4 wall "B" | 3 | 6.62 | 2.25 | 44.685
d | Ladies dressing front wall "C" | 1 | 3.5 | 2.25 | 7.875
e | Less door (-) | -1 | 0.7 | 2.25 | -1.575
f | Less opening (-) | -1 | 1.13 | 2.25 | -2.5425
g | Ladies changing room inside 4 wall | 1 | 5.47 | 2.25 | 12.3075
h | Right & Left wall "D" | 2 | 1.8 | 2.25 | 8.1
i | Bath side wall "E" | 1 | 1.445 | 2.25 | 3.2513
j | Entry gate side wall "F" | 1 | 1.7 | 2.25 | 3.825
k | Handicap toilet 1 | 2 | 2.16 | 3 | 12.96
l | Handicap toilet 2 | 2 | 2.63 | 3 | 15.78
m | Less Door (-) | -1 | 1 | 2.25 | -2.25
n | Gents WC Front wall "L" type | 1 | 5.625 | 2.25 | 12.6562
o | Less doors of bathroom (-) | -3 | 0.72 | 2.25 | -4.86
p | WC Inside 4 wall | 3 | 5.32 | 2.25 | 35.91
q | Gents Bathroom Wash basin to till door | 1 | 4.03 | 2.25 | 9.0675
159.2625
3.7 | Italian Marble Wall Cladding for in strip format | smt
Clean existing wall surface before fixing wall cladding, Marble shall be minimum 18 mm thick fixed to Fire rated plywood panelling plastered wall siporex block work, Marble shall be cut from slabs of even thickness, Marble shall be installed with suitable adhesive, if installed on plywood, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. Including up to 3 mm V grooves chamfer edge moulding, mirror polished and finished. including Approved sealer to be applied on all sides (On site cost of Italian marble @ Rs.450 sft without tax)
| D7 right side wall | 1 | 1.255 | 3.25 | 4.0787
| Ladies side wall | 1 | 4.2 | 3.01 | 12.642
| Gents side wall | 1 | 4.355 | 3.01 | 13.1086
| Less Door (-) | -2 | 0.83 | 2.12 | -3.5192
| Handicapped wall | 1 | 1.56 | 3.01 | 4.6956
| Less Door (-) | -1 | 0.83 | 2.1 | -1.743
| Corridor long wall till ramp | 1 | 2.58 | 3.25 | 8.385
| Dirty Garbage "C" type 3 wall | 1 | 10 | 3.5 | 35
| Corridor left side wall | 1 | 4.01 | 3.25 | 13.0325
| Step side | 1 | 2.32 | 3.5 | 8.12
93.8002
3.8 | Jointless ceramic tiles cladding ( for staff toilet Service Corridor ) | smt
Cladding shall comprise of ceramic tile of 600 mm x 300 mm, Tiles to be fixed in ordinary Portland cement only, Tiles to be put with Spacer required with Leticrete grout in joints in plumb, including levelling coat if any , Joints to be filled with matching grout.(Basic cost of ceramic tiles at Rs.60 sft) make Johnson Somany Kajaria Nitco
| Long wall 2 nos bath room wall Both side | 2 | 2.4 | 2.35 | 11.28
| Less Door (-) | -2 | 0.7 | 2.25 | -3.15
| Bathroom small wall both side | 2 | 1.25 | 2.35 | 5.875
0
0
14.005
3.9 | Decorative Glass Mosaic Tiles In General Toilets ( customize design ) | smt
Clean existing wall surface before fixing Glass Mosaic tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. Basic cost of mosaic tiles at Rs.1200 sft without tax
| Ladies toilet main wall | 1 | 3.475 | 3 | 10.425
| Gents urinal right-side wall | 1 | 2.6 | 3 | 7.8
| Gents Washbasin left side wall | 1 | 2.65 | 3 | 7.95
26.175
3.10 | Plain Glass Mosaic Tile Wall Cladding | smt
Clean existing wall surface before fixing Glass Mosaic tile, Before starting, carefully read the suppliers laying plan and instructions. Decorative mosaic tiles shall be fixed and finished as per manufacturers instructions, preferably by a nominated contractor. (Basic cost of mosaic tiles at Rs.450 sft without tax)
| Ladies wash basin wall | 1 | 3.95 | 3 | 11.85
| Dressing wall | 1 | 1.8 | 0.75 | 1.35
| Dressing wall to duct | 1 | 6.15 | 0.75 | 4.6125
| Wc "L" shape wall | 1 | 6.2 | 0.75 | 4.65
| Gents Urinal wall | 1 | 6.75 | 0.75 | 5.0625
| Wash basin right side wall | 1 | 0.9 | 2.25 | 2.025
| Wc "L" shape wall | 1 | 6.5 | 0.75 | 4.875
| Wash basin wall | 1 | 2.85 | 3 | 8.55
| Hand dryier wall | 1 | 1.28 | 0.75 | 0.96
|  | 1 | 4.07 | 0.7 | 2.849
| Hnadi capped dryer wall side | 2 | 2.15 | 0.75 | 3.225
|  | 2 | 2.6 | 0.75 | 3.9
[5 empty] | 53.909 | 80.084
3.11 | Synthetic Marble Jamb lining for common Toilet Door Openings | rmt
Marble jamb lining for EWC doors including rebate, up to 230 mm wide, up to 2250 mm ht all around, At least 18 mm thk per-polished slabs to be used, Slabs to be cut as per approved size drawings, Include mitre joints at all junctions as per Architects instructions, Including V groove to match wall cladding, Marble to be fitted with white cement only, Marble shall be installed as per tech specs on plastered siporex block work, Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides (Basic cost of Synthetic Marble at Rs.275 sft without tax)
| Ladies bathroom wc | 12 | 2.25 |  | 27
| Ladies bathroom wc | 12 | 2.25 |  | 27
54
3.12 | Granite jamb lining Door Openings | rmt
Granite for kitchen doors including rebate, up to 250 mm wide, up to 2250 mm ht all around, At least 18 mm thk per-polished Granite to be used. Granite to be cut as per approved size drawings. Include mitre joints at all junctions as per Architects instructions, Granite shall be installed as per tech specs on plastered siporex block work, Moulding to Granite edge as approved including polish, Joint filling and finishing and mirror polishing as per tech specs. (Basic cost of Granite at Rs.200 sft without tax)
3.13 | Granite Architrave for Door Openings | rmt
50 mm wide Granite Architrave for kitchen back office doors , At least 18 mm thk per-polished Granite to be used. Include mitre joints at all junctions as per Architects instructions, Granite shall be installed as per tech specs on plastered siporex block work, Moulding to Granite edge as approved including polish, Joint filling and finishing and mirror polishing as per tech specs. (Basic cost of Granite at Rs.200 sft without tax)
3.13a | 150 mm high Kotah Finish Skirting | rmt
P F of 19mm thick Kota Stone Skirting , stone to be machine cut, machine polished, fixed with cement paste including cleaning and preparing the surface of wall, Kotah to be fixed with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. as per site engineer s instruction. It is considered for service area.
COUNTER AND LEDGES
3.14 | Italian Marble Finish Wash Basin Counter for Common toilet | rmt
The counter shall be supported on 38mm x 38mm x 5mm thk MS angle fixed to block work. Brackets shall be inserted within wall by at least 125mm, MS brackets shall be coated with 2 coats of anti-corrosive paint and 3 coats of synthetic enamel paint, 18mm thk ordinary Indian marble placed within bracket and screwed through bracket, At least 20mm thk cement mortar bedding in 1 4 ratio, Pre-finished and pre-polished marble slabs shall be fixed as per tech specs. Counter shall have up to 300 mm wide fascia marble with mitre joints All top edges of counter shall have chamfer moulding. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides. Including all plumbing cutout as shown in drawing
(Basic cost of marble at Rs.450 sft including fibber filling polish)
| Ladies Wash Basin Counter | 1 | 3.93 |  | 3.93
| Gents Washbasin counter | 1 | 2.85 |  | 2.85
| Napi counter | 1 | 1.45 |  | 1.45
8.23
3.15 | Synthetic Marble Ledges for all WC | rmt
Using 18mm thick marble top, Including 2 high Marble fascia, Pre-polished finish marble shall be installed as per tech specs. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides.
(Basic cost of Synthetic Marble at Rs.275 sft without tax)
| Ladies Wc Ledge wall top | 3 | 1.25 |  | 3.75
| Handicapped ledge wall | 1 | 2.16 |  | 2.16
| Staff bathh ledge wall top | 2 | 1.25 |  | 2.5
| Gents Wc Ledge wall top | 3 | 1.25 |  | 3.75
12.16
3.16 | Synthetic Marble Dressing Vanity Ledge in Common Ladies toilet | rmt
Using 18 mm thick marble top, including 2 high Marble fascia, Pre-polished finish marble shall be installed as per tech specs. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides
(Basic cost of Synthetic Marble at Rs.275 sft without tax)
3.17 | Urinal Divider for Gents Toilet | nos
Overall size 2000 mm x 400 mm, in approved profile. Frame in 25mmx25mm SS finish pipe in glossy matt copper finish in profile to be approved by Architects, Insert of 18 mm synthetic marble slabs pre-polished on both sides including Approved sealer to be applied on all sides (Basic cost of Marble at Rs.275 sft without tax)
| Urinal divider | 4 |  |  | 4
3.16 | Granite Ledge in Janitor room | rmt
Using 18 mm thick marble top, including 2 high Marble fascia, Pre-polished finish marble shall be installed as per tech specs. Joint filling and finishing and mirror polishing as per tech specs. including Approved sealer to be applied on all sides
(Basic cost of Synthetic Marble at Rs.200 sft without tax)
IV | FRENCH PLASTER WORK
4.1 | Fire line Gypsum board ceiling | smt
All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c, 12.5 mm thk Gypsum board to be used manufactured by Saint Gobin Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibber tape reinforcement, Include finished cutouts for light fixtures, AC grills including necessary framework ply support , Include horizontal structural member to span below HVAC ducting for ceiling suspenders ( Note - existing structural ceiling height is 4300 mm )
Ladis toilet
| Ceiling | 1 | 6.25 | 5.64 | 35.25
| Less column (-) | -1 | 1.05 | 5.35 | -5.6175
Handicap Toilet
| Ceiling | 1 | 2.133 | 2.712 | 5.7847
Gents toilet
| Ceiling | 1 | 4.572 | 7.09 | 32.4155
Toilet entry Corridor
|  | 1 | 3.505 | 1.346 | 4.7177
|  | 1 | 4.267 | 3.048 | 13.0058
|  | 1 | 2.946 | 1.346 | 3.9653
|  | 1 | 1.524 | 4.318 | 6.5806
96.1022
4.2 | Fire line Gypsum board Facia Band 50 mm | rmt
All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibber tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum
| Gents | 1 | 19.8 |  | 19.8
| Ladies | 1 | 18.23 |  | 18.23
38.03
4.3 | Indirect Light Coves in Ceiling | rmt
In L shape with 100 mm deep up to 300mm high and 50 mm wide fascia, All G.I framework for ceiling to be used manufactured by GYPSteel only, 12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only, Gypsum Board sheets shall be fitted finished as per manufacturer s specification, All joints to be filled with jointing compound including fibber tape reinforcement, Include finished cutouts for, AC grills including necessary framework ply support required, Exclude painting, Only fire line Gypsum
| Gents | 1 | 22.86 |  | 22.86
| Ladies | 1 | 21.33 |  | 21.33
44.19
4.4 | Shadow groove in ceiling | rmt
providing and Fixing ready made powder coated aluminium profile up to 18 mm x 18 mm as approved by Architect
4.5 | Universal plaster punning on wall | smt
Average 12 mm thk Universal plaster punning by Gyproc Stucco, Tile bull marks to be used for channel gliding tracks, Bull marks to be removed before apply punning, Surface to be in perfect plum, line and level, Include pencil rounding to wall corners as instructed, Smooth finished to receive finishing coating, Exclude painting work.
a | Water lounge corridor staff toilet entry wall | 1 | 5.2 | 3.8 | 19.76
b | Less doors (-) | -2 | 0.78 | 2.53 | -3.9468
c | Less offset (-) | -1 | 1.2 | 1 | -1.2
d | Electric room and janitor room divider wall (A) | 2 | 1.4 | 2.6 | 7.28
e | Electric room panel backside wall (B) | 1 | 2.85 | 2.6 | 7.41
f | Electric room left side panel wall (C) | 1 | 1.4 | 2.6 | 3.64
g | Electric entry wall from inside (D) | 1 | 1.4 | 2.6 | 3.64
h | Less door (-) | -1 | 1.45 | 2.05 | -2.9725
IV | Fire panel backside and right-side wall "E" | 1 | 1.9 | 2.119 | 4.0261
| corridor | 1 | 21.19 | 3.15 | 66.7485
104.3853
V | CARPENTRY WORK
5.1 | P F of 304 grade 3mm thick SS Corner guard (30mm x 30mm, hairline matt finished as per approved sample) fixing with SS full thread screws on each corner of the kitchen s wall after cladding of tiles, so that the corner may be protected from the damages, including cleaning, etc. Complete in proper line level as per site engineer s instruction. It is for the back kitchen area. | rmt
5.2 | Frosted Glass Screen with satin Glossy Copper Finish SS Frame in Toilets | smt
| Frosted, textured, toughened and laminated glass overall 10 mm thick, as per samples approved by Architect. All glass edges to be fine cut and polished and sealed. The glass shall be fitted into a rebate of special fabricated 16G 304 grade SS copper finish frame of 50mmx50mm, as approved by Architect. The entire assembly shall be fitted on wall and floor with proper accessories and protected till handover. | 1 | 2.2 | 2.3 | 5.06
5.3 | SS satin Glossy Copper Finish Band in Toilets | rmt
SS satin Glossy Copper finish sheet 304 grade, minimum 16 gauge thk. cladding on the ply with joints as required by Architect. The C shape SS band shall be 50 mm wide with turned in sides up to 25 mm and shall be fixed on 12 mm marine ply band fixed to wall and jambs. SS sheets fixed with recommended adhesive including protection film till handover
| Ladeise toilet wc side | 1 | 3.92 |  | 3.92
| Changing room inside | 1 | 5.94 |  | 5.94
| Wc inside | 3 | 5.14 |  | 15.42
| Entranmce Rectengle | 1 | 8.36 |  | 8.36
| Gents Toilet Wc side | 1 | 4.1 |  | 4.1
| Napi change side | 1 | 1.56 |  | 1.56
| Door entrance Wash basin to urinal side | 1 | 9.785 |  | 9.785
| Wc inside | 3 | 5.12 |  | 15.36
0
64.445
5.4 | Decorative Toilet Vanity Mirrors in Oval Circular Rectangular Shapes | smt
The mirrors shall be mounted on a backing of aluminium framework and marine ply of overall 30 to 40 mm thickness, which shall be fixed to the wall. Including provision for LED strip light. Mirror shall be 8 mm thick to receive bevelling and shall be laminated at the back for protection, and backed with felt lining. All Mirrors shall have 18-25 mm bevelling on all edges. All edges of mirror shall have CNC edge polish, Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect. exclude cost of LED strip lighting
| Ladies | 3 | 0.61 | 1.1 | 1.83
| Gents | 3 | 0.61 | 1.1 | 1.83
| Handicapped | 1 | 0.7 | 1.2 | 0.7
4.36
5.5 | Plain mirror panelling ( dressing room ) | smt
The mirrors shall be mounted on a backing of marine ply of overall 18 mm thickness, which shall be fixed to the wall. Including L shape SS finish Angle profile covering on All around the mirror. Mirror shall be 8 mm thick to receive bevelling and shall be laminated at the back for protection, and backed with felt lining. All Mirrors shall have 18-25 mm bevelling on all edges. All edges of mirror shall have CNC edge polish. Mirrors shall be fixed to the backing ply with recommended adhesive or tape as approved by the Architect.
| Ladires changing room inside | 1 | 0.65 | 2.05 | 0.65
|  | 1 | 1.05 | 1.63 | 1.05
1.7
DOORS
5.6 | Toilet Main Doors in Timber and Veneer Finish- D1 | nos
Overall size 1000 mm x 2250 mm ht 900 mm x 2250 mm ht
Door frame
Overall size 275 mm wide x 50 mm thick x 2250 ht Door frame to be Made up Using 18 mm thick marine ply as rough ground, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk NBTW wood, Rebate to be separately put in NBTW wood, Wood to be treated with anti-termite medicine,
Shutter
Overall size 900 mm wide x 2200 mm ht. x 1 leaf, up to 59 mm thk, Using 35 mm thick readymade fireproof shutter covered with 8 mm thick marine ply on both sides , The shutter shall be clad with 4 mm thick approved veneer on both sides including NBTW beading all around. basic cost of veneer up to Rs. 125 sft
Polish
Frame entire door to be Finished in Approved water base PU polish
Hardware
The shutter shall be mounted on min. 3 nos. bearing SS finished hinges with proprietary screws, made by Hafele Dorma or equivalent approved by Architect. The shutter shall have a “Dorma” concealed door closer. Include a set of lock and approved handle,( basic cost of handle Rs. 8,000 pair )
| Ladies & Gents | 2 |  |  | 2
5.7 | Disabled Toilet Entrance Door (Sliding) D-3 ( electronic operated ) | nos
Size 1050mm x 2250mm
Door frame
Overall size 275 mm wide x 50 mm thick x 2250 ht Using Door frame to be Made up Using 18 mm thick marine ply as rough ground, fixed to masonry wall in perfect plumb, line and level by using 6 long Hilti Anchor bolt (total 6 nos - 3 nos each side), Clad with 12 mm thk NBTW wood, Rebate to be separately put in NBTW wood, Wood to be treated with anti-termite medicine,
Openable Pelmet
Pelmet to be made out of Using 18 mm thick ply with Pelmet to be covered with 4 mm thk approved veneer with 0.50 mm thk wooden face pressed on outside and approved 1 mm thk laminate pressed inside, including matching
Shutter
Overall size 950 mm wide x 2250 mm ht. x 1 leaf, up to 59 mm thk. Using 35 mm thick readymade fireproof shutter covered with 8 mm thick marine ply on both sides , The shutter shall be clad with 4 mm thick approved veneer on both sides including NBTW beading all around. basic cost of veneer up to Rs. 125 sft
Polish
Frame , All wood Veneer to be Veneer to be Finished in Approved water base PU polish
Hardware
Sliding channel system by HAWA hafle dorma with bottom guide concealed within sliding shutter (Note No guide shall be fixed on floor), Concealed handle for sliding shutter, as approved, Concealed sliding lock with knob on inside, (Basic cost of concealed sliding handle at Rs.2500 - per set),
| Handicapped bathroom | 1 |  |  | 1
5.8 | WC Cubicle Shutter in Laminate Finish in Toilets D-2 | nos
Shutter
Overall size 700 mm wide x 2250 mm ht.x 53 mm thick, Using 35 mm thick readymade fireproof shutter to be covered with 8 mm thick ply from both side including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side ( basic cost of laminate sheet Rs 1600 sheet )
Hardware
Min. 3nos. SS hinges, and lock, handle and indicator set with 1 double robe hook, by Hafele Dorma or equivalent approved,
| Ladies & Gents | 7 |  |  | 7
5.9 | WC Cubicle Shutter in Laminate Finish in Toilets D-2a | nos
Shutter
Overall size 800 mm wide x 2250 mm ht.x 53 mm thick, Using 35 mm thick readymade fireproof shutter to be covered with 8 mm thick ply from both side including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side ( basic cost of laminate sheet Rs 1600 sheet )
Hardware
Min. 3nos. SS hinges, and lock, handle and indicator set with 1 double robe hook, by Hafele Dorma or equivalent approved,
| Staff | 2 |  |  | 2
5.10 | 2 Way Double Door in Laminate Finish with Vision Panel D-7 ( for Kitchen toilet Corridor ) | nos
Shutter
Overall size 1500 mm wide x 2250 mm ht.x 53 mm thick, Using 35 mm thick readymade fireproof shutter to be covered with 8 mm thick ply from both side including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side. ( basic cost of laminate sheet Rs 1600 sheet )
Vision panel
400 mm dia, 8 mm thk toughened glass vision panel including 16SWG 304 grade SS finish Profile as approved by architect
Hardware
300 mm x 200 mm x 2 nos Handle push plate. hafle dorma Heavy duty floor spring. 300 mm high, 16 G 304 grade SS Kick plate fixed to door on both side with suitable adhesive Including locks, etc. complete
| Staff | 1 |  |  | 1
5.11 | Door in Laminate Finish with Vision Panel ( for Garbage Janitor room ) | nos
Shutter
Overall size 900 mm wide x 2250 mm ht.x 53 mm thick, Using 35 mm thick readymade fireproof shutter to be covered with 8 mm thick ply from both side including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side. ( basic cost of laminate sheet Rs 1600 sheet )
Vision panel
400 mm dia, 8 mm thk toughened glass vision panel including 16SWG 304 grade SS finish Profile as approved by architect
Hardware
300 mm x 200 mm x 2 nos Handle push plate. hafle dorma Heavy duty floor spring. 300 mm high, 16 G 304 grade SS Kick plate fixed to door on both side with suitable adhesive Including locks, etc. complete
| Janitor & Electrical room | 3 |  |  | 3
5.12 | Lockers | sqmt
OVERALL SIZE 2100 MM HIGH X 350 M DEEP
size 400x400 mm division - CARCASS SHUTTER 18 MM thk. Prelaminated PB board with PVC Edge band With openable Shutter including handle as approved by architect, lock etc. completed . BACK 12 MM thk. Prelaminated PB board with PVC Edge band.
5.13 | Shaft Door | nos
Shutter
Overall size 600 mm wide x 1800 mm ht.x 37 mm thick, Using 35 mm thick readymade fireproof shutter to be used including NBTW beading all around. The shutter shall be clad with 1 mm thick approved Laminate from both side ( basic cost of laminate sheet Rs 1600 sheet )
Hardware
Min. 3nos. SS hinges, and lock, handle
VI | SANITARY CP FITTINGS - ONLY FIXING
COMMON LADIES AND GENTS TOILET
6.1 | WC for common toilet | nos
6.2 | Flush tank | nos
6.3 | Flush plate | nos
6.4 | Wash basin - Gents | nos
6.5 | Wash basin - Ladies | nos
6.6 | health faucet for WC | nos
6.7 | wash basin faucet | nos
6.8 | toilet paper holder | nos
6.9 | hand dryer | nos
6.10 | tissue paper holder | nos
6.11 | Napi change ledge | nos
6.12 | Urinals | nos
6.13 | Urinals censor plates | nos
6.14 | Soap dispenser | nos
6.15 | Robe hook | nos
6.16 | Dust bin | nos
6.17 | Flush tank | nos
6.18 | Flush plate | nos
6.19 | handicap WC | nos
6.20 | Wash basin - Handicap | nos
6.21 | wash basin faucet for handicap | nos
6.22 | toilet paper holder | nos
6.23 | hand dryer | nos
6.24 | tissue paper holder | nos
6.25 | Grab bar for handicap toilet | nos
6.26 | Soap dispenser | nos
6.27 | Robe hook | nos
6.28 | Dust bin | nos
VII | PAINTING WORKS
7.1 | Painting to walls in pearl luster | smt
Sanding and preparing surface for receiving primer, One coat of cement primer in solvent base, Two coats of putty in water synthetic enamel base, Three coats of luster paint in approved shed, Complete as per manufacturer s specifications
7.2 | Painting to ceiling in acrylic emulsion paint | smt
Sanding and preparing surface for receiving primer, One coat of cement primer in solvent base, Two coats of putty in water synthetic enamel, Three coats of acrylic emulsion paint in approved shed, Complete as per manufacturer s specifications
|  | 1 | 2.62 | 2.13 | 5.5806
|  | 1 | 5.7 | 5.05 | 28.785
|  | 1 | 4.8 | 0.75 | 3.6
|  | 1 | 4.1 | 0.75 | 3.075
| Deduction | -1 | 1.05 | 1 | -1.05
|  | 1 | 4.13 | 6.72 | 27.7536
|  | 1 | 3.23 | 0.75 | 2.4225
|  | 1 | 5.82 | 0.75 | 4.365
68.9511
CIVIL WET WORK
CIVIL-WET WORK
1.1 | 200 mm thick solid concrete block work | SQM
Walls to start from floor slab up to 4300 mm height
Include 100 mm high RCC lintel at 1.5m, 3.0m with 6nos x 8 mm MS twisted bars and 6 mm MS rod rings at 150 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel )
8 mm MS bar grade FE 500
Only 43 or 53 grade Cement Adhesive to be used
Cement mortar in 1 4 ratio, minimum 12mm thk
Constructed In perfect plum, line and level
Wall to be cured for at least 3 days
including scaffolding and staging etc. complete.
25 mm gap between block wall and slab shall be filled with expandable foam
B00B01-TFS-I_ID-DOM-0A-DWG-0001
1.2 | 200 mm thick Aerocon block wall | SQM
Walls to start from floor slab up to 4300 mm height
Include 200 mm high RCC Patli to be after every 5 layers above doors with 6nos x 8 mm MS twisted bars and 6 mm MS rod rings at 150 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel )
8 mm MS bar grade FE 500
Only 43 or 53 grade cement Adhesive to be used
Cement mortar in 1 4 ratio, minimum 12mm thk
Constructed In perfect plum, line and level
Wall to be cured for at least 3 days
including scaffolding and staging etc. complete.
25 mm gap between block wall and slab shall be filled with expandable foam
B00B01-TFS-I_ID-DOM-0A-DWG-0001
1.3 | 150 mm thick solid concrete block work | SQM
Include 150 mm high RCC lintel at 1.8m, 3.6m above doors with 4nos x 8 mm MS twisted bars and 6 mm MS rod rings at 150 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel )
8 mm MS bar grade FE 500
Only 43 or 53 grade Cement Adhesive to be used
Cement mortar in 1 4 ratio, minimum 12mm thk
Constructed In perfect plum, line and level
Wall to be cured for at least 3 days
including scaffolding and staging etc. complete.
25 mm gap between block wall and slab shall be filled with expandable foam
B00B01-TFS-I_ID-DOM-0A-DWG-0001
1.4 | 150 mm thick solid Aerocon block wall
Walls to start from floor slab up to 4300 mm height
Include 150 mm high RCC Patli to be after every 5 layers above doors with 4nos x 8 mm MS twisted bars and 6 mm MS rod rings at 100 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel )
8 mm MS bar grade FE 500
Only 43 or 53 grade Cement Adhesive to be used
Cement mortar in 1 4 ratio, minimum 12mm thk
Constructed In perfect plum, line and level
Wall to be cured for at least 3 days
including scaffolding and staging etc. complete.
25 mm gap between block wall and slab shall be filled with expandable foam
B00B01-TFS-I_ID-DOM-0A-DWG-0001
1.5 | Building 100 mm thk. Aerocon block wall | smt
Walls to start from floor slab up to 4300 mm height
Include 100 mm high RCC Patli to be after every 5 layers above doors with 4nos x 8 mm MS twisted bars and 6 mm MS rod rings at 150 mm c c. Concrete in 1 2 4 ratio, incl. shuttering. ( including door opening lintel )
8 mm MS bar grade FE 500
Only 43 or 53 grade Cement Adhesive to be used
Cement mortar in 1 4 ratio, minimum 12mm thk
Constructed In perfect plum, line and level
Wall to be cured for at least 3 days
including scaffolding and staging etc. complete.
25 mm gap between block wall and slab shall be filled with expandable foam
B00B01-TFS-I_ID-DOM-0A-DWG-0001
1.6 | Raised flooring in Brick bat Coba
Providing waterproofing treatment to Slab (India water proofing or alike) Light weight block filling with cement mortar. Top to be finished with 60-70mm 1 2 4 screed, mixed with water proofing compound etc.
Floor surface to be cleaned of any dust particles
Surface to be watered well before laying blocks
Only 43 or 53 grade cement to be used
Cement mortar in 1 4 ratio, minimum 12mm thk
Blocks shall be laid with alternate joints
Cured for at least 3 days
Slope to be maintained as per drawing
B00B01-TFS-I_ID-DOM-0A-DWG-0001
| 150 mm thick | smt
| 250 mm thick | smt
| 300 mm thick | smt
1.7 | Construction of ramp using Aerocon block
Floor surface to be cleaned of any dust particles
Surface to be watered well before laying blocks
Only 43 or 53 grade cement to be used
Cement mortar in 1 4 ratio, minimum 12mm thk
Ramp block shall start from slab level height shall increase gradually match raised flooring height
Blocks shall be laid with alternate joints
Cured for at least 3 days
B00B01-TFS-I_ID-DOM-0A-DWG-0001
| 0 to 150 mm thick | smt
| 0 to 250 mm thick | smt
| 0 to 300 mm thick | smt
1.8 | Applying cement plaster to NEW wall | smt
Wall surface to be free from any loose particles before plastering
Surface to be watered well before plastering
Only river sand to be used free of minerals salts
Sand shall be fine fibred before using
Only 43 or 53 grade cement to be used
Cement mortar in 1 4 ratio, up to 20mm thk.
Include 600 m wide PVC chicken mesh on junctions of RCC and brick siporex wall
In perfect plum, line and level
Smooth lined surface as instructed
Plaster to be cured for at least 3 days
| Applying cement plaster to EXISTING wall | smt
1.9 | PCC screed on slab ( grade M15 ) | smt
Clean slab surface before laying mortar
Aggregate of 0 and 1 no. size to be used
At least average 75 mm thk (min. 50 mm ) mortar in 1 2 4 ratio
Coba shall not cover raceway junction box
Coba to be cured for at least 3 days
1.10 | Chemical waterproofing over walls
Providing and laying proprietary chemical water proofing system consisting of polymer modified acrylic base coating in two coats in form of slurry (total consumption of 1.5 Kg Sqm) as approved by the PM and as directed by the approved manufacturer of waterproofing coating, with sandwiched fibre mesh and protective screed. The work shall include cleaning of surface, grouting porous surfaces including making ‘V’ grooves at junctions, cracks with non shrink crystalline base cementitious grout etc. Further including horizontal and vertical surfaces protected with 20mm screeding in 1 4 mortar (1 cement 4 sand), finished in ready to receive Architectural finish, in correct line, level and plumb, curing, grouting, testing, etc. all complete to entire satisfaction of the PM, contractor to provide guarantee for 10 years Rs.100 - stamp paper in approved proforma. MAKE WPM 002-AROEX ENDURA. CONTRCTING HAS TO FOLLOW THE DETAILED METHODOLOGY OF THE MANUFCATURERS INSTRUCTION. ONLY FOR WET AREA.
Waterproofing to wrap up on the walls up to 900 mm height
Vendor to submit brand specifications for approval
Waterproofing shall be done within plumbing chases before installing pipes and after filling chases with cement plaster
| For Toilet and Kitchen | smt
| SPA room floor | 1 | 2.55 | 1.2 | 3.06
| SPA Bathroom walls |  |  |  | 0
| R | 1 | 2.55 | 0.9 | 2.295
| F | 1 | 1.2 | 0.9 | 1.08
| L | 1 | 2.55 | 0.9 | 2.295
| E | 2 | 1.2 | 0.9 | 2.16
| Door edges | 2 | 0.2 | 0.9 | 0.36
| Less door | -1 | 0.75 | 0.9 | -0.675
| Basin wall | 1 | 1.77 | 0.9 | 1.593
| Basin area flooring | 1 | 1.77 | 1.2 | 2.124
| Duct wall | 1 | 1.2 | 0.9 | 1.08
| Floor raise | 1 | 0.2 | 1.77 | 0.354
| Sports Bar |  |  |  | 0
| Sports bar floor | 1 |  |  | 0
| Sports bar walls and counter |  |  |  | 0
| Curved wall | 1 | 27.05 | 0.9 | 24.345
| Spots bar front wall (B) | 1 | 7.75 | 0.9 | 6.975
| Less door | -1 | 0.9 | 0.7 | -0.63
| water lounge |  |  |  | 0
| Whole water lounge area (D x E) | 1 | 13.475 | 6.8 | 91.63
| Less Duct area (F) | -1 | 6.075 | 1.4 | -8.505
| Walls |  |  |  | 0
| G | 1 | 2.262 | 0.9 | 2.0358
| H | 1 | 4.395 | 0.9 | 3.9555
| J | 1 | 6.8 | 0.9 | 6.12
| K | 1 | 4.2 | 0.9 | 3.78
| Less Duct area (F) | 1 | 1.6 | 0.9 | 1.44
| M | 1 | 7.3 | 0.9 | 6.57
| N | 1 | 5.1 | 0.9 | 4.59
| O | 1 | 6.2 | 0.9 | 5.58
| Less doors | -1 | 1.8 | 0.9 | -1.62
[5 empty] | 13.0063 | check with masle
174.9986
1.11 | Membrane waterproofing on floor walls in Kitchen toilets | smt
Up to 3mm thk. membrane sheet, manufactured by reputed brand
Slab to be dust free before starting process
1 4 ratio cement mortar with waterproofing compound
Membrane to be installed by Bonafide approved installer
Installation to be carried strictly as per manufacturer s specifications
Waterproofing to wrap up on the wall, up to 900 mm ht
Waterproofing shall be warranted for 10 years on Rs.100 - stamp paper
1.12 | Jointless ceramic tiles cladding ( for Garbage station ) | smt
Cladding shall comprise of ceramic tile of 600 mm x 300 mm, Tiles to be fixed in ordinary Portland cement only, Spacer required with Leticrete grout in joints. in plumb, including levelling coat if any , Joints to be filled with matching grout.(Basic cost of ceramic tiles at Rs.60 sft) make Johnson Somany Kajaria Nitco
1.13 | P F of 19mm thick Kota Stone flooring (selected approved grey colour - size, 550mm x550mm, basic cost INR. 538.00 SM), stone to be machine cut, machine polished, laid in pattern and sizes as detailed in drawing, bedded over cement sand mortar of mix ratio of 1 6 (1 cement 6 sand) including cleaning and preparing the surface for bedding, Kotah to be laid with tight hairline joints , joints to be cleaned and grouted with matching colour approved quality Epoxy based readymade grout, curing, machine polishing, cleaning, etc. complete at all depths, heights and leads to the satisfactions, necessary cut out for services purpose, etc. Complete in proper line level as per site engineer s instruction. It is considered for kitchen service area. | smt
B00B01-TFS-I_ID-DOM2-0A-DWG-0004
1.14 | P F of 304 grade 3mm thick SS Corner guard (50x50x2mmthick SS angles) fixing with SS full thread screws on each corner of the kitchen s wall after cladding of tiles, so that the corner may be protected from the damages, including cleaning, etc. Complete in proper line level as per site engineer s instruction. It is for the back kitchen area. | rmt
II | CEILING AND POP
2.1 | Fire line Gypsum Board ceiling | smt
All G.I framework for ceiling to be used manufactured by GYPSteel only at 400 mm c c suspenders, closer at 1200 mm c c
12.5 mm thk Gypsum board to be used manufactured by India Gypsum Board or La Farge only
Gypsum Board sheets shall be fitted finished as per manufacturer s specification
All joints to be filled with jointing compound including fibre tape reinforcement
Include finished cutouts for light fixtures, AC grills including necessary framework ply support
Include 3 mm thk gyp veneer coat on gypsum board (3 mm thk jointing compound filled like punning on wall)
Include horizontal structural member to span below HVAC ducting for ceiling suspenders
Exclude painting
Only fire line Gypsum
B00B01-TFS-I_ID-DOM-0A-DWG-0006
2.2 | Universal plaster punning on wall | smt
Average 12 mm thk Universal plaster punning by Gyproc Stucco
Tile bull marks to be used for channel gliding tracks
Bull marks to be removed before apply punning
Surface to be in perfect plum, line and level
Include pencil rounding to wall corners as instructed
Smooth finished to receive finishing coating
Exclude painting work
2.3 | P F of metalized grid ceiling with selected approved Armstrong or eqv. make metal sheet (suspended lay-in square Armstrong metal ceiling, standard plain square tiles of 600mm x 600mm in off white colour, exposed grid white Armstrong metal false ceiling, thickness 0.5 mm, surface treatment in galvanized, off white colour coated, features -water proof, corrosion resistant - basic cost INR. 1345.00 SM) and section (as per approved sample) with grid section framework, frame work should be hanged from the existing slab as per manufacture s instruction, including scaffolding, all necessary hardware fittings etc., making provision for lighting, including opening for ventilation grills, duct, etc. as required on site. Complete as per architectural detail drawing site engineer s instruction. It is for kitchen area. | smt
|  | 1 | 4.425 | 1.25 | 5.5312
2.4 | SS Foot Rail | rmt
up to 200 mm high -Providing and fixing in position 304 grade S.S Satin Bronze finish foot rail of 38mm diameter with horizontal vertical members, Grouting in concrete, etc. complete, as specified and as directed by Architect
PLUMBING
Item Code | Item Name | UOM | Quantity | Length | Total quantity
A | WATER SUPPLY PIPING
1 | Providing fixing PPR-C ( 3 layer pipes-SDR-7.4) confirming to DIN 8078, 8077 - for Domestic, RO, flushing and Hot water, including cutting the pipes to correct length, Fusion welded jointing as per manufacturer, fixing with Ms clamps, including necessary fittings like elbows ,tees, unions reducers, coupling, pipe nipples etc. Complete, with testing, painting. The work shall also include chasing the walls with machine wherever required for concealed piping require sleeve in walls and making good of chased surface (Pipe shall be tested with 1.5 times working pressure as covered in specifications)
1.1 | 20 mm Dia | R.mt
| Ladies Toilet Zet spray to above the ceiling (vertical) |  | 3 | 3 | 9
| Wash basin point to above the ceiling |  | 1 | 3 | 3
| Horizontal |  | 1 | 2 | 2
| Sensor point |  | 3 | 0.55 | 1.65
| Gents Toilet Zet spray to above the ceiling (vertical) |  | 3 | 3 | 9
| Wash basin point to above the ceiling |  | 1 | 3 | 3
| Horizontal |  | 1 | 2 | 2
| Sensor point |  | 3 | 0.55 | 1.65
| Urinal Point Vertical |  | 2 | 3 | 6
| Horizontal |  | 1 | 1.45 | 1.45
| Horizontal |  | 1 | 2.75 | 2.75
| Staff Toilet 1& 2 |  |  |  | 0
| Gents Toilet Zet spray to above the ceiling (vertical) |  | 2 | 2.7 | 5.4
| Horizontal |  | 2 | 2.1 | 4.2
| Handicapped Toilet |  |  |  | 0
| Zet spray to above the ceiling (vertical) |  | 1 | 2.9 | 2.9
| Horizontal |  | 1 | 3.1 | 3.1
| Live Kitchen |  |  |  | 0
| Hot & cold Vertical |  | 2 | 4.7 | 9.4
| Horizontal |  | 2 | 3.75 | 7.5
| Live kitchen out side to buffet counter |  | 1 | 10.55 | 10.55
| Bar area |  |  |  | 0
| Hot & cold Vertical |  | 2 | 2.3 | 4.6
| Horizontal |  | 2 | 9.3 | 18.6
| Bar Store above door hot & cold horizontal |  | 2 | 2.25 | 4.5
| Geyser Line |  | 1 | 1.2 | 1.2
| Bar back Counter Vertical |  | 1 | 1.5 | 1.5
| Horizontal |  | 1 | 6.9 | 6.9
| Spa Toilet |  |  |  | 0
| Wash basin to main line above the ceiling |  | 1 | 4.5 | 4.5
| Toilet cold line |  | 1 | 5.7 | 5.7
| Normal water |  | 1 | 3.1 | 3.1
| Hot line |  | 1 | 6.1 | 6.1
| Wash basin to sink |  | 1 | 1.2 | 1.2
142.45
1.2 | 25 mm Dia | R.mt
Staff Toilet
| Left side right side to Horizontal |  | 1 | 4.5 | 4.5
| staff toilet to ladies toilet |  | 1 | 3.05 | 3.05
| Wash basin to ladies toilet above |  | 1 | 5.04 | 5.04
| Handicapped to janitor room above ceiling Horizontal |  | 1 | 3.9 | 3.9
| Gents toilet right to left side Horizontal |  | 1 | 2.8 | 2.8
| Gents toilet above janitor room Horizontal |  | 1 | 4.9 | 4.9
| Janitor room to wash basin above ceiling Horizontal |  | 1 | 8.6 | 8.6
| Bar Area |  |  |  | 0
| Bar store room to AHU room Ro normal water |  | 2 | 6 | 12
| AHU to Spa room |  | 2 | 7.3 | 14.6
| Spa Area |  |  |  | 0
| Spa seating to to spa room |  | 2 | 5.2 | 10.4
| Wash basin to above ro plant |  | 2 | 1.2 | 2.4
| Old meter to RO plant |  | 2 | 2.1 | 4.2
| Bathroom to terrace |  | 1 | 2.2 | 2.2
| Spa above to terrace Ro plant Horizontal |  | 1 | 3.2 | 3.2
| Vertical |  | 4 | 0.3 | 1.2
| Staff toilet terrace ro plant to Live kitchen |  | 2 | 8.3 | 16.6
0
0
0
99.59
1.3 | 32mm Dia | R.mt
| Janitor room to Handicapped Horizontal above ceiling |  | 1 | 4.15 | 4.15
| Handicapped to ladies toilet Horizontal above ceiling ladies toilet to staff |  | 1 | 6.4 | 6.4
| Ro water to Janitor room |  | 1 | 1.15 | 1.15
| Old water meter to Janitor room |  | 1 | 6.1 | 6.1
0
17.8
1.4 | 40mm Dia | R.mt
3 | Providing Fixing of gun metal heavy Ball Valves (approved makes as covered in specification) screwed type for water system of the following diameters(15Kg Sq.cm). Valve shall have with unions.
3.1 | 20mm Dia | Nos.
3.2 | 25mm Dia | Nos.
3.3 | 32mm Dia | Nos.
3.4 | 40mm Dia | Nos.
4 | Providing ,fixing, testing and commissioning Electromagnetic flow meter-flow (30 GPM-1.89 LPS) including providing fixing matching with required accessories 16Kgs Sq.cm). - Contractor to check existing make in BIAL airport and provide that.
4.2 | 32 mm Dia incoming line | Nos.
4.3 | 40 mm Dia incoming line | Nos.
|  |  | 4 |  | 4
5 | Supply, installation, testing commissioning of Storage Type Electric Hot Water Generator of mentioned capacity, suitable for 3 KG cm2 pressure, Wall Mounted Floor standing type, with Auto Shut-off Thermostat, along with isolation Valves, Air Release valve, SS flexible connections and all other std accessories ( Prior to proceed check with client for instant geyser requirement if any)
4.2 | 20 L Capacity | Nos.
a |  |  | 2 |  | 2
B | RO PLANT-PRIOR TO PROCEED LOCATION TO BE FINALISED
1 | Supply , installations, testing and communising of Package RO plant 200 Lit Hr including required internal pumps , all accessories, valves and membrane cleaning system, ultra-violet sterilizer, internal piping within the whole package suitable to connect the inlet and outlet to plumbing contractor work including pressure gages etc. | Nos
2 | Syntex storage tank -300 lit (RO water) | Nos
3 | Horizontal, pressure booster pumps with motors mounted on a single base frame, complete with all accessories, suction discharge butterfly valves, suction strainers, discharge non-return valves, pressure gauges and of the following capacities
| a)For RO water supply | Nos
50 lpm @ 2.0 kg cm2 discharge pressure.
C | DRAINAGE
1 | Providing Fixing spun Chihulys Pipes as per IS 3989 1729 (As peris 6594 As per IS 15905) to correct grade length and alignment including cutting pipes to correct lengths joining as specified by manufacturer including required h Mossbacked, clamps, testing, painting the pipes with three coats of bitumatic paint complete as per specifications for the following diameters including fittings such as tees. bends, single junction, double junction etc.
1.1 | 75mm Dia | R.mt
Bar Area
| Glass washer to Chamber |  | 1 | 2.935 | 2.935
| Ice Cube Machine to Chamber |  | 1 | 1.062 | 1.062
| Bar blender to chamber |  | 1 | 1.1 | 1.1
| Ice Cube machine Chamber |  | 1 | 2.65 | 2.65
| Chamber to AHU Chamber |  | 1 | 4.55 | 4.55
| Spa Room |  |  |  | 0
| Nehni trap to Duct |  | 1 | 6.04 | 6.04
| Water Lounge |  |  |  | 0
| Gents toilet wash basin to janitor room main use |  | 1 | 10.07 | 10.07
| All Main line to Nehni trap |  | 5 | 0.65 | 3.25
| Staff toilet to handicapped toilet out side |  | 1 | 9.5 | 9.5
| Toilet to wash basin |  | 1 | 3.4 | 3.4
| Staff to staff |  | 1 | 3.4 | 3.4
| All nehni trap to main line |  | 6 | 0.7 | 4.2
52.157
1.2 | 100 mm Dia | R.mt
Spa Room
| Wc to duct |  | 1 | 5.47 | 5.47
| Water Lounge |  |  |  | 0
| Staff toilet to duct |  | 1 | 13.15 | 13.15
| Clean out point in staff toilet |  | 1 | 0.65 | 0.65
| Gents toilet to Janitor room |  | 1 | 7.55 | 7.55
| Gents toilet to Clean out |  | 1 | 0.4 | 0.4
0
0
27.22
0
1.3 | 150 mm Dia
2 | UPVC Type B pipe confirming to IS 13592 (6 Kg CM2) for Soil, Waste up to 65mm dia. confirming to IS 13592 in correct grade,length alignment in Solvent Cement joints including cutting the pipes to correct length, jointing with solvent cement joints, fixing with M.S heavy brackets clamps testing, including cutting holes in R.C.C walls floors making good the same etc all complete including plain fittings such as bends, tees etc. of the following diameters ( basin Sink to FT in toilet internal)
1.1 | 40mm Dia | R.mt
| Buffet Counter to coffee machine |  | 1 | 7.15 | 7.15
| Live kitchen to wash basin |  | 1 | 3.3 | 3.3
| Urinal area |  | 1 | 6.05 | 6.05
| Staff toilet area |  | 1 | 2.3 | 2.3
| Staff toilet area |  | 1 | 2.15 | 2.15
| Ladies washbasin area |  | 1 | 3.4 | 3.4
| Gents Washbasin area |  | 1 | 3.75 | 3.75
| Handicapped wash basin area |  | 1 | 2.35 | 2.35
30.45
1.2 | 50mm Dia | R.mt
| Spa Nehni trap to washbasin |  | 1 | 1.93 | 1.93
| Sink to nehni trap |  | 1 | 0.52 | 0.52
| Hair wash to duct |  | 1 | 5.57 | 5.57
0
8.02
1.3 | 65mm Dia | R.mt
1.4 | 75mm Dia | R.mt
3 | Supply, Install PVAC multitaps including fixing with lead caulked joints and rings, c w Circular SS 304 Grating, ( in bar and live kitchen) | Nos.
4 | Supply, Install CI multitaps including fixing with lead caulked joints and rings, c w Circular SS 304 Grating, ( Subject to site requirement) | Nos.
5 | Supply, Install CI floor Traps including fixing with lead caulked joints and rings, c w Circular SS 304 Grating, | Nos.
6 | Supply, Install CI urinal Traps including fixing with necessary consumables with Circular SS Grating with anti cockroach jali Suitable for 75mm Dia outlet | Nos.
8 | Supply, Install CI custom made clean out plunges with brass cap including fixing with necessary consumables.(Optional if required at site)
8.2 | 75 mm Dia | Nos.
8.3 | 100 mm Dia | Nos.
9 | Supply, Install GREASE TRAP-MODEL LIPUMOBIL-S | Nos.
|  |  | 2 |  | 2
10 | Only Installation of S.S. grating of 300x300mm shown in the layout (Note- supply of SS gratings will be by kitchen consultant or TFS) | Nos. | 0.00 | 1.00 | 1
D | CORE CUTS
1 | Providing core cuts as per following size with backfilling water proofing core cuts to be sealed as required standard as required by project manager
1.3 | 150 mm Dia | Nos.
D | CORE CUTS
E | SANITARY AND C. P. FITTINGS FIXTURES
Only installation, testing and commissioning of sanitary and C.P. fittings
1.1 | EWC with seat cover | Nos
1.2 | Concealed flush tank | Nos
1.4 | Health Faucet | Nos
1.5 | 2 Way Bib-Cock with connection for Health Faucet | Nos
1.7 | Under Counter Wash Basin including waste Coupling | Nos
1.8 | Wash Basin Cock | Nos
1.11 | Under Counter Sink including waste Coupling | Nos
1.12 | Sink Pillar Cock | Nos
1.13 | Bottle Trap for WHB sink and urinal with all connecting pipes | Nos
1.14 | Angle Cock with PVC pipe connection up to WHB sink Geyser connection | Nos
1.15 | Urinal | Nos
1.16 | Auto Flush Valve Sensor with connecting piping spreader for urinal(DC) | Nos
1.17 | Soap Dispenser | Nos
1.18 | Paper Holder | Nos

## RA-3 Extra item
Extra work | [5 empty] | RA-2 |  | RA-3
Item Code | Item Name | UOM | Qty | Unit Price | Amount | % | RA-2 Gross Amount | Qty | % | Amount | RA-3 Actual Amout
MS STRUCTURE LIVE KITCHEN
1 | Supply, fabrication and erection of structural steel beams, columns and purlins including all consumables, bolts, nuts etc., painting the fabricated items with two coats of zinc phosphate primer, over coated with synthetic enamel paint of approval shade and brand as per drawings and as directed by the Engineer. The steel material shall be of approved make such as JSW, TATA, Apollo etc., | Kgs | 865 | 350 | 302750 | 0% | 0 | 865 | 100% | 302750 | 302750
2 | Supply and installation of colour coated single skin roof sheet of 0.45 TCT for Live kitchen area including providing self tapping screws, flashing etc., complete. The roof sheet shall be of approved brand such as Tata BlueScope, Pennar etc., | Sq. | 24.3902 | 975 | 23780.4878 | 0% | 0 | 24.3902 | 100% | 23780.4878 | 23780.4878
3 | Supply and installation of Stainless steel M-10x90 HST-R Stud anchor of Hilti make, including drilling of holes in the concrete slab and fixing the anchor as per manufacturer's recommendation | Each | 4 | 10750 | 43000 | 0% | 0 | 4 | 100% | 43000 | 43000
[5 empty] | 0 |  | 0 | 0 |  | 0 | 0
| DISMANTALING |  |  |  | 0 |  | 0 | 0 |  | 0 | 0
1 | Cartage to remove the debris' from Yard Phase-1 | Trip | 6 | 17500 | 105000 | 100% | 105000 | 6 | 100% | 105000 | 0
2 | Complete the Balance dismantling work | [6 empty] | 0 |  | 0
a) | Floor tile and Screed chipping wherever is balance | Sqm | 163.9955 | 385 | 63138.2675 | 100% | 63138.2675 | 163.9955 | 100% | 63138.2675 | 0
b) | Removing of existing wooden Bulk-head and keeping in a safe place with all its hardware and other reusable materials, including cleaning all debris' from site & throwing the debris' from the premises. | Sqm | 84.2648 | 490 | 41289.752 | 100% | 41289.752 | 84.2648 | 100% | 41289.752 | 0
c) | Removing of existing all existing not useable MEP services and keeping in a safe place with all its hardware and other reusable materials, including cleaning all debris' from site & throwing the debris' from the premises. | L.S | 1 | 18750 | 18750 | 100% | 18750 | 1 | 100% | 18750 | 0
d) | Removing of Plaster 15/20mm thick from plaster finished brick masonry wall, including cleaning the surface & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors. | Sqm | 168.837 | 560 | 94548.72 | 100% | 94548.72 | 168.837 | 100% | 94548.72 | 0
e) | Removing of existing gypsum false ceiling with GI framing and 12/15mm thick gypsum board, including cleaning all debris' from site & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors. | Sqm | 27.0719 | 450 | 12182.355 | 100% | 12182.355 | 27.0719 | 100% | 12182.355 | 0
f) | Cartage to remove the debris' from Yard 2nd part | Trip | 14 | 17500 | 245000 | 100% | 175000 | 14 | 100% | 245000 | 70000
g) | Removing of IPS flooring including 50mm to 75mm thick sand cement layer, cleaning surface of slab & throwing the debris' from the site premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors. | Sqm | 68.2395 | 695 | 47426.4525 | 100% | 47426.4525 | 68.2395 | 100% | 47426.4525 | 0
h) | Demolition of existing 200 mm thick brick wall with both sides finished of 10/15 mm thick plaster, including cleaning the surface & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors. | sqm | 28.33 | 715 | 20255.95 | 90% | 18230.355 | 28.33 | 100% | 20255.95 | 2025.595
I) | Demolition of existing 125mm thick Reinforced cement concrete overhanging eave along with steel & throwing the debris from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris from both the floors. | L.S | 1.648 | 1500 | 2472 | 90% | 2224.8 | 1.648 | 100% | 2472 | 247.2
j) | Removing 25mm thick Granite stone along with MS framing including cleaning all debris' from site & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors. | Sqm | 45.904 | 550 | 25247.2 | 100% | 25247.2 | 45.904 | 100% | 25247.2 | 0
k) | Removing MS structure including cleaning all debris' from site & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris from | Sqm | 22 | 960 | 21120 | 100% | 21120 | 22 | 100% | 21120 | 0
l) | Removing aluminium frame with glass wool including cleaning all debris' from site & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors | Sqm | 46.5854 | 550 | 25621.97 | 100% | 25621.97 | 46.5854 | 100% | 25621.97 | 0
m) | Removing of existing all existing not useable MEP,Ducting,Water tank, MS frame etc. | Sqm | 1 |  | 0 | 0% | 0 | 1 | 0% | 0 | 0
n) | Spa Duct wall Niche breaking as per details drawing | L.S | 1 | 3950 | 3950 | 100% | 3950 | 1 | 100% | 3950 | 0
o) | Water Lounge area Bathroom wall breaking for Euronics hand dryer | Nos | 3 | 4950 | 14850 | 100% | 14850 | 3 | 100% | 14850 | 0
| Additional Interior work |  |  |  | 0 |  | 0 | 0 |  | 0 | 0
1 | providing and fixing 12 mm thk Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at centre of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material | Sqm | 14.2 | 2650 | 37630 | 100% | 37630 | 14.2 | 100% | 37630 | 0
2 | 36mm x 36 mm, 16 SWG aluminium framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment, including provision for Electrical Conduit and slot for Digital screen as shown in drawing | Sqm | 9.3 | 4250 | 39525 | 100% | 39525 | 9.3 | 100% | 39525 | 0
3 | providing and fixing 6 mm thk Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at centre of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material | Sqm | 15.82 | 1850 | 29267 | 100% | 29267 | 15.82 | 100% | 29267 | 0
4 | Providing & Fixing 12 mm thick plywood Arch type making & Finish with 6 mm thick HDHmr Finish , Rate inclusive of Fixing of ceiling . | Rmt | 20.4 | 4500 | 91800 | 100% | 91800 | 20.4 | 100% | 91800 | 0
5 | Proving & Fixing "I" type channel fixing on Arch type ceiling frame | Rmt | 20.4 | 1500 | 30600 | 100% | 30600 | 20.4 | 100% | 30600 | 0
6 | Spa trapdoor | Sqm | 0.36 | 16750 | 6030 | 100% | 6030 | 0.36 | 100% | 6030 | 0
7 | Relax area tile fixing for wooden floor base | Sqm | 77.2 | 1975 | 152470 | 70% | 106729 | 77.2 | 100% | 152470 | 45741
8 | Water lounge Mosaic behind tile fixing | Sqm | 80.084 | 1975 | 158165.9 | 91.11% | 144094 | 80.084 | 100% | 158165.9 | 14071.9
9 | Relax area Wooden flooring | Sqm | 77.2 | 14750 | 1138700 | 75% | 854025 | 77.2 | 80% | 910960 | 56935
10 | Ac Duct & equipment removing BOH area terrace | Nos | 1 | 70000 | 70000 | 100% | 70000 | 1 | 100% | 70000 | 0
11 | Supply & Installation Grundfos Pressure pump | Nos | 2 | 185000 | 370000 | 90% | 333000 | 2 | 100% | 370000 | 37000
12 | Supply Steel Grating Chamber | Nos | 2 | 22750 | 45500 | 100% | 45500 | 2 | 95% | 43225 | -2275
13 | Floor grating nehni trap | Nos | 7 | 1150 | 8050 |  | 0 | 7 | 80% | 6440 | 6440
14 | Lift lobby Steel B th side U Patti & Middle portion Texture steel sheetwork lift1 & lift2 | Nos | 2 | 125000 | 250000 |  | 0 | 2 | 70% | 175000 | 175000
15 | Welcome zone area Ms column steel cladding |  |  |  | 0 |  | 0 | 0 |  | 0 | 0
16 | Sports bar area screen Stell pvd coating cladding( 70 mm dhar x 800 mm wide x 3500 mm ) | Nos | 3 | 42000 | 126000 |  | 0 | 3 | 70% | 88200 | 88200
17 | Bar Area brass Foot railing cost difference steel vs brass | L.S | 1 | 27500 | 27500 |  | 0 | 1 | 70% | 19250 | 19250
18 | Sports bar area Marble cost difference (3850/- per sft including fluted & polishing BOQ rate 1000/-=2850 sft difference | Sqm | 10.8 | 30677.4 | 331315.92 |  | 0 | 10.8 | 100% | 331315.92 | 331315.92
19 | Live kitchen Round piller steel cladding 3395 mm x 281 mm | Nos | 1 | 65000 | 65000 |  | 0 | 1 | 70% | 45500 | 45500
20 | Dining Area Round piler Steel cladding 3425 mm x 435 mm | Nos | 1 | 75000 | 75000 |  | 0 | 1 | 70% | 52500 | 52500
21 | Welcome zone Exotic marble Cost difference (BOQ 1000/-sft , 2500/-sft= difference 1,500/- sft | Sqm | 19.155 | 16146 | 309276.63 |  | 0 | 19.155 | 100% | 309276.63 | 309276.63
22 | Providing & fixing Nirali Sink 3 nos | Nos | 3 | 7960 | 23880 |  | 0 | 3 | 100% | 23880 | 23880
23 | Kohler Sink cock (3 nos) | Nos | 3 | 7960 | 23880 |  | 0 | 3 | 70% | 16716 | 16716
24 | Angle cock | Nos | 14 | 2450 | 34300 |  | 0 | 14 | 100% | 34300 | 34300
25 | Connector pipe | Nos | 18 | 450 | 8100 |  | 0 | 18 | 100% | 8100 | 8100
26 | Ph1 & ph2 8 nos tall table veneer vs Corian rate difference | Nos | 8 | 13750 | 110000 |  | 0 | 8 | 70% | 77000 | 77000
27 | Green mosaic boq rate 450 (purchase rate 650 (10 mm x10 mm) difference 200persft , grouting kerakoll extra rate per sft 225 less normal grout 75 sft = grout 150 + mosaic 200=350/- per sftdifference | Sqm | 53.91 | 3767.4 | 203100.534 |  | 0 | 53.91 | 95% | 192945.5073 | 192945.5073
28 | Synthetic marble boq rate 275 purchase rate 305/- sft difference 30/- per sft | Sqm | 159.26 | 322.92 | 51428.2392 |  | 0 | 159.26 | 100% | 51428.2392 | 51428.2392
29 | Tree house rib glass regular vs extra clear glass With Anti shatter film | Sqm | 15 | 4843.8 | 72657 |  | 0 | 15 | 100% | 72657 | 72657
30 | TV screen 5 Box 8 labour | L.S | 1 | 8000 | 8000 |  | 0 | 1 | 100% | 8000 | 8000
31 | Sports bar high table table top solid wood & height increase | Nos | 6 | 12500 | 75000 |  | 0 | 6 | 100% | 75000 | 75000
32 | Brick cladding sealer applying (2 teeper column + Bar area wall+ Relax wall) | Sqm | 68.24 | 409.032 | 27912.3437 |  | 0 | 68.24 | 100% | 27912.3437 | 27912.3437
33 | Live kitchen above veneer with polish | Nos | 3 | 6500 | 19500 |  | 0 | 3 | 95% | 18525 | 18525
34 | Sport bar store room fridge 12 Labour | Nos | 1 | 12000 | 12000 |  | 0 | 1 | 100% | 12000 | 12000
35 | Tea garden Fridge 14 Labour | Nos | 1 | 14000 | 14000 |  | 0 | 1 | 100% | 14000 | 14000
36 | Gypsum ceiling redo | L.S | 1 | 25000 | 25000 |  | 0 | 1 | 80% | 20000 | 20000
37 | Gypsum Partition for live kitchen above terrace | Sqm | 34.2615 | 2280 | 78116.22 |  | 0 | 34.2615 | 100% | 78116.22 | 78116.22
38 | Sport bar area Near Tepper column coffee station | L.S | 1 | 82750 | 82750 |  | 0 | 1 | 95% | 78612.5 | 78612.5
39 | Plywood veneer storage (Dust bin) | Nos | 2 | 75750 | 151500 |  | 0 | 2 | 95% | 143925 | 143925
40 | Sports bar onyx marble below led light trey with paint | Nos | 16 | 1175 | 18800 |  | 0 | 16 | 100% | 18800 | 18800
41 | Ro plant Making Water lounge above | Nos | 2 | 18750 | 37500 |  | 0 | 2 | 100% | 37500 | 37500
42 | Duct plumbing connection including CI & UPVC pipe Water lounge side rate inclusive of bamboo Franchi | Nos | 1 | 218691 | 218691 |  | 0 | 0 | 100% | 0 | 0
43 | Duct plumbing connection including CI & UPVC pipe Spa side rate inclusive of bamboo Franchi | Nos | 1 | 116903 | 116903 |  | 0 | 0 | 100% | 0 | 0
44 | Duct passing wall Breaking & Balance gap filling with brick work & Plaster Spa & Lift 2 | Nos | 7 | 8750 | 61250 |  | 0 | 7 | 100% | 61250 | 61250
45 | Hood Loading & Unloading 3 time 12 Labour | Nos | 3 | 12000 | 36000 |  | 0 | 3 | 100% | 36000 | 36000
46 | Kota wall cladding BOH Area | Sqm | 87.6536 | 3250 | 284874.3625 | 80% | 227899.49 | 87.6536 | 80% | 227899.49 | 0
47 | Level-1 Removing of Plaster 15/20mm thick from plaster finished brick masonry wall, including cleaning the surface & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors. | Sqm | 29.7006 | 560 | 16632.336 |  | 0 | 29.7006 | 100% | 16632.336 | 16632.336
48 | Level-1 Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including approved sealer to be applied on all sides, with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft | Sqm | 6.2892 | 11500 | 72325.8 |  | 0 | 6.2892 | 100% | 72325.8 | 72325.8
49 | At least 18 mm thk polished marble Cladding fixed to Plastered masonry, Marble shall be cut from slabs of even thickness, Marble shall be installed with white cement paste, Include all finished marble niches, with V groove edge polish etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, including Approved sealer to be applied on all sides, All visible edges of Marble shall be mirror polished, Basic cost of marble Rs 450 sft | Sqm | 23.4114 | 12500 | 292642.5 |  | 0 | 23.4114 | 80% | 234114 | 234114
50 | Level 1 Barricading with flex | L.S | 1 | 16500 | 16500 |  | 0 | 1 | 100% | 16500 | 16500
51 | Level 2 Water lounge side Barricading with flex | Nos | 2 | 13500 | 27000 |  | 0 | 2 | 100% | 27000 | 27000
52 | Level-2 barricading removing & Plywoodeceilling breaking & through from the site | L.s | 1 | 15750 | 15750 |  | 0 | 1 | 100% | 15750 | 15750
53 | Service Corridor to spa fresh return air partition (4'6" x6'0") | L.S | 1 | 13750 | 13750 |  | 0 | 1 | 100% | 13750 | 13750
54 | Material store room 2 month room rent | L.S | 1 | 30000 | 30000 |  | 0 | 1 | 100% | 30000 | 30000
55 | Porter Materials ware house to airport | L.S | 1 | 10000 | 10000 |  | 0 | 1 | 100% | 10000 | 10000
56 | Providing & fixing floor fixing BOH area | Sqm | 5 | 10750 | 53750 |  | 0 | 5 | 100% | 53750 | 53750
57 | Breaking Granite floor cutting & debris removing BOH area | L.S | 1 | 9750 | 9750 |  | 0 | 1 | 100% | 9750 | 9750
58 | Bar store room inside Ply wood packing | L.S | 1 | 5750 | 5750 |  | 0 | 1 | 100% | 5750 | 5750
59 | Relax Zone Wooden Flooring Brass T profile | L.S | 1 | 35750 | 35750 |  | 0 | 1 | 70% | 25025 | 25025
60 | Lift 1 & Lift 2 Plywood Covering | Nos | 2 | 12750 | 25500 |  | 0 | 2 | 100% | 25500 | 25500
[8 empty] | 0 |  | 0
| Subtotal Excluding Gst |  |  |  | 6892456.9402 |  | 2684679.362 |  |  | 5967953.041 | 3283273.679

## RA-3 EXT MEAS
Sr.no | Item Description | Ucom | Qty | Length | Height | Total Qty
Ms structure Live Kitchen
| Section |  | Unit wt (kg/m) | Length (mm) | Length (m) | Weight (Kgs)
1 | RHS 200x100x6 (beams) |  | 26.4 | 17145 | 17.145 | 452.628
| RHS 80x40x4 (Purlins) |  | 6.71 | 14820 | 14.82 | 99.4422
| ISMC 150 box (Column) |  | 33.6 | 4320 | 4.32 | 145.152
| SHS 50x50x3.6 (Bulk head support) |  | 4.98 | 20350 | 20.35 | 101.343
| Plates |  | Unit wt (kg/m) | Area (sq.m) |  | Weight (Kgs)
| 10thk Stiffener plate (ST2) |  | 78.5 | 0.704 |  | 55.264
| 10thk Connection plate (CP1) |  | 78.5 | 0.0486 |  | 3.8151
| 12thk Column Base plate (BP1) |  | 94.2 | 0.0625 |  | 5.8875
|  | Kg |  |  | Total wt. (Kgs) | 863.5318
2 | Supply and installation of colour coated single skin roof sheet of 0.45 TCT for Live kitchen area including providing self tapping screws, flashing etc., complete. The roof sheet shall be of approved brand such as Tata BlueScope, Pennar etc., | Sqm | 1 | 4.878 | 5 | 24.3902
3 | Supply and installation of Stainless steel M-10x90 HST-R Stud anchor of Hilti make, including drilling of holes in the concrete slab and fixing the anchor as per manufacturer's recommendation | Nos | 4 |  |  | 4
DISMANTALING
1 | Cartage to remove the debris from Yard Phase-1 |  | 6 | Trip |  | 6
2 | Complete the Balance dismantling work
a) | Floor tile and Screed chipping wherever is balance
| Live kitchen back area raised floor |  | 1 | 4.426 | 0.6 | 2.6556
| Buffet back area raised floor |  | 1 | 2.4 | 0.6 | 1.44
| Live kitchen FLOOR |  | 1 | 4.326 | 3 | 12.978
| Tea garden area FLOOR |  | 1 | 4.8 | 4.8 | 23.04
| Relax zone raised floor |  | 1 | 2.4 | 2.2 | 5.28
| Sports zone beside bar counter left side |  | 1 | 19.5 | 2.1 | 40.95
| Sports zone beside bar counter centre |  | 1 | 4.08 | 10.25 | 41.82
| Welcome zone - Infront of lift |  | 1 | 3.16 | 4.145 | 13.0982
| SPA room outside Infront of entry door |  | 1 | 1.77 | 2.42 | 4.2834
| SPA and IT service corridor |  | 1 | 3.73 | 1.23 | 4.5879
| Passage beside lift 1 (lift corridor) |  | 1 | 4.32 | 2.17 | 9.3744
| Passage beside live kitchen |  | 1 | 2.04 | 2.2 | 4.488
163.9955
b) | Removing of existing wooden Bulk-head and keeping in a safe place with all its hardware and other reusable materials, including cleaning all debris' from site & throwing the debris' from the premises.
| Bar counter left side bulkhead |  | 1 | 3.9 | 3.3 | 12.87
| Bar counter right side bulkhead |  | 1 | 2.9 | 3.3 | 9.57
| Relax area above the back side service lift |  | 1 | 6.71 | 1.88 | 12.6148
|  |  | 1 | 1.45 | 2.7 | 3.915
| Dining area |  | 1 | 1.4 | 1.88 | 2.632
| Bar counter left side wall panelling |  | 1 | 2.6 | 3 | 7.8
| Electric panel box |  | 2 | 0.67 | 2.45 | 3.283
|  |  | 1 | 1.5 | 0.67 | 1.005
| IT room right side wall panelling |  | 2 | 1.6 | 3.15 | 10.08
| Above the door |  | 1 | 2.1 | 1.25 | 2.625
| Fire box area |  | 1 | 1.45 | 2.2 | 3.19
| Less fire box (-) |  | 1 | -1.5 | 1.1 | -1.65
| Wooden db. rack |  | 1 | 1.65 | 2.2 | 3.63
| Welcome area left side partition |  | 1 | 3.5 | 0.84 | 2.94
| Lift lobby front wall |  | 1 | 2 | 2.44 | 4.88
| Fire panel opposite to Ms column |  | 1 | 2 | 2.44 | 4.88
84.2648
c) | Removing of existing all existing not useable MEP services and keeping in a safe place with all its hardware and other reusable materials, including cleaning all debris' from site & throwing the debris from the premises. |  | 1 | L.S |  | 1
d) | Removing of Plaster 15/20mm thick from plaster finished brick masonry wall, including cleaning the surface & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris from both the floors.
| Spa room duct wall plaster remove |  | 1 | 1.3 | 3.2 | 4.16
|  |  | 1 | 3.05 | 0.9 | 2.745
| Toilet area plaster remove |  | 1 | 3.4 | 0.4 | 1.36
| Existing ledge wall |  | 1 | 4.9 | 4.6 | 22.54
| Hvac area wall |  | 1 | 1.6 | 2.75 | 4.4
| Centre duct area |  | 1 | 6.2 | 0.75 | 4.65
| Live kitchen door side wall |  | 1 | 4.32 | 3.05 | 13.176
| Less door (-) |  | 1 | -1.5 | 2.4 | -3.6
| Live kitchen back wall |  | 1 | 5.58 | 3.05 | 17.019
|  |  | 1 | 1.53 | 1.2 | 1.836
| Ladies toilet duct side wall |  | 1 | 5 | 3.3 | 16.5
| Back passage wall |  | 1 | 4.43 | 3.3 | 14.619
| Duct wall |  | 1 | 1.63 | 3.3 | 5.379
|  |  | 1 | 2.68 | 3.3 | 8.844
| Passage back wall |  | 1 | 1.47 | 3.3 | 4.851
|  |  | 1 | 6.62 | 3.3 | 21.846
| Kitchen passage wall |  | 1 | 3.4 | 3.3 | 11.22
| Relax zone and lift passage divider wall |  | 1 | 4.323 | 4 | 17.292
168.837
e) | Removing of existing gypsum false ceiling with GI framing and 12/15mm thick gypsum board, including cleaning all debris' from site & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors.
| Lift lobby welcome area |  | 1 | 4.78 | 3.35 | 16.013
| Vertical |  | 1 | 0.6 | 3.35 | 2.01
| Live kitchen area lift lobby |  | 1 | 4.17 | 2.17 | 9.0489
27.0719
f) | Cartage to remove the debris' from Yard Phase-2 |  | 20 | Trip |  | 10
g) | Removing of IPS flooring including 50mm to 75mm thick sand cement layer, cleaning surface of slab & throwing the debris' from the site premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors.
| Gents Toilet and Staff toilet Area |  | 1 | 5.1 | 4.55 | 23.205
|  |  | 1 | 5.7 | 0.75 | 4.275
| Live Kitchen area |  | 1 | 4.426 | 0.75 | 3.3195
| Buffet back area |  | 1 | 2.4 | 0.75 | 1.8
| Bar counter inside area |  | 1 | 3.4 | 0.75 | 2.55
|  |  | 1 | 2.7 | 6.7 | 18.09
| Lift lobby |  | 1 | 3 | 5 | 15
68.2395
h) | Demolition of existing 200 mm thick brick wall with both sides finished of 10/15 mm thick plaster, including cleaning the surface & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris from both the floors.
| Live kitchen area ,Layout new door area |  | 1 | 1 | 4 | 4
| Back corridor Layout new entry door |  | 1 | 2.2 | 4 | 8.8
| Existing toilet Ledge wall |  | 1 | 4.9 | 1.4 | 6.86
| Janitor room door opening |  | 1 | 1 | 2.4 | 2.4
| Electrical room door opening |  | 1 | 1 | 2.4 | 2.4
|  |  | 1 | 1.8 | 2.15 | 3.87
28.33
I) | Demolition of existing 125mm thick Reinforced cement concrete overhanging eave along with steel & throwing the debris from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris from both the floors.
| RCC chajja above HVAC entry door |  | 1 | 1.6 | 1.03 | 1.648
1.648
j) | Removing 25mm thick Granite stone along with MS framing including cleaning all debris' from site & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors.
| Relax zone and sports zone column |  | 4 | 1.5 | 3.02 | 18.12
|  |  | 4 | 2.3 | 3.02 | 27.784
45.904
k) | Removing MS structure including cleaning all debris' from site & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris from
| Tea garden MS structure |  | 4 | 1.1 | 5 | 22
22
l) | Removing aluminium frame with glass wool including cleaning all debris' from site & throwing the debris' from the premises includes stacking at the ground level of building/society compound. Rates inclusive with the required empty bags and bring the debris' from both the floors
| AHU room |  | 2 | 5.65 | 3 | 33.9
| Less Door |  | -1 | 1.39 | 2.14 | -2.9746
| AHU room |  | 2 | 2.61 | 3 | 15.66
46.5854
m) | Removing of existing all existing not useable MEP,Ducting,Water tank, MS frame etc. | Nos |  |  |  | 1
n) | Spa room Niche breaking | Nos |  |  |  | 1
o) | Water Lounge area Bathroom Hand-drier (ladies+Gents+Handicapped) | Nos |  |  |  | 3
Additional Interior work
1 | providing and fixing 12 mm thk Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at centre of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material Welcome zone 12 mm ply fixing | Sqm | 1 | 3.1 | 3 | 9.3
| Spa entry Above | Sqm | 1 | 1.75 | 2.8 | 4.9
14.2
2 | 36mm x 36 mm, 16 SWG aluminium framework at 600 mm c c on wall column , 18 mm x 18mm, 3 mm aluminium angle to be used for assembling panelling framework, Only round head, full thread, sheet metal screws to be used, Framework to be fixed to wall in perfect plum, line and level, Suitable bracket to be provided behind framework for correct alignment, including provision for Electrical Conduit and slot for Digital screen as shown in drawing | Sqm | 1 | 3.1 | 3 | 9.3
3 | providing and fixing 6 mm thk Fire rated plywood to existing framework pop wall surface with flat head, full thread, sheet metal screws, Edges of plywood to end at centre of aluminium framework. Edges to be tightly screwed to aluminium framework at 300 mm c c. Edges to be planed properly to receive finish material | Sqm | 1 | 1.75 | 2.8 | 4.9
| Welcome zone area | Sqm | 1 | 3.1 | 1.2 | 3.72
|  | Sqm | 2 | 3 | 1.2 | 7.2
15.82
4 | Providing & Fixing 12 mm thick plywood Arch type making & Finish with 6 mm thick HDHmr Finish , Rate inclusive of Fixing of ceiling . | Rmtr | 4 | 5.1 |  | 20.4
5 | Proving & Fixing "I" type channel fixing on Arch type ceiling frame | Rmtr | 4 | 5.1 |  | 20.4
6 | Spa trapdoor | Sqm | 1 | 0.6 | 0.6 | 0.36
7 | Relax area Flooring tile fixing As per AutoCAD | Sqm |  |  |  | 77.2
8 | Water lounge Mosaic behind tile fixing
| Ladies toilet main wall |  | 1 | 3.475 | 3 | 10.425
| Gents urinal right-side wall |  | 1 | 2.6 | 3 | 7.8
| Gents Washbasin left side wall |  | 1 | 2.65 | 3 | 7.95
| Ladies wash basin wall |  | 1 | 3.95 | 3 | 11.85
| Dressing wall |  | 1 | 1.8 | 0.75 | 1.35
| Dressing wall to duct |  | 1 | 6.15 | 0.75 | 4.6125
| Wc "L" shape wall |  | 1 | 6.2 | 0.75 | 4.65
| Gents Urinal wall |  | 1 | 6.75 | 0.75 | 5.0625
| Wash basin right side wall |  | 1 | 0.9 | 2.25 | 2.025
| Wc "L" shape wall |  | 1 | 6.5 | 0.75 | 4.875
| Wash basin wall |  | 1 | 2.85 | 3 | 8.55
| Hand drier wall |  | 1 | 1.28 | 0.75 | 0.96
|  |  | 1 | 4.07 | 0.7 | 2.849
| Hnadi capped dryer wall side |  | 2 | 2.15 | 0.75 | 3.225
|  |  | 2 | 2.6 | 0.75 | 3.9
80.084
9 | Relax area Wooden flooring As per AutoCAD | Sqm |  |  |  | 77.2
10 | BOH Area Terrace Ducting removing & Spilker Removing All debris through from the site to materials yard | Nos |  |  |  | 1
11 | Supply & Installation Ground fos Pressure pump | Nos |  |  |  | 2
12 | Supply Steel Grating Chamber | Nos |  |  |  | 2
13 | Floor grating nehni trap | Nos |  |  |  | 7
14 | Lift lobby Steel B th side U patti & Middle portion Texture steel sheetwork lift1 & lift2 | Nos |  |  |  | 2
15 | Welcome zone area Ms column steel cladding | Nos
16 | Sports bar area screen Stell pvd coating cladding( 70 mm dhar x 800 mm wide x 3500 mm ) | Nos |  |  |  | 3
17 | Bar Area brass Foot railing cost difference steel vs brass | Nos |  |  |  | 1
18 | Sports bar area Marble cost difference (3850/- per sft including fluted & polishing BOQ rate 1000/-=2850 sft difference | Sqm | 1 | 0.9 | 12 | 10.8
19 | Live kitchen Round pallet steel cladding | Nos |  |  |  | 1
20 | Dining Area Round piler Steel cladding | Nos |  |  |  | 1
21 | Welcome zone Exotic marble Cost difference (BOQ 1000/-sft , 2500/-sft= difference 1,500/- sft | Sqm |  |  |  | 19.155
22 | Providing & fixing Nirali Sink (Spa sink 1 + Bar counter 2) | Nos |  |  |  | 3
23 | Kohler Sink cock (3 nos) | Nos |  |  |  | 3
24 | Angle cock | Nos |  |  |  | 14
25 | Connector pipe | Nos |  |  |  | 18
26 | Ph1 & ph2 8 nos tall table veneer vs Corian rate difference | Nos |  |  |  | 8
27 | Green mosaic boq rate 450 (purchase rate 650 (10 mm x10 mm) difference 200persft , grouting kerakoll extra rate per sft 225 less normal grout 75 sft = grout 150 + mosaic 200=350/- per sftdifference | Sqm |  |  |  | 53.91
28 | Synthetic marble boq rate 275 purchase rate 305/- sft difference 30/- per sft | Sqm |  |  |  | 159.26
29 | Tree house rib glass regular vs extra clear glass With Anti shatter film | sqm |  |  |  | 15
30 | TV screen 5 Box 8 labour |  |  |  |  | 1
31 | Sports bar high table table top solid wood & height increase |  |  |  |  | 6
32 | Brick cladding sealer applying |  |  |  |  | 68.24
33 | Live kitchen above veneer with polish |  |  |  |  | 3
34 | Sport bar store room fridge 12 Labour |  |  |  |  | 1
35 | Tea garden Fridge 14 Labour |  |  |  |  | 1
36 | Gypsum ceiling redo |  |  |  |  | 1
37 | Gypsum Partition for live kitchen above |  |  |  |  | 1
| Terminal side to lounge side | Sqm | 1 | 1.35 | 6.4 | 8.64
|  | Sqm | 1 | 1.45 | 4.47 | 6.4815
|  | sqm | 1 | 1.5 | 5.4 | 8.1
|  | sqm | 1 | 1.5 | 3.7 | 5.55
|  | sqm | 1 | 1.83 | 3 | 5.49
34.2615
38 | Sport bar area Near Tepper column coffee station |  |  |  |  | 1
39 | Plywood veneer storage (Dust bin) |  |  |  |  | 2
40 | Sports bar onyx marble below led light trey with paint |  |  |  |  | 16
41 | Ro plant Making Water lounge above |  |  |  |  | 2
42 | Duct plumbing connection including CI & UPVC pipe Water lounge side rate inclusive of bamboo Franchi |  |  |  |  | 7
43 | Duct plumbing connection including CI & UPVC pipe Spa side rate inclusive of bamboo Franchi |  |  |  |  | 1
44 | Duct passing wall Breaking & Balance gap filling with brick work & Plaster Spa & Lift 2 |  |  |  |  | 1
45 | Hood Loading & Unloading 3 time ( |  |  |  |  | 3
46 | Kota wall cladding
| Live kitchen to janitor room wall |  | 1 | 11.37 | 1.715 | 19.4995
| Less live kitchen door(-) |  | -1 | 0.89 | 1.715 | -1.5264
| Less electric room door (-) |  | -1 | 1.56 | 1.715 | -2.6754
| Less janitor room door (-) |  | -1 | 0.91 | 1.715 | -1.5607
| Fire exit wall |  | 1 | 15.15 | 1.715 | 25.9823
| Less fire exit door (-) |  | -1 | 1.5 | 1.715 | -2.5725
| Duct wall |  | 1 | 3.1 | 1.715 | 5.3165
| Passage ladies toilet out side wall |  | 1 | 6.4 | 1.715 | 10.976
| Passage entry front wall |  | 1 | 3.2 | 1.715 | 5.488
| Passage back right side wall |  | 1 | 4.5 | 1.715 | 7.7175
| Back side passage left side wall |  | 1 | 7.5 | 1.715 | 12.8625
| Back side passage Right side wall |  | 1 | 5.5 | 1.715 | 9.4325
| Less staff door (-) |  | -1 | 0.75 | 1.715 | -1.2863
87.6536
47 | Level 1 wall Plaster removing
| Right & Left side wall | Sqm | 2 | 2.16 | 3.05 | 13.176
| Front & back both side | Sqm | 2 | 2.47 | 3.05 | 15.067
| Less (-) Lift door | Sqm | -1 | 1.67 | 2.33 | -3.8911
| Less (-) terminal side | Sqm | -1 | 1.51 | 2.1 | -3.171
| Lift Patta vertical | Sqm | 2 | 0.19 | 2.33 | 0.8854
| Horizontal | Sqm | 1 | 0.19 | 1.67 | 0.3173
| Terminal side Patta vertical | Sqm | 2 | 0.18 | 2.1 | 0.756
| Horizontal | Sqm | 1 | 0.18 | 1.51 | 0.2718
| Floor breaking | Sqm | 1 | 2.16 | 2.47 | 5.3352
| lift kwacha floor | Sqm | 1 | 0.3 | 1.67 | 0.501
| Terminal side kwacha floor | Sqm | 1 | 0.3 | 1.51 | 0.453
29.7006
48 | Level-1 West side Flooring shall consist of Marble as per drawing, At least 50 mm thk bedding mortar in 1 4 ratio, At least 18 mm thk marble to be fixed in white cement only, Marble shall be mirror polished, Marble to be cut as per size and laid with tight hairline joints, Joints to be filled Joint sealant, matching to marble in TIM-X or equivalent joint filler, including approved sealer to be applied on all sides, with edge polish etc., complete, Including using plastic Pvc sheet and POP to protect on marble flooring as protection , Include removal and disposing of protection materials before handover, Basic cost of marble Rs 450 sft
| Floor breaking | Sqm | 1 | 2.16 | 2.47 | 5.3352
| lift kwacha floor | Sqm | 1 | 0.3 | 1.67 | 0.501
| Terminal side kwacha floor | Sqm | 1 | 0.3 | 1.51 | 0.453
6.2892
49 | Level -1 West side At least 18 mm thk polished marble fixed to Plastered masonry, Marble shall be cut from slabs of even thickness, Marble shall be installed with white cement paste, Include all finished marble niches, with V groove edge polish etc. complete, All joints of Marble shall be filled with matching colour TIM-X or equivalent grout filler, including Approved sealer to be applied on all sides, All visible edges of Marble shall be mirror polished, Basic cost of marble Rs 450 sft
| Right & Left side wall | Sqm | 2 | 2.16 | 3.05 | 13.176
| Front & back both side | Sqm | 2 | 2.47 | 3.05 | 15.067
| Less (-) Lift door | Sqm | -1 | 1.67 | 2.33 | -3.8911
| Less (-) terminal side | Sqm | -1 | 1.51 | 2.1 | -3.171
| Lift Patta vertical | Sqm | 2 | 0.19 | 2.33 | 0.8854
| Horizontal | Sqm | 1 | 0.19 | 1.67 | 0.3173
| Terminal side Patta vertical | Sqm | 2 | 0.18 | 2.1 | 0.756
| Horizontal | Sqm | 1 | 0.18 | 1.51 | 0.2718
23.4114
50 | Level 1 Barricading with flex | Nos | 1 |  |  | 1
51 | Level 2 Water lounge side Barricading | Nos | 1 |  |  | 1
52 | Level-2 barricading removing & Plywoodeceilling breaking & through from the site | Nos | 1 |  |  | 1
53 | Service Corridor to spa fresh return air partition (4'6" x6'0") | Nos | 1 |  |  | 1
54 | Material store room 2 month room rent | L.S | 1 |  |  | 1
55 | Porter Materials ware house to airport | L.S | 1 |  |  | 1
56 | Providing & fixing Granite fixing | Sqm | 1 | 6.54 | 0.65 | 4.251
57 | Breaking Granite floor cutting & debris removing | L.S | 1 |  |  | 1
58 | Bar store room inside Ply wood packing | Nos | 1 |  |  | 1
59 | Relax Zone Wooden Flooring Brass T profile | L.S | 1 |  |  | 1
60 | Lift 1 & Lift 2 Plywood Covering | Nos | 2 |  |  | 2