## RA Bill
| Cafeccino | BOQ for Cafeccino Cart: 4x 2.6x 3 (mtr.) | Lucknow | Indoor |  |  | For PO |  | RA BILL
S.No | Head | Description | Refence Picture | Make | Unit | Qty | Rate | Amount (INR) | Qty | Amount (INR)
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer and powder coated paint of approved shared at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. |  | Jindal/Tata | Kgs | 370 | 165 | 61050 | 370 | 61050
2 | Base & Flooring | Providing and fixing of 18mm FR Ply with 1.5mm thick aluminium checker sheet finish mounted over MS pipe 50mm SHS , C/C 600x600mm grid, 4mm thick MS Sheet |  | Century Ply, Tata/ Jindal | Sqm | 10.08 | 4000 | 40320 | 9.6 | 38400
3 | ACP Work (Ceiling) | Providing , installing and fixing in position FR Aluminium Composite Panel Cladding for linear as well as curvilinear portions of the building , for all heights and all levels etc. including: a) Structural analysis & design and preparation of shop drawings') Back framing for panel as suited to site condition.eg.Alluminium or MS box sections etc c) Providing, fabricating and supplying and fixing panels of aluminium composite panel cladding in pan shape in metallic colour of approved shades as per specifications below. The Contractor shall provide wall with aluminium composite panel cladding, having all the performance characteristics all complete . (approved Shade) (MS Structure cost not included) |  | Timex Alu decor or equivalent | Sqm | 14.4 | 3500 | 50400 | 9.6 | 33600
4 | Shade for Roof | Providing & fixing of of 6mm Semi Transparent/opac sheet with MS Framing fix with self screw with required paint finish. (note : MS Structure is not included in this cost) |  |  | Sqm | 16 | 1500 | 24000 | 16 | 24000
5 | Rafter's Foof | Providing and fixing of Wooden Rafter 12mm HDMR Laminate cladding with approved shade matt finish. |  | Century Ply & Veneer | Rmt. | 12 | 1650 | 19800 | 12 | 19800
6 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. |  | Century or equivalent | Sqm | 40.32 | 3200 | 129024 | 38.171 | 122147.2
7 | Wall Tile | Providing , installing and fixing in of red brick pattern tile on back wall |  | Customise Make | Sqm | 11 | 2400 | 26400 | 4 | 9600
8 | Corian Cladding | Providing & fixing of 12mm Acrylic solid surface outside of side partion & front low height partion (Base Rate : 850 Sqft.) |  | LG Hi mac | Sqm | 4 | 12500 | 50000 | 4 | 50000
9 | Paint | Apply of black duco paint on pillar & side partition left&right |  | Duco Paint | Sqm | 6 | 2400 | 14400 | 6 | 14400
10 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with solid acrylic suface & inside laminate finish , Hydraulic hinges, SS knob, tower bolt etch. |  | Century Ply, FGV hinges | EA | 1 | 8800 | 8800 | 1 | 8800
11 | Awining/Canvas | P& F Awinings on both of side Red & White Colour SRF make cloths with 40 mm x 40mm x3mm Thick Asian make squire aluminium pipe frame including 02 coat red oxide paint , 02 coat asian make primer, and 02 coat asian make oil paint on Rolling frame. |  | Cavas, HP Latex | Sqm | 10 | 3600 | 36000 | 10 | 36000
12 | Kitchen Wooden Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, 2 nos soft close drawers, storage, MS pipe support (As per approved GFC) | 10 | Century Ply, FGV hinges | No. | 1 | 52405 | 52405 | 1 | 52405
13 | Sink Cabinet | Providing and fixing of Sink counter made of 18mm FR Ply with laminate finish, 450x500mm SS 304 sink, storage, plumbing fitting etc.(As Per approved GFC) | 9 | Century/Merino, SS Sink | No. | 1 | 44486 | 44486 | 1 | 44486
14 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with solid acryilc surface top finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | 7 | Century/Merino/ FGV | No. | 1 | 42000 | 42000 | 1 | 42000
15 | Chiller Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, 2 nos soft close drawers, storage, MS pipe support (As per approved GFC) | 8 | Century/Merino/ FGV | No. | 1 | 48000 | 48000 | 1 | 48000
16 | Skink New Sensor Tap | Providing & Fitting of Sensor Tap as required |  | Euronics | Nos. | 1 | 7500 | 7500 | 1 | 7500
17 | Water Pump | Providing & Fitting of Waterpump as required |  | Crompton AQUAGOLD 100-33 Residential Water Pump Self Priming Regenerative 1 HP Single Phase | Nos. | 1 | 8500 | 8500 | 1 | 8500
18 | Linear Profile Light | Providing & fixing linear profile light consealed in Rafter |  | Custom make | No. | 5 | 1800 | 9000 | 5 | 9000
19 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, DB panel, MCB, ELCB, as per requirement or as approved electrical drawing |  | Polycab, Finolex, Roma, Crompton | EA | 1 | 51000 | 51000 | 1 | 51000
20 | industrial Socket | Industrial Socket & Panel Box (32amp ) |  |  | No. | 5 | 3200 | 16000 | 2 | 6400
21 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork |  | HP Latex, 3M , LG Vinyl or equivalent | Sqm | 2.4 | 1500 | 3600 | 2.4 | 3600
22 | Signages1 | Providing and fixing of backlit channelium raised signages, NGX LED & Osram water proof supply with all required support structure (1800x500x1 ps) |  | A cast , NGX , Osram | No. | 1 | 16000 | 16000 | 1 | 16000
23 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. |  | A cast , NGX , Osram | No. | 3 | 4500 | 13500 | 3 | 13500
24 | TV Screen Menu | 32" LED TV with hanging Stand |  | Samsung/LG | No. |  | 28000 | 0 | 0 | 0
25 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 4 nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire |  | Hikvision | Set | 1 | 38600 | 38600 | 0 | 0
26 | Installation | Lucknow Airport |  |  | EA | 1 | 35000 | 35000 | 1 | 35000
27 | Transportation | Lucknow Airport |  |  | EA | 1 | 21000 | 21000 | 1 | 21000
28 | Labour Union Charges | Extra as on actual | [6 empty] | 0 | 0
29 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) |  | Havells, Syska or equivalent | No. | 4 | 2500 | 10000 | 3 | 7500
| Sub -Total | [6 empty] | 876785 |  | 783688.2
| GST Extra - 18% | [6 empty] | 157821.3 |  | 141063.876
| Total | [6 empty] | 1034606.3 |  | 924752.076

## MB Sheet
| Cafeccino | BOQ for Cafeccino Cart: 4x 2.6x 3 (mtr.) | Lucknow | Indoor |  |  | PO Qty | Actual Measurement Qty. |  |  |  |  | Billing Qty.
S.No | Head | Description | Refence Picture | Make | Size(in mm) | Unit | Qty | Length | Width | Height | Nos /Weigth | Qty | Qty
1 | MS Work | Providing & fixing of MS work in single section fixed with or without connecting plate including cutting, hoisting, fixing in position and applying a priming coat of approved red oxide steel primer and powder coated paint of approved shared at the top all complete. Item includes all MS steel items including sections, MS plates of grade Yst- 250,cleats,stiffners, anchor fasteners/ bolts, sleeves for pipes and wire management etc, as required for fixing. |  | Apollo/Jindal/Tata |  | Kgs | 370 |  |  |  |  | 387.3127 | 370
|  | Base Structures 50x50x2mm | [5 empty] | 55.56 | 0.2 | 0.0015 | 130.8438
|  | Back Stuctures 40x40x2mm | [5 empty] | 56.4 | 0.16 | 0.0015 | 106.2576
|  | Side Stuctures 40x40x2mm | [5 empty] | 24.17 | 0.16 | 0.0015 | 45.5363
|  | Top Structure 40x40x2mm | [5 empty] | 55.56 | 0.16 | 0.0015 | 104.675
2 | Base & Flooring | Providing and fixing of 18mm FR Ply with 1.5mm thick aluminium checker sheet finish mounted over MS pipe 50mm SHS , C/C 600x600mm grid, 4mm thick MS Sheet |  | Century Ply, Tata/ Jindal |  | Sqm | 10.08 | 4 | 2.4 |  | 1 | 9.6 | 9.6
3 | ACP Work (Ceiling) | Providing , installing and fixing in position FR Aluminium Composite Panel Cladding for linear as well as curvilinear portions of the building , for all heights and all levels etc. including: a) Structural analysis & design and preparation of shop drawings') Back framing for panel as suited to site condition.eg.Alluminium or MS box sections etc c) Providing, fabricating and supplying and fixing panels of aluminium composite panel cladding in pan shape in metallic colour of approved shades as per specifications below. The Contractor shall provide wall with aluminium composite panel cladding, having all the performance characteristics all complete . (approved Shade) (MS Structure cost not included) |  | Timex Alu decor or equivalent |  | Sqm | 14.4 | 4 | 2.4 |  | 1 | 9.6 | 9.6
4 | Shade for Roof | Providing & fixing of of 6mm Semi Transparent/opac sheet with MS Framing fix with self screw with required paint finish. (note : MS Structure is not included in this cost) |  |  |  | Sqm | 16 | 4 | 4 |  | 1 | 16 | 16
5 | Rafter's Foof | Providing and fixing of Wooden Rafter 12mm HDMR Laminate cladding with approved shade matt finish. |  | Century Ply & Veneer |  | Rmt. | 12 | 2.4 |  |  | 5 | 12 | 12
6 | Plywood Panelling | Providing , installing and fixing in position FR Plywood for linear as well as curvilinear portions of the building , for all heights and all levels & one side laminate finish etc. (MS Frame work charged seperatly) Includes all the performance characteristics all complete with 12mm PR Ply. |  | Century or equivalent |  | Sqm | 40.32 |  |  |  |  | 38.171 | 38.171
|  | Back Wall | [5 empty] | 4 | 2.7 | 2 | 21.6
|  | Right | [5 empty] | 2.445 | 0.95 | 2 | 4.6455 |  |  | 3200 | 297.2873 | 90 | 50 | 100 | 240 | 288
|  | Left Wall | [5 empty] | 2.445 | 0.95 | 2 | 4.6455
|  | Front | [5 empty] | 4 | 0.91 | 2 | 7.28
7 | Wall Tile | Providing , installing and fixing in of red brick pattern tile on back wall |  | Customise Make |  | Sqm | 11 | 4 | 1 |  | 1 | 4 | 4
8 | Corian Cladding | Providing & fixing of 12mm Acrylic solid surface outside of side partion & front low height partion (Base Rate : 850 Sqft.) |  | LG Hi mac |  | Sqm | 4 | 4 | 1 |  | 1 | 4 | 4
9 | Paint | Apply of black duco paint on pillar & side partition left&right |  | Duco Paint |  | Sqm | 6 |  |  |  |  | 8 | 6
[8 empty] | 4 | 0.2 | 2 | 1.6
[8 empty] | 8 | 0.2 | 4 | 6.4
10 | Flap Door | Providing & Fixing of Slab & Flap door made of 18mm FR Ply with solid acrylic suface & inside laminate finish , Hydraulic hinges, SS knob, tower bolt etch. |  | Century Ply, FGV hinges |  | EA | 1 |  |  |  | 1 | 1 | 1
11 | Awining/Canvas | P& F Awinings on both of side Red & White Colour SRF make cloths with 40 mm x 40mm x3mm Thick Asian make squire aluminium pipe frame including 02 coat red oxide paint , 02 coat asian make primer, and 02 coat asian make oil paint on Rolling frame. |  | Cavas, HP Latex |  | Sqm | 10 |  |  |  |  | 10 | 10
[8 empty] | 4 | 1 | 1 | 4
[8 empty] | 3 | 1 | 2 | 6
12 | Kitchen Wooden Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, 2 nos soft close drawers, storage, MS pipe support (As per approved GFC) | 10 | Century Ply, FGV hinges | 2325x750x900 | No. | 1 |  |  |  |  | 1 | 1
13 | Sink Cabinet | Providing and fixing of Sink counter made of 18mm FR Ply with laminate finish, 450x500mm SS 304 sink, storage, plumbing fitting etc.(As Per approved GFC) | 9 | Century/Merino, SS Sink | 1500x750x900 | No. | 1 |  |  |  |  | 1 | 1
14 | POS Counter | Providing and fixing of POS counter made of 18mm FR Ply with solid acryilc surface top finish, Step & inside laminate finish, two drawer, key board tray, storage, wire manager etc. (As per approved GFC) | 7 | Century/Merino/ FGV | 825x750x900 | No. | 1 |  |  |  |  | 1 | 1
15 | Chiller Counter | Providing & Installation of counter made of FR Plywood with approved shade laminate finish, 2 nos soft close drawers, storage, MS pipe support (As per approved GFC) | 8 | Century/Merino/ FGV | 2025x750x900 | No. | 1 |  |  |  |  | 1 | 1
16 | Skink New Sensor Tap | Providing & Fitting of Sensor Tap as required |  | Euronics |  | Nos. | 1 |  |  |  |  | 1 | 1
17 | Water Pump | Providing & Fitting of Waterpump as required |  | Crompton AQUAGOLD 100-33 Residential Water Pump Self Priming Regenerative 1 HP Single Phase |  | Nos. | 1 |  |  |  |  | 1 | 1
18 | Linear Profile Light | Providing & fixing linear profile light consealed in Rafter |  | Custom make | 1200x1 | No. | 5 |  |  |  |  | 5 | 5
19 | Electrical | Supply and Laying of 1.5mm, 2.5mm & 4sqmm wiring with PVC conduit , 5amp & 15amp switch socket with box & plate, DB panel, MCB, ELCB, as per requirement or as approved electrical drawing |  | Polycab, Finolex, Roma, Crompton | 4000x3000 | EA | 1 |  |  |  |  | 1 | 1
20 | industrial Socket | Industrial Socket & Panel Box (32amp ) |  |  |  | No. | 5 |  |  |  |  | 2 | 2
21 | Branding | Supply and pasting of HP latex printed artwork on grey back LG/Ivory/Pioneer media as per approved design artwork |  | HP Latex, 3M , LG Vinyl or equivalent |  | Sqm | 2.4 | 0.6 | 4 |  | 1 | 2.4 | 2.4
22 | Signages1 | Providing and fixing of backlit channelium raised signages, NGX LED & Osram water proof supply with all required support structure (1800x500x1 ps) |  | A cast , NGX , Osram |  | No. | 1 |  |  |  |  | 1 | 1
23 | Menu Board | Providing and fixing of Auto snap channel 32x32 powder coated with acrylic 040 & Clear Acrylic, edge lit LED, Changeable Translite Print. |  | A cast , NGX , Osram | 2x 3 | No. | 3 |  |  |  |  | 3 | 3
24 | TV Screen Menu | 32" LED TV with hanging Stand | If Required | Samsung/LG |  | No.
25 | CCTV Camera (4 Channel DVR) | DVR 5MP, 1 TB, 4 nos. 5MP Camera with Audio, 16" Display Monitor, 90mtr. D Link Wire |  | Hikvision |  | Set | 1 |  |  |  |  | 0 | 0
26 | Installation | Lucknow Airport |  |  |  | EA | 1 | [5 empty] | 1
27 | Transportation | Lucknow Airport |  |  |  | EA | 1 | [5 empty] | 1
28 | Labour Union Charges | Extra as on actual
29 | Pendant Light | LED Light fixtures-Supply, installation, testing & commissioning of lighting fittings/ fixtures complete with LED driver, complete as required:- (Hanging Lamp) | Missed to Add in last BOQ, Approved Rate | Havells, Syska or equivalent |  | No. | 4 |  |  |  |  | 3 | 3
TOTAL