## Abstract Summary
Semolina Projects
Project : CIP Lounge, Lucknow
Details: Project invoicing
PO No : PO/SKPL/23-24/001793
CIP Lounge - Bill Summary
S.N | Item | PO Value | Previous bills | This Bill | Cumulative | Varition ( In Amt ) | % Billing | Po No. | JMR Status
1 | Civil & int | 18926619 | 5208036.4076 | 3821193.7656 | 9029230.1732 | 9897388.8268 | 4771% | PO/SKPL/23-24/001793 | Done
2 | Structure Steel Work | 546000 | 0 | 0 | 0 | 546000
3 | ELECTRICAL WORKS | 4038720 | 0 | 2653064 | 2653064 | 1385656
4 | PLUMBING WORKS & Fire | 1229775 | 320498.865 | 139625 | 460123.865 | 769651.135
5 | HVAC WORKS | 1638700 |  | 1147090 | 1147090 | 491610
6 | FIX FURNITURE | 3636500 |  | 3636500 | 3636500 | 0
7 | LIGHTS & PANELS | 1905480 |  | 340160 | 340160 | 1565320
| Subtotal = | 31921794 | 5528535.2726 | 11737632.7656 | 17266168.0382 | 14655625.9618
GST @ 18% |  | 5745922.92 | 995136.3491 | 2112773.8978 | 3107910.2469 | 2638012.6731
Grand Total |  | 37667716.92 | 6523671.6217 | 13850406.6634 | 20374078.285 | 17293638.635
* | Material Advance given Before Taxes |  | #REF! | 0 | #REF!
GST @ 18% |  | 0 | #REF! | 0 | #REF! | 0
As advance paid amount |  | 0 | #REF! | 0 | #REF! | 0
* | Balance Payable
| Payable before taxes |  |  |  | #REF!
GST @ 18% |  | 0 | 0 | 0 | #REF! | 0
Payable with Taxes |  | 0 | 0 | 0 | #REF! | 0

## Summary-2 (hidden)
Summary
Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
S. No. | Description of Item | Impulse Branding
|  | PO Amount | RA=-01
1 | Civil & Interior
a | DISMENTLING & CLEANING WORKS | 0
b | CIVIL WORK | 402008.0342
c | FLOORING WORK/CLADDING WORK | 5844562.556
d | DOOR WINDOW WORK | 628670.3316
e | OTHER WOOD WORK FOR WALL PANELLING, PARTITIONS & STORAGES | 7183655.377
f | FALSE CEILING WORK | 678364.5
g | FINISHING WORK | 1061962.382
h | MISC WORK | 3119146.2
2 | Structural Steel | 546000
3 | Electrical Work
a | SUB-HEAD I WIRING | 2253020
b | SUB-HEAD II CABLES & RACEWAYS | 424200
c | SUB-HEAD III DISTRIBUTION BOARD & ELECTRICAL PANEL | 727650
d | SUB-HEAD IV FIRE DETECTION & PA SYSTEM | 519300
e | SUB-HEAD V CCTV SYSTEM | 114550
4 | PHE and FF
a | SANITARY FIXTURES AND FITTINGS | 538400
b | WATER SUPPLY | 97725
c | DRAINAGE | 94480
d | FIRE FIGHTING | 499170
5 | HVAC
a | DUCTWORK AND AIR DISTRIBUTION | 1148700
b | VENTILATION FANS AND ARRANGEMENT | 490000
6 | Furniture | 3636500
7 | Light Fixtures | 1905480
| Total Basic Amount (in Rs.) | 31913544.3808
| GST @18% | 5744437.9885
| Total Amount (in Rs.) | 37657982.3693

## Inv Summary
Semolina Projects
Project : CIP Lounge, Lucknow
Details: Project invoicing
PO No : PO/SKPL/23-24/001793
CIP Lounge - Bill Summary
S.N | Item | PO Value | RA-01 Value | RA-02 Value | RA-03 Value | RA-08 Value | RA-09 Value | RA-10 Value | Cumulative | Varition ( In Amt ) | JMR status
1 | Civil & interior | 18926619 | 562553.64 | 3641121.8346 | 1004360.933 | 3821193.7656 | 8098719.26 |  | 17127949.4332 | 1798669.5668 | Done
2 | Structure Steel Work | 546000 | 594900 | [5 empty] | 594900 | -48900 | Done
3 | ELECTRICAL WORKS | 4038720 |  | 160455.89 |  | 2653064 | 804498 |  | 3618017.89 | 420702.11 | Done
4 | PLUMBING WORKS & Fire | 1229775 |  |  | 320498.865 | 139625 |  | 524109 | 984232.865 | 245542.135 | Done
5 | HVAC WORKS | 1638700 |  |  |  | 1147090 |  | 350385.92 | 1497475.92 | 141224.08 | Done
6 | FIX FURNITURE | 3636500 |  |  |  | 3636500 |  |  | 3636500 | 0 | Done
7 | LIGHTS & PANELS | 1905480 |  |  |  | 340160 | 1478086 |  | 1818246 | 87234 | Done
Total |  | 31921794 | 1157453.64 | 3801577.7246 | 1324859.798 | 11737632.7656 | 10381303.26 | 874494.92 | 29277322.1082 | 2644471.8918
GST @ 18% |  | 5745922.92 | 208341.6552 | 684283.9904 | 238474.7636 | 2112773.8978 | 1868634.5868 | 157409.0856 | 5269917.9795 | 476004.9405
Grand Total |  | 37667716.92 | 1365795.2952 | 4485861.715 | 1563334.5616 | 13850406.6634 | 12249937.8468 | 1031904.0056 | 34547240.0876 | 3120476.8324

## Civil JMR RA Bill 1
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.01.2024
Project : CIP Lounge T3 Lucknow
W/O No : PO/SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge
RA Bill MEASUREMENT SHEET
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Qty. | Sqm | Rs | Amount
Wall Panalling
1 | E2 | PLY /BOARD CLADDING (One Layer/Single Sided
Premium Lounge
|  |  | Right Side Wall |  | 8625 | 3310 | Sqm | 1 | 28.5487
|  |  | Left wall BAR Area |  | 10000 | 3310 | Sqm | 2 | 66.2
|  |  | Door Deduction |  | -1200 | 2400 | Sqm | 2 | -5.76
|  |  | Door side patti |  | 100 | 2400 | Sqm | 2 | 0.48
|  |  | Door top patti |  | 100 | 1200 | Sqm | 1 | 0.12
|  |  | Total Sqm | [5 empty] | 89.5888 | 2700 | 241889.625
Kitchen Wall
|  |  | Door wall |  | 2155 | 3290 | Sqm | 2 | 14.1799
|  |  | Patti on face |  | 100 | 3290 | Sqm | 1 | 0.329
|  |  | Total Sqm | [5 empty] | 14.5089 | 2700 | 39174.03
SPA
|  |  | Left Side Wall |  | 5120 | 3215 | Sqm | 1 | 16.4608
|  |  | Right Side Wall |  | 5000 | 3300 | Sqm | 2 | 33
|  |  | Total Sqm | [5 empty] | 49.4608 | 2700 | 133544.16
Dining Area
|  |  | Glass wall inside |  | 2080 | 3210 | Sqm | 1 | 6.6768
|  |  | Total Sqm | [5 empty] | 6.6768 | 2700 | 18027.36
Admin Office
|  |  | Door front wall inside |  | 1800 | 3250 | Sqm | 1 | 5.85
|  |  | Door Deduction |  | -900 | 2400 | Sqm | 1 | -2.16
|  |  | Right Side Wall inside |  | 2845 | 3250 | Sqm | 1 | 9.2462
|  |  | Patti on face |  | 100 | 2400 | Sqm | 2 | 0.48
|  |  | Left wall inside |  | 1830 | 3250 | Sqm | 1 | 5.9475
|  |  | Door Back wall inside |  | 1856 | 3250 | Sqm | 1 | 6.032
|  |  | Total Sqm | [5 empty] | 25.3957 | 2700 | 68568.525
Reception
|  |  | wall inside |  | 6970 | 3260 | Sqm | 1 | 22.7222
|  |  | Total Sqm | [5 empty] | 22.7222 | 2700 | 61349.94
|  |  | Total Qty Sqm = | [5 empty] | 208.3532
|  |  | Total Amount in Rupees | [7 empty] | 562553.64

## Civil JMR RA Bill 2
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Nos | Qty. | Rate | Amount
1 | 5 | MARBLE FLOORING:Providing and fixing Marble work 16-18 mm thick ,Mirror Polished ,Prepolished, machine cut of required size approved shade colour and texture laid over 20mm thick base cement mortar 1:4 (1 cement : 4 coarse sand ) ,white cement slurry, joints teeated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level ( Actual size of stone to be measured & paid ). Cost also include the protection covering till handover with polythin+POP as per advised by the project incharge.
| a | Marble Flooring Type 1 : Base Price of Marble @ 450/- Per sft,
|  |  | Floor marbal | 10.65 | 13.5 |  | Sqm | 1 | 143.775
|  |  |  | 7.4 | 2.1 |  | Sqm | 1 | 15.54
|  |  |  | 4.1 | 1.2 |  | Sqm | 1 | 4.92
|  |  |  | 6.775 | 13.7 |  | Sqm | 1 | 92.8175
[7 empty] | Total Qty |  | 257.0525
9300
[7 empty] | Total Amount |  |  |  | 2390588.25
2 | c | Marble Skirting upto 100mm high : Base Price of Marble @ 1200/- Per sft, | Premioum Lounge,Admin,Reception BAR Area,SPA | 82.368 | [5 empty] | 8500 | 700128
[7 empty] | SUB TOTAL |  |  |  | 3090716.25
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 20.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF GYPSUM CELLING
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Nos | Qty. | Rate | Amount
1 |  | FR GRADE GYPSUM BOARD CEILING : Providing and fixing Single Layer Boarding with 12.5mm thick plain and split level with Firebloc gypsum plasterboards, This includes ST50 fully knurled Perimeter Channel (0.50mm thick having one flange of 20mm and another flange of 30mm and a web of 28mm) screw fixed to brick wall/partition/ hanging with existing ceiling / existing MS framework and suspended GI frame with the help of approved screws at 600mm centers. Then suspending ST-50 fully knurled intermediate section (45mm x 0.90mm thick with two flanges of 15mm each) from the soffit at 1220mm centers with ST-50 fully knurled Ceiling L Angle (25x10mmx0.50mm thick) fixed to RCC Slab with USG Boral 227x35x1.5mm Soffit Cleat and 50mm Approved dash Fasteners @ 1200mm Centers respectively. ST-50 profiles are rolled with G.I Steel (120GSM & 230 MPa Yield Strength) Conforming to IS 277. ST-50 fully knurled Ceiling Section (51mm x 0.50mm thick with two flanges of 26mm each) is then fixed to the Intermediate channel with the help of 2.5mm dia wire connecting in a perpendicular direction to the intermediate channel at 457mm centers. 12.5mm thick Firebloc Pasteboards (Conforming to BS 1230 (Parti-1) is screw fixed with 25mm long Drywall screws at 230 mm centers. The screw fixing of gypsum boards to the metal framing at the periphery, openings, and cut edges should be at 150mm centers. All the fire Bloc gypsum plasterboards must be staggered. All joints are to be taped & finished with Paper tape & All-Purpose Joint Compound confirming to ASTM C475. above item include with all the vertical band, curve band, pelmet, cove, split level etc. also wall to wall plan area shall be measured for claim, vendor to quote as per design/dwg.
|  |  | Premioum Lounge | 9.081 | 4.09 |  | Sqm |  | 37.1413
|  |  |  | 26.31 | 0.15 |  | Sqm |  | 3.9465
|  |  | SPA | 5.0535 | 3.65 |  | Sqm |  | 18.4453
|  |  |  | 10.33 | 0.15 |  | Sqm |  | 1.5495
|  |  | Passage | 5.9 | 1.2 |  | Sqm |  | 7.08
|  |  | Reception | [5 empty] | 15.57
|  |  | Admin | [5 empty] | 4.37
|  |  |  | 1.835 | 0.15 |  |  |  | 0.27525
|  |  |  | 2.873 | 0.25 |  |  |  | 0.71825
|  |  | Disable Restroom | 3.65 | 1.6 |  | Sqm |  | 5.84
[7 empty] | Total Qty |  | 94.9361
2000
189872.13
2 |  | MOISTURE RESISTANT GYPSUM CEILING : Providing and fixing MR grade gypsum board false ceiling including providing and fixing GI grade 175 (120 gm/m2) perimeter, channels (20 x 30 x 27 x 0.50mm thick) fixed to brick masonry / partition / hanging with existing ceiling / existing M.S. frame work and suspended GI intermediate channel. Rate to include making necessary cut out/opening for light fitting A C diffuser, cove, pelmet, band etc. The cut out to have perimeter channel of size 20x27x30x.5mm all round and supported suitably and finally finished with gypsum board and finally finished with two or more coat of paint (Paint cost excluded) of approved make & shade with required tapping the joints, base primer, putty complete in all respect. Rate quoted should be included for all design work, Nothing to be paid extra for design work. ( Actual Plain Area to be measured & paid ).( Male, Female, & Handicap Toilet false ceiling )
|  |  | Male Restroom | 8.1 | 2.35 |  | Sqm |  | 19.035
|  |  | Femail Restroom | 3.9 | 2.45 |  | Sqm |  | 9.555
[7 empty] | Total Qty |  | 28.59
2300
65757
4 |  |  |  | 10.073 | 8.999 |  |  |  | 90.6469
|  |  |  | 8.1425 | 7.092 |  |  |  | 57.7466
|  |  |  | 6.6255 | 2.32 |  |  |  | 15.3712
[7 empty] | Total Qty |  | 163.7647
1850
302964.6895
[8 empty] | Total Amount |  |  | 558593.8195

## Civil JMR RA Bill 3
Date:- 22.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF GRID CELLING
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Nos | Qty. | Rate | Amount
1 |  | GI Metal Ceiling Clip in plain Bevelled edge global white colour plain tiles of size 600x600 and 0.5 mm thick with 25 mm height, made of G I sheet having galvanizing of 100 gms/ sqm (both sides inclusive) and electro statically polyester powder coated of thickness 60 microns (minimum), including factory painted after bending. ( For Kitchen false ceiling | Kitchen Celling | 7.3 | 3.6 |  | Sqm | 1 | 26.28 | 3600 | 94608
[7 empty] | Total Qty .in Sqm |  | 26.28
[7 empty] | Rate in Rupees |  | 3600
[7 empty] | Total Amount in Rupees |  | 94608
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF WALL TILE IN KITCHEN
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Nos | Qty. | Rate | Amount
1 | 1 | Providing and fixing 1st Quality Vitrified wall tiles conforming to IS:15622 (thickness to be specified by the manufacturer), of approved make, in all colours, shades as approved by Engineer-in-Charge for dado fixed with cement based high polymer modified quick set tile adhesive ( water based ) conforming to IS : 15477, in a average 6 mm thickness including spacer and filling the joints with epoxy cementious grout of pigment to match the shade of the tiles to give a smooth surface. complete as per detail dwg
| b | Wall Tile - Type 2 : Size as approved, Base Price 55 per sft - | For Kitchen | 31.455 |  | 2.4 | Sqm | 1 | 75.492
[7 empty] | Total Qty. in Sqm |  | 75.492
[7 empty] | Rate in Rupees |  |  | 2300
[7 empty] | Total Amount in Rupees |  |  |  | 173631.6
| 5a | SCREEDING WORK : Providing & laying Screeding with 1:2:4 cement conc. (1 cement :2 coarse sand :4 graded stone agg 10mm nominal size ) in line and level including required channel shuttering, curing, troller finish etc. complete in all respect |  |  |  |  | CUM |  | 21 | 7500 | 157500
| 6 | NEAT CEMENT SLURRY : Extra for above screeding work for floating quote of neat cement punning upto 6mm including curing etc. where as carpet, wooden floor, vinyl floor comes & as per site required. |  |  |  |  | SQM |  | 21 | 120 | 2520
| 10 | FLOOR FILLING : Providing and laying fillers of AAC Light weight block filling with full /break pieces as per the requirements of Approved make as per LOM and size as required to Fill/Raise the floor with conceal the pipes, drains, etc as per site requirement. The filling to be cured and Compacted to prevent any voids and dust pockets . The filler to be adequately leveled to receive the finished flooring as |  |  |  |  | CUM |  | 15 | 2300 | 34500
[8 empty] | SUB TOTAL IN RUPEES |  |  | 368151.6
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF BASIN COUNTER WORK
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Nos | Qty. | Rate | Amount
1 | 5 | BASIN COUNTER WORK : Providing & fixing Basin counter with the understructure to be made in MS Angle 45x45mm with 4mm thick of appropriate cross section and to be treated with anti rust paint and enamel black paint. The MS frame to be clad with 12mm thick bison board / Marine ply to receive the final finish material of the counter. Counter to be 600 mm deep with a vertical fascia of 100mm on splash & upto 500mm on front drop vertical facia to be clad with the finish material as approved. The counter to have required cutout for basin, Tap faucet, drain, dustbin etc. (Excl. cost of Stone
|  |  | Female Restroom | 2.5 |  |  | Rmt | 1 | 2.5
|  |  | Male Restroom | 2 |  |  | Rmt | 1 | 2
[7 empty] | Total Qty.in Rmt |  | 4.5
[7 empty] | Rate in Rupees |  |  | 10500
[7 empty] | Total Amount in Rupees |  |  |  | 47250
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF POP PUNNING
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Nos | Qty. | Rate | Amount
1 | 8 | POP PUNNING : Providing & applying Water Resistant and Quick Drying, Non Curable Type of average upto 12mm thick plaster of Paris and wiremesh at joints of diff. material to the walls and columns in square plumb line and level. The cost to include scraping and removing the existing neeru finish and also the hacking the surface of walls/columns. After leveling, the surfaces to be finished to receive paint . Rate to include provisioning of grooves as per design. The POP puning to be carried out 100mm above the finished ceiling level and not for the area above
Premioum Lounge
|  |  | Back Wall | 4 |  | 3.3 | Sqm | 1 | 13.2
0
|  |  | BAR Area | [5 empty] | 0
|  |  | Wall | 28 |  | 3.3 | Sqm | 1 | 92.4
0
|  |  | Electrical Room | [5 empty] | 0
|  |  | Wall | 6.273 |  | 3.3 |  | 1 | 20.7009
0
0
[7 empty] | Total Qty in Sqm |  | 126.3009
[7 empty] | Rate in Rupees |  |  | 370
[7 empty] | Total Amount in Rupees |  |  |  | 46731.333
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF CELLING PAINT
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Nos | Qty. | Rate | Amount
1 | b | Texture Paint Type 2 - (Lenaluck - Hammering shade) : Base Rate of Texture paint @ 85/- Per sft, Providing & Applying Resin Texture (SKK Lenaluck) (Spray Finish/Roller Finish) to be on (smooth plaster/concrete) surface with (spray/roller) textured coating by SKK, which is Acrylic resin body (spray/roller) textured coating with Singapore Green Mark Certificate. Primer coat to be of (SKK Color Binder EX), Texture Coat: SKK Lenaluck (Spray Finish/Roller Finish), a water reducible modified acrylic resin reinforced (spray/roller) body texture, Final Coat to be (Compo Silicon W55), scaffolding including. | Celling Paint as per BOQ |  |  |  | Sqm | 1 | 278.5 | 1320 | 367620
[7 empty] | Total Qty. in Sqm |  | 278.5
[7 empty] | Rate in Rupees |  | 1320
[7 empty] | Total Amount in Rupees |  | 367620
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF WALL PAINT
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Nos | Qty. | Rate | Amount
1 | 2 | Plastic Emulsion Paint : Providing & Applying three or more coats of Acrylic Plastic Emulsion Paint of approved make & shade including preparation of base by Acrylic based putty & primer complete in all respect. ( Ceiling/wall as per design and site
Premioum Lounge
|  |  | Left Wall | 8.615 |  | 3 | Sqm | 1 | 25.845
|  |  | Right Wall | 9.87 |  | 3 | Sqm | 1 | 29.61
|  |  | Back Wall | 4.09 |  | 3 | Sqm | 1 | 12.27
|  |  | Front Wall | 3.62 |  | 3 | Sqm | 1 | 10.86
|  |  | Door Deduction | 1.2 |  | 2.4 | Sqm | 1 | -2.88
|  |  | Glass Door Deduction | 2.1 |  | 2.4 | Sqm | 1 | -5.04
0
|  |  | Reception | [5 empty] | 0
|  |  | Front Wall | 7 |  | 3.2 |  | 1 | 22.4
0
|  |  | Adime | [5 empty] | 0
|  |  | Inside Wall | 8.417 |  | 3.2 |  | 1 | 26.9344
|  |  | Door Deduction | 1.2 |  | 2.4 |  | 1 | -2.88
0
|  |  | Bar Area | [5 empty] | 0
|  |  | Wall | 23.95 |  | 3.2 |  | 1 | 76.64
0
|  |  | Dinning Area | [5 empty] | 0
|  |  | Wall | 34.44 |  | 3.2 |  | 1 | 110.208
|  |  | Glass Door Deduction 1 | 3 |  | 2.4 |  | 1 | -7.2
|  |  | Glass Door Deduction 2 | 3 |  | 2.4 |  | 1 | -7.2
|  |  | Passage Door Deduction | 1.2 |  | 2.4 |  | 1 | -2.88
0
|  |  | Kitchen Wall | [5 empty] | 0
|  |  | Door Partation wall | 5.456 |  | 3.2 |  | 1 | 17.4592
|  |  | Door Deduction | 1.232 |  | 2.1 |  | 1 | -2.5872
|  |  | Kitchen Inside Wall | 27.205 |  | 0.3 |  | 1 | 8.1615
0
|  |  | Restroom Passage | [5 empty] | 0
|  |  | Wall | 13.849 |  | 3.2 |  | 1 | 44.3168
|  |  | Door Deduction | 1.2 |  | 2.4 |  | 5 | -14.4
0
|  |  | SPA and Electrical Room | [5 empty] | 0
|  |  | Wall | 24.959 |  | 3.2 |  | 1 | 79.8688
|  |  | Door Deduction | 0.9 |  | 2.4 |  | 1 | -2.16
|  |  | Glass Door Deduction | 2.715 |  | 2.4 |  | 1 | -6.516
0
|  |  | Dinning Column | [5 empty] | 0
|  |  |  | 7.8 |  | 3.2 |  | 1 | 24.96
0
|  |  | Reception Column | [5 empty] | 0
|  |  |  | 1.2 |  | 3.2 |  | 1 | 3.84
0
|  |  | BAR Column | [5 empty] | 0
|  |  |  | 1 |  | 3.2 |  | 1 | 3.2
0
|  |  | ISLAND Column | 3.1 |  | 3.2 |  | 1 | 9.92
[7 empty] | Total Qty.in Sqm |  | 452.7505
[7 empty] | Rate in Rupees |  |  | 400
[7 empty] | BOQ Qty 200 |  | 200 | NT Qty | 252.751
[7 empty] | Total Amount in Rupees |  |  |  | 181100.2

## Civil JMR RA Bill 8
Date:24/03/2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-08 MEASUREMENT SHEET OF CIVIL WORK
S. No. | Item. Code | Specification | Descreption | L | B | H | Unit |  | Site Qty | WOQ | Rate | Amount | Extra Qty | Remarks
| B | CIVIL WORK
| 2 | LINTEL : R.C.C- ( 1 : 1.5 : 3 ) ( 1 cement : 1.5 coarse send : 3 graded stone aggregate 20mm nominal size ) for lintels, Lintel in arch etc. or where ever required I/c reinforcement for lintel 4no 12mm dia bars with 8mm dia rings @ 150c/c & centering shuttering for all levels and height.( Door Lintel length as per drawing 100mm wide x 100mm height ) The rate includes de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge.
|  |  | Above kitchen door | 1.4 |  |  | Rmt.
|  |  | Female Restroom door | 1.2 |  |  | Rmt.
|  |  | Male Restroom | 1.2 |  |  | Rmt.
|  |  | Disable Restroom | 1.4 |  |  | Rmt.
[7 empty] | Rmt. |  | 5.2 | 9.9 | 944 | 4908.8
| 4 | RCC COUNTER : R.C.C in ( 1: 1.5 : 3 ) for counters, slabs ( upto 75mm thick) I/c reinforcement 10mm dia bar @ 150mm c/c both ways & centering shuttering for all levels and height. The rate includes de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge
|  |  | Female Restroom | 2.3 | 0.55 |  | Sqm |  | 1.265
|  |  | Male Restroom | 1.75 | 0.55 |  | Sqm |  | 0.9625
| C | FLOORING WORK/CLADDING WORK |  |  |  |  | Sqm |  | 2.2275 | 2.71 | 1950 | 4343.625
| 3.1 | TILE FLOORING
| 1 | Providing and laying Vitrified Antiskid tiles in floor in different sizes (thickness to be specified by the manufacturer) with water absorption less than 0.08% and conforming to IS:15622, of approved brand & manufacturer, in all colours and shade, laid on 20 mm thick cement mortar 1:4 (1 cement: 4 coarse sand) jointing with grey cement slurry @3.3 kg/sqm including spacers with epoxy cementious grout matching to pigments etc. The tiles must be cut with the zero chipping diamond cutter only . Laying of tiles will be done with the notch trowel, plier, wedge, clips of required thickness, leveling system and rubber mallet for placing the tiles gently etc, cost also include the Protection covering of tile with 6mm Bubble sheet with jointing using clear tape till handover with complete as per advised by the Project Incharge.
| a | Vitrified Tile Floor - Type 1 : Size as approved, Base Price 65 per sft
|  |  | Male Restroom | 5.26 | 2.2 |  | Sqm |  | 11.572
|  |  | Female Restroom | 4 | 2.34 |  | Sqm |  | 9.36
Disable Restroom
[7 empty] | Sqm |  | 20.932 | 39.02 | 2300 | 48143.6
| 3.3 | TILE STRIPS : P/F tile strips made out of vitrified tiles of size as per manufacturer as approved colour, shade, texture, design in varying strip sizes (38/50/25 mm wide & 200/300/400 mm long) of approved make & manufacture for dado fixed with cement based high polymer modified quick set tile adhesive ( water based ) conforming to IS : 15477, in a average 3mm thickness including filling the joints mixed epoxy cementious grout with pigment to match the shade of the tiles to give a smooth surface. Base Rate of Tile @ 65 per sf
|  |  | BAR Area |  |  |  | Sqm |  | 0 | 5 | 2300 | 0 |  | ON HOLD
| 3.4 | TILE SKIRTING : Providing and fixing Vitrified tile Skirting upto 100mm high fixed with 12 mm thick bed of cement mortar 1:3 (1 cement : 3 coarse sand) and jointing with grey cement slurry @ 3.3kg per sqm, including pointing and joint finish in epoxy cemetious grout with pigment of matching shade complete. Base Rate of Tile @ 65 per sft
|  |  | Kichen | 15 |  |  | Rmt |  | 0 | 15 | 1500 | 0 |  | ON HOLD
| 4 | CORION CLADDING : Providing and fixing 12mm thick Solid surface ( Corian ) for Basin Counter/Ledge/Jamb/cill etc fixed with adhesive of approved make including jointing with adhesive mixed with pigment to matching the shade of solid surface complete as per drawing .including edge chamfering, buffing, polishing complete in all respect. ( Basic cost of solid surface ( Corian ) @ Rs. 750/- Sft )( Actual size to be measured & paid ).
Female Restroom
|  |  | Left wall | 2.3 | 2.9 |  | Sqm |  | 6.67
|  |  | Right wall | 3.32 | 2.9 |  | Sqm |  | 9.628
|  |  | Basin Counter | 2.3 | 1.04 |  | Sqm |  | 2.392
|  |  |  | 1.32 | 0.4 |  | m |  | 0.528
|  |  | Shink | 1.5 | 0.3 |  | Sqm |  | 0.45
Male Restroom
|  |  | Right wall | 3 | 2.18 |  | Sqm |  | 6.54
|  |  | Basin Counter | 3.44 | 1.04 |  | Sqm |  | 3.5776
|  |  |  | 0.7 | 0.9 |  | Sqm |  | 0.63
|  |  | Shink | 1.5 | 0.3 |  | Sqm |  | 0.45
[7 empty] | Sqm |  | 30.8656 | 35.06 | 13000 | 401252.8
| 12 | KOTA STONE FLOORING : Provide and lay 25mm thick, machine cut and polished Kota Stone of aprroved colour and texture laid over 20 mm thick base cement mortar 1:4 (1 cement : 4 coarse sand), joints treated with white cement, mixed with matching pigment, epoxy touch ups, including rubbing polihing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with polythin+POP as per advised by the Project Incharge. ( Basic cost of Granite stone @ Rs. 65/- per sft)
|  |  | Kitchen | 7 | 3.41 |  | Sqm |  | 23.87 | 26.67 | 1750 | 41772.5
| D | DOOR WINDOW WORK
| 1 | DOOR / WINDOW FRAME : Providing and fixing door and window frames made out of Natural Fiber Polymer Composite Wood/Board (Eco freindly, Recyclable) with necessary groove ( 6mm x 6 mm ) & single rebate including necessary M.S. hold fasts in cement concrete blocks 1: 2: 4 / fasteners ( expendable 10mm dia ) on either side fixed in line and level. The frame to be treated with necessary anti termite chemical and fire retardant paint on partition side & finally finished with PU polish/Paint complete in all respect
|  |  | Kitchen | 5.95 | 0.1 | 0.1 | Cum |  | 0.0595
|  |  | SPA | 5.854 | 0.1 | 0.1 | Cum |  | 0.05854
|  |  | Electrical Room | 5.712 | 0.1 | 0.1 | Cum |  | 0.05712
|  |  | Male Restroom | 5.724 | 0.1 | 0.1 | Cum |  | 0.05724
|  |  | Female Restroom | 5.724 | 0.1 | 0.1 | Cum |  | 0.05724
|  |  | Disable Restroom | 5.874 | 0.1 | 0.1 | Cum |  | 0.05874
|  |  | Admin room | 5.7 | 0.1 | 0.1 | Cum |  | 0.057
[9 empty] | 0.40538 | 0.15 | 150000 | 38307 | 0.25538
| 3 | LAMINATED DOOR SHUTTER : Providing and fixing 38 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both sides of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, vision slit as per design with 6mm thick glass with wooden beading ( white ash wood ), handles,motrise dead lock with one side key knob cylinder finish in rose gold SS etc. complete in all respect. .( Basic cost of laminate @ Rs. 90/- sft ) ( Actual size of shutter to be measured & paid )
| a | With Vision panel - Size 250mm x 900mm or as per design approved -for SPA&Admin
|  |  | SPA | 2.4 | 1 |  | Sqm |  | 2.4
|  |  | Admin | 2.4 | 0.9 |  | Sqm |  | 2.16
[9 empty] | 4.56 | 5.28 | 10500 | 38304 | 3.648 | 80% Released
| a | Single Leaf Door-900/1200mm long x2400mm high ,For Toilet doors |  |  |  |  | Nos |  | 3 | 3 | 17000 | 40800 | 2.4 | 80% Released
| b | Without vision Panel-Kitchen and Electrical Room
|  |  | Kitchen | 2.4 | 1.2 |  | Sqm |  | 2.88
|  |  | Electrical Room | 2.4 | 0.9 |  | Sqm |  | 2.16
[9 empty] | 5.04 | 8.15 | 9700 | 39110.4 | 4.032 | 80% Released
| 6 | FRAMED GLASS PARTITION : Providing and installation of framed allumunium with vision glass partition sytem of approved series and brand as per approved list of make, fixed glass partition using 10mm thick Toughened glass in proprietary natural anodised approved aluminium sections with Concealed sealing (No visible Gaskets/Seals) with acoustic. The profile will have Carpert Groove at the Bottom on both sides for accommodating max. 8mm carpets. Glass to be fixed with help of Proprietary Stability GRIPPER Clamp to have a stable system. It should consists of intermediate slim junction profiles for Glass to Glass vertical joints, 90 Degree L Junction and T Junction profiles suitably to be used as per room configuration designs. No VISIBLE Clip Lines to provide clutter free view at both side of section. The Glass to be Offset mounted towards outer edge leading to minimum aluminium frame on one side. Optional Profile Bottom Seal pair for additional acoustic if required. All Profiles are min 1.5mm thickness excluding 20 microns of Anodizing, Standards applicable • Structural stability test accordance to BS 5234: Part2:1992 & EN 1991-1-1:2002 • Acoustic test for sound insulation in accordance to DIN EN ISO 10140-2 ASTME E 90
| a | Single Glazed Partition, Size 50mm wide x 30mm high, color as approved |  |  |  |  | Sqm |  | 0 | 4.38 | 7609 | 0 |  | ON HOLD
| b | Single Glazed Partition, Size 100mm wide x 30mm high, color as approved
|  |  | P Lounge | 2.16 | 2.7 |  | Sqm |  | 5.832
|  |  | Dinning Area | 2.96 | 2.7 |  | Sqm |  | 7.992
|  |  |  | 2.79 | 2.7 |  | Sqm |  | 7.533
|  |  |  | 2.6 | 2.7 |  | Sqm |  | 7.02
[9 empty] | 28.377 | 28.51 | 8600 | 0 |  | ON HOLD
| 7 | Providing & fixing Hydraulic sleek door closer of approved make including all fixing arrangement complete in all respect. Door weight capacity upto 80kg, with 10year manufacturer warranty complete as per design approved. | Admin,SPA, Kitchen,Electrical, |  |  |  | Nos |  | 0 | 4 | 6700 | 0 |  | ON HOLD
| 8 | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in rose gold SS ) of approved make including all fixing arrangement complete in all respect. | Toilets, spa,Kitchen |  |  |  | Nos |  | 0 | 5 | 6500 | 0 |  | ON HOLD
| 11 | Providing & fixing 50mm dia SS 304 grade (finish : As per approved ) 600mm Long H type Handle including all the accessories and fitting as per requirement complete. |  |  |  |  | Set |  | 0 | 2 | 6500 | 0 |  | ON HOLD
| E | OTHER WOOD WORK FOR WALL PANELLING, PARTITIONS & STORAGE
| 2 | PLY /BOARD CLADDING (One Layer/Double Sided) : Providing and fixing 12mm thick Natural Fiber Polymer Composite Wood/Board (Eco freindly, Recyclable) board of approved make on existing M.S. frame work including all fixing arrangement complete in all respect . (Partition Length to be measured only)
Premium Lounge
|  |  | Right glass door inside |  | 640 | 3300 | Sqm | 1 | 2.112
|  |  | Left glass door inside |  | 640 | 3300 | Sqm | 1 | 2.112
|  |  | Above glass door inside |  | 600 | 2140 | Sqm | 1 | 1.284
|  |  | Left wall outer glass door side |  | 740 | 2750 | Sqm | 1 | 2.035
|  |  | Right wall outer glass door inside |  | 675 | 2750 | Sqm | 1 | 1.8563
Reception
|  |  | Back side wall |  | 6990 | 3400 | Sqm | 1 | 23.766
|  |  | Left wall outer glass door side |  | 1220 | 2750 | Sqm | 1 | 3.355
|  |  | Admin Office | [5 empty] | 0
|  |  | Outer Wall |  | 6920 | 3400 | Sqm | 1 | 23.528
Above door outer
|  |  | Door deduction |  | 0.9 | 2.4 | Sqm | 1 | -2.16
|  |  | Column Clidig |  | 560 | 3300 | Sqm | 1 | 1.848
|  |  | Dining Area | [5 empty] | 0
|  |  | Inside Wall |  | 2500 | 3300 | Sqm | 1 | 8.25
|  |  | Above glass door inside with reception |  | 2980 | 600 | Sqm | 1 | 1.788
|  |  | Above glass door inside with SPA |  | 2780 | 600 | Sqm | 1 | 1.668
|  |  | Outer wall glass door side |  | 5100 | 2750 | Sqm | 1 | 14.025
|  |  | Outer column Cliding | [5 empty] | 0
|  |  | RCC Column |  | 6800 | 3330 | Sqm | 1 | 22.644
|  |  | BAR Area | [5 empty] | 0
|  |  | Column |  | 940 | 3240 | Sqm | 1 | 3.0456
|  |  | Kitchen wall |  | 3550 | 3300 | Sqm | 1 | 11.715
|  |  | SPA | [5 empty] | 0
|  |  | Left wall glass door inside |  | 900 | 3100 | Sqm | 1 | 2.79
|  |  | Above glass door inside |  | 400 | 2650 | Sqm | 1 | 1.06
|  |  | Bathroom side wall |  | 1470 | 3300 | Sqm | 1 | 4.851
|  |  | Left wall glass door outre side |  | 725 | 2750 | Sqm | 1 | 1.9937
|  |  | Right wall glass door outer side | [5 empty] | 0
Electrical Room
|  |  | Outer wall |  | 1850 | 3400 | Sqm | 1 | 6.29
|  |  | Inner wall |  | 1770 | 3400 | Sqm | 1 | 6.018
|  |  | Above door |  | 550 | 1100 | Sqm | 2 | 1.21
|  |  | Door side | [5 empty] | 0
|  |  | Above Door Passage |  | 900 | 1100 | Sqm | 2 | 1.98
|  |  | Disable bathroom Above door |  | 600 | 1100 | Sqm | 2 | 1.32
|  |  | Kitchen Column cliding |  | 800 | 3300 | Sqm | 2 | 5.28
[9 empty] | 155.6646 | 192.33 | 3200 | 498126.72
| 8 | Providing and fixing Under Counter storage with necessary drawers & Shelves as per design made out of 19mm thick Marine ply board structure fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with designer tile, storage includes required shutter / drawer storage unit with required shelves , shutters with required hardware like concealed channel / handle, knobs, magnetic catcher, drawer lock, hinges, shutter lock, drawer channel etc. all are superior quality of approved make & 100mm high Gold Plated finish Aluminium skirting at floor level complete in all respect. also the Storage top will be finish with Marble top in 20mm thickness with dimaond polish all over surface and edge to be double strip with gola polish complete in all respact of detail drawing. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, , Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
| a | Size : 3500mm long x 600mm deep x 850mm high,For bar back area |  |  |  |  | Nos |  | 1 | 1 | 72765 | 50935.5 | 0.7 | 70% Released
| b | Size : 1300mm long x 600mm deep x 850mm high,For SPA basin counter |  |  |  |  | Nos |  | 1 | 1 | 35000 | 24500 | 0.7 | 70% Released
| 9 | Providing and fixing partly open partly closed Servery counter storage as per drawing made out of 19mm thick BWP / Marine board structure fixed with the help of all necessary hardware like nail and fasteners and all closed internal area of storage to be finished with 0.8mm thick laminate and open area with external finish of 1mm thick SS Sheet cladding of triangle shape emboss texture with white Gold Leafing antique Coating finish all over apart shelf as marble with double patti edge will be fixed with diamond polish shelves for open space, All the external surface area shall be wrapped and finished in designer tile & top surface of survery storage to be finished with plain polish Marble fixed with adhesive & 100mm high Gold Plated finish Aluminium skirting at floor level, including required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, drawer channel, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
| a | Size 5500mm long x 600mm deep x 850mm high -For kitchen out side survery area |  |  |  |  | Nos |  | 1 | 1 | 125000 | 87500 | 0.7 | 70% Released
| b | Size 3529mm long x 600mm deep x 850mm high -For bar area open lounge |  |  |  |  | Nos |  | 1 | 1 | 72765 | 50935.5 | 0.7 | 70% Released
| c | Size 2000mm long x 600mm deep x 850mm high -For P lounge |  |  |  |  | Nos |  | 1 | 1 | 41580 | 29106 | 0.7 | 70% Released
| 10 | Providing and fixing ISLAND Counter storage as per drawing, Storage as per drawing made out of 19mm thick BWP / Marine board structure fixed with the help of all necessary hardware like nail and fasteners and all closed internal area of storage to be finished with 0.8mm thick laminate and open area with external finish of 1mm thick SS Sheet cladding of triangle shape emboss texture with white Gold Leafing antique Coating finish all over apart shelf as marble with double patti edge will be fixed with diamond polish shelves for open space (If Any), All the external surface area shall be wrapped and finished in designer tile & top surface of survery storage to be finished with plain polish Marble fixed with adhesive & 100mm high Gold Plated finish Aluminium skirting at floor level, including required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, drawer channel, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
| a | Size 4000mm long x 1200mm deep x 850mm high - kitchen outside servery area |  |  |  |  | Nos |  | 1 | 1 | 121400 | 84980 | 0.7 | 70% Released
| 11 | Providing and fixing High counter Console as per drawing, structure made out of 19mm thick BWP / Marine board construct in boxing form and fixed to existing wall/panneling fixed with the help of all necessary hardware like nail and fasteners all internal back exposed area surface to be finished with 1mm thick laminate , external front 1mm thick SS Sheet cladding of triangle shape emboss texture with white Gold Leafing antique Coating finish & top surface to be finished with plain diamond polish Marble fixed with adhesive & 100mm high Gold plated finish Aluminium skirting at floor level all around , (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface SS Texture Emboss Antique finish coating Sheet @ Rs.2500/- per Sft, Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
| a | Size 7753mm long x 400mm wide from top with below covered boxing structure x 1050mm high for Around large tree hight counter |  |  |  |  | Nos |  | 1 | 1 | 92400 | 64680 | 0.7 | 70% Released
| 12 | Providing and fixing High Counter Ledge as per drawing, made out of 19mm thick BWP Board / Ply structure construct in L form with latak 35mm high in front to covered the base supported MS painted 25x25mm angle frames fixed at maximum 1200mm c/c with the help of all necessary hardware like nail and fasteners. all the Ply surface latak / top finished with plain Marble with diamond polish fixed with adhesive complete as per detail drawing. (Base Price of Marble @ Rs. 450/- per sft )
| a | Size 3935mm long x 400mm wide from Top For high counter ledge |  |  |  |  | Nos |  | 1 | 1 | 46200 | 32340 | 0.7 | 70% Released
| 13 | Providing and fixing Reception Table ( Size : 1000mm long x 1000mm deep x 750/1050mm high) made out of 19mm thick BWP Board / Ply structure including necessary hardware of superior quality, structure made in double ht form which make front portion along with sides finished in Italion Marble finished with flutted pattern all polish, then worktop / double ht vertical screen in Acrylic surface finish of 12mm thick on base ply with complete buffing /rubbing as per design. front facade, sides & top finish with Italian marble stone of approved make, shade & texture including all fixing arrangement ,grinding polishing, edge chamfering & polishing & all internal surface to be finished with 0.8mm thick laminate & at floor level 100mm high skirting & top & sides edging finished with PVD coated color as approved finish in aluminium . complete in all respect. ( Basic cost of internal laminate @ Rs.28/- sft & external laminate @ Rs90/-Sft & Italian marble stone @ Rs. 1200/- sft + 500 per sft for flutted CNC cutting) & (Acrylic surface @ 900/- per sft, Basic cost PVD finish Aluminium Skirting @ Rs. 450/-Rmtr,) |  |  |  |  | Nos |  | 2 | 2 | 45000 | 63000 | 1.4 | 70% Released
| 14 | Providing and fixing BAR COUNTER front Counter as per drawing structure with necessary drawers & Shelves as per design made out of 19mm thick Marine ply board structure fixed with the help of all necessary hardware like nail and fasteners and all internal surface of Partition / storage to be finished with 0.8mm thick laminate & external surface to be finished with designer tile, internal area shall be finished with worktop at upto 850mm high level with Marble finish polish / Double ht top also finihed in same mable with polish complete along with shape and design . 100mm high Gold Plated finish Aluminium skirting at floor level complete in all respect. Marble top in 20mm thickness with dimaond polish all over surface and edge to be double strip with gola polish complete in all respact of detail drawing. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, , Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
| a | Size 3900mm long x overall 700mm deep / Double ht 300mm wide from top x 850/1050mm high For bar front counter |  |  |  |  | Nos |  | 1 | 1 | 64449 | 45114.3 | 0.7 | 70% Released
| 22 | FEATURE ROUND CNC CUT SCREEN : Providing & fixing feature round cnc cut screen made in 1mm thick SS sheet with factory made laser cut design and finished in PVD finished color as approved, Entire RIM will be moulded with Pencil round edge & 3mm dia tube shot welded on end circumference with neat / clean finish buffing prior to PVD coating application. Finished RIM shall be packed and cover with temprory packing wooden patti /frame/box to avoid any damgaes and deliver with safety at site, RIM will be install on Existing wall /partition with heavy duty SS clamp / bracket support including fastner complete as per satisfactory of Project Incharge
| b | Art work Type 1 : Round size 1500mm dia |  |  |  |  | Nos |  | 2 | 2 | 54000 | 75600 | 1.4 | 70% Released
| 24 | TREE ELEMENT : Providing and fixing Tree of Life Design Element made in part and combine in Tree Element as per design, part element is desicribe and detail below with the specification and material used. Also the element has petal and leaves feature with variable sizes of fixed / decorative light as per the design and requirement which include the all provision for base support and other allied requirements
| A | FOR BAR AREA
| 1 | TRUNK ELEMENT : made in 15mm dia SS pipe with PVD finish as per color /shade approved or detail drawing. Pipe to be fixed and welded with inner circle pipe fitted for support in bottom and top where curve form start, also the curve and horizontal form in ceiling shall be be fitted with ceiling support with neat & clean finish complete as per detail drawing. pipe length is variable as per the design and provision petal/leaves attachment complete in all respact or advise by the Architect. (note : Length to measured as per actual and paid) | BAR Tree |  |  |  | Rmt |  | 208 | 211.67 | 4500 | 655200 | 145.6 | 70% Released
| 7 | Honeycell Blinds : Providing and fixing Translucent Honeycell Blinds. The fabric shall be non woven polyester in double cell structure with high quality sealing in variable of light filtring option. All complete (shade a approved; Make : Deck)
|  |  | P Lounge | 2.36 | 2.9 |  | Sqm |  | 6.844
|  |  | Dinning Area | 3.07 | 2.9 |  | Sqm |  | 8.903
|  |  | Dinning Area | 3.09 | 2.9 |  | Sqm |  | 8.961
|  |  | SPA | 2.95 | 2.9 |  | Sqm |  | 8.555
[9 empty] | 33.263 | 37.31 | 3200 | 90475.36 | 28.2735 | 85% Released
| 8 | Motor For Blind/Curtain : Providing and installing wired / Wirefree, plug-and-play curtain / Blind motorization by Deck / Somfy or approved make. Designed for silence, Manual operation possible in case of power failure, Adjustable speed, Soft start and Soft stop, Touch Motion, Powered / Battery operated motor, model as per requirement and approved. motor for single roller track / Curtain track considered. | P Lounge=2 Dinning Area=4 SPA=2 |  |  |  | Nos |  | 8 | 7 | 27000 | 216000 | 1
| 9 | Remote : Providing a five channel remote control to control one piece or one group of equipments simple intuitive control with operating and memory “Memory” function to memorize your favourite position of the application and find it instantly by pressing “memory” button Modern aesthetic design, comfortable in the hand thanks to a modern soft touch finish, discreet and elegant wall support. all complete single Remote to operate the motorised curtain & blind. | P Lounge=1 Dinning Area=2 SPA=1 |  |  |  | Nos |  | 4 | 3 | 1200 | 4800 | 1
| G | FINISHING WORK | [10 empty] | 0
| 4 | WallPaper : Providing & fixing Fabric backed Vinyl Wall covering(10.05mtr. X .52mtr ) ( 300gsm Type-II) fire Retardant as per approved sample including all fixing arrangement complete in all respect. ( Basic cost of Fabric backed Vinyl Wall covering @ Rs. 90/- per sft ) ASper dwg elevation | P Lounge,BAR Area,Dinning Area,SPA,Passage,ALL Columns |  |  |  | Sqm |  | 312 | 409.16 | 1350 | 421200 | -97.16
| d | Wall Art element 1 - As per design and approved, Base range Rs. 8500/- each, custom made SS Framed /1mm thick sheet of PVD Mirror finish Petals. Size 225mm high x 100mm wide | P Lounge,BAR Area,Dinning Area |  |  |  | Nos |  | 13 | 13 | 12500 | 162500
| e | Wall Art element 2 - As per design and approved, Base range Rs. 15000/- each, custom made SS Framed /1mm thick sheet of PVD Mirror finish Petals. Size 450mm high x 200mm wide | P Lounge,BAR Area,Dinning Area |  |  |  | Nos |  | 23 | 23 | 22500 | 517500
| C | FLOORING WORK/CLADDING WORK
| 7 | MARBLE CLADDING : Providing and fixing Marble work 16-18 mm thick, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge
| a | Marble Cladding Type 1 : Base Price of Marble @ 450/- Per sft, For counter splash area
|  |  | ISLAND Counter | 5.919 | 0.25 |  | Sqm |  | 1.4797
|  |  | BAR Counter | 3.46 | 0.25 |  | Sqm |  | 0.865
|  |  | Buffar Counter | 2.05 | 0.25 |  | Sqm |  | 0.5125
|  |  |  | 1.5 | 1.1 |  | Sqm |  | 1.65
|  |  | High Counter | 3.512 | 0.1 |  | Sqm |  | 0.3512
|  |  | SPA Counter | 2.4 | 0.25 |  | Sqm |  | 0.6
|  |  | Male Basin Top Counter | 1.75 | 0.2 |  | Sqm |  | 0.35
[9 empty] | 0 | 11.86 | 9300 | 0 |  | ON HOLD
| 8 | MARBLE DESIGNER CLADDING : Providing and fixing Marble designer work 16 18 mm thick marble with random size cut pcs in 200/300/400mm high x 75/100/125mm in width with making taper cut on edge to ake 4mm wide groove on vertical/horizontal as per design, all the surface, edges, V groove shall be mirror polished, all the marble will be jet water machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone area legth x height to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge
| a | Marble Designer Cladding Type 1 : Base Price of Marble @ 450/- Per sft, For toilets wall
FemaleRestroom
|  |  | Front wall | 3.78 |  | 2.7 | Sqm |  | 10.206
|  |  | Back wall | 3.78 |  | 2.7 | Sqm |  | 10.206
|  |  | Door Deduction | 2.4 |  | 0.9 | Sqm |  | -2.16
Male Restroom
|  |  | Front wall | 5.42 |  | 2.7 | Sqm |  | 14.634
|  |  | Back wall | 5.42 |  | 2.7 | Sqm |  | 14.634
|  |  | Left Wall | 2.14 |  | 2.7 | Sqm |  | 5.778
|  |  | Door Deduction | 2.4 |  | 0.9 | Sqm |  | -2.16
|  |  | Mirror Deduction | 1.75 |  | 1.15 | Sqm |  | -2.0125
Disable Restroom
|  |  | Front wall | 3.55 |  | 2.7 | Sqm |  | 9.585
|  |  | Back wall | 3.55 |  | 2.7 | Sqm |  | 9.585
|  |  | Right wall | 1.52 |  | 2.7 | Sqm |  | 4.104
|  |  | Left wall | 1.52 |  | 2.7 | Sqm |  | 4.104
|  |  | Door Deduction | 2.4 |  | 1 | Sqm |  | -2.4
[9 empty] | 0 | 67.14 | 8500 | 0 |  | ON HOLD
[10 empty] | Total |  | 3831436.105

## Abstract Furniture
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Code / Area Specified | Qty. | UoM | Impulse Branding |  | RA-08 |  | Cumulative |  | Variance
[5 empty] | Unit Price | Total Amount | QTY | Amount | QTY | Amount | QTY | Amount
[5 empty] | INR | INR
0
| LOUNGE FURNITURE |  |  |  |  | 0
1 | Providing & supply Chair as per approved sample (Dining Area chair ) | CF-01 | 13 | Nos | 18500 | 240500 | 13 | 240500
2 | Providing & supply Chair as per approved sample (Dining Area chair ) | CF-02 | 13 | Nos | 18500 | 240500 | 13 | 240500
3 | Providing & laying Round/Square Coffe table ( 650x650mm x H 550mm ) as per approved sample (Dining Area chair | CF-03 | 13 | Nos | 23000 | 299000 | 13 | 299000
4 | Providing & laying Round Side table ( 350mm dia x H 550mm ) as per approved sample ( SPA Area) | CF-04 | 2 | Nos | 10500 | 21000 | 2 | 21000
5 | Providing & laying Round Side table (750mm dia x H 550mm ) as per approved sample (Bar Area) | CF-05 | 4 | Nos | 27000 | 108000 | 4 | 108000
6 | Providing & supply ARMCHAIR as per approved sample (Bar Lounge) | CF-06 | 6 | Nos | 21600 | 129600 | 6 | 129600
7 | Providing & supply ARMCHAIR as per approved sample (Bar Lounge) | CF-07 | 6 | Nos | 32000 | 192000 | 6 | 192000
8 | Providing & supply ARMCHAIR as per approved sample (Premium Lounge) | CF-08 | 10 | Nos | 35000 | 350000 | 10 | 350000
9 | Providing & supply ARMCHAIR as per approved sample (Premium Lounge) | CF-09 | 10 | Nos | 35000 | 350000 | 10 | 350000
10 | Providing & laying Side table ( W 300 x D 1200x H 500mm ) as per approved sample ( Premium Lounge Area ) | CF-10 | 9 | Nos | 25000 | 225000 | 9 | 225000
11 | Providing & laying Side table ( W 300 x D 600x H 500mm ) as per approved sample ( Premium Lounge Area ) | CF-11 | 2 | Nos | 27000 | 54000 | 2 | 54000
12 | High Stool : Providing & supply High Stool as per approved sample ( Bar & High Counter Ledge Area ) Base Range @ 8500/- each | RF 01 | 5 | Nos | 9500 | 47500 | 5 | 47500
13 | High Stool : Providing & supply High Stool as per approved sample ( Bar & High Counter Ledge Area ) Base Range @ 12500/- each | RF 02 | 12 | Nos | 15500 | 186000 | 12 | 186000
14 | RECLINER : Rocking Revolving Leatherette 1 Seater Recliner Sofa (Green) Dimensions (Meter) Metrology : 0.9 L X 0.9 W X 1.1 H Seating Height (Meter) Metrology : 0.5 Dimensions (Cm) Metrology : 86.4 L X 86.4 W X 106.7 H Seating Height (Cm) Metrology : 48.3 Base Range @ 65000/- each | RF 03 | 2 | Nos | 75000 | 150000 | 2 | 150000
15 | Hybrid Massage Lounger : Airbags based massaging Lounger pod for a total-body relaxtation. 70 built-in airbags use compression technology to massage muscles in the arms, shoulders, waist, legs, and feet. Precisely programmed to rhythmically inflate & deflate in concert with the mechanics of the chair, the layered airbags give a gentle yet effective compression massage that treats muscles of the arms, legs, and hips. • TOUCHSCREEN CONTROLLER • QUICK ACCESS ARM CONSOLE • WIRELESS & USB CHARGING PORTS Make : Daiwa / Infinity or Equivlant | RF 04 | 1 | Nos | 1005000 | 1005000 | 1 | 1005000
16 | Linear Curve workstation - Providing & Supplying Linear Curve workstation made of 25mm thick Pre-Laminated particle board with Rehau make 2mm thick PVC edge banding Tape top along with MS powder coated Leg system with under top raceway, wire manager cutout with flap, magnetic writable glass screen (upto 300mm high) on top and complete as per the approved hop drawing by the Architect. workstation size ; 2150mm Long x 650mm Deep x 750mm high ( Admin Area ) Make & Brand : AFC / HNI / Featherlite Base Range @ 12500/- for Size 1050mm long workstation | MF-01 | 1 | Nos | 17400 | 17400 | 1 | 17400
17 | Pedestial Unit : Providing & Supply mobile pedistal unit ( 450mm W x 500mm D x 650mm H ) for Admin area finished in laminate with caster and lock complete as per approved shop drawing by the Architect. Make & Brand : AFC / HNI / Featherlite Base Range @ 5500/- each | MF-02 | 1 | Nos | 7500 | 7500 | 1 | 7500
18 | Workstation chair 1 : Providing & Supply workstation chair with mid back , adjustable Arm / seat, lumber support with adjustable nylon fininsh, revolving with caster base in metal with powder coated finish, seat / back : fabric finish as approved. Make & Brand : AFC / HNI / Featherlite Base Price @ 10500/- each | MF-03 | 1 | Nos | 13500 | 13500 | 1 | 13500
19 | [6 empty] | Sub Total | 3636500
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39

## JMR Sheet Furniture
PROJECT : LKO, DOMESTIC CIP LOUNGE AT T3, LUCKNOW AIRPORT
FURNITURE ITEM WORKS BOQ
S.NO. | ITEM CODE | FURNITURE WORK / DETAIL | UNIT | QTY. | Rs | Amount | IMAGES
C |  |  |  | Lounge
LOUNGE FURNITURE
1 | CF-01 | Providing & supply Chair as per approved sample (Dining Area chair ) | No | 13 | 18500 | 240500
2 | CF-02 | Providing & supply Chair as per approved sample (Dining Area chair ) | No | 13 | 18500 | 240500
3 | CF-03 | Providing & laying Round/Square Coffe table ( 650x650mm x H 550mm ) as per approved sample (Dining Area chair ) | No | 13 | 23000 | 299000
4 | CF-04 | Providing & laying Round Side table ( 350mm dia x H 550mm ) as per approved sample ( SPA Area) | No | 2 | 10500 | 21000
5 | CF-05 | Providing & laying Round Side table (750mm dia x H 550mm ) as per approved sample (Bar Area) | No | 4 | 27000 | 108000
6 | CF-06 | Providing & supply ARMCHAIR as per approved sample (Bar Lounge) | No | 6 | 21600 | 129600
7 | CF-07 | Providing & supply ARMCHAIR as per approved sample (Bar Lounge) | No | 6 | 32000 | 192000
8 | CF-08 | Providing & supply ARMCHAIR as per approved sample (Premium Lounge) | No | 10 | 35000 | 350000
9 | CF-09 | Providing & supply ARMCHAIR as per approved sample (Premium Lounge) | No | 10 | 35000 | 350000
10 | CF-10 | Providing & laying Side table ( W 300 x D 1200x H 500mm ) as per approved sample ( Premium Lounge Area ) | No | 9 | 25000 | 225000
11 | CF-11 | Providing & laying Side table ( W 300 x D 600x H 500mm ) as per approved sample ( Premium Lounge Area ) | No | 2 | 27000 | 54000
B |  | READYMADE FURNITURE
1 | RF-01 | High Stool : Providing & supply High Stool as per approved sample ( Bar & High Counter Ledge Area ) Base Range @ 8500/- each | No | 5 | 9500 | 47500
2 | RF-02 | High Stool : Providing & supply High Stool as per approved sample ( Bar & High Counter Ledge Area ) Base Range @ 12500/- each | No | 12 | 15500 | 186000
3 | RF-03 | RECLINER : Rocking Revolving Leatherette 1 Seater Recliner Sofa (Green) Dimensions (Meter) Metrology : 0.9 L X 0.9 W X 1.1 H Seating Height (Meter) Metrology : 0.5 Dimensions (Cm) Metrology : 86.4 L X 86.4 W X 106.7 H Seating Height (Cm) Metrology : 48.3 Base Range @ 65000/- each | No | 2 | 75000 | 150000
4 | RF-04 | Hybrid Massage Lounger : Airbags based massaging Lounger pod for a total-body relaxtation. 70 built-in airbags use compression technology to massage muscles in the arms, shoulders, waist, legs, and feet. Precisely programmed to rhythmically inflate & deflate in concert with the mechanics of the chair, the layered airbags give a gentle yet effective compression massage that treats muscles of the arms, legs, and hips. • TOUCHSCREEN CONTROLLER • QUICK ACCESS ARM CONSOLE • WIRELESS & USB CHARGING PORTS Make : Daiwa / Infinity or Equivlant | No | 1 | 1005000 | 1005000
B |  | MODULAR FURNITURE |  |  |  | 0
1 | MF-01 | Linear Curve workstation - Providing & Supplying Linear Curve workstation made of 25mm thick Pre-Laminated particle board with Rehau make 2mm thick PVC edge banding Tape top along with MS powder coated Leg system with under top raceway, wire manager cutout with flap, magnetic writable glass screen (upto 300mm high) on top and complete as per the approved hop drawing by the Architect. workstation size ; 2150mm Long x 650mm Deep x 750mm high ( Admin Area ) Make & Brand : AFC / HNI / Featherlite Base Range @ 12500/- for Size 1050mm long workstation | No | 1 | 17400 | 17400
2 | PD-01 | Pedestial Unit : Providing & Supply mobile pedistal unit ( 450mm W x 500mm D x 650mm H ) for Admin area finished in laminate with caster and lock complete as per approved shop drawing by the Architect. Make & Brand : AFC / HNI / Featherlite Base Range @ 5500/- each | No | 1 | 7500 | 7500
3 | CH-01 | Workstation chair 1 : Providing & Supply workstation chair with mid back , adjustable Arm / seat, lumber support with adjustable nylon fininsh, revolving with caster base in metal with powder coated finish, seat / back : fabric finish as approved. Make & Brand : AFC / HNI / Featherlite Base Price @ 10500/- each | No | 1 | 13500 | 13500

## JMR LIGHTS & PANELS
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:24/03/2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : Light Fixtures CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF Light Fixtures
S. No. | Item. Code | Specification | Unit | Location | Site Qty | WOQ | Rate | Amount | Extra Qty | Remarks
| A | Supply, assembling, erection, connecting, testing and commissioning of the following LED light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required
| 1 | Recessed Downlighter - 9W Ceiling light fixture LED Recessed 9W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each | Nos | Male Restroom=8 Female Restroom=4 Disable Restroom=2 Electrical Room=2 | 16 | 16 | 1560 | 24960
| 2 | Recessed Downlighter - 15W Ceiling light fixture LED Recessed 15W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each | Nos | Admin=2 | 2 | 2 | 1750 | 3500
| 4 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 6 W 4000 K LED Recessed 6W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 1045/- each | Nos | P,Lounge=11 BAR Area=4 Dinning Area=2 Passage=4 Female Restroom=1 | 20 | 22 | 1500 | 30000 |  | Balance=2 nos
| 6 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 450/- each (All the Taxes Inclusive) | Nos | SPA=6 | 6 | 31 | 750 | 4500 |  | Balance=25 nos
| 7 | Recessed Downlighter - ASTRAL ROUND 2 W Warm Daylight (WDL) 4000 K LED Recessed 2W LED, colour temperature of 3000K-4000K, Ø = 41mm Base Price @ 215/- each (All the Taxes Inclusive) | Nos | BAR Wall=16 P LOUNG Wall=13 | 0 | 29 | 430 | 0 |  | Balance=29 nos
| 8 | Recessed Downlighter - LED recessed luminaire system power 18W, colour temperature of 4000K, L = 595mm, B = 595mm, H = 70mm Base Price @ 2500/- each | Nos | Kitchen=5 | 5 | 5 | 3600 | 18000
DECORATIVE LIGHTING - Supply & Installation Only (Brand & Make : Zolux / Truemoon / White Teak (Asian Paints) / Jainsons / Jaquar
| 2 | WALL DECORATIVE LIGHT : Marvel at this innovative design featuring an A classy leaf shaped, multicolor body paint with day lamp highlight the ornate finishing doubles as a wall hanging too. Switch it on for a warm glow, or let it add subtle elegance to your walls as it rests. Leaf metal shade that cover back LED lamp, The frame in diffrent color shade, housing the orb of light within itself as well. It's an incredible wall light for lounges. No. of Bulb Holders :1 Holder & Plug Type :E-27 Recommended Bulb :40 Watts (Max) Package Contents :1 Premium Wall Light. Bulb Provided: LED bulb Provided Product Material : Metal Body in Matte multicolor color Finish as approved. Product Weight (in Kg)0.5 Country Of Origin: custom / Imported Size & Shape : 225mm high x 100mm wide, Leaf shape Base Range : Rs. 2900/- each | Nos | P,Lounge=32 BAR Area=32 Survery Area=8 Expention Column=0 | 72 | 75 | 3600 | 259200 | 11 | Incresed due to change in Drawing of Buffar Counter COLUMN Balance=14
[7 empty] | Total Amount | 340160

## Abstract Electrical
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Code / Area Specified | Qty. | UoM | Impulse Branding |  | RA-08 |  | RA-02 |  | RA Bill 09 |  | Extra Qty RA Bill 09 |  | Cumulative |  | Variance
[5 empty] | Unit Price | Total Amount | QTY | Amount | QTY | Amount | QTY | Amount |  |  | QTY | Amount | QTY | Amount
[5 empty] | INR | INR
ELECTRICAL WORKS
SUB-HEAD I WIRING
1.1 | Wiring for primary light points for Switch controlled points with 2.5 sq. mm LSHF PVC insulated stranded /multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface /concealed conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting, and including the cost of Supply and fixing a 6 amp 240 Volt grid plate mounted switch with moulded cover plate in zinc chromate passivated GI box and including the cost of running 2.5 sq. mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. |  | 30 | nos | 3200 | 96000 | 21 | 67200 |  |  | 9 | 28800 | 3 | 9600
1.2 | Wiring for primary light points for DB / Dimmer/ Sensor/ Automation controlled points with 2.5 sq mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item)(Normal) |  | 45 | nos | 3200 | 1,44,000 | 31.5 | 100800 |  |  | 4.5 | 14400 |  | 0
1.3 | Wiring for primary light points for DB/ Dimmer/ Sensor/ Automation controlled points with 2.5 sq mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item). (Emergency) |  | 11 | nos | 3200 | 35200 | 7.7 | 24640 |  |  | 3.3 | 10560 |  | 0
1.4 | Wiring for secondary light points with 1.5 sq. mm LSHF PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia 16 SWG GI conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 1.5 sq. mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Normal) |  | 352 | nos | 2100 | 7,39,200 | 246.4 | 517440 |  |  | 105.6 | 221760 | 44 | 92400
1.5 | Wiring for secondary light points with 1.5 sq. mm LSHF PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia 16 SWG GI conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 1.5 sq. mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Emergency) |  | 46 | nos | 2100 | 96600 | 32.2 | 67620 |  |  | 13.8 | 28980 | 17 | 35700
1.6 | Wiring for 240 volt 6 amp Multistandard single phase and neutral switch socket outlet with 4 sq. mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing circuit wiring with 2.5 sq mm LSHF PVC insulated stranded/ multistranded copper conductor 1100 volt grade wires and including the cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and Supply and fixing of a 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 2.5 sq. mm LSHF PVC insulated copper earth wire conductor wires complete as directions of Engineer-in- charge and as required. |  | 11 | nos | 3500 | 38500 | 7.7 | 26950 |  |  | 3.3 | 11550 |  | 0
1.7 | Wiring as in Item 1.6 above looped from an adjacent switch socket outlet as required and Supply and fixing of a combined 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 2.5 sq. mm LSHF PVC insulated copper earth wire conductor wires complete as directions of Engineer-in-charge and as required. |  | 28 | nos | 3500 | 98000 | 19.6 | 68600 |  |  | 8.4 | 29400 | 11 | 38500
1.8 | Wiring for a multi-pin 240 volt 6-16 amp single phase and neutral universal switch socket outlet with 4.0 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed conduit including the cost of providing circuit wiring with 4.0 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a combined multi-pin 240 volt 6-16 amp universal socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed galvanized box and including earthing of the 3rd pin with 4.0 sq mm 1100 volt grade LSHF PVC insulated stranded copper conductor wires complete as directions of Engineer-in-charge and as required. |  | 46 | nos | 3500 | 1,61,000 | 32.2 | 112700 |  |  | 13.8 | 48300 | 55 | 192500
1.9 | Wiring as in Item 1.8 above looped from an adjacent switch socket outlet as per specifications and directions of Engineer-in-charge and providing and fixing of a modular type multi-pin 240 Volt 6-16 amp shuttered socket outlet and a modular type 16 amp 240 Volt single pole switch in a recessed galvanized boxes with internal wiring and moulded front plates complete as directions of Engineer-in-charge and as required. |  | 21 | nos | 2500 | 52500 | 14.7 | 36750 |  |  | 6.3 | 15750 | 23 | 57500
1.1 | Supply , Installation, Testing and comissioning of Pop-up Boxes with all standard accessories consisting of following: a) 3 nos 6 amp socket with 1 no. 16A Switch b) 2 nos Data outlets which includes of Data wiring and terminations. Wiring for socket outlet with 4.0 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 4.0 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a pop up Box on Table/furniture/wall complete as directions of Engineer-in-charge and as required. - Workstations. |  | 3 | nos | 17500 | 52500 | 2.1 | 36750 |  |  | 0.9 | 15750 |  | 0
1.11 | Supply , Installation, Testing and comissioning of Switch socket on furniture with all standard accessories consisting of following: a) 2 nos 6 amp socket with 1 no. 10A Switch b) 2 nos Data outlets which includes of Data wiring and terminations. Wiring for socket outlet with 2.5 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 2.5 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a Box set on furniture/wall complete as directions of Engineer-in-charge and as required. - Dinning Area. |  | 7 | nos | 2500 | 17500 | 4.9 | 12250 |  |  | 2.1 | 5250 | 4 | 10000
1.12 | Supply , Installation, Testing and comissioning of Switch socket on furniture with all standard accessories consisting of following: a) 2 nos 6 amp socket with 1 no. 10A Switch b) 1 nos Data outlets which includes of Data wiring and terminations. Wiring for socket outlet with 2.5 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 2.5 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a Box set on furniture/wall complete as directions of Engineer-in-charge and as required. - Premium Lounge & BAR Area. |  | 17 | nos | 2500 | 42500 | 11.9 | 29750 |  |  | 5.1 | 12750 | 12 | 30000
1.13 | Wiring for 6 pin 240 volt 16 amp single phase and neutral Universal switch socket outlets with 4.0 sq. mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including Supply and fixing of a 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switch with moulded cover plate in a recessed zinc chromate passivated GI box including earthing of the 3rd pin with 4.0 sq. mm 1100 volt grade LSHF PVC insulated stranded copper earth wire complete as directions of Engineer-in-charge and as required. |  | 14 | Nos. | 3500 | 49000 | 9.8 | 34300 |  |  | 4.2 | 14700 | 11 | 38500
1.14 | Wiring as in Item 1.13 above looped from an adjacent switch socket outlet as per specifications and directions of Engineer-in-charge and providing and fixing of a modular type multi-pin 240 Volt 6-16 amp shuttered socket outlet and a modular type 16 amp 240 Volt single pole switch in a recessed galvanized boxes with internal wiring and moulded front plates complete as directions of Engineer-in-charge and as required. |  | 13 | nos | 3100 | 40300 | 9.1 | 28210 |  |  | 3.9 | 12090 | 17 | 52700
1.15 | Wiring for 6 pin 240 volt 25 amp single phase and neutral switch socket outlets with 4.0 sq. mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including Supply and fixing of a 240 volt 16 amp socket outlet with safety shutters and 25 amp 240 volt single pole grid plate mounted switch with moulded cover plate in a recessed zinc chromate passivated GI box including earthing of the 3rd pin with 4.0 sq. mm 1100 volt grade LSHF PVC insulated stranded copper earth wire complete as directions of Engineer-in-charge and as required. |  | 1 | Nos. | 6500 | 6500 | 0.7 | 4550 |  |  | 0.3 | 1950 |  | 0
1.16 | Supplying, fixing, testing & commissioning of 32 A, 240 V, SPN metal clad Industrial type socket outlet (IP‐65), with 2 pole and earth, plug top along with 32 A, “C” curve, SP, MCB, in Polycarbonate enclosure, on surface or in recess, with cover for the socket out let and complete with connections, testing and commissioning etc. as required. |  | 12 | Nos. | 6500 | 78000 | 8.9 | 57850 |  |  | 0.1 | 650 |  | 0
1.17 | Supplying fixing, testing & commissioning of 32 A, 415 V, TPN Industrial type socket outlet (IP‐65), with 4 pole and earth, plug top along with 32 A, “C” curve, TP MCB, in polycarbonate enclosure, on surface or in recess, with cover for the socket out let and complete with connections, testing and commissioning etc. as required. |  | 3 | Nos. | 6000 | 18000 | 2.1 | 12600 |  |  | 0.9 | 5400 |  | 0
1.18 | Supplying fixing, testing & commissioning of 32 A, 415 V, TPN 5 pole Industrial type socket outlet (IP‐65), with 4 pole and earth, plug top along with 32 A, “C” curve, MCB, in polycarbonate enclosure, on surface or in recess, with cover for the socket out let and complete with connections, testing and commissioning etc. as required. |  | 1 | Nos. | 6500 | 6500 | 0.7 | 4550 |  |  | 0.3 | 1950 |  | 0
1.19 | Providing and fixing of a Data outlet plate mounted outlet unit (RJ-45) with moulded cover plate in recessed zinc chromate passivated GI box complete as directions of Engineer-in-charge and as required for Data system. |  | - |  |  | - | [7 empty] | 0
a) | 1 No. data outlet |  | 8 | nos | 2500 | 20000 | 5.6 | 14000 |  |  | 2.4 | 6000 | 2 | 5000
b) | 2 Nos. data outlet |  | 2 | nos | 2500 | 5000 | 1.4 | 3500 |  |  |  | 0 |  | 0
1.2 | Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair computer cable with 24 AWG solid copper conductors in surface/concealed conduit/raceways/modular furniture , complete as directions of Engineer-in-charge and as required. |  | 320 | Mtrs | 85 | 27200 | 320 | 27200 |  |  | 0 | 0 | 1373.5 | 116747.5
1.21 | Supplying, Installation, testing and commissioning of 12U Networking Rack with PDU, switches, jack, patch cords, Ios, and all other accessories complete as required for Server, router & network video recorder. |  | 1 | nos | 35000 | 35000 | 0.7 | 24500 |  |  | 0.3 | 10500 | 1.3 | 45500
1.22 | Supplying, Installation, testing and commissioning of Occupancy Sensor for light control with all accessories and complete as directions of Engineer-in-charge and as required. |  | 11 | nos | 3500 | 38500 | 7.7 | 26950 | [5 empty] | 0
1.23 | Supplying and drawing wiring with single core stranded copper conductor PVC insulated 1100 volt grade LSHF PVC insulated wires in surface/recessed steel conduit systems including the cost of running copper conductor LSHF PVC insulated loop earthing wire complete as directions of Engineer-in-charge and as required as below. |  | - |  |  | - | [7 empty] | 0
a) | 2 x 1.5 sq mm with 1 x 1.5 sq mm earth wire |  | - | Mtrs | 150 | - | [7 empty] | 0
b) | 2 x 2.5 sq mm with 1 x 2.5 sq mm earth wire |  | 90 | Mtrs | 210 | 18900 | 63 | 13230 |  |  | 27 | 5670 | 438 | 91980
c) | 2 x 4 sq mm with 1 x 4.0 sq mm earth wire |  | 330 | Mtrs | 300 | 99000 | 231.7 | 69510 |  |  | 98.3 | 29490 | 420.91 | 126273
d) | 2 x 6 sq mm with 1 x 6.0 sq mm earth wire |  | 90 | Mtrs | 320 | 28800 | 63 | 20160 |  |  | 6.9 | 2208 |  | 0
g) | 4 x 4 sq mm with 2 x 4.0 sq mm earth wire |  | 90 | Mtrs | 400 | 36000 | 63 | 25200 |  |  | 27 | 10800 | 209.2 | 83680
h) | 4 x 6 sq mm with 2 x 6.0 sq mm earth wire |  | 50 | Mtrs | 450 | 22500 | 35 | 15750 |  |  | -24 | -10800 |  | 0
i) | 4 x 10 sq mm with 2 x 10 sq mm earth wire |  | - | Mtrs | 600 | - | [7 empty] | 0
j) | 4 x 16 sq mm with 2 x 16 sq mm earth wire |  | - | Mtrs | 650 | - | [7 empty] | 0
1.24 | Supplying and drawing recessed/surface IS embossed GI conduiting system including cost of providing saddles etc for surface/recess conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer- in-charge and as required as below. |  | - |  |  | - | [7 empty] | 0
a) | 20 mm |  | 110 | Mtrs | 145 | 15950 | 77 | 11165 |  |  | 3 | 435 |  | 0
b) | 25 mm |  | 200 | Mtrs | 165 | 33000 | 140 | 23100 |  |  | 42 | 6930 |  | 0
c) | 32 mm |  | 110 | Mtrs | 176 | 19360 | 77 | 13552 |  |  | 7 | 1232 |  | 0
d) | 40 mm |  | 110 | Mtrs | 210 | 23100 | 77 | 16170 |  |  | 21 | 4410 |  | 0
e) | 50 mm |  | - | Mtrs | 250 | - | [7 empty] | 0
1.25 | Supplying and drawing recessed/surface medium class PVC conduit including cost of providing saddles etc accessories for surface/recess conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer- in-charge and as required as below. |  | - |  |  | - | [7 empty] | 0
a) | 20 mm |  | 30 | Mtrs | 65 | 1950 | 21 | 1365 |  |  | -1 | -65 |  | 0
b) | 25 mm |  | - | Mtrs | 75 | - | [7 empty] | 0
c) | 32 mm |  | - | Mtrs | 90 | - | [7 empty] | 0
d) | 40 mm |  | - | Mtrs | 120 | - | [7 empty] | 0
1.26 | Supply and fixing GI flexible conduit including all fittings complete as required as below. |  | - |  |  | - | [7 empty] | 0
a) | 20 mm |  | 265 | Mtrs | 154 | 40810 | 185.5 | 28567 |  |  | 62 | 9548 |  | 0
b) | 25 mm |  | 95 | Mtrs | 170 | 16150 | 66.5 | 11305 |  |  | 8.5 | 1445 |  | 0
c) | 32 mm |  | - | Mtrs | 210 | - | [5 empty] | 557793
d) | 40 mm |  | - | Mtrs | 240 | -
| TOTAL FOR WIRING |  |  |  |  | 22,53,020 |  | 1588734 |  |  |  | 557793 |  | 1026580.5
B | SUB-HEAD II CABLES & RACEWAYS
1 | Supply and laying cables on Tray / clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling with sand and brick protection as required and including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and PVC sheathed copper conductor cable complete as required. The costs shall include for all cables to be provided with a 1D gap and shall be properly clamped with cable clamps and ties. Identification tags shall be provided for all cables and route markers for cables in ground. |  |  |  |  | -
a) | 3 -1/2 core 240 Sq mm AL. XLPE AR. Cable |  | - | Mtrs | 1200 | -
b) | 3 -1/2 core 95 Sq mm AL. XLPE AR. Cable |  | - | Mtrs | 750 | -
c) | 3 -1/2 core 70 Sq mm AL. XLPE AR. Cable |  | 50 | Mtrs | 650 | 32500 | 35 | 22750 |  |  | 3 | 1950
d) | 3 -1/2 core 50 Sq mm AL. XLPE AR. Cable |  | - | Mtrs | 450 | -
e) | 4 core 16 Sq mm CU. XLPE AR. Cable |  | 30 | Mtrs | 750 | 22500 | 21 | 15750 |  |  | -5 | -3750 | 22 | 16500
f) | 4 core 6 Sq mm CU. XLPE AR. Cable |  | - | Mtrs | 450 | -
g) | 4 core 4 Sq mm CU. XLPE AR. Cable |  | 160 | Mtrs | 400 | 64000 | 120 | 48000 |  |  | -52 | -20800
2 | Cable end termination of the following XLPE insulated and PVC sheathed Aluminium conductor cable 1100 Volt grade including cost of crimping heavy duty aluminium lugs, nickel plated brass double compression glands, insulation tape and all requisite material for completion of termination complete as required and as below. |  |  |  |  | -
a) | 3 -1/2 core 240 Sq mm AL. XLPE AR. Cable |  | - | Nos | 1200 | -
b) | 3 -1/2 core 95 Sq mm AL. XLPE AR. Cable |  | - | Nos | 850 | -
c) | 3 -1/2 core 70 Sq mm AL. XLPE AR. Cable |  | 4 | Nos | 2100 | 8400 | 2.8 | 5880 |  |  | 1.2 | 2520 | 2 | 4200
d) | 3 -1/2 core 50 Sq mm AL. XLPE AR. Cable |  | - | Nos | 750 | -
3 | Cable end termination of the following XLPE insulated and PVC sheathed Aluminium/ copper conductor cable 1100 Volt grade including cost of crimping heavy duty copper lugs, nickel plated brass double compression glands, insulation tape and all requisite material for completion of termination complete as required and as below. |  |  |  |  | -
a) | 4 core 16 Sq mm CU. XLPE AR. Cable |  | 2 | Nos | 1500 | 3000 | 1.4 | 2100 |  |  | 0.6 | 900 | 6 | 9000
b) | 4 core 6 Sq mm CU. XLPE AR. Cable |  | - | Nos | 1000 | -
c) | 4 core 4 Sq mm CU. XLPE AR. Cable |  | 20 | Nos | 1200 | 24000 | 14 | 16800 |  |  | -6 | -7200
4 | Supply and fixing of perforated sheet steel slotted cable trays with vertical sides on both ends as per approved design and GI angle supports spaced 1000 mm apart throughout the length as specified, including the cost of 1 meter GI rod hangers, hooks, dash fasteners, painting etc. for suspension from ceiling complete as required. |  |  |  |  | -
a) | 300 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cover |  | 20 | Mtrs | 1560 | 31200 |  |  | 11.939 | 18624.84
b) | 150 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cover |  | 20 | Mtrs | 1150 | 23000 |  |  | 10.54 | 12121
c) | 100 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cover |  | 60 | Mtrs | 850 | 51000 |  |  | 6.413 | 5451.05
| GI Raceway & Junction boxes (IP 55) |  |  |  |  | -
5 | Supply, assembly and laying of under floor trunking made out of minimum 1.6 mm thick pre galavised sheet with enamel paint finish complete with jointing sleeve, horizontal bends, vertical bends, level adjustment components and closer, vertical elbow, covers, access outlet. etc. complete with all other accessories under floor installation including cutting and chasing the floor/ or on surface, making good the same, placing in position and cleaning from inside complete etc. as required. |  |  |  |  | -
a) | 300 mm x 40 mm (3 compartment - 1 For Power, 1 for Data, 1 blank for seperation ) |  | - | Mtrs | 2500 | -
b) | 225 mm x 40 mm (2 compartment - 1 For Power, 1 for Data ) |  | 40 | Mtrs | 2300 | 92000 |  |  | 26.12 | 60076
c) | 150 mm x 40 mm (1 compartment) |  | 10 | Mtrs | 1250 | 12500 |  |  | 5.6 | 7000
d) | 100 mm x 40 mm (2 compartment - 1 For Power, 1 for Data ) |  | 20 | Mtrs | 900 | 18000 |  |  | 15.87 | 14283
e) | 75 mm x 40 mm (1 compartment) |  | 10 | Mtrs | 850 | 8500
f) | Providing and fixing 350 x 350 x 50 mm deep junction box for Power & Data raceways in floor |  | - | Nos | 2100 | -
g) | Providing and fixing 250 x 250 x 50 mm deep junction box for Power & Data raceways in floor |  | 12 | Nos | 1500 | 18000 |  |  | 13 | 19500
h) | Providing and fixing 150 x 150 x 50 mm deep junction box for Power & Data raceways in floor |  | 13 | Nos | 1200 | 15600 |  |  | 9 | 10800
i) | Providing and fixing 100 x 100 x 50 mm deep junction box for Data raceways in floor |  | - | Nos | 900 | - |  |  | 14 | 12600 |  | -26380
| TOTAL FOR CABLES & RACEWAYS |  |  |  |  | 4,24,200 |  | 111280 |  | 160455.89 |  | -26380 |  | 29700
C | SUB-HEAD III DISTRIBUTION BOARD & ELECTRICAL PANEL
1 | Supply, erection, testing and commissioning of the following sheet steel clad wall/recess mounting dust and vermin proof double distribution boards constructed from 1.2mm sheet steel IP 42 construction, finished with rust proof red oxide coating and two coats of paint with hinged gasketted door and housing the following complete with suitably rated PVC insulated tinned copper busbars with interconnections and neutral bar assembly, earthing terminals/bar, din bar complete, powder painted including earthing as approved by the Architects/ Engineer in charge. Padlocking facility shall be provided on the door. The DB shall be provided with cable end boxes. |  |  |  |  | -
a) | 14 WAY SPN DB Incoming: 1-25 amp DP 10 kA MCB, B curve with thermal magnetic protective releases incoming with 1nos. 25 amp DP 30 mA RCCB in each phase Outgoings: 14 nos 6/10 amps SP 10 kA MCB, B curve with thermal magnetic protective releases out goings. For FLDB |  | 1 | nos | 38000 | 38000 | 0.7 | 26600 |  |  | 0.3 | 11400
b) | 12 WAY TPN DB-1 Incoming: 1-63 amp FP 10 kA MCB, C curve with thermal magnetic protective releases incoming with 1nos. 63 amp DP 30 mA RCCB in each phase Outgoings: 36 nos 16/20/25/32 amps SP 10 kA MCB, C curve with thermal magnetic protective releases out goings. For PDB |  | 1 | nos | 36000 | 36000 | 0.7 | 25200 |  |  | 0.3 | 10800
c) | 12 WAY TPN DB-2 Incoming: 1-32 amp FP 10 kA MCB, B curve with thermal magnetic protective releases incoming with 1nos. 32 amp DP 30 mA RCCB in each phase Outgoings: 36 nos 10 amps SP 10 kA MCB, B curve with thermal magnetic protective releases out goings. For LDB |  | 1 | nos | 35000 | 35000 | 0.7 | 24500 |  |  | 0.3 | 10500
1.1 | 10 WAY TPN DB Supplying & fixing of following double door Emergency Lighting DB's enclosures, with minimum IP 55, UV resistant as per IEC 61439,flame retardant, self extinguishing material for outdoor / harsh environment like resistant to weather influences (humidity, temperature, water sprays). The DB shall include all accessories i.e. earth bar, din bar, neutral bar, tinned copper bus bars, earthing terminal, power painting & cable end box etc. as required. Incoming: 1-32 amp FP 10 kA MCB, C curve with thermal magnetic protective releases Outgoings: 30 nos 10/16/20 amps SP 10 kA MCB, C curve with thermal magnetic protective releases out goings. For EDB (10A MCBs shall be for lighting circuits only) |  | 1 | nos | 32000 | 32000 | 0.7 | 22400 |  |  | 0.3 | 9600
1.2 | SITC of All VTPN DB's double door and modules, shall be pre assembled with vertical bus bars & minimum IP‐55, UV resistant as per IEC 61439, suitable for outdoor/harsh environment like resistant to weather influences (humidity, temperature, water spray s), chemical resistanc etc. The DB shall include all accessories i.e. earth bar, din bar, neutral bar, tinned copper bus bars, earthing terminal, power painting & cable end box etc. as required. |  | - |  |  | -
a) | 12 WAY VTPN DB INCOMER 1 No. 160A 4 pole MCCB (16 KA) with over load, short circcuit & earth fault protection OUTGOINGS 36 nos. of 20/25/32A modules for SP/TP MCB's, C curve (10KA) as required (Refer DB schedule). DB as described above For KTB-1 |  | 1 | nos | 35000 | 35000 | 0.7 | 24500 |  |  | 0.3 | 10500
b) | 10 WAY VTPN DB INCOMER 1 No. 160A 4 pole MCCB (16 KA) with over load, short circcuit & earth fault protection OUTGOINGS 30 nos. of 20/25/32A modules for SP/TP MCB's (10KA), C curve as required (Refer DB schedule). DB as described above For KTB-1 |  | 1 | nos | 35000 | 35000 | 0.7 | 24500 |  |  | 0.3 | 10500
| Electrical Panel- IN Electrical Room (Floor Mounted) |  | - |  |  | -
2 | Design, Manufacture, Supply, delivery and coordination for Installation of the following front operated modular compartmentalised construction cubicle type, front access, dead back, 2mm thick steel enclosed free standing / wall mounted, dust and vermin proof, switchboard with IP42/Specified protection with hinged and lockable doors duly powder coated complete with interconnections, tinned copper crimping lugs, bonding to earth and painting, suitable for use at 415 volts, 3 phase 4 wire 50 Hertz system, and to withstand a symetrical fault level of 25 kA |  | - |  |  | -
| All Switchboards shall have provision for entry of cables from the top or bottom as required. |  | - |  |  | -
| All live accessible parts shall be shrouded and all equipment shall be finger touch proof. The Busbars insulation shall be with heat shrinkable sleeves. SMC/DMC shrouds and busbar supports shall be used. Padlocking facility shall be provided on all outgoing feeders doors and switch handles shall be lockable in OFF position |  | - |  |  | -
| The cost shall include providing and fixing of 75 x 50 x 6 mm channels for switchboard support. |  | - |  |  | -
| All MCCB shall have rotary handles & extension terminal, phase barrier on both sides as required at site. |  | - |  |  | -
| All metering panel shall be extendable type with cable alley. |  | - |  |  | -
| GA drawings shall be got approved from Owners/ Architects/ Consultants before fabrication. |  | - |  |  | -
| Note:- The Manufacturer/Supplier shall supervise the installation, testing and commissioning of the cubicle panels by the electrical contractor. |  | - |  |  | -
| INCOMING |  | - |  |  | -
| 1 No. 250Amps. 4P MCCB '25ka, Icu=Ics with micro processor release having O/L , S/C, earth fault protection equipped with the following: |  | - |  |  | -
| The incomers shall have the following indicating panel |  | - |  |  | -
a) | 1 set of phase indication lamps (R, Y, B) with 2A MCB |  | - |  |  | -
b) | 1 set of ON,OFF,TRIP indicating light with 2A MCB |  | - |  |  | -
c) | Digital Multifunction Meter, accuracy class 1s, with LED/LCD screen of Max Demand Load, I ;V; Hz; Active, Reactive , Apparent Power & Energy; Power factor; % unbalance of current & voltage; with RS 485 / Ethernet port with 3 Nos. cast resin current transformers of dual core CT's of suitable Amp. ratio, 15 VA Class1.0 m etering., protection MCBs as required accessories to complete the system. |  | - |  |  | -
| BUSBAR |  | - |  |  | -
| FP aluminium extensible type main bus bars of minimum of 300 Amp 25kA capacity with heat shrinkable coloured sleeves and i/c DMC/SMC bus bars supports at required intervals complete. |  | - |  |  | -
| OUTGOING UNITS |  | - |  |  | -
| 3 Nos. 160A TPN MCCB, 16kA, (Ics=lcu) with O/L, S/C |  | - |  |  | -
| 3 nos 63 amp 4P 10 kA MCB with thermal magnetic protective releases |  | - |  |  | -
| 2 nos 25 amp 4P 10 kA MCB with thermal magnetic protective releases |  | - |  |  | -
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required. (Note: Length of the panel should not increase more than 1600mm, 400mm depth and 2000mm height). |  | 1 | nos | 1,45,000 | 1,45,000 | 0.7 | 101500 |  |  | 0.3 | 43500
| UPS 8KVA |  | - |  |  | -
3 | Supply, installation, testing and commissioning of 8kVA UPS system comprising of online units with a battery backup of 30 minutes duration for full load and with all standards fittings, accessories, protection, instruments, indications and controls including but not restricted to transformer, rectifier, inverter, SMF battery with float cum boost battery charger, static bypass switch, maintenance bypass, interconnections etc. The UPS shall be suitble for three phase 415V Input with variation of + 15% and give constant output supply of 415V + 2%. |  | 1 | nos | 3,15,000 | 3,15,000 | 0.7 | 220500 |  |  | 0.3 | 94500
4 | Supplying and laying of the following earthing strip on cable tray/ wall clamped to wall with suitable clamps saddles and fixing bolts/soldering as required and complete as required to comply with IS 3043:1987. All joints shall be timed. The body earthing of UPS and Panel shall be looped from the existing earthing system. |  | - |  |  | -
a) | 25 mm x 3 mm GI strip |  | 50 | Mtrs | 145 | 7250 | 35 | 5075 |  |  | 4 | 580
b) | 25 mm x 3 mm Copper strip for UPS |  | 20 | Mtrs | 165 | 3300 | 14 | 2310 |  |  | -6 | -990
c) | 6 SWG GI Wire |  | 120 | Mtrs | 180 | 21600 | 84 | 15120
d) | 8 SWG GI Wire |  | - | Mtrs | 180 | -
e) | 4 sq.mm dia copper wire |  | 100 | Mtrs | 180 | 18000 | 70 | 12600 |  |  | 30 | 5400
4 | Providing and fixing M.V danger notice plate of 200 mm x 150 mm, made mild steel, atleast 2 mm thick, and vitreous enameled white on both sides, and with inscription in single red colour on front side as required. |  | - | nos | 2000 | -
5 | Supplying and fixing of 40A 4P, 415V Isolator in sheet steel enclosure with, connection, testing & commissioning as required. |  | 1 | nos | 6500 | 6500 | 0.7 | 4550 |  |  | 0.3 | 1950
| TOTAL FOR DISTRIBUTION BOARD & ELECTRICAL PANEL |  |  |  |  | 7,27,650 |  | 509355 |  |  |  | 208240
D | SUB-HEAD IV FIRE DETECTION & PA SYSTEM
I | Fire Detection System |  |  |  |  | -
1 | Supply, installation, testing and commissioning of 1 Loop wall recess mounting microprocessor based networkable analogue addressable Fire Control Panel having a Fire Alarm Capability of 100/125/150 detectors/devices per loop with each loops length being restricted to 80% of manufacturer specified maximum loop length). The Fire control panel shall have 100% hot redundancy for CPU, load etc. It shall be expandable by minimum 1 additional loops. The operating panel shall have minimum 80 character LCD display, 4 access levels, 1000 events historical logging, flash E- PROM, 240 volts ac power supply, automatic battery charger, 24V sealed lead-acid battery suitable operating the system for 24 hours in emergency condition. The Panel shall be Integrated with the PA System and with suitable power amplifiers for the hooter/strobes and main building fire alarm panel. |  |  |  |  | -
| The Panel shall be Integrated with the BMS System and shall include cost of supply of any additional modules, software and interfaces as required for the same and as required by the Client. The Panel shall provide either or all BACNET/RS485/ LON/MODBUS protocols as required. The panel shall be complete as per specifications and as required. |  |  |  |  | -
a) | 1 Loop |  | 1 | nos | 35000 | 35000 | 0.7 | 24500
2 | Supply, installation, testing and commissioning of plug-in type intelligent analogue addressable multi criteria Smoke detectors including the cost of base plate, 75 mm dia M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. |  | 42 | nos | 3300 | 1,38,600 | 29.4 | 97020
3 | Supply, installation, testing and commissioning of plug-in type intelligent analogue addressable rate of rise cum fixed temperature Heat detectors including the cost of base plate, 75 mm dia M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. |  | 3 | nos | 3000 | 9000 | 2.1 | 6300
4 | Supply, installation, testing and commissioning of Addressable type fault for isolating shorted, dewired and loose circuits between two successive fault isolators with automatic resetting arrangement (base Model) |  | 5 | nos | 4000 | 20000 | 3.5 | 14000
5 | Supply, installation, testing and commissioning of Addressable type Response indicatior. |  | 25 | nos | 2500 | 62500 | 17.5 | 43750
3 | Supply, installation, testing and commissioning of addressable type duct detector including the cost of plate, M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. |  | 4 | nos | 3600 | 14400 | 2.8 | 10080
6 | Supply, installation, testing and commissioning of intelligent analogue addressable Control Modules including the cost of 75 mm dia MS outlet box for fixing of the module, mounting accessories complete as per specifications and as required. |  | - | nos | 4000 | -
7 | Supply, installation, testing and commissioning of intelligent analogue addressable dry contact Monitor Modules including the cost of 75 mm dia MS outlet box for fixing of the module, mounting accessories complete as per specifications and as required. |  | - | nos | 4500 | -
8 | Supply, installation, testing and commissioning of recess/surface mounting dust and vermin proof intelligent addressable analogue Manual Pull stations including cost of all required modules, mounting accessories etc including the cost of M.S. outlet box for fixing of the station, mounting accessories etc. complete as per specifications and as required. |  | 1 | nos | 4000 | 4000 | 0.7 | 2800
9 | Supply, Installation, Testing and commissioning of high intensity hooters cum Strobe Lights with 110 cd. The strobes shall be synchronized for better evacuation. |  | 1 | nos | 3700 | 3700 | 0.7 | 2590
10 | Supply, laying, testing and commissioning of 2 core 1.5 sqmm copper conductor LSHF PVC insulated 1100 volt wires in IS embossed black enameled 25mm dia 16 SWG MS recessed and/or surface conduiting system including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting as required and including the cost of crimped termination's complete as required. (Smoke detector and speaker) |  | 600 | Mtrs | 145 | 87000 | 420 | 60900
II | Public Address system |  | - |  |  | -
1 | Supply, installation, testing and commissioning of recess/ surface mounting 3W CEILING SPEAKER ,metal grille, dia 150mm and Spring clamps suitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required. |  | 21 | nos | 3000 | 63000 | 14.7 | 44100 |  |  | 3.3 | 9900
2 | Supply, installation, testing and commissioning of Wall surface mounting 3W CEILING SPEAKER with 6W/3W optionssuitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required. |  | 2 | nos | 3500 | 7000 | 1.4 | 4900
3 | Supply, installation, testing and commissioning of MS Amplifier Rack Assembly with 30 minutes power backup including 1 no. CD player unit, 1 nos 200 W POWER AMPLIFIER, connectors, internal wiring, interconnection etc capable of voice operated priority complete as required. (PA System fully integrated type with Fire Alarm System with facility for automatic override of music for emergency announcements) |  | 1 | nos | 25000 | 25000 | 0.7 | 17500 |  |  | 0.3 | 7500
4 | Supply, installation, testing and commissioning of CONTROL PANEL with single zone selection, ascending 4 tone chime, emergency microphone, expandable upto 5 zones using expansion control panel complete as required. |  | 1 | nos | 35000 | 35000 | 0.7 | 24500 |  |  | 0.3 | 10500
5 | Supply, installation, testing and commissioning of Wireless lepal microphone DB technology complete as required |  | 1 | nos | 6500 | 6500 | 0.7 | 4550
6 | Supply, installation, testing and commissioning of Microphone with table stand |  | 1 | nos | 8600 | 8600 | 0.7 | 6020 |  |  | 0.3 | 2580
| TOTAL FOR FIRE DETECTION & PA SYSTEM |  |  |  |  | 5,19,300 |  | 363510 |  |  |  | 30480
E | SUB-HEAD V CCTV SYSTEM
1 | Design, Engineering, Supply, Receiving, handling, storage, installation, testing and commissioning of the CLOSED CIRCUIT TELEVESION (CCTV) SURVEILLANCE SYSTEM with IP based indoor type fixed varifocal dome camera for the proposed application with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation. |  | 13 | nos | 4500 | 58500 | 9.1 | 40950 |  |  | 3.9 | 17550 | 5 | 22500
2 | Supply of Network Video/Disk Recorder -16 channel (Including HDD for minimum recording of 30 days) with minimum 500GB Usable Space with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation. |  | 1 | nos | 28000 | 28000 | 0.7 | 19600 |  |  | 0.3 | 8400
3 | Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair with 24 AWG solid copper conductors in surface/concealed conduit/raceways complete as required |  | 330 | Mtrs | 85 | 28050 | 231 | 19635 |  |  | 99 | 8415 | 72.8 | 6188
| TOTAL FOR CCTV SYSTEM |  |  |  |  | 1,14,550 |  | 80185 |  |  |  | 34365 |  | 28688
A |  |  |  | ₹ |  | 40,38,720 |  | 2653064 |  | 160455.89 |  | 804498 |  | 1084968.5
B |  |  |  | ₹ |  | 7,26,970 |  | RA Bill O8 |  | RA Bill 03 |  | RA Bill 09 |  | ExtraQty RA Bill 09
C |  |  |  | ₹ |  | 47,65,690

## Electrical JMR RA Bill 09
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.06.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : Electrical CIP Lounge T3 Lok
RA-05 MEASUREMENT SHEET OF Electrical
S. No. | Item. Code | Specification | Description | W | H | Unit | Nos | Qty.
1 |  | Electrical
1.1 |  | Wiring for primary light points for Switch controlled points with 2.5 sq. mm LSHF PVC insulated stranded /multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface /concealed conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting, and including the cost of Supply and fixing a 6 amp 240 Volt grid plate mounted switch with moulded cover plate in zinc chromate passivated GI box and including the cost of running 2.5 sq. mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required.
|  | Premum Lounge |  |  |  | Nos | 5
|  | Admin Room |  |  |  | Nos | 3
|  | Kitchen |  |  |  | Nos | 3
|  | Spa Room |  |  |  | Nos | 3
|  | Electrical Room |  |  |  | Nos | 2
|  | Male Washroom |  |  |  | Nos | 3
|  | Female Washroom |  |  |  | Nos | 3
|  | Handicab Washroom |  |  |  | Nos | 2
|  | Recepsion Flote Light |  |  |  | Nos | 2
|  | Baar Area |  |  |  | Nos | 4
|  | Dining Area |  |  |  | Nos | 3
|  | Total Qty |  |  |  |  | 33
|  | WO Qty |  |  |  |  | 30 | Nos
|  | RA 08Qty |  |  |  |  | 21
|  | RA 09Qty |  |  |  |  | 9
|  | RA 09 Extra Qty |  |  |  |  | 3
1.2 |  | Wiring for primary light points for DB / Dimmer/ Sensor/ Automation controlled points with 2.5 sq mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item)(Normal)
|  | Premum Lounge |  |  |  | Nos | 3
|  | Admin Room |  |  |  | Nos | 2
|  | Kitchen |  |  |  | Nos | 2
|  | Spa Room |  |  |  | Nos | 3
|  | Electrical Room |  |  |  | Nos | 2
|  | Male Washroom |  |  |  | Nos | 3
|  | Female Washroom |  |  |  | Nos | 3
|  | Handicab Washroom |  |  |  | Nos | 2
|  | Recepsion Flote Light |  |  |  | Nos | 2
|  | Baar Area |  |  |  | Nos | 5
|  | Dining Area |  |  |  | Nos | 9
|  | Total Qty |  |  |  |  | 36
|  | WO Qty |  |  |  |  | 45 | Nos
|  | RA 08Qty |  |  |  |  | 31.5
|  | RA 09Qty |  |  |  |  | 4.5
Wiring for primary light points for DB/ Dimmer/ Sensor/ Automation controlled points with 2.5 sq mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item). (Emergency)
|  | Premum Lounge |  |  |  | Nos | 1
|  | Admin Room |  |  |  | Nos | 1
|  | Kitchen |  |  |  | Nos
|  | Spa Room |  |  |  | Nos | 1
|  | Electrical Room |  |  |  | Nos
|  | Male Washroom |  |  |  | Nos | 3
|  | Female Washroom |  |  |  | Nos | 3
|  | Handicab Washroom |  |  |  | Nos | 2
|  | Recepsion Flote Light |  |  |  | Nos
|  | Baar Area |  |  |  | Nos
|  | Dining Area |  |  |  | Nos
|  | Total Qty |  |  |  |  | 11
|  | WO Qty |  |  |  |  | 11 | Nos
|  | RA 08Qty |  |  |  |  | 7.7
|  | RA 09Qty |  |  |  |  | 3.3
Wiring for secondary light points with 1.5 sq. mm LSHF PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia 16 SWG GI conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 1.5 sq. mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Normal)
|  | Premum Lounge Ceilling Light |  |  |  | Nos | 9
|  | Premum Lounge Lamp Light |  |  |  | Nos | 11
|  | Premum Lounge Wall Light |  |  |  | Nos | 32
|  | Admin Room Ceilling Light |  |  |  | Nos | 2
|  | Kitchen Ceiiling Light |  |  |  | Nos | 5
|  | Spa Room Ceilling Light |  |  |  | Nos | 29
|  | Electrical Room Ceilling Light |  |  |  | Nos | 2
|  | Male Washroom Ceilling Light |  |  |  | Nos | 8
|  | Female Washroom Ceilling Light |  |  |  | Nos | 6
|  | Handicab Washroom Ceilling Light |  |  |  | Nos | 2
|  | Recepsion Ceilling Light |  |  |  | Nos | 81
|  | Recepsion Wall Light |  |  |  | Nos | 13
|  | Baar Area Ceilling Light |  |  |  | Nos | 46
|  | Baar Area Wall Light |  |  |  | Nos | 32
|  | Dining Area Ceilling Light |  |  |  | Nos | 111
|  | Dining Area Wall Light |  |  |  | Nos | 16
|  | Total Qty |  |  |  |  | 396
|  | WO Qty |  |  |  |  | 352 | Nos
|  | RA 08Qty |  |  |  |  | 246.4
|  | RA 09Qty |  |  |  |  | 105.6
|  | RA 09 Extra Qty |  |  |  |  | 44
Wiring for secondary light points with 1.5 sq. mm LSHF PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia 16 SWG GI conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 1.5 sq. mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Emergency)
|  | Premum Lounge Ceilling Light |  |  |  | Nos | 9
|  | Premum Lounge Lamp Light |  |  |  | Nos | 11
|  | Admin Room Ceilling Light |  |  |  | Nos | 2
|  | Kitchen Ceiiling Light |  |  |  | Nos | 2
|  | Spa Room Ceilling Light |  |  |  | Nos | 2
|  | Electrical Room Ceilling Light |  |  |  | Nos | 1
|  | Male Washroom Ceilling Light |  |  |  | Nos | 6
|  | Female Washroom Ceilling Light |  |  |  | Nos | 3
|  | Handicab Washroom Ceilling Light |  |  |  | Nos | 1
|  | Recepsion Light Ceilling Light |  |  |  | Nos | 10
|  | Baar Area Ceilling Light |  |  |  | Nos | 10
|  | Dining Area Ceilling Light |  |  |  | Nos | 15
|  | Total Qty |  |  |  |  | 63
|  | WO Qty |  |  |  |  | 46 | Nos
|  | RA 08Qty |  |  |  |  | 32.2
|  | RA 09Qty |  |  |  |  | 13.8
|  | RA 09 Extra Qty |  |  |  |  | 17
Wiring for 240 volt 6 amp Multistandard single phase and neutral switch socket outlet with 4 sq. mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing circuit wiring with 2.5 sq mm LSHF PVC insulated stranded/ multistranded copper conductor 1100 volt grade wires and including the cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and Supply and fixing of a 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 2.5 sq. mm LSHF PVC insulated copper earth wire conductor wires complete as directions of Engineer-in- charge and as required.
|  | Dinning Area Serwari Counter Wall Box |  |  |  | Nos | 11
|  | Total Qty |  |  |  |  | 11
|  | WO Qty |  |  |  |  | 11 | Nos
|  | RA 08Qty |  |  |  |  | 7.7
|  | RA 09Qty |  |  |  |  | 3.3
Wiring as in Item 1.6 above looped from an adjacent switch socket outlet as required and Supply and fixing of a combined 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 2.5 sq. mm LSHF PVC insulated copper earth wire conductor wires complete as directions of Engineer-in-charge and as required.
|  | Dinning Area Serwari Counter Wall Box |  |  |  | Nos | 9
|  | Dinning Area Floor Box |  |  |  | Nos | 13
|  | Admin Area Floor Box |  |  |  | Nos | 1
|  | Recepsion Floor Box |  |  |  | Nos | 1
|  | Baar Area Floor Box |  |  |  | Nos | 2
|  | Baar Couter |  |  |  | Nos | 2
|  | Premum Lounge Wall Box |  |  |  | Nos | 11
|  | Total Qty |  |  |  |  | 39
|  | WO Qty |  |  |  |  | 28 | Nos
|  | RA 08Qty |  |  |  |  | 19.6
|  | RA 09Qty |  |  |  |  | 8.4
|  | RA 09 Extra Qty |  |  |  |  | 11
Wiring for a multi-pin 240 volt 6-16 amp single phase and neutral universal switch socket outlet with 4.0 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed conduit including the cost of providing circuit wiring with 4.0 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a combined multi-pin 240 volt 6-16 amp universal socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed galvanized box and including earthing of the 3rd pin with 4.0 sq mm 1100 volt grade LSHF PVC insulated stranded copper conductor wires complete as directions of Engineer-in-charge and as required.
|  | Dinning Area Floor Box |  |  |  | Nos | 43
|  | Baar Area Floor Box |  |  |  | Nos | 4
|  | Dinning Area Wall |  |  |  | Nos | 14
|  | Admin Area Wall |  |  |  | Nos | 1
|  | Recepsion Wall |  |  |  | Nos | 2
|  | Baar Area Wall |  |  |  | Nos | 11
|  | Premum Lounge Wall |  |  |  | Nos | 8
|  | Premum Lounge Floor Box |  |  |  | Nos | 7
|  | Spa Room Wall Box |  |  |  | Nos | 4
|  | Signage Point |  |  |  | Nos | 1
|  | Roller Binder |  |  |  | Nos | 4
|  | Gizer |  |  |  | Nos | 1
|  | RO |  |  |  | Nos | 1
|  | Total Qty |  |  |  |  | 101
|  | WO Qty |  |  |  |  | 46 | Nos
|  | RA 08Qty |  |  |  |  | 32.2
|  | RA 09Qty |  |  |  |  | 13.8
|  | RA 09 Extra Qty |  |  |  |  | 55
Wiring as in Item 1.8 above looped from an adjacent switch socket outlet as per specifications and directions of Engineer-in-charge and providing and fixing of a modular type multi-pin 240 Volt 6-16 amp shuttered socket outlet and a modular type 16 amp 240 Volt single pole switch in a recessed galvanized boxes with internal wiring and moulded front plates complete as directions of Engineer-in-charge and as required.
|  | Primum Loune Table |  |  |  | Nos | 22
|  | Dinning Area Teble |  |  |  | Nos | 13
|  | Premum Lounge Floor Box |  |  |  | Nos | 7
|  | Gizer |  |  |  | Nos | 2
|  | Total Qty |  |  |  |  | 44
|  | WO Qty |  |  |  |  | 21 | Nos
|  | RA 08Qty |  |  |  |  | 14.7
|  | RA 09Qty |  |  |  |  | 6.3
|  | RA 09 Extra Qty |  |  |  |  | 23
Supply , Installation, Testing and comissioning of Pop-up Boxes with all standard accessories consisting of following: a) 3 nos 6 amp socket with 1 no. 16A Switch b) 2 nos Data outlets which includes of Data wiring and terminations. Wiring for socket outlet with 4.0 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 4.0 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a pop up Box on Table/furniture/wall complete as directions of Engineer-in-charge and as required. - Workstations.
|  | Recepsion Table |  |  |  | Nos | 2
|  | Admin Room |  |  |  | Nos | 1
|  | Total Qty |  |  |  |  | 3
|  | WO Qty |  |  |  |  | 3 | Nos
|  | RA 08Qty |  |  |  |  | 2.1
|  | RA 09Qty |  |  |  |  | 0.9
Supply , Installation, Testing and comissioning of Switch socket on furniture with all standard accessories consisting of following: a) 2 nos 6 amp socket with 1 no. 10A Switch b) 2 nos Data outlets which includes of Data wiring and terminations. Wiring for socket outlet with 2.5 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 2.5 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a Box set on furniture/wall complete as directions of Engineer-in-charge and as required. - Dinning Area.
|  | Dinning Room Table |  |  |  | Nos | 11
|  | Total Qty |  |  |  |  | 11
|  | WO Qty |  |  |  |  | 7 | Nos
|  | RA 08Qty |  |  |  |  | 4.9
|  | RA 09Qty |  |  |  |  | 2.1
|  | RA 09 Extra Qty |  |  |  |  | 4
Supply , Installation, Testing and comissioning of Switch socket on furniture with all standard accessories consisting of following: a) 2 nos 6 amp socket with 1 no. 10A Switch b) 1 nos Data outlets which includes of Data wiring and terminations. Wiring for socket outlet with 2.5 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 2.5 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a Box set on furniture/wall complete as directions of Engineer-in-charge and as required. - Premium Lounge & BAR Area.
|  | Primum Lounge Table |  |  |  | Nos | 25
|  | Baar Area Table |  |  |  | Nos | 4
|  | Total Qty |  |  |  |  | 29
|  | WO Qty |  |  |  |  | 17 | Nos
|  | RA 08Qty |  |  |  |  | 11.9
|  | RA 09Qty |  |  |  |  | 5.1
|  | RA 09 Extra Qty |  |  |  |  | 12
Wiring for 6 pin 240 volt 16 amp single phase and neutral Universal switch socket outlets with 4.0 sq. mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including Supply and fixing of a 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switch with moulded cover plate in a recessed zinc chromate passivated GI box including earthing of the 3rd pin with 4.0 sq. mm 1100 volt grade LSHF PVC insulated stranded copper earth wire complete as directions of Engineer-in-charge and as required.
|  | Premum Lounge |  |  |  | Nos | 3
|  | Baar Area |  |  |  | Nos | 5
|  | Spa Room |  |  |  | Nos | 3
|  | Kitchen Area |  |  |  | Nos | 5
|  | Dinning Area |  |  |  | Nos | 7
|  | Recepsion Area |  |  |  | Nos | 1
|  | Roller Binder |  |  |  | Nos | 0
|  | Handycap |  |  |  | Nos | 1
|  | Total Qty |  |  |  |  | 25
|  | WO Qty |  |  |  |  | 14 | Nos
|  | RA 08Qty |  |  |  |  | 9.8
|  | RA 09Qty |  |  |  |  | 4.2
|  | RA 09 Extra Qty |  |  |  |  | 11
Wiring as in Item 1.13 above looped from an adjacent switch socket outlet as per specifications and directions of Engineer-in-charge and providing and fixing of a modular type multi-pin 240 Volt 6-16 amp shuttered socket outlet and a modular type 16 amp 240 Volt single pole switch in a recessed galvanized boxes with internal wiring and moulded front plates complete as directions of Engineer-in-charge and as required.
|  | Premum Lounge |  |  |  | Nos | 7
|  | Baar Area |  |  |  | Nos | 5
|  | Spa Room |  |  |  | Nos | 3
|  | Kitchen Area |  |  |  | Nos | 3
|  | Dinning Area |  |  |  | Nos | 8
|  | Recepsion Area |  |  |  | Nos | 2
|  | Roller Binder |  |  |  | Nos | 1
|  | Handycap |  |  |  | Nos | 1
|  | Total Qty |  |  |  |  | 30
|  | WO Qty |  |  |  |  | 13 | Nos
|  | RA 08Qty |  |  |  |  | 9.1
|  | RA 09Qty |  |  |  |  | 3.9
|  | RA 09 Extra Qty |  |  |  |  | 17
Wiring for 6 pin 240 volt 25 amp single phase and neutral switch socket outlets with
4.0 sq. mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including Supply and fixing of a 240 volt 16 amp socket outlet with safety shutters and 25 amp 240 volt single pole grid plate mounted switch with moulded cover plate in a recessed zinc chromate passivated GI box including earthing of the 3rd pin with 4.0 sq. mm 1100 volt grade LSHF PVC insulated stranded copper earth wire complete as directions of Engineer-in-charge and as required.
[6 empty] | Nos | 1
Kitchen
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Supplying, fixing, testing & commissioning of 32 A, 240 V, SPN metal clad Industrial type socket outlet (IP‐65), with 2 pole and earth, plug top along with 32 A, “C” curve, SP, MCB, in Polycarbonate enclosure, on surface or in recess, with cover for the socket out let and complete with connections, testing and commissioning etc. as required.
|  | Kitchen |  |  |  | Nos | 9
|  | Total Qty |  |  |  |  | 9
|  | WO Qty |  |  |  |  | 12 | Nos
|  | RA 08Qty |  |  |  |  | 8.9
|  | RA 09Qty |  |  |  |  | 0.1
Supplying fixing, testing & commissioning of 32 A, 415 V, TPN Industrial type socket outlet (IP‐65), with 4 pole and earth, plug top along with 32 A, “C” curve, TP MCB, in polycarbonate enclosure, on surface or in recess, with cover for the socket out let and complete with connections, testing and commissioning etc. as required.
|  | Kitchen |  |  |  | Nos | 3
|  | Total Qty |  |  |  |  | 3
|  | WO Qty |  |  |  |  | 3 | Nos
|  | RA 08Qty |  |  |  |  | 2.1
|  | RA 09Qty |  |  |  |  | 0.9
Supplying fixing, testing & commissioning of 32 A, 415 V, TPN 5 pole Industrial type socket outlet (IP‐65), with 4 pole and earth, plug top along with 32 A, “C” curve, MCB, in polycarbonate enclosure, on surface or in recess, with cover for the socket out let and complete with connections, testing and commissioning etc. as required.
|  | RO |  |  |  | Nos | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Providing and fixing of a Data outlet plate mounted outlet unit (RJ-45) with moulded cover plate in recessed zinc chromate passivated GI box complete as directions of Engineer-in-charge and as required for Data system.
|  | Recepsion |  |  |  | Nos | 4
|  | Premum Lounge |  |  |  | Nos | 6
10
|  | Total Qty |  |  |  |  | 10
|  | WO Qty |  |  |  |  | 8 | Nos
|  | RA 08Qty |  |  |  |  | 5.6
|  | RA 09Qty |  |  |  |  | 2.4
|  | RA 09 Extra Qty |  |  |  |  | 2
Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair computer cable with 24 AWG solid copper conductors in surface/concealed conduit/raceways/modular furniture , complete as directions of Engineer-in-charge and as required.
|  | Electric Room To Baar Area Floor | Rmt | 40 |  | 4 | 160
|  | Electric Room To Baar Area Wall | Rmt | 40 |  | 4 | 160
|  | Electric Room To Dinning Area Floor | Rmt | 25 |  | 13 | 325
|  | Electric Room To Dinning Area Wall | Rmt | 25 |  | 4 | 100
|  | Electric Room To Premium Lounge Floor | Rmt | 42.5 |  | 11 | 467.5
|  | Electric Room To Premium Lounge Wall | Rmt | 42.5 |  | 3 | 127.5
|  | Electric Room To Recepsion Floor | Rmt | 36.5 |  | 4 | 146
|  | Electric Room To Recepsion Wall | Rmt | 36.5 |  | 2 | 73
|  | Electric Room To Admin Wall | Rmt | 36.5 |  | 3 | 109.5
|  | Electric Room To Spa Wall | Rmt | 25 |  | 1 | 25
1693.5
|  | Total Qty |  |  |  |  | 1693.5
|  | WO Qty |  |  |  |  | 320 | Rmt
|  | RA 08Qty |  |  |  |  | 320
|  | RA 09Qty |  |  |  |  | 0
|  | RA 09 Extra Qty |  |  |  |  | 1373.5
Supplying, Installation, testing and commissioning of 12U Networking Rack with PDU, switches, jack, patch cords, Ios, and all other accessories complete as required for Server, router & network video recorder.
|  | Electric Room |  |  |  | Nos | 2
|  | Total Qty |  |  |  |  | 2
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
|  | RA 09 Extra Qty |  |  |  |  | 1.3
Supplying, Installation, testing and commissioning of Occupancy Sensor for light control with all accessories and complete as directions of Engineer-in-charge and as required.
|  | Premum Lounge |  |  |  | Nos | 0
|  | Spa Room |  |  |  | Nos | 0
|  | Kitchen Area |  |  |  | Nos | 0
|  | Dinning Area |  |  |  |  | 0
|  | Male Washroom |  |  |  | Nos | 0
|  | Female Washroom |  |  |  | Nos | 0
|  | Handycap Washroom |  |  |  | Nos | 0
|  | Total Qty |  |  |  |  | 0
|  | WO Qty |  |  |  |  | 11 | Nos
RA 08Qty
RA 09Qty
Supplying and drawing wiring with single core stranded copper conductor PVC insulated 1100 volt grade LSHF PVC insulated wires in surface/recessed steel conduit systems including the cost of running copper conductor LSHF PVC insulated loop earthing wire complete as directions of Engineer-in-charge and as required as below.
2 x 2.5 sq mm with 1 x 2.5 sq mm earth wire
|  | Admin Room To Premium Lounge | Rmt | 13 |  | 3 | 39
|  | Admin Room To Baar Area | Rmt | 14 |  | 5 | 70
|  | Admin Room To Dinning Area | Rmt | 15 |  | 8 | 120
|  | Admin Room Room To Recepsion | Rmt | 10 |  | 8 | 80
|  | Admin Room To Admin Room | Rmt | 5 |  | 2 | 10
|  | Electric Room To Spa | Rmt | 14.5 |  | 2 | 29
|  | Admin Room To Male Washroom | Rmt | 26 |  | 2 | 52
|  | Admin Room To Fmale Washroom | Rmt | 26 |  | 2 | 52
|  | Admin Room To Handycap Washroom | Rmt | 30 |  | 1 | 30
|  | Admin Room To Kitchen | Rmt | 23 |  | 2 | 46
528
|  | Total Qty |  |  |  |  | 528
|  | WO Qty |  |  |  |  | 90 | Rmt
|  | RA 08Qty |  |  |  |  | 63
|  | RA 09Qty |  |  |  |  | 27
|  | RA 09 Extra Qty |  |  |  |  | 438
Supplying and drawing wiring with single core stranded copper conductor PVC insulated 1100 volt grade LSHF PVC insulated wires in surface/recessed steel conduit systems including the cost of running copper conductor LSHF PVC insulated loop earthing wire complete as directions of Engineer-in-charge and as required as below.
2 x 4 sq mm with 1 x 4.0 sq mm earth wire
|  | Admin Room To Premium Lounge Wall | Rmt | 13.93 |  | 7 | 97.51
|  | Admin Room To Premium Lounge Floor | Rmt | 14 |  | 7 | 98
|  | Admin Room To Baar Area | Rmt | 13.5 |  | 7 | 94.5
|  | Admin Room To Dinning Area | Rmt | 15 |  | 8 | 120
|  | Admin Room Room To Recepsion | Rmt | 14.4 |  | 5 | 72
|  | Admin Room To Admin Room | Rmt | 6 |  | 3 | 18
|  | Electric Room To Spa | Rmt | 10.5 |  | 4 | 42
|  | Admin Room To Male Washroom | Rmt | 18.3 |  | 3 | 54.9
|  | Admin Room To Fmale Washroom | Rmt | 24 |  | 2 | 48
|  | Admin Room To Handycap Washroom | Rmt | 27 |  | 2 | 54
|  | Admin Room To Washroom Passage | Rmt | 26 |  | 2 | 52
750.91
|  | Total Qty |  |  |  |  | 750.91
|  | WO Qty |  |  |  |  | 330 | Rmt
|  | RA 08Qty |  |  |  |  | 231.7
|  | RA 09Qty |  |  |  |  | 98.3
|  | RA 09 Extra Qty |  |  |  |  | 420.91
Supplying and drawing wiring with single core stranded copper conductor PVC insulated 1100 volt grade LSHF PVC insulated wires in surface/recessed steel conduit systems including the cost of running copper conductor LSHF PVC insulated loop earthing wire complete as directions of Engineer-in-charge and as required as below.
2 x 6 sq mm with 1 x 6.0 sq mm earth wire
|  | Kitchen Room To Kitchen | Rmt | 11.65 |  | 6 | 69.9
69.9
|  | Total Qty |  |  |  |  | 69.9
|  | WO Qty |  |  |  |  | 90 | Rmt
|  | RA 08Qty |  |  |  |  | 63
|  | RA 09Qty |  |  |  |  | 6.9
Supplying and drawing wiring with single core stranded copper conductor PVC insulated 1100 volt grade LSHF PVC insulated wires in surface/recessed steel conduit systems including the cost of running copper conductor LSHF PVC insulated loop earthing wire complete as directions of Engineer-in-charge and as required as below.
4 x 4 sq mm with 2 x 4.0 sq mm earth wire
|  | Kitchen Room To Sarvary Back Counter | Rmt | 17.6 |  | 17 | 299.2
299.2
|  | Total Qty |  |  |  |  | 299.2
|  | WO Qty |  |  |  |  | 90 | Rmt
|  | RA 08Qty |  |  |  |  | 63
|  | RA 09Qty |  |  |  |  | 27
|  | RA 09 Extra Qty |  |  |  |  | 209.2
Supplying and drawing wiring with single core stranded copper conductor PVC insulated 1100 volt grade LSHF PVC insulated wires in surface/recessed steel conduit systems including the cost of running copper conductor LSHF PVC insulated loop earthing wire complete as directions of Engineer-in-charge and as required as below.
4 x 6 sq mm with 2 x 6.0 sq mm earth wire
|  | Kitchen Passage To Kitchen DB Erthing | Rmt | 5.5 |  | 2 | 11
11
|  | Total Qty |  |  |  |  | 11
|  | WO Qty |  |  |  |  | 50 | Rmt
|  | RA 08Qty |  |  |  |  | 35
|  | RA 09Qty |  |  |  |  | -24
Supplying and drawing recessed/surface IS embossed GI conduiting system including cost of providing saddles etc for surface/recess conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer- in-charge and as required as below.
20 mm
|  | Kitchen To Sarvari Back Wall | Rmt | 8 |  | 10 | 80
80
|  | Total Qty |  |  |  |  | 80
|  | WO Qty |  |  |  |  | 110 | Rmt
|  | RA 08Qty |  |  |  |  | 77
|  | RA 09Qty |  |  |  |  | 3
Supplying and drawing recessed/surface IS embossed GI conduiting system including cost of providing saddles etc for surface/recess conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer- in-charge and as required as below.
25 mm
|  | Kitchen To Sarvari Back Wall | Rmt | 13 |  | 14 | 182
182
|  | Total Qty |  |  |  |  | 182
|  | WO Qty |  |  |  |  | 200 | Rmt
|  | RA 08Qty |  |  |  |  | 140
|  | RA 09Qty |  |  |  |  | 42
Supplying and drawing recessed/surface IS embossed GI conduiting system including cost of providing saddles etc for surface/recess conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer- in-charge and as required as below.
32 mm
|  | Admin Room To Ceilling Wall | Rmt | 7 |  | 12 | 84
84
|  | Total Qty |  |  |  |  | 84
|  | WO Qty |  |  |  |  | 110 | Rmt
|  | RA 08Qty |  |  |  |  | 77
|  | RA 09Qty |  |  |  |  | 7
Supplying and drawing recessed/surface IS embossed GI conduiting system including cost of providing saddles etc for surface/recess conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer- in-charge and as required as below.
40 mm
|  | Electric Room To Ceilling Wall | Rmt | 7 |  | 14 | 98
98
|  | Total Qty |  |  |  |  | 98
|  | WO Qty |  |  |  |  | 110 | Rmt
|  | RA 08Qty |  |  |  |  | 77
|  | RA 09Qty |  |  |  |  | 21
Supplying and drawing recessed/surface medium class PVC conduit including cost of providing saddles etc accessories for surface/recess conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer- in-charge and as required as below.
20 mm
|  | For Data | Rmt | 20 |  | 1 | 20
|  | Total Qty |  |  |  |  | 20
|  | WO Qty |  |  |  |  | 30 | Rmt
|  | RA 08Qty |  |  |  |  | 21
|  | RA 09Qty |  |  |  |  | -1
Supply and fixing GI flexible conduit including all fittings complete as required as below.
20 mm
|  | Ceilling | Rmt | 1.5 |  | 165 | 247.5
|  | Total Qty |  |  |  |  | 247.5
|  | WO Qty |  |  |  |  | 265 | Rmt
|  | RA 08Qty |  |  |  |  | 185.5
|  | RA 09Qty |  |  |  |  | 62
Supply and fixing GI flexible conduit including all fittings complete as required as below.
25 mm
|  | Ceilling | Rmt | 1.5 |  | 50 | 75
|  | Total Qty |  |  |  |  | 75
|  | WO Qty |  |  |  |  | 95 | Rmt
|  | RA 08Qty |  |  |  |  | 66.5
|  | RA 09Qty |  |  |  |  | 8.5
Supply and laying cables on Tray / clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling with sand and brick protection as required and including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and PVC sheathed copper conductor cable complete as required. The costs shall include for all cables to be provided with a 1D gap and shall be properly clamped with cable clamps and ties. Identification tags shall be provided for all cables and route markers for cables in ground.
3 -1/2 core 70 Sq mm AL. XLPE AR. Cable
|  | LT Pannel | Rmt | 8 |  | 1 | 8
|  | LT Pannel To Kitchen DB | Rmt | 15 |  | 1 | 15
|  | LT Pannel To Kitchen Passage DB | Rmt | 15 |  | 1 | 15
|  | Total Qty |  |  |  |  | 38
|  | WO Qty |  |  |  |  | 50 | Rmt
|  | RA 08Qty |  |  |  |  | 35
|  | RA 09Qty |  |  |  |  | 3
Supply and laying cables on Tray / clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling with sand and brick protection as required and including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and PVC sheathed copper conductor cable complete as required. The costs shall include for all cables to be provided with a 1D gap and shall be properly clamped with cable clamps and ties. Identification tags shall be provided for all cables and route markers for cables in ground.
4 core 16 Sq mm CU. XLPE AR. Cable
|  | LT Pannel To Admin Room | Rmt | 26 |  | 2 | 52
|  | Total Qty |  |  |  |  | 52
|  | WO Qty |  |  |  |  | 30 | Rmt
|  | RA 08Qty |  |  |  |  | 35
|  | RA 09Qty |  |  |  |  | -5
|  | RA 09 Extra Qty |  |  |  |  | 22
Supply and laying cables on Tray / clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling with sand and brick protection as required and including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and PVC sheathed copper conductor cable complete as required. The costs shall include for all cables to be provided with a 1D gap and shall be properly clamped with cable clamps and ties. Identification tags shall be provided for all cables and route markers for cables in ground.
4 core 4 Sq mm CU. XLPE AR. Cable
|  | LT Pannel To Admin Room | Rmt | 26 |  | 1 | 26
|  | LT Pannel To UPS Input | Rmt | 6 |  | 1 | 6
|  | LT Pannel To AHU | Rmt | 36 |  | 1 | 36
|  | Total Qty |  |  |  |  | 68
|  | WO Qty |  |  |  |  | 160 | Rmt
|  | RA 08Qty |  |  |  |  | 120
|  | RA 09Qty |  |  |  |  | -52
Cable end termination of the following XLPE insulated and PVC sheathed Aluminium conductor cable 1100 Volt grade including cost of crimping heavy duty aluminium lugs, nickel plated brass double compression glands, insulation tape and all requisite material for completion of termination complete as required and as below.
3 -1/2 core 70 Sq mm AL. XLPE AR. Cable
|  | LT Pannel | Nos |  |  | 6 | 6
|  | Total Qty |  |  |  |  | 6
|  | WO Qty |  |  |  |  | 4 | Nos
|  | RA 08Qty |  |  |  |  | 2.8
|  | RA 09Qty |  |  |  |  | 1.2
|  | RA 09 Extra Qty |  |  |  |  | 2
Cable end termination of the following XLPE insulated and PVC sheathed Aluminium conductor cable 1100 Volt grade including cost of crimping heavy duty aluminium lugs, nickel plated brass double compression glands, insulation tape and all requisite material for completion of termination complete as required and as below.
4 core 16 Sq mm CU. XLPE AR. Cable
|  | LT Pannel | Nos |  |  | 8 | 8
|  | Total Qty |  |  |  |  | 8
|  | WO Qty |  |  |  |  | 2 | Nos
|  | RA 08Qty |  |  |  |  | 1.4
|  | RA 09Qty |  |  |  |  | 0.6
|  | RA 09 Extra Qty |  |  |  |  | 6
Cable end termination of the following XLPE insulated and PVC sheathed Aluminium conductor cable 1100 Volt grade including cost of crimping heavy duty aluminium lugs, nickel plated brass double compression glands, insulation tape and all requisite material for completion of termination complete as required and as below.
4 core 4 Sq mm CU. XLPE AR. Cable
|  | LT Pannel | Nos |  |  | 8 | 8
|  | Total Qty |  |  |  |  | 8
|  | WO Qty |  |  |  |  | 20 | Nos
|  | RA 08Qty |  |  |  |  | 14
|  | RA 09Qty |  |  |  |  | -6
14 WAY SPN DB Incoming: 1-25 amp DP 10 kA MCB, B curve with thermal magnetic protective releases incoming with 1nos. 25 amp DP 30 mA RCCB in each phase Outgoings: 14 nos 6/10 amps SP 10 kA MCB, B curve with thermal magnetic protective releases out goings. For FLDB
|  | Electrical Room | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
12 WAY TPN DB-1 Incoming: 1-63 amp FP 10 kA MCB, C curve with thermal magnetic protective releases incoming with 1nos. 63 amp DP 30 mA RCCB in each phase Outgoings: 36 nos 16/20/25/32 amps SP 10 kA MCB, C curve with thermal magnetic protective releases out goings. For PDB
|  | Admin Room | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
12 WAY TPN DB-2 Incoming: 1-32 amp FP 10 kA MCB, B curve with thermal magnetic protective releases incoming with 1nos. 32 amp DP 30 mA RCCB in each phase Outgoings: 36 nos 10 amps SP 10 kA MCB, B curve with thermal magnetic protective releases out goings. For LDB
|  | Admin Room | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
10 WAY TPN DB Supplying & fixing of following double door Emergency Lighting DB's enclosures, with minimum IP 55, UV resistant as per IEC 61439,flame retardant, self extinguishing material for outdoor / harsh environment like resistant to weather influences (humidity, temperature, water sprays). The DB shall include all accessories i.e. earth bar, din bar, neutral bar, tinned copper bus bars, earthing terminal, power painting & cable end box etc. as required. Incoming: 1-32 amp FP 10 kA MCB, C curve with thermal magnetic protective releases Outgoings: 30 nos 10/16/20 amps SP 10 kA MCB, C curve with thermal magnetic protective releases out goings. For EDB (10A MCBs shall be for lighting circuits only)
|  | Admin Room | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
12 WAY VTPN DB INCOMER 1 No. 160A 4 pole MCCB (16 KA) with over load, short circcuit & earth fault protection OUTGOINGS 36 nos. of 20/25/32A modules for SP/TP MCB's, C curve (10KA) as required (Refer DB schedule). DB as described above For KTB-1
|  | Kitchen Passage | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
12 WAY VTPN DB INCOMER 1 No. 160A 4 pole MCCB (16 KA) with over load, short circcuit & earth fault protection OUTGOINGS 36 nos. of 20/25/32A modules for SP/TP MCB's, C curve (10KA) as required (Refer DB schedule). DB as described above For KTB-1
|  | Kitchen | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Electrical LT Panel- IN Electrical Room (Floor Mounted)
|  | Electrical Room | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Supply, installation, testing and commissioning of 8kVA UPS system comprising of online units with a battery backup of 30 minutes duration for full load and with all standards fittings, accessories, protection, instruments, indications and controls including but not restricted to transformer, rectifier, inverter, SMF battery with float cum boost battery charger, static bypass switch, maintenance bypass, interconnections etc. The UPS shall be suitble for three phase 415V Input with variation of + 15% and give constant output supply of 415V + 2%.
|  | Electrical Room | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Supplying and laying of the following earthing strip on cable tray/ wall clamped to wall with suitable clamps saddles and fixing bolts/soldering as required and complete as required to comply with IS 3043:1987. All joints shall be timed. The body earthing of UPS and Panel shall be looped from the existing earthing system.
25 mm x 3 mm GI strip
|  | Electrical Room To Admin Room | Rmt |  | 26 | 1 | 26
|  | Electrical Room To Kitchen | Rmt |  | 13 | 1 | 13
|  | Total Qty |  |  |  |  | 39
|  | WO Qty |  |  |  |  | 50 | Nos
|  | RA 08Qty |  |  |  |  | 35
|  | RA 09Qty |  |  |  |  | 4
Supplying and laying of the following earthing strip on cable tray/ wall clamped to wall with suitable clamps saddles and fixing bolts/soldering as required and complete as required to comply with IS 3043:1987. All joints shall be timed. The body earthing of UPS and Panel shall be looped from the existing earthing system.
25 mm x 3 mm Copper strip for UPS
|  | UPS | Rmt |  | 8 | 1 | 8
|  | Total Qty |  |  |  |  | 8
|  | WO Qty |  |  |  |  | 20 | Nos
|  | RA 08Qty |  |  |  |  | 14
|  | RA 09Qty |  |  |  |  | -6
Supplying and laying of the following earthing strip on cable tray/ wall clamped to wall with suitable clamps saddles and fixing bolts/soldering as required and complete as required to comply with IS 3043:1987. All joints shall be timed. The body earthing of UPS and Panel shall be looped from the existing earthing system.
4 sq.mm dia copper wire
|  | All DB Looping | Rmt |  | 100 | 1 | 100
|  | Total Qty |  |  |  |  | 100
|  | WO Qty |  |  |  |  | 100 | Nos
|  | RA 08Qty |  |  |  |  | 70
|  | RA 09Qty |  |  |  |  | 30
Supplying and fixing of 40A 4P, 415V Isolator in sheet steel enclosure with, connection, testing & commissioning as required.
4 sq.mm dia copper wire
|  | DB Pannel | Nos |  | 1 | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Supply, installation, testing and commissioning of recess/ surface mounting 3W CEILING SPEAKER ,metal grille, dia 150mm and Spring clamps suitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required.
|  | All Area | Nos |  |  | 18 | 18
|  | Total Qty |  |  |  |  | 18
|  | WO Qty |  |  |  |  | 21 | Nos
|  | RA 08Qty |  |  |  |  | 14.7
|  | RA 09Qty |  |  |  |  | 3.3
Supply, installation, testing and commissioning of Wall surface mounting 3W CEILING SPEAKER with 6W/3W optionssuitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required.
|  | All Area | Nos |  |  | 0 | 0
|  | Total Qty |  |  |  |  | 0
|  | WO Qty |  |  |  |  | 2 | Nos
RA 08Qty
RA 09Qty
Supply, installation, testing and commissioning of MS Amplifier Rack Assembly with 30 minutes power backup including 1 no. CD player unit, 1 nos 200 W POWER AMPLIFIER, connectors, internal wiring, interconnection etc capable of voice operated priority complete as required. (PA System fully integrated type with Fire Alarm System with facility for automatic override of music for emergency announcements)
|  | Admin Room | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Supply, installation, testing and commissioning of CONTROL PANEL with single zone selection, ascending 4 tone chime, emergency microphone, expandable upto 5 zones using expansion control panel complete as required.
|  | Kitchen | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Supply, installation, testing and commissioning of Wireless lepal microphone DB technology complete as required
|  | Admin Room | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Design, Engineering, Supply, Receiving, handling, storage, installation, testing and commissioning of the CLOSED CIRCUIT TELEVESION (CCTV) SURVEILLANCE SYSTEM with IP based indoor type fixed varifocal dome camera for the proposed application with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation.
|  | All Area | Nos |  |  | 18 | 18
|  | Total Qty |  |  |  |  | 18
|  | WO Qty |  |  |  |  | 13 | Nos
|  | RA 08Qty |  |  |  |  | 9.1
|  | RA 09Qty |  |  |  |  | 3.9
|  | RA 09 Extra Qty |  |  |  |  | 5
Supply of Network Video/Disk Recorder -16 channel (Including HDD for minimum recording of 30 days) with minimum 500GB Usable Space with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation.
|  | Electric Room | Nos |  |  | 1 | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09Qty |  |  |  |  | 0.3
Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair with 24 AWG solid copper conductors in surface/concealed conduit/raceways complete as required
|  | Electric Room To Baar Area Ceilling | Rmt | 25 |  | 3 | 75
|  | Electric Room To Admin Room Ceilling | Rmt | 25 |  | 1 | 25
|  | Electric Room To Dinning Area Ceilling | Rmt | 21 |  | 5 | 105
|  | Electric Room To Premium Lounge Ceilling | Rmt | 29 |  | 2 | 58
|  | Electric Room To Recepsion Ceilling | Rmt | 28.6 |  | 3 | 85.8
|  | Electric Room To Spa Ceilling | Rmt | 10 |  | 2 | 20
|  | Electric Room To Kitchen | Rmt | 15 |  | 2 | 30
|  | Electric Room | Rmt | 4 |  | 1 | 4
|  | Total Qty |  |  |  |  | 402.8
|  | WO Qty |  |  |  |  | 330 | Rmt
|  | RA 08Qty |  |  |  |  | 231
|  | RA 09Qty |  |  |  |  | 99
|  | RA 09 Extra Qty |  |  |  |  | 72.8

## JMR Electrical RA Bill 8
Price Comparative Statement
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for Toilet & Pantry Work at CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Sort Text | PO Qty. | Site Qty | Units
ELECTRICAL WORKS
A | SUB-HEAD I WIRING
1.1 | Wiring for primary light points for Switch controlled points with 2.5 sq. mm LSHF PVC insulated stranded /multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface /concealed conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting, and including the cost of Supply and fixing a 6 amp 240 Volt grid plate mounted switch with moulded cover plate in zinc chromate passivated GI box and including the cost of running 2.5 sq. mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. | primary light points | 30 | 21 | nos
1.2 | Wiring for primary light points for DB / Dimmer/ Sensor/ Automation controlled points with 2.5 sq mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item)(Normal) | primary light points | 45 | 31.5 | nos
1.3 | Wiring for primary light points for DB/ Dimmer/ Sensor/ Automation controlled points with 2.5 sq mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting and including the cost of running 2.5 sq mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Cost of MCB/Switch shall be consider in this item). (Emergency) | primary light points | 11 | 7.7 | nos
1.4 | Wiring for secondary light points with 1.5 sq. mm LSHF PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia 16 SWG GI conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 1.5 sq. mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Normal) | secondary light points | 352 | 246.4 | nos
1.5 | Wiring for secondary light points with 1.5 sq. mm LSHF PVC insulated stranded/multistranded copper conductor 1100 Volt grade wires in surface/concealed in IS embossed 25mm dia 16 SWG GI conduit including cost of providing saddles hangers supports from soffit of slab etc for surface conduiting, ceiling conduiting and/or cost of cutting and filling chases for recessed conduiting including the cost of running 1.5 sq. mm LSHF PVC insulated copper earth wire for loop earthing etc. complete as directions of Engineer-in-charge and as required. (Emergency) | secondary light points | 46 | 32.2 | nos
1.6 | Wiring for 240 volt 6 amp Multistandard single phase and neutral switch socket outlet with 4 sq. mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 Volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing circuit wiring with 2.5 sq mm LSHF PVC insulated stranded/ multistranded copper conductor 1100 volt grade wires and including the cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and Supply and fixing of a 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 2.5 sq. mm LSHF PVC insulated copper earth wire conductor wires complete as directions of Engineer-in- charge and as required. | 6 amp Multistandard single phase and neutral switch socket | 11 | 7.7 | nos
1.7 | Wiring as in Item 1.6 above looped from an adjacent switch socket outlet as required and Supply and fixing of a combined 240 volt 6 amp Multistandard socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed zinc chromate passivated GI box and including earthing of the 3rd pin with 2.5 sq. mm LSHF PVC insulated copper earth wire conductor wires complete as directions of Engineer-in-charge and as required. | looped from an adjacent switch socket | 28 | 19.6 | nos
1.8 | Wiring for a multi-pin 240 volt 6-16 amp single phase and neutral universal switch socket outlet with 4.0 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed conduit including the cost of providing circuit wiring with 4.0 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a combined multi-pin 240 volt 6-16 amp universal socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed galvanized box and including earthing of the 3rd pin with 4.0 sq mm 1100 volt grade LSHF PVC insulated stranded copper conductor wires complete as directions of Engineer-in-charge and as required. | 16 amp single phase and neutral universal switch socket | 46 | 32.2 | nos
1.9 | Wiring as in Item 1.8 above looped from an adjacent switch socket outlet as per specifications and directions of Engineer-in-charge and providing and fixing of a modular type multi-pin 240 Volt 6-16 amp shuttered socket outlet and a modular type 16 amp 240 Volt single pole switch in a recessed galvanized boxes with internal wiring and moulded front plates complete as directions of Engineer-in-charge and as required. | looped from an adjacent switch socket | 21 | 14.7 | nos
1.1 | Supply , Installation, Testing and comissioning of Pop-up Boxes with all standard accessories consisting of following: a) 3 nos 6 amp socket with 1 no. 16A Switch b) 2 nos Data outlets which includes of Data wiring and terminations. Wiring for socket outlet with 4.0 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 4.0 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a pop up Box on Table/furniture/wall complete as directions of Engineer-in-charge and as required. - Workstations. |  | 3 | 2.1 | nos
1.11 | Supply , Installation, Testing and comissioning of Switch socket on furniture with all standard accessories consisting of following: a) 2 nos 6 amp socket with 1 no. 10A Switch b) 2 nos Data outlets which includes of Data wiring and terminations. Wiring for socket outlet with 2.5 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 2.5 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a Box set on furniture/wall complete as directions of Engineer-in-charge and as required. - Dinning Area. |  | 7 | 4.9 | nos
1.12 | Supply , Installation, Testing and comissioning of Switch socket on furniture with all standard accessories consisting of following: a) 2 nos 6 amp socket with 1 no. 10A Switch b) 1 nos Data outlets which includes of Data wiring and terminations. Wiring for socket outlet with 2.5 sq. mm LSHF PVC insulated stranded copper conductor 1100 Volt grade wires in 25 mm dia GI surface/concealed Conduit / Raceways including the cost of providing circuit wiring with 2.5 sq mm LSHF PVC insulated stranded copper conductor 1100 volt grade wires and including cost of providing brackets, saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and providing and fixing of a Box set on furniture/wall complete as directions of Engineer-in-charge and as required. - Premium Lounge & BAR Area. |  | 17 | 11.9 | nos
1.13 | Wiring for 6 pin 240 volt 16 amp single phase and neutral Universal switch socket outlets with 4.0 sq. mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including Supply and fixing of a 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switch with moulded cover plate in a recessed zinc chromate passivated GI box including earthing of the 3rd pin with 4.0 sq. mm 1100 volt grade LSHF PVC insulated stranded copper earth wire complete as directions of Engineer-in-charge and as required. |  | 14 | 9.8 | Nos.
1.14 | Wiring as in Item 1.13 above looped from an adjacent switch socket outlet as per specifications and directions of Engineer-in-charge and providing and fixing of a modular type multi-pin 240 Volt 6-16 amp shuttered socket outlet and a modular type 16 amp 240 Volt single pole switch in a recessed galvanized boxes with internal wiring and moulded front plates complete as directions of Engineer-in-charge and as required. |  | 13 | 9.1 | nos
1.15 | Wiring for 6 pin 240 volt 25 amp single phase and neutral switch socket outlets with 4.0 sq. mm LSHF PVC insulated stranded/multi stranded copper conductor 1100 volt grade wires in IS embossed 25mm dia 16 SWG GI surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and including Supply and fixing of a 240 volt 16 amp socket outlet with safety shutters and 25 amp 240 volt single pole grid plate mounted switch with moulded cover plate in a recessed zinc chromate passivated GI box including earthing of the 3rd pin with 4.0 sq. mm 1100 volt grade LSHF PVC insulated stranded copper earth wire complete as directions of Engineer-in-charge and as required. |  | 1 | 0.7 | Nos.
1.16 | Supplying, fixing, testing & commissioning of 32 A, 240 V, SPN metal clad Industrial type socket outlet (IP‐65), with 2 pole and earth, plug top along with 32 A, “C” curve, SP, MCB, in Polycarbonate enclosure, on surface or in recess, with cover for the socket out let and complete with connections, testing and commissioning etc. as required. |  | 12 | 8.9 | Nos.
1.17 | Supplying fixing, testing & commissioning of 32 A, 415 V, TPN Industrial type socket outlet (IP‐65), with 4 pole and earth, plug top along with 32 A, “C” curve, TP MCB, in polycarbonate enclosure, on surface or in recess, with cover for the socket out let and complete with connections, testing and commissioning etc. as required. |  | 3 | 2.1 | Nos.
1.18 | Supplying fixing, testing & commissioning of 32 A, 415 V, TPN 5 pole Industrial type socket outlet (IP‐65), with 4 pole and earth, plug top along with 32 A, “C” curve, MCB, in polycarbonate enclosure, on surface or in recess, with cover for the socket out let and complete with connections, testing and commissioning etc. as required. |  | 1 | 0.7 | Nos.
1.19 | Providing and fixing of a Data outlet plate mounted outlet unit (RJ-45) with moulded cover plate in recessed zinc chromate passivated GI box complete as directions of Engineer-in-charge and as required for Data system. |  | -
a) | 1 No. data outlet |  | 8 | 5.6 | nos
b) | 2 Nos. data outlet |  | 2 | 1.4 | nos
1.2 | Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair computer cable with 24 AWG solid copper conductors in surface/concealed conduit/raceways/modular furniture , complete as directions of Engineer-in-charge and as required. |  | 320 | 320 | Mtrs
1.21 | Supplying, Installation, testing and commissioning of 12U Networking Rack with PDU, switches, jack, patch cords, Ios, and all other accessories complete as required for Server, router & network video recorder. |  | 1 | 0.7 | nos
1.22 | Supplying, Installation, testing and commissioning of Occupancy Sensor for light control with all accessories and complete as directions of Engineer-in-charge and as required. |  | 11 | 7.7 | nos
1.23 | Supplying and drawing wiring with single core stranded copper conductor PVC insulated 1100 volt grade LSHF PVC insulated wires in surface/recessed steel conduit systems including the cost of running copper conductor LSHF PVC insulated loop earthing wire complete as directions of Engineer-in-charge and as required as below. |  | -
a) | 2 x 1.5 sq mm with 1 x 1.5 sq mm earth wire |  | - |  | Mtrs
b) | 2 x 2.5 sq mm with 1 x 2.5 sq mm earth wire |  | 90 | 63 | Mtrs
c) | 2 x 4 sq mm with 1 x 4.0 sq mm earth wire |  | 330 | 231.7 | Mtrs
d) | 2 x 6 sq mm with 1 x 6.0 sq mm earth wire |  | 90 | 63 | Mtrs
g) | 4 x 4 sq mm with 2 x 4.0 sq mm earth wire |  | 90 | 63 | Mtrs
h) | 4 x 6 sq mm with 2 x 6.0 sq mm earth wire |  | 50 | 35 | Mtrs
i) | 4 x 10 sq mm with 2 x 10 sq mm earth wire |  | - |  | Mtrs
j) | 4 x 16 sq mm with 2 x 16 sq mm earth wire |  | - |  | Mtrs
1.24 | Supplying and drawing recessed/surface IS embossed GI conduiting system including cost of providing saddles etc for surface/recess conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer- in-charge and as required as below. |  | -
a) | 20 mm |  | 110 | 77 | Mtrs
b) | 25 mm |  | 200 | 140 | Mtrs
c) | 32 mm |  | 110 | 77 | Mtrs
d) | 40 mm |  | 110 | 77 | Mtrs
e) | 50 mm |  | - |  | Mtrs
1.25 | Supplying and drawing recessed/surface medium class PVC conduit including cost of providing saddles etc accessories for surface/recess conduiting and/or cost of cutting and filling chases for recessed conduiting complete as directions of Engineer- in-charge and as required as below. |  | -
a) | 20 mm |  | 30 | 21 | Mtrs
b) | 25 mm |  | - |  | Mtrs
c) | 32 mm |  | - |  | Mtrs
d) | 40 mm |  | - |  | Mtrs
1.26 | Supply and fixing GI flexible conduit including all fittings complete as required as below. |  | -
a) | 20 mm |  | 265 | 185.5 | Mtrs
b) | 25 mm |  | 95 | 66.5 | Mtrs
B | SUB-HEAD II CABLES & RACEWAYS
1 | Supply and laying cables on Tray / clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling with sand and brick protection as required and including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and PVC sheathed copper conductor cable complete as required. The costs shall include for all cables to be provided with a 1D gap and shall be properly clamped with cable clamps and ties. Identification tags shall be provided for all cables and route markers for cables in ground.
a) | 3 -1/2 core 240 Sq mm AL. XLPE AR. Cable |  | - |  | Mtrs
b) | 3 -1/2 core 95 Sq mm AL. XLPE AR. Cable |  | - |  | Mtrs
c) | 3 -1/2 core 70 Sq mm AL. XLPE AR. Cable |  | 50 | 35 | Mtrs
d) | 3 -1/2 core 50 Sq mm AL. XLPE AR. Cable |  | - |  | Mtrs
e) | 4 core 16 Sq mm CU. XLPE AR. Cable |  | 30 | 21 | Mtrs
f) | 4 core 6 Sq mm CU. XLPE AR. Cable |  | - |  | Mtrs
g) | 4 core 4 Sq mm CU. XLPE AR. Cable |  | 160 | 120 | Mtrs
2 | Cable end termination of the following XLPE insulated and PVC sheathed Aluminium conductor cable 1100 Volt grade including cost of crimping heavy duty aluminium lugs, nickel plated brass double compression glands, insulation tape and all requisite material for completion of termination complete as required and as below.
a) | 3 -1/2 core 240 Sq mm AL. XLPE AR. Cable |  | - |  | Nos
b) | 3 -1/2 core 95 Sq mm AL. XLPE AR. Cable |  | - |  | Nos
c) | 3 -1/2 core 70 Sq mm AL. XLPE AR. Cable |  | 4 | 2.8 | Nos
d) | 3 -1/2 core 50 Sq mm AL. XLPE AR. Cable |  | - |  | Nos
3 | Cable end termination of the following XLPE insulated and PVC sheathed Aluminium/ copper conductor cable 1100 Volt grade including cost of crimping heavy duty copper lugs, nickel plated brass double compression glands, insulation tape and all requisite material for completion of termination complete as required and as below.
a) | 4 core 16 Sq mm CU. XLPE AR. Cable |  | 2 | 1.4 | Nos
b) | 4 core 6 Sq mm CU. XLPE AR. Cable |  | - |  | Nos
c) | 4 core 4 Sq mm CU. XLPE AR. Cable |  | 20 | 14 | Nos
4 | Supply and fixing of perforated sheet steel slotted cable trays with vertical sides on both ends as per approved design and GI angle supports spaced 1000 mm apart throughout the length as specified, including the cost of 1 meter GI rod hangers, hooks, dash fasteners, painting etc. for suspension from ceiling complete as required.
a) | 300 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cover |  | 20 |  | Mtrs
b) | 150 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cover |  | 20 |  | Mtrs
c) | 100 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cover |  | 60 |  | Mtrs
GI Raceway & Junction boxes (IP 55)
5 | Supply, assembly and laying of under floor trunking made out of minimum 1.6 mm thick pre galavised sheet with enamel paint finish complete with jointing sleeve, horizontal bends, vertical bends, level adjustment components and closer, vertical elbow, covers, access outlet. etc. complete with all other accessories under floor installation including cutting and chasing the floor/ or on surface, making good the same, placing in position and cleaning from inside complete etc. as required.
a) | 300 mm x 40 mm (3 compartment - 1 For Power, 1 for Data, 1 blank for seperation ) |  | - |  | Mtrs
b) | 225 mm x 40 mm (2 compartment - 1 For Power, 1 for Data ) |  | 40 |  | Mtrs
c) | 150 mm x 40 mm (1 compartment) |  | 10 |  | Mtrs
d) | 100 mm x 40 mm (2 compartment - 1 For Power, 1 for Data ) |  | 20 |  | Mtrs
e) | 75 mm x 40 mm (1 compartment) |  | 10 |  | Mtrs
f) | Providing and fixing 350 x 350 x 50 mm deep junction box for Power & Data raceways in floor |  | - |  | Nos
g) | Providing and fixing 250 x 250 x 50 mm deep junction box for Power & Data raceways in floor |  | 12 |  | Nos
h) | Providing and fixing 150 x 150 x 50 mm deep junction box for Power & Data raceways in floor |  | 13 |  | Nos
C | SUB-HEAD III DISTRIBUTION BOARD & ELECTRICAL PANEL
1 | Supply, erection, testing and commissioning of the following sheet steel clad wall/recess mounting dust and vermin proof double distribution boards constructed from 1.2mm sheet steel IP 42 construction, finished with rust proof red oxide coating and two coats of paint with hinged gasketted door and housing the following complete with suitably rated PVC insulated tinned copper busbars with interconnections and neutral bar assembly, earthing terminals/bar, din bar complete, powder painted including earthing as approved by the Architects/ Engineer in charge. Padlocking facility shall be provided on the door. The DB shall be provided with cable end boxes.
a) | 14 WAY SPN DB Incoming: 1-25 amp DP 10 kA MCB, B curve with thermal magnetic protective releases incoming with 1nos. 25 amp DP 30 mA RCCB in each phase Outgoings: 14 nos 6/10 amps SP 10 kA MCB, B curve with thermal magnetic protective releases out goings. For FLDB |  | 1 | 0.7 | nos
b) | 12 WAY TPN DB-1 Incoming: 1-63 amp FP 10 kA MCB, C curve with thermal magnetic protective releases incoming with 1nos. 63 amp DP 30 mA RCCB in each phase Outgoings: 36 nos 16/20/25/32 amps SP 10 kA MCB, C curve with thermal magnetic protective releases out goings. For PDB |  | 1 | 0.7 | nos
c) | 12 WAY TPN DB-2 Incoming: 1-32 amp FP 10 kA MCB, B curve with thermal magnetic protective releases incoming with 1nos. 32 amp DP 30 mA RCCB in each phase Outgoings: 36 nos 10 amps SP 10 kA MCB, B curve with thermal magnetic protective releases out goings. For LDB |  | 1 | 0.7 | nos
1.1 | 10 WAY TPN DB Supplying & fixing of following double door Emergency Lighting DB's enclosures, with minimum IP 55, UV resistant as per IEC 61439,flame retardant, self extinguishing material for outdoor / harsh environment like resistant to weather influences (humidity, temperature, water sprays). The DB shall include all accessories i.e. earth bar, din bar, neutral bar, tinned copper bus bars, earthing terminal, power painting & cable end box etc. as required. Incoming: 1-32 amp FP 10 kA MCB, C curve with thermal magnetic protective releases Outgoings: 30 nos 10/16/20 amps SP 10 kA MCB, C curve with thermal magnetic protective releases out goings. For EDB (10A MCBs shall be for lighting circuits only) |  | 1 | 0.7 | nos
1.2 | SITC of All VTPN DB's double door and modules, shall be pre assembled with vertical bus bars & minimum IP‐55, UV resistant as per IEC 61439, suitable for outdoor/harsh environment like resistant to weather influences (humidity, temperature, water spray s), chemical resistanc etc. The DB shall include all accessories i.e. earth bar, din bar, neutral bar, tinned copper bus bars, earthing terminal, power painting & cable end box etc. as required. |  | -
a) | 12 WAY VTPN DB INCOMER 1 No. 160A 4 pole MCCB (16 KA) with over load, short circcuit & earth fault protection OUTGOINGS 36 nos. of 20/25/32A modules for SP/TP MCB's, C curve (10KA) as required (Refer DB schedule). DB as described above For KTB-1 |  | 1 | 0.7 | nos
b) | 10 WAY VTPN DB INCOMER 1 No. 160A 4 pole MCCB (16 KA) with over load, short circcuit & earth fault protection OUTGOINGS 30 nos. of 20/25/32A modules for SP/TP MCB's (10KA), C curve as required (Refer DB schedule). DB as described above For KTB-1 |  | 1 | 0.7 | nos
| Electrical Panel- IN Electrical Room (Floor Mounted) |  | -
2 | Design, Manufacture, Supply, delivery and coordination for Installation of the following front operated modular compartmentalised construction cubicle type, front access, dead back, 2mm thick steel enclosed free standing / wall mounted, dust and vermin proof, switchboard with IP42/Specified protection with hinged and lockable doors duly powder coated complete with interconnections, tinned copper crimping lugs, bonding to earth and painting, suitable for use at 415 volts, 3 phase 4 wire 50 Hertz system, and to withstand a symetrical fault level of 25 kA |  | -
| All Switchboards shall have provision for entry of cables from the top or bottom as required. |  | -
| All live accessible parts shall be shrouded and all equipment shall be finger touch proof. The Busbars insulation shall be with heat shrinkable sleeves. SMC/DMC shrouds and busbar supports shall be used. Padlocking facility shall be provided on all outgoing feeders doors and switch handles shall be lockable in OFF position |  | -
| The cost shall include providing and fixing of 75 x 50 x 6 mm channels for switchboard support. |  | -
| All MCCB shall have rotary handles & extension terminal, phase barrier on both sides as required at site. |  | -
| All metering panel shall be extendable type with cable alley. |  | -
| GA drawings shall be got approved from Owners/ Architects/ Consultants before fabrication. |  | -
| Note:- The Manufacturer/Supplier shall supervise the installation, testing and commissioning of the cubicle panels by the electrical contractor. |  | -
| INCOMING |  | -
| 1 No. 250Amps. 4P MCCB '25ka, Icu=Ics with micro processor release having O/L , S/C, earth fault protection equipped with the following: |  | -
| The incomers shall have the following indicating panel |  | -
a) | 1 set of phase indication lamps (R, Y, B) with 2A MCB |  | -
b) | 1 set of ON,OFF,TRIP indicating light with 2A MCB |  | -
c) | Digital Multifunction Meter, accuracy class 1s, with LED/LCD screen of Max Demand Load, I ;V; Hz; Active, Reactive , Apparent Power & Energy; Power factor; % unbalance of current & voltage; with RS 485 / Ethernet port with 3 Nos. cast resin current transformers of dual core CT's of suitable Amp. ratio, 15 VA Class1.0 m etering., protection MCBs as required accessories to complete the system. |  | -
| BUSBAR |  | -
| FP aluminium extensible type main bus bars of minimum of 300 Amp 25kA capacity with heat shrinkable coloured sleeves and i/c DMC/SMC bus bars supports at required intervals complete. |  | -
| OUTGOING UNITS |  | -
| 3 Nos. 160A TPN MCCB, 16kA, (Ics=lcu) with O/L, S/C |  | -
| 3 nos 63 amp 4P 10 kA MCB with thermal magnetic protective releases |  | -
| 2 nos 25 amp 4P 10 kA MCB with thermal magnetic protective releases |  | -
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required. (Note: Length of the panel should not increase more than 1600mm, 400mm depth and 2000mm height). |  | 1 | 0.7 | nos
| UPS 8KVA |  | -
3 | Supply, installation, testing and commissioning of 8kVA UPS system comprising of online units with a battery backup of 30 minutes duration for full load and with all standards fittings, accessories, protection, instruments, indications and controls including but not restricted to transformer, rectifier, inverter, SMF battery with float cum boost battery charger, static bypass switch, maintenance bypass, interconnections etc. The UPS shall be suitble for three phase 415V Input with variation of + 15% and give constant output supply of 415V + 2%. |  | 1 | 0.7 | nos
4 | Supplying and laying of the following earthing strip on cable tray/ wall clamped to wall with suitable clamps saddles and fixing bolts/soldering as required and complete as required to comply with IS 3043:1987. All joints shall be timed. The body earthing of UPS and Panel shall be looped from the existing earthing system. |  | -
a) | 25 mm x 3 mm GI strip |  | 50 | 35 | Mtrs
b) | 25 mm x 3 mm Copper strip for UPS |  | 20 | 14 | Mtrs
c) | 6 SWG GI Wire |  | 120 | 84 | Mtrs
d) | 8 SWG GI Wire |  | - |  | Mtrs
e) | 4 sq.mm dia copper wire |  | 100 | 70 | Mtrs
4 | Providing and fixing M.V danger notice plate of 200 mm x 150 mm, made mild steel, atleast 2 mm thick, and vitreous enameled white on both sides, and with inscription in single red colour on front side as required. |  | - |  | nos
5 | Supplying and fixing of 40A 4P, 415V Isolator in sheet steel enclosure with, connection, testing & commissioning as required. |  | 1 | 0.7 | nos
TOTAL FOR DISTRIBUTION BOARD & ELECTRICAL PANEL
D | SUB-HEAD IV FIRE DETECTION & PA SYSTEM
I | Fire Detection System
1 | Supply, installation, testing and commissioning of 1 Loop wall recess mounting microprocessor based networkable analogue addressable Fire Control Panel having a Fire Alarm Capability of 100/125/150 detectors/devices per loop with each loops length being restricted to 80% of manufacturer specified maximum loop length). The Fire control panel shall have 100% hot redundancy for CPU, load etc. It shall be expandable by minimum 1 additional loops. The operating panel shall have minimum 80 character LCD display, 4 access levels, 1000 events historical logging, flash E- PROM, 240 volts ac power supply, automatic battery charger, 24V sealed lead-acid battery suitable operating the system for 24 hours in emergency condition. The Panel shall be Integrated with the PA System and with suitable power amplifiers for the hooter/strobes and main building fire alarm panel.
The Panel shall be Integrated with the BMS System and shall include cost of supply of any additional modules, software and interfaces as required for the same and as required by the Client. The Panel shall provide either or all BACNET/RS485/ LON/MODBUS protocols as required. The panel shall be complete as per specifications and as required.
a) | 1 Loop |  | 1 | 0.7 | nos
2 | Supply, installation, testing and commissioning of plug-in type intelligent analogue addressable multi criteria Smoke detectors including the cost of base plate, 75 mm dia M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. |  | 42 | 29.4 | nos
3 | Supply, installation, testing and commissioning of plug-in type intelligent analogue addressable rate of rise cum fixed temperature Heat detectors including the cost of base plate, 75 mm dia M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. |  | 3 | 2.1 | nos
4 | Supply, installation, testing and commissioning of Addressable type fault for isolating shorted, dewired and loose circuits between two successive fault isolators with automatic resetting arrangement (base Model) |  | 5 | 3.5 | nos
5 | Supply, installation, testing and commissioning of Addressable type Response indicatior. |  | 25 | 17.5 | nos
3 | Supply, installation, testing and commissioning of addressable type duct detector including the cost of plate, M.S. outlet box for fixing of the detector base, mounting accessories etc. complete as per specifications and as required. |  | 4 | 2.8 | nos
6 | Supply, installation, testing and commissioning of intelligent analogue addressable Control Modules including the cost of 75 mm dia MS outlet box for fixing of the module, mounting accessories complete as per specifications and as required. |  | - |  | nos
7 | Supply, installation, testing and commissioning of intelligent analogue addressable dry contact Monitor Modules including the cost of 75 mm dia MS outlet box for fixing of the module, mounting accessories complete as per specifications and as required. |  | - |  | nos
8 | Supply, installation, testing and commissioning of recess/surface mounting dust and vermin proof intelligent addressable analogue Manual Pull stations including cost of all required modules, mounting accessories etc including the cost of M.S. outlet box for fixing of the station, mounting accessories etc. complete as per specifications and as required. |  | 1 | 0.7 | nos
9 | Supply, Installation, Testing and commissioning of high intensity hooters cum Strobe Lights with 110 cd. The strobes shall be synchronized for better evacuation. |  | 1 | 0.7 | nos
10 | Supply, laying, testing and commissioning of 2 core 1.5 sqmm copper conductor LSHF PVC insulated 1100 volt wires in IS embossed black enameled 25mm dia 16 SWG MS recessed and/or surface conduiting system including cost of providing saddles etc for surface conduiting and/or cost of cutting and filling chases for recessed conduiting as required and including the cost of crimped termination's complete as required. (Smoke detector and speaker) |  | 600 | 420 | Mtrs
II | Public Address system |  | -
1 | Supply, installation, testing and commissioning of recess/ surface mounting 3W CEILING SPEAKER ,metal grille, dia 150mm and Spring clamps suitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required. |  | 21 | 14.7 | nos
2 | Supply, installation, testing and commissioning of Wall surface mounting 3W CEILING SPEAKER with 6W/3W optionssuitable for broadcast of speech and alarm siren including cost of supplying all mounting accessories complete as required. |  | 2 | 1.4 | nos
3 | Supply, installation, testing and commissioning of MS Amplifier Rack Assembly with 30 minutes power backup including 1 no. CD player unit, 1 nos 200 W POWER AMPLIFIER, connectors, internal wiring, interconnection etc capable of voice operated priority complete as required. (PA System fully integrated type with Fire Alarm System with facility for automatic override of music for emergency announcements) |  | 1 | 0.7 | nos
4 | Supply, installation, testing and commissioning of CONTROL PANEL with single zone selection, ascending 4 tone chime, emergency microphone, expandable upto 5 zones using expansion control panel complete as required. |  | 1 | 0.7 | nos
5 | Supply, installation, testing and commissioning of Wireless lepal microphone DB technology complete as required |  | 1 | 0.7 | nos
6 | Supply, installation, testing and commissioning of Microphone with table stand |  | 1 | 0.7 | nos
TOTAL FOR FIRE DETECTION & PA SYSTEM
E | SUB-HEAD V CCTV SYSTEM
1 | Design, Engineering, Supply, Receiving, handling, storage, installation, testing and commissioning of the CLOSED CIRCUIT TELEVESION (CCTV) SURVEILLANCE SYSTEM with IP based indoor type fixed varifocal dome camera for the proposed application with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation. |  | 13 | 9.1 | nos
2 | Supply of Network Video/Disk Recorder -16 channel (Including HDD for minimum recording of 30 days) with minimum 500GB Usable Space with all components, accessories, fixing & mounting accessories etc. as complete as required for the succesfull operation. |  | 1 | 0.7 | nos
3 | Supplying, laying, testing and commissioning of 4-pair Non-plenum Enhanced Cat 6 unshielded twisted pair with 24 AWG solid copper conductors in surface/concealed conduit/raceways complete as required |  | 330 | 231 | Mtrs
A | Total Basic |  |  |  | ₹
B | Taxes |  |  |  | ₹
C | Price [A+B] |  |  |  | ₹

## JMR Electrical RA Bill 02
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 11.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF RACEWAY
S. No. | Item. Code | Specification | Qty. | Unit | Rate | Amount | Remrks
1 | 5 | Supply,assembly and laying of under floor trunking made out of minimum 1.6 mm thick pre galavised sheet with enamel paint finish complete with jointing sleeve,horizontal bends,vertical bends,level adjustment components and closer,vertical elbow,covers,access outlet.etc. complete with all other accessories under floor installation including cutting and chasing the floor/or on surface, making good the same,placing in the position and cleaning from inside complete etc.as required.
|  | b) 225 mm x 40 mm (2 compartment - 1 For Power, 1 for Data ) | 26.12 | MTR. | 2300 | 60076
|  | c) 150 mm x 40 mm (1 compartment) | 5.6 | MTR. | 1250 | 7000
|  | d) 100 mm x 40 mm (2 compartment - 1 For Power, 1 for Data | 15.87 | MTR. | 900 | 14283
|  | e) 75 mm x 40 mm (1 compartment) | 3.52 | MTR. | 850 |  | NT Item
|  | g) Providing and fixing 250 x 250 x 50 mm deep junction box for Power & Data raceways in floor | 13 | NOS. | 1500 | 19500
|  | h) Providing and fixing 150 x 150 x 50 mm deep junction box for Power & Data raceways in floor | 9 | NOS. | 1200 | 10800
|  | i) Providing and fixing 100 x 100 x 50 mm deep junction box for Data raceways in floor | 14 | NOS. | 900 | 12600
|  |  | Total Amount in Rupees |  |  | 124259
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 11.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF CABLETRAY
S. No. | Item. Code | Specification | Qty. | Unit | Rate | Amount | Remrks
1 | 4 | Supply and fixing of perforated sheet steel slotted Cable trays with vertical sides on both ends as per approved design and GI angle supports spaced 1000 mm aparts throut the length as specified ,including the cast of 1 meter GI rod hangers, hooks,dash fasteners,painting etc. for suspension from celling complete as required.
|  | a) 300 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cover | 11.939 | MTR. | 1560 | 18624.84
|  | b) 150 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cove | 10.54 | MTR. | 1150 | 12121
|  | c) 100 mm x 50 mm x 50 mm (with 40 x 40 x 6 mm GI angle supports) and with Cove | 6.413 | MTR. | 850 | 5451.05
|  |  |  | Total Amount |  | 36196.89

## Abstract Sheet HVAC
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Code / Area Specified | Qty. | UoM | Impulse Branding |  | RA Bill -08 |  | RA Bill -10 |  | Cumulative |  | Variance
[5 empty] | Unit Price | Total Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount
[5 empty] | INR | INR
HVAC WORKS
A | DUCTWORK AND AIR DISTRIBUTION |  |  |  |  | -
1 | Supply, installation and testing of SITE Fabricated GI sheet metal ducts as per IS- 655 Standard in accordance with the approved shop drawings as required by the specifications. Quoted price shall be inclusive of all necessary supports by MS structural steel if required, hangers, clamp supports from walls, floors and ceiling including cutting holes and chases in brick, R.C.C. work, making good the same to original condition complete in all respects with painting with one coat of primer and two coats of paint to supports of MS work Note:All exposed surfaces & duct shall be painted in black mat finish by the HVAC contractor. |  |  |  |  | -
a | 24 gauge galvanised sheet steel (0.63 mm) |  | 370 | Sqm. | 1350 | 4,99,500 | 259 | 349650 | 59.2087 | 79931.745
b | 22 gauge galvanised sheet steel (0.8 mm) |  | 100 | Sqm. | 1650 | 1,65,000 | 70 | 115500 | 4.144 | 6837.6
c | 20 gauge galvanised sheet steel (1.0 mm) |  | - | Sqm. | 1850 | -
d | 18 gauge galvanised sheet steel (1.25 mm) |  | - | Sqm. | 2000 | -
2 | Supply, fabrication, installation, testing and comissioning of Flexible Canvas constructed of fire resistant double resin sleeve as per the approved shop drawings. |  | 8 | RMT | 500 | 4000 | 5.6 | 2800
3 | Supply, Installation,Testing and Balancing of flexible ducting comprising of inner as well as outer skin constructed out of aluminium & fibre glass insulation 25mm thick of minimum 24 kg/cu.m density insulation sandwitched in between. Duct should confirm to fire rating standards BS-476 part 5, 6 & 7. Flexible Ducts of following sizes as per approved shop drawings, specifications : |  | - |  |  | -
a | 300 mm dia. |  | - | Mtr. | 2350 | -
b | 200 mm dia. |  | - | Mtr. | 1850 | -
c | 150 mm dia. |  | - | Mtr. | 1450 | -
d | 100 mm dia. |  | - | Mtr. | 1200 | -
4 | Supply, installation and testing of GI construction Opposed blade Volume control dampers within ducts to be provided with suitable ducts lever and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system. |  | 3.5 | Sqm. | 3500 | 12250 | 2.45 | 8575 | 1 | 3500
5 | Supply, installation, testing and commissioning of Fire damper from approved shop drawings and as per specifications. |  | - |  |  | -
a | Fire Dampers (Fusible link) |  | 1.5 | Sqm. | 8600 | 12900 | 1.05 | 9030
6 | Supply, installation, testing and balancing of powder coated Extruded Aluminium Supply Air Grilles with volume control dampers in accordance with the approved shop drawings and specifications. |  | 2.5 | Sqm. | 8600 | 21500 | 1.75 | 15050 | -0.435 | -3741
7 | Supply, installation, testing and balancing of powder coated extruded Aluminium Exhaust/Return Air Grilles without volume control dampers with adjustable double louvers. |  | 3.5 | Sqm. | 6500 | 22750 | 2.45 | 15925 | 1.0518 | 6836.7
8 | Supply, installation, testing and balancing of Powder coated extruded aluminium construction square / round shape Return / Exhaust Air Diffusers with removable core & anti smudge ring & as per approved drawings and specifications. |  | 1.5 | Sqm. | 6500 | 9750 | 1.05 | 6825
9 | Supply, installation, testing and balancing of Powder coated extruded aluminium construction square / round shape Supply Air Diffusers with removable core & anti smudge ring & volume control dampers as per approved drawings and specifications. |  | 1.3 | Sqm. | 6500 | 8450 | 0.91 | 5915
10 | Supply, installation, testing and balancing of Powder coated/Anodised extruded aluminium construction. Louvers with bird screen for exhaust air as per specifications and approved drawings. |  | - | Sqm. | 6500 | -
11 | Supply, installation, testing and balancing of Powder coated/Anodised extruded aluminium construction Inlet air louvers with bird screen and volume damper for outside air as per specifications and approved shop drawings. |  | - | Sqm. | 6500 | -
12 | Supply, Installation and Testing of single piece GI round spigot made out of spinning process with 50mm height and having grooves on both sides and circular flanges. Spigots shall be installed on main ducts to facilitate connection of flexible ducts.
a | 300 mm dia. |  | - | Mtr. | 2100 | -
b | 200 mm dia. |  | - | Mtr. | 1800 | -
c | 150 mm dia. |  | - | Mtr. | 1500 | -
d | 100 mm dia. |  | - | Mtr. | 1200 | -
13 | Supply, Installation and Testing of Butterfly damper of aluminium sheet construction with two flap with sleeve as per thespecifications and shop drawings. |  | - |  |  | -
a | 300 mm dia. |  | - | Mtr. | 2500 | -
b | 200 mm dia. |  | - | Mtr. | 2100 | -
c | 150 mm dia. |  | - | Mtr. | 1650 | -
d | 100 mm dia. |  | - | Mtr. | 1200 | -
14 | Air Transfer Grilles |  | - |  |  | -
| Supply, Installation and testing of extruded aluminium powder coated air transfer grilles to be provided at the door of toilets/pantry. |  | 1 | Sqm | 7600 | 7600 | 0.7 | 5320
15 | THERMAL INSULATION |  | - |  |  | -
15.1 | THERMAL INSULATION FOR DUCTWORK |  | - |  |  | -
| Supply and Application of external thermal insulation of supply /return air ducting using closed cell elastomeric nitrile rubber insulation with class 'O' fire retardant properties as per the specifications and drawings. Quoted price shall be inclusive of adhesive, tapes as per specification. insulation shall be provided with aluminium foil, factory laminated. |  | - |  |  | -
| Insulation thickness/application will be as per approved shop drawing notes. |  | - |  |  | -
a. | 25 mm thick |  | - | Sqm | 1500 | -
b. | 19 mm thick (Fresh air Duct in Non AC Area) |  | - | Sqm | 1300 | -
c. | 16 mm thick (S/Air duct in Non AC Area) |  | - | Sqm | 1200 | -
d. | 13 mm thick (R/Air duct in non AC Area) |  | 50 | Sqm | 950 | 47500 | 35 | 33250
e. | 9 mm thick (S/Air duct in R/Air Contact) |  | 270 | Sqm | 1250 | 3,37,500 | 189 | 236250 | 205.6167 | 257020.875
15.2 | ACOUSTIC LINING OF DUCTS |  | - |  |  | -
| Supply and Application of internal acoustic lining of supply air ducting using open cell nitrile rubber insulation with density within 140-180 Kg/m3 as per the approved shop drawings and specifications. Insulation material shall be bonded with the ducts using metal screw and washers to facilitate grip to the GI sheet. |  | - |  |  | -
a. | 10mm thick lining |  | - | Sqm | 1350 | -
b. | 25mm thick lining |  | - | Sqm | 1650 | -
| TOTAL FOR DUCTWORK AND AIR DISTRIBUTION |  |  |  |  | 11,48,700 |  | 804090 |  | 350385.92
B | VENTILATION FANS AND ARRANGEMENT
1 | VENTILATION FANS |  |  |  |  | -
1.1 | INLINE FANS WITHOUT FILTER |  |  |  |  | -
| Supply, installation, testing and commissioning of duct mounted IN-LINE FANS for exhaust air as shown in drawings. Each fan shall be complete with motor, mounting flanges, accessories like bird screen, fixed louvers and GI sheet canopy for weather protection as required. Quoted price shall be inclusive of electronic speed regulator and wiring between fan & speed regulator for single phase fans. Incase of 3 phase fans quoted price shall be inclusive of DOL starter panel with cabling between starter panel and fan. Fans shall have low noise level in rage of 35-40dBA @3m and shall be suitable for indoor installations. |  |  |  |  | -
| Quoted prices shall be inclusive of all necessary supports by MS structural steel if required, hangers, clamp supports from walls, floors and ceiling with painting with one coat of primer and two coats of paint to supports of MS work. In addition, 18G GI sheet canopy work and vibration isolator pads to make installation vibration free for fans to be installed on terrace. Note : Static Pressure for all fans need to checked by the contractor after the installation of ducting. |  |  |  |  | -
| Fan Selection arrangement shall be as follows: |  |  |  |  | -
| Fan Capacity S.P Area to |  |  |  |  | -
| No. (Cfm) (mmWG) to be exhausted |  |  |  |  | -
a. | IF-1 500 14-15 Electrical Room |  | 1 | No | 65000 | 65000 | 0.7 | 45500
b. | IF-1 500 14-15 Toilet |  | 1 | No | 65000 | 65000 | 0.7 | 45500
1.2.1 | Supply, Installation, Testing and Commissioning of Dry Type Scrubber each comprising of extract air intake section, electrostatic precipitation technology, dry type air cleaner to remove oil, smoke and fumes from exhaust air, as per the Specifications. |  | - |  |  | -
| Electrostatic section shall be made of 16/18 gauge galvanised sheet, high baked epoxy powder coated, washable type aluminium mesh filters, stainless steel spiked ionizers to create high voltage DC field, aluminum collector plates which should be alternatively charged positive and negative with large collecting area with 14" deep cell, to work as magnet for charged smoke and oil particles. Average efficiency of 90- 95% in single pass as per ASHRAE test method. Electrostatic Precipitator should be able to charge particles from 0.01 micron to 10 microns through solid state power supply. Collector cell should be of permanent type and incorporate slide out facility for easy removal for cleaning. Power supplies shall be 100% solid state UL Listed, Module of capacity above 3000 CFM shall be equipped with Pulse width modulating (PWM)The system should be fitted with interlock switch for safety . The system should allow connection to a fan section to achieve 500 FPM velocity across the air cleaner. Vendor to include cost of MCB & single phase wiring for AC supply to the Scrubber. |  | - |  |  | -
| Operating Voltage : 220V, 50 Hz Ionizing Voltage : 12.5 to 13 KVDC Collector Cell Voltage : 6 to 6.5 KVDC Power Consumption : Not more than 50W per cell. |  | - |  |  | -
| The Scrubber Machines (EAC) shall be of following duty parameters : |  | - |  |  | -
| M/c No Capacity (CFM) |  | - |  |  | -
| AS-1 2000 |  | 1 | No | 1,95,000 | 1,95,000 | 0.7 | 136500
1.1.3 | Supply, Installation, Testing & Commissioning of direct driven TUBE/VANE AXIAL FLOW FAN. Vane Axial flow fan for Normal Fresh air supply. Fan motor shall be suitable for 415 ± 10% volts, 50 cycles, 3 phase power supply with high efficiency, IE-3 type for normal application and fan total efficiency should not be less than 65%. The fan shall be equipped with mounting bracket & spring isolators for the installation of the fans. Fan static pressure shall be as indicated but actual duting & fan static pressure to be checked by vendor. Fan shall be with fire proof flexible connection at inlet and outlet. Noise level for normal application fans shall be less than 70 dbA @1 meter distance. If required, shall be included to meet the desired sound levels. All Fans shall be with back draft damper and cost will be included in the cost. |  | - |  |  | -
| Description CFM ESP (mm.of wg) |  | - |  |  | -
| Kitchen Fresh Air 1500 60 |  | 1 | No | 1,65,000 | 1,65,000 | 0.7 | 115500
1.2 | AIR CURTAIN |  | - |  |  | -
| Supply, installation, testing and commissioning of Air Curtain as shown in drawings.Unit consist of Blowers,motors & nozzles .It has velocity control switch & door sensors. Material of the Body is MS Powder Coated and having dB level in between 60-70. |  | - |  |  | -
a | SIZE-900x230x212 410W Cigar Room |  | - | No | 4000 | -
| TOTAL FOR VENTILATION FANS AND ARRANGEMENT |  |  |  |  | 4,90,000 |  | 343000
A |  |  |  | ₹ |  | 16,38,700 |  | 1147090
B |  |  |  | ₹ |  | 2,94,966
C |  |  |  | ₹ |  | 19,33,666
Note on J52: Urmila Jadhav: Please check (Qty missing in JMR)

## JMR HVAC RA Bill 10
Impulse Branding Solutions
PROJECT:- |  | Lucknow Airport T-3 , CIP LOUNGE Site
MEASUREMENT FOR RECTANGULAR DUCTING CFM-6500
Sr. Nos | Type's | Width | Height | Width | Height | Perimeter | Length | Qty | Area (Sq. Mtr.) | 22G | 24G | Insulation | Accoustic
1 | Canvas | 700 | 500 | 700 | 500 | 2400 | 150 | 1
2 | offset | 700 | 500 | 700 | 500 | 2400 | 700 | 1 | 1.68 | 1.68 |  | 1.75
3 | Taper | 700 | 500 | 750 | 450 | 2400 | 350 | 1 | 0.84 | 0.84 |  | 0.875
4 | Elbow | 750 | 450 | 750 | 450 | 2400 | 1800 | 2 | 8.64 | 8.64 |  | 9
5 | offset | 750 | 450 | 750 | 450 | 2400 | 1600 | 1 | 3.84 | 3.84 |  | 4
6 | Strate | 750 | 450 | 750 | 450 | 2400 | 1200 | 2 | 5.76 | 5.76 |  | 6
7 | Strate | 750 | 450 | 750 | 450 | 2400 | 1200 | 3 | 8.64 | 8.64 |  | 9
8 | Elbow | 750 | 450 | 750 | 450 | 2400 | 1800 | 2 | 8.64 | 8.64 |  | 9
9 | y pcs | 750 | 450 | 600 | 450 | 2250 | 500 | 2 | 2.25 | 2.25 |  | 2.35
9.1 | y pcs | 250 | 450 | 250 | 450 | 1400 | 500 | 1 | 0.7 |  | 0.7 | 0.75
10 | Taper | 250 | 450 | 350 | 300 | 1350 | 500 | 1 | 0.675 |  | 0.675 | 0.725
11 | Strate | 350 | 300 | 350 | 300 | 1300 | 1200 | 2 | 3.12 |  | 3.12 | 3.36
12 | y pcs | 350 | 300 | 200 | 300 | 1150 | 400 | 1 | 0.46 |  | 0.46 | 0.5
12.1 | y pcs | 200 | 300 | 200 | 300 | 1000 | 600 | 4 | 2.4 |  | 2.4 | 2.64
13 | Taper | 200 | 300 | 250 | 150 | 900 | 400 | 1 | 0.36 |  | 0.36 | 0.4
14 | Strate | 250 | 150 | 250 | 150 | 800 | 2000 | 1 | 1.6 |  | 1.6 | 1.8
15 | End | 350 | 250 |  |  |  |  | 1 | 0.0875 |  | 0.0875 | 0.0875
16 | Taper | 200 | 300 | 250 | 250 | 1000 | 600 | 1 | 0.6 |  | 0.6 | 0.66
17 | Elbow | 250 | 250 | 250 | 250 | 1000 | 1250 | 1 | 1.25 |  | 1.25 | 1.375
18 | offset | 250 | 250 | 250 | 250 | 1000 | 1000 | 1 | 1 |  | 1 | 1.1
19 | Strate | 250 | 250 | 250 | 250 | 1000 | 1800 | 1 | 1.8 |  | 1.8 | 1.98
20 | Taper | 250 | 250 | 200 | 200 | 900 | 600 | 1 | 0.54 |  | 0.54 | 0.6
21 | Strate | 200 | 200 | 200 | 200 | 800 | 1250 | 1 | 1 |  | 1 | 1.125
22 | End | 300 | 300 |  |  |  |  | 1 | 0.09 |  | 0.09 | 0.09
23 | Taper | 600 | 450 | 750 | 450 | 2250 | 600 | 1 | 1.35 | 1.35 | 1.35 | 1.41
24 | Taper | 750 | 450 | 700 | 280 | 2180 | 600 | 1 | 1.308 | 1.308 | 1.308 | 1.368
25 | Strate | 700 | 280 | 700 | 280 | 1960 | 2300 | 2 | 9.016 | 9.016 | 9.016 | 9.476
26 | Taper | 700 | 400 | 700 | 280 | 2080 | 1000 | 1 | 2.08 | 2.08 | 2.08 | 2.18
27 | Strate | 700 | 400 | 700 | 400 | 2200 | 1000 | 1 | 2.2 | 2.2 | 2.2 | 2.3
28 | Strate | 700 | 400 | 700 | 400 | 2200 | 2450 | 2 | 10.78 | 10.78 | 10.78 | 11.27
29 | Taper | 700 | 400 | 550 | 350 | 2000 | 950 | 1 | 1.9 | 1.9 | 1.9 | 1.995
30 | Elbow | 550 | 350 | 550 | 350 | 1800 | 1450 | 2 | 5.22 | 5.22 | 5.22 | 5.51
31 | Strate | 550 | 350 | 550 | 350 | 1800 | 1050 | 1 | 1.89 |  | 1.89 | 1.995
32 | Strate | 550 | 350 | 550 | 350 | 1800 | 2450 | 2 | 8.82 |  | 8.82 | 9.31
33 | Taper | 550 | 350 | 550 | 300 | 1750 | 600 | 1 | 1.05 |  | 1.05 | 1.11
34 | Strate | 550 | 300 | 550 | 300 | 1700 | 2450 | 2 | 8.33 |  | 8.33 | 8.82
35 | Taper | 550 | 300 | 350 | 300 | 1500 | 600 | 1 | 0.9 |  | 0.9 | 0.96
36 | Taper | 350 | 300 | 400 | 250 | 1300 | 500 | 1 | 0.65 |  | 0.65 | 0.7
37 | y pcs | 400 | 250 | 250 | 250 | 1100 | 1100 | 2 | 2.42 |  | 2.42 | 2.64
37.1 | y pcs | 200 | 250 | 200 | 250 | 900 | 800 | 1 | 0.72 |  | 0.72 | 0.8
38 | Strate | 250 | 200 | 250 | 200 | 900 | 600 | 1 | 0.54 |  | 0.54 | 0.6
39 | Strate | 250 | 200 | 250 | 200 | 900 | 2450 | 2 | 4.41 |  | 4.41 | 4.9
40 | End | 300 | 350 |  |  |  |  | 1 | 0.105 |  | 0.105 | 0.105
41 | Strate | 200 | 250 | 200 | 250 | 900 | 2050 | 1 | 1.845 |  | 1.845 | 2.05
42 | End | 300 | 350 |  |  | 650 |  | 1 | 0.105 |  | 0.105 | 0.105
43 | Show Collar | 350 | 200 | 450 | 200 | 1200 | 300 | 1 | 0.36 |  | 0.36 | 0.39
44 | Strate | 350 | 200 | 350 | 200 | 1100 | 900 | 1 | 0.99 |  | 0.99 | 1.08
45 | Bend | 350 | 200 | 350 | 200 | 1100 | 900 | 3 | 2.97 |  | 2.97 | 3.24
46 | Strate | 350 | 200 | 350 | 200 | 1100 | 950 | 1 | 1.045 |  | 1.045 | 1.14
47 | Strate | 350 | 200 | 350 | 200 | 1100 | 1250 | 2 | 2.75 |  | 2.75 | 3
48 | Strate | 350 | 200 | 350 | 200 | 1100 | 800 | 1 | 0.88 |  | 0.88 | 0.96
49 | End | 450 | 300 |  |  |  |  | 1 | 0.135 |  | 0.135 | 0.135
50 | Show Collar | 250 | 150 | 350 | 150 | 900 | 250 | 3 | 0.675 |  | 0.675 | 0.75
51 | Strate | 250 | 150 | 250 | 150 | 750 | 900 | 4 | 2.7 |  | 2.7 | 3.06
52 | End | 350 | 250 |  |  |  |  | 4 | 0.35 |  | 0.35 | 0.35
53 | Show Collar | 250 | 150 | 350 | 150 | 900 | 250 | 2 | 0.45 |  | 0.45 | 0.5
54 | Strate | 250 | 150 | 250 | 150 | 800 | 650 | 1 | 0.52 |  | 0.52 | 0.585
55 | Strate | 250 | 150 | 250 | 150 | 800 | 850 | 1 | 0.68 |  | 0.68 | 0.765
56 | End | 350 | 250 |  |  |  |  | 2 | 0.175 |  | 0.175 | 0.175
57 | Show Collar | 350 | 200 | 450 | 200 | 1200 | 260 | 1 | 0.312 |  | 0.312 | 0.338
58 | Strate | 350 | 200 | 350 | 200 | 1100 | 300 | 1 | 0.33 |  | 0.33 | 0.36
59 | Bend | 350 | 200 | 350 | 200 | 1100 | 750 | 2 | 1.65 |  | 1.65 | 1.8
60 | Strate | 350 | 200 | 350 | 200 | 1100 | 1000 | 1 | 1.1 |  | 1.1 | 1.2
61 | Strate | 350 | 200 | 350 | 200 | 1100 | 1250 | 3 | 4.125 |  | 4.125 | 4.5
62 | Bend | 350 | 200 | 350 | 200 | 1100 | 650 | 1 | 0.715 |  | 0.715 | 0.78
63 | Strate | 350 | 200 | 350 | 200 | 1100 | 850 | 1 | 0.935 |  | 0.935 | 1.02
64 | End | 450 | 300 |  |  |  |  | 1 | 0.135 |  | 0.135 | 0.135
65 | Show Collar | 350 | 150 | 250 | 150 | 900 | 270 | 2 | 0.486 |  | 0.486 | 0.54
66 | Strate | 250 | 200 | 250 | 200 | 900 | 800 | 1 | 0.72 |  | 0.72 | 0.8
67 | Strate | 250 | 200 | 250 | 200 | 900 | 600 | 1 | 0.54 |  | 0.54 | 0.6
68 | End | 350 | 200 |  |  |  |  | 2 | 0.14 |  | 0.14 | 0.14
69 | Show Collar | 400 | 200 | 500 | 200 | 1300 | 270 | 1 | 0.351 |  | 0.351 | 0.378
70 | Strate | 400 | 200 | 400 | 200 | 1200 | 1700 | 1 | 2.04 |  | 2.04 | 2.21
71 | Bend | 400 | 200 | 400 | 200 | 1200 | 650 | 2 | 1.56 |  | 1.56 | 1.69
72 | End | 500 | 300 |  |  |  |  | 1 | 0.15 |  | 0.15 | 0.15
73 | Strate | 400 | 200 | 400 | 200 | 1100 | 700 | 1 | 0.77 |  | 0.77 | 0.84
74 | Show Collar | 250 | 150 | 350 | 150 | 900 | 270 | 2 | 0.486 |  | 0.486 | 0.54
75 | Strate | 250 | 150 | 250 | 150 | 800 | 1100 | 2 | 1.76 |  | 1.76 | 1.98
76 | End | 350 | 250 |  |  |  |  | 2 | 0.175 |  | 0.175 | 0.175
77 | Strate | 400 | 250 | 400 | 250 | 1300 | 1200 | 1 | 1.56 |  | 1.56 | 1.68
78 | Collar | 400 | 250 | 400 | 250 | 1300 | 200 | 1 | 0.26 |  | 0.26 | 0.28
79 | Elbow | 400 | 250 | 400 | 250 | 1300 | 1250 | 1 | 1.625 |  | 1.625 | 1.75
80 | Strate | 400 | 250 | 400 | 250 | 1300 | 2450 | 1 | 3.185 |  | 3.185 | 3.43
81 | End | 500 | 350 |  |  |  |  | 1 | 0.175 |  | 0.175 | 0.175
82 | Strate | 250 | 200 | 250 | 200 | 900 | 1650 | 1 | 1.485 |  | 1.485 | 1.65
83 | End | 350 | 300 |  |  |  |  | 1 | 0.105 |  | 0.105 | 0.105
84 | Strate | 300 | 100 | 300 | 100 | 800 | 1250 | 4 | 4 |  | 4 | 4.5
85 | End | 400 | 200 |  |  |  |  | 1 | 0.08 |  | 0.08 | 0.08
86 | Offset | 350 | 350 | 350 | 350 | 1400 | 520 | 1 | 0.728 |  | 0.728 | 0.78
87 | Strate | 350 | 350 | 350 | 350 | 1400 | 700 | 1 | 0.98 |  | 0.98 | 1.05
88 | Elbow | 350 | 350 | 350 | 350 | 1400 | 1170 | 1 | 1.638 |  | 1.638 | 1.755
89 | Strate | 350 | 350 | 350 | 350 | 1400 | 2450 | 2 | 6.86 |  | 6.86 | 7.35
90 | Strate | 350 | 350 | 350 | 350 | 1300 | 1050 | 1 | 1.365 |  | 1.365 | 1.47
91 | End | 450 | 450 |  |  |  |  | 1 | 0.2025 |  | 0.2025 | 0.2025
BRANCH DROPER
92 | Offset | 300 | 150 | 300 | 150 | 900 | 1700 | 4 | 6.12 |  | 6.12 | 6.8
93 | Offset | 300 | 150 | 300 | 150 | 900 | 1700 | 2 | 3.06 |  | 3.06 | 3.4
94 | Offset | 300 | 100 | 300 | 100 | 800 | 1350 | 4 | 4.32 |  | 4.32 | 4.86
95 | Offset | 300 | 100 | 300 | 100 | 800 | 1600 | 1 | 1.28 |  | 1.28 | 1.44
96 | Strate Droper | 300 | 100 | 300 | 100 | 800 | 1100 | 4 | 3.52 |  | 3.52 | 3.96
97 | Offset | 300 | 100 | 300 | 100 | 800 | 1400 | 1 | 1.12 |  | 1.12 | 1.26
98 | Strate Droper | 300 | 100 | 300 | 100 | 800 | 1000 | 1 | 0.8 |  | 0.8 | 0.9
99 | Offset | 300 | 100 | 300 | 100 | 800 | 1100 | 1 | 0.88 |  | 0.88 | 0.99
100 | Strate Droper | 300 | 100 | 300 | 100 | 800 | 600 | 1 | 0.48 |  | 0.48 | 0.54
101 | End | 400 | 200 |  |  |  |  | 3 | 0.24 |  | 0.24 | 0.24
102 | Strate Droper | 300 | 100 | 300 | 100 | 800 | 700 | 3 | 1.68 |  | 1.68 | 1.89
103 | Strate Droper | 300 | 100 | 300 | 100 | 800 | 900 | 5 | 3.6 |  | 3.6 | 4.05
104 | End | 400 | 200 |  |  |  |  | 15 | 1.2 |  | 1.2 | 1.2
105 | Plenem | 300 | 100 | 300 | 100 | 800 | 800 | 20 | 12.8 |  | 12.8 | 14.4
106 | Strate Droper | 300 | 100 | 300 | 100 | 800 | 1450 | 2 | 2.32 |  | 2.32 | 2.61
107 | Strate Droper | 300 | 100 | 300 | 100 | 800 | 1200 | 4 | 3.84 |  | 3.84 | 4.32
108 | Ring | 150 dia |  |  |  | 0.471 | 150 | 46 | 3.2499 |  | 3.2499 | 3.9399
109 | Flaxibal Pipe | 151 dia |  |  |  | 0.471 | 2000 | 30 | 28.26 |  | 28.26 | 34.26
110 | Strate | 550 | 350 | 550 | 350 | 1700 | 650 | 1 | 1.105 |  | 1.105 | 1.17
111 | Strate | 700 | 400 | 700 | 400 | 2200 | 600 | 3 | 3.96 |  | 3.96 | 4.14
112 | Taper | 400 | 150 | 400 | 250 | 1200 | 600 | 1 | 0.72 |  | 0.72 | 0.78
113 | Bend | 400 | 250 | 400 | 250 | 1300 | 600 | 1 | 0.78 |  | 0.78 | 0.84
114 | Strate | 400 | 250 | 400 | 250 | 1300 | 600 | 1 | 0.78 |  | 0.78 | 0.84
115 | Strate | 300 | 350 | 300 | 350 | 1300 | 800 | 1 | 1.04 |  | 1.04 | 1.12
116 | Strate | 550 | 300 | 550 | 300 | 1700 | 1300 | 2 | 4.42 |  | 4.42 | 4.68
117 | Strate | 250 | 150 | 250 | 150 | 800 | 1200 | 1 | 0.96 |  | 0.96 | 1.08
118 | Show Collar | 250 | 150 | 350 | 150 | 900 | 270 | 1 | 0.243 |  | 0.243 | 0.27
119 | End | 350 | 250 |  |  |  |  | 1 | 0.0875 |  | 0.0875 | 0.0875
120 | Bend | 250 | 150 | 250 | 150 | 800 | 500 | 1 | 0.4 |  | 0.4 | 0.45
EXHAUST TOILET
121 | End | 400 | 300 |  |  |  |  | 2 | 0.24 |  | 0.24 | 0.24
122 | Strate | 300 | 200 | 300 | 200 | 1000 | 2450 | 2 | 4.9 |  | 4.9 | 5.39
123 | Strate | 300 | 200 | 300 | 200 | 1000 | 1100 | 1 | 1.1 |  | 1.1 | 1.21
124 | Elbow | 350 | 250 | 350 | 250 | 1200 | 1000 | 1 | 1.2 |  | 1.2 | 1.3
125 | Show Collar | 450 | 250 | 350 | 250 | 1300 | 300 | 1 | 0.39 |  | 0.39 | 0.42
126 | Show Collar | 150 | 100 | 250 | 100 | 600 | 250 | 4 | 0.6 |  | 0.6 | 0.7
127 | Strate | 150 | 100 | 150 | 100 | 500 | 2300 | 2 | 2.3 |  | 2.3 | 2.76
128 | Strate | 150 | 100 | 150 | 100 | 500 | 2450 | 2 | 2.45 |  | 2.45 | 2.94
129 | End | 250 | 200 |  |  |  |  | 4 | 0.2 |  | 0.2 | 0.2
130 | Strate | 100 | 100 | 100 | 100 | 400 | 2300 | 1 | 0.92 |  | 0.92 | 1.15
131 | Strate | 100 | 100 | 100 | 100 | 400 | 1750 | 1 | 0.7 |  | 0.7 | 0.875
132 | Elbow | 100 | 100 | 100 | 100 | 400 | 1100 | 2 | 0.88 |  | 0.88 | 1.1
133 | Show Collar | 200 | 100 | 100 | 100 | 500 | 280 | 2 | 0.28 |  | 0.28 | 0.336
134 | End | 200 | 200 |  |  |  |  | 2 | 0.08 |  | 0.08 | 0.08
135 | Down Throw Elbow | 100 | 100 | 100 | 100 | 400 | 2500 | 2 | 2 |  | 2 | 2.5
136 | Down Throw Elbow | 100 | 100 | 100 | 100 | 400 | 2000 | 1 | 0.8 |  | 0.8 | 1
137 | Down Throw Elbow | 100 | 100 | 100 | 100 | 400 | 2250 | 2 | 1.8 |  | 1.8 | 2.25
138 | Down Throw Elbow | 100 | 100 | 100 | 100 | 400 | 2000 | 2 | 1.6 |  | 1.6 | 2
139 | Down Throw Elbow | 100 | 100 | 100 | 100 | 400 | 2450 | 2 | 1.96 |  | 1.96 | 2.45
140 | Strate | 300 | 200 | 300 | 200 | 1000 | 2000 | 1 | 2 |  | 2 | 2.2
141 | Elbow | 300 | 200 | 300 | 200 | 1000 | 1500 | 1 | 1.5 |  | 1.5 | 1.65
FRESH AIR DUCT HOOD
142 | Taper | 600 | 400 | 500 | 350 | 1850 | 600 | 1 | 1.11 |  | 1.11 | 1.17
143 | Elbow | 500 | 350 | 500 | 350 | 1700 | 1800 | 1 | 3.06 |  | 3.06 | 3.24
144 | Taper | 250 | 200 | 500 | 350 | 1300 | 400 | 1 | 0.52 |  | 0.52 | 0.56
145 | Offset | 250 | 200 | 250 | 200 | 900 | 600 | 1 | 0.54 |  | 0.54 | 0.6
146 | Strate | 250 | 200 | 250 | 200 | 900 | 1250 | 1 | 1.125 |  | 1.125 | 1.25
147 | Elbow | 250 | 200 | 250 | 200 | 900 | 950 | 2 | 1.71 |  | 1.71 | 1.9
148 | Strate | 250 | 200 | 250 | 200 | 900 | 2000 | 2 | 3.6 |  | 3.6 | 4
149 | Strate | 250 | 200 | 250 | 200 | 900 | 2150 | 1 | 1.935 |  | 1.935 | 2.15
150 | End | 350 | 300 |  |  |  |  | 1 | 0.105 |  | 0.105 | 0.105
151 | Elbow | 400 | 250 | 400 | 250 | 1300 | 900 | 1 | 1.17 |  | 1.17 | 1.26
152 | Strate | 400 | 250 | 400 | 250 | 1300 | 1650 | 1 | 2.145 |  | 2.145 | 2.31
153 | Strate | 250 | 200 | 250 | 200 | 900 | 1200 | 1 | 1.08 |  | 1.08 | 1.2
154 | Strate | 400 | 250 | 400 | 250 | 1300 | 1650 | 1 | 2.145 |  | 2.145 | 2.31
155 | End | 500 | 350 |  |  |  |  | 1 | 0.175 |  | 0.175 | 0.175
156 | Offset Dropper | 250 | 250 | 250 | 250 | 1000 | 1500 | 1 | 1.5 |  | 1.5 | 1.65
157 | Collar | 300 | 150 | 300 | 150 | 900 | 300 | 4 | 1.08 |  | 1.08 | 1.2
158 | Collar | 150 | 150 | 150 | 150 | 600 | 200 | 2 | 0.24 |  | 0.24 | 0.28
159 | Strate Offset | 150 | 150 | 150 | 150 | 600 | 1200 | 2 | 1.44 |  | 1.44 | 1.68
160 | Strate | 300 | 150 | 300 | 150 | 900 | 1250 | 1 | 1.125 |  | 1.125 | 1.25
HOOD EXHAUST
161 | Elbow | 500 | 350 | 500 | 350 | 1700 | 1400 | 1 | 2.38 |  | 2.38 | 2.52
162 | Taper | 500 | 350 | 450 | 200 | 1500 | 550 | 1 | 0.825 |  | 0.825 | 0.88
163 | Elbow | 450 | 200 | 450 | 200 | 1300 | 1500 | 1 | 1.95 |  | 1.95 | 2.1
164 | Elbow | 450 | 200 | 450 | 200 | 1300 | 1250 | 1 | 1.625 |  | 1.625 | 1.75
165 | Y pcs | 450 | 200 | 250 | 200 | 1100 | 600 | 1 | 0.66 |  | 0.66 | 0.72
165.1 | Y pcs | 250 | 200 | 250 | 200 | 900 | 600 | 1 | 0.54 |  | 0.54 | 0.6
167 | Strate | 250 | 200 | 250 | 200 | 900 | 1200 | 2 | 2.16 |  | 2.16 | 2.4
168 | Elbow | 250 | 200 | 250 | 200 | 900 | 950 | 1 | 0.855 |  | 0.855 | 0.95
169 | End | 350 | 300 |  |  |  |  | 1 | 0.105 |  | 0.105 | 0.105
170 | Strate | 250 | 200 | 250 | 200 | 900 | 1200 | 2 | 2.16 |  | 2.16 | 2.4
171 | Elbow | 250 | 200 | 250 | 200 | 900 | 950 | 2 | 1.71 |  | 1.71 | 1.9
172 | Strate | 250 | 200 | 250 | 200 | 900 | 1400 | 1 | 1.26 |  | 1.26 | 1.4
173 | Strate | 250 | 200 | 250 | 200 | 900 | 2450 | 2 | 4.41 |  | 4.41 | 4.9
174 | End | 350 | 300 |  |  |  |  | 1 | 0.105 |  | 0.105 | 0.105
175 | Collar | 300 | 300 | 300 | 300 | 1200 | 300 | 5 | 1.8 |  | 1.8 | 1.95
176 | Collar | 150 | 150 | 150 | 150 | 600 | 300 | 1 | 0.18 |  | 0.18 | 0.21
177 | Offset | 150 | 150 | 150 | 150 | 600 | 1500 | 1 | 0.9 |  | 0.9 | 1.05
178 | Taper | 150 | 150 | 300 | 300 | 900 | 600 | 1 | 0.54 |  | 0.54 | 0.6
179 | Offset | 300 | 300 | 300 | 300 | 1200 | 1250 | 2 | 3 |  | 3 | 3.25
180 | Strate | 300 | 300 | 300 | 300 | 1200 | 900 | 1 | 1.08 |  | 1.08 | 1.17
181 | Strate | 300 | 300 | 300 | 300 | 1200 | 1200 | 1 | 1.44 |  | 1.44 | 1.56
182 | End | 400 | 400 |  |  |  |  | 1 | 0.16 |  | 0.16 | 0.16
183 | End | 400 | 200 |  |  |  |  | 1 | 0.08 |  | 0.08 | 0.08
184 | Ring | 150 dia |  |  |  | 0.471 | 150 | 2 | 0.1413 |  | 0.1413 | 0.1713
185 | Flaxibal | 150dia |  |  |  | 0.471 | 2000 | 1 | 0.942 |  | 0.942 | 1.142
186 | Collar | 250 | 250 | 250 | 250 | 1000 | 300 | 1 | 0.3 |  | 0.3 | 0.33
187 | Dropper | 250 | 250 | 250 | 250 | 1000 | 1200 | 1 | 1.2 |  | 1.2 | 1.32
[7 empty] | TOTAL Qty. |  |  | 74.144 | 318.2087 | 394.6167
[7 empty] | RA Bill 08 QTY |  |  | 70 | 259 | 189
[7 empty] | RA Bill 10 QTY |  |  | 4.144 | 59.2087 | 205.6167
JANITOR DOOR |  | 100 | 200 |  |  |  |  | 2 | 0.04
1
SUPPLY GRILL
1 | Grill | 300 | 150 |  |  |  |  | 10 | 0.45
2 | Grill | 300 | 100 |  |  |  |  | 9 | 0.27
3 | Grill | 500 | 100 |  |  |  |  | 8 | 0.4
4 | Grill | 100 | 100 |  |  |  |  | 12 | 0.12
5 | Grill | 500 | 150 |  |  |  |  | 1 | 0.075
[6 empty] | Total Qty. |  |  | 1.315
[6 empty] | RA Bill 08 QTY |  |  | 1.75
[6 empty] | RA Bill 10 QTY |  |  | -0.435
COLLAR DAMPER
1 |  | 300 | 150 |  |  |  |  | 10
2 |  | 300 | 100 |  |  |  |  | 7
3 |  | 500 | 100 |  |  |  |  | 1
4 |  | 100 | 100 |  |  |  |  | 10
5 |  | 500 | 150 |  |  |  |  | 1
[6 empty] | Total Qty. |  | 29
RETURN AIR GRILL
1 |  | 100 | 3200 |  |  |  |  | 1 | 0.32
2 |  | 100 | 11549 |  |  |  |  | 1 | 1.1549
3 |  | 100 | 3098 |  |  |  |  | 1 | 0.3098
4 |  | 100 | 8164 |  |  |  |  | 1 | 0.8164
5 |  | 100 | 8907 |  |  |  |  | 1 | 0.8907
6 |  | 100 | 100 |  |  |  |  | 1 | 0.01
[6 empty] | Total Qty. |  |  | 3.5018
[6 empty] | RA Bill 08 QTY |  |  | 2.45
[6 empty] | RA Bill 10 QTY |  |  | 1.0518
DIFFUSER
1 | Supply Diffuser | 600 | 600 |  |  |  |  | 3 | 1.08
2 | Coller Damper | 375 | 375 |  |  |  |  | 3 | 0.42188
[6 empty] | Total Qty. |  |  | 1.5019
3 | Return Diffuser | 600 | 600 |  |  |  |  | 3 | 1.08
4 | Coller Damper | 375 | 375 |  |  |  |  | 3 | 0.42188
[6 empty] | Total Qty. |  |  | 1.5019
VCD
1 |  | 750 | 450 | 150 |  | 2.4 |  | 1 | 0.36
2 |  | 350 | 300 | 150 |  | 1.3 |  | 1 | 0.195
3 |  | 400 | 250 | 150 |  | 1.3 |  | 1 | 0.195
4 |  | 350 | 300 | 150 |  | 1.3 |  | 2 | 0.39
5 |  | 700 | 400 | 150 |  | 2.2 |  | 2 | 0.66
6 |  | 250 | 150 | 150 |  | 0.8 |  | 2 | 0.24
7 |  | 250 | 250 | 150 |  | 1 |  | 1 | 0.15
8 |  | 400 | 200 | 150 |  | 1.2 |  | 1 | 0.18
9 |  | 550 | 350 | 150 |  | 1.8 |  | 3 | 0.81
10 |  | 200 | 250 | 150 |  | 0.9 |  | 2 | 0.27
[6 empty] | Total Qty. |  |  | 3.45
[6 empty] | RA Bill 08 QTY |  |  | 2.45
[6 empty] | RA Bill 10 QTY |  |  | 1

## JMR HVAC RA Bill 8
Price Comparative Statement
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for Toilet & Pantry Work at CIP Lounge at Terminal-03, CCSI Airport, Lucknow
HVAC ABSTRACT SHEET - RA - 08
Sr No | Particulars | Sort Text | Units | WO Qty. | WO RS | WO Amount | Site Qty
[5 empty] | INR | INR
| HVAC |  |  |  |  | -
A | DUCTWORK AND AIR DISTRIBUTION |  |  |  |  | -
1 | Supply, installation and testing of SITE Fabricated GI sheet metal ducts as per IS- 655 Standard in accordance with the approved shop drawings as required by the specifications. Quoted price shall be inclusive of all necessary supports by MS structural steel if required, hangers, clamp supports from walls, floors and ceiling including cutting holes and chases in brick, R.C.C. work, making good the same to original condition complete in all respects with painting with one coat of primer and two coats of paint to supports of MS work Note:All exposed surfaces & duct shall be painted in black mat finish by the HVAC contractor. |  |  |  |  | -
a | 24 gauge galvanised sheet steel (0.63 mm) |  | Sqm. | 370 | 1350 | 499500 | 259
b | 22 gauge galvanised sheet steel (0.8 mm) |  | Sqm. | 100 | 1650 | 165000 | 70
2 | Supply, fabrication, installation, testing and comissioning of Flexible Canvas constructed of fire resistant double resin sleeve as per the approved shop drawings. |  | RMT | 8 | 500 | 4000 | 5.6
3 | Supply, Installation,Testing and Balancing of flexible ducting comprising of inner as well as outer skin constructed out of aluminium & fibre glass insulation 25mm thick of minimum 24 kg/cu.m density insulation sandwitched in between. Duct should confirm to fire rating standards BS-476 part 5, 6 & 7. Flexible Ducts of following sizes as per approved shop drawings, specifications : |  |  | -
a | 300 mm dia. |  | Mtr. | - | 2350
b | 200 mm dia. |  | Mtr. | - | 1850
c | 150 mm dia. |  | Mtr. | - | 1450
d | 100 mm dia. |  | Mtr. | - | 1200
4 | Supply, installation and testing of GI construction Opposed blade Volume control dampers within ducts to be provided with suitable ducts lever and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system. |  | Sqm. | 3.5 | 3500 | 12250 | 2.45
5 | Supply, installation, testing and commissioning of Fire damper from approved shop drawings and as per specifications. |  |  | -
a | Fire Dampers (Fusible link) |  | Sqm. | 1.5 | 8600 | 12900 | 1.05
6 | Supply, installation, testing and balancing of powder coated Extruded Aluminium Supply Air Grilles with volume control dampers in accordance with the approved shop drawings and specifications. |  | Sqm. | 2.5 | 8600 | 21500 | 1.75
7 | Supply, installation, testing and balancing of powder coated extruded Aluminium Exhaust/Return Air Grilles without volume control dampers with adjustable double louvers. |  | Sqm. | 3.5 | 6500 | 22750 | 2.45
8 | Supply, installation, testing and balancing of Powder coated extruded aluminium construction square / round shape Return / Exhaust Air Diffusers with removable core & anti smudge ring & as per approved drawings and specifications. |  | Sqm. | 1.5 | 6500 | 9750 | 1.05
9 | Supply, installation, testing and balancing of Powder coated extruded aluminium construction square / round shape Supply Air Diffusers with removable core & anti smudge ring & volume control dampers as per approved drawings and specifications. |  | Sqm. | 1.3 | 6500 | 8450 | 0.91
10 | Supply, installation, testing and balancing of Powder coated/Anodised extruded aluminium construction. Louvers with bird screen for exhaust air as per specifications and approved drawings. |  | Sqm. | - | 6500
11 | Supply, installation, testing and balancing of Powder coated/Anodised extruded aluminium construction Inlet air louvers with bird screen and volume damper for outside air as per specifications and approved shop drawings. |  | Sqm. | - | 6500
12 | Supply, Installation and Testing of single piece GI round spigot made out of spinning process with 50mm height and having grooves on both sides and circular flanges. Spigots shall be installed on main ducts to facilitate connection of flexible ducts. |  |  | -
a | 300 mm dia. |  | Mtr. | - | 2100
b | 200 mm dia. |  | Mtr. | - | 1800
c | 150 mm dia. |  | Mtr. | - | 1500
d | 100 mm dia. |  | Mtr. | - | 1200
13 | Supply, Installation and Testing of Butterfly damper of aluminium sheet construction with two flap with sleeve as per thespecifications and shop drawings. |  |  | -
a | 300 mm dia. |  | Mtr. | - | 2500
b | 200 mm dia. |  | Mtr. | - | 2100
c | 150 mm dia. |  | Mtr. | - | 1650
d | 100 mm dia. |  | Mtr. | - | 1200
14 | Air Transfer Grilles |  |  | -
| Supply, Installation and testing of extruded aluminium powder coated air transfer grilles to be provided at the door of toilets/pantry. |  | Sqm | 1 | 7600 | 7600 | 0.7
15 | THERMAL INSULATION |  |  | -
15.1 | THERMAL INSULATION FOR DUCTWORK |  |  | -
| Supply and Application of external thermal insulation of supply /return air ducting using closed cell elastomeric nitrile rubber insulation with class 'O' fire retardant properties as per the specifications and drawings. Quoted price shall be inclusive of adhesive, tapes as per specification. insulation shall be provided with aluminium foil, factory laminated. |  |  | -
| Insulation thickness/application will be as per approved shop drawing notes. |  |  | -
a. | 25 mm thick |  | Sqm | - | 1500
b. | 19 mm thick (Fresh air Duct in Non AC Area) |  | Sqm | - | 1300
c. | 16 mm thick (S/Air duct in Non AC Area) |  | Sqm | - | 1200
d. | 13 mm thick (R/Air duct in non AC Area) |  | Sqm | 50 | 950 | 47500 | 35
e. | 9 mm thick (S/Air duct in R/Air Contact) |  | Sqm | 270 | 1250 | 337500 | 189
15.2 | ACOUSTIC LINING OF DUCTS |  |  | -
| Supply and Application of internal acoustic lining of supply air ducting using open cell nitrile rubber insulation with density within 140-180 Kg/m3 as per the approved shop drawings and specifications. Insulation material shall be bonded with the ducts using metal screw and washers to facilitate grip to the GI sheet. |  |  | -
a. | 10mm thick lining |  | Sqm | - | 1350
b. | 25mm thick lining |  | Sqm | - | 1650
B | VENTILATION FANS AND ARRANGEMENT
1 | VENTILATION FANS
1.1 | INLINE FANS WITHOUT FILTER
Supply, installation, testing and commissioning of duct mounted IN-LINE FANS for exhaust air as shown in drawings. Each fan shall be complete with motor, mounting flanges, accessories like bird screen, fixed louvers and GI sheet canopy for weather protection as required. Quoted price shall be inclusive of electronic speed regulator and wiring between fan & speed regulator for single phase fans. Incase of 3 phase fans quoted price shall be inclusive of DOL starter panel with cabling between starter panel and fan. Fans shall have low noise level in rage of 35-40dBA @3m and shall be suitable for indoor installations.
Quoted prices shall be inclusive of all necessary supports by MS structural steel if required, hangers, clamp supports from walls, floors and ceiling with painting with one coat of primer and two coats of paint to supports of MS work. In addition, 18G GI sheet canopy work and vibration isolator pads to make installation vibration free for fans to be installed on terrace. Note : Static Pressure for all fans need to checked by the contractor after the installation of ducting.
Fan Selection arrangement shall be as follows:
Fan Capacity S.P Area to
No. (Cfm) (mmWG) to be exhausted
a. | IF-1 500 14-15 Electrical Room
b. | IF-1 500 14-15 Toilet |  | No | 1 | 65000 | 65000 | 0.7
1.2.1 | Supply, Installation, Testing and Commissioning of Dry Type Scrubber each comprising of extract air intake section, electrostatic precipitation technology, dry type air cleaner to remove oil, smoke and fumes from exhaust air, as per the Specifications. |  | No | 1 | 65000 | 65000 | 0.7
| Electrostatic section shall be made of 16/18 gauge galvanised sheet, high baked epoxy powder coated, washable type aluminium mesh filters, stainless steel spiked ionizers to create high voltage DC field, aluminum collector plates which should be alternatively charged positive and negative with large collecting area with 14" deep cell, to work as magnet for charged smoke and oil particles. Average efficiency of 90- 95% in single pass as per ASHRAE test method. Electrostatic Precipitator should be able to charge particles from 0.01 micron to 10 microns through solid state power supply. Collector cell should be of permanent type and incorporate slide out facility for easy removal for cleaning. Power supplies shall be 100% solid state UL Listed, Module of capacity above 3000 CFM shall be equipped with Pulse width modulating (PWM)The system should be fitted with interlock switch for safety . The system should allow connection to a fan section to achieve 500 FPM velocity across the air cleaner. Vendor to include cost of MCB & single phase wiring for AC supply to the Scrubber. |  |  | -
| Operating Voltage : 220V, 50 Hz Ionizing Voltage : 12.5 to 13 KVDC Collector Cell Voltage : 6 to 6.5 KVDC Power Consumption : Not more than 50W per cell. |  |  | -
| The Scrubber Machines (EAC) shall be of following duty parameters : |  |  | -
| M/c No Capacity (CFM) |  |  | -
| AS-1 2000 |  |  | -
1.1.3 | Supply, Installation, Testing & Commissioning of direct driven TUBE/VANE AXIAL FLOW FAN. Vane Axial flow fan for Normal Fresh air supply. Fan motor shall be suitable for 415 ± 10% volts, 50 cycles, 3 phase power supply with high efficiency, IE-3 type for normal application and fan total efficiency should not be less than 65%. The fan shall be equipped with mounting bracket & spring isolators for the installation of the fans. Fan static pressure shall be as indicated but actual duting & fan static pressure to be checked by vendor. Fan shall be with fire proof flexible connection at inlet and outlet. Noise level for normal application fans shall be less than 70 dbA @1 meter distance. If required, shall be included to meet the desired sound levels. All Fans shall be with back draft damper and cost will be included in the cost. |  | No | 1 | 1,95,000 | 195000 | 0.7
| Description CFM ESP (mm.of wg) |  |  | -
| Kitchen Fresh Air 1500 60 |  |  | -
1.2 | AIR CURTAIN |  | No | 1 | 1,65,000 | 165000 | 0.7
| Supply, installation, testing and commissioning of Air Curtain as shown in drawings.Unit consist of Blowers,motors & nozzles .It has velocity control switch & door sensors. Material of the Body is MS Powder Coated and having dB level in between 60-70. |  |  |  | WO Amount | 1638700

## JMR Plambing RA Bill 8
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:24/03/2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-08 MEASUREMENT SHEET OF PLUMBING
S. No. | Item. Code | Specification | Unit | Descreption | Site Qty | PO Qty | Rate | Amount | Remarks
| a) | All Sanitary fixtures including bottle traps (from approved make list), shall be issued free of cost by the "Employer". The contractor rates to include for supply all fixing/supporting accessories like nuts, bolts, screws, hangers, rubber buffers, CI or MS brackets, anchor fastners, sealents, washers, adhesives, Flanges, plumber's tape, white cement, masking tape (if required for protection), which are required for the successful installation of the fixtures/fittings in a neat workman like manner.
| b) | Rates are inclusive of fixing/ work at all the heights, depths and locations within the project premises.-
| c) | Rates are inclusive of fixing/work for underslung plumbing system or embeded piping. Mostly, all the toilets in the residencial units have been designed for under slung piping
| d) | Provision of extension piece for final connection of CP fitting shall be supplied and installed by the contractor accordingly (as required
| e) | All pressure pipe will be tested on 1.5 times of there working pressure
| 1 | Providing, Supply, installation, testing and commisning of white vitreous china Wall mounted type "European" water closet pan with seat cover, closed coupled dual flush cistern (with all internal moving parts) with PVC heavy duty connectors, bolts, nuts, supporting arrangements, bakelite seat & cover with CP hinges & rubber buffers, P or S trap, connection to main pipe on shaft complete with all accessories including cutting & making good masonry holes/chasing in the walls & floors wherever required & health faucet with regulator with flexible pipe 1.5 m long, wall hooked complete as required, with all required accessories that includes Flush Plate ,bib cock made of CP brass complete as required | Nos | Male Restroom=2 Femal Restroom=2 | 4 | 4 | 29000 |  | ON HOLD
| 2 | Providing, Supply, installation, testing and commisning of white vitreous china "Floor mounted" type Composite Water closet (European type W.C. pan) with seat and lid, including with white Vitreous Chinaware matching Cistern complete with all accessories , also including with matching W.C. Pan with ISI marked white/Black solid plastic seat and Lid.Details of COST of one Pan composite with Cistern, Flush Pipe, EWC & Cistern complete with Fittings & Seat Cover,and one no. of Faucet for WB,with all required accessories that includes bib cock made of CP brass complete as required | Nos | Disable Restroom=1 | 1 | 1 | 26000 |  | ON HOLD
| 3 | Providing and fixing white vitreous china rectangular Half pedestal Wash Basin & its accessories etc, also with all fittings and fixtures complete including cutting and making good the walls and floors wherever required. (for Handicapped person's Toilets) (colour- Star White) painted white, 32mm C.P. waste coupling, 32mm dia C.P. bottle trap and connection pipe upto wall with wall flange and rubber adopter for waste connection, complete including cutting and making good the walls, wherever required. | Nos | Disable Restroom=1 | 1 | 1 | 22000 |  | ON HOLD
| 4 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass basin mixer top mounted with C.P. wall flange of approved quality | Nos | SPA=1 | 1 | 1 | 2500 |  | ON HOLD
| 5 | Providing, Supply, installation, testing and commisning of CP Grab Bar swing type (in horizontal & vertical grabbing) & Grab rails 60 cm, complete including cutting and making good the walls, wherever required. | Nos | BAR Basin=1 | 1 | 1 | 3200 |  | ON HOLD
| 6 | Providing, Supply, installation, testing and commisning of CP Grab rails 60 cm, complete including cutting and making good the walls, wherever required. | Nos | Kitchen=1 | 1 | 1 | 3200 |  | ON HOLD
| 7 | Providing, Supply, installation, testing and commisning of C.P. toilet paper holder with roller, with C.P brass screws, complete including cutting and making good the walls wherever required. | Nos | Male Restroom=2 Femal Restroom=2 Disable Restroom=1 | 5 | 5 | 2500 |  | ON HOLD
| 9 | Providing, Supply, installation, testing and commisning of C.P twin Robt hook, fixed to wooden cleats with C.P. brass screws including cutting and making good the walls wherever required. | Nos | SPA=1 Male Restroom=1 Femail Restroom=1 Disable Restroom=1 | 4 | 4 | 650 |  | ON HOLD
| 11 | Providing, Supply, installation, testing and commisning of Automatic liquid soap dispenser with simple push lever fitted with liquid soap (one time),C.P. brass screws including cutting and making good the walls wherever required | Nos | Male Restroom=2 Femal Restroom=2 Disable Restroom=1 | 5 | 5 | 6500 |  | ON HOLD
| 13 | Providing, Supply, installation, testing and commisning of SS 204 Grade Bin | Nos | Male Restroom=1 Femal Restroom=1 Disable Restroom=1 Kitchen=2 | 5 | 5 | 3500 |  | ON HOLD
| 14 | Providing, Supply, installation, testing and commisning of C.P. Paper Towel Dispenser,with C.P brass screws, complete including cutting and making good the walls wherever required. | Nos | Male Restroom=1 Femal Restroom=1 | 2 | 2 | 9500 |  | ON HOLD
| 15 | Providing and fixing white vitreous china rectangular wash basin under / over counter mounting, specially fabricated brackets to support the wash basin as per standard practice, painted white, 32mm C.P. waste coupling, 32mm dia C.P. bottle trap and connection pipe upto wall with wall flange and rubber adopter for waste connection, complete including cutting and making good the walls, wherever required. | Nos | SPA Counter=1 BAR Counter=1 Kitchen=2 | 4 | 4 | 6500 |  | ON HOLD
| 18 | Providing, fixing, testing and commissioning of white viterous china large flat back / half stall urinal supported by CI / MS bracket (duly painted with 2 coats of paints over a coat of primer), including CP brass waste with dome type grating, CP cast brass bottle trap with extension piece, wall flanges complete with all accessories & urinal partition with concealed CI bracket, cutting and making good, Including battery operated sensor based automatic flushing system for urinals, including sensor and required electrical and water connections etc, complete in all respect to make it fully functional including cutting and making good the walls etc. | Nos | Male Restroom=3 | 3 | 2 | 26000 |  | ON HOLD
| 19 | Providing, Supply, installation, testing and commisning of C.P. brass angle valve with C.P. wall flange, Nut and Washer etc. complete as required for 15 mm & 20 mm dia | Nos | SPA Counter=2 BAR Counter=4 Kitchen=5 Janitour Room=1 Male Restroom=8 Female Restroom=5 Disable Restroom=3 | 28 | 28 | 3200 |  | ON HOLD
| 20 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass bib cock with C.P. wall flange of approved quality | Nos | SPA Counter=1 BAR Counter=1 Kitchen=2 Janitor=1 | 5 | 5 | 3000 |  | ON HOLD
| 21 | Providing, Supply, installation,testing and commissioning of Stainless steel sink (Single bowl with drainboard sink) 304 Grade SS,Matt Finish medium size 1000 X 500MM) supported by CI / MS Brackets duly painted, CP cast brass bottle trap with extension piece, rubber adaptor, CP copper connecting pipes, wall flange, union, CP brass chain, rubber plug, nuts, washers, waste connection complete & making good the walls, floor wherever required. | Nos | Kitchen=1 | 1 | 1 | 31000 |  | ON HOLD
| 22 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass sink mixer (wall mounted ) with 150 MM swivel spout, with C.P. wall flange of approved quality | Nos | Kitchen=1 | 1 | 1 | 3000 |  | ON HOLD
| 23 | Providing, Supply, installation,testing and commissioning of High Speed hand dryer suitable to be operated with 230 volts, single phase, with fully hygienic operations with all accessories including cutting and making good the walls, wherever required. | Nos | Male Restroom=1 Femail Restroom=1 Disable Restroom=1 | 3 | 3 | 15600 |  | ON HOLD
| 24 | Providing and fixing CP Brass 32mm size Bottle Trap of approved quality & make and as per the direction of Engineer-in-charge. | Nos | Male Restroom=3 Femail Restroom=3 Disable Restroom=2 | 8 | 6 | 3000 |  | ON HOLD
| B | WATER SUPPLY
Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain & brass threaded fittings, including fixing the pipe with clamps at 1.00 m spacing. This includes jointing of pipes & fittings with one step CPVC solvent cement and testing of joints complete as per direction of Engineer in Charge
Internal work - Exposed on wall
| a) | 15mm dia | Mtrs | Male,Female,Disable Restroom | 57.3 | 60 | 170 | 9741
| b) | 20mm dia | Mtrs | Male,Female,Disable Restroom,Kitchen,SPA | 29.8 | 30 | 190 | 5662
| c) | 25mm dia | Mtrs | Male,Female,Disable Restroom,Kitchen,BAR | 13.23 | 15 | 220 | 2910.6
| d) | 32mm dia | Mtrs | Male,Female,Disable Restroom,Kitchen,BAR | 14 | 15 | 275 | 3850
| e) | 40mm dia | Mtrs | Male ,Female Restroom | 8.8 | 10 | 300 | 2640
| f) | 50mm dia | Mtrs | Male ,Female Restroom | 13.5 | 15 | 320 | 4320
| 26 | Providing and fixing CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure - 7 Bar @ 82 Deg C and 28 Bar @ 23 Deg C)for pipes from 1/2 Inch to 2 Inch. Schedule 40 Pipe to be used from 2-1/2 Inch to 6 Inch. Pipes shall be joined using solvent welded CPVC fittings i.e. Tees, Elbows, Couplers, Unions, Reducers, brushings etc. including transition fittings (connection between CPVC & metal pipe/GI) i.e. Brass Adaptors (both Male & Female threaded) conforming to ASTM D-2846. ASTM F441 with only CPVC solvent cement conforming to ASTM F-493.
Cost shall be inclusive of (a)Making maximum of 7.5 x 7.5 cm chasing in wall and floors for the pipe, making good the same by using 1:1 cement mortar over the wire mesh and providing protection to embedded pipes and fittings (in wall chase) by wrapping two layers of 400 micron polythene sheet including proper overlaps on joints complete as required or (b) Fixing/supporting the pipes (& fittings) at wall/ceiling level supported by galvanized clamps, hangers etc, as per specification. Exposed pipes to be painted of legends with direction arrow. GI pipe sleeves suitable higher size shall be provided wherever the pipes are crossing the fire rated walls / floors slab and sealing the sleeves with glass wool in between and fire sealant compound at either end all as per Project Manager's / Consultant requirement. All termination points for installation of faucets shall have brass termination fittings. Installation shall be to as per Technical Manual of manufacturer of pipes & fittings.
| a) | 15 mm dia | Mtrs | Male,Female,Disable Restroom | 96.76 | 100 | 145 | 14030.2
| b) | 20mm dia | Mtrs | Male,Female,Disable Restroom | 13.87 | 15 | 160 | 2219.2
| 27 | Providing & fixing full way lever operated forged brass ball valve of brass body with forged brass hard chromeplated steel ball tested to a pressure not less than 15 Kg / sqcm with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc.
|  | 15mm | Nos | Restroom | 2 | 2 | 650 |  | ON HOLD
|  | 20mm | Nos | Restroom | 10 | 10 | 700 |  | ON HOLD
|  | 25mm | Nos | Restroom | 1 | 1 | 700 |  | ON HOLD
|  | 32mm | Nos | Restroom | 1 | 1 | 750 |  | ON HOLD
| 28 | Providing & fixing of butterfly valve (PN 16) with flanges, nut bolts, gaskets and necessary pad locking arrangement complete required.
|  | 50 mm dia | Nos | Fire pipe | 1 | 1 | 1500 | 1500
| 29 | Supplying, laying/ fixing, testing and commissioning of following thickness resin bonded fiber glass pipe section insulation having density 80 kg/cum or mineral wool (non combustible) having density of 144 Kg/ cu m duly covered with a layer of 120 gm/sqm polythene sheet (vapour barrier) on existing pipe and finally applying 0.63mm aluminium sheet cladding complete with type3 , grade 1 roofing feltstrip(as per IS:1322 as amended up to date ) at joints etc. as per specifications and as required.
| a) | 25 mm thick mineral wool insulation (15 mm dia) | Mtrs | Restroom,BAR Area | 52.8 | 55 | 350 |  | ON HOLD
| b) | 25 mm thick mineral wool insulation (20 mm dia) | Mtrs | Restroom,BAR Area | 13.5 | 15 | 400 |  | ON HOLD
| c) | 25 mm thick mineral wool insulation (25 mm dia) | Mtrs | Restroom,BAR Area | 12.8 | 15 | 430 |  | ON HOLD
| d) | 25 mm thick mineral wool insulation (32mm dia) | Mtrs | Restroom,BAR Area | 14.01 | 15 | 450 |  | ON HOLD
| C | DRAINAGE
| 30 | Providing, Supply, installation,testing and commissioning of UPVC Soil, Waste & Vent system conforming to IS : 13592 - Type B and UPVC fittings (moulded as well as fabricated) like bends, tees, Y-tees, crosses, boss connections, access pieces, saddle pieces, cleanouts, adaptors for connections to other materials, plugs, reducers, cowls, offSet and other specials. Jointing shall be done with pushfit EPDM ring jointing technique in general. Solvent cement joints may be provided for fittings and specials which are not manufactured with pushfit rubber joints. Pipes may be laid / fixed in sunken floors, under slung from ceiling. The pipes laid in sunken floor shall be encased with 75 mm thick cement concrete (1:2:4) all around. The installation shall be complete in all respects including cutting chases / holes in walls, slabs and making good the same as per specifications
Providing GI pipe sleeves of suitable higher size wherever pipes crossing a fire rated wall / floor slab and sealing of space around pipe and pipe sleeve with glass wool in between and fire proof sealent at either end to the satisfaction of the Project Manager / Consultants and making good the same after pipes have been duly laid and testing complete.
| a) | 110mm dia | Mtrs | Male,Female,Disable Restroom,Kitchan,Janetor Room,SPA | 52.87 | 53 | 500 | 26435
| b) | 75mm dia | Mtrs | Male,Female,Disable Restroom | 28.02 | 30 | 450 | 12609
| c) | 50mm dia | Mtrs | Restroom,Kitchan | 49 | 50 | 380 | 18620
| d) | 40mm dia | Mtrs | Restroom,Kitchan,BAR | 8.88 | 10 | 350 | 3108
| 31 | Providing and fixing of UPVC Floor Traps formed out of bore 'P' trap with 50 mm water seal, setting in 1:2:4 mix cement concrete block or clamping to the wall or suspending with the ceiling including cutting and making good the walls and floors wherever required, With Heavy class SS grating with Cockroach proof SS strainer of approved design including setting in floor with cement motor to match with floor finish as per architect requirement suitable for waster F.D. & F.T
| a) | 110 mm inlet and 110 mm outlet. | Nos | BAR Area=2 Kitchen=3 Male Restroom=2 Female Restroon=2 Disable Restroom=1 Janitor=1 spa=1 | 10 | 10 | 1500 | 15000
| 32 | Providing and fixing of UPVC Nani Traps with 50 mm water seal, setting in 1:2:4 mix cement concrete block or clamping to the wall or suspending with the ceiling including cutting and making good the walls and floors wherever required, With Heavy class SS grating with Cockroach proof SS strainer of approved design including setting in floor with cement motor to match with floor finish as per architect requirement suitable for waster trap
| a) | 110 mm inlet and 110 mm outlet. | Nos | Janitor=1 Kitchen=3 SPA=1 Male Restroom=1 Female Restroom=1 Disable Restroom=1 | 8 | 8 | 1500 | 12000
| 33 | Providing and fixing Floor drain made out of 110x75 mm OD uPVC. elbow connected to uPVC pipe complete as per direction of Project Manager | Nos | Disable Restroom=4 | 4 | 4 | 600 | 2400
| 34 | Providing and fixing clean out/floor clean out plug consist of CI bend & GI socket heavy class with cap & key for opening male threaded cap etc. including lead caulked to CI pipes complete in all respects as per drawing/ sample approved by Engineer -in -Charge FCO (floor clean out plug shall be flushed with floor finish).: 100 mm dia. and Matching with Item no.31 or as per Architure approvals. | Nos | Male Restroom=1 Femail Eestroom=1 Disable Restroom=1 | 3 | 3 | 860 | 2580
[7 empty] | Total Amount | 139625

## JMR FF RA Bill 03
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.02.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : CVL INT CIP Lounge T3 Lok
RA-1 MEASUREMENT SHEET OF FIRE FIGHTING
S. No. | Item. Code | Specification | Description | L | W | H | Unit | Nos | Qty. | Rate | Amount
1 | D | FIRE FIGHTING
| 35 | Supply, installation, testing and commissioning of following sizes of pipes conforming to IS-1239 with all accessories like all fittings ( all pipes & fittings upto 50mm dia threaded shall be the threaded Ductile Iron (ASTM A536) or Cast Iron (ASTM A126) or Forged Steel fittings and for pipes above 50 mm dia MS fitting with welded joint shall be used) including tees, elbows, reducers, union, flanges, rubber gaskets, GI nuts bolts, washer including supporting/fixing the pipe on wall /ceiling with clamps, hangers (using anchor fastners) as per specification, Including synthetic enamel paint of approved shade over a coat of primer. Prior to application of primer the surface should be cleaned for any dirt, rusts, rough substance etc. Including painting of legends both direction arrow as per the approval of the Project Manager
MS pipe sleeve of suitable higher size shall be provided wherever the pipes are crossing the walls/floors and sealing the sleeves with glass wool in between & fire sealent compound at either end all as per Project Manager’s requirements including cutting holes and chases in brick, R.C.C work and making good the same to original conditions complete in all respects. All hangers, clamps, brackets etc. shall be of galvanized iron unless specified otherwise and the supply of the same shall also be included in rates under this head. Welding of any kind on the galvanized support / hanger shall not be permitted
For Sprinkler system - MS `C' Heavy class pipe
|  |  | a) 25 mm dia | 89.0737 |  |  | Rmt. | 1 | 89.0737 | 650 | 57897.905
|  |  | b) 32 mm dia | 13.471 |  |  | Rmt. | 1 | 13.471 | 750 | 10103.25
|  |  | c) 40 mm dia | 5.823 |  |  | Rmt. | 1 | 5.823 | 820 | 4774.86
|  |  | d) 50 mm dia | 15.921 |  |  | Rmt. | 1 | 15.921 | 900 | 14328.9
|  |  | e) 65 mm dia | 13.182 |  |  | Rmt. | 1 | 13.182 | 1100 | 14500.2
|  |  | f) 80 mm dia | 11.875 |  |  | Rmt. | 1 | 11.875 | 1650 | 19593.75
| 36 | Supply, installation, testing and commissioning of brass quartzoid sprinklers (UL approved) of 15 mm dia size, suitable for sustaining the pressure on the seat & water hammer effect. The type & temperature rating shall be as follows
|  | Spray recessed (adjustable) rossette (68°C) sprinkler quick response pendent type |  |  |  |  | Nos | 1 | 47 | 500 | 23500
| 37 | Supplying, installation, testing & commissioning of sprinkler flexible pipe (UL Listed) of stainless steel complete with 15 NPT on reducer thread with maximum working pressure of 175 PSI test pressure of 875 PSI (Burst) with branch line (Inlet) 25mm NPT male thread to sprinkler head (Outlet) 15mm NPT female thread with reducer, nipple, 2 side brackets, center bracket, stockbar of following sizes complete as required.
|  | 1000mm |  |  |  |  | Nos | 1 | 47 | 2700 | 126900
| 38 | Providing and fixing fully charged ABC powder type (Mono-Ammonium Phosphate - MAP 90) portable fire extinguishers conforming to IS:15683, fixed to wall with brackets complete with initial charge. (Note: The cost for stand of fire extinguisher shall be included in this rate
|  | Capacity 6 Kg. |  |  |  |  | Nos | 1 | 3 | 6500 | 19500
| 39 | Providing and fixing CO2 type cylindrical shape fire extinguisher with fixing hangers, hose, brackets, screws to required size etc.complete as per IS:15683:2006 - wall mounted type.
|  | Capacity 4.5 Kg. |  |  |  |  | Nos | 1 | 3 | 5600 | 16800
| 40 | Providing & fixing of butterfly valve (PN 16) with flanges, nut bolts, gaskets and necessary pad locking arrangement complete required.
|  | 100 mm dia |  |  |  |  | Nos | 1 | 1 | 12600 | 12600
[8 empty] | Total Amount in Rupees |  |  | 320498.865

## Abstract Sheet FF & Plambing
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Code / Area Specified | Qty. | UoM | Impulse Branding |  | RA-08 |  | RA Bill 10 |  | Extra Qty RA Bill 10 |  | Cumulative |  | Variance
[5 empty] | Unit Price | Total Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount
[5 empty] | INR | INR
Plambing WORKS
1 | Providing, Supply, installation, testing and commisning of white vitreous china Wall mounted type "European" water closet pan with seat cover, | WC | 4 | Nos | 29000 | 116000 |  |  | 4 | 116000
0
2 | Providing, Supply, installation, testing and commisning of white vitreous china "Floor mounted" type Composite Water closet (European type W.C. | WC /HC | 1 | Nos | 26000 | 26000 |  |  | 1 | 26000
0
3 | Providing and fixing white vitreous china rectangular Half pedestal Wash Basin | Wash Basin | 1 | Nos | 22000 | 22000 |  |  | 1 | 22000
0
4 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass basin mixer top mounted with C.P. wall flange of approved quality | 15 mm dia C.P. brass | 1 | Nos | 2500 | 2500 |  |  | 1 | 2500
0
5 | Providing, Supply, installation, testing and commisning of CP Grab Bar swing type (in horizontal & vertical grabbing) & Grab rails 60 cm, complete including cutting and | CP Grab Bar swing type | 1 | Nos | 3200 | 3200 |  |  | 1 | 3200
0
6 | Providing, Supply, installation, testing and commisning of CP Grab rails 60 cm, complete including cutting and making good the walls, wherever required. | CP Grab Bar swing type | 1 | Nos | 3200 | 3200 |  |  | 1 | 3200
0
7 | Providing, Supply, installation, testing and commisning of C.P. toilet paper holder with roller, with C.P brass screws, complete including cutting and making good the walls wherever required. | C.P. toilet paper | 5 | Nos | 2500 | 12500 |  |  | 5 | 12500
0
8 | Providing, Supply, installation, testing and commisning of C.P twin Robt hook, fixed to wooden cleats with C.P. brass screws including cutting and making good the walls wherever required. | C.P twin Robt hook | 4 | Nos | 650 | 2600 |  |  | 4 | 2600
0
9 | Providing, Supply, installation, testing and commisning of Automatic liquid soap dispenser with simple push lever fitted with liquid soap (one time),C.P. brass screws including cutting and making good the walls wherever required. | soap dispenser | 5 | Nos | 6500 | 32500 |  |  | 5 | 32500
0
10 | Providing, Supply, installation, testing and commisning of SS 204 Grade Bin | SS 204 Grade Bin | 5 | Nos | 3500 | 17500 |  |  | 4 | 14000
0
11 | Providing, Supply, installation, testing and commisning of C.P. Paper Towel Dispenser,with C.P brass screws, complete including cutting and making good the walls wherever required. | C.P. Paper Towel Dispenser | 2 | Nos | 9500 | 19000 |  |  | 2 | 19000 | 1 | 9500
0
11 | Providing and fixing white vitreous china rectangular wash basin under / over counter mounting, specially fabricated brackets | white vitreous china rectangular wash basin under | 4 | Nos | 6500 | 26000 |  |  | 2 | 13000
0
12 | Providing, fixing, testing and commissioning of white viterous china large flat back / half stall urinal supported by CI / MS bracket | white viterous china large flat back / half stall urinal | 2 | Nos | 26000 | 52000 |  |  | 3 | 78000
0
13 | Providing, Supply, installation, testing and commisning of C.P. brass angle valve with C.P. wall flange, Nut and Washer etc. complete as required for 15 mm & 20 mm dia | C.P. brass angle valve | 28 | Nos | 3200 | 89600 |  |  | 28 | 89600
0
14 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass bib cock with C.P. wall flange of approved quality | 15 mm dia C.P. brass bib | 5 | Nos | 3000 | 15000 |  |  | 5 | 15000
0
15 | Providing, Supply, installation,testing and commissioning of Stainless steel sink (Single bowl with drainboard sink) 304 Grade SS,Matt Finish medium size 1000 X 500MM) | Stainless steel sink | 1 | Nos | 31000 | 31000 |  |  | 0 | 0
0
16 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass sink mixer (wall mounted ) with 150 MM swivel spout, with C.P. wall flange of approved quality | 15 mm dia C.P. brass sink mixer | 1 | Nos | 3000 | 3000 |  |  | 1 | 3000
0
17 | Providing, Supply, installation,testing and commissioning of High Speed hand dryer suitable to be operated with 230 volts, single phase, with fully hygienic operations with all accessories including cutting and making good the walls, wherever required. | High Speed hand dryer suitable | 3 | Nos | 15600 | 46800 |  |  | 3 | 46800
0
18 | Providing and fixing CP Brass 32mm size Bottle Trap of approved quality & make and as per the direction of Engineer-in-charge. | CP Brass 32mm size Bottle Trap | 6 | Nos | 3000 | 18000 |  |  | 5 | 15000
0
19 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain | 15 mm dia | 60 | Rmt | 170 | 10200 | 57.3 | 9741 | 2.7 | 459 | 17.3 | 2941
0
20 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain | 20 mm dia | 30 | Rmt | 190 | 5700 | 29.8 | 5662 |  |  | 30 | 5700
0
21 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain | 25 mm dia | 15 | Rmt | 220 | 3300 | 13.23 | 2910.6 |  |  | 14 | 3080
0
22 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain | 32 mm dia | 15 | Rmt | 275 | 4125 | 14 | 3850 |  |  | 13 | 3575
0
23 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain | 40 mm dia | 10 | Rmt | 300 | 3000 | 8.8 | 2640 |  |  | 8.8 | 8.8
0
24 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain | 50 mm dia | 15 | Rmt | 320 | 4800 | 13.5 | 4320 |  |  | 13.5 | 13.5
[6 empty] | 0 |  | 0
25 | Providing and fixing CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure | 15 mm dia | 100 | Rmt | 145 | 14500 | 96.76 | 14030.2
0
26 | Providing and fixing CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure | 20 mm dia | 15 | Rmt | 160 | 2400 | 13.87 | 2219.2
0
27 | Providing & fixing full way lever operated forged brass ball valve of brass body with forged brass hard chromeplated steel ball tested to a pressure not less than 15 Kg / sqcm with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc. | 15 mm dia | 2 | Nos | 650 | 1300 |  |  | 2 | 1300
0
28 | Providing & fixing full way lever operated forged brass ball valve of brass body with forged brass hard chromeplated steel ball tested to a pressure not less than 15 Kg / sqcm with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc. | 20 mm dia | 10 | Nos | 700 | 7000 |  |  | 10 | 7000
0
29 | Providing & fixing full way lever operated forged brass ball valve of brass body with forged brass hard chromeplated steel ball tested to a pressure not less than 15 Kg / sqcm with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc. | 25 mm dia | 1 | Nos | 700 | 700 |  |  | 1 | 700
0
30 | Providing & fixing full way lever operated forged brass ball valve of brass body with forged brass hard chromeplated steel ball tested to a pressure not less than 15 Kg / sqcm with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc. | 32 mm dia | 1 | Nos | 750 | 750 |  |  | 1 | 750
0
31 | PProviding & fixing of butterfly valve (PN 16) with flanges, nut bolts, gaskets and necessary pad locking arrangement complete required. | 50 mm dia | 1 | Nos | 1500 | 1500 | 1 | 1500
0
32 | Supplying, laying/ fixing, testing and commissioning of following thickness resin bonded fiber glass pipe section insulation having | 25 mm thick mineral wool insulation (15 mm dia) | 55 | Rmt | 350 | 19250 |  |  |  |  | 52.8 | 18480
33 | Supplying, laying/ fixing, testing and commissioning of following thickness resin bonded fiber glass pipe section insulation having | 25 mm thick mineral wool insulation (20 mm dia) | 15 | Rmt | 400 | 6000 |  |  |  |  | 13.5 | 5400
34 | Supplying, laying/ fixing, testing and commissioning of following thickness resin bonded fiber glass pipe section insulation having | 25 mm thick mineral wool insulation (25 mm dia) | 15 | Rmt | 430 | 6450 |  |  |  |  | 12.8 | 5504
35 | Supplying, laying/ fixing, testing and commissioning of following thickness resin bonded fiber glass pipe section insulation having | 25 mm thick mineral wool insulation (32 mm dia) | 15 | Rmt | 450 | 6750 |  |  |  |  | 14.01 | 6304.5
0
36 | Providing, Supply, installation,testing and commissioning of UPVC Soil, Waste & Vent system conforming to IS : 13592 - Type B and UPVC fittings (moulded as well as fabricated) like bends, tees, Y-tees, crosses, boss connections | 110 mm dia | 53 | Rmt | 500 | 26500 | 52.87 | 26435
0
37 | Providing, Supply, installation,testing and commissioning of UPVC Soil, Waste & Vent system conforming to IS : 13592 - Type B and UPVC fittings (moulded as well as fabricated) like bends, tees, Y-tees, crosses, boss connections | 75 mm dia | 30 | Rmt | 450 | 13500 | 28.02 | 12609
38 | Providing, Supply, installation,testing and commissioning of UPVC Soil, Waste & Vent system conforming to IS : 13592 - Type B and UPVC fittings (moulded as well as fabricated) like bends, tees, Y-tees, crosses, boss connections | 50 mm dia | 50 | Rmt | 380 | 19000 | 49 | 18620
39 | Providing, Supply, installation,testing and commissioning of UPVC Soil, Waste & Vent system conforming to IS : 13592 - Type B and UPVC fittings (moulded as well as fabricated) like bends, tees, Y-tees, crosses, boss connections | 40 mm dia | 10 | Rmt | 350 | 3500 | 8.88 | 3108
40 | Providing, Supply, installation,testing and Providing and fixing of UPVC Floor Traps formed out of bore 'P' trap with 50 mm water seal, setting in 1:2:4 mix cement concrete | 110 mm inlet and 110 mm outlet. | 10 | Nos | 1500 | 15000 | 10 | 15000
41 | Providing and fixing of UPVC Nani Traps with 50 mm water seal, setting | 110 mm inlet and 110 mm outlet. | 8 | Nos | 1500 | 12000 | 8 | 12000
42 | Providing and fixing Floor drain made out of 110x75 mm OD uPVC. elbow connected to uPVC pipe complete as per direction of Project Manager. | Floor drain made out of 110x75 mm OD uPVC. Elbow | 4 | Nos | 600 | 2400 | 4 | 2400 |  |  | 15 | 9000
43 | Providing and fixing clean out/floor clean out plug consist of CI bend & GI socket heavy class with cap & key for opening male threaded cap | clean out/floor clean out plug | 3 | Nos | 860 | 2580 | 3 | 2580
| Sub Total |  |  |  | Sub Total | 730605 |  | 139625 |  | 524109 |  | 69506.8
| GST 18% |  |  |  | GST 18%
| Total Amount |  |  |  | Total Amount
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Code / Area Specified | Qty. | UoM | Impulse Branding |  | RA-03 | [5 empty] | Cumulative |  | Variance
[5 empty] | Unit Price | Total Amount | QTY | Amount |  |  |  |  | QTY | Amount | QTY | Amount
[5 empty] | INR | INR
Plambing WORKS
D | FIRE FIGHTING
35 | Supply, installation, testing and commissioning of following sizes of pipes conforming to IS-1239 with all accessories like all fittings ( all pipes & fittings upto 50mm dia threaded shall be the threaded Ductile Iron (ASTM A536) or Cast Iron (ASTM A126) or Forged Steel fittings and for pipes above 50 mm dia MS fitting with welded joint shall be used) including tees, elbows, reducers, union, flanges, rubber gaskets, GI nuts bolts, washer including supporting/fixing the pipe on wall /ceiling with clamps, hangers (using anchor fastners) as per specification, Including synthetic enamel paint of approved shade over a coat of primer. Prior to application of primer the surface should be cleaned for any dirt, rusts, rough substance etc. Including painting of legends both direction arrow as per the approval of the Project Manager |  |  |  | -
| MS pipe sleeve of suitable higher size shall be provided wherever the pipes are crossing the walls/floors and sealing the sleeves with glass wool in between & fire sealent compound at either end all as per Project Manager’s requirements including cutting holes and chases in brick, R.C.C work and making good the same to original conditions complete in all respects. All hangers, clamps, brackets etc. shall be of galvanized iron unless specified otherwise and the supply of the same shall also be included in rates under this head. Welding of any kind on the galvanized support / hanger shall not be permitted. |  |  |  | -
| For Sprinkler system - MS `C' Heavy class pipe |  |  |  | -
a) | 25 mm dia |  | 100 | Mtrs | 650 | 65000 | 89.0737 | 57897.905
b) | 32 mm dia |  | 15 | Mtrs | 750 | 11250 | 13.471 | 10103.25
c) | 40 mm dia |  | 11 | Mtrs | 820 | 9020 | 5.823 | 4774.86
d) | 50 mm dia |  | 19 | Mtrs | 900 | 17100 | 15.921 | 14328.9
e) | 65 mm dia |  | 15 | Mtrs | 1100 | 16500 | 13.182 | 14500.2
f) | 80 mm dia |  | 15 | Mtrs | 1650 | 24750 | 11.875 | 19593.75
g) | 100 mm dia |  | 11 | Mtrs | 2100 | 23100
h) | 150 mm dia |  | 11 | Mtrs | 2500 | 27500
36 | Supply, installation, testing and commissioning of brass quartzoid sprinklers (UL approved) of 15 mm dia size, suitable for sustaining the pressure on the seat & water hammer effect. The type & temperature rating shall be as follows : |  | -
| Note : i)All sprinkler shall be chrome finish / powder coated. ii) Contractor shall ensure provision of sprinkler guard at no additional cost, as required by the Client. |  | -
| Spray recessed (adjustable) rossette (68°C) sprinkler quick response upright type |  | 51 | nos | 550 | 28050 |  | 0
| Spray recessed (adjustable) rossette (68°C) sprinkler quick response pendent type |  | 51 | nos | 500 | 25500 | 47 | 23500
37 | Supplying, installation, testing & commissioning of sprinkler flexible pipe (UL Listed) of stainless steel complete with 15 NPT on reducer thread with maximum working pressure of 175 PSI test pressure of 875 PSI (Burst) with branch line (Inlet) 25mm NPT male thread to sprinkler head (Outlet) 15mm NPT female thread with reducer, nipple, 2 side brackets, center bracket, stockbar of following sizes complete as required. |  | -
| 1000mm |  | 75 | nos | 2700 | 202500 | 47 | 126900
38 | Providing and fixing fully charged ABC powder type (Mono-Ammonium Phosphate - MAP 90) portable fire extinguishers conforming to IS:15683, fixed to wall with brackets complete with initial charge. (Note: The cost for stand of fire extinguisher shall be included in this rate) |  | -
| Capacity 6 Kg. |  | 3 | nos | 6500 | 19500 | 3 | 19500
39 | Providing and fixing CO2 type cylindrical shape fire extinguisher with fixing hangers, hose, brackets, screws to required size etc.complete as per IS:15683:2006 - wall mounted type. |  | -
| Capacity 4.5 Kg. |  | 3 | nos | 5600 | 16800 | 3 | 16800
40 | Providing & fixing of butterfly valve (PN 16) with flanges, nut bolts, gaskets and necessary pad locking arrangement complete required. |  | -
| 100 mm dia |  | 1 | nos | 12600 | 12600 | 1 | 12600
[6 empty] | 499170 |  | 320498.865
[6 empty] | WO Amount |  | RA Bill 03
Note on J32: Urmila Jadhav: Please consider Extra qty separate
Note on L48: Urmila Jadhav: Please check (Qty Repeated)

## JMR Plumbing RA Bill 10
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793 |  |  |  | Date:13/07/2024
Name of the Work : Plumbing Work of CIP Lounge T3 Lok
RA-10 MEASUREMENT SHEET OF PLUMBING
S. No. | Item. Code | Specification | Unit | Descreption | Site Qty | EXTRA QTY
| a) | All Sanitary fixtures including bottle traps (from approved make list), shall be issued free of cost by the "Employer". The contractor rates to include for supply all fixing/supporting accessories like nuts, bolts, screws, hangers, rubber buffers, CI or MS brackets, anchor fastners, sealents, washers, adhesives, Flanges, plumber's tape, white cement, masking tape (if required for protection), which are required for the successful installation of the fixtures/fittings in a neat workman like manner.
| b) | Rates are inclusive of fixing/ work at all the heights, depths and locations within the project premises.-
| c) | Rates are inclusive of fixing/work for underslung plumbing system or embeded piping. Mostly, all the toilets in the residencial units have been designed for under slung piping
| d) | Provision of extension piece for final connection of CP fitting shall be supplied and installed by the contractor accordingly (as required
| e) | All pressure pipe will be tested on 1.5 times of there working pressure
| 1 | Providing, Supply, installation, testing and commisning of white vitreous china Wall mounted type "European" water closet pan with seat cover, closed coupled dual flush cistern (with all internal moving parts) with PVC heavy duty connectors, bolts, nuts, supporting arrangements, bakelite seat & cover with CP hinges & rubber buffers, P or S trap, connection to main pipe on shaft complete with all accessories including cutting & making good masonry holes/chasing in the walls & floors wherever required & health faucet with regulator with flexible pipe 1.5 m long, wall hooked complete as required, with all required accessories that includes Flush Plate ,bib cock made of CP brass complete as required | Nos | Male Restroom=2 Femal Restroom=2 | 4
| 2 | Providing, Supply, installation, testing and commisning of white vitreous china "Floor mounted" type Composite Water closet (European type W.C. pan) with seat and lid, including with white Vitreous Chinaware matching Cistern complete with all accessories , also including with matching W.C. Pan with ISI marked white/Black solid plastic seat and Lid.Details of COST of one Pan composite with Cistern, Flush Pipe, EWC & Cistern complete with Fittings & Seat Cover,and one no. of Faucet for WB,with all required accessories that includes bib cock made of CP brass complete as required | Nos | Disable Restroom=1 | 1
| 3 | Providing and fixing white vitreous china rectangular Half pedestal Wash Basin & its accessories etc, also with all fittings and fixtures complete including cutting and making good the walls and floors wherever required. (for Handicapped person's Toilets) (colour- Star White) painted white, 32mm C.P. waste coupling, 32mm dia C.P. bottle trap and connection pipe upto wall with wall flange and rubber adopter for waste connection, complete including cutting and making good the walls, wherever required. | Nos | Disable Restroom=1 | 1
| 4 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass basin mixer top mounted with C.P. wall flange of approved quality | Nos | Disable Room=1 | 1
| 5 | Providing, Supply, installation, testing and commisning of CP Grab Bar swing type (in horizontal & vertical grabbing) & Grab rails 60 cm, complete including cutting and making good the walls, wherever required. | Nos | Male Restroom=1 | 1
| 6 | Providing, Supply, installation, testing and commisning of CP Grab rails 60 cm, complete including cutting and making good the walls, wherever required. | Nos | Female Restroom=1 | 1
| 7 | Providing, Supply, installation, testing and commisning of C.P. toilet paper holder with roller, with C.P brass screws, complete including cutting and making good the walls wherever required. | Nos | Male Restroom=2 Femal Restroom=2 Disable Restroom=1 | 5
| 9 | Providing, Supply, installation, testing and commisning of C.P twin Robt hook, fixed to wooden cleats with C.P. brass screws including cutting and making good the walls wherever required. | Nos | Admin Room=3 Electrical Room=1 | 4
| 11 | Providing, Supply, installation, testing and commisning of Automatic liquid soap dispenser with simple push lever fitted with liquid soap (one time),C.P. brass screws including cutting and making good the walls wherever required | Nos | Male Restroom=2 Femal Restroom=2 Disable Restroom=1 | 5
| 13 | Providing, Supply, installation, testing and commisning of SS 204 Grade Bin | Nos | Male Restroom=2 Femal Restroom=2 Disable Restroom=1 | 4
| 14 | Providing, Supply, installation, testing and commisning of C.P. Paper Towel Dispenser,with C.P brass screws, complete including cutting and making good the walls wherever required. | Nos | Male Restroom=1 Femal Restroom=1 Disable Restroom=1 | 2 | 1
| 15 | Providing and fixing white vitreous china rectangular wash basin under / over counter mounting, specially fabricated brackets to support the wash basin as per standard practice, painted white, 32mm C.P. waste coupling, 32mm dia C.P. bottle trap and connection pipe upto wall with wall flange and rubber adopter for waste connection, complete including cutting and making good the walls, wherever required. | Nos | SPA Counter=1 Desable Counter=1 | 2
| 18 | Providing, fixing, testing and commissioning of white viterous china large flat back / half stall urinal supported by CI / MS bracket (duly painted with 2 coats of paints over a coat of primer), including CP brass waste with dome type grating, CP cast brass bottle trap with extension piece, wall flanges complete with all accessories & urinal partition with concealed CI bracket, cutting and making good, Including battery operated sensor based automatic flushing system for urinals, including sensor and required electrical and water connections etc, complete in all respect to make it fully functional including cutting and making good the walls etc. | Nos | Male Restroom=3 | 3
| 19 | Providing, Supply, installation, testing and commisning of C.P. brass angle valve with C.P. wall flange, Nut and Washer etc. complete as required for 15 mm & 20 mm dia | Nos | SPA Counter=2 BAR Counter=4 Kitchen=11 Janitour Room=1 Male Restroom=4 Female Restroom=4 Disable Restroom=2 | 28
| 20 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass bib cock with C.P. wall flange of approved quality | Nos | BAR Counter=1 Male Restroom=2 Female Restroom=2 | 5
| 21 | Providing, Supply, installation,testing and commissioning of Stainless steel sink (Single bowl with drainboard sink) 304 Grade SS,Matt Finish medium size 1000 X 500MM) supported by CI / MS Brackets duly painted, CP cast brass bottle trap with extension piece, rubber adaptor, CP copper connecting pipes, wall flange, union, CP brass chain, rubber plug, nuts, washers, waste connection complete & making good the walls, floor wherever required. | Nos | Bar Counter=1 | 0
| 22 | Providing, Supply, installation, testing and commisning of 15 mm dia C.P. brass sink mixer (wall mounted ) with 150 MM swivel spout, with C.P. wall flange of approved quality | Nos | SPA=1 | 1
| 23 | Providing, Supply, installation,testing and commissioning of High Speed hand dryer suitable to be operated with 230 volts, single phase, with fully hygienic operations with all accessories including cutting and making good the walls, wherever required. | Nos | Male Restroom=1 Female Restroom=1 Disable Restroom=1 | 3
| 24 | Providing and fixing CP Brass 32mm size Bottle Trap of approved quality & make and as per the direction of Engineer-in-charge. | Nos | Male Restroom=2 Femail Restroom=2 Disable Restroom=1 Kitchen=1 | 5
| B | WATER SUPPLY
Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain & brass threaded fittings, including fixing the pipe with clamps at 1.00 m spacing. This includes jointing of pipes & fittings with one step CPVC solvent cement and testing of joints complete as per direction of Engineer in Charge
Internal work - Exposed on wall
| a) | 15mm dia | Mtrs | RO Supply and Return | 2.7 | 17.3
| b) | 20mm dia | Mtrs | Gysure Supply=16 Water tank Supply and Return=20 |  | 30
| c) | 25mm dia | Mtrs | AHU return water=20 |  | 14
| d) | 32mm dia | Mtrs | Male Restroom Female Restroom Disable Restroom Kitchen |  | 13
| e) | 40mm dia | Mtrs | Fresh Water Tap |  | 8.8
| f) | 50mm dia | Mtrs | Supply Water Tap |  | 13.5
| 27 | Providing & fixing full way lever operated forged brass ball valve of brass body with forged brass hard chromeplated steel ball tested to a pressure not less than 15 Kg / sqcm with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc.
|  | 15mm | Nos | Restroom | 2
|  | 20mm | Nos | Restroom | 10
|  | 25mm | Nos | Restroom | 1
|  | 32mm | Nos | Restroom | 1
| 29 | Supplying, laying/ fixing, testing and commissioning of following thickness resin bonded fiber glass pipe section insulation having density 80 kg/cum or mineral wool (non combustible) having density of 144 Kg/ cu m duly covered with a layer of 120 gm/sqm polythene sheet (vapour barrier) on existing pipe and finally applying 0.63mm aluminium sheet cladding complete with type3 , grade 1 roofing feltstrip(as per IS:1322 as amended up to date ) at joints etc. as per specifications and as required.
| a) | 25 mm thick mineral wool insulation (15 mm dia) | Mtrs | BAR and Restroom |  | 52.8
| b) | 25 mm thick mineral wool insulation (20 mm dia) | Mtrs | BAR and Restroom |  | 13.5
| c) | 25 mm thick mineral wool insulation (25 mm dia) | Mtrs | BAR and Restroom |  | 12.8
| d) | 25 mm thick mineral wool insulation (32mm dia) | Mtrs | BAR and Restroom |  | 14.01
| C | DRAINAGE
| 31 | Providing and fixing of UPVC Floor Traps formed out of bore 'P' trap with 50 mm water seal, setting in 1:2:4 mix cement concrete block or clamping to the wall or suspending with the ceiling including cutting and making good the walls and floors wherever required, With Heavy class SS grating with Cockroach proof SS strainer of approved design including setting in floor with cement motor to match with floor finish as per architect requirement suitable for waster F.D. & F.T
| a) | 110 mm inlet and 110 mm outlet. | Nos | Kitchen=4 Male Restroom=5 Female Restroon=3 Disable Restroom=2 Janitor=1 |  | 15

## JMR STRUCTURE STEEL RA 01
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.01.2024
Project : CIP Lounge T3 Lucknow
W/O No : PO/SKPL/23-24/001793
Name of the Work : STRUCTURE STEEL WORK CIP Lounge
RA Bill MEASUREMENT SHEET
S. No. | Item. Code | Specification | L | W | H | T | Unit Wt. (g/cm^3) | Number | Unit | Site Qty. | Rs | Amount
STRUCTURE STEEL WORK
1 | 17 | Providing, fabricating and erecting structural steel beams, columns, shear walls, canopy, MEP services, ramps, insert plates, embedded plates, shear angles, base plates, fasteners, stud connectors etc., of readymade / built-up / rolled sections of grade upto Fy 240-450 in position at all levels and at all heights as specified in the drawings conforming to IS 226/800; The rate shall include base Primer and applying one or Two coat of Anti-Corrosive Fire Retardent Paint color as approved to the Entrie MS work such as Members/walls & beams; main steel, fasteners and miscellaneous items; The rate shall also include the provision of Mobile crane, Lifting crane, scaffolding etc. for erection as required and described elsewhere; rate is deemed to include all wastages; steel procurement price shall be considered as basic rate provided and any variation between the actual procurement price and this rate shall be paid extra; if steel is provided as free issue, the cost of such steel computed at the basic rate shall be deducted from the overall price after adjustment of rolling margins only; no adjustments shall be permitted for wastages and same shall be considered as included in the rate.
Premium Lounge
|  | Right Side Wall | 76490 | 50 | 50 | 5 | 7.3 | 1 | KG | 502.54
|  | Left Side Wall | 96430 | 50 | 50 | 5 | 7.3 | 1 | KG | 633.55
Kitchen Wall
|  | Door wall | 17740 | 50 | 50 | 5 | 7.3 | 1 | KG | 116.55
SPA
|  | Left Side Wall | 42730 | 50 | 50 | 5 | 7.3 | 1 | KG | 280.74
|  | Right Side Wall | 40710 | 50 | 50 | 5 | 7.3 | 1 | KG | 267.46
|  | Glass door wall | 9100 | 50 | 50 | 5 | 7.3 | 1 | KG | 59.79
Electrical Room
|  | Door Partation | 27510 | 50 | 50 | 5 | 7.3 | 1 | KG | 180.74
Dining Area
|  | Glass door wall | 40410 | 50 | 50 | 5 | 7.3 | 1 | KG | 265.49
Admin Office
|  | Wall | 66790 | 50 | 50 | 5 | 7.3 | 1 | KG | 438.81
Reception
|  | wall | 73930 | 50 | 50 | 5 | 7.3 | 1 | KG | 485.72
|  | 8 mm Base Plate with 50mm Hight |  |  |  |  | 0.5 | 70 | KG | 35
[8 empty] | Total Weight in KG |  | 3266.39 | 150 | 489958.5
[9 empty] | MT | 3.266
| 2 | Anchoring Work
Providing, scanning, drilling and driving of various Dia and Shape Anchor rods / Anchor fastener of HILTI (Chemical anchors - RE500) including all other consumables like chemicals, foils, Grouting materials, using HILTI / Bosch make machinery, tools & plants, all accessories etc. complete at all levels as directed by the Engineer-in-charge.
| a | RE 500-Hilti Anchor-10mm dia (150mm anchoring) |  | 140 | Nos |  |  |  |  | 140
| b | RE 500-Hilti Anchor-16mm dia (150mm anchoring) |  | - | Nos

## Abstract STRUCTURE STEEL WORK
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Code / Area Specified | Qty. | UoM | Impulse Branding |  | RA-01 |  | Cumulative |  | Variance
[5 empty] | Unit Price | Total Amount | QTY | Amount | QTY | Amount | QTY | Amount
[5 empty] | INR | INR
STRUCTURE STEEL WORK
a | Cost of all materials, labour, equipment / tools & plants required, conveyance, infrastructure facilities required etc. at all heights and levels.
b | Work at any depth below ground level or any height above ground level and at all levels, heights & elevation and location.
c | Weight of steel will be the measured on weight basis in accordance with IS 1200, but no wastage will be considered.
d | Fabrication of the structural steel items shall be completed in all respects including all associated costs up to delivery at site.
e | Erection of fabricated items shall be carried out including lifting, placing in position, jointing and painting as specified in the Bill of Quantities. No extra cost shall be paid for temporary bracings wherever required.
f | All welding with electrodes shall be in accordance with IS specification and as approved.
h | The rate to include the cost of all materials, labour, tools, tackles, devices and plants, wastage etc., as per specification and drawings complete
i | Rate to include shims and packing pieces. No extra on this account will be paid for and rate to include preparation of fabrication drawings for Employer / OE & PMCs approval.
j | The structural steel work shall include built up sections and girders, with gusset plates, base plates, cleats, installing inserts etc., as per drawings. Cost to include fabricating necessary Gusset Plates, Cleats, seating angles, etc., to the required size, shape, alignment etc., as per the drawings
k | 1 Coat (50 micron) of Zinc phosphate primer shall be applied at the welded joints/welded surfaces for MS work
l | Base Primer to be applied over all exposed surfaces of the Entire MS work
m | Quantities verified by structural consultant/Client In-charge shall be payable only.
1.1 | Providing, fabricating and erecting structural steel beams, columns, shear walls, canopy, MEP services, ramps, insert plates, embedded plates, shear angles, base plates, fasteners, stud connectors etc., of readymade / built-up / rolled sections of grade upto Fy 240-450 in position at all levels and at all heights as specified in the drawings conforming to IS 226/800; The rate shall include base Primer and applying one or Two coat of Anti-Corrosive Fire Retardent Paint color as approved to the Entrie MS work such as Members/walls & beams; main steel, fasteners and miscellaneous items; The rate shall also include the provision of Mobile crane, Lifting crane, scaffolding etc. for erection as required and described elsewhere; rate is deemed to include all wastages; steel procurement price shall be considered as basic rate provided and any variation between the actual procurement price and this rate shall be paid extra; if steel is provided as free issue, the cost of such steel computed at the basic rate shall be deducted from the overall price after adjustment of rolling margins only; no adjustments shall be permitted for wastages and same shall be considered as included in the rate.
a | Fy-240 Grade MS TUBE (Rolled) |  | 2.94 | MT
b | MS PLATE |  | - | MT | 1,50,000 | 4,41,000 | 3.266 | 489900
[5 empty] | 1,73,000 | -
2 | Anchoring Work
Providing, scanning, drilling and driving of various Dia and Shape Anchor rods / Anchor fastener of HILTI (Chemical anchors - RE500) including all other consumables like chemicals, foils, Grouting materials, using HILTI / Bosch make machinery, tools & plants, all accessories etc. complete at all levels as directed by the Engineer-in-charge.
a | RE 500-Hilti Anchor-10mm dia (150mm anchoring) |  | 140 | Nos
b | RE 500-Hilti Anchor-16mm dia (150mm anchoring) |  | - | Nos | 750 | 1,05,000 | 140 | 105000
|  |  |  | ₹ | 950 | -
|  |  |  | ₹ | Total Basic | 5,46,000 |  | 594900
|  |  |  | ₹ | Taxes | 98280
[5 empty] | Price [A+B] | 6,44,280

## LIGHT FITTING JMR RA Bill 09
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.06.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : Electrical CIP Lounge T3 Lok
RA-09 MEASUREMENT SHEET OF LIGHT FITTING
S. No. | Item. Code | Specification | Description | W | H | Unit | Nos | Qty.
1 |  | Electrical
Recessed Downlighter - 9W Ceiling light fixture LED Recessed 9W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each
|  | Male Washroom |  |  |  | Nos | 8
|  | Fmale Washroom |  |  |  | Nos | 6
|  | Handycap |  |  |  | Nos | 2
|  | Electrical Room |  |  |  | Nos | 2
|  | Total Qty |  |  |  |  | 18
|  | WO Qty |  |  |  |  | 16 | Nos
|  | RA 08Qty |  |  |  |  | 16
|  | RA 09Qty |  |  |  |  | 0
|  | RA 09 Extra Qty |  |  |  |  | 2
Recessed Downlighter - 15W Ceiling light fixture LED Recessed 15W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each
|  | Admin Room |  |  |  | Nos | 2
|  | Total Qty |  |  |  |  | 2
|  | WO Qty |  |  |  |  | 2 | Nos
|  | RA 08Qty |  |  |  |  | 2
|  | RA 09Qty |  |  |  |  | 0
|  | RA 09 Extra Qty |  |  |  |  | 0
Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 62mm Base Price @ 810/- each (All the Taxes Inclusive)
|  | Admin Room |  |  |  | Nos
|  | Total Qty |  |  |  |  | 0
|  | WO Qty |  |  |  |  | 6 | Nos
RA 08Qty
RA 09Qty
Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 6 W 4000 K LED Recessed 6W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 1045/- each
|  | Male Washroom |  |  |  | Nos | 0
|  | Fmale Washroom |  |  |  | Nos | 0
|  | Passege |  |  |  | Nos | 7
|  | Baar Area |  |  |  | Nos | 4
|  | Premium Lounge |  |  |  | Nos | 11
22
|  | Total Qty |  |  |  |  | 22
|  | WO Qty |  |  |  |  | 22 | Nos
|  | RA 08Qty |  |  |  |  | 20
|  | RA 09Qty |  |  |  |  | 2
Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 450/- each (All the Taxes Inclusive)
|  | Baar Counter Wall |  |  |  | Nos | 16
|  | Recepsion Wall |  |  |  | Nos | 13
29
|  | Total Qty |  |  |  |  | 29
|  | WO Qty |  |  |  |  | 29 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 29
Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 450/- each (All the Taxes Inclusive)
|  | Spa Room |  |  |  | Nos | 29
29
|  | Total Qty |  |  |  |  | 29
|  | WO Qty |  |  |  |  | 31 | Nos
|  | RA 08Qty |  |  |  |  | 6
|  | RA 09Qty |  |  |  |  | 23
Recessed Downlighter - LED recessed luminaire system power 18W, colour temperature of 4000K, L = 595mm, B = 595mm, H = 70mm Base Price @ 2500/- each
|  | Kitchen Ceilling Light |  |  |  | Nos | 5
5
|  | Total Qty |  |  |  |  | 5
|  | WO Qty |  |  |  |  | 5 | Nos
|  | RA 08Qty |  |  |  |  | 5
RA 09Qty
Profile Strip Light - FLEXION LED STRIP 22 W Warm Daylight (WDL) 4000K (5 Meter roll) + LED Driver LED Profile Strip Light , colour temperature of 3000- 4000K Base Price Strip @ 810/- Each Roll 5mtr Base Price Profile @ 550/- Per mtr
|  | Premium Lounge Cove Light |  | Rmt |  |  | 26.2
|  | Dinning Area Cove Light |  | Rmt |  |  | 11.5
|  | Recepsion Cove Light |  | Rmt |  |  | 6.5
|  | Male Washroom Cove Light |  | Rmt |  |  | 14
|  | Fmale Washroom Cove Light |  | Rmt |  |  | 11.4
|  | Recepsion Table Skerting |  | Rmt |  |  | 2.5
|  | Baar Table Skerting |  | Rmt |  |  | 11
|  | Dinning Area Table Skerting |  | Rmt |  |  | 28.5
|  | Spa Rom Cove Light |  | Rmt |  |  | 9
|  | Admin Room Cove Light |  | Rmt |  |  | 4
|  | Male Washroom Behind Mirror |  | Rmt |  |  | 4.8
|  | Fmale Washroom Behind Mirror |  | Rmt |  |  | 4.4
|  | Handycap Washroom Behind Mirror |  | Rmt |  |  | 3.5
137.3
|  | Total Qty |  |  |  |  | 137.3
|  | WO Qty |  |  |  |  | 175 | Rmt
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09Qty |  |  |  |  | 137.3
Recessed Floor Light - LED Recessed 5W LED, colour temperature of 3000K- 4000K, Ø = 90mm Base Price Strip @ 2500/- Each
|  | Premium Lounge |  | Nos |  |  | 2
|  | Recepsion Garden |  | Nos |  |  | 4
|  | Baar Area Garden |  | Nos |  |  | 3
|  | Dinning Area Garden |  | Nos |  |  | 2
|  | Kitchen Passage |  | Nos |  |  | 1
12
|  | Total Qty |  |  |  |  | 12
|  | WO Qty |  |  |  |  | 12 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09Qty |  |  |  |  | 12
Table Lamp : Take a deep breath and move steadily while I fashion your spaces. A beauty that’s warm & attractive, growing on you slowly and steadily beyond comprehension and expression. A beauty that’s clad in black and gold, she’s sheer sophistication and elegance. Product Dimensions - Overall Dimensions- Height: 22.5" Length: 15" Width: 15" Shade Dimensions- Height: 6" Diameter: 15" Base Dimensions- Height: 1" Diameter: 9.5" Holder & Plug TypeE -27 Recommended BulbL ED Only. No. of Bulb Holders1
|  | Premium Lounge Table |  | Nos |  |  | 11
11
|  | Total Qty |  |  |  |  | 11
|  | WO Qty |  |  |  |  | 11 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 11
WALL DECORATIVE LIGHT : Marvel at this innovative design featuring an A classy leaf shaped, multicolor body paint with day lamp highlight the ornate finishing doubles as a wall hanging too. Switch it on for a warm glow, or let it add subtle elegance to your walls as it rests. Leaf metal shade that cover back LED lamp, The frame in diffrent color shade, housing the orb of light within itself as well. It's an incredible wall light for lounges. No. of Bulb Holders :1 Holder & Plug Type :E -27 Recommended Bulb :4 0 Watts (Max) Package Contents :1 Premium Wall Light. Bulb Provided: LED bulb Provided Product Material : Metal Body in Matte multicolor color Finish as approved. Product Weight (in Kg)0 .5 Country Of Origin: custom / Imported Size & Shape : 225mm high x 100mm wide, Leaf shape Base Range : Rs. 2900/- each
|  | Premium Lounge Wall |  | Nos |  |  | 32
|  | Baar Area Wall |  | Nos |  |  | 32
|  | Dinning Area Wall |  | Nos |  |  | 16
80
|  | Total Qty |  |  |  |  | 80
|  | WO Qty |  |  |  |  | 75 | Nos
|  | RA 08Qty |  |  |  |  | 72
|  | RA 09Qty |  |  |  |  | 3
|  | RA 09 Extra Qty |  |  |  |  | 5
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR BAR AREA
|  | L1 : Size 620mm Long x 275mm wide x 1 each |  |  |  | Nos | 11
|  | Total Qty |  |  |  |  | 11
|  | WO Qty |  |  |  |  | 11 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 11
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR BAR AREA
|  | L2 : Size395/530/620mm Long x 175/225/275mm wide x 1 each |  |  |  | Nos | 12
|  | Total Qty |  |  |  |  | 12
|  | WO Qty |  |  |  |  | 10 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 10
|  | RA 09 Extra Qty |  |  |  |  | 2
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR HIGH COUNTER AREA
|  | L1 : Size 615/700/800mm Long x 275/325/350mm wide x 1 each |  |  |  | Nos | 17
|  | Total Qty |  |  |  |  | 17
|  | WO Qty |  |  |  |  | 16 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 16
|  | RA 09 Extra Qty |  |  |  |  | 1
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR HIGH COUNTER AREA
|  | L2 : Size 475/620/700/800/810mm Long x 225/275/325/350/375mm wide x 1 each |  |  |  | Nos | 27
|  | Total Qty |  |  |  |  | 27
|  | WO Qty |  |  |  |  | 15 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 15
|  | RA 09 Extra Qty |  |  |  |  | 12
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR RECEPTION AREA
|  | L1 - Ceiling : Size 440/485/585/585mm Long x 130/190/225/255mm wide x 1 each |  |  |  | Nos | 15
|  | Total Qty |  |  |  |  | 15
|  | WO Qty |  |  |  |  | 17 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 15
CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light
FOR RECEPTION AREA
|  | L2 - Ceiling : Size 290/440/525/640/mm Long x 110/160/190/255mm wide x 1 each |  |  |  | Nos | 15
|  | Total Qty |  |  |  |  | 15
|  | WO Qty |  |  |  |  | 17 | Nos
RA 08Qty
|  | RA 09Qty |  |  |  |  | 15

## Abstract LIGHTS & PANELS
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Code / Area Specified | Qty. | UoM | Impulse Branding |  | RA-08 |  | RA 09 |  | Extra Qty RA 09 |  | Cumulative |  | Variance
[5 empty] | Unit Price | Total Amount | QTY | Amount | Qty | Amount | Qty | Amount | QTY | Amount | QTY | Amount
[5 empty] | INR | INR
LIGHT FITTING - Supply & Installation Only (Brands/Make : Havells / Philips /
Supply, assembling, erection, connecting, testing and commissioning of the following LED light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required
1 | Recessed Downlighter - 9W Ceiling light fixture LED Recessed 9W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each |  | 16 | nos | 1560 | 24960 | 16 | 24960 | 0 | 0 | 2 | 3120
2 | Recessed Downlighter - 15W Ceiling light fixture LED Recessed 15W LED, colour temperature of 3000K-4000K, Ø = 100mm Base Price @ 1020/- each |  | 2 | nos | 1750 | 3500 | 2 | 3500
3 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 62mm Base Price @ 810/- each (All the Taxes Inclusive) |  | 6 | nos | 1250 | 7500
4 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 6 W 4000 K LED Recessed 6W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 1045/- each |  | 22 | nos | 1500 | 33000 | 20 | 30000 | 2 | 3000
5 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 9 W 4000 K LED Recessed 9W LED, colour temperature of 3000K-4000K, Ø = 78mm Base Price @ 1395/- each |  | 0 | nos | 1850 | 0
6 | Recessed Downlighter - LED CRYSTA COB SWIVEL SPOTLIGHT 3 W 4000 K LED Recessed 3W LED, colour temperature of 3000K-4000K, Ø = 71mm Base Price @ 450/- each (All the Taxes Inclusive) |  | 31 | nos | 750 | 23250 | 6 | 4500 | 23 | 17250
7 | Recessed Downlighter - ASTRAL ROUND 2 W Warm Daylight (WDL) 4000 K LED Recessed 2W LED, colour temperature of 3000K-4000K, Ø = 41mm Base Price @ 215/- each (All the Taxes Inclusive) |  | 29 | nos | 430 | 12470 |  |  | 29 | 12470
8 | Recessed Downlighter - LED recessed luminaire system power 18W, colour temperature of 4000K, L = 595mm, B = 595mm, H = 70mm Base Price @ 2500/- each |  | 5 | nos | 3600 | 18000 | 5 | 18000
9 | Profile Strip Light - FLEXION LED STRIP 22 W Warm Daylight (WDL) 4000K (5 Meter roll) + LED Driver LED Profile Strip Light , colour temperature of 3000- 4000K Base Price Strip @ 810/- Each Roll 5mtr Base Price Profile @ 550/- Per mtr |  | 175 | Per Mtr | 420 | 73500 |  |  | 137.3 | 57666
10 | Recessed Floor Light - LED Recessed 5W LED, colour temperature of 3000K- 4000K, Ø = 90mm Base Price Strip @ 2500/- Each |  | 12 | nos | 3200 | 38400 |  |  | 12 | 38400
11 | DECORATIVE LIGHTING - Supply & Installation Only (Brand & Make : Zolux / Truemoon / White Teak (Asian Paints) / Jainsons / Jaquar) |  |  |  |  | 0
12 | Table Lamp : Take a deep breath and move steadily while I fashion your spaces. A beauty that’s warm & attractive, growing on you slowly and steadily beyond comprehension and expression. A beauty that’s clad in black and gold, she’s sheer sophistication and elegance. Product Dimensions - Overall Dimensions- Height: 22.5" Length: 15" Width: 15" Shade Dimensions- Height: 6" Diameter: 15" Base Dimensions- Height: 1" Diameter: 9.5" Holder & Plug TypeE -27 Recommended BulbL ED Only. No. of Bulb Holders1 Bulb ProvidedN ot Provided Package Contents1 Table Lamp. Product MaterialT he Metal in Matte Gold Finish with Metal Base and Fabric Shade. Product Weight (in Kg)4 .1 Country Of Origin: Imported Base Range : Rs. 16000/- each |  | 11 | Nos | 23000 | 253000 |  |  | 11 | 253000
13 | WALL DECORATIVE LIGHT : Marvel at this innovative design featuring an A classy leaf shaped, multicolor body paint with day lamp highlight the ornate finishing doubles as a wall hanging too. Switch it on for a warm glow, or let it add subtle elegance to your walls as it rests. Leaf metal shade that cover back LED lamp, The frame in diffrent color shade, housing the orb of light within itself as well. It's an incredible wall light for lounges. No. of Bulb Holders :1 Holder & Plug Type :E -27 Recommended Bulb :4 0 Watts (Max) Package Contents :1 Premium Wall Light. Bulb Provided: LED bulb Provided Product Material : Metal Body in Matte multicolor color Finish as approved. Product Weight (in Kg)0 .5 Country Of Origin: custom / Imported Size & Shape : 225mm high x 100mm wide, Leaf shape Base Range : Rs. 2900/- each |  | 75 | Nos | 3600 | 270000 | 72 | 259200 | 3 | 10800 | 5 | 18000
14 | CEILING DECORATIVE LIGHTS : Providing, making & Installing The newest ddition custom curvy designs lights, custom Sleepover draws you in with its curvaceous profile, glistening gold finish and long lamp life of LEDs. This swoon- worthy beauty is perfect for all interiors and seamlessly blends across settings. Introduce the flexibility of shapes and ease of innovative features to your entryway with this modern light. The silicone diffuser houses the LEDs, thus creating a sleek appearance. Switch the colour temperatures of this dimmable LED light to suit your changing moods with the help of the remote that comes with the unit. Browse through our extensive range of LED chandeliers for more. ColourG old or As per Approved Temperature3 000K to 6500K Wattage5 Watts, 30 Watts Color TemperatureD ay Light Holder & Plug TypeD immable Built in LED Package Contents1 Premium Dimmable Built-In LED With Remote Control, Bulb ProvidedD immable Built in LED Product Material: Metal Ceiling Cup In Gold Finish or as approved with Flexible Plastic Body in Good Finish and Silicon Diffuser. Product Weight (in Kg)0 .5 - 2.8 Country Of Origin: cutom / Imported Base Range : Rs. 7500/- small upto 400mm long, & Rs. 9500/- mid upto 600mm long & Rs. 12500/- 800mm long each |  |  |  |  | 0
15 | FOR BAR AREA |  |  |  |  | 0
16 | L1 : Size 620mm Long x 275mm wide x 1 each |  | 11 | Nos | 11500 | 126500 |  |  | 11 | 126500
17 | L2 : Size395/530/620mm Long x 175/225/275mm wide x 1 each |  | 10 | Nos | 10500 | 105000 |  |  | 10 | 105000 | 2 | 21000
18 | FOR HIGH COUNTER AREA |  |  |  |  | 0
19 | L1 : Size 615/700/800mm Long x 275/325/350mm wide x 1 each |  | 16 | Nos | 9500 | 152000 |  |  | 16 | 152000 | 1 | 9500
20 | L2 : Size 475/620/700/800/810mm Long x 225/275/325/350/375mm wide x 1 each |  | 15 | Nos | 15600 | 234000 |  |  | 15 | 234000 | 12 | 187200
21 | FOR RECEPTION AREA |  |  |  |  | 0
22 | L1 - Ceiling : Size 440/485/585/585mm Long x 130/190/225/255mm wide x 1 each |  | 17 | Nos | 15600 | 265200 |  |  | 15 | 234000
23 | L2 - Ceiling : Size 290/440/525/640/mm Long x 110/160/190/255mm wide x 1 each |  | 17 | Nos | 15600 | 265200 |  |  | 15 | 234000
24 |  |  |  |  | Sub Total | 1905480 |  | 340160 |  | 1478086 |  | 238820
25
26
27
28
29
30

## Civil JMR RA Bill 09
IMPULSE BRANDING SOLUTIONS
03/204, SUNDAR DARSHAN CHSL, MIRA BHAYANDER, THANE - 401107
Date:- 22.06.2024
Project : Adani CIP Lounge T3 Lok
W/O No : SKPL/23-24/001793
Name of the Work : Electrical CIP Lounge T3 Lok
RA-09 MEASUREMENT SHEET OF Civil Int
S. No. | Item. Code | Specification | Description | W | H | Unit | Nos | Qty.
1 |  | Civil & Int RA Bill 09
1 |  | CORION CLADDING : Providing and fixing 12mm thick Solid surface ( Corian ) for Basin Counter/Ledge/Jamb/cill etc fixed with adhesive of approved make including jointing with adhesive mixed with pigment to matching the shade of solid surface complete as per drawing .including edge chamfering, buffing, polishing complete in all respect. ( Basic cost of solid surface ( Corian ) @ Rs. 750/- Sft )( Actual size to be measured & paid ).
|  | Baar Area | Sqm | 3.4 | 2.2 | 1 | 7.48
|  | Recepsion | Sqm | 1.74 | 3.2 | 1 | 5.568
|  | Premium Lounge | Sqm | 1.74 | 2.86 | 1 | 4.9764
|  | Total Qty |  |  |  |  | 18.0244
|  | WO Qty |  |  |  |  | 35.6 | Sqm
|  | RA 08Qty |  |  |  |  | 30.8656
|  | RA 09 Qty |  |  |  |  | 4.7344
2 |  | MARBLE STRIPS : Providing and fixing Marble strip work in existing flooring using diffrent color shade and sizes in width strips of 16-18 mm thick, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:4 (1 cement : 4 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual Lenght of stone strps to be measured & paid ). Cost also include the Protection covering till handover with polythin+POP as per advised by the Project Incharge.
| a. | Marble Flooring Strips Type 1 upto 25-45mm wide : Base Price of Marble @ 900/- Per sft, For Reception area | site specific | Rmt
|  | Baar Area |  |  |  |  | 5.85
|  | Recepsion |  |  |  |  | 5.42
11.27
|  | Total Qty |  |  |  |  | 11.27
|  | WO Qty |  |  |  |  | 10 | 10
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 1.27
| b. | Marble Flooring Strips Type 1 upto 75-150mm wide : Base Price of Marble @ 900/- Per sft, For Reception area | site specific | Rmt
|  | Baar Area |  |  |  |  | 16.78
|  | Recepsion |  |  |  |  | 10.84
27.62
|  | Total Qty |  |  |  |  | 27.62
|  | WO Qty |  |  |  |  | 10 | 10
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 17.62
MARBLE CLADDING : Providing and fixing Marble work 16-18 mm thick, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge.
| a. | Marble Cladding Type 1 : Base Price of Marble @ 450/- Per sft, | For counter Splash area
|  | Total Qty |  |  |  |  | 6.84
|  | WO Qty |  |  |  |  | 11.88 | Sqm
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 6.84
MARBLE FLOORING : Providing and fixing Marble work 16-18 mm thick, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:4 (1 cement : 4 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with polythin+POP as per advised by the Project Incharge.
| a. | Marble Flooring Type 1 : Base Price of Marble @ 450/- Per sft,
|  | Washroom Passage |  |  |  |  | 3.57
|  | Total Qty |  |  |  |  | 3.57
|  | WO Qty |  |  |  |  | 263.86 | Sqm
|  | RA 02Qty |  |  |  |  | 257.05
|  | RA 09 Qty |  |  |  |  | 3.57
MARBLE CLADDING : Providing and fixing Marble work 16-18 mm thick, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge.
| c. | Marble Skirting upto 100mm high : Base Price of Marble @ 1200/- Per sft, | site specific
|  | Total Qty |  |  |  |  | 0
|  | WO Qty | [5 empty] | Rmt
|  | RA 02Qty |  |  |  |  | 82.36
RA 09 Qty
MARBLE DESIGNER CLADDING : Providing and fixing Marble designer work 16-18 mm thick marble with random size cut pcs in 200/300/400mm high x 75/100/125mm in width with making taper cut on edge to ake 4mm wide groove on vertical/horizontal as per design, all the surface, edges, V groove shall be mirror polished, all the marble will be jet water machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone area legth x height to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge.
| a. | Marble Designer Cladding Type 1 : Base Price of Marble @ 450/- Per sft, | for toilets wall
|  | Male Washroom |  |  |  |  | 34.37
|  | Fmale Washroom |  |  |  |  | 19.62
|  | Desable Washroom |  |  |  |  | 27.17
|  | Total Qty |  |  |  |  | 81.16
|  | WO Qty |  |  |  |  | 67.14 | Sqm
RA 02Qty
|  | RA 09 Qty |  |  |  |  | 14.02
Providing & fixing Carpet / Rug of Handmade / Machine tuffted with Pile Yarn (80% wool & 20% nylon or 100% Viscose/Bamboo silk) Dyed in Eco freindly pigment color with Enviromental freindly standards. Sanitized with stain free and Alergy resistant quality. Carpet should have warranty of Minimum 10-15 year and installed by the expert installer or manufacturer recommended agency. (1500GSM 12 to 14mm thick Nylon Printed Customized or Axminster) with Protection covering till Handover of the Project.
| Karpet | Baar Area |  |  |  |  | 32.13
|  | Premium Lounge |  |  |  |  | 37.51
|  | Spa Room |  |  |  |  | 15.53
0.68
|  | Total Qty |  |  |  |  | 85.85
|  | WO Qty |  |  |  |  | 86.3 | Sqm
RA 02Qty
|  | RA 09 Qty |  |  |  |  | 85.85
MARBLE COMBINATION FLOORING : Providing and fixing Marble combination work with 20mm thick, mirror polished, prepolished, water jet cuting of required size and pattern, approved shade, colour and texture inlay as per the design approved by the Architect, laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. Marble stone should be of well known brand with A+ Grade of complies use the Moisture absorption test as per IS 1124 & Hardness test is done as per Mho’s scale and Specific gravity test is done as per IS 1122.( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge.
|  | Kitchen Ramp |  |  |  |  | 2.76
|  | Washroom Ramp |  |  |  |  | 2.16
|  | Total Qty |  |  |  |  | 4.92
|  | WO Qty |  |  |  |  | 5 | Sqm
RA 02Qty
|  | RA 09 Qty |  |  |  |  | 4.92
KOTA STONE FLOORING : Provide and lay 25mm thick, machine cut and polished Kota Stone of aprroved colour and texture laid over 20 mm thick base cement mortar 1:4 (1 cement : 4 coarse sand), joints treated with white cement, mixed with matching pigment, epoxy touch ups, including rubbing polihing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with polythin+POP as per advised by the Project Incharge. ( Basic cost of Granite stone @ Rs. 65/- per sft)
|  | Eelctric Room |  |  |  |  | 4.37
|  | Total Qty |  |  |  |  | 4.37
|  | WO Qty |  |  |  |  | 26.67 | Sqm
|  | RA 08Qty |  |  |  |  | 23.87
|  | RA 09 Qty |  |  |  |  | 4.37
LAMINATED DOOR SHUTTER : Providing and fixing 38 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both sides of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, vision slit as per design with 6mm thick glass with wooden beading ( white ash wood ), handles,motrise dead lock with one side key knob cylinder finish in rose gold SS etc. complete in all respect. .( Basic cost of laminate @ Rs. 90/- sft ) ( Actual size of shutter to be measured & paid ).
|  | SPA | Sqm |  | 2.4 | 1 | 2.4
|  | Admin | Sqm |  | 2.4 | 0.9 | 2.16
4.56
|  | Total Qty |  |  |  |  | 4.56
|  | WO Qty |  |  |  |  | 5.28 | Sqm
|  | RA 08Qty |  |  |  |  | 3.648
|  | RA 09 Qty |  |  |  |  | 0.912
LAMINATED DOOR SHUTTER : Providing and fixing 38 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both sides of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, vision slit as per design with 6mm thick glass with wooden beading ( white ash wood ), handles,motrise dead lock with one side key knob cylinder finish in rose gold SS etc. complete in all respect. .( Basic cost of laminate @ Rs. 90/- sft ) ( Actual size of shutter to be measured & paid ).
|  | Toilet | Nos |  | 3 |  | 3
3
|  | Total Qty |  |  |  |  | 3
|  | WO Qty |  |  |  |  | 3 | Nos
|  | RA 08Qty |  |  |  |  | 2.4
|  | RA 09 Qty |  |  |  |  | 0.6
LAMINATED DOOR SHUTTER : Providing and fixing 38 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both sides of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, vision slit as per design with 6mm thick glass with wooden beading ( white ash wood ), handles,motrise dead lock with one side key knob cylinder finish in rose gold SS etc. complete in all respect. .( Basic cost of laminate @ Rs. 90/- sft ) ( Actual size of shutter to be measured & paid ).
| b. | Double Leaf Door - 1500/1800mm Long x 2400mm high | For Merchandise wall |  | 1 |  | 1
1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 1
LAMINATED DOOR SHUTTER : Providing and fixing 38 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both sides of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, vision slit as per design with 6mm thick glass with wooden beading ( white ash wood ), handles,motrise dead lock with one side key knob cylinder finish in rose gold SS etc. complete in all respect. .( Basic cost of laminate @ Rs. 90/- sft ) ( Actual size of shutter to be measured & paid ).
| b. | Kitchen | Sqm | 1.2 | 2.4 |  | 2.88
|  | Electrical Room | Sqm | 0.9 | 2.4 |  | 2.16
5.04
|  | Total Qty |  |  |  |  | 5.04
|  | WO Qty |  |  |  |  | 8.18 | Sqm
|  | RA 08Qty |  |  |  |  | 4.032
|  | RA 09 Qty |  |  |  |  | 1.008
LAMINATED SHAFT SHUTTER : Providing and fixing 25 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both faces of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, etc. complete in all respect.( Basic cost of laminate @ Rs. 970/-Sqm) ( Actual size of shutter to be measured & paid ). ( Shaft & Janitor Room Entry Door )
|  | Janitor Room |  | 2.7 |  | 1.6 | 4.32
|  | Total Qty |  |  |  |  | 4.32
|  | WO Qty |  |  |  |  | 4.75 | Sqm
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 4.32
FRAMED GLASS PARTITION : Providing and installation of framed allumunium with vision glass partition sytem of approved series and brand as per approved list of make, fixed glass partition using 10mm thick Toughened glass in proprietary natural anodised approved aluminium sections with Concealed sealing (No visible Gaskets/Seals) with acoustic. The profile will have Carpert Groove at the Bottom on both sides for accommodating max. 8mm carpets. Glass to be fixed with help of Proprietary Stability GRIPPER Clamp to have a stable system. It should consists of intermediate slim junction profiles for Glass to Glass vertical joints, 90 Degree L Junction and T Junction profiles suitably to be used as per room configuration designs. No VISIBLE Clip Lines to provide clutter free view at both side of section. The Glass to be Offset mounted towards outer edge leading to minimum aluminium frame on one side. Optional Profile Bottom Seal pair for additional acoustic if required. All Profiles are min 1.5mm thickness excluding 20 microns of Anodizing, Standards applicable • Structural stability test accordance to BS 5234: Part2:1992 & EN 1991-1-1:2002 • Acoustic test for sound insulation in accordance to DIN EN ISO 10140-2 ASTME-E 90
| a. | Single Glazed Partition, Size 50mm wide x 30mm high, color as approved | Sqm
|  | Recepsion | Sqm |  |  |  | 8.32
|  | Total Qty |  |  |  |  | 8.32
|  | WO Qty |  |  |  |  | 4.38 | Sqm
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 3.94
| b. | Single Glazed Partition, Size 100mm wide x 30mm high, color as approved
|  | P Lounge | Sqm | 2.16 | 2.7 | 1 | 5.832
|  | Dinning Area | Sqm | 2.96 | 2.7 | 1 | 7.992
|  | Dinning Area | Sqm | 2.79 | 2.7 | 1 | 7.533
|  | Spa Room | Sqm | 2.6 | 2.7 | 1 | 7.02
28.377
|  | Total Qty |  |  |  |  | 28.377
|  | WO Qty |  |  |  |  | 28.51 | Sqm
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 28.377
| 7 | Providing & fixing Hydraulic sleek door closer of approved make including all fixing arrangement complete in all respect. Door weight capacity upto 80kg, with 10year manufacturer warranty complete as per design approved.
|  | Admin,SPA, Kitchen,Electrical, | Nos |  |  |  | 4
|  | Total Qty |  |  |  |  | 4
|  | WO Qty |  |  |  |  | 4 | Nos
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 4
| 8 | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in rose gold SS ) of approved make including all fixing arrangement complete in all respect.
|  | Toilets, spa,Kitchen | Nos |  |  |  | 7
|  | Total Qty |  |  |  |  | 7
|  | WO Qty |  |  |  |  | 5 | Nos
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 2
| 11 | Providing & fixing 50mm dia SS 304 grade (finish : As per approved ) 600mm Long H type Handle including all the accessories and fitting as per requirement complete.
|  | Kitchen & Jonithor | Nos |  |  |  | 2
|  | Total Qty |  |  |  |  | 2
|  | WO Qty |  |  |  |  | 2 | Nos
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 2
Providing & fixing 1.2mm thick aluminium. Skirting PVDF coated (100mm height rose gold finish ) / anodised as per approved sample over existing partition including all fixing arrangement complete in all respect. ( Basic cost Aluminium Skirting @ Rs. 450/-Rmtr)
|  | Oute Side Wall | Rmt |  |  |  | 8.87
|  | Total Qty |  |  |  |  | 8.87
|  | WO Qty |  |  |  |  | 55 | Rmt
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 8.87
Providing and fixing over head storage with necessary shelves as per design made out of 19mm thick Natural Fiber Polymer composite Board/Wood Material ply fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with 1mm thick laminate including required shelves, shutters and required hardware like handle, knobs, magnetic catcher, hinges, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface laminate@ Rs.90/-Sft
|  | Admin Room | Sqm |  | 0.925 | 1.85 | 1.7113
|  | Total Qty |  |  |  |  | 1.7113
|  | WO Qty |  |  |  |  | 1.73 | Sqm
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 1.7113
Providing and fixing Under Counter storage with necessary drawers & Shelves as per design made out of 19mm thick Marine ply board structure fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with designer tile, storage includes required shutter / drawer storage unit with required shelves , shutters with required hardware like concealed channel / handle, knobs, magnetic catcher, drawer lock, hinges, shutter lock, drawer channel etc. all are superior quality of approved make & 100mm high Gold Plated finish Aluminium skirting at floor level complete in all respect. also the Storage top will be finish with Marble top in 20mm thickness with dimaond polish all over surface and edge to be double strip with gola polish complete in all respact of detail drawing. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, , Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
|  | Baar Area | Nos | 1 |  |  | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09 Qty |  |  |  |  | 0.3
|  | For Spa basin counter | Nos | 1 |  |  | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 10Qty |  |  |  |  | 0.3
Providing and fixing partly open partly closed Servery counter storage as per drawing made out of 19mm thick BWP / Marine board structure fixed with the help of all necessary hardware like nail and fasteners and all closed internal area of storage to be finished with 0.8mm thick laminate and open area with external finish of 1mm thick SS Sheet cladding of triangle shape emboss texture with white Gold Leafing antique Coating finish all over apart shelf as marble with double patti edge will be fixed with diamond polish shelves for open space, All the external surface area shall be wrapped and finished in designer tile & top surface of survery storage to be finished with plain polish Marble fixed with adhesive & 100mm high Gold Plated finish Aluminium skirting at floor level, including required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, drawer channel, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
| a | Size 5500mm long x 600mm deep x 850mm high - | For kitchen outside servery area |  |  |  | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09 Qty |  |  |  |  | 0.3
| b | Size 3529mm long x 600mm deep x 850mm high - | For Bar area open lounge |  |  |  | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09 Qty |  |  |  |  | 0.3
| c | Size 2000mm long x 600mm deep x 850mm high - | For P Lounge
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09 Qty |  |  |  |  | 0.3
Providing and fixing ISLAND Counter storage as per drawing, Storage as per drawing made out of 19mm thick BWP / Marine board structure fixed with the help of all necessary hardware like nail and fasteners and all closed internal area of storage to be finished with 0.8mm thick laminate and open area with external finish of 1mm thick SS Sheet cladding of triangle shape emboss texture with white Gold Leafing antique Coating finish all over apart shelf as marble with double patti edge will be fixed with diamond polish shelves for open space (If Any), All the external surface area shall be wrapped and finished in designer tile & top surface of survery storage to be finished with plain polish Marble fixed with adhesive & 100mm high Gold Plated finish Aluminium skirting at floor level, including required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, drawer channel, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
| a | Size 4000mm long x 1200mm deep x 850mm high - kitchen outside servery area |  |  |  |  | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09 Qty |  |  |  |  | 0.3
| 11 | Providing and fixing High counter Console as per drawing, structure made out of 19mm thick BWP / Marine board construct in boxing form and fixed to existing wall/panneling fixed with the help of all necessary hardware like nail and fasteners all internal back exposed area surface to be finished with 1mm thick laminate , external front 1mm thick SS Sheet cladding of triangle shape emboss texture with white Gold Leafing antique Coating finish & top surface to be finished with plain diamond polish Marble fixed with adhesive & 100mm high Gold plated finish Aluminium skirting at floor level all around , (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface SS Texture Emboss Antique finish coating Sheet @ Rs.2500/- per Sft, Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
| a | Size 7753mm long x 400mm wide from top with below covered boxing structure x 1050mm high | for Around Large Tree high counter |  |  |  | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09 Qty |  |  |  |  | 0.3
| 12 | Providing and fixing High Counter Ledge as per drawing, made out of 19mm thick BWP Board / Ply structure construct in L form with latak 35mm high in front to covered the base supported MS painted 25x25mm angle frames fixed at maximum 1200mm c/c with the help of all necessary hardware like nail and fasteners. all the Ply surface latak / top finished with plain Marble with diamond polish fixed with adhesive complete as per detail drawing. (Base Price of Marble @ Rs. 450/- per sft )
| a | Size 3935mm long x 400mm wide from Top | For High counter Ledge |  |  |  | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09 Qty |  |  |  |  | 0.3
| 13 | Providing and fixing Reception Table ( Size : 1000mm long x 1000mm deep x 750/1050mm high) made out of 19mm thick BWP Board / Ply structure including necessary hardware of superior quality, structure made in double ht form which make front portion along with sides finished in Italion Marble finished with flutted pattern all polish, then worktop / double ht vertical screen in Acrylic surface finish of 12mm thick on base ply with complete buffing /rubbing as per design. front facade, sides & top finish with Italian marble stone of approved make, shade & texture including all fixing arrangement ,grinding polishing, edge chamfering & polishing & all internal surface to be finished with 0.8mm thick laminate & at floor level 100mm high skirting & top & sides edging finished with PVD coated color as approved finish in aluminium . complete in all respect. ( Basic cost of internal laminate @ Rs.28/- sft & external laminate @ Rs90/-Sft & Italian marble stone @ Rs. 1200/- sft + 500 per sft for flutted CNC cutting) & (Acrylic surface @ 900/- per sft, Basic cost PVD finish Aluminium Skirting @ Rs. 450/-Rmtr,)
|  | Recepsion Counter | Nos |  |  |  | 2
|  | Total Qty |  |  |  |  | 2
|  | WO Qty |  |  |  |  | 2 | Nos
|  | RA 08Qty |  |  |  |  | 1.4
|  | RA 09 Qty |  |  |  |  | 0.6
| 14 | Providing and fixing BAR COUNTER front Counter as per drawing structure with necessary drawers & Shelves as per design made out of 19mm thick Marine ply board structure fixed with the help of all necessary hardware like nail and fasteners and all internal surface of Partition / storage to be finished with 0.8mm thick laminate & external surface to be finished with designer tile, internal area shall be finished with worktop at upto 850mm high level with Marble finish polish / Double ht top also finihed in same mable with polish complete along with shape and design . 100mm high Gold Plated finish Aluminium skirting at floor level complete in all respect. Marble top in 20mm thickness with dimaond polish all over surface and edge to be double strip with gola polish complete in all respact of detail drawing. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, , Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr)
| a | Size 3900mm long x overall 700mm deep / Double ht 300mm wide from top x 850/1050mm high | For Bar front counter |  |  |  | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | Nos
|  | RA 08Qty |  |  |  |  | 0.7
|  | RA 09 Qty |  |  |  |  | 0.3
| 21 | SOILD PVD SHEET CLADDING : Providing Making & fixing/pasting with approved adhesive in position 1mm thick SS Sheet of grade 304 PVD coated with approved colour, shade, texture & finish over 12mm thick base FLEXI Ply board of approved brand & manufacture, PVD coated sheet shall be wrapped around the base ply frame at site with approved quality adhesive etc complete as per drawings & instructions of Project-in-Charge. cost include the provision of offset spacing for light provision and any back base suface paint in matching shade of PVD finish prior installtion complete as per detail drawing. ( Basic cost of PVD coated SS sheet @ Rs.410/- Sft) (Emboss Print design @ 100/- per sft)
| a. | Solid Sheet Cladding Plain type 1 | Sqm
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 34.95 | Sqm
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 1
FEATURE ROUND CNC CUT SCREEN : Providing & fixing feature round cnc cut screen made in 1mm thick SS sheet with factory made laser cut design and finished in PVD finished color as approved, Entire RIM will be moulded with Pencil round edge & 3mm dia tube shot welded on end circumference with neat / clean finish buffing prior to PVD coating application. Finished RIM shall be packed and cover with temprory packing wooden patti /frame/box to avoid any damgaes and deliver with safety at site, RIM will be install on Existing wall /partition with heavy duty SS clamp / bracket support including fastner complete as per satisfactory of Project Incharge.
| a. | Art work Type 1 : Round Dia | Premum Lounge | Nos |  |  | 2
|  | Total Qty |  |  |  |  | 2
|  | WO Qty |  |  |  |  | 2 | Nos
|  | RA 08Qty |  |  |  |  | 1.4
|  | RA 09 Qty |  |  |  |  | 0.6
| B. | Art work Type 2 : Round Dia | Baar A rea & Dinning | Nos |  |  | 4
|  | Total Qty |  |  |  |  | 4
|  | WO Qty |  |  |  |  | 2 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 2
| 24 | TREE ELEMENT : Providing and fixing Tree of Life Design Element made in part and combine in Tree Element as per design, part element is desicribe and detail below with the specification and material used. Also the element has petal and leaves feature with variable sizes of fixed / decorative light as per the design and requirement which include the all provision for base support and other allied requirements.
| A. | FOR BAR AREA | Rmt | 6 |  | 25 | 150
|  |  | Rmt | 4.5 |  | 15 | 67.5
|  | Recepsion Glass Wall | Rmt | 3.3 |  | 16 | 52.8
|  | Total Qty |  |  |  |  | 270.3
|  | WO Qty |  |  |  |  | 211.67 | RMT
|  | RA 08Qty |  |  |  |  | 145.6
|  | RA 09 Qty |  |  |  |  | 66.07
|  | RA 09 Extra Qty |  |  |  |  | 58.63
| i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved complete with fixing support above to fixed on ceiling complete as per detail drawing.
| a. | L1 : Size 130/250/310/395mm Long x 75/125/150/175mm wide x 1 each | Nos |  |  |  | 21
|  | Total Qty |  |  |  |  | 21
|  | WO Qty |  |  |  |  | 21 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 21
| i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved complete with fixing support above to fixed on ceiling complete as per detail drawing.
| b. | L2 : Size 220/285/355mm Long x 100/125/150mm wide x 1 each | Nos |  |  |  | 19
|  | Total Qty |  |  |  |  | 19
|  | WO Qty |  |  |  |  | 19 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 19
| ii) | ii) Grill Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from bottom with perforation for AC air ventilation as per design and drawing complete.
| a. | L1 : Size 475mm Long x 225mm wide x 1 each |  |  |  |  | 13
|  | Total Qty |  |  |  |  | 13
|  | WO Qty |  |  |  |  | 11 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 11
|  | RA 09 Extra Qty |  |  |  |  | 2
| iii) | iii) Light Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from top with central area for light provision with side profile light as per design and drawing complete. (Note : LED Profile & light cost not included and will be paid seperate)
| a. | L1 : Size 620mm Long x 275mm wide x 1 each | Nos |  |  |  | 11
|  | Total Qty |  |  |  |  | 11
|  | WO Qty |  |  |  |  | 11 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 11
| iii) | iii) Light Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from top with central area for light provision with side profile light as per design and drawing complete. (Note : LED Profile & light cost not included and will be paid seperate)
| b. | L2 : Size395/530/620mm Long x 175/225/275mm wide x 1 each | Nos |  |  |  | 12
|  | Total Qty |  |  |  |  | 12
|  | WO Qty |  |  |  |  | 10 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 10
|  | RA 09 Extra Qty |  |  |  |  | 2
| B. | FOR HIGH COUNTER AREA
| 1 | TRUNK ELEMENT : made in 15mm dia SS pipe with PVD finish as per color /shade approved or detail drawing. Pipe to be fixed and welded with inner circle pipe fitted for support in bottom and top where curve form start, also the curve and horizontal form in ceiling shall be be fitted with ceiling support with neat & clean finish complete as per detail drawing. pipe length is variable as per the design and provision petal/leaves attachment complete in all respact or advise by the Architect. (note : Length to measured as per actual and paid)
|  | HIGH COUNTER AREA | Rmt | 47 | 7.5 |  | 352.5
|  | Low Hight Area | Rmt | 24 | 3 |  | 72
424.5
|  | Total Qty |  |  |  |  | 424.5
|  | WO Qty |  |  |  |  | 386 | Rmt
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 386
|  | RA 09 Extra Qty |  |  |  |  | 38.5
| i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved complete with fixing support above to fixed on ceiling complete as per detail drawing.
| a. | L1 : Size 130/250/310/400mm Long x 75/125/150/175mm wide x 1 each | Nos |  |  |  | 40
|  | Total Qty |  |  |  |  | 40
|  | WO Qty |  |  |  |  | 40 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 40
| i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved complete with fixing support above to fixed on ceiling complete as per detail drawing.
| b. | L2 : Size 220/285/355mm Long x 100/125/150mm wide x 1 each | Nos |  |  |  | 36
|  | Total Qty |  |  |  |  | 36
|  | WO Qty |  |  |  |  | 36 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 36
| ii) | ii) Grill Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from bottom with perforation for AC air ventilation as per design and drawing complete.
|  | HIGH COUNTER AREA | Nos |  |  |  | 19
| a. | L1 : Size 475mm Long x 225mm wide x 1 each
|  | Total Qty |  |  |  |  | 19
|  | WO Qty |  |  |  |  | 11 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 11
|  | RA 09 Extra Qty |  |  |  |  | 8
| iii) | iii) Light Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from top with central area for light provision with side profile light as per design and drawing complete.
| a. | L1 : Size 615/700/800mm Long x 275/325/350mm wide x 1 each | Nos |  |  |  | 23
|  | Total Qty |  |  |  |  | 23
|  | WO Qty |  |  |  |  | 16 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 16
|  | RA 09 Extra Qty |  |  |  |  | 7
| iii) | iii) Light Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from top with central area for light provision with side profile light as per design and drawing complete.
| b. | L2 : Size 475/620/700/800/810mm Long x 225/275/325/350/375mm wide x 1 each | Nos |  |  |  | 22
|  | Total Qty |  |  |  |  | 22
|  | WO Qty |  |  |  |  | 15 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 15
|  | RA 09 Extra Qty |  |  |  |  | 7
| D. | FOR RECEPTION AREA
| 1 | TRUNK ELEMENT : made in 15mm dia SS pipe with PVD finish as per color /shade approved or detail drawing. Pipe to be fixed and welded with inner circle pipe fitted for support in bottom and top where curve form start, also the curve and horizontal form in ceiling shall be be fitted with ceiling support with neat & clean finish, also on wall bottom fixd to profile skirting as per design complete / detail drawing. pipe length is variable as per the design and provision petal/leaves attachment complete in all respact or advise by the Architect. (note : Length to measured as per actual and paid)
|  | FOR RECEPTION AREA Piller | Rmt | 6 |  | 18 | 108
|  | FOR RECEPTION AREA Piller | Rmt | 4.5 |  | 27 | 121.5
|  | FOR RECEPTION AREA Piller | Rmt | 9 |  | 15 | 135
|  | FOR RECEPTION AREA Wall | Rmt | 3.3 |  | 29 | 95.7
460.2
|  | Total Qty |  |  |  |  | 460.2
|  | WO Qty |  |  |  |  | 450.65 | Rmt
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 450.65
|  | RA 09 Extra Qty |  |  |  |  | 9.55
| i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with Plain Mirror finish / hammered texture emboss / Solid Color PVD Coated finished as per the shade approved complete with fixing support above to fixed on ceiling /wall complete as per detail drawing.
| a. | L1 - Ceiling : Size 305/440/535/585mm Long x 140/440/535/585mm wide x 1 each | Nos |  |  |  | 32
|  | Total Qty |  |  |  |  | 32
|  | WO Qty |  |  |  |  | 32 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 32
| i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with Plain Mirror finish / hammered texture emboss / Solid Color PVD Coated finished as per the shade approved complete with fixing support above to fixed on ceiling /wall complete as per detail drawing.
| b. | L2 - Ceiling : Size 350/485/580/640mm Long x 160/175/210/265mm wide x 1 each | Nos |  |  |  | 32
|  | Total Qty |  |  |  |  | 32
|  | WO Qty |  |  |  |  | 32 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 32
| i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with Plain Mirror finish / hammered texture emboss / Solid Color PVD Coated finished as per the shade approved complete with fixing support above to fixed on ceiling /wall complete as per detail drawing.
| c. | A&B type Wall Leaf : Size 280/335/410/485/560mm Long x 112/148/192/240/285mm x 1 each | Nos |  |  |  | 45
|  | Total Qty |  |  |  |  | 45
|  | WO Qty |  |  |  |  | 35 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 35
|  | RA 09 Extra Qty |  |  |  |  | 10
| iii) | iii) Light Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from top with central area for light provision with side profile light as per design and drawing complete.
| a. | L1 - Ceiling : Size 440/485/585/585mm Long x 130/190/225/255mm wide x 1 each | Nos |  |  |  | 17
|  | Total Qty |  |  |  |  | 17
|  | WO Qty |  |  |  |  | 17 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 17
| iii) | iii) Light Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from top with central area for light provision with side profile light as per design and drawing complete.
| b. | L2 - Ceiling : Size 290/440/525/640/mm Long x 110/160/190/255mm wide x 1 each | Nos |  |  |  | 17
|  | Total Qty |  |  |  |  | 17
|  | WO Qty |  |  |  |  | 17 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 17
| 28 | ELIPTICAL SHAPE NICHE BOX : Providing,making & fixing Eliptical shape niche box made in 12mm thick Natural Fiber Polymer Composite Board / wood / Ply( Eco freindly, Recyclable material ) using 100mm deep niche with backing of 12mm thick ply with 4mm thick thick mirror pasted both side as per niche shape and design with 12x12mm SS PVD finish moulding in front & back, shelf & pelmet box for light inside the niche, side in curve shape with duco paint finish as per the approved detail drawing. ( Overall Niche Box Size 500mm high x 255mm wide x 100mm deep)
|  | Baar Area & Recepsion | Nos |  |  |  | 29
|  | Total Qty |  |  |  |  | 29
|  | WO Qty |  |  |  |  | 29 | Nos
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 29
| 4 | WallPaper : Providing & fixing Fabric backed Vinyl Wall covering(10.05mtr. X .52mtr ) ( 300gsm Type-II) fire Retardant as per approved sample including all fixing arrangement complete in all respect. ( Basic cost of Fabric backed Vinyl Wall covering @ Rs. 90/- per sft ) ASper dwg elevation
|  | P,Lounge | Sqm | 26.3 | 3.83 |  | 100.729
|  | Open Door Deduction | Sqm | 1.15 | 2.27 |  | -2.6105
|  | Glass Door Deduction | Sqm | 2.15 | 2.7 |  | -5.805
|  | Photo Frame Glass Deduction | Sqm | 1.59 | 3.1 |  | -4.929
|  | Roller Binder Box | Sqm | 2.5 | 0.3 |  | 0.75
|  |  | Sqm |  |  |  | 0
|  | BAR Area | Sqm | 20.14 | 3.2 |  | 64.448
|  | P,Lounge door Deduction | Sqm | 1.15 | 2.27 |  | -2.6105
|  | Admin Door Deduction | Sqm | 0.94 | 2.33 |  | -2.1902
|  |  | Sqm |  |  |  | 0
|  | Dinning Area | Sqm | 37.4 | 3.2 |  | 119.68
|  | Kitchen Door Deduction | Sqm | 1.23 | 2.34 |  | -2.8782
|  | Passage Door Deduction | Sqm | 1.12 | 2.3 |  | -2.576
|  | Glass Door Deduction (G1) | Sqm | 2.96 | 2.7 |  | -7.992
|  | Glass Door Deduction (G2) | Sqm | 2.79 | 2.7 |  | -7.533
|  | Roller Binder Box | Sqm | 3 | 0.3 |  | 0.9
|  | Roller Binder Box | Sqm | 3 | 0.3 |  | 0.9
Sqm
|  | SPA Wall | Sqm | 18.1 | 3.1 |  | 56.11
|  | Electrical Room Door Deduction | Sqm | 0.98 | 2.34 |  | -2.2932
|  | SPA Door Deduction | Sqm | 1.2 | 2.34 |  | -2.808
|  | Glass Door Deduction | Sqm | 2.625 | 2.7 |  | -7.0875
|  | Roller Binder Box | Sqm | 3 | 0.3 |  | 0.9
|  |  | Sqm |  |  |  | 0
|  | PASSAGE Wall | Sqm | 14.4 | 3.2 |  | 46.08
|  | Dinnig Open Door Deduction | Sqm | 1.1 | 2.35 |  | -2.585
|  | SPA Door Deduction | Sqm | 1.2 | 2.35 |  | -2.82
|  | Disable Restroom Deduction | Sqm | 1.2 | 2.35 |  | -2.82
|  | Male Restroom Deduction | Sqm | 0.96 | 2.35 |  | -2.256
|  | Female Restroom Deduction | Sqm | 0.96 | 2.35 |  | -2.256
|  |  | Sqm |  |  |  | 0
|  | RCC Column | Sqm | 7 | 3.3 |  | 23.1
|  | Buffar Column | Sqm | 3.08 | 3.3 |  | 10.164
|  | BAR Column | Sqm | 1.1 | 3.3 |  | 3.63
|  | Reception Column | Sqm | 1.36 | 3.3 |  | 4.488
367.8289
|  | Total Qty |  |  |  |  | 367.8289
|  | WO Qty |  |  |  |  | 409.16 | Sqm
|  | RA 08Qty |  |  |  |  | 312
|  | RA 09 Qty |  |  |  |  | 55.8289
| 2 | Providing & fixing 6mm thick silver back finish looking mirror with adhesive of approved make on existing Natural Fiber Polymer composite Board/Wood Material ply as per design including all fixing arrangement complete in all respect. ( Basic cost of looking Mirror @ Rs. 120/- Sqft)
| a. | Mirror Panneling with back ply - For Ladies toilet full ht mirror | Sqm | 2 |  |  | 2
|  | Total Qty |  |  |  |  | 2
|  | WO Qty |  |  |  |  | 2 | Sqm
|  | RA 08Qty |  |  |  |  | 0
|  | RA 09 Qty |  |  |  |  | 2
| 2 | Providing & fixing 6mm thick silver back finish looking mirror with adhesive of approved make on existing Natural Fiber Polymer composite Board/Wood Material ply as per design including all fixing arrangement complete in all respect. ( Basic cost of looking Mirror @ Rs. 120/- Sqft)
| b. | Mirror with SS PVD Finish Profile Frame and back ply : Size 800mm long x 900mm high - For Toilets | Nos | 2 |  |  | 2
|  | Total Qty |  |  |  |  | 2
|  | WO Qty |  |  |  |  | 5 | Nos
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 2
| 3 | Providing & fixing Trims profile in wall partition,floor,ceiling etc in Rose Gold or approved color finish as per approved sample fixed with adhesive of approved make including all fixing arrangement complete in all respect.
| a | L- angle profile ( 12mm x 12mm x 1.5mm thick )( Basic cost of profile @ Rs. 350 Rmtr. ) | site specifc | Rmt
72.26
|  | Total Qty |  |  |  |  | 72.26
|  | WO Qty |  |  |  |  | 55 | Rmt
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 55
|  | RA 09 Extra Qty |  |  |  |  | 17.26
| 3 | Providing & fixing Trims profile in wall partition,floor,ceiling etc in Rose Gold or approved color finish as per approved sample fixed with adhesive of approved make including all fixing arrangement complete in all respect.
| b | Transition Profile : size 25mm wide - For where change in in floor such carpet,wooden floor,tile, stone etc. ( Basic cost of profile @ Rs. 350 Rmtr. ) | site specifc | Rmt
64.8
29.2
94
|  | Total Qty |  |  |  |  | 94
|  | WO Qty |  |  |  |  | 15 | Rmt
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 15
|  | RA 09 Extra Qty |  |  |  |  | 79
| 3 | Providing & fixing Trims profile in wall partition,floor,ceiling etc in Rose Gold or approved color finish as per approved sample fixed with adhesive of approved make including all fixing arrangement complete in all respect.
| c | Insert BRASS Strip Trims - size 5mm wide on top x 4mm thick x 25mm deep, Base Price Rs. 550/- per rmt | site specifc | Rmt |  |  | 26.6
|  | Total Qty |  |  |  |  | 26.6
|  | WO Qty |  |  |  |  | 25 | Rmt
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 26.6
|  | RA 09 Extra Qty |  |  |  |  | 1.6
| 7 | Joint Trims/Profile : Providing and fixing Expansion joint cover Trim made in SS with PVD finish size upto 150mm wide complete as per manufacturer details and all ht level. Base rate of Trims @ Rs. 1500 Per mtr. (Cost not include of Expansion joint treatment between slab and will be seperate)
| c | wall | Rmt |  |  |  | 26.4
|  | Total Qty |  |  |  |  | 26.4
|  | WO Qty |  |  |  |  | 28 | Rmt
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 26.4
| 9 | Artifact of approved design , texture , shape fix in wall/ceiling or placing with require hardware and arrangements support, complete as per design.
| a. | Artifact element - Large, Base Range Rs. 255000/- each, | In Reception area |  |  |  | 6
|  | Total Qty |  |  |  |  | 6
|  | WO Qty |  |  |  |  | 6 | Nos
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 6
| f. | Artifical Turf / Creeper bail Green wall : Made with fine quality polyester fabric which is long lasting, easy to clean and maintain. Material – Polyester Fabric, strings – Strings, Length – 6ft,approx. Area to covered approx 30 sqm floor /wall , Base range @ 150/- per String for creeper & Turf base price Rs. @ 120/- per sft, Note : Dense for string qty shall be advise by the Architect to enhance the green wall look. | In planter area | LS |  |  | 1
|  | Total Qty |  |  |  |  | 1
|  | WO Qty |  |  |  |  | 1 | LS
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 1
| 11 | Access Panels ; Providing Access Panel Trap Doors with not more than 1/16" shadow/gap on finished surfaces. Panel inlay duplicates wall and ceiling specifications to ensure acoustic integrity. Hardware free finish, opens with concealed touch-latches. The panel can be removed completely for full access. Access Panels arrive ready for installation with factory installed gypsum board inlay. Aluminium extrusion with gypsum board installed.
| a | Size- 450x450 mm | Nos |  |  |  | 4
|  | Total Qty |  |  |  |  | 4
|  | WO Qty |  |  |  |  | 4 | Nos
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 4
HASRDWARE & ACCESSORIES : Corner joinery section made of SS grade 304, brush finish, of size 40x16x0.8mm with thick plastic film pasted for surface protection. Wall joinery section with hamming profile of size 21x22x0.8mm, Fixed front panel to be anchored to floor with L Bracket of SS316 and covered with SS316 grade box type plate from all directions with 100 mm clear height from ground, Matt finish surface. SS grade 304 butt hinges Matt finish, coat hook of SS304 grade lacquer finish with rubber stopper, round knob 30mm dia of SS304 grade lacquer finish, SS 304 grade screws, anti-rotation nylon polyamide grade-6 expandable wall plugs etc complete as per approved design, shade, colour, size etc complete
|  | Divider, Pilaster and other fixed panels including doors one number per cubicle. Make : Action Tessa / Green / Merino | Nos |  |  |  | 4
|  | Total Qty |  |  |  |  | 4
|  | WO Qty |  |  |  |  | 4 | Nos
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 4
| 24 | FROST GLASS FILM : Providing and Pasting Frosted Glass film on Existing Glass partition surface with using Liquid shampoo spraying to set the plotter and wiping process with rubber clipper to ensure all bubble removal and any gap complete in all respact to the satisfaction of Project Incharge. * Face Film appearance 80 micron cast film with frosted. * Back with self Adhesive permanent, acrylic based. * Backing paper one side coated bleached kraft paper, 135 g/m2. * Durability: 15 years (indoor)/ 7 years (outdoor) Make : Avery / 3M / Garware | Existing Glazing | Sqm
28.377
|  | Total Qty |  |  |  |  | 28.377
|  | WO Qty |  |  |  |  | 18.66 | Sqm
RA 08Qty
|  | RA 09 Qty |  |  |  |  | 18.66
|  | RA 09 Extra Qty |  |  |  |  | 9.717

## Abstract Civil & Dismantling
Company Name : | LKO INTNL ARPT LTD
Project Name : | Finishing work for CIP Lounge at Terminal-03, CCSI Airport, Lucknow
Sr No | Particulars | Code / Area Specified | Qty. | UoM | Impulse Branding |  | RA-01 |  | RA-02 |  | RA-03 |  | RA-08 |  | RA-09 |  | Extra Qty RA Bill 09 |  | Cumulative |  | Variance
[5 empty] | Unit Price | Total Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | Qty | Amount | QTY | Amount | QTY | Amount
[5 empty] | INR | INR
0
A | DISMENTLING & CLEANING WORKS |  |  |  |  | 0
1 | Dismantling of existing flooring to the mother slab, with the help of permissible tools & during the specifies time of the day so as to minimise the disturbance to the adjacent occupants/users etc |  |  | SQM | 250 | 0
2 | Demolishing of brick work in cement mortar & cleaning the site for work able |  |  |  |  | 0
a | 230mm brick wall |  |  | Cum | 1200 | 0
b | 115mm brick wall |  |  | Sqm | 200 | 0
3 | Dismantling of existing floor & wall tiles with base mortar & cleaning the site for work able condition. |  |  | Sqm | 180 | 0
4 | Dismantling of existing Door with frame & stacking the same in the premises. |  |  | Each | 1000 | 0
5 | Dismantling of RCC works in beams, columns, slabs etc. including sub-base, cutting and removal of reinforcement, stacking of serviceable material. |  |  | Cum | 2250 | 0
6 | Disposal of building rubbish / malba / similar unserviceable, dismantled or waste materials by mechanical means, including loading, transporting, unloading to approved municipal dumping ground or as approved by Engineer-in-charge, beyond 50 m initial lead, for all leads and lifts complete. |  |  | Cum | 500 | 0
7 | Dismantling of existing plaster with P.O.P. & cleaning the site for workable |  | 0 | Sqm | 50 | 0
8 | Dismantling of cement concrete flooring & cleaning the site for workable |  | 0 | Cum | 2250 | 0
9 | Removing of Cinder filling & cleaning the site for workable |  | 0 | Cum | 500 | 0
10 | Core Cutting on RCC work with diamond core drilling machine for any services work Pipe crossing with 3M™ Fire Barrier tuck in wrap strips to be fixed onto the pipes and the remain gap to be filled with Fire Seal 3M™ Fire Barrier Sealant IC 15WB+ (Depth consider upto 300mm) |  |  |  |  | 0
a. | 100-150mm dia |  |  | Nos | 500 | 0
b. | 150-200mm dia |  | 0 | Nos | 1200 | 0
c. | Any Maximum depth 600-900mm / upto 300mm dia |  | 0 | Nos | 4000 | 0
11 | Temprory Barricating till the work completion material shall include the GI Frame with fire paint ( with one side single layer of 12.5mm thick FR Gypsum Board cladding (Cost include errection/removal at end with cleaning and repair the area for handover) (Vinyl Print on outer surface also include in cost as per art work approved) Note : All the Barricating work shall be as per approved permision permited by the Airport Authoruity/ operating agency including the required compliance and requirement fulfill by the project owner or their hired agency. |  |  | sqm | 1450 | 0
| TOTAL FOR DISMENTLING & CLEANING WORKS |  |  |  |  | 0
B | CIVIL WORK
1 | AAC BLOCK WORK : Providing and laying 100mm thick ACC block wall with grade -1 AAC Blocks of density 551 to 650kg / cum conforming to IS : 2185 ( Part -3) in superstructure above plinth level with R.C.C. bend at cill & Lintel level with approved block laying polymer modified adhesive mortar all complete as per direction of Engineer-in-Charge. (The payment of RCC band and reinforcement shall be made for separately). size of block (2'-0" x 0'-8" and width 0'-4" ). the rate also including scaffolding, curing etc. complete as specified. |  |  | Sqm | 1150 | 0
2 | LINTEL : R.C.C- ( 1 : 1.5 : 3 ) ( 1 cement : 1.5 coarse send : 3 graded stone aggregate 20mm nominal size ) for lintels, Lintel in arch etc. or where ever required I/c reinforcement for lintel 4no 12mm dia bars with 8mm dia rings @ 150c/c & centering shuttering for all levels and height.( Door Lintel length as per drawing 100mm wide x 100mm height ) The rate includes de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge. |  | 9.9 | Rmt | 944.2424 | 9347.9999 | [6 empty] | 5.2 | 4910.0606
3 | LINTEL BEAM : R.C.C- ( 1 : 1.5 : 3 ) ( 1 cement : 1.5 coarse send : 3 graded stone aggregate 20mm nominal size ) for Bends where ever required I/c reinforcement 2Nos 8mm dia bar with 8mm dia links @ 150mm c/c including centering shuttering for all levels and height,( bend cross section size 100mm wide x 75mm thick ) etc. complete. The rate includes de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge. |  | 87.0848 | Rmt | 1050 | 91439.04
4 | RCC COUNTER : R.C.C in ( 1: 1.5 : 3 ) for counters, slabs ( upto 75mm thick) I/c reinforcement 10mm dia bar @ 150mm c/c both ways & centering shuttering for all levels and height. The rate includes de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge. |  | 2.706 | Sqm | 1950 | 5276.7 | [6 empty] | 2.2275 | 4343.625
5 | BASIN COUNTER WORK : Providing & fixing Basin counter with the understructure to be made in MS Angle 45x45mm with 4mm thick of appropriate cross section and to be treated with anti rust paint and enamel black paint. The MS frame to be clad with 12mm thick bison board / Marine ply to receive the final finish material of the counter. Counter to be 600 mm deep with a vertical fascia of 100mm on splash & upto 500mm on front drop vertical facia to be clad with the finish material as approved. The counter to have required cutout for basin, Tap faucet, drain, dustbin etc. (Excl. cost of Stone) |  | 4.51 | Rmt | 10500 | 47355 |  |  |  |  | 4.5 | 47250
6 | WATERPROOFING (LIQUID MEMBRANE) : Providing and applying ready to use Single Component liquid applied elastomeric waterproof membrane comprises of special blend of copolymers and additives to provide an excellent, seamless, flexible and quick - drying waterproofing membrane. product shall be complies the Tensile Strength: 2.15 N/mm at 20° C 1.05 N/mm at 40° C Elongation: 114% at 20° C, 86 % at 40° C Crack Bridging: > 0.75mm at 0.8mm dft for wet areas takes care of critical areas such as Pipe Penetrations, Corner Fillet, Inlet / Outlet pipes etc. The surface to be treated must be dry, clean, structurally sound, free from oil, grease, wax, polish, laitance, dust and other barrier materials. New substrate shall be allowed to cure as per standard procedure. All cracks, construction joints, pipe penetration, bore packing and corners shall be treated prior to application of waterproofing membrane. Primer on the prepared substrate to seal off porosity and improve the substrate and allow to dry for approx. 60 minutes. Stir the waterproof liquid manually before application. Using a brush, roller or spray, apply waterproof liquid coat on the primed surface. While the coat is still wet, Deckweb/Sealing tape should be placed on all corners, floor/wall junctions, pipe penetrations and other critical areas ensuring no air is entrapped and allow to dry. Apply 2nd coat of waterproof coat on the entire surface and allow it to cure for 4 hours before laying the screed/protection plaster/tiling. The laying of waterproofing application membrane shall be got done through the authorised applicator of the manufacturer reccomended with providing the work execution Test / warranty certification for the min 5years and max 15 years as per advised by the Project Incharge. |  |  | Sqm | 1450 | 0
6 | WATERPROOFING (MEMBRANE HDPE WITH HEAT TORCH) : Providing and laying APP (Atactic Polypropylene Polymer) modified prefabricated five layer, 3 mm thick water proofing membrane, black finished reinforced with glass fibre matt consisting of a coat of bitumen primer for bitumen membrane @ 0.40 litre/sqm by the same membrane manufactured of density at 25°C, 0.87 - 0.89 kg/litre and viscocity 70 - 160 cps. Over the primer coat the layer of membrane shall be laid using butane torch and sealing all joints etc., and preparing the surface complete. The vital physical and chemical parameters of the membrane shall be as under : Joint strength in longitudinal and transverse direction at 23°C as 350/300 N/5 cm. Tear strength in longitudinal and transverse direction as 60/80N. Softening point of membrane not less than 150°C. Cold flexibility shall be upto -2°C when tested in accordance with ASTM, D - 5147. The laying of membrane shall be got done through the authorised applicator of the manufacturer of membrane. the top most layer shall be finished with 15mm thick cement mortar 1:3 (1 cement : 3 fine sand) mixed with 2% integral water proofing compound by weight of cement and finally finished with neat cement punning Complete. The laying of waterproofing application membrane shall be got done through the authorised applicator of the manufacturer reccomended with providing the work execution Test / warranty certification for the min 5years and max 15 years as per advised by the Project Incharge. |  |  | Sqm | 2800 | 0
5a | Extra for covering top of membrane with Geotextile, 120 gsm non woven, 100% polyester of thickness 1 to 1.25 mm bonded to the membrane with intermittent touch by heating the membrane by Butane Torch as per manufactures recommendation. |  | 0 | Sqm | 350 | 0
6 | SCREEDING WORK : Providing & laying Screeding with 1:2:4 cement conc. (1 cement :2 coarse sand :4 graded stone agg 10mm nominal size ) in line and level including required channel shuttering, curing, troller finish etc. complete in all respect |  | 21.45 | Cum | 7500 | 160875 |  |  |  |  | 21 | 157500
6a | NEAT CEMENT SLURRY : Extra for above screeding work for floating quote of neat cement punning upto 6mm including curing etc. where as carpet, wooden floor, vinyl floor comes & as per site required. |  | 22 | Sqm | 120 | 2640 |  |  |  |  | 21 | 2520
7 | CEMENT PLASTER : Providing and applying 15 mm thick cement plaster of mix in 1:4 (1 cement : 4 coarse sand) with admixture of waterproof binding agent liquid at 1:1 ratio with cement or as per manufacturer recomendation and applying at all levels & heights including scaffolding, curing etc. complete as specified. |  |  | Sqm | 370 | 0
8 | POP PUNNING : Providing & applying Water Resistant and Quick Drying, Non Curable Type of average upto 12mm thick plaster of Paris and wiremesh at joints of diff. material to the walls and columns in square plumb line and level. The cost to include scraping and removing the existing neeru finish and also the hacking the surface of walls/columns. After leveling, the surfaces to be finished to receive paint . Rate to include provisioning of grooves as per design. The POP puning to be carried out 100mm above the finished ceiling level and not for the area above. |  | 127.9146 | sqm | 370 | 47328.402 |  |  |  |  | 126.3009 | 46731.333
9 | GYPSUM VERMICULITE PLASTER : Providing & Applying Gypsum vermiculite plaster upto 22-25mm thick of refined and processed gypsum and vermiculite along with a mix of premium quality special binders and additives to provide easier application, better bonding, and a smooth finish. It creates a surface so smooth that no other layer is required below or above it and direct application of paint can be done over it. Conforms to IS 2547: Part 1 and 2 of “The Bureau of Indian Standard”. Direct application on brick block, RCC, and other surfaces. Ready to paint surface achieved. Spreads and finishes to a minimum thickness increasing the surface area. Fire-resistant. Eco-friendly. No shrinkage cracks. Better, smoother, and consistent finish. More durable. Lesser dead load on the structure as it is lightweight plaster. No water curing is required. Bulk Density: 1020 Kg/m2 , Setting time: 30-35 mins. Coverage as per manufacturer recomendation with Compressive strength : 60-70 Kg/cm2. item for all height level with required scaffolding complete as per the site and advised by the Project Incharge. |  | 0 | sqm | 450 | 0
10 | FLOOR FILLING : Providing and laying fillers of AAC Light weight block filling with full /break pieces as per the requirements of Approved make as per LOM and size as required to Fill/Raise the floor with conceal the pipes, drains, etc as per site requirement. The filling to be cured and Compacted to prevent any voids and dust pockets . The filler to be adequately leveled to receive the finished flooring as specified. |  | 16.4113 | Cum | 2300 | 37745.8923 |  |  |  |  | 15 | 34500
| TOTAL FOR CIVIL WORK |  |  |  |  | 402008.0342 | [5 empty] | 288501.333 |  | 9253.6856
C | FLOORING WORK/CLADDING WORK
3.1 | TILE FLOORING |  |  |  |  | 0
1 | Providing and laying Vitrified Antiskid tiles in floor in different sizes (thickness to be specified by the manufacturer) with water absorption less than 0.08% and conforming to IS:15622, of approved brand & manufacturer, in all colours and shade, laid on 20 mm thick cement mortar 1:4 (1 cement: 4 coarse sand) jointing with grey cement slurry @3.3 kg/sqm including spacers with epoxy cementious grout matching to pigments etc. The tiles must be cut with the zero chipping diamond cutter only . Laying of tiles will be done with the notch trowel, plier, wedge, clips of required thickness, leveling system and rubber mallet for placing the tiles gently etc, cost also include the Protection covering of tile with 6mm Bubble sheet with jointing using clear tape till handover with complete as per advised by the Project Incharge. |  |  |  |  | 0
a. | Vitrified Tile Floor - Type 1 : Size as approved, Base Price 65 per sft | T-02 | 39.4716 | sqm | 2300 | 90784.749
b. | Vitrified Tile Floor - Type 2 : Size as approved, Base Price 85 per sft |  | 0 | sqm | 2600 | 0
2 | Deduct for not using 20 mm thick Cement Mortar 1:4 ( 1 Cement: 4 coarse sand) bedding in laying of floor tiles and jointing with grey cement slurry @ 3.3 kg/ sqm. |  | 0 | Sqm | 650 | 0
3 | Fixing glazed/ Ceramic/ Vitrified floor tiles with cement based high polymer modified quick-set tile adhesive (Water based) conforming to IS: 15477,in average 3mm thickness. |  | 0 | Sqm | 430 | 0
3.2 | WALL TILES |  |  |  |  | 0
1 | Providing and fixing 1st Quality Vitrified wall tiles conforming to IS:15622 (thickness to be specified by the manufacturer), of approved make, in all colours, shades as approved by Engineer-in-Charge for dado fixed with cement based high polymer modified quick set tile adhesive ( water based ) conforming to IS : 15477, in a average 6 mm thickness including spacer and filling the joints with epoxy cementious grout of pigment to match the shade of the tiles to give a smooth surface. complete as per detail dwg. |  |  |  |  | 0
a. | Wall Tile - Type 1 : Size as approved, Base Price 65 per sft - | For Toilets, janitor & Kitchen | 100.0296 | sqm | 2300 | 230068.08 |  |  |  |  | 75.492 | 173631.6
b. | Wall Tile - Type 2 : Size as approved, Base Price 55 per sft - | For Kitchen | 75.8208 | sqm | 2200 | 166805.76 | [5 empty] | 0
2 | Providing and fixing 1st Quality Designer Ceramic tiles conforming to IS:15622 (thickness to be specified by the manufacturer), of approved make, in all colours, shades as approved by Engineer-in-Charge for dado fixed with cement based high polymer modified quick set tile adhesive ( water based ) conforming to IS : 15477, in a average 6 mm thickness including spacer and filling the joints with epoxy cementious grout of pigment to match the shade of the tiles to give a smooth surface. complete as per detail dwg. |  |  |  |  | 0
a. | Designer Tile - Type 1 : Size as approved, Base Price 150 per sft |  | 0 | Sqm | 4500 | 0
b. | Designer Tile - Type 2 : Size as approved, Base Price 350 per sft |  | 0 | Sqm | 8200 | 0
b. | Designer Tile - Type 3 : Size as approved, Base Price 550 per sft |  | 5 | Sqm | 8400 | 42000
3.3 | TILE STRIPS : P/F tile strips made out of vitrified tiles of size as per manufacturer as approved colour, shade, texture, design in varying strip sizes (38/50/25 mm wide & 200/300/400 mm long) of approved make & manufacture for dado fixed with cement based high polymer modified quick set tile adhesive ( water based ) conforming to IS : 15477, in a average 3mm thickness including filling the joints mixed epoxy cementious grout with pigment to match the shade of the tiles to give a smooth surface. Base Rate of Tile @ 65 per sft | site specific | 5 | Sqm | 2300 | 11500
3.4 | TILE SKIRTING : Providing and fixing Vitrified tile Skirting upto 100mm high fixed with 12 mm thick bed of cement mortar 1:3 (1 cement : 3 coarse sand) and jointing with grey cement slurry @ 3.3kg per sqm, including pointing and joint finish in epoxy cemetious grout with pigment of matching shade complete. Base Rate of Tile @ 65 per sft | site specific | 15 | Rmt | 1500 | 22500
4 | STONE WORK |  |  |  |  | 0
1 | GRANITE FLOORING : Providing and fixing 18 mm thick gang saw cut, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:4 (1 cement : 4 coarse sand), joints treated with white cement, mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with polythin+POP as per advised by the Project Incharge. ( Basic cost of Granite stone @ Rs. 250/- per sft) |  | 0 | Sqm | 6500 | 0
2 | GRANITE CLADDING : Providing and fixing 18 mm thick gang saw cut, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), joints treated with white cement, mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge. ( Basic cost of Granite stone @ Rs. 250/- per sft) |  | 0 | Sqm | 9500 | 0
3 | GRANITE SKIRTING : Providing 18 mm thick Granite stone in Skirting of upto 75-100 mm high with epoxy resin based adhesive, including cleaning etc. complete or alternatively laid over 12mm. thick cement mortar 1:3 (1 cement :3 coarse sand) and jointed with cement slurry complete as per pattern and design .including necessary grooves, edge chamfering, grinding & polishing as required complete in all respect. ( Basic cost of Granite stone @ Rs. 250/- per sft ( As per approved)( Actual Length to be measured & paid ). |  | 0 | Rmt | 2500 | 0
4 | CORION CLADDING : Providing and fixing 12mm thick Solid surface ( Corian ) for Basin Counter/Ledge/Jamb/cill etc fixed with adhesive of approved make including jointing with adhesive mixed with pigment to matching the shade of solid surface complete as per drawing .including edge chamfering, buffing, polishing complete in all respect. ( Basic cost of solid surface ( Corian ) @ Rs. 750/- Sft )( Actual size to be measured & paid ). | For Male & Female toilet basin counter, ledge wall top | 35.0592 | Sqm | 13000 | 455769.6 | [6 empty] | 30.8656 | 401252.8 | 4.7344 | 61547.2 | 13.29 | 172770
5 | MARBLE FLOORING : Providing and fixing Marble work 16-18 mm thick, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:4 (1 cement : 4 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with polythin+POP as per advised by the Project Incharge. |  |  |  |  | 0
a. | Marble Flooring Type 1 : Base Price of Marble @ 450/- Per sft, | ST-01 / For Entire Lounge,spa area | 263.8558 | sqm | 9300 | 2453858.847 |  |  | 257.0525 | 2390588.25 |  |  |  |  | 3.57 | 33201
b. | Marble Flooring Type 2 : Base Price of Marble @ 1300/- Per sft, |  | 0 | sqm | 21000 | 0
6 | MARBLE STRIPS : Providing and fixing Marble strip work in existing flooring using diffrent color shade and sizes in width strips of 16-18 mm thick, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:4 (1 cement : 4 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual Lenght of stone strps to be measured & paid ). Cost also include the Protection covering till handover with polythin+POP as per advised by the Project Incharge. |  |  |  |  | 0
a. | Marble Flooring Strips Type 1 upto 25-45mm wide : Base Price of Marble @ 900/- Per sft, For Reception area | site specific | 10 | Rmt | 9500 | 95000 | [8 empty] | 10 | 95000 | 1.27 | 12065
b. | Marble Flooring Strips Type 1 upto 75-150mm wide : Base Price of Marble @ 900/- Per sft, For Reception area | site specific | 10 | Rmt | 9500 | 95000 | [8 empty] | 10 | 95000 | 17.62 | 167390
7 | MARBLE CLADDING : Providing and fixing Marble work 16-18 mm thick, mirror polished, prepolished, machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge. |  |  |  |  | 0
a. | Marble Cladding Type 1 : Base Price of Marble @ 450/- Per sft, | For counter Splash area | 11.8844 | sqm | 9300 | 110524.92 | [8 empty] | 6.84 | 63612
b. | Marble Cladding Type 2 : Base Price of Marble @ 1200/- Per sft, |  | 0 | sqm | 19000 | 0
c. | Marble Skirting upto 100mm high : Base Price of Marble @ 1200/- Per sft, | site specific | 82.5 | Rmt | 8500 | 701250 |  |  | 82.368 | 700128
8 | MARBLE DESIGNER CLADDING : Providing and fixing Marble designer work 16-18 mm thick marble with random size cut pcs in 200/300/400mm high x 75/100/125mm in width with making taper cut on edge to ake 4mm wide groove on vertical/horizontal as per design, all the surface, edges, V groove shall be mirror polished, all the marble will be jet water machine cut of required size, approved shade, colour and texture laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. ( Actual size of stone area legth x height to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge. |  |  |  |  | 0
a. | Marble Designer Cladding Type 1 : Base Price of Marble @ 450/- Per sft, | for toilets wall | 67.1352 | sqm | 8500 | 570649.2 | [8 empty] | 67.14 | 570690 | 14.02 | 119170
b. | Marble Designer Cladding Type 2 : Base Price of Marble @ 1200/- Per sft, |  | 0 | sqm | 19000 | 0
9 | WOODEN FLOORING |  |  |  |  | 0
1 | Providing & fixing 15mm thick Engineered wooden flooring of approved make & shade in chevron pattern with 2mm thick base foam including all fixing arrangement & required profile & skirting complete in all respect. (Basic cost of Engineered Wooden flooring@ Rs. 550 per sft) (Actual Laying area at site to be measured & paid ). |  | 0 | Sqm | 8000 | 0
10 | CARPET / RUG FLOORING |  |  |  |  | 0
1 | Providing & fixing Carpet / Rug of Handmade / Machine tuffted with Pile Yarn (80% wool & 20% nylon or 100% Viscose/Bamboo silk) Dyed in Eco freindly pigment color with Enviromental freindly standards. Sanitized with stain free and Alergy resistant quality. Carpet should have warranty of Minimum 10-15 year and installed by the expert installer or manufacturer recommended agency. (1500GSM 12 to 14mm thick Nylon Printed Customized or Axminster) with Protection covering till Handover of the Project. | For Premium Lounge & Spa Area |  |  |  | 0
a | Carpet type 1 : Base Price of Carpet @ Rs. 1500 per sft |  | 0 | Sqm | 6700 | 0
b | Carpet type 2 : Base Price of Carpet @ Rs. 3500 per Sqm |  | 86.295 | Sqm | 7500 | 647212.5 | [8 empty] | 85.85 | 643875
11 | MARBLE COMBINATION FLOORING : Providing and fixing Marble combination work with 20mm thick, mirror polished, prepolished, water jet cuting of required size and pattern, approved shade, colour and texture inlay as per the design approved by the Architect, laid over 20 mm thick base cement mortar 1:3 (1 cement : 3 coarse sand), white cement slurry , joints treated with teenaxe mixed with matching pigment, epoxy touch ups, including rubbing etc. complete and at all level. Marble stone should be of well known brand with A+ Grade of complies use the Moisture absorption test as per IS 1124 & Hardness test is done as per Mho’s scale and Specific gravity test is done as per IS 1122.( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with bubble sheet as per advised by the Project Incharge. |  |  |  |  | 0
a. | Marble Combination / Inlay Flooring : Type 1, Base Rate ST01 @ 1300/- per sft, ST02 @ 950/- per sft, For Reception area Circular highlighter/ insert | Combination of ST-01 & ST-02 / In around | 4.9984 | Sqm | 21000 | 104966.4 | [8 empty] | 4.92 | 103320
12 | KOTA STONE FLOORING : Provide and lay 25mm thick, machine cut and polished Kota Stone of aprroved colour and texture laid over 20 mm thick base cement mortar 1:4 (1 cement : 4 coarse sand), joints treated with white cement, mixed with matching pigment, epoxy touch ups, including rubbing polihing etc. complete and at all level. ( Actual size of stone to be measured & paid ). Cost also include the Protection covering till handover with polythin+POP as per advised by the Project Incharge. ( Basic cost of Granite stone @ Rs. 65/- per sft) | T-01 / For Kitchen | 26.67 | SqM | 1750 | 46672.5 | [6 empty] | 23.87 | 41772.5 | 4.37 | 7647.5
| TOTAL FOR FLOORING WORK/CLADDING WORK |  |  |  |  | 5844562.556 |  |  |  | 3090716.25 |  | 173631.6 |  | 443025.3 |  | 1673892.7 |  | 471395
D | DOOR WINDOW WORK
1 | DOOR / WINDOW FRAME : Providing and fixing door and window frames made out of Natural Fiber Polymer Composite Wood/Board (Eco freindly, Recyclable) with necessary groove ( 6mm x 6 mm ) & single rebate including necessary M.S. hold-fasts in cement concrete blocks 1: 2: 4 / fasteners ( expendable 10mm dia ) on either side fixed in line and level. The frame to be treated with necessary anti-termite chemical and fire retardant paint on partition side & finally finished with PU polish/Paint complete in all respect. |  | 0.15186 | Cum | 150000 | 22778.25 | [6 empty] | 0.40538 | 60807
2 | ALLUMUNIUM EXTRUDED DOOR FRAME : Providing and fixing Allumunium extruded door frame of section 100x25mm with 2.5mm thickness Extruded allumunium frame with using door stop trim/rebate of 20x11mm on frame all three side compatible for 35-45mm thick door panel complete as per the manufacturer technical specfication & dwg. with approved color as per Architect. |  |  |  |  | 0
a. | Single Leaf Door - 900/1200mm Long x 2400mm high | For Toilet doors | 3 | Nos | 17000 | 51000 | [6 empty] | 2.4 | 40800 | 0.6 | 10200
b. | Double Leaf Door - 1500/1800mm Long x 2400mm high | For Merchandise wall | 1 | Nos | 22000 | 22000 | [8 empty] | 1 | 22000
3 | LAMINATED DOOR SHUTTER : Providing and fixing 38 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both sides of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, vision slit as per design with 6mm thick glass with wooden beading ( white ash wood ), handles,motrise dead lock with one side key knob cylinder finish in rose gold SS etc. complete in all respect. .( Basic cost of laminate @ Rs. 90/- sft ) ( Actual size of shutter to be measured & paid ). |  |  |  |  | 0
a. | With Vision panel - Size 250mm x 900mm or as per design approved - | For Spa & admin office | 5.28 | Sqm | 10500 | 55440 | [6 empty] | 3.648 | 38304 | 0.912 | 9576
b. | Without vision Panel - | For toilets | 8.184 | Sqm | 9700 | 79384.8 | [6 empty] | 4.032 | 39110.4 | 1.008 | 9777.6
4 | LAMINATED SHAFT SHUTTER : Providing and fixing 25 mm. thick flush door shutters core of block board ( MR Grade ) construction with well matched 1mm thick laminate sheet of approved make & shade on both faces of shutter including white ash wood edge lipping (12mm thick) finish with PU polish, all required fittings such as 4 nos. 125 mm. size brass butt hinges per leaf with necessary screws and S.S. fittings including handles, tower bolts, door stopper, rubber buffer, etc. complete in all respect.( Basic cost of laminate @ Rs. 970/-Sqm) ( Actual size of shutter to be measured & paid ). ( Shaft & Janitor Room Entry Door ) |  | 4.752 | Sqm | 9200 | 43718.4 | [8 empty] | 4.32 | 39744
5 | FIRE RATED WOODEN DOOR 2HR. RATING : Providing & Fixing of 120min rating wooden fire door shutter with frames as per the specification as per below : - Frame : P/f Door frames manufactured out of Hardwood Mirandi of nominal section 120mm x 70mm with heat activated Intumescent fire seal strips of size 10mm x 4 mm provided in grooves on all three sides of the frame on both side. Hardwood to be Treated with VIPER Fire Retardant Primer FR 880 and VIPER Finishing Paint FRS 881 Use two coats of Fireguard FR880 Wood Primer followed by 2/3 coats of Fireshield FRS 881 Finishing paint even on prev iously painted/polished surfaces. (FIRESHIELD FRS 881 FINISHING PAINT FR-881 of CPWD-DSR approved item Ref.Page 165 Code no 13.88a-2002) as per color approved by the Architect. Shutter : Door shutter of 52mm thickness conforming to BS:476 part 22 and IS-3614 Part 2 as per prototype tested from CBRI Roorkee for stability and integrity and insulation, with comprising of 75x48mm hardwood internal timber frame work, with infill 25mm thick Fire rated rock wool insulation having density 96kg/m3, the insulation shall be sandwiched between 2nos 12mm thick noncombustible(calcium silicate) boards, cladded with 3mm thick commercial ply on both sides of shutter with heat activated intumescent fire seal strip of size 20x4mm make Sealz mounted in the grooves of expose/concealed lipping all around the shutter except bottom.. Finishing / Hardware :- Frame to be painted with VIPER Finishing Paint FRS 881 as per color approved by the Architect Shutter finish with 1mm thick Laminate on Both Side - conforming to HSN 4823 SS Hinges - 04 nos per leaf - conforming to HSN 8302 Door Closer - conforming to HSN 8302 6mm thick VP Fire Rated Clear - 200x300mm - conforming to HSN 7007 Trim- conforming to HSN 8302 Dash Fastner-08nos.per leaf- conforming to HSN 7318 Panic Bar conforming to HSN 8302 (Optional) cost to be separated Note : Contracter shall need to submit the manufacturer shop drawing for the fire for approval before ordering. |  |  |  |  | 0
6 | FRAMED GLASS PARTITION : Providing and installation of framed allumunium with vision glass partition sytem of approved series and brand as per approved list of make, fixed glass partition using 10mm thick Toughened glass in proprietary natural anodised approved aluminium sections with Concealed sealing (No visible Gaskets/Seals) with acoustic. The profile will have Carpert Groove at the Bottom on both sides for accommodating max. 8mm carpets. Glass to be fixed with help of Proprietary Stability GRIPPER Clamp to have a stable system. It should consists of intermediate slim junction profiles for Glass to Glass vertical joints, 90 Degree L Junction and T Junction profiles suitably to be used as per room configuration designs. No VISIBLE Clip Lines to provide clutter free view at both side of section. The Glass to be Offset mounted towards outer edge leading to minimum aluminium frame on one side. Optional Profile Bottom Seal pair for additional acoustic if required. All Profiles are min 1.5mm thickness excluding 20 microns of Anodizing, Standards applicable • Structural stability test accordance to BS 5234: Part2:1992 & EN 1991-1-1:2002 • Acoustic test for sound insulation in accordance to DIN EN ISO 10140-2 ASTME-E 90 |  |  |  |  | 0
a. | Single Glazed Partition, Size 50mm wide x 30mm high, color as approved |  | 4.3824 | Sqm | 7609 | 33345.6816 | [8 empty] | 4.38 | 33327.42 | 3.94 | 29979.46
b. | Single Glazed Partition, Size 100mm wide x 30mm high, color as approved |  | 28.512 | Sqm | 8600 | 245203.2 | [8 empty] | 28.377 | 244042.2
c. | Single Glazed without framed - For kitchen window |  | 0 | Sqm | 4500 | 0
7 | Providing & fixing Hydraulic sleek door closer of approved make including all fixing arrangement complete in all respect. Door weight capacity upto 80kg, with 10year manufacturer warranty complete as per design approved. |  | 4 | No | 6700 | 26800 | [8 empty] | 4 | 26800
8 | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in rose gold SS ) of approved make including all fixing arrangement complete in all respect. |  | 5 | No | 6500 | 32500 | [8 empty] | 5 | 32500 | 2 | 13000
9 | Providing & fixing Door Lock ( Motrise lever one side knob cylinder & one side key finish in SS ) of approved make including all fixing arrangement complete in all respect. |  | 0 | No | 7500 | 0
10 | Providing & fixing Floor Spring of approved make including all fixing arrangement complete in all respect. Door weight capacity upto 70kg, with 10year manufacturer warranty complete as per design approved. For Handicape toilet door |  | 1 | No | 3500 | 3500
11 | Providing & fixing 50mm dia SS 304 grade (finish : As per approved ) 600mm Long H type Handle including all the accessories and fitting as per requirement complete. |  | 2 | Set | 6500 | 13000 | [8 empty] | 2 | 13000
| TOTAL FOR DOOR WINDOW WORK |  |  |  |  | 628670.3316 | [7 empty] | 179021.4 |  | 440967.22 |  | 42979.46
E | OTHER WOOD WORK FOR WALL PANELLING, PARTITIONS & STORAGES
1 | PLY /BOARD CLADDING (Two Layer/Double Sided) : Providing and fixing 12mm thick Natural Fiber Polymer Composite Wood/Board (Eco freindly, Recyclable) Ply of approved make on existing M.S. frame work including all fixing arrangement complete in all respect . (Partition Length to be measured only) |  | 0 | Sqm | 2250 | 0
2 | PLY /BOARD CLADDING (One Layer/Double Sided) : Providing and fixing 12mm thick Natural Fiber Polymer Composite Wood/Board (Eco freindly, Recyclable) board of approved make on existing M.S. frame work including all fixing arrangement complete in all respect . (Partition Length to be measured only) |  | 192.3294 | Sqm | 3200 | 615454.048 | [6 empty] | 155.6646 | 498126.72
3 | PLY /BOARD CLADDING (Two Layer/Single Sided) : Providing and fixing 12mm thick Natural Fiber Polymer Composite Wood/Board (Eco freindly, Recyclable) board of approved make on existing M.S. frame work including all fixing arrangement complete in all respect . (Partition Length to be measured only) |  | 0 | Sqm | 4500 | 0
4 | PLY /BOARD CLADDING (One Layer/Single Sided) : Providing and fixing 12mm thick Natural Fiber Polymer Composite Wood/Board (Eco freindly, Recyclable) board of approved make on existing M.S. frame work including all fixing arrangement complete in all respect . (Partition Length to be measured only) |  | 53.6054 | Sqm | 2700 | 144734.634 | 208.3532 | 562553.64 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0
5 | LAMINATE PANNELING : Providing and fixing 1mm thick laminate panelling over existing partition as per approved sample including all fixing arrangement complete in all respect. Only finished area to be measured & paid. ( Basic cost of Laminate@ Rs.90/-Sft ). | site specific | 16.5 | Sqm | 1800 | 29700
6 | Providing & fixing 1.2mm thick aluminium. Skirting PVDF coated (100mm height rose gold finish ) / anodised as per approved sample over existing partition including all fixing arrangement complete in all respect. ( Basic cost Aluminium Skirting @ Rs. 450/-Rmtr) |  | 55 | Rmt | 650 | 35750 | [8 empty] | 8.87 | 5765.5
7 | Providing and fixing over head storage with necessary shelves as per design made out of 19mm thick Natural Fiber Polymer composite Board/Wood Material ply fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with 1mm thick laminate including required shelves, shutters and required hardware like handle, knobs, magnetic catcher, hinges, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface laminate@ Rs.90/-Sft |  |  |  |  | 0
a | Size : 450mm |  | 1.7325 | Sqm | 4500 | 7796.25 | [8 empty] | 1.7113 | 7700.625
8 | Providing and fixing Under Counter storage with necessary drawers & Shelves as per design made out of 19mm thick Marine ply board structure fixed with the help of all necessary hardware like nail and fasteners and all internal surface of storage to be finished with 0.8mm thick laminate & external surface to be finished with designer tile, storage includes required shutter / drawer storage unit with required shelves , shutters with required hardware like concealed channel / handle, knobs, magnetic catcher, drawer lock, hinges, shutter lock, drawer channel etc. all are superior quality of approved make & 100mm high Gold Plated finish Aluminium skirting at floor level complete in all respect. also the Storage top will be finish with Marble top in 20mm thickness with dimaond polish all over surface and edge to be double strip with gola polish complete in all respact of detail drawing. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, , Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr) |  |  |  |  | 0
a | Size : 3500mm long x 600mm deep x 850mm high | For Bar back area | 1 | Nos | 72765 | 72765 | [6 empty] | 0.7 | 50935.5 | 0.3 | 21829.5
b | Size : 1300mm long x 600mm deep x 850mm high | For Spa basin counter | 1 | Nos | 35000 | 35000 | [6 empty] | 0.7 | 24500 | 0.3 | 10500
9 | Providing and fixing partly open partly closed Servery counter storage as per drawing made out of 19mm thick BWP / Marine board structure fixed with the help of all necessary hardware like nail and fasteners and all closed internal area of storage to be finished with 0.8mm thick laminate and open area with external finish of 1mm thick SS Sheet cladding of triangle shape emboss texture with white Gold Leafing antique Coating finish all over apart shelf as marble with double patti edge will be fixed with diamond polish shelves for open space, All the external surface area shall be wrapped and finished in designer tile & top surface of survery storage to be finished with plain polish Marble fixed with adhesive & 100mm high Gold Plated finish Aluminium skirting at floor level, including required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, drawer channel, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr) |  |  |  |  | 0
a | Size 5500mm long x 600mm deep x 850mm high - | For kitchen outside servery area | 1 | Nos | 125000 | 125000 | [6 empty] | 0.7 | 87500 | 0.3 | 37500
b | Size 3529mm long x 600mm deep x 850mm high - | For Bar area open lounge | 1 | Nos | 72765 | 72765 | [6 empty] | 0.7 | 50935.5 | 0.3 | 21829.5
c | Size 2000mm long x 600mm deep x 850mm high - | For P Lounge | 1 | Nos | 41580 | 41580 | [6 empty] | 0.7 | 29106 | 0.3 | 12474
10 | Providing and fixing ISLAND Counter storage as per drawing, Storage as per drawing made out of 19mm thick BWP / Marine board structure fixed with the help of all necessary hardware like nail and fasteners and all closed internal area of storage to be finished with 0.8mm thick laminate and open area with external finish of 1mm thick SS Sheet cladding of triangle shape emboss texture with white Gold Leafing antique Coating finish all over apart shelf as marble with double patti edge will be fixed with diamond polish shelves for open space (If Any), All the external surface area shall be wrapped and finished in designer tile & top surface of survery storage to be finished with plain polish Marble fixed with adhesive & 100mm high Gold Plated finish Aluminium skirting at floor level, including required hardware like handle, knobs, magnetic catcher, drawer lock, hinges, drawer channel, shutter lock etc. all are superior quality of approved make complete in all respect. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr) |  |  |  |  | 0
a | Size 4000mm long x 1200mm deep x 850mm high - kitchen outside servery area |  | 1 | Nos | 121400 | 121400 | [6 empty] | 0.7 | 84980 | 0.3 | 36420
11 | Providing and fixing High counter Console as per drawing, structure made out of 19mm thick BWP / Marine board construct in boxing form and fixed to existing wall/panneling fixed with the help of all necessary hardware like nail and fasteners all internal back exposed area surface to be finished with 1mm thick laminate , external front 1mm thick SS Sheet cladding of triangle shape emboss texture with white Gold Leafing antique Coating finish & top surface to be finished with plain diamond polish Marble fixed with adhesive & 100mm high Gold plated finish Aluminium skirting at floor level all around , (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface SS Texture Emboss Antique finish coating Sheet @ Rs.2500/- per Sft, Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr) |  |  |  |  | 0
a | Size 7753mm long x 400mm wide from top with below covered boxing structure x 1050mm high | for Around Large Tree high counter | 1 | Nos | 92400 | 92400 | [6 empty] | 0.7 | 64680 | 0.3 | 27720
12 | Providing and fixing High Counter Ledge as per drawing, made out of 19mm thick BWP Board / Ply structure construct in L form with latak 35mm high in front to covered the base supported MS painted 25x25mm angle frames fixed at maximum 1200mm c/c with the help of all necessary hardware like nail and fasteners. all the Ply surface latak / top finished with plain Marble with diamond polish fixed with adhesive complete as per detail drawing. (Base Price of Marble @ Rs. 450/- per sft ) |  |  |  |  | 0
a | Size 3935mm long x 400mm wide from Top | For High counter Ledge | 1 | Nos | 46200 | 46200 | [6 empty] | 0.7 | 32340 | 0.3 | 13860
13 | Providing and fixing Reception Table ( Size : 1000mm long x 1000mm deep x 750/1050mm high) made out of 19mm thick BWP Board / Ply structure including necessary hardware of superior quality, structure made in double ht form which make front portion along with sides finished in Italion Marble finished with flutted pattern all polish, then worktop / double ht vertical screen in Acrylic surface finish of 12mm thick on base ply with complete buffing /rubbing as per design. front facade, sides & top finish with Italian marble stone of approved make, shade & texture including all fixing arrangement ,grinding polishing, edge chamfering & polishing & all internal surface to be finished with 0.8mm thick laminate & at floor level 100mm high skirting & top & sides edging finished with PVD coated color as approved finish in aluminium . complete in all respect. ( Basic cost of internal laminate @ Rs.28/- sft & external laminate @ Rs90/-Sft & Italian marble stone @ Rs. 1200/- sft + 500 per sft for flutted CNC cutting) & (Acrylic surface @ 900/- per sft, Basic cost PVD finish Aluminium Skirting @ Rs. 450/-Rmtr,) |  | 2 | No | 45000 | 90000 | [6 empty] | 1.4 | 63000 | 0.6 | 27000
14 | Providing and fixing BAR COUNTER front Counter as per drawing structure with necessary drawers & Shelves as per design made out of 19mm thick Marine ply board structure fixed with the help of all necessary hardware like nail and fasteners and all internal surface of Partition / storage to be finished with 0.8mm thick laminate & external surface to be finished with designer tile, internal area shall be finished with worktop at upto 850mm high level with Marble finish polish / Double ht top also finihed in same mable with polish complete along with shape and design . 100mm high Gold Plated finish Aluminium skirting at floor level complete in all respect. Marble top in 20mm thickness with dimaond polish all over surface and edge to be double strip with gola polish complete in all respact of detail drawing. (Basic cost of laminate for internal surface @ Rs. 28/- sft & external surface Metal Pentagon shape mirror reflection + Gold plated finish Tiles (As per sample approved) @ Rs.750/- per Sft, , Marble at Top @ 450/- per sft, Basic cost Gold plated finish Aluminium Skirting @ Rs. 450/-Rmtr) |  |  |  |  | 0
a | Size 3900mm long x overall 700mm deep / Double ht 300mm wide from top x 850/1050mm high | For Bar front counter | 1 | Nos | 64449 | 64449 | [6 empty] | 0.7 | 45114.3 | 0.3 | 19334.7
21 | SOILD PVD SHEET CLADDING : Providing Making & fixing/pasting with approved adhesive in position 1mm thick SS Sheet of grade 304 PVD coated with approved colour, shade, texture & finish over 12mm thick base FLEXI Ply board of approved brand & manufacture, PVD coated sheet shall be wrapped around the base ply frame at site with approved quality adhesive etc complete as per drawings & instructions of Project-in-Charge. cost include the provision of offset spacing for light provision and any back base suface paint in matching shade of PVD finish prior installtion complete as per detail drawing. ( Basic cost of PVD coated SS sheet @ Rs.410/- Sft) (Emboss Print design @ 100/- per sft) |  |  |  |  | 0
a. | Solid Sheet Cladding Plain type 1 |  | 34.9495 | Sqm | 12600 | 440363.385 | [8 empty] | 1 | 12600
b. | Solid Sheet Cladding with Emboss design Print Texture type 2 |  | 0 | Sqm | 17600 | 0
22 | FEATURE ROUND CNC CUT SCREEN : Providing & fixing feature round cnc cut screen made in 1mm thick SS sheet with factory made laser cut design and finished in PVD finished color as approved, Entire RIM will be moulded with Pencil round edge & 3mm dia tube shot welded on end circumference with neat / clean finish buffing prior to PVD coating application. Finished RIM shall be packed and cover with temprory packing wooden patti /frame/box to avoid any damgaes and deliver with safety at site, RIM will be install on Existing wall /partition with heavy duty SS clamp / bracket support including fastner complete as per satisfactory of Project Incharge. |  |  |  |  | 0
a. | Art work Type 1 : Round size 2000mm dia |  | 2 | nos | 65000 | 130000 | [6 empty] | 1.4 | 91000 | 0.6 | 39000
b. | Art work Type 1 : Round size 1500mm dia |  | 2 | nos | 54000 | 108000 | [8 empty] | 2 | 108000 | 2 | 108000
23 | TWISTED BRANCH ELEMENT : Providing, making & fixing twisted tree branch looks design element in ceiling fix on existing ceiling support with using required fixing hardware of fastners,screw,clutch wire as per load bearing and stabilty requirements. Twisted branch element made in approx size of upto 200mm dia x Length as per design & drawing adjoining with neat and clean joints. the twisted branch shall be made in 2-3 or more 25mm dia round Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) twisting to make the hollow tube feature and fix in ceiling with complete finish in duco paint shade as per approved. |  | 66 | RMT | 2100 | 138600
24 | TREE ELEMENT : Providing and fixing Tree of Life Design Element made in part and combine in Tree Element as per design, part element is desicribe and detail below with the specification and material used. Also the element has petal and leaves feature with variable sizes of fixed / decorative light as per the design and requirement which include the all provision for base support and other allied requirements. |  |  |  |  | 0
A. | FOR BAR AREA |  |  |  |  | 0
1 | TRUNK ELEMENT : made in 15mm dia SS pipe with PVD finish as per color /shade approved or detail drawing. Pipe to be fixed and welded with inner circle pipe fitted for support in bottom and top where curve form start, also the curve and horizontal form in ceiling shall be be fitted with ceiling support with neat & clean finish complete as per detail drawing. pipe length is variable as per the design and provision petal/leaves attachment complete in all respact or advise by the Architect. (note : Length to measured as per actual and paid) |  | 211.673 | Rmt | 4500 | 952528.5 | [6 empty] | 145.6 | 655200 | 66.07 | 297315 | 58.63 | 263835
2 | PETAL / LEAVES ELEMENT : Providing, making & fixing Petal / Leaves element to emerge with Tree of life Design Element as per design/ Drawing. Petal / Leaves are made in variable size and finishes as per the design / detail drawing. Design create in two diffrentiate detail L1 & L2 which makes of solid marquise shape form of petal / leaves. (Base price for SS PVD sheet 450/- per sft + 100/- per sft for emboss texture per sft) |  |  |  |  | 0
i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved complete with fixing support above to fixed on ceiling complete as per detail drawing. |  |  |  |  | 0
a. | L1 : Size 130/250/310/395mm Long x 75/125/150/175mm wide x 1 each |  | 21 | Nos | 6500 | 136500 | [8 empty] | 21 | 136500
b. | L2 : Size 220/285/355mm Long x 100/125/150mm wide x 1 each |  | 19 | Nos | 7500 | 142500 | [8 empty] | 19 | 142500
ii) | ii) Grill Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from bottom with perforation for AC air ventilation as per design and drawing complete. |  |  |  |  | 0
a. | L1 : Size 475mm Long x 225mm wide x 1 each |  | 11 | Nos | 3400 | 37400 | [8 empty] | 11 | 37400 | 2 | 6800
iii) | iii) Light Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from top with central area for light provision with side profile light as per design and drawing complete. (Note : LED Profile & light cost not included and will be paid seperate) |  |  |  |  | 0
a. | L1 : Size 620mm Long x 275mm wide x 1 each |  | 11 | Nos | 8600 | 94600 | [8 empty] | 11 | 94600
b. | L2 : Size395/530/620mm Long x 175/225/275mm wide x 1 each |  | 10 | Nos | 8000 | 80000 | [8 empty] | 10 | 80000 | 2 | 16000
B. | FOR HIGH COUNTER AREA |  |  |  |  | 0
1 | TRUNK ELEMENT : made in 15mm dia SS pipe with PVD finish as per color /shade approved or detail drawing. Pipe to be fixed and welded with inner circle pipe fitted for support in bottom and top where curve form start, also the curve and horizontal form in ceiling shall be be fitted with ceiling support with neat & clean finish complete as per detail drawing. pipe length is variable as per the design and provision petal/leaves attachment complete in all respact or advise by the Architect. (note : Length to measured as per actual and paid) |  | 386.375 | Rmt | 950 | 367056.25 | [8 empty] | 386 | 366700 | 38.5 | 36575
2 | PETAL / LEAVES ELEMENT : Providing, making & fixing Petal / Leaves element to emerge with Tree of life Design Element as per design/ Drawing. Petal / Leaves are made in variable size and finishes as per the design / detail drawing. Design create in two diffrentiate detail L1 & L2 which makes of solid marquise shape form of petal / leaves. |  |  |  |  | 0
i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved complete with fixing support above to fixed on ceiling complete as per detail drawing. |  |  |  |  | 0
a. | L1 : Size 130/250/310/400mm Long x 75/125/150/175mm wide x 1 each |  | 40 | Nos | 1500 | 60000 | [8 empty] | 40 | 60000
b. | L2 : Size 220/285/355mm Long x 100/125/150mm wide x 1 each |  | 36 | Nos | 1650 | 59400 | [8 empty] | 36 | 59400
ii) | ii) Grill Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from bottom with perforation for AC air ventilation as per design and drawing complete. |  |  |  |  | 0
a. | L1 : Size 475mm Long x 225mm wide x 1 each |  | 11 | Nos | 1600 | 17600 | [8 empty] | 11 | 17600 | 8 | 12800
iii) | iii) Light Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from top with central area for light provision with side profile light as per design and drawing complete. |  |  |  |  | 0
a. | L1 : Size 615/700/800mm Long x 275/325/350mm wide x 1 each |  | 16 | Nos | 1600 | 25600 | [8 empty] | 16 | 25600 | 7 | 11200
b. | L2 : Size 475/620/700/800/810mm Long x 225/275/325/350/375mm wide x 1 each |  | 15 | Nos | 1600 | 24000 | [8 empty] | 15 | 24000 | 7 | 11200
C. | FOR ISLAND COUNTER AREA |  |  |  |  | 0
1 | TRUNK ELEMENT : made in 15mm dia SS pipe with PVD finish as per color /shade approved or detail drawing. Pipe to be fixed and welded with inner circle pipe fitted for support in bottom and top where curve form start, also the curve and horizontal form in ceiling shall be be fitted with ceiling support with neat & clean finish complete as per detail drawing. pipe length is variable as per the design and provision petal/leaves attachment complete in all respact or advise by the Architect. (note : Length to measured as per actual and paid) |  | 139.0906 | Rmt | 950 | 132136.07
2 | PETAL / LEAVES ELEMENT : Providing, making & fixing Petal / Leaves element to emerge with Tree of life Design Element as per design/ Drawing. Petal / Leaves are made in variable size and finishes as per the design / detail drawing. Design create in two diffrentiate detail L1 & L2 which makes of solid marquise shape form of petal / leaves. |  |  |  |  | 0 | hold
i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved complete with fixing support above to fixed on ceiling complete as per detail drawing. |  |  |  |  | 0
a. | L1 : Size 130/250mm Long x 75/125mm wide x 1 each |  | 46 | Nos | 1500 | 69000
b. | L2 : Size 250/310mm Long x 110/135mm wide x 1 each |  | 46 | Nos | 1500 | 69000
D. | FOR RECEPTION AREA |  |  |  |  | 0
1 | TRUNK ELEMENT : made in 15mm dia SS pipe with PVD finish as per color /shade approved or detail drawing. Pipe to be fixed and welded with inner circle pipe fitted for support in bottom and top where curve form start, also the curve and horizontal form in ceiling shall be be fitted with ceiling support with neat & clean finish, also on wall bottom fixd to profile skirting as per design complete / detail drawing. pipe length is variable as per the design and provision petal/leaves attachment complete in all respact or advise by the Architect. (note : Length to measured as per actual and paid) |  | 450.648 | Rmt | 950 | 428115.6 | [8 empty] | 450.65 | 428117.5 | 9.55 | 9072.5
2 | PETAL / LEAVES ELEMENT : Providing, making & fixing Petal / Leaves element to emerge with Tree of life Design Element as per design/ Drawing. Petal / Leaves are made in variable size and finishes as per the design / detail drawing. Design create in two diffrentiate detail L1 & L2 which makes of solid marquise shape form of petal / leaves. |  |  |  |  | 0
i) | i) Solid petal and leaves : made of base 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) with 1mm thick SS sheet finished with Plain Mirror finish / hammered texture emboss / Solid Color PVD Coated finished as per the shade approved complete with fixing support above to fixed on ceiling /wall complete as per detail drawing. |  |  |  |  | 0
a. | L1 - Ceiling : Size 305/440/535/585mm Long x 140/440/535/585mm wide x 1 each |  | 32 | Nos | 12000 | 384000 | [8 empty] | 32 | 384000
b. | L2 - Ceiling : Size 350/485/580/640mm Long x 160/175/210/265mm wide x 1 each |  | 32 | Nos | 12000 | 384000 | [8 empty] | 32 | 384000
c. | A&B type Wall Leaf : Size 280/335/410/485/560mm Long x 112/148/192/240/285mm x 1 each |  | 35 | Nos | 12000 | 420000 | [8 empty] | 35 | 420000 | 10 | 120000
iii) | iii) Light Petal / Leaves : made of 18mm thick Natural Fiber Polymer Composite Board wood ( Eco freindly, Recyclable material ) side frame of 25mm wide with 1mm thick SS sheet finished with hammered texture emboss and coated in PVD finished as per the shade approved, covered and wrap from top with central area for light provision with side profile light as per design and drawing complete. |  |  |  |  | 0
a. | L1 - Ceiling : Size 440/485/585/585mm Long x 130/190/225/255mm wide x 1 each |  | 17 | Nos | 13000 | 221000 | [8 empty] | 17 | 221000
b. | L2 - Ceiling : Size 290/440/525/640/mm Long x 110/160/190/255mm wide x 1 each |  | 17 | Nos | 13000 | 221000 | [8 empty] | 17 | 221000
26 | JAALI FRAME SCREEN : Providing and fixing CNC cut pattern as per design Jaali frame screen made in 15mm thick Natural Fiber Polymer Composite Board / Wood / Ply ( Eco freindly, Recyclable material ) around LED TV size approx 55" with side jaali frame of 185mm wide. Jaali with solid 15x15mm profile in outer / inner frame edges and rest part in CNC cut jaali pattern. frame shall be fixed on wall with using SS clamp / bracket / spacers to match with LED depth to make flush / eveness detail, Entire frame will be in Duco Paint fininsh as per the RAL color shade approved by the Architect and complete in all respact. (Size Approx : 1110mm wide x 1635mm high x 15mm thick) |  | 3 | Nos | 25000 | 75000
28 | ELIPTICAL SHAPE NICHE BOX : Providing,making & fixing Eliptical shape niche box made in 12mm thick Natural Fiber Polymer Composite Board / wood / Ply( Eco freindly, Recyclable material ) using 100mm deep niche with backing of 12mm thick ply with 4mm thick thick mirror pasted both side as per niche shape and design with 12x12mm SS PVD finish moulding in front & back, shelf & pelmet box for light inside the niche, side in curve shape with duco paint finish as per the approved detail drawing. ( Overall Niche Box Size 500mm high x 255mm wide x 100mm deep) |  | 29 | Nos | 1700 | 49300 | [8 empty] | 29 | 49300
29 | ANTIQUE MIRROR / DESIGNER GLASS PANNELING : Providing and pasting Antique mirror / Designer glass pasting on wall / partition / panneling using base of 12mm thick Natural Fiber Polymer Composite Board / wood / Ply( Eco freindly, Recyclable material ) and 6-8mm thick Antique mirror with factory cut of eliptical shape cutout for niche as per design in panel, pasted using required silicon or adhesive and complete in all respact to design and approved by the Architect. (Antique mirror / Designer Glass base price @ 550/- per sft) | For bar back / Merchandise wall | 37.4374 | sqm | 8600 | 321961.64 | hold
| TOTAL FOR WOOD WORK FOR WALL PANELLING |  |  |  |  | 7183655.377 | [7 empty] | 1777418.02 |  | 3850566.325 |  | 595482.5
F | FALSE CEILING WORK
1 | FR GRADE GYPSUM BOARD CEILING : Providing and fixing Single Layer Boarding with 12.5mm thick plain and split level with Firebloc gypsum plasterboards, This includes ST50 fully knurled Perimeter Channel (0.50mm thick having one flange of 20mm and another flange of 30mm and a web of 28mm) screw fixed to brick wall/partition/ hanging with existing ceiling / existing MS framework and suspended GI frame with the help of approved screws at 600mm centers. Then suspending ST-50 fully knurled intermediate section (45mm x 0.90mm thick with two flanges of 15mm each) from the soffit at 1220mm centers with ST-50 fully knurled Ceiling L Angle (25x10mmx0.50mm thick) fixed to RCC Slab with USG Boral 227x35x1.5mm Soffit Cleat and 50mm Approved dash Fasteners @ 1200mm Centers respectively. ST-50 profiles are rolled with G.I Steel (120GSM & 230 MPa Yield Strength) Conforming to IS 277. ST-50 fully knurled Ceiling Section (51mm x 0.50mm thick with two flanges of 26mm each) is then fixed to the Intermediate channel with the help of 2.5mm dia wire connecting in a perpendicular direction to the intermediate channel at 457mm centers. 12.5mm thick Firebloc Pasteboards (Conforming to BS 1230 (Parti-1) is screw fixed with 25mm long Drywall screws at 230 mm centers. The screw fixing of gypsum boards to the metal framing at the periphery, openings, and cut edges should be at 150mm centers. All the fire Bloc gypsum plasterboards must be staggered. All joints are to be taped & finished with Paper tape & All-Purpose Joint Compound confirming to ASTM C475. above item include with all the vertical band, curve band, pelmet, cove, split level etc. also wall to wall plan area shall be measured for claim, vendor to quote as per design/dwg. and no extra item/charges will be entartain or approved in any manner. Note : Above item excluding the cost of painting. |  | 108.185 | Sqm | 2000 | 216370 |  |  | 94.9361 | 189872.13
2 | MOISTURE RESISTANT GYPSUM CEILING : Providing and fixing MR grade gypsum board false ceiling including providing and fixing GI grade 175 (120 gm/m2) perimeter, channels (20 x 30 x 27 x 0.50mm thick) fixed to brick masonry / partition / hanging with existing ceiling / existing M.S. frame work and suspended GI intermediate channel. Rate to include making necessary cut out/opening for light fitting A C diffuser, cove, pelmet, band etc. The cut out to have perimeter channel of size 20x27x30x.5mm all round and supported suitably and finally finished with gypsum board and finally finished with two or more coat of paint (Paint cost excluded) of approved make & shade with required tapping the joints, base primer, putty complete in all respect. Rate quoted should be included for all design work, Nothing to be paid extra for design work. ( Actual Plain Area to be measured & paid ).( Male, Female, & Handicap Toilet false ceiling ) |  | 30.415 | Sqm | 2300 | 69954.5 |  |  | 28.59 | 65757
3 | METAL GRID CEILING : Providing and fixing Gl Clip in Metal Ceiling System of 600x600 mm module which includes providing and fixing 'C' wall angle of size 20x30x20 mm made of 0.5 mm thick pre painted steel along the perimeter of the room with help of nylon sleeves and wooden screws at 300 mm center to centre, suspending the main C carrier of size 10x38x10 mm made of G.I steel 0.7 mm thick from the soffit with the help of soffit cleat 37x27x25x1.6 mm, rawl plugs of size 38x12 mm and C carrier suspension clip and main carrier bracket at 1000 mm c/c. Inverted triangle shaped Spring Tee having height of 24 mm and width of 34 mm made of Gl steel 0.45 mm thick is then fixed to the main C carrier and in direction perpendicular to it at 600 mm centers with help of suspension brackets. Wherever the main C carrier and spring T have to join, C carrier and spring T connectors have to be used. All sections to be galvanized @ 120 gms/sqm (both side inclusive), fixing with clip in tiles into spring T with : |  |  |  |  | 0
| GI Metal Ceiling Clip in plain Bevelled edge global white colour plain tiles of size 600x600 and 0.5 mm thick with 25 mm height, made of G I sheet having galvanizing of 100 gms/ sqm (both sides inclusive) and electro statically polyester powder coated of thickness 60 microns (minimum), including factory painted after bending. ( For Kitchen false ceiling) |  | 26.4 | Sqm | 3600 | 95040 |  |  |  |  | 26.28 | 94608
4 | WOODEN CEILING : Providing and fixing Wooden Ceiling for base made in MS Frame rolled section upto 25 to 45mm x 1.6mm thickness (Tubular,angle,channel support frame ) supported to existing sub frame / slab using mechanical / Chemical fastners complete in all respat to ensure the Load bearing capacity technical requirements as per advise by the project incharge. Frame shall be finish at false ceiling level with 12mm thick Natural Fiber Polymer Composite Wood/Board (Eco freindly, Recyclable) Ply cladding as per design & detail drawing. (Paint work shall be excluded & seperate) |  | 165 | sqm | 1800 | 297000 |  |  | 163.7647 | 294776.4546
| TOTAL FOR FALSE CEILING WORK |  |  |  |  | 678364.5 |  |  |  | 550405.5846 |  | 94608
G | FINISHING WORK
1 | Painting & applying of texture paint ( interior / exterior grade) including base preparation with sanding of existing surface of plain wall/partion & repairing with putty for achieving even surface of approved Finish or as per manufacturer etc requirements, Applying of texture base design with coating water based base which is highly abrasion & scratch resistant with 6 coat system & PU Based clear top coat which shall be highly water repellant, Anti-algae & anti-fungal in nature. The coating shall also cover hairline cracks with application method which includes Surface Preparation, 2 coats of two component silicate based primer, Making groove, 2 coats of Cereskaken & 2 coats of PU based clear to,coat and complete as per sample approved by the Architect. |  |  |  |  | 0
a. | Texture Paint Type 1 - (Rough Sand Stone finish shade): Base Rate of Texture paint @ 220/- Per sft, Providing and applying external surface Stone texture coating SKK Eleganstone Sagan approved customized shade consisting of water based Natural Sand stone material which is highly abrasion & scratch resistant with 6 coat system & PU Based clear top coat which shall be highly water repellant, Anti-algae & anti-fungal in nature. The coating shall also cover hairline cracks with application method which includes Surface Preparation, 2 coats of two component silicate based primer, Making groove, 2 coats of Elaganstone Sagan (wet on wet) & 2 coats of PU based clear top coat. |  | 0 | Sqm | 2900 | 0
b. | Texture Paint Type 2 - (Lenaluck - Hammering shade) : Base Rate of Texture paint @ 85/- Per sft, Providing & Applying Resin Texture (SKK Lenaluck) (Spray Finish/Roller Finish) to be on (smooth plaster/concrete) surface with (spray/roller) textured coating by SKK, which is Acrylic resin body (spray/roller) textured coating with Singapore Green Mark Certificate. Primer coat to be of (SKK Color Binder EX), Texture Coat: SKK Lenaluck (Spray Finish/Roller Finish), a water reducible modified acrylic resin reinforced (spray/roller) body texture, Final Coat to be (Compo Silicon W55), scaffolding including. | In Entire Lounge area ceiling | 280 | Sqm | 1320 | 369600 |  |  |  |  | 278.5 | 367620
2 | Plastic Emulsion Paint : Providing & Applying three or more coats of Acrylic Plastic Emulsion Paint of approved make & shade including preparation of base by Acrylic based putty & primer complete in all respect. ( Ceiling/wall as per design and site) |  | 200 | Sqm | 400 | 80000 |  |  |  |  | 200 | 80000
3 | Duco / PU Paint : Providing & Applying Duco / PU Paint as per approved color, shade and sample approve by the Architect, base to be prepare on dry surface with smooth / plain with proper sanding with duco / PU patti 3-4 coat and make it smooth to receive the final finish paint with spray machine including base primer complete as the instructuion by the manufacturer or satisfactory level of finish by the Project Incharge. |  | 15 | SQM | 4000 | 60000
4 | WallPaper : Providing & fixing Fabric backed Vinyl Wall covering(10.05mtr. X .52mtr ) ( 300gsm Type-II) fire Retardant as per approved sample including all fixing arrangement complete in all respect. ( Basic cost of Fabric backed Vinyl Wall covering @ Rs. 90/- per sft ) | As per dwg / Elevation | 409.1573 | Sqm | 1350 | 552362.382 | [5 empty] | 0 | 312 | 421200 | 55.8289 | 75369.015
| TOTAL FOR FINISHING WORK |  |  |  |  | 1061962.382 | [5 empty] | 447620 |  | 421200 |  | 75369.015
G | MISC WORK
1 | Providing & filling 50mm thick Fibre Glass wool ( 64kg density ) in M. S. frame work for partition wall for making sound proof |  | 0 | Sqm | 550 | 0
2 | Providing & fixing 6mm thick silver back finish looking mirror with adhesive of approved make on existing Natural Fiber Polymer composite Board/Wood Material ply as per design including all fixing arrangement complete in all respect. ( Basic cost of looking Mirror @ Rs. 120/- Sqft) |  |  |  |  | 0
a. | Mirror Panneling with back ply - For Ladies toilet full ht mirror |  | 2 | Sqm | 2750 | 5500 | [8 empty] | 2 | 5500
b. | Mirror with SS PVD Finish Profile Frame and back ply : Size 800mm long x 900mm high - For Toilets |  | 5 | Nos | 4500 | 22500 | [8 empty] | 2 | 9000
3 | Providing & fixing Trims profile in wall partition,floor,ceiling etc in Rose Gold or approved color finish as per approved sample fixed with adhesive of approved make including all fixing arrangement complete in all respect. |  |  |  |  | 0 | [9 empty] | 0
a | L- angle profile ( 12mm x 12mm x 1.5mm thick )( Basic cost of profile @ Rs. 350 Rmtr. ) | site specifc | 55 | Rmtr | 550 | 30250 | [8 empty] | 55 | 30250 | 17.26 | 9493
b | Transition Profile : size 25mm wide - For where change in in floor such carpet,wooden floor,tile, stone etc. ( Basic cost of profile @ Rs. 350 Rmtr. ) | site specifc | 15 | Rmtr | 650 | 9750 | [8 empty] | 15 | 9750 | 79 | 51350
c | Insert BRASS Strip Trims - size 5mm wide on top x 4mm thick x 25mm deep, Base Price Rs. 550/- per rmt | site specifc | 25 | Rmtr | 860 | 21500 | [8 empty] | 26.6 | 22876 | 1.6 | 1376
4 | P/F Planter Threshold (size 100mm thick x 150mm high) made in MS frame 25x25 with 1.4mm thickness and cladd with single layer of BWP Natural Fiber Polymer composite Board/Wood Material Board all around with hardware as required and finish with approved material as per below and pasted with required ashesive and buffing polish complete as per the design. |  |  |  |  | 0 | [9 empty] | 0
a | Type 1 with Corion finsh, Base price of marble Rs. 850/- per sft |  | 10 | Rmt | 2450 | 24500 | [9 empty] | 0
b | Type 2 with Marble finsh, Base price of marble Rs. 900/- per sft |  | 7 | Rmt | 2450 | 17150 | [9 empty] | 0
5 | Curtain : Providing and installing Curtain made in approved fabric shade and color with fabric transperency as approved, cost include the curtain track channel single/double along with curtain hold tie and complete as per the design and requirements. |  |  |  |  | 0 | [9 empty] | 0
a. | Shear Curtain : Base Price of fabric @ 450/- per mtr |  | 0 | sqm | 650 | 0 | [9 empty] | 0
b. | Fabric Curtain : Base Price of fabric @ 850/- per mtr |  | 0 | sqm | 1050 | 0 | [9 empty] | 0
6 | Roller Blind : Providing and fixing Roller blind of approved shade, color and fabric. Fabric shall be woven from formulated platisol extruded over a polyaster yarn. The fabric should be weaved to provide subtle view of the side of the blind and should offer elimination of glare and sunlight radiance upto a minimum of 80%. The fabric shall be flame retardant.The fabric should have 3% openess. Roller Tube shall be of extruded Aluminium alloy 38mm O.D with a minimum wall thickness of 1.0mm duly anodised for long life. Clutch shall be wrap spring design with high strength fibreglass reinforced polyster assembly and high carbon steel springs to transmit motion from driving to driven members of clutch mechanism. Clutch shall operate by directionally with the use of an endless beaded chain. Clutch mechanism shall be crash proof, prevent slippage and shall raise and lower smoothly to any desired height.Clutch shall never need adjustment. Installation Brackets shall be of tomised steel powdercoated to give superior finish. Bracket shall accommodateoverhead, side or face mounting with clutch assembly on either end of the roller. Bottom of the blind shall be provided with aluminium tube powder coated in a colour matching to the fabric. The fabric shall be enclosed in the suitably created pocket along with the tube. The tube shall be closed from sides with end caps to give a neat look. All complete (shade a approved; Make : Deck) |  | 0 | Sqm | 3200 | 0 | [9 empty] | 0
7 | Honeycell Blinds : Providing and fixing Translucent Honeycell Blinds. The fabric shall be non woven polyester in double cell structure with high quality sealing in variable of light filtring option. All complete (shade a approved; Make : Deck) |  | 37.312 | Sqm | 3200 | 119398.4 | [6 empty] | 28.2735 | 90475.36 |  | 0
8 | Motor For Blind/Curtain : Providing and installing wired / Wirefree, plug-and-play curtain / Blind motorization by Deck / Somfy or approved make. Designed for silence, Manual operation possible in case of power failure, Adjustable speed, Soft start and Soft stop, Touch Motion, Powered / Battery operated motor, model as per requirement and approved. motor for single roller track / Curtain track considered. |  | 7 | Nos | 27000 | 189000 | [6 empty] | 8 | 216000 |  | 0
9 | Remote : Providing a five channel remote control to control one piece or one group of equipments simple intuitive control with operating and memory “Memory” function to memorize your favourite position of the application and find it instantly by pressing “memory” button Modern aesthetic design, comfortable in the hand thanks to a modern soft touch finish, discreet and elegant wall support. all complete single Remote to operate the motorised curtain & blind. |  | 3 | Nos | 1200 | 3600 | [6 empty] | 4 | 4800 |  | 0
6 | Providing & fitting extra support arrangements for chandlier hangging as per requirements with MS support frame/ Ply support complete with all the fastner hardware as required. |  | 0 | Nos | 3000 | 0 | [9 empty] | 0
7 | Expansion Joint Trims/Profile : Providing and fixing Expansion joint cover Trim made in SS with PVD finish size upto 150mm wide complete as per manufacturer details and all ht level. Base rate of Trims @ Rs. 1500 Per mtr. (Cost not include of Expansion joint treatment between slab and will be seperate) |  |  |  |  | 0 | [9 empty] | 0
a | Floor |  | 11.09 | Rmt | 650 | 7208.5 | [9 empty] | 0
b | Ceiling |  | 11.09 | Rmt | 650 | 7208.5 | [9 empty] | 0
c | wall |  | 28 | Rmt | 650 | 18200 | [8 empty] | 26.4 | 17160
9 | Artifact of approved design , texture , shape fix in wall/ceiling or placing with require hardware and arrangements support, complete as per design. |  |  |  |  | 0 | [9 empty] | 0
a. | Artifact element - Large, Base Range Rs. 255000/- each, | In Reception area | 6 | Each | 295000 | 1770000 | [8 empty] | 6 | 1770000
b. | Artifact element - Mid size, Base Range Rs. 175000/- each |  | 0 | Each | 240000 | 0 | [9 empty] | 0
c. | Artifact element - small size, Base Range Rs. 85000/- each |  | 0 | Each | 160000 | 0 | [9 empty] | 0
d. | Wall Art element 1 - As per design and approved, Base range Rs. 8500/- each, custom made SS Framed /1mm thick sheet of PVD Mirror finish Petals. Size 225mm high x 100mm wide | As per design / Elavation | 13 | Each | 12500 | 162500 | [6 empty] | 13 | 162500 |  | 0
e. | Wall Art element 2 - As per design and approved, Base range Rs. 15000/- each, custom made SS Framed /1mm thick sheet of PVD Mirror finish Petals. Size 450mm high x 200mm wide | As per design / Elavation | 23 | Each | 22500 | 517500 | [6 empty] | 23 | 517500 |  | 0
f. | Artifical Turf / Creeper bail Green wall : Made with fine quality polyester fabric which is long lasting, easy to clean and maintain. Material – Polyester Fabric, strings – Strings, Length – 6ft,approx. Area to covered approx 30 sqm floor /wall , Base range @ 150/- per String for creeper & Turf base price Rs. @ 120/- per sft, Note : Dense for string qty shall be advise by the Architect to enhance the green wall look. | In planter area | 1 | LS | 25000 | 25000 | [8 empty] | 1 | 25000
11 | Access Panels ; Providing Access Panel Trap Doors with not more than 1/16" shadow/gap on finished surfaces. Panel inlay duplicates wall and ceiling specifications to ensure acoustic integrity. Hardware free finish, opens with concealed touch-latches. The panel can be removed completely for full access. Access Panels arrive ready for installation with factory installed gypsum board inlay. Aluminium extrusion with gypsum board installed. |  |  |  |  | 0 | [9 empty] | 0
a | Size- 450x450 mm |  | 4 | Each | 3200 | 12800 | [8 empty] | 4 | 12800
23 | TOILET CUBICAL : Supply & Installation of fixing 18mm box up series Cubical of specified dimensions ( approximately 1200 x 2000mm each ) made from solid grade compact high pressure laminate as per IS:2046 manufactured under high pressure >5MPa and temperature 120degree C with bunch of Kraft papers, impregnated with thermo setting phenolic resin and decorative papers made of cellulose fibre, impregnated with thermosetting melamine resin which provides superior scratch , abrasion, heat, chemical, impact, graffiti moisture resistance along with anti bacterial properties of approved make Marion or equivalent; |  |  |  |  | 0 | [9 empty] | 0
| DOORS: All doors will be of single colour and made of 18 mm thick HPL compact panel or equivalent with chamfered edges, minimum three SS hinges affixed to pilasters, SS door knob, SS coat hook on each panel of door. The Door will be routed at the vertical ends and the rubber sponge lining will be inserted in the routed ends. |  |  |  |  | 0 | [9 empty] | 0
| PILASTERS: All pilasters will be made of 18 mm thick HPL Compact Panel or equivalent and completed with SS made lock set, comprising thumb -turn and occupancy indicator. Pilasters will be anchored to teh floor using steel made L Brackets and box up fixtures used for covering the floor anchored mechanism. All pilasters will be routed at vertical ends to facilitate closure of doors. |  |  |  |  | 0 | [9 empty] | 0
| DIVIDERS: All intermediate partitions or dividers will be made of 18mm thick HPL Compact laminate panels. They are fixed with SS made U-channels at their ends for stability. Design finish as sopecified in teh drawings and sizes etc as per drawings. |  |  |  |  | 0 | [9 empty] | 0
| HASRDWARE & ACCESSORIES : Corner joinery section made of SS grade 304, brush finish, of size 40x16x0.8mm with thick plastic film pasted for surface protection. Wall joinery section with hamming profile of size 21x22x0.8mm, Fixed front panel to be anchored to floor with L Bracket of SS316 and covered with SS316 grade box type plate from all directions with 100 mm clear height from ground, Matt finish surface. SS grade 304 butt hinges Matt finish, coat hook of SS304 grade lacquer finish with rubber stopper, round knob 30mm dia of SS304 grade lacquer finish, SS 304 grade screws, anti-rotation nylon polyamide grade-6 expandable wall plugs etc complete as per approved design, shade, colour, size etc complete |  |  |  |  | 0 | [9 empty] | 0
| Divider, Pilaster and other fixed panels including doors one number per cubicle. Make : Action Tessa / Green / Merino |  | 4 | Nos | 30500 | 122000 | [8 empty] | 4 | 122000
24 | FROST GLASS FILM : Providing and Pasting Frosted Glass film on Existing Glass partition surface with using Liquid shampoo spraying to set the plotter and wiping process with rubber clipper to ensure all bubble removal and any gap complete in all respact to the satisfaction of Project Incharge. * Face Film appearance 80 micron cast film with frosted. * Back with self Adhesive permanent, acrylic based. * Backing paper one side coated bleached kraft paper, 135 g/m2. * Durability: 15 years (indoor)/ 7 years (outdoor) Make : Avery / 3M / Garware | Existing Glazing | 18.656 | sqm | 1800 | 33580.8 | [8 empty] | 18.66 | 33588 | 9.717 | 17490.6
| TOTAL FOR MISC WORK |  |  |  |  | 3119146.2 | 0 | 0 | 0 | 0 | 0 | 0 | 76.2736 | 991275.36 |  | 2057924 |  | 79709.6 | 0 | 0 | 0 | 0
A | Total Basic |  |  | ₹ |  | 18918369.3808 | 104.1766 | 562553.64 | 313.3556 | 3641121.8346 | 384.0365 | 1004360.933 | 423.7801 | 3821193.7656 |  | 8098719.26 |  | 1189566.56 | 0 | 0 | 0 | 0
B | Taxes |  |  | ₹ |  | 3405306.4885 | 18.7518 | 101259.6552 | 56.404 | 655401.9302 | 69.1266 | 180784.9679 | 76.2804 | 687814.8778 |  |  |  |  | 0 | 0 | 0 | 0
C | Price [A+B] |  |  | ₹ |  | 22323675.8693 | 122.9284 | 663813.2952 | 369.7596 | 4296523.7648 | 453.163 | 1185145.9009 | 500.0605 | 4509008.6434 |  |  |  |  | 0 | 0 | 0 | 0