## SUMMARY
Semolina Kitchens Pvt.Ltd.
Project : Shawarama,Taco,Burger
PO NO : PO/SKPL/23-24/001637
Venodr Name : Pioneer Infra
Bill : RA 03
SUMMARY OF BILL
Sr.No. | Item Description | PO Value | Previous Bill Amt | This Bill Amt | Cumulative Amt | Variance Amt
1 | CVCP | 2674013.4 | 1419565.18 | 824666.305 | 2244231.485 | 429781.915
2 | PLUMBING | 151425 | 109041 | 68595 | 177636 | -26211
3 | HVAC | 598200 | 80249.5 | 428236.5 | 508486 | 89714
4 | LIGHTING | 295750 | 0 | 275460 | 275460 | 20290
5 | ELECTRICAL | 1007750 | 290308 | 448840 | 739148 | 268602
6 | CCTV | 76250 | 0 | 76250 | 76250 | 0
7 | FIRE & SAFETY | 109400 | 0 | 0 | 0 | 109400
8 | OTHERS | 50150 | 0 | 0 | 0 | 50150
9 | Extra Payment in plumbing RA 2 so in this bill the extra amount will be deduct |  |  | -56561 | -56561 | 0
NET TOTAL |  | 4962938.4 | 1899163.68 | 2065486.805 | 3964650.485 | 941726.915
GST 18% |  | 893328.912 | 341849.4624 | 371787.6249 | 713637.0873 | 169510.8447
TOTAL |  | 5856267.312 | 2241013.1424 | 2437274.4299 | 4678287.5723 | 1111237.7597
Note on D8: Divesh Tripathi: ok as per last ra bill
Note on D9: Divesh Tripathi: as per pioneer they are saying they get double amount in plumbing
Note on D10: Divesh Tripathi: ok as per last bill amount is ok
Note on D12: Divesh Tripathi: ok as per last ra bill

## CVCP
BILL OF QUANTITIES- INTERIOR WORKS
D41- Shawarma,Tacos,Burger
|  |  | AS PER PO |  |  |  | Previous Bill Amount(INR) |  | This Bill Amount (INR) |  | Cumulative Amount (INR)
S. No. | Location | Description | Unit | Qty | Rate | Amount | Qty | Amount | Qty | Amount | Qty | Amount
Preamble
| a | Base Rate shall mean the landed cost of material at site excluding all taxes and duties (Net of GST). Base rate also includes loading, transport, packing, forwarding, unloading and handling charges (FOR site) required for the works to be executed but exclude contractor’s profit and overheads.
| b | The item rate shall include cost of equipments and machineries, all leads and lifts, loading and unloading charges, transportation cost and conveyance of all material and all other incidental charges etc., complete for successful completion of work and as directed by the project manager.
| c | The BOQ shall be read in conjunction with the available drawings, technical specifications and FFE.
| d | Teak Wood to be used unless specified by project manager.
| e | Veneer to be used - TEAK STRAIGHT LINE unless specified
| f | Hardwood used shall be kiln seasoned, fire retardant and anti-termite treated of adequate and approved size. Timber used should be free from shrinkage. The size and distance of placing may vary as per Site conditions and drawings as instructed by project manager.
| g | All flooring items shall be inclusive of protection with adhesive sheet/ cello bubble roll on the flooring till final handover to avoid breakage. Any breakage till final handover to Operations Team shall be the responsibility of the contractor.
| h | All flooring items shall be of minimum thickness specified in the item and no extra cost shall be paid for any thickness over and above the minimum specified thickness. Nothing extra to be paid for wastage.
| i | All paints shall have low VOC / zero VOC. For all types of paint, Contractor shall provide product warranty of minimum 7 years.
| j | The Contractor has to do the housekeeping on daily basis without claiming any additional cost.
| k | Storage and safety of materials shall be the responsibility of the Contractor.
| l | Barricading material for the safety and work progress to be arranged by the concern contractor
| l | Shift working in operational areas to be considered by the vendor. Prior approval of the logistic and shift working to be taken by the contractor.
1 | Location | FLOORING, SKIRTING & CLADDING WORKS
1.1 |  | FLOORING
1.1.1 | TL-01 FOH FLOOR | Providing & Laying FULL BODY VITRIFIED PRINTED TILES TL-01 of Size 600x600 mm, Make, Grout as specified in the drawing or material schedule, refer as shown in flooring layout. Plan area to be measured. Base Rate of Tile - Rs.100/- Sq.Ft | Sqm | 18 | 1920 | 34560 | 16.02 | 30758.4 |  | 0 | 16.02 | 30758.4
1.1.1 | TL-02 FOH FLOOR | Providing & Laying FULL BODY VITRIFIED WOODEN TILES TL-02 of Size as per material schedule, Make, Grout as specified in the drawing or material schedule, refer as shown in flooring layout. Plan area to be measured. Base Rate of Tile - Rs.100/- Sq.Ft | Sqm | 48 | 1920 | 92160 | 47.1 | 90432 |  | 0 | 47.1 | 90432
1.1.2 | TL-03 BOH FLOOR | FULL BODY VITRIFIED TILE , Size- 600x600mm, Make - Nitco, Product Code - BELGIUM GREY TILE, refer as shown in detail drawing. Base Rate of Tile - Rs.100/- Sq.Ft. | Sqm | 42 | 1920 | 80640 | 40.8075 | 78350.4 |  | 0 | 40.8075 | 78350.4
1.2 |  | INLAY & TRANSITION PROFILE
|  | Providing & fixing of Transition profile, custom made in desired location as per drawing, in between different types of flooring materials or wall cladding materials, including all necessary fixing arrangements etc. complete as per design and drawing as per satisfaction of Project Manager. | [7 empty] | 0
1.2.1 | MT-01 | Flooring 5mm w metal SS trim profile at the corner of flooring as shown in detail drawing & design. | Rm. | 35 | 850 | 29750 | 0 | 0 | 33.5 | 28475 | 33.5 | 28475
1.3 |  | TILE CLADDING
|  | Providing and fixing tiles in cladding/ dado/ jamb/ soffit/ cill of uniform thickness, size, shade and pattern as approved, fixed with rich cement slurry over a bedding plaster of cement mortar 1:3 (1 cement : 3 fine sand) of minimum 20mm or more thickness/ 7mm thick adhesive to masonary/RCC structure, including the cost of rough base plaster, providing grooves using 2/3mm PVC spacers and grouted with EPOXY grouts of laticrete / Kerakoll make to match shade of tile, cleaning with acid wash, cutting of tile for electrical switches and sockets, curing, Cello bubble/ Adhesive sheet roll for protection layer etc. complete in all respects as per drawing and as directed by Project Manager. | [5 empty] | 0 |  | 0 | 0 | 0
1.3.1 | TL-04 SHAARMA BOH AREA | Providing & Laying FULL BODY VITRIFIED PRINTED TILES TL-04 of Size 300x300mm as per material schedule, Make, Grout as specified in the drawing or material schedule, refer as shown in flooring layout. Plan area to be measured. Base Rate of Tile - Rs.210/- Sq.Ft | Sqm | 7 | 3450 | 24150 | 2.681 | 9249.45 | 0 | 0 | 2.681 | 9249.45
1.3.2 | TL-05 SHAARMA BOH AREA | Providing & Laying FULL BODY VITRIFIED WHITE SUBWAY TILES TL-05 of Size 74X300 mm as per material schedule, Make, Grout as specified in the drawing or material schedule, refer as shown in flooring layout. Plan area to be measured. Base Rate of Tile - Rs.150/- Sq.Ft | Sqm | 5 | 2750 | 13750 | 4.2 | 11550 | 0 | 0 | 4.2 | 11550
1.3.3 | TL-06 FOH WALL | Providing & Laying Ceramic CLEO MUSTARD GLOSSY SUBWAT WALL TILE TL-06 of Size 75X300MM, Make, Grout as specified in the drawing or material schedule, refer as shown in wall finishes layout. Base Rate of Tile - Rs.150/- Sq.Ft. | Sqm | 17 | 2780 | 47260 | 10.836 | 30124.08 | 0 | 0 | 10.836 | 30124.08
1.3.4 | TL-07 MASALA KITCHEN BOH AREA | Providing & Laying FULL BODY VITRIFIED MOROCCAN TILES TL-07 of Size 300X300 mm as per material schedule, Make, Grout as specified in the drawing or material schedule, refer as shown in flooring layout. Plan area to be measured. Base Rate of Tile - Rs.210/- Sq.Ft | Sqm | 15 | 3450 | 51750 | 9.996 | 34486.2 | 0 | 0 | 9.996 | 34486.2
1.4 |  | SKIRTING 7 Rails | [7 empty] | 0
1.4.1 | Tile Skirting | Providing & Fixing 100mm high skirting made of tile matching with Flooring TL03 to be provided as shown in the detail drawing and design. Base Rate of Tile - Rs.100/- Sq.Ft. | Rm. | 20 | 350 | 7000 | 0 | 0 | 14.6 | 5110 | 14.6 | 5110 | QTY MATCH WITH JMR
1.4.2 | SS floor rail | Providing & Fixing 50mm DIA SS floor rail to be provided in front of counter as shown in the detail drawing and design. | Rm. | 14 | 3000 | 42000 | 0 | 0 | 12 | 36000 | 12 | 36000
1.4.3 | SS Skirting | Providing & Fixing 100mm high SS skirting MT-01 to be provided in FOH as shown in the detail drawing and design. | Rm. | 16.6 | 1180 | 19588 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waterproofing | [7 empty] | 0
1.5 | Waterproofing Work | Providing and applying 2 Coats of Chemical Waterproofing of make Fosroc brush bond RFX water proofing)with 20x25mm fosroc nitobond sbr coving. including curing. As instructed by the client. Complete as per drawing details / Instructions by Design Team / site-incharge | Sqm | 103.88 | 950 | 98686 | 40.3038 | 38288.5625 | 0 | 0 | 40.3038 | 38288.5625
1.6 |  | Base Preparation | [5 empty] | 0 |  | 0 | 0 | 0
1.6.1 | Bund Wall | Bund Wall : Providing & Constructing bund wall in Brick masonry of width 1000mm and 500 mm ht.with well burnt brick with Cement Sand mortar in 1:4 ratio in proper line, level & plumb. should be provided complete with proper line, level, plumb & curing. (Rate inclusive of all necessary tools, tackles, shuttering, propping, scaffolding, chisellng of existing floor & cleaning etc.) Complete as per drawing details / Instructions by Design Team / site-incharge Without Stiffners. | Rmt | 12.26 | 1340 | 16428.4 | 0 | 0 |  | 0 | 0 | 0
1.6.2 | Screeding | Providing and laying in position cement concrete screeding 25mm of specified grade excluding the cost of centering and shuttering | Sqm | 42 | 900 | 37800 | 40.3038 | 36273.375 | 0 | 0 | 40.3038 | 36273.375 | 36273.375
1.6.3 | Ciporex Filling | Providing and filling the sunken portion of slab with Ciporex etc. with cinder concrete in 1:3:6 mix (1 cement, 3 fine sand and 6 cinder), complete. | Sqm | 42 | 1050 | 44100 | 40.3038 | 42318.9375 | 0 | 0 | 40.3038 | 42318.9375 | 42318.9375
1.6.4 | PCC | Providing & Laying PCC 50mm thick , manual/Machine mixed Plain Cement Concrete in volumetric proportion 1:3:6 - specified thickness, Mix and gradation incl. centering, Shuttering if required, laying spreading, Ramming consolidating and curin,PCC work for tile flooring. | Sqm | 42 | 900 | 37800 | 40.3038 | 36273.375 | 0 | 0 | 40.3038 | 36273.375 | 36273.375
|  | Sub Total |  |  |  | 677422.4 |  | 438104.78 |  | 69585 |  | 507689.78
2 |  | FALSE CEILING WORKS
2.1 |  | FALSE CEILING
2.1.1 | Giproc Gupsum Ceiling | Providing & fixing Gypsum False Ceiling with 12.5 mm thick Gypsum boards & G.I. Frame work at any height/ level (as per India Gypsum specifications). Framework shall include necessary extra supports from Slabs, Steel Girders & Purlins as required. including making cutouts and providing extra supports for light fittings, grills, diffusers, speakers, smoke detectors, sprinklers and at joints of boards etc and also includes necessary vertical fascia at drops, Offsets, grooves, chamfering, molding, Template for casting sheets , Bends, all joints of ceiling tiles filled and finished with India Gypsum jointing compound, jointing tapes etc. as per directions of the architect. complete as per specifications to entire satisfaction of Engg in charge/ Architect for all leads & lifts. Plan area will be measured for the ceiling. | Sqm | 61 | 1145 | 69845 | 61 | 69845 | 0 | 0 | 61 | 69845 | 69845
2.1.2 | Wooden Plank ceiling | Wooden Ceiling:- Providing and installation of wooden ceiling in plank shape made out12mm thick fire rated ply finished with 1mm thick laminate by using GI/metal frame system.This job includes all lead,lifts for all floor,scafolding,Material & labour etc.complete and nothing will be paid extra for execution of the item.All work is to be executed including the cost of making openings for light fittings, grills, diffusers cutouts made with frame of perimeter channels suitably fixed all complete as per drawing , direction and approval . Only the plan area will be measured for payment. | Sqm | 31.5 | 3400 | 107100 | 31.5 | 107100 | 0 | 0 | 31.5 | 107100 | 107100
2.1.3 | 12mm HDMR Designer Ceiling | 12mm HDMR Designer Wooden Ceiling:- Providing and installation of wooden ceiling in plank shape made out 12mm HDMR Board fixed on base 12mm thick fire rated ply. Top surface shall be finished with PU Paint by using GI/metal frame system.This job includes all lead,lifts for all floor,scafolding,Material & labour etc.complete and nothing will be paid extra for execution of the item.All work is to be executed including the cost of making openings for light fittings, grills, diffusers cutouts made with frame of perimeter channels suitably fixed all complete as per drawing , direction and approval . Only the plan area will be measured for payment. | Sqm | 13.5 | 4500 | 60750 | 13.5 | 60750 |  | 0 | 13.5 | 60750 | 60750
2.1.4 | MS mesh ceiling | MS mesh Ceiling: Providing and fixing metal MS mesh ceiling with outer frame made in 38x38mm ms Pipe and mesh in approved design with powder coating with profile light on bottom edge. All work is to be executed including the cost of making openings for light fittings, grills, diffusers cutouts made with frame of perimeter channels suitably fixed all complete as per drawing , direction and approval . | Nos | 10 | 3500 | 35000 | 10 | 35000 |  | 0 | 10 | 35000 | 35000
|  | Sub Total |  |  |  | 272695 |  | 272695 |  | 0 |  | 272695
3 |  | PAINTING WORKS
(Quoted Rate shall be for all heights, depths, levels, leads and lifts. All paints must be very low or zero VOC).
3.1 |  | PAINT FINISH
3.1.1 | PT-01 (Ceiling +Walls) | Providing and applying three (minimum) coats of PT-01 Royal Emulsion Luxury Paint, Make - Asian Paints, as specified in drawing, with a coat of approved primer including the cost of scraping, levelling & preparing the surfaces with filling materials (putty) required primer, along with sand papering wherever required, scaffolding etc. complete as per specs with giving necessary drying period for each coat of approved colours and shade with roller. Contractor must get sample approved by the Architect before executing. All complete to the entire satisfaction of Project Manager. Refer finishing schedule for the Paint code. | Sqm | 108 | 400 | 43200 | 0 | 0 | 73.8459 | 29538.36 | 73.8459 | 29538.36
|  | Sub Total |  |  |  | 43200 |  | 0 |  | 29538.36 |  | 29538.36
4 |  | PARTITION & PANELLING WORKS
4.1 |  | PARTITION & PANELLING WORK
4.1.1 | Bison Board Panelling (with Single Frame) | Providing & fixing paneling made of 12mm thk. Bison Board on one side of MS framework of 40x40mm @ 600mm c/c bothways (framework to be followed with Fire Resistant Coating) along with existing Airport's walls to receive different finishes (as specified) over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures. | Sqm | 29 | 2750 | 79750 | 28.42 | 78155 |  | 0 | 28.42 | 78155 | 78155
4.1.2 | 150mm Thick Bison Board Partition (with Double Frame) | Providing & fixing 150mm thick partition made 12mm thk. Bison Board on both side of double MS framework 40x40mm @ 600mm c/c bothways (framework to be followed with Fire Resistant Coating) as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures. Note: 125mm depth to be achieve by double MS framework and bison board on both side of it. Finishes on both sides are exclusive of this depth. | Sqm | 9 | 4200 | 37800 | 13.562 | 56960.4 | 0 | 0 | 13.562 | 56960.4 | 56960.4
4.1.3 | 88 mm thick Bison Board Partition (with Single Frame) | Providing & fixing 88 mm thick partition made 12mm thk. Bison Board on both side of MS framework 40x40mm @ 600mm c/c bothways (framework to be followed with Fire Resistant Coating) as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures. Note: 125mm depth to be achieve by double MS framework and bison board on both side of it. Finishes on both sides are exclusive of this depth. | Sqm | 27 | 2750 | 74250 | 0 | 0 | 25.955 | 71376.25 | 25.955 | 71376.25
4.1.4 | 100 mm thick Siporex blocl wall | Providing & laying Light Weight siporex Block Filling 100mm thick in cement mortar 1:4 in equal layers including compaction curing etc completed at any height as directed by Architect | Sqm | 27 | 1100 | 29700 | 0 | 0 |  | 0 | 0 | 0
4.1.5 | Stand alone partition | Providing & Fixing stand alone partition of size 1000mm x900mm outer framing made with 38x38mm ms pipe fixed on floor finished with paint PT-13, center portion to be fabricated in 6mm MS tube in design pattern fixed on 3mm thick 12mm wide MS strip finished with paintPT-04, top shall be finished 12mm thick corian (CR-02) fixed on 8mm thick Fr ply.All complete as per the details, drawings or as directed by Architect/Engineer. | Nos | 4 | 17500 | 70000 | 0 | 0 | 4 | 70000 | 4 | 70000
5 |  | CLADDING WITH SS SHEET |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
5.1 | SS Sheet Cladding MT-01 (directly over existing panelling) | Providing, making & fixing of 1mm thk. SS sheet (Grade 304), fixed over existing wall/panelling surfaces with approved adhesive, as shown in drawing, all to be made & fixed with necessary arrangements & hardware- screw, adhesive, etc., as per approved sample. Rate is inclusive of all wastage, all incidentals, cutting, fixing, lead, lift, scaffolding, staging, provision for opening if any required for MEP services, as shown in drawing, complete in all respect as per drawing, designs and directions by Architect/Project-In-charge. | Sqm | 17 | 5300 | 90100 | 0 | 0 | 15.3733 | 81478.49 | 15.3733 | 81478.49
|  | Sub Total : |  |  |  | 381600 |  | 135115.4 |  | 222854.74 |  | 357970.14
5 |  | MS/SS WORKS & MISCELLANEOUS WORK
SITE BARRICADING
5.1 |  | Providing and fixing MS framing with GI pre-painted corrugated sheet (3m high) to cover construction portion as indicated in architect's drawing including all fixing material as per requirement of the PMC, provision of secured pedestrian access doors through barricade including all civil work and foundation etc. The barricade will have to be retained and maintained by the contractor till the end of the project. The barricade must be structurally sound to withstand wind and other applicable loads. ( ONLY ACTUAL SURFACE AREA OF THE COVERING TO BE MEASURED FOR PAYMENT ONCE UPTO THE COMPLETION OF THE WORK. ) | Sqm | 85 | 1100 | 93500 | 51 | 56100 | 16.3728 | 18010.08 | 67.3728 | 74110.08 | 56100
5.2 |  | Providing & Fixing fabricated MS Structure using Heavy Duty / Section / C Sections, all the joints to be properly welded, anchored with necessary accessories, cliquets as per detail drawing and as instructed. MS section to be painted with 1 Coat of Red Oxide and Two coats of Enamel Paint of approved shade Complete as per drawing details / Instructions by Design Team / site-incharge. The cost shall be calculated based on the weight of the structure. The cost is inclusive of Paint and Red Oxide. | Kg | 3300 | 121 | 399300 | 2250 | 272250 | 0 | 0 | 2250 | 272250 | 272250
5.3 | DMB Sturcture | Providing and fixing in position MS Round Pipe as structure to hang DMB, made of 43mm dia. round MS pipe finished with black powder coating, hanged from roof slab from necessary MS plates and hilti fasteners. Rate shall include all necessary hardware, fixtures. All complete as per the details, drawings or as directed by Architect/Engineer.for43" display | Nos. | 2 | 16000 | 32000 | 0 | 0 |  | 0 | 0 | 0
5.4 | Equipment Loading/Unloading | The item rate shall include cost of all leads and lifts, loading and unloading charges of kitchen equipments and machinaries, DMBs, Electrical items, screens, etc, complete for successful completion of work and as directed by the project manager. | LS | 1 | 25000 | 25000 | 0 | 0 |  | 0 | 0 | 0
|  | Sub Total |  |  |  | 549800 |  | 328350 |  | 18010.08 |  | 346360.08
6 |  | WOOD WORK
6.1 | Front Counter Detail | Providing and fixing 950mm deep complete front counter. Complete box to be made up of 19mm thick FR Ply including shelves, shutters, drawers etc. and front facia made of 12mm thk. CNC cut HDMR board finish with paint B-00A Top and front nosing of partition & complete counter to be finished with Corian CR-01. At front of counter, SS skirting to be provided of 100mm height as mentioned in drawing. Above that CNC cut 12mm thk. HDMR to be provided of pattern as shown in the detail drawing finished with PU Paint B-1001A Further above this, 12mm thk. Provision of LED strip to be made at bottom of nosing of counter & partition both. Rear surfaces of partition & counter and all internal visible surfaces & drawers, shutters of counter to be finished with Laminate LM-02. Sneeze Guard made of toughned glass of thickness as mentioned in drawing with chamfered edges to be provided at top of counter as shown in detail drawing. Cut-out for ban marie to be made in counter as shown in the drawing. Provision of POS machine and cash till/drawer to be made in the counter. Provision for wire manager, electrical etc to completed as per details & design provided or as directed by Architect. Cost includes completing the job including all finishes with all necessary hard ware complete as mentioned in detail drawings. Low Height Partition (as per the drawing) made of 19 mm thk. FR Ply from inside and 12mm thk. HDMR on outer side and top closed with same ply. Finishing of top & front of partition is as explained matching to the counter as shown in detail drawing. Elevation area shall be measured. Base Rate of Laminate - Rs.1400/- Per sheet. | Sqm | 15 | 17500 | 262500 | 8 | 140000 | 7.0036 | 122562.125 | 15.0036 | 262562.125
6.2 | Back Counter | Providing & Fixing total 750mm deep complete back counter and DB box cabinet made of 19mm thk. FR Ply. Complete box to be made up of 19mm thick FR Ply including shelves & shutters finished with lamiate LM-02 from all visible surfaces. Provision of open space to be left at some area as shown in elevation/detail drawing to accomodate equipments under it. Shutter of DB box to be made louvered with 19mm thk. FR Ply finished with laminate finish as shown in detail/elevation drawings. Providing & fixing concealed SS sink & counter mount mixer is included in the job. Top of counter and front nosing to be finished withstone ST01. Provision for sink, mixer, plumbing and electrical points etc to completed as per details & design provided or as directed by Architect. Cost includes completing the job including all finishes with all necessary hard ware complete as mentioned in detail drawings. Elevation area shall be measured. Base Rate of Laminate - Rs.1400/- Per sheet. | Sqm | 9 | 12000 | 108000 | 5.175 | 62100 | 3.6 | 43200 | 8.775 | 105300
6.3 | Overhead Storage Cabinet | Providing and fixing in position 500mm deep Overhead Storage with a horizontal shelf in the center and openable shutters at front. Complete unit & shelf to be made of FR Ply of 19mm thk. finished with laminate LM-01 from all sides. Provision for 25x12mm aluminum strip light to be made under the unit as shown in detail drawing. Menu screens to be fixed over the openable shutters with clip-on system and the shutters behind these to be made upward openable with uplift shockers. Rate shall include all wastage, necessary hardware, fixtures. All complete as per the details, drawings or as directed by Architect/Engineer. Front Elevation Area to be Measured. Base Rate of Laminate - Rs.1400/- Per sheet. | Sqm | 7 | 21000 | 147000 | 0 | 0 | 7 | 147000 | 7 | 147000
6.4 | Counter Bulkhead (On all Side) | Providing & fixing 200mm wide & 350mm high bulkhead made of double MS framework of 40x40mm (framework to be followed with Fire Resistant Coating)wrapped with 12mm thk. Bison board on both inside & out side surfaces & bottom. Outer surfaces & bottom of bulkhead to be provided with a further 6mm CNC cut HDMR Board in horizontal planks finished with PU paint B-100B.Provision to recess signage inside the bulkhead alongwith its electrical point to be made on both left side & front bulkhead. Support of bulkhead to be taken from MS structure provided inside rear bison panelling and bison partition on both left & right side. Please refer the elevation drawing and ceiling drawing for more details of bulkhead and partition/paneling. Rate is inclusive of all necessary hardware & fixtures. Running length of center line of bulkhead from top to be measured. | Rm. | 14 | 4800 | 67200 | 9 | 43200 | 4.3 | 20640 | 13.3 | 63840
6.6 | FLUSH DOOR | Flush Door: Providing and fixing single leaf solid core flush door 35mm thick factory made–., finished on both sides with 1.0mm thick laminate (KM-03) of approved shade as indicated in drawing. Shutter to be lipped on all sides with 12mm thick teak wood beading. Applicable hardwares to be considered for following doors according to requirement as per detailed drawings including below mentioned hardware-Door closer,SS Ball bearing Hinges ,SS foot operated Door stopper,SS Mortise Latch Lock / concealed dead lock,SS Mortise Handle.900x211 | Nos. | 1 | 26500 | 26500 | 0 | 0 | 1 | 26500 | 1 | 26500
6.7 | Planter Boxes | Providing and fixing in position Planter Box of size - 1900mm long, 1200mm high & 190mm width (including all finishes). Box to be made of 12mm thk. waterproof fixed on all sides of double MS framework of size 40x40mm (framework to be followed with Fire Resistant Coating) fixed on the floor. Box to be finished with 8mm thick laminate(LM-02) with 6mm thick grove between laminated planks from top. Provision of electrical point for light fixtures to be made in planter box as per drawing.Rate shall include all wastage, necessary hardware, fixtures. All complete as per the details, drawings or as directed by Architect/Engineer. | Sqm | 3 | 18500 | 55500 | 0 | 0 | 2.28 | 42180 | 2.28 | 42180
6.8 | Planter Box with Sofa seating | Providing and fixing in position Planter Box with seating of size - 3020mm long, 1200mm high & 190mm width (including all finishes). Box to be made of 12mm thk. waterproof fixed on all sides of double MS framework of size 40x40mm (framework to be followed with Fire Resistant Coating) fixed on the floor. Box to be finished with 8mm thick laminate (LM-02) with 6mm thick grove between laminated planks from top. Provision of electrical point for light fixtures to be made in planter box as per drawing. Including seating arrangements both side of partition having width of 500mm each side framing made made with 40x40mm Ms frame (framework to be followed with Fire Resistant Coating) fixed on the floor and partition covered base 19mm thick FR ply+12mm thick FR ply finished with laminate (LM-02).seating top finished with cushioned form With Leatherite & 100mm thick HD Foam used in seat & and same finish in Back support of size 400mm high and 60mm thick. Rate shall include all wastage, necessary hardware, fixtures. All complete as per the details, drawings or as directed by Architect/Engineer. | RMT | 3.02 | 9800 | 29596 | 0 | 0 | 3.02 | 29596 | 3.02 | 29596
6.9 | LT panel | Providing & Fixing LT panel : 500mm deep LT panel cabinet made of 19mm thk. FR Ply. Complete box to be made up of 19mm thick FR Ply with lamiate LM-02 from all visible surfaces. Provision of open space to be left at some area as shown in elevation/detail drawing to accomodate equipments under it. Shutter be made louvered with 19mm thk. FR Ply finished with laminate finish as shown in detail/elevation drawings.Cost includes completing the job including all finishes with all necessary hard ware complete as mentioned in detail drawings. Elevation area shall be measured. Base Rate of Laminate - Rs.1400/- Per sheet.Size 1200x500x2100mm | Nos. | 1 | 53000 | 53000 | 0 | 0 | 1 | 53000 | 1 | 53000
|  | Sub Total |  |  |  | 749296 |  | 245300 |  | 484678.125 |  | 729978.125
7 |  | SIGNAGES
7.1 | SIGNAGES | SIGNAGES in lit Acrylic signage -3mm thk Acrylic router cut White & Red colour front & all sides in same colour. Size:1000 X 250mm | No. | 12 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Sub Total |  |  |  | 2674013.4 |  | 1419565.18 |  | 824666.305 |  | 2244231.485

## PLUMBING
BILL OF QUANTITIES FOR PLUMBING WORK PROJECT :JONES THE GROCER - EXPRESS | [6 empty] | Previous Bill Amount(INR) |  | This Bill Amount (INR) |  | Cumulative Amount (INR)
AS PER PO
SR. NO. | MATERIAL | DESCRIPTION | UNIT | QTY. | RATE | AMOUNT | QTY. | AMOUNT | QTY. | AMOUNT | QTY. | AMOUNT
1 |  | WATER SUPPLY PIPES
| CPVC Pipes | Supply, laying, testing & commissioning of FOOD GRADE CPVC pipes conforming to CTS (Copper Tube Size) SDR-11 as per (is 15778 ASTM D 2846) with necessary fittings up to the size of 50 mm dia. (Make – SUPREME / KASTA) including all necessary fitting as per site.
1.01 |  | 15mm dia | R.M. |  | 0 | 0
1.02 |  | 20mm dia | R.M. | 56 | 450 | 25200 | 44 | 19800 |  | 0 | 44 | 19800
1.03 |  | 25mm dia | R.M. |  | 0 | 0
| TOTAL |  |  |  |  | 25200 |  | 19800 |  |  |  | 19800
2 |  | WATER DRAIN PIPES
| UPVC WASTE PIPE | UPVC Pipe for Drainage (Make – SUPREME / KASTA) including all necessary fitting as per site.
2.01 |  | 150mm dia | R.M. |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
2.02 |  | 100mm dia | R.M. | 6 | 450 | 2700 | 0 | 0 | 5 | 2250 | 5 | 2250 | JMR ATTCHED
2.03 |  | 75mm dia | R.M. |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
2.04 |  | 50mm dia | R.M. | 15 | 315 | 4725 | 12 | 3780 | 3 | 945 | 15 | 4725 | JMR ATTCHED
| TOTAL |  |  |  |  | 7425 | Total | 3780 | Total | 3195 | Total | 6975
3 |  | CHAMBER & GRATING
3.01 | INSPECTION CHAMBER | Supply, Laying, Testing & Commissioning of Approved SS Inspection Chamber along of Size- 300mmx300mm with SS Cover & SS Grating over it. Make Jaquar / Ozone. Including trenching and finishing with ceramic tiles as per dwg and details. | Nos. | 1 | 12500 | 12500 | 1 | 12500 |  | 0 | 1 | 12500
[5 empty] | 0 | [5 empty] | 0 | 0
3.02 | OPEN GRATING | Providing & Fixing 20mm heavy quality SS triple layer Grating along with Perforated Mesh & Angle Frame of width 200mm, complete as per detail Drawings. Rate inclusive of chamber construction |  |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
|  | Size - 600mm x 200mm | Nos. | 1 | 4500 | 4500 | 0 | 0 |  | 0 | 0 | 0
|  | Size - 1000mm x 200mm | R.M. |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
| TOTAL |  |  |  |  | 17000 | Total | 12500 | Total | 0 | Total | 12500
4 |  | FLOOR TRAP
4.01 | FLOOR TRAP | Supply, Laying, Testing & Commissioning of 75x75mm Floor Trap with Approved Make heavy duty round or Square. | Nos. | 1 | 1500 | 1500 | 0 | 0 |  | 0 | 0 | 0
| TOTAL |  |  |  |  | 1500 | Total | 0 | Total | 0 | Total | 0
5 |  | VALVE AND TAP
5.01 | ANGLE VALVE | Providing & Fixing Angle Valve with connector pipe. | Nos. | 13 | 1700 | 22100 | 0 | 0 | 12 | 20400 | 12 | 20400 | JMR ATTCHED
5.02 | LONG BODY TAP | Providing & Fixing Sink Cock. with foot operated | Nos. | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
5.03 | Table Mixer | Providing & Fixing Sink Cock. | Nos. | 3 | 2200 | 6600 | 0 | 0 | 3 | 6600 | 3 | 6600 | JMR ATTCHED
5.04 | Gate Valves | Providing & Fixing PPR Ball Valve ISI mark. (For Inlet) | Nos. | 1 | 3400 | 3400 | 1 | 3400 |  | 0 | 1 | 3400
6.04 | Sink Mixer |  | Nos. | 1 | 3400 | 3400 | 0 | 0 | 4 | 13600 | 4 | 13600 | JMR ATTCHED
| TOTAL |  |  |  |  | 35500 | Total | 3400 | Total | 40600 | Total | 44000
6 |  | ACCESSORIES
6.01 | Grease Trap | Providing & Fixing of portable grease trap NGT-8 from Nugreen | Nos. | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
6.02 | Grease Trap | Providing & Fixing of portable grease trap NGT-50 from Nugreen | Nos. | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
6.03 | Bottle Trap | Providing & fixing 32mm CP finished Bottle Trap with wall flanges. (Make – JAQUAR / OZONE) | Nos. | 2 | 2500 | 5000 | 0 | 0 | 3 | 7500 | 3 | 7500 | JMR ATTCHED
6.04 | Water Meter | 25mm Dia Water meter | Nos. | 1 | 7500 | 7500 | 0 | 0 | 1 | 7500 | 1 | 7500 | JMR ATTCHED
6.05 | GEYSER | 6 LITER GEYSER | Nos. | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
6.06 | GEYSER | 25 LITER GEYSER | Nos. | 1 | 9800 | 9800 | 0 | 0 | 1 | 9800 | 1 | 9800 | JMR ATTCHED
6.07 | Waste Coupling | Providing Waste Coupling 32mm size full thread waste coupling to be use for 3-bowl sink. | Nos. | 4 | 500 | 2000 | 0 | 0 | 0 | 0 | 0 | 0
6.08 | Water supply connection | water supply connection taken from existing point complete with all necessary fittings. | Nos. | 1 | 7500 | 7500 | 1 | 7500 |  | 0 | 1 | 7500
6.09 | Drainage connection | Drainage connection connect to existing drain point complete with all necessary fittings including cleanout plug | Nos. | 1 | 5500 | 5500 | 1 | 5500 |  | 0 | 1 | 5500
6.1 | Pressure Pump | Pressure Pump | Nos. |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
6.11 | RO Plant | Providing and fixing of RO Plant on MS platform with all necessary valves and fiting required. | Nos. |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
6.12 | Domestic RO | Providing and fixing of Domestic RO with water storage with all necessary valves and fiting required. | Nos. | 1 | 12500 | 12500 | 0 | 0 |  | 0 | 0 | 0
6.13 | Water Tank | Providing and fixing of 200 Ltr. Storage Loft Tank on MS Platform with all necessary valves and fiting required. | Nos. | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
6.14 | Trench (125 mm wide) | Making 125 mm wide 300 mm deep trench with 4" thk. Block wall on both side of trench. Floor & inner surfaces of walls to be finished with plaster followed with 12mm ceramic tiles. Top of the trench to be covered with floor tile fixed inside L-angle frame placed over another L-angle which is fixed on trench top, complete as per dwg/details. Rate inclusive of making trench, providing finish tiles & top tiles in frame. | RMT | 6 | 2500 | 15000 | 0 | 0 |  | 0 | 0 | 0
| TOTAL |  |  |  |  | 64800 | Total | 13000 | Total | 24800 | Total | 37800
| GRAND TOTAL |  |  |  |  | 151425 |  | 52480 |  | 68595 |  | 121075
[7 empty] | Payt Recd | 109041
[7 empty] | extra | -56561
-10180.98
2241013.4

## HVAC
D41 & D41A AT LUCKNOW AIRPORT
SUMMARY TO SCHEDULE OF PRICES
A | Part A: HVAC Equipments |  |  |  | 114000 | [5 empty] | 114000
B | Part B: Low Side Works |  |  |  | 447600 | [5 empty] | 357886
C | Part C: Electrical Works |  |  |  | 36600 | [5 empty] | 36600
TOTAL |  |  |  |  | 598200 | [5 empty] | 508486
GST @ 18% |  |  |  |  | 107676 | [5 empty] | 91527.48
GRAND TOTAL |  |  |  |  | 705876 | [5 empty] | 600013.48
D41 & D41A AT LUCKNOW AIRPORT
SUMMARY TO SCHEDULE OF PRICES
The prices are to be quoted in the below mentioned form and shall include the supply, installation, Testing and Commissioning at site of all the equipments, ancillary materials except where specified otherwise and all such items whatsoever which may be required to fulfill the intent and purpose as laid down in the drawings and specifications shall include all taxes and duties on a basis works contract.
|  | AS PER PO |  |  |  | Previous Bill Amount(INR) |  | This Bill Amount (INR) |  | Cumulative Amount (INR)
S.No. | Description | Unit | Qty. | Rate(Rs.) | Amount(Rs.) | Qty | Amount(Rs.) |  |  | Qty | Amount(Rs.)
Part A | HVAC Equipments
1 | Air Handling Units (Indoor Type)
Supply, installation,testing and commissioning of factory built Air handling units in Double skin type with 40 mm thick panels consisting of G.I casing of thickness 0.6 mm outside layer and 0.6 mm inside layer with 275 GSM zinc coating and polyurethene foam(PUF) insulation having density of 42 kg/m3,complete with Backward curved DIDW Blower, chilled water cooling coil with aluminium finned copper tubes with face velocity 500 FPM. Filter section having 50 mm thick pre filters , IE3 motor suitable for 415 +10% volts,50 Hz, 3 phase AC supply,drain connections with 18G stainless steel drain pan and necessary vibration isolation arrangement to avoid any vibration etc. complete as per specifications and drawings. Suitable acoustic to be done inside the AHU to limit the noise ofassembly to 55Db @ 1.5 mtr .
Design Parameters- 25 deg C -R.A.Temp, 55% RH, 7.0 deg C- CHW IN
Water Flow Rate- 2.4 GPM/ TR
Blowers upto 50 mm Total Static Pressure shall be Forward curved and above 50 mm shall be Backward curved
1.1 | Ceiling Suspended Type
1.1.1 | 3400 CMH(2000 CFM) at 35 mm Total Static Pressure with Single blower , 6 RD Cooling Coil, Approx 5.0 TR, 1 x 1.1 KW Motors | Nos | 1 | 85000 | 85000 | 0 | 0 | 1 | 85000 | 1 | 85000
1.2 | Digital Heating/Cooling Thermostat for Air Handling Units | Nos. | 1 | 9500 | 9500 | 0 | 0 | 1 | 9500 | 1 | 9500
1.3 | Fire Retardant Canvas
1.3.1 | Supply & Installation of fire retardant canvas connections for Air Handling Units | Sqm. | 5 | 3900 | 19500 | 0 | 0 | 5 | 19500 | 5 | 19500
Sub Total Part A |  |  |  |  | 114000 |  |  |  | 114000 |  | 114000
Part B | Low Side Works
1 | Chilled Water Piping confirmning to IS 1239 / IS3589 code with Nitrile Rubber Insulation
Supplying, laying/ fixing, testing and commissioning of MS C class chilled water piping (cut of required length and installed with welded joints. The necessary fittings such as elboues, tees etc. shall all to included in this item). The Insulation shall be Class O nitrile Rubber pre-slit, pipe sleeve upto 100 mm dia and sheet for bigger dia with factory Laminated 7 mill woven glass cloth of thicknesses as specified, with approved adhesive. Manufactured supplied, suitable sized nitrile rubber pipe supports with PUF/PIR inserts shall be used. Thermal conductivity should not exceed 0.035 W/MK at 0 degree celsius and water vaper resisitance > 7000. Manufactures tapes and adhesive to used only. The pipe supports should also be of nitrile rubber with PUF/PIR inserts and are to be installed as per manufacturer's recomendation. The pipe fittings shall be MS. class for pipes upto 150 mm and for 200mm and above, same material of the pipe shall be usee all bends/ Reducess/ Tee upto 150 mm shall be factory fabricated ready made MS 'C' class. Note : Use proper template for marking block colour Arrows pipe. for supply/return.
i | 32mm dia with 32 mm thick insulation with factory Laminated 7 mil glass cloth upper layer | Mtrs. | 15 | 750 | 11250 | 0 | 0 | 14 | 10500 | 14 | 10500
ii | 20mm dia with 32 mm thick insulation with factory Laminated 7 mil glass cloth upper layer | Mtrs. | RO
2 | Insulated Valves
2.1 | Dynamic Balancing Valve-PID type
Supply & installation, testing and commissioning of BMS Compatible electronic self balancing valve with integrated two way modulating control valves in a single body. The actuator shall be capable of accepting 230V/ 24V/ 2-10VDC/4-20 mA electrical signed and shall provided similar transduced feed back output singed to control system. The minimum close off pressure of actuator must be 1.5 times shut of head of pump as per Specification of following size. The actuator shall be microprocessor based with self calibration feature. All the valve shall be complete with step down transformers, thermostat, control wiring and probe.
i | 10-20 USGPM -( Insulation as per Chilled water pipe) | Nos. | 1 | 15000 | 15000 | 0 | 0 | 1 | 15000 | 1 | 15000
2.2 | Providing and Fixing digital type thermometers with copper well, valve & probe suitable for binder test point application.
2.2.1 | 6" long -( Insulation as per Chilled water pipe) | Nos. | 2 | 2800 | 5600 | 0 | 0 | 2 | 5600 | 2 | 5600
2.3 | Ball valves with Strainer (Insulated)
Providing and Fixing of the following insulated ball valve having a heavy duty forged body as per approved make. The ball shall be of bronze construction duty chrome plated.
2.5.1 | 32 mm dia - PN-16 with insulation same a Chilled water piping | Nos | 1 | 4500 | 4500 | 0 | 0 | 1 | 4500 | 1 | 4500
2.4 | Ball valves without Strainer (Insulated)
| Providing and Fixing of the following insulated ball valve having a heavy duty forged body as per approved make. The ball shall be of bronze construction duty chrome plated. | [5 empty] | 0 |  |  |  | 0
2.4.1 | 32 mm dia - PN-16 with insulation same a Chilled water piping | Nos | 1 | 4500 | 4500 | 0 | 0 | 1 | 4500 | 1 | 4500
2.5 | Dial Presure Guages (glycerine filled Type) with SS Encasing with isolating valve & piping etc.The gauge should be with appropriate range and valve and fitted with probe suitable for binder test point application as well.
2.5.1 | 4" Dial -( Insulation as per Chilled water pipe) | Nos. | 2 | 11000 | 22000 | 0 | 0 | 2 | 22000 | 2 | 22000
2.6 | Providing and Fixing of automatic air vent of approved make with insulation valves as per specifications/drawings
2.8.1 | 20mm dia | Nos. | 2 | 7000 | 14000 | 0 | 0 | 2 | 14000 | 2 | 14000
3 | Drain Piping
Supply, Installation, testing and commissioning of UPVC condensate drain pipe along with necessary clamps, fittings sich as bends, tees, etc. it shall be insulated with 9 mm thick nitrile foam insulation in tubular form as per specifications.
3.1 | 32 mm dia | Mtrs. | RO
3.2 | 20 mm dia | Mtrs. | 10 | 400 | 4000 | 0 | 0 | 9 | 3600 | 9 | 3600
4 | DUCTING
4.1 | Factory Fabricated Ducting (GSS)
Supply, installation, balancing and commissioning of factory fabricated GSS sheet metal rectangular/round ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
4.1.1 | 0.5 MM (26 Gauge) | Sqm. | 10 | 1350 | 13500 |  | 0 | 0 | 0 | 0 | 0
4.1.2 | 0.63 MM (24 Gauge) | Sqm. | 60 | 1350 | 81000 | 25.37 | 34249.5 | 27.77 | 37489.5 | 53.14 | 71739
4.1.3 | 0.8 MM (22 Gauge) | Sqm. | 10 | 1450 | 14500 |  | 0 | 0 | 0 | 0 | 0
4.1.4 | 1.0 MM (20 Gauge) | Sqm. | R.O
4.1.5 | 1.25 MM (18 Gauge) | Sqm. | R.O
4.2 | Site Fabricated Ducting (GSS)
Supply , Installation, Testing and Commissioning of site fabricated GSS sheet metal rectangular ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required.
4.2.1 | 0.63 MM (24 Gauge) | Sqm. | 10 | 1050 | 10500 |  | 0 | 2 | 2100 | 2 | 2100
4.2.2 | 0.80 MM (22 Gauge) | Sqm. | R.O
4.3 | Ducting (Exhaust)- MS Welded Construction- Site Fabricated
Supply, fabrication and erection of following gauges of MS ducting complete with welded drip proof seams and having access doors at every change in direction with maximum spacing of 6 meters in horizontal direction and maximun of 3 floors of vertical risers & elbows spliters, supports/suspenders bends, tees, vanes, double canvas connection of the equipment etc all complete as required. Duct shall be insulated 25 MM Thich High Density Rockwool Insulation 48 KG/m3 . The insulation material and its installation shall be in accordance with the specifications as provided. The entire insulation shall be covered with muslin cloth over which 2 coats of Star Bond / approved fire paint is applied to make the insulation hard and fire retardant.
4.3.1 | 1.00 MM (20 Gauge)- Kitchen Exhaust Ducting with 25 mm thick high density of glasswool / rockwool insulation of density 48kg/m3 . The insulation shall be covered with muslin cloth over which 2 coats of Starbond / approved fire paint is applied to make the insulation hard and fire retardant . | Sqm. | 35 | 2300 | 80500 | 20 | 46000 | 15 | 34500 | 35 | 80500
5 | INSULATION
5.1 | Nitrile Rubber Insulation- Class 'O'
Supplying and fixing of closed cell elastomeric insulation of following thickness of density 55 kg/cu.m.and K valueof not less than 0.037W/mk at 20 deg C as per specifications and drawings (For indoor applications) with factory Laminated 7 mill woven glass cloth
5.1.1 | 19 mm Thick (Supply Air Duct / Fresh Air Duct) | Sqm | 75 | 1050 | 78750 |  | 0 | 53.14 | 55797 | 53.14 | 55797
5.2 | Acoustic Lining (Upto 3 Mtr)
Supplying and Application of Acoustic lining within the Supply Air duct with 15 mm thick class 'O' open cell nitrile Rubber of density 140-160 kg./Cubm. as per spefications.
5.2.1 | 15 MM Thick | Sqm | 5 | 1100 | 5500 |  | 0 | 3 | 3300 | 3 | 3300
6 | DUCT ACCESSORIES
6.1 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded Aluminium Continuous Grille as per specifications
6.1.1 | Continuos Grille 100MM Wide | RM | 20 | 1400 | 28000 |  | 0 | 10 | 14000 | 10 | 14000
6.2 | Supply, Installation, Testing and Commissioning of multiblade Al volume control Collar / Grille / exhaust Air Opening damper complete with suitable links, lever and quadrants for manual control of airflow and with suitable links , lever and quadrants for manual control of airflow and neoprene rubber gaskets, nuts, bolts, screws, flanges etc., as per specifications. | Sqm | 1 | 7000 | 7000 |  | 0 | 1 | 7000 | 1 | 7000
6.3 | Supply, Installation, Testing and Commissioning of GI multiblade volume control duct damper complete with neoprene rubber gaskets, nuts, bolts, screws linkages, flanges etc., as per specifications. | Sqm | 1 | 8500 | 8500 |  | 0 | 1 | 8500 | 1 | 8500
6.4 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded aluminium Supply / Exhaust Air Grille with aluminium volume control dampers as per specifications | Sqm. | 3 | 7500 | 22500 |  | 0 | 2.5 | 18750 | 2.5 | 18750
6.5 | Supply, Installation, Testing and Commissioning & fixing of powder coated extruded aluminium Return Air Grille without aluminium volume control dampers as per specifications | Sq.m | 1 | 6500 | 6500 |  | 0 | 1 | 6500 | 1 | 6500
6.6 | Supply, Installation, Testing and Commissioning of Exhaust Air Opening damper complete with suitable links, lever and quadrants for manual control of airflow and with suitable links , lever and quadrants for manual control of airflow and neoprene rubber gaskets, nuts, bolts, screws, flanges etc., as per specifications | Sqm | 1 | 10000 | 10000 |  | 0 | 1 | 10000 | 1 | 10000
Sub Total Part B |  |  |  |  | 447600 |  | 80249.5 |  | 277636.5 |  | 357886
Part C | Electrical Works
1 | Electrical Control Panel
Supply, installation, testing and commissioning of panel boards made of 2.0 mm thick steel sheet duly powder coated with voltmeter, ammeter, electronic energy meter, indicating lights, Stop/manual /Auto selector switch in each, outgoing current operated single phase preventer. The starters should have potential free contacts for connection to Building Automation System. The panel shall include contactors /over load relay with built in single phase protection / Time delay relay for delayed automatic start of the motor. All panels should have spare NO/ NC Contacts for BMS applications as required.
1.1 | Panel-P01 (Ceiling Suspended AHU- 2000 CFM)
OUTGOING
1 No. 16 Amps TP MCB Outgoing for AHU Fans - 1.1 KW Each
1 Nos On/ Off Indicating Lights and Push Buttons for each Outgoing
1 Nos. DOL starter for 2.25 KW of Fan Motors .
1 Nos. of single phase preventor (current based-MPRD2)
| Panel Shall have suitable provisions for Installation of VFDs , Spare NO / NC Contacts for BMS Integration, Looping with Fire Alarm Panel to trip the AHU and Exhaust Fan in case of Fire. | Set | 1 | 25000 | 25000 |  | 0 | 1 | 25000 | 1 | 25000
2 | Cables
2.1 | Supplying, laying, testing and commissioning of XLPE insulated aluminium conductor armored cables of 1.1 KV grade of following sizes directly on wall/structural frame/ cable trays or racks using approved type of clamps,End terminations with Double Compression type glands on both ends, double earthing with GI strip/wire of suitable size and hardware as per specifications.
i | 3 C x 4 Sq. mm | Mtrs | 10 | 400 | 4000 |  | 0 | 10 | 4000 | 10 | 4000
3 | Earthing
Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required
3.1 | 25 mm x 3 mm GI strip | RM | 10 | 650 | 6500 |  | 0 | 10 | 6500 | 10 | 6500
3.2 | 8 SWG GI Wire | RM | 10 | 110 | 1100 |  | 0 | 10 | 1100 | 10 | 1100
Sub Total Part C |  |  |  |  | 36600 |  | 0 |  | 36600 |  | 36600
[7 empty] | 80249.5 |  | 428236.5 |  | 508486

## LIGHTING
BILL OF QUANTITIES FOR LIGHTING PROJECT : D 41 & 41a Shawarma,Tacos,Burger + Indian at T3_Lucknow Airport
|  | AS PER PO |  |  |  | AS PER SITE
S.NO. | DISCRIPTION | UNIT | QTY. | RATE | TOTAL | QTY. | Amt
1.01 | RECESSED DOWN LIGHT WHITE POWDER COATED. LAMP :COB LED 12W, 6500K Make- Wipro, Code-D111265 | NOS | 12 | 2200 | 26400 | 12 | 26400
1.02 | RECESSED DOWN LIGHT WHITE POWDER COATED. LAMP :COB LED 15W, 4000K Make- Wipro, Code-D121540 | NOS | 40 | 2200 | 88000 | 40 | 88000
1.03 | COPPER PENDANT LIGHT- 6 W LAMP 3000k.Height - 2250 Bottom Link- https://www.amazon.sa/-/en/Hobaca-Pendant-Hanging-Fixtures-Kitchen/dp/B07SS4J9KZ | NOS | 9 | 6500 | 58500 | 9 | 58500
1.04 | LED STRIP LIGHTS WITH ALUMINUM CHANNEL 5V PER METER, 4000K Make- Wipro, Code-D42840-1 | R.MT | 88 | 450 | 39600 | 45.8 | 20610
1.05 | WHITE JAPANESE STYLE PENDANT LIGHT- 6 W LAMP 3000k.Height - 1800 Bottom Link-https://www.amazon.co.uk/Junzc-Japanese-Spherical-Chandelier-Restaurant/dp/B0B3XHZCGF?th=1 | NOS | 4 | 6500 | 26000 | 4 | 26000
1.06 | 50mm LED STRIP LIGHTS WITH ALUMINUM CHANNEL | R.MT | 15 | 650 | 9750 | 13 | 8450
1.07 | 2NO'S OF FABRICATORS LIGHT MADE WITH 38MM X 38MM MS. HOLLOW SQUARE PIPE WITH STRETCH MESH FINISHED WITH PU PAINT AND LED STRIPS LIGHT ON BOTTOM. REF DETAIL -A-102F | NOS | 5 | 9500 | 47500 | 5 | 47500
1.08 |  |  |  |  | 0
| TOTAL |  |  |  | 295750 |  | 275460

## ELECTRICAL
D41 & D41A _Lucknow Airport
Bill of Quantities - Electrical Works Dated 09th Oct 2023
The prices are to be quoted in the section mentioned below and shall include the supply, Installation, Testing and commissioning at site of all the equipments, ancillary materials as specified and all such items what so ever required to fulfill the intent and purpose as laid down in the specifications and/or drawings and shall include all taxes and duties on works contract basis.
|  | AS PER PO |  |  |  | Previous Bill Amount(INR) |  | This Bill Amount (INR) |  | Cumulative Amount (INR)
S. No. | Description | Unit | Qty. | Rate | Amount |  |  |  |  | Qty. | Amount
Design, fabrication, assembling, wiring , supply , Erection , Installation , testing and commissioning of MDB Panels fabricated out of 2mm thick for structural members (Load bearing members) and 1.6mm thick for door and covers (Non load bearing members) CRCA painted sheet steel in cubicle formation with reinforcement of suitable size angle iron, channels, T irons, flats wherever necessary for large meter boards. Cable gland plates shall be provided at top and bottom both and windows for meter reading, locking arrangement (pad-lock & seal) with wiring upto KWH meter & meter to MCB shall be done by using adequately rated flexible single core copper wire. The boards shall be treated with all anticorrosive process before painting as per standards with final approved shade of powder coated as approved, 2 nos. earthing terminals shall be provided for all panels. The boards shall be suitable for 415 V, 3 phase, 4 wire, 50 Hz supply system. Boards shall be fabricated in length, height, depth etc to match with site conditions.
An approval shall be taken for each panel before manufacturing. Galvanised hardwares with zinc passivation shall be used in fabrication of boards.
Note: The following provisions shall be required to be made in the switchboard detailed below
The Switchboard shall have provision for entry of all PVCA cables from the top/bottom as required.
All live accessible parts shall be shrouded and all equipment shall be finger touch proof. The busbar insulation shall be with heat shrinkable sleeves. SMC/DMC shrouds and busbar supports shall be used.
Suitable tinned copper extension links for incoming/outgoing cables shall be provided wherever required
Control circuits includes breaker control switch, auto manual selector switch, anti pumping relay, spring charging trip indication, TIMER, control wiring, Auxiliary contactors MCB’s as required at site.
Positive isolation of all breakers.
All fault level breaking capacity indicates shall be ICS value at 415 volts (ICS = ICU = ICW = 100%).
Space Heater/ light/air filter shall be provided for each vertical compartment
Link and drops from MCCB shall be designed for full rated current of MCCB ratings at same current density as of Main Bus Bar
2 nos. GI earth strip throughout the panel.
1 | MAIN MDB
A | Incoming
1 No. 160 amps 25 kA 440 volt FP MCCB with Thermal Magnetic overcurrent and short circuit and with following
B | Metering, Indication & Protection:
a | 1 Nos. 6 Parameter Multi Function Mater with 3 Nos. Cast Resin CTs and MCBs
b | Breaker ON OFF indication Lamps
c | R-Y-B indication lamps with MCBs
d | ELR with CBCT
C | Bus Bar:
200 A, TPN Al. Bus Bar of suitable length having Current density 1Amp/sq.mm & having high conductivity electrical grade suitable to withstand symmetrical fault level of 25 kA. Neutral busbar shall be of 100% capacity.
D | Outgoings:
a | 2 No. 63 amps 4P MCB ( Type C)
b | 2 No. 40 amps 4P MCB ( Type C)
c | 1 No. 20 amps 4P MCB ( Type C)
d | 1 No. 63 amps 2P MCB ( Type C)
e | 1 No. 25 amps 2P MCB ( Type C)
f | 2 No. 40 amps 2P MCB + RCCB of 100mA sensitivity.
g | 1 No. 32 amps 2P MCB + RCCB of 100mA sensitivity.
h | 1 No. 25 amps 2P MCB + RCCB of 100mA sensitivity.
E | PDB (In built Inside the Panel)
1-63amp FP MCB with 3 single phase banks each comprising of 63A DP RCCB(100 mA) and 7 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings.
| Main MDB as described above | 1 | Set | 80000 | 80000 | 0 | 0 | 1 | 80000 | 1 | 80000
1.1 | DISTRIBUTION BOARDS
Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof double door type distribution boards constructed from 16 SWG sheet steel IP 42 construction, finished with rust proof duly powder coated in approved shade with hinged gasketed door and housing the following complete with P.V.C. insulated copper busbars rated 200 amp with interconnections, neutral and earth bar assembly per phase, earthing terminals complete as approved by Architects.
Note : All MCBs in distribuition board for power circuits shall be of C curve
i | Type A
| 1-63amp FP MCB with 3 single phase banks each comprising of 63A DP RCCB(100 mA) and 6 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 27500 | 27500 | 0 | 0 | 1 | 27500 | 1 | 27500
ii | Type B
| 1-40amp FP MCB with 3 single phase banks each comprising of 40A DP RCCB(100 mA) and 8 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 25500 | 25500 | 0 | 0 | 1 | 25500 | 1 | 25500
iii | Type C
| 1-32 amp DP MCB + DP RCCB ( 100mA) and 10 nos. 6/16/20/25 amps SP 10 kA MCB(Type C) with thermal magnetic protective releases out goings. | 1 | Set | 12500 | 12500 | 0 | 0 | 1 | 12500 | 1 | 12500
2 | Supply installation testing and commisioning 3.0 kVA online ( 1ph input and 1ph output) UPS with 15 Min power back up complete with in buit Static by pass switch , Mannual external maintenance by pass switch , Rectifiers , Sealed MF batteries etc as required | 1 | No. | 50000 | 50000 | 0 | 0 | 1 | 50000 | 1 | 50000
3 | Supply, laying, testing & commissioning of following sizes of Al/Cu. conductor 1.1 kV grade, armoured, XLPE insulated FRLS LT Cables/ Control Cables including necessary cleats, clamps etc. (Cables shall be partly laid in Pipes, O/H cable tray, on wall as required )
3.1 | 3.5C – 70.0 (Al.) FRLS Armoured XLPE Cable * | 40 | Mtrs | 600 | 24000 | 0 | 0 | 8 | 4800 | 8 | 4800
3.2 | 4C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 40 | Mtrs | 500 | 20000 | 0 | 0 | 18 | 9000 | 18 | 9000
3.3 | 3C – 6.0 (Cu.) FRLS Armoured XLPE Cable | 20 | Mtrs | 400 | 8000 | 0 | 0 | 8 | 3200 | 8 | 3200
* Approximate and shall be as per point of supply from Airport Panel/ Isolator
4 | Supply, erection, testing & commissioning of following sizes of cable end terminations with Single compression gland for 1.1 kV grade, XLPE insulated, Al/Cu Conductor cable
4.1 | 3.5C – 70.0 (Al.) FRLS Armoured XLPE Cable *(Double Compression) | 2 | Nos. | 1150 | 2300 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | 4C – 4.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 800 | 1600 | 0 | 0 | 2 | 1600 | 2 | 1600
4.3 | 3C – 6.0 (Cu.) FRLS Armoured XLPE Cable | 2 | Nos. | 800 | 1600 | 0 | 0 | 0 | 0 | 0 | 0
5 | Wiring for DB Submains with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in surface/concealed MS surface/concealed conduit including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases as required and making suitable end termination with copper lugs complete as required and as below
5.1 | 4 x 16 sq.mm + 2 No. 6.0 Sq. mm in 40 mm dia MS Conduit | 10 | Mtrs | 1500 | 15000 | 0 | 0 | 8 | 12000 | 8 | 12000
5.2 | 4 x 10 sq.mm + 2 No. 4.0 Sq. mm in 32 mm dia MS Conduit | 10 | Mtrs | 1200 | 12000 | 0 | 0 | 8 | 9600 | 8 | 9600
5.3 | 4 x 4 sq.mm + 2 No. 2.5 Sq. mm in 32 mm dia MS Conduit | RO | Mtrs
5.4 | 2 x 10 sq.mm + 1 No. 6 Sq. mm in 25 mm dia MS Conduit | 15 | Mtrs | 1000 | 15000 | 0 | 0 | 8 | 8000 | 8 | 8000
5.4 | 2 x 6 sq.mm + 1 No. 4 Sq. mm in 25 mm dia MS Conduit | 20 | Mtrs | 500 | 10000 | 0 | 0 | 8 | 4000 | 8 | 4000
5.5 | 2 x 4 sq.mm + 1 No. 2.5 Sq. mm in 25 mm dia MS Conduit | 200 | Mtrs | 310 | 62000 | 181.8 | 56358 | 0 | 0 | 181.8 | 56358
6 | Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All copper joints shall be tinned. The rates shall be inclusive of making test joints where ever required | [5 empty] | 0
6.1 | 25X6 mm GI Strip | 20 | Mtrs | 650 | 13000 | 0 | 0 |  | 0 | 0 | 0
6.2 | 25X3 mm GI Strip | 30 | Mtrs | 550 | 16500 | 0 | 0 |  | 0 | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0 | 0
6.3 | 8 SWG Copper Wire | 30 | Mtrs | 130 | 3900 | 0 | 0 | 0 | 0 | 0 | 0
6.4 | 8 SWG GI Wire | 150 | Mtrs | 80 | 12000 | 0 | 0 |  | 0 | 0 | 0
6.5 | 1 Core 6.0 Sq. Mm FRLS Green Wire | 35 | Mtrs | 85 | 2975 | 0 | 0 |  | 0 | 0 | 0
7 | Supply, erection, testing & commissioning of prefabricated GI Perforated type cable trays including Tees / Bends / Crossing / Reducers / Couping to be laid in cable trench, overhead on wall or hanged from ceiling complete with all accessories as required including support at every 1500mm as required
7.1 | 150 mm x 40 x 40 x 2 mm thick with 2 Nos. 25X3mm GI Earth Strip | 30 | Mtrs | 1600 | 48000 | 0 | 0 | 0 | 0 | 0 | 0
8 | Wiring for MCB controlled normal primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 18 | Pt | 1850 | 33300 | 18 | 33300 |  | 0 | 18 | 33300
9 | Wiring for secondary MCB controlled normal light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 65 | Pt | 1300 | 84500 | 62 | 80600 | 2 | 2600 | 64 | 83200
10 | Wiring for MCB controlled Emergency primary light points/ Wall Point/ Floor Point with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm dia 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq. mm PVC insulated copper conductor wire for loop earthing etc. complete as required. (Cost of MCB included in the item for per DB). | 2 | Pt | 2250 | 4500 | 2 | 4500 | 0 | 0 | 2 | 4500
11 | Wiring for secondary MCB controlled Emergency light points/ Wall Point/ Floor Point( Looped from above point) with 1.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade FRLS wires in 25 mm 16 SWG MS conduit in wall / ceiling including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including the cost of running 1.5 Sq mm PVC insulated copper conductor wire for loop earthing etc. complete as required. | 12 | Pt | 1600 | 19200 | 2 | 3200 | 9 | 14400 | 11 | 17600
12 | Wiring for a 5 pin 240 volt 6 amp single phase and neutral switch socket outlet with 2.5 sq. mm PVC insulated stranded copper conductor 1100 Volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / ceiling including cost of providing circuit wiring with 2.5 sq mm PVC insulated stranded copper conductor 1100 volt grade wires and including cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and providing and fixing of a combined 5 pin 240 volt 6 amp socket outlet with safety shutters and 6 amp 240 volt single pole grid plate mounted switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires complete as requied( Switch and socket shall be as approved by the architect / Client) | 6 | Pt. | 2900 | 17400 | 5 | 14500 |  | 0 | 5 | 14500
13 | Wiring same as in Item 12 above looped from an adjacent 6 amp switch socket outlet as required and providing and fixing of a modular type 5 pin 240 Volt 6 amp shuttered socket outlet and a modular type 6 amp 240 Volt single pole switch in a recessed GI boxes with internal wiring and moulded front plates complete as required. ( Switch and socket shall be as approved by the architect / Client) | 14 | Pt. | 2650 | 37100 | 10 | 26500 | 3 | 7950 | 13 | 34450
14 | Same as above but switch and socket provided at separate location including wiring berween switch and socket and complete as required | RO | Pt. |  |  | 0
15 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 2.5 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 2 | Pt. | 2800 | 5600 | 2 | 5600 |  | 0 | 2 | 5600
16 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (1 outlet wired on 1 circuit) with 4.0 sq. mm PVC insulated stranded copper conductor 1100 volt grade wires (FRLS) in 25mm dia 16 SWG MS conduit in wall / Ceiling including the cost of cutting and filling chases for recessed conduiting and supports in case of surface conduit including all bends , saddles , Junction boxes etc and including providing and fixing 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted modular type switch with moulded cover plate in recessed GI box and including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wires and complete as requied( Switch and socket shall be as approved by the architect / Client) | 14 | Pt. | 2800 | 39200 | 11 | 30800 |  | 0 | 11 | 30800
17 | Wiring for 6 pin 240 volt 16 amp single phase and neutral switch socket outlets (2 outlets wired on 1 circuit) with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 4.0 sq mm upto the first outlet and 2.5 sq mm from first to the second outlet in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing of two sets of 6 pin 240 volt 16 amp socket outlet with safety shutters and 16 amp 240 volt single pole grid plate mounted switches with moulded cover plate in a recessed GI box including earthing of the 3rd pin with 2.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) | 4 | Pt. | 3000 | 12000 | 0 | 0 | 3 | 9000 | 3 | 9000
18 | Wiring for primary switch board consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A switch with PVC insulated stranded copper conductor 1100 volt grade wires (FRLS), 2.5 sq FRLS copper wire mm in 25mm dia 16 SWG MS conduit in wall / Ceiling including cost of providing saddles etc as required for surface conduiting and/or cost of cutting and filling chases and including providing and fixing prewired switch board each consisting of 3 Nos. 5 pin 240 volt 6 amp single phase and neutral switch socket outlets with 3 Nos. 6A modular switch , safety shutters in a recessed/surface GI box including earthing of the 3rd pin with 1.5 sq mm 1100 volt grade PVC insulated stranded copper conductor wire complete as required. (Switch/Socket Shall be as per approved sample by Architect) Note- Conduits shall be 16 SWG MS on surface and FRLS PVC for wall concealed | 3 | Pt. | 2850 | 8550 | 5 | 14250 |  | 0 | 5 | 14250
19 | Supply installation testing and fixing 3 pin 20A , 240V , single Phase metal Clad industrial socket outlet with 20A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 6 | Nos. | 3450 | 20700 | 6 | 20700 |  | 0 | 6 | 20700
20 | Supply installation testing and fixing 3 pin 25A/32A , 240V , single Phase metal Clad industrial socket outlet with 25A/32A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 12 | Nos. | 3800 | 45600 | 0 |  |  | 0 | 0 | 0
21 | Supply installation testing and fixing 3 pin 40A , 240V , single Phase metal Clad industrial socket outlet with 40A DP MCB and complete in all respects( Wiring Excluded from scope of this item) | 2 | Nos. | 4000 | 8000 | 0 | 0 | 2 | 8000 | 2 | 8000
22 | Supply installation testing and fixing 5 pin 25A/20A , 415V , single Phase metal Clad industrial socket outlet with 25A/20A FP MCB and complete in all respects( Wiring Excluded from scope of this item) | RO | Nos. |  |  |  | 0
23 | Supply , fixing & Laying 2.0mm Thick FRLS PVC conduits on surface or concealed complete with PVC junction boxes, cover plates, PVC bends, PVC saddles, base and other accessories all made in PVC with GI screws as required to complete the job. . | [5 empty] | 0
i | 25 mm dia FRLS PVC conduit | 125 | Mtrs | 145 | 18125 | 0 | 0 | 45 | 6525 | 45 | 6525
ii | 20 mm dia FRLS PVC conduit | 100 | Mtrs | 125 | 12500 | 0 | 0 | 87 | 10875 | 87 | 10875
24 | Supply , fixing & Laying 16 SWG MS conduits on surface or concealed complete with PVC junction boxes, cover plates, bends, saddles, base and other accessories all made in PVC with GI screws as required to complete the job. .
i | 25 mm dia 16 SWG MS conduit | RO | Mtrs
ii | 20 mm dia 16 SWG MS conduit | RO | Mtrs
25 | Supply and installation of flush mounted (Enhanced Category 6T 568 A or B) outlets with 2 mm thick GI box complete including cutting, chases, fixing of GI boxes and making good. The plastic shall be high impact, flame-retardant, UL rate thermoplastic. Dust cover / blank shall be provided to protect unused faceplate openings. Termination caps and plastic cover shall be provided to protect jack wiring.
i | Single outlet face plate with RJ-45 Jack with information outlet | 10 | Nos. | 1000 | 10000 | 0 | 0 | 6 | 6000 | 6 | 6000
ii | Duplex outlet face plate with RJ-45 Jack with information outlet | 3 | Nos. | 1200 | 3600 | 0 | 0 | 2 | 2400 | 2 | 2400
26 | Supply,installtion testing and commisioning of Cat-6A UTP cables in existing Conduit complete as required for Telephone and Data System | 250 | Mtrs | 75 | 18750 | 0 | 0 | 162 | 12150 | 162 | 12150
27 | Supplying,installation and commisioning of CAT-6A patch cords 2 mtrs. | 16 | Nos | 900 | 14400 | 0 | 0 |  | 0 | 0 | 0
28 | Supplying,installation and commisioning of CAT-6A patch cords 1 mtr. | 16 | Nos | 450 | 7200 | 0 | 0 |  | 0 | 0 | 0
29 | Installation of following light fixtures including connections and complete in all respects
i | 15/12Watt Recessed Down Lighter | 55 | No. | 950 | 52250 | 0 | 0 | 52 | 49400 | 52 | 49400
ii | LED Strip Light ( Per Meter) | 88 | Mtrs | 300 | 26400 | 0 | 0 | 87.8 | 26340 | 87.8 | 26340
[9 empty] | 0 | 0 | 0
iii | Signage | 12 | No. | 0 | 0 |  | 0 |  | 0 | 0 | 0
iv | 6W Pendant Light | 13 | No. | 3500 | 45500 | 0 | 0 | 13 | 45500 | 13 | 45500
Total For Electrical Works - INR |  |  |  |  | 1007750 |  | 290308 |  | 448840 |  | 739148
THE ABOVE EXCLUDES THE FOLLOWING:-
1 | Equipment ( Server , Ports etc) for networking / LAN system / EPABX and Centrex system , however infrastructure like Conduits / Pipes /RJ-45 sockets have been considered
2 | Fire Alarm System
3 | Supply of light fixtures. However installation and Wiring considered

## CCTV
BILL OF QUANTITIES FOR CCTV & MUSIC LOCATION:- D 41 & 41a Shawarma,Tacos,Burger + Indian at T3_Lucknow Airport
[5 empty] | AS PER PO |  |  | AS PER SITE
S.No | Items | Specification | Model | Make | PO Qty | Rate | PO Amount | Executed Qty | Bill Amount
1 | Dome Cameras | Full HD 720p Video Output, Adopt HDTVI Technology, Trud Day & Night, Lens 3.6mm, 12LED, Upto 20M IR Distance | DS-2CE5ZCOT-IRP | Hikvision | 12 | 2500 | 30000 | 12 | 30000
2 | Bullet Camera | 1080P Outdoor 2 MP bullet camera fixed lens | DS-2CE1ADOT-IT1F | Hikvision | 0 |  | 0 |  | 0
3 | Digital Video Recorder | 4 Channel DVR, Supported 1mp, H.264 /H.264 & Dual stream video compression, Support HD-TVI/Analoge and AHD Cameras with adaptive access. HDMI and VGA output to 1920x1080P resolution, Supported 1 Hard disk upto 4TB | DS-7A04HGHI-F1/N | Hikvision | 0 |  | 0 |  | 0
4 | Digital Video Recorder | 8 Channel DVR, Supported 1mp, H.264 /H.264 & Dual stream video compression, Support HD-TVI/Analoge and AHD Cameras with adaptive access. HDMI and VGA output to 1920x1080P resolution, Supported 1 Hard disk upto 6TB | DS-7A08HGHI-F1/N | Hikvision | 0 |  | 0 |  | 0
5 | Digital Video Recorder | 16 Channel DVR, Supported 1mp, H.264 /H.264 & Dual stream video compression, Support HD-TVI/Analoge and AHD Cameras with adaptive access. HDMI and VGA output to 1920x1080P resolution, Supported 1 Hard disk upto 6TB | DS-7A16HGHI-F1/N | Hikvision | 0 |  | 0 |  | 0
6 | Digital Video Recorder | 16 Channel DVR, Supported 1mp, H.264 /H.264 & Dual stream video compression, Support HD-TVI/Analoge and AHD Cameras with adaptive access. HDMI and VGA output to 1920x1080P resolution, Supported 2 Hard disk upto 8TB | DS-7016/7216 HQHI/K1 | Hikvision | 1 | 14000 | 14000 | 1 | 14000
7 | CEILING SUSPENDED CAMERA PIPE | MS power coated white/black color 3.5'-5.5' tele4scopic mount with provision to make mount in straight line and box to install power supply inside for dome camera installation. | No |  | 0 |  | 0 |  | 0
8 | Hard Disk - SURVEILLANCE | 2TB | WD/ Purple | Seagate / Toshiba | 0 |  | 0 |  | 0
9 | Hard Disk - SURVEILLANCE | 4TB | WD/ Purple | Seagate / Toshiba | 1 | 10000 | 10000 | 1 | 10000
10 | Screen | 18-19" | with HDMI | Acer/LG/Dell | 1 | 11000 | 11000 | 1 | 11000
11 | BNC Connectors |  |  |  | 0 |  | 0 |  | 0
12 | DC Connectors |  |  |  | 0 |  | 0 |  | 0
13 | Power Supply | 8 Cameras - 10 amps X 2 |  | CP-PLUS / ZEBRONICS | 0 |  | 0 |  | 0
14 | Power Supply | 16 Cameras - 20 amps X 2 |  | CP-PLUS / ZEBRONICS | 1 | 2500 | 2500 | 1 | 2500
15 | HDMI Cable | 5 Mtrs |  | MX | 1 | 2250 | 2250 | 1 | 2250
16 | Cameras Installation | All Over India |  | Hikvision | 1 | 6500 | 6500 | 1 | 6500
17 | Music System | 10 Watt to 60Watt JBL | CSS1/ST | JBL | 0 |  | 0 |  | 0
18 | Music System | Amplifier | Libra 250 | JBL | 0 |  | 0 |  | 0
19 | Music System | Amplifier | Libra 500 | JBL | 0 |  | 0 |  | 0
20 | Music Installation | All Over India |  | JBL | 0 |  | 0 |  | 0
Total Amount | [6 empty] | 76250 |  | 76250

## FIRE & SAFETY
BILL OF QUANTITIES FOR FIRE WORK LOCATION:-D 41 & 41a Shawarma,Tacos,Burger + Indian at T3_Lucknow Airport
S. NO. | DESCRIPTION | UNIT | QTY. | Rate | Amount
1 | R1 (RESPONSE INDICATORS)
| Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Response indicators are connected to automatic fire detectors in order to indicate quickly the source of an alarm signal from detectors which are not easily accessible or visible. They light up as soon as the connected fire detector gives an alarm.(Wiring from switches to panel and stair case pressurization not included) | Nos | 5 | 1500 | 7500
2 | HD (HEAT DETECTOR) INSTALL NEAR HOOD
| Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) A heat detector is a fire alarm device designed to respond when the convected thermal energy of a fire increases the temperature of a heat sensitive element. The thermal mass and conductivity of the element regulate the rate flow of heat into the element. All heat detectors have this thermal lag (Wiring from switches to panel and stair case pressurization not included) (Edwards / Apollo) | Nos | 3 | 1800 | 5400
3 | CONVENTIONAL FIRE PANEL | Nos | 0 |  | -
4 | MCP (MANUAL CALL POINT)
| Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Manual call points are used to initiate an alarm signal, and operate by means of a simple button press or when glass is broken revealing a button. They can form part of a manual alarm system or an automatic alarm system.Model : Edwards / Apollo and FM approved with GI mounting Box | Nos | 1 | 3500 | 3500
5 | H (HOOTER)
| Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) Fire Alarm Systems. A fire alarm system is a electrical / electronic system which is connected with many type of devices such as main panel, smoke / heat detectors, mcp, sounder etc.. to detect the fire event by indiacating audio or visualize signal at the main or individual devices.Model : Edwards / Apollo with GI mounting Box | Nos | 1 | 3500 | 3500
6 | SD (SMOKE DETECTOR ABOVE CEILING)
| Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay.Model : Edwards / Apollo. | NOS | 5 | 3800 | 19000
7 | SD (SMOKE DETECTOR BELOW CEILING)
| Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model : Edwards / Apollo. | NOS | 0 |  | -
8 | MSD (MULTI SENSOR DETECTOR BELOW CEILING)
| Providing and fixing electrically operated flow indicating mechanical foam type (ISI marked) An optical smoke detector. Smoke enters through the slits around the side, triggering an electronic horn, which sounds through the large circular opening on the right. The dark circle in the middle is a test button with a built-in LED that flashes to show the detector is working okay. Model : Edwards / Apollo. | NOS | 2 | 3800 | 7600
9 | MONITOR MODULE
| Providing and fixing Emonitor module . Model : Edwards FMM-1 flash scan type UL listed and FM approved. | NOS | 0 |  | -
10 | 4.5 KG CO2 portable fire extinguiser ARAFFF capacity.(IS. 15683)Providing and fixing water Co2(ISI marked) extinguishers including all accessories as per IS specification with wall bracket with rawl plug. | NOS | 4 | 5600 | 22400
11 | 4 KG ABC Dry powder portable fire extinguiser capacity. (IS. 15683) Providing and fixing (ISI marked) extinguishers including all accessories as per IS specification with wall bracket with rawl plug. | NOS | 4 | 2500 | 10000
12 | 6 KG TRS K-type fire extinguiser capacity. (IS. 15683) Providing and fixing (ISI marked) extinguishers including all accessories as per IS specification with wall bracket with rawl plug. | NOS | 4 | 4500 | 18000
13 | Automatic 5 KG MOUDLAR ABC TYPE fire extinguiser capacity. (IS. 15683) Providing and fixing (ISI marked) extinguishers including all accessories as per IS specification with wall bracket with rawl plug. | NOS | 0 |  | -
14 | Fire Blanket-6'x4' | NOS | 3 | 2500 | 7500
15 | Acrylic EXIT Glow Sign Board with LED Lights, Size 10 x 6.5 inch, | NOS | 2 | 2500 | 5000
NOTE:
GRAND TOTAL |  |  |  |  | 109400

## OTHERS
BILL OF QUANTITIES FOR SPRINKLER WORK LOCATION:- D 41 & 41a Shawarma,Tacos,Burger + Indian at T3_Lucknow Airport
SR. NO. | DESCRIPTION | UNIT | QTY. | Rate | Amount
1 | Providing, Laying, Jointing & Testing of Pipes for Sprinkler System - G.I Pipe confirming IS Codes Class `C' Heavy Pipe & with necessary support & anchore fastening from slab.
a. | 25 mm dia | Rft. | 0 |  | -
b. | 32 mm dia | Rft. | 0 |  | -
c. | 40 mm dia | Rft. | 0 |  | -
d. | 50 mm dia | Rft. | 0 |  | -
e. | 65mm dia | Rft. | 0 |  | -
2 | Synthetic Enamel Paint.
a. | 25 mm dia | Rft. | 0 |  | -
b. | 32 mm dia | Rft. | 0 |  | -
c. | 40 mm dia | Rft. | 0 |  | -
d. | 50 mm dia | Rft. | 0 |  | -
e. | 65mm dia | Rft. | 0 |  | -
3 | Providing & Fixing of Butterfly Valve.
a. | 50 mm dia | No.
b. | 65 mm dia | No. | 0 |  | -
4 | Providing & Fixing of Ball Valve.
a. | 25 mm dia | No. | 0 |  | -
b. | 32 mm dia | No. | 0 |  | -
c. | 40 mm dia | No. | 0 |  | -
d. | 50 mm dia | No. | 0 |  | -
e. | 65 mm dia | No. | 0 |  | -
5 | HEADER FITTING.
a. | Flow Switch | No. | 0 |  | -
b | Pressure Gauge | No. | 0 |  | -
c | Air Release Valve | No. | 0 |  | -
d | 65 mm dia NRV | No. | 0 |  | -
6 | Providing & Fixing C.P. Brass 68 degree Quartzoid Bulb Sprinklers. Make : Tyco / viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed & EN approved.
a. | Pendant Type | No. | 11 | 750 | 8250
b. | UP Right Type | No. | 0 |  | -
7 | Providing & Fixing C.P. Brass 79 degree(QR) Quartzoid Bulb Sprinklers. Make : Tyco / viking temp rating standard coverage discharge coefficent k- 6.6 quick response UL listed & EN approved for high temperature area in Kitchen temprating shall be 79degree c (QR)
a. | Pendant Type | No. | 6 | 750 | 4500
b. | UP Right Type | No. | 0 |  | -
8 | Flexible Sprinkler Drop.
a. | 25mm | No. | 17 | 2200 | 37400
b. | 100mm | No. | 0 |  | -
c. | 150mm | No. | 0 |  | -
9 | Drain Valve | No. | 0 |  | -
NOTE:
GRAND TOTAL |  |  |  |  | 50150