## SUMMARY
SUMMARY FOR INTERIOR CIVIL, CARPENTRY & FINISHES WORK -
SR NO. | DESCRIPTION | BOQ AMOUNT | RA 1
1 | Interior work | 569990 | 349083
2 | Electrical Work | 339130 | 237391
3 | PLUMBING WORK | 166450 | 116515
Total amount |  | 1075570 | 702989
| GST 18% | 193602.6 | 126538.02
| Total amount with gst | 1269172.6 | 829527.02

## INTERIOR
ItemCode : ItemName : Interior Work | [7 empty] | RA -01
Sr No | Item Code | Item Name | UOM | Remarks | Quantity | Supplier Rate | Amount | AS PER SITE QTY | AS PER BOQ % | AMOUNT
1 | 3.2 | Back counter - Overall size 11 long x 2 6 deep x 3 ht in profile made made using 18 mm ply 25mm thk marine block board with supports as shown in drawing, counter top,50mm fascia finished in granite as per details in mirror polish.including shutters 3 | no |  | 1 | 71300 | 71300
2 | 1.2 | Existing false ceiling rework - Repairing existing fall ceiling Repainting | sqft |  | 122 | 120 | 14640 | 122 | 0.7 | 10248
3 | 1.1 | Dismantling front back counter Removing dubris to out side of Airport campus | No |  | 1 | 20000 | 20000 | 1 | 0.7 | 14000
4 | 5.1 | Partition- providing fixing Aluminum frame with both side ply panelling one laminate finish (10 X4 ) (8 X5 ) | sqft |  | 100 | 420 | 42000 | 100 | 0.7 | 29400
5 | 1.3 | Wall tiles removng - removing wall tiles making surface smooth for new tiles fixing (4 X11 1 ) | sqft |  | 45 | 100 | 4500 | 45 | 0.7 | 3150
6 | 3.3 | Coffee counter- overall size( 2 X3 ) 3 ht profil;e made up 18mm ply 25mm thk blockboard with support as shown in drawing counter top should be 50mm finished ijn granite as per details in mirror finish polish includding shutters intermidiate selves | no |  | 1 | 30000 | 30000 | 1 | 0.7 | 21000
7 | I | DEMOLITION REMOVAL |  |  | 0 | 0 | 0
8 | 1.7 | Removing breaking ply partition , dubris should be throught outside of campus | nos |  | 1 | 10000 | 10000 | 1 | 0.7 | 7000
9 | 1.9 | Painting- Repairing painting in fall ceiling | sqft |  | 200 | 100 | 20000 | 200 | 0.7 | 14000
10 |  | Back kitchen |  |  | 0 | 0 | 0
11 | 3.4 | Ledge wall - Providing fixing ledge wall 14 X3 X9 thk using 18 mm plywood for frame covering all with plywood top 1 is corian and the pending Area is laminate finish | sqft |  | 54 | 1450 | 78300 | 54 | 0.7 | 54810
12 | V | Carpentry works |  |  | 0 | 0 | 0 |  |  | 0
13 | 3.1 | Pass counter- at 4 X3 wide tops, including drawer made using 18 mm ply 25mm thk marine block board with supports as shown in drawing, counter top,fascia finished in Granite as per details in mirror polish, front apron finished in 1mm thick approved lami | no |  | 1 | 23000 | 23000 | 1 | 0.7 | 16100
14 | 1.4 | Back kitchen- back kitchen wall laminate removing , making smooth surface for new tiles fixing ( 11 2 X10 ) | sqft |  | 310 | 100 | 31000 | 310 | 0.7 | 21700
15 | 2.1 | Door - providing fixing door in back kitchen including frame both side laminate finish with all necessary hardware hinges,door closer, handle , stopper (7 X3 ) | nos |  | 1 | 18000 | 18000 | 1 | 0.7 | 12600
16 | 3.1 | Providing fixing laminate for signage 6 x4 | no |  | 1 | 7000 | 7000 | 1 | 0.7 | 4900
17 | IV | Civil works |  |  | 0 | 0 | 0
18 | 4.2 | Back kitchen - providing fixing back kitchen wall tiles( 11 2 X 10 )4 sides | sqft |  | 400 | 300 | 120000 | 400 | 0.7 | 84000
19 | 4.4 | Waterproofing - Providing making waterproofing in whole back kitchen area in (Dr Fixit)+on in betwwen granites to make 3 mm gape need to apply apoxy grout | nos |  | 1 | 10000 | 10000 | 1 | 0.7 | 7000
20 | 4.3 | back kitchen - Providing Making chamber including ss chamber jali, cutting floor tiles , chipping for laying drain pipe line | nos |  | 1 | 10000 | 10000 | 1 | 0.7 | 7000
21 | III | MISCELLANEOUS WORKS |  |  | 0 | 0 | 0
22 | 3.2 | Co2 cylinder boxing - Overall size 1600X330X750mm using 18mm thk ply for boxing for oxygen cylinder including door both side should be laminate finish | Sqm |  | 2.5 | 8000 | 20000 | 2.5 | 0.7 | 14000
23 | 1.8 | shifting table desk into new cctv room | nos |  | 1 | 3000 | 3000 | 1 | 0.7 | 2100
24 | II | DOORS |  |  | 0 | 0 | 0
25 | 1.5 | Temporary Barrication - Using 50mm x 50mm wood framework, covered with 6mm plywood vinyl film, up to 2.1 meter height, including door opening in barirication with lockable door arrangement.(existing at site) | sqft |  | 150 | 95 | 14250 | 150 | 0.7 | 9975
26 | 1.6 | TV- Shifting Tv in new cc tv room | nos |  | 1 | 2000 | 2000 | 1 | 0.7 | 1400
27 | 4.1 | Tiles - Providing fixing shadow wall tiles 24 x12 near pass through Window groove should be fill with grey grout (3 6 X2 6 )(5 8 X8 )(8 8 X2 4 )(4 8 X8 8 ) tiles should be provide by TFS team | sqft |  | 150 | 140 | 21000 | 150 | 0.7 | 14700
Total : |  |  |  |  | 1544.5 |  | 569990 |  |  | 349083

## PLUMBING
ItemCode : ItemName : Plumbing Work | [7 empty] | RA -01
Sr No | Item Code | Item Name | UOM | Remarks | Quantity | Supplier Rate | Amount | AS FOR SITE | AS FOR BOQ% | AMOUNT
1 | 6.1 | Hanging light - proving fixing plyboxing for strip light on front facia finish should in green lam should be provide by tfs team | sqft |  | 14 | 1450 | 20300 | 14 | 0.7 | 14210
2 | 6.7 | Hose pipe - Providing fixing hose pipe for geaser | nos |  | 6 | 600 | 3600 | 6 | 0.7 | 2520
3 | 6.4 | Geaser - providing fixing geaser with hot cold mixture | nos |  | 2 | 18000 | 36000 | 2 | 0.7 | 25200
4 |  | Plumbing works Subway Back kitchen |  |  | 0 | 0 | 0
5 | 6.2 | Angle cock - Providnig fixing angle cock in jaguar brand | nos |  | 10 | 900 | 9000 | 10 | 0.7 | 6300
6 | 6.9 | tap - Providing fixing tap | nos |  | 11 | 1500 | 16500 | 11 | 0.7 | 11550
7 | 6.1 | Pipe - Providing laying 20 mm cpvc pipe line for Ro domestic water | rft |  | 60 | 750 | 45000 | 60 | 0.7 | 31500
8 | 6.3 | Ball valve - Providing fixing ball valve | nos |  | 4 | 2250 | 9000 | 4 | 0.7 | 6300
9 | 6.5 | Sink - providing fixing sink on top of back counter | nos |  | 1 | 5500 | 5500 | 1 | 0.7 | 3850
10 | 6.8 | Meter - Providing fixing Ro water meter | nos |  | 1 | 4500 | 4500 | 1 | 0.7 | 3150
11 | 6.6 | Drain - providing laying drain pipe line 3 cpvc | rmt |  | 22 | 775 | 17050 | 22 | 0.7 | 11935
Total : |  |  |  |  | 131 |  | 166450 |  |  | 116515

## ELECTRIC
RA-01
Sr. No | Item Description | Pur. Grp. | Qty | UOM | Net Rate | Total Amount | AS FOR SITE | AS FOR BOQ% | AMOUNT
1 | Electrical | C01 | 1 | NOS | 339130 | 339130 | 1 | 0.7 | 237391
[6 empty] | 339130 |  |  | 237391