## C& I ABSTRACT
GOLD FINGER EST. PVT. LTD.
T1- CIP LOUNGE |  |  |  |  | Date :09/8/2024
C& I ABSTRACT
|  |  |  | As per Work Order |  | As per Work Done
S.NO | DESCRIPTION OF ITEMS | CODE / AREA SPECIFIED | UNIT | Total Qty | RATE | RA 01 BILL Total Qty | RA 01 BILL AMOUNT
1 | DISMENTLING & CLEANING WORKS | [6 empty] | AS PER SITE QTY EXTRA QTY ADD IN EXTRA ITEMS
2 | Dismantling of RCC works in beams, columns, slabs etc. including sub-base, cutting and removal of reinforcement, stacking of serviceable material. |  | Cum | 5 | 7820 | 5.00 | 39,100.00 | 20.83
3 | Disposal of building rubbish / malba / similar unserviceable, dismantled or waste materials by mechanical means, including loading, transporting, unloading to approved municipal dumping ground or as approved by Engineer-in-charge, beyond 50 m initial lead, for all leads and lifts complete. |  | Cum | 50 | 830.875 | 50.00 | 41,543.75 | 325.51
4 | 115mm brick wall |  | Sqm | 15 | 317.6875 | 15.00 | 4,765.31 | 0
5 | Dismentling, Removing, stacking & Re-using of Existing MS Partion frame work (considering or assuming 50% of total qty for re- using ) as per the actual work done at site, to be vrified and inspect by the site incharge. (Note : Actual measurement to be verified at site by the site incharge) Non used material to be handover to project client team by the GC vendor. |  | MT | 3 | 10263.75 | 3.00 | 30,791.25 | 0
6 | AAC BLOCK WORK : Providing and laying 100mm thick ACC block wall with grade -1 AAC Blocks of density 551.to 650kg / cum conforming to IS : 2185 ( Part -3) in superstructure above plinth level with R.C.C. bend at cill & Lintel level with approved block laying polymer modified adhesive mortar all complete as per direction of Engineer-in-Charge. (The payment of RCC band and reinforcement shall be made for separately). size of block (2'-0" x 0'-8" and width 0'-4" ). the rate also including scaffolding, curing etc. complete as specified. | [5 empty] | -
| 100mm thick Block work |  | Sqm | 551.74 | 1168.1125 | 223.6609 | 261,261.14
7 | LINTEL BEAM : R.C.C- ( 1 : 1.5 : 3 ) ( 1 cement : 1.5 coarse send : 3 graded stone aggregate 20mm nominal size ) for Bends where ever required I/c reinforcement 2Nos 8mm dia bar with 8mm dia links @ 150mm c/c including centering shuttering for all levels and height,( bend cross section size 100mm wide x 75mm thick ) etc. complete. The rate includes de-shuttering, shuttering oil, binding wire, curing, tools tackles all leads & heights as per direction of engineer- in -charge. |  | Rmt | 442.56 | 210.1625 | 280.7305 | 58,999.02
8 | CEMENT PLASTER : Providing and applying 15 mm thick cement plaster of mix in 1:4 (1 cement : 4 coarse sand) with admixture of waterproof binding agent liquid at 1:1 ratio with cement or as per manufacturer recomendation and applying at all levels & heights including scaffolding, curing etc. complete as specified. |  | Sqm | 1557.91 | 491.6825 | 437.7618 | 215,239.81
| TOTAL WORK DONE AMOUNT | [5 empty] | 651,700.28