## PI
VART
Infracon Pvt Ltd
229, Neha Ind. Est., Off Duttapada Road,
Opp. Oberoi Sky, Borivali (E), Mumbai - 400066
Contact No :- 022-40233596 / 28700110 Email : info@vartinfra.com
Proforma Invoice for The Irish House Extra item 3 LKO
To, | Simolina Kitchen Pvt. Ltd. |  |  | 2024-09-07
Ext-03 Ra-1st
Kindly Attn.:- Mr. Irfaan ji
Sr. No. | Description | Unit | Previous | Up To Date | This Bill
1 | The Irish House Extra Item -03 Ra-1st Bill | Job |  | 202569.0404 | 202569.0404
| Basic Total |  | 0 | 202569.0404 | 202569.0404
| Add GST @ 18% |  | 0 | 36462.4273 | 36462.4273
| Grand Total |  | 0 | 239031.4676 | 239031.4676
| This Bill Amount |  |  |  | 239031.4676
Work Completion Time Period
Material Delivery 1o days from the Date of PO with advance
Payment terms :
100% Advance with Work order
No Retention
For VART Infracon Pvt. Ltd.
Authorised Signatory

## Abstract
PRICE COMPARATIVE Extra item -03 , Ra-1st
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3 | [5 empty] | Qty. |  |  | Amount (RS) |  |  |  | Remarks
SR. NO. | ITEM DESCRIPTION | UOM | QTY. | UNIT RATE | Amount | Previous bill | This bill | Up To Date | Previous bill | This bill | Up To Date | Qty Varation | Remarks
EXTRA ITEM -03
1 | Providing Waterproof and flexible Led strips Lights for planters and Bar counter cove as per approved make and specification or as per project in-charge. | Rmt | 44.95 | 212.14 | 9535.693 |  | 43.85 | 43.85 |  | 9302.339 | 9302.339 | -233.354
2 | Providing Spike lights in 6 watt for a planters as per approved make and specification or as per project in-charge. | nos | 12 | 723.74 | 8684.88 |  | 12 | 12 |  | 8684.88 | 8684.88 | 0
3 | Proving and fixing 20mm SS (304) T- profile Finished in Brass PVD coating between Two diffrrent flooring,Fixed with Adhesive super glue or complete as per approved drawing and make and as directed by Engineer - In- Charge | Rmt | 44.29 | 1507.48 | 66766.2892 |  | 44.29 | 44.29 |  | 66766.2892 | 66766.2892 | 0
4 | Providing and applying Enamal black paint on Existing Cable Tray Height 3.75 m Height or per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate) | Sft. | 189.69 | 22 | 4173.18 |  | 189.6897 | 189.6897 |  | 4173.1727 | 4173.1727 | -0.0073392
5 | Providing and fixing exsting ceiling gypsum board to inseated FR grade fire board as per project in charge | Sft. | 1812.23 | 18.91 | 34269.2693 |  | 1812.23 | 1812.23 |  | 34269.2695 | 34269.2695 | 0.00020544
6 | Supplying, installation, Testing and commissioning flush mounting floor metallic boxes(POP-UP BOX) IP 66 3 module of 6/16A International switch & socket outlet + 1 set complete with all installation kits, accessories, required to finish the installation Make- Legrand | nos | 13 | 4955.93 | 64427.09 |  | 13 | 13 |  | 64427.09 | 64427.09 | 0
7 | Installation and testing of TV both side all nessery hardware required for fixing or as per project engineer. | Nos | 2 | 1173 | 2346 |  | 2 | 2 |  | 2346 | 2346 | 0
8 | Providing and fixing electric metre Make- Secure | Nos | 1 | 12600 | 12600 |  | 1 | 1 |  | 12600 | 12600 | 0
| TOTAL |  |  |  | 202802.4015 |  |  |  | 0 | 202569.0404 | 202569.0404 | -233.3611
| GST 18% |  |  |  | 36504.4323 |  |  |  | 0 | 36462.4273 | 36462.4273 | -42.005
| G.Total |  |  |  | 239306.8338 |  |  |  | 0 | 239031.4676 | 239031.4676 | -275.3661

## MB
MB Sheet
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3
SR. NO. | ITEM DESCRIPTION | Unit | No. | Length | Width | Height | Total | Remarks
1 | Providing Waterproof and flexible Led strips Lights for planters and Bar counter cove as per approved make and specification or as per project in-charge.
| Flexible Led strips for planters-01 | rmt. | 1 | 22 |  |  | 22
| Flexible Led strips for planters-02 | rmt. | 1 | 12 |  |  | 12
| Bar counter front | Rmt | 1 | 3.85 |  |  | 3.85
| Side | Rmt | 1 | 3 |  |  | 3
| Side | Rmt | 1 | 3 |  |  | 3
| Total Qty in Rmt | Rmt. |  |  |  |  | 43.85
| Previous Qty | Rmt |  |  |  |  | 0
| This Bill Qty | Rmt |  |  |  |  | 43.85
2 | Providing Spike lights in 6 watt for a planters as per approved make and specification or as per project in-charge.
| Spike Light for Planters | Nos | 12 |  |  |  | 12
| Total Qty in Rmt | Nos |  |  |  |  | 12
| Previous Qty | Nos |  |  |  |  | 0
| This Bill Qty | Nos |  |  |  |  | 12
3 | Proving and fixing 20mm SS (304) T- profile Finished in Brass PVD coating between Two diffrrent flooring,Fixed with Adhesive super glue or complete as per approved drawing and make and as directed by Engineer - In- Charge
| T profile | Rmt | 2 | 19.2 |  |  | 38.4
| Front of Bar counter | Rmt | 1 | 5.89 |  |  | 5.89
| Total Qty in Rmt | Rmt |  |  |  |  | 44.29
| Previous Qty | Rmt |  |  |  |  | 0
| This Bill Qty | Rmt |  |  |  |  | 44.29
4 | Providing and applying Enamal black paint on Existing Cable Tray Height 3.75 m Height or per desire and as per project -in - charge.(Quantity will be change after measurment,so far taken a close approximate)
| Cable tray | Sqm | 2 | 19.155 | 0.46 |  | 17.6226
| Total Qty in | sqm |  |  |  |  | 17.6226
| Total Qty in | Sft |  |  |  | 10.764 | 189.6897
| Previous Qty | Sft |  |  |  |  | 0
| This Bill Qty | Sft |  |  |  |  | 189.6897
5 | Providing and fixing exsting ceiling gypsum board to inseated FR grade fire board as per project in charge
| Flat area | Sqm | 1 | 18.3 | 9.2 |  | 168.3603
| Total Qty in | sqm |  |  |  |  | 168.3603
| Total Qty in | Sft |  |  |  | 10.764 | 1812.23
| Previous Qty | Sft |  |  |  |  | 0
| This Bill Qty | Sft |  |  |  |  | 1812.23
6 | Supplying, installation, Testing and commissioning flush mounting floor metallic boxes(POP-UP BOX) IP 66 3 module of 6/16A International switch & socket outlet + 1 set complete with all installation kits, accessories, required to finish the installation Make- Legrand
| Floor Pop up box | Nos | 13 |  |  |  | 13
| Total Qty in Rmt | Nos |  |  |  |  | 13
| Previous Qty | Nos |  |  |  |  | 0
| This Bill Qty | Nos |  |  |  |  | 13
7 | Installation and testing of TV both side all nessery hardware required for fixing or as per project engineer.
| TV Both side | Nos | 2 |  |  |  | 2
| Total Qty in Rmt | Nos |  |  |  |  | 2
| Previous Qty | Nos |  |  |  |  | 0
| This Bill Qty | Nos |  |  |  |  | 2
8 | Installation and testing of TV both side all nessery hardware required for fixing or as per project engineer.
| Electric Metre | Nos | 1 |  |  |  | 1
| Total Qty in Rmt | Nos |  |  |  |  | 1
| Previous Qty | Nos |  |  |  |  | 0
| This Bill Qty | Nos |  |  |  |  | 1