## PI
VART
Infracon Pvt Ltd
229, Neha Ind. Est., Off Duttapada Road,
Opp. Oberoi Sky, Borivali (E), Mumbai - 400066
Contact No :- 022-40233596 / 28700110 Email : info@vartinfra.com
Proforma Invoice
To, | Simolina Kitchen Pvt. Ltd. |  |  | 2024-03-07
Kindly Attn.:- Mr. Irfaan ji
Sr. No. | Description | Unit | Previous | Up To Date | This Bill
1 | The Irish House Interior and finishing work RA -4th | Job | 3087559.5957 | 4085227.0252 | 997667.4295
| Credit Note Against RA 01 |  | 16695.7627 | 16695.7627
| Basic Total |  | 3104255.3584 | 4101922.7879 | 997667.4295
| Add GST @ 18% |  | 558765.9645 | 738346.1018 | 179580.1373
| Grand Total |  | 3663021.323 | 4840268.8898 | 1177247.5668
| This Bill Amount |  |  |  | 1177247.5668
Work Completion Time Period
Material Delivery 1o days from the Date of PO with advance
Payment terms :
100% Advance with Work order
No Retention
For VART Infracon Pvt. Ltd.
Authorised Signatory

## Summary
THE IRISH HOUSE RA-4th
Sr No. | Ra Bills | PO Amount | Certified Amount incl GST | Remarks
| PO Amount | 5785249
1 | RA Biil 1 Civil & Interior |  | 1050216.4367
2 | RA Bill 2 Civil & Interior |  | 1226129.354
3 | RA Bill 3 Civil & interior |  | 1386675.5323
3 | RA Bill 4 Civil & interior |  | 1177247.5668
| Total |  | 4840268.8898

## Abstract
PRICE COMPARATIVE RA-3rd
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3 |  |  | Boq |  |  | Qty. |  |  | Amount (RS) |  |  | Varation | Remarks
SR. NO. | ITEM DESCRIPTION | UOM | QTY. | UNIT RATE | Amount | Previous bill | This bill | Up To Date | Previous bill | This bill | Up To Date
General Site Works
1 | Providing Pest Control & Anti-termite treatment by appointing a specialized agency as per the specifications mentioned by the Bureau of Indian Standard & Agencies specification (Whichever is higher ) for General Civil , Plumbing / Drainage & timber / Carpentry works , Gypsum related work including 5 Years guarantee under suitable undertaking on stamp paper etc complete as directed . ( Mode of Measurement to be on carpet area of floor & not the area of surface treated.) | sq.ft | QRO | 13
2 | Site Barricading - Providing and fixing flex board out. Cost to include framework cost, opening for door, flex printing and installation. ( digital file provided by client ) Sizes as mentioned below | sq.ft | QRO | 98
Waterproofing
3 | P&A Waterproofing on mother slabs, with single coats of chemical (Zypex or Equivalent chemical to be used) treatment on the mother slab, before doing the treatment mother slab needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team. (bar and flower bed entire carpet area considered) | sq.ft | QRO | 75 |  | 51.7899 | 0 | 51.7899 | 3884.2432 | 0 | 3884.2432 | 3884.2432
4 | P&A Waterproofing on mother slab & vertical wall up to 600mm height, with two coats of chemical (Zypex or Equivalent chemical to be used) treatment on wall surface, before doing the treatment wall surafce needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, including laying of 25mm protective layer of 1:4 , cement sand mortar on the mambaran sheet. After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team. (bar counter and flower bed wall considered) | sq.ft | QRO | 85 |  | 136.6802 | 0 | 136.6802 | 11617.8166 | 0 | 11617.8166 | 11617.8166
| Construction of Walls | [10 empty] | 0
5 | P&C of 100mm thick full height exposed brick wall in CM 1:4 proportion, including scaffolding, ranking out the joints, cutting, providing & fixing of 12mm thick MS rod for the each one meter height of the wall, lintel work for the doors & windows opening, seven days water treatment to the walls, etc. complete as per site engineer's instruction. (All internal divider wall up to 4000mm ht.) | sq.ft | QRO | 110 |  | 791.7697 | 0 | 791.7697 | 87094.6671 | 0 | 87094.6671 | 87094.6671
6 | P&C of 100mm thick height brick wall in CM 1:4 proportion, including scaffolding, ranking out the joints, cutting, providing & fixing of 12mm thick MS rod for the each one meter height of the wall, lintel work for the doors & windows opening, seven days water treatment to the walls, etc. complete as per site engineer's instruction. (Bar counter's walls of 1200mm ht.) | sq.ft | QRO | 115 | [7 empty] | 0
7 | P&C of 100mm thick height brick wall in CM 1:4 proportion, including scaffolding, ranking out the joints, cutting, providing & fixing of 12mm thick MS rod for the each one meter height of the wall, lintel work for the doors & windows opening, seven days water treatment to the walls, etc. complete as per site engineer's instruction. (flowerbed walls of 450mm ht.) | sq.ft | QRO | 110 |  | 136.6802 | 0 | 136.6802 | 15034.8215 | 0 | 15034.8215 | 15034.8215
| Plaster Works |  |  | -
8 | P&A of single coat backing plaster of 20 / 25 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction. | sq.ft | QRO | 65 |  | 781.8313 | 64.584 | 846.4153 | 50819.0345 | 4197.96 | 55016.9945 | 55016.9945
| Kobah works |  |  | -
9 | P&C of 150mm height Kobah with 100mm thick modifoam in 1:4 cement sand proportion, modifoam to be laid on the waterproofing treated floor in proper leveling, after laying of the block, void area to be filled up with Siporex or equivalent light weight materials including making of 50mm thick PCC in 1:4 cement sand proportion & stone chips, laying the same in proper line & level over the siporex block to get smooth surface to lay the finishing material on the said surface. Complete as per instruction by the site engineer. It is considered for performance platform. (For bar flooring raised area) | sq.ft | QRO | 150 |  | 117.8604 | 0 | 117.8604 | 17679.0627 | 0 | 17679.0627 | 17679.0627
| Flooring,Dado and counter works |  |  | -
10 | P&L of 19mm thick Kotah Stone (selected & approved grey colour) flooring ( Size, 600mm x 600mm ) @ Kitchen, laying with 38mm thick cement sand mortar bed in 1:4 proportions, including finishing of joints in white cement with added color pigments, etc. Rate inclusive of polish finished (not mirror finished) of the stone surface up to the mark as per client's satisfaction, necessary cut out for services purpose, chamfer of edges, etc. Complete in proper line & level as per site engineer's instruction.( It is considered for bar area) | sq.ft | 155 | 150 | 23250 | 117.8604 | 0 | 117.8604 | 17679.0627 | 0 | 17679.0627 | -5570.9373
11 | Fixing of Vitrified tile flooring of 1200mm X 600mm seating area's flooring, including laying of 38 / 45 mm thick cement sand mortar bed in 1:4 proportions below the tiles, finishing of joints in white cement with added color pigments. Rate should be included with sand, cement, spacer, grouting etc. all raw materials to lay the tiles up to the mark. Complete in proper line & level as per architectural drawing & site engineer's instruction..(Flooring pattern as per design). & Cleaning of the same as per intructions.tiles to be supplied by client. Basic cost - 120/ - | sq.ft | 1100 | 230 | 253000 | 1155.4896 | 139.7135 | 1295.2031 | 265762.6003 | 32134.1029 | 297896.7032 | 44896.7032
12 | Fixing of wooden finish Vitrified tile flooring of 1200mm X 300mm seating area's flooring, including laying of 38 / 45 mm thick cement sand mortar bed in 1:4 proportions below the tiles, finishing of joints in white cement with added color pigments. Rate should be included with sand, cement, spacer, grouting etc. all raw materials to lay the tiles up to the mark. Complete in proper line & level as per architectural drawing & site engineer's instruction..(Flooring pattern as per design). & Cleaning of the same as per intructions.tiles to be supplied by client. Basic cost - 150/ - | sq.ft | 600 | 265 | 159000 | 471.0676 | 0 | 471.0676 | 124832.9201 | 0 | 124832.9201 | -34167.0799
13 | Fixing of pattern Vitrified tile flooring in various size lasar cut entrance area's flooring, including laying of 38 / 45 mm thick cement sand mortar bed in 1:4 proportions below the tiles, finishing of joints in white cement with added color pigments. Rate should be included with sand, cement, spacer, grouting etc. all raw materials to lay the tiles up to the mark. Complete in proper line & level as per architectural drawing & site engineer's instruction..(Flooring pattern as per design). & Cleaning of the same as per intructions.tiles to be supplied by client. Basic cost - 150/ - | sq.ft | 275 | 270 | 74250 | 118.1887 | 0 | 118.1887 | 31910.9544 | 0 | 31910.9544 | -42339.0456
14 | P&F of 18 mm thick black leather finish granite skirting of 100mm height (selected & approved make. on existing wall's / column's surface with cement sand mortar bed in 1:4 proportions, finishing of joints in white cement with added color pigments, including cutting of random flamed granite slabs, finishing of top edges up to the mark, making cut out provision for all related services such as electrical switch board, plumbing fittings, etc as require. Complete laying in proper line & level as per architectural detail drawing & site engineer's instruction. Basic cost - 250/ - | RFT | 70 | 195 | 13650 | 146.9754 | 0 | 146.9754 | 28660.2069 | 0 | 28660.2069 | 15010.2069
15 | P&F of Semi vitrified tiles dado of 300mm x 600mm (Marbomax / Marbonite make, basic cost INR. 538.00/SM.) at bar's internal wall, fixing with cement sand mortar bed in 1:4 proportions / cement neru mortar bed in 1:1 proportions, including finishing of joints in white cement with added matching color pigments, etc, making cut out provisions for all related services such as electrical switch board, plumbing sanitary ware fittings, etc as required on site. Complete in proper line & level as per architectural detail drawing & site engineer's instruction. Tiles is considered up to 1200mm ht. Basic cost - 45/ - (COLOR DARK GREY) | sq.ft | 55 | 130 | 7150 | 98.9212 | 0 | 98.9212 | 12859.7508 | 0 | 12859.7508 | 5709.7508
16 | Chasing in existing brick/siphorex/concrete wall, up to 200mm wide and 75mm deep, for installation of A.C. copper pipes/drain pipes as required and making good of chases with cement plaster/POP ready for application of paint. | RFT | 20 | 59 | 1180 | 29.753 | 0 | 29.753 | 1755.4294 | 0 | 1755.4294 | 575.4294
17 | Making punctures in existing brick/siphorex/concrete wall block up to 600mm diameter, for passing A.C. copper pipes/drain pipes as required and making good the same with cement plaster/POP. | Nos | 5 | 1100 | 5500 | [6 empty] | -5500
18 | P & Fixing of approved & selected granite cladding on one step's tread & riser from sitting area to the bar area with sand cement mortar / adhesive bed in 1:4 proportion on the existing plaster finished wall, having necessary supporting to hold the ledge on the wall, including complete edge polishing & joints in added color pigments, making edge polish. Complete in proper line & level as per architectural detail drawing of step's dado & tread-riser stone cladding | sq.ft | 5 | 462 | 2310 | [6 empty] | -2310
19 | 150mm wide Leather Finsh Granite threshold between lobby and restaurant flooring and between the service corridor and the bond room. sand cement mortar / adhesive bed in 1:4 proportion on the existing plaster finished wall, having necessary supporting to hold the ledge on the wall, including complete edge polishing & joints in added color pigments, making edge polish. Complete in proper line & level as per architectural detail drawing. | RFT | 65 | 225 | 14625 | [6 empty] | -14625
Sub total for civil work.
20 | P&F of Flat false ceiling in 12mm thick India Gypsum or equivalent Gypboard, with GI perimeter channels of size 0.55 mm.thick ( having one flange of 20 mm.& another flange of 30 mm. and a web of 270 mm. ), GI intermediate channels of size 45 mm ( 0.9mm thick to flanges of 15 mm each), GI cleat and steel expansion fasteners, ceiling section of 0.55 thickness having with the help of connecting clip, 12.5mm tapered edge Gypboard ( confirming to IS 2095-1996:part-1), 25mm drywall screws etc necessary hardware fittings as required, after fixing the Gypboard, the joints to be filled with jointing compound, joint paper, tape and two coats of drywall tape suitable for Gypboard ( as per recommended practices of BPB India Gypsum) to gain smooth surface of the ceiling, including all necessary provision making & cutting for light fixtures, AC grills, diffusers, speakers, etc.. Complete in proper line & level as per architectural detail drawing & Site Engineer's instruction. (All GI perimeter , channels - should be Gypsteel India make & Gypboard- India Gypsum or equivalent make). Complete as per architectural detail drawings & site engineer's instruction. | sq.ft | 1800 | 118 | 212400 | 1540.393 | 271.8341 | 1812.227 | 181766.3721 | 32076.4186 | 213842.7907 | 1442.7907
21 | Providing and applying of POP Punning on plastered walls with plaster of paris of average thickness of 15 to 30 mm thk of approved make to true line, level, plumb including leveling, sanding of surface fit to receive further finish. ( For Wall Only) | sq.ft | 550 | 44 | 24200 | 363.5929 | 550.6479 | 914.2408 | 15998.0854 | 24228.5085 | 40226.5939 | 16026.5939
Sub total for POP work.
22 | P&A of Acrylic Emulsion Paint, approved make & shade on POP Gypboard finished ceilings/ wall/ mother slab with sand papering & cleaning the surface, applying double boiled linseed acrylic/oil/cement primer & Lambi putty to surface 3 times, there after painting the surface in three finishing coats over base primer coat to achieve even finish. Complete up to the mark & site engineer's instruction. including all ceiling. | sq.ft | 1800 | 35 | 63000 | 1087.3362 | 724.8908 | 1812.227 | 38056.7678 | 25371.1786 | 63427.9464 | 427.9464
23 | P&A of Luster Paint, approved make & shade on POP punning finished wall with sand papering & cleaning the surface, applying double boiled linseed acrylic/oil/cement primer & Lambi putty to surface 3 times, there after painting the surface in three finishing coats over base primer coat to achieve even finish. Complete up to the mark & site engineer's instruction. main wall | sq.ft | 550 | 42 | 23100 | 305.418 | 442.0507 | 747.4687 | 12827.5558 | 18566.1312 | 31393.6869 | 8293.6869
24 | P&A of texture metal paint on exposed duct, approved make & shade on decorative pop panel with sand papering & cleaning the surface, applying double boiled linseed acrylic/oil/cement primer, there after painting the surface in three finishing coats over base primer coat to achieve even finish. Complete up to the mark & site engineer's instruction. | sq.ft | 150 | 30 | 4500 |  | 923.3359 | 923.3359 |  | 27700.0776 | 27700.0776 | 23200.0776
25 | P&A of Linseed oil/lacquer for exposed red brick wall including the number of quotes up to the mark as per site engineer's instructions. | sq.ft | 450 | 60 | 27000 | 405.4911 | 421.972 | 827.4631 | 24329.467 | 25318.3205 | 49647.7875 | 22647.7875
26 | Fire sprinkler paint_Providing & applying Three (03) coats of fire rated paint as per standard on exposed surface on metal including removing of old paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | sq.ft | 50 | 35 | 1750 | 81.6154 | 0 | 81.6154 | 2856.5387 | 0 | 2856.5387 | 1106.5387
Sub total for Painting work.
27 | P&C of Service Station, with 19mm thick ashwood/ sheesham wood structure, unit having 4 nos. of drawers with necessary drawer compartment finished in felt, 1nos. of wooden shelves in side the unit, lower part having 3 nos. of open able shutters provision on one of the shutters (300mm L x 125mm H). unit finished with melanine polish. Rate inclusive of all necessary hardware fittings - like hinges, draw telescopic channels, cup board lock, decorative antique bolt handle, wire managers, locks etc. (approved & branded make) & necessary cut out for services requirements. Counter having 150mm ht. 18 mm thick flamed granite skirting on front side. Service desk back in paint finish as per refrence image with rough wood log borders in dark stain melamine polish as per reference image and the top front appron should have green paint with hand writtern text done by artist. Complete as per architectural detail drawing & site engineer's instruction. Size: 1000mm L x 600mm W x 1800mm H. | Nos | 2 | 44500 | 89000 | 1.6 | 0.4 | 2 | 71200 | 17800 | 89000 | 0
28 | P&C of Service Station, with 19mm thick ashwood/ sheesham wood structure, unit having 4 nos. of drawers with necessary drawer compartment finished in felt, 1nos. of wooden shelves in side the unit, lower part having 3 nos. of open able shutters provision on one of the shutters (300mm L x 125mm H). unit finished with melanine polish. Rate inclusive of all necessary hardware fittings - like hinges, draw telescopic channels, cup board lock, decorative antique bolt handle, wire managers, locks etc. (approved & branded make) & necessary cut out for services requirements. Counter having 150mm ht. 18 mm thick flamed granite skirting on front side. Service desk back in paint finish as per refrence image with rough wood log borders in dark stain melamine polish as per reference image and the top front appron should have green paint with hand writtern text done by artist. Complete as per architectural detail drawing & site engineer's instruction. Size: 1600mm L x 600mm W x 1800mm H. | Nos | 1 | 59500 | 59500 | 0.8 | 0.2 | 1 | 47600 | 11900 | 59500 | 0
29 | P&F of 600mm wide Bar counter solid wooden top with 19mm thick double plywood (selected & approved make, bwr grade) backing, plywood to be fixed on the existing low height bar wall's top having pelmet provision as shown details. After fixing the plywood 12mm thick x 200 mm wide seasoned 1st quality btc wooden plank to be fixed on the top of the bar counter, having half round shape molding on both the edges, wooden top be finished with high gloss lamination polish ( stain free) as per approved sample up to the mark. Complete as per architectural detail drawing & site engineer's instruction. Size: 12000mm L x 600mm W x 50mm H | RFT | 40 | 1327 | 53080 | 31.8876 | 0 | 31.8876 | 42314.8983 | 0 | 42314.8983 | -10765.1017
30 | P&F of 18mm thk marien plywood paneling on bar counter front surface in levels with 30mm offset to give provision of led light, with 50mm x 25mm aluminium pipe framing out of vertical members at 400 mm c/c & with horizontal members at 550 mm c/c, fixing the framing on the existing plaster finished wall, after fixing farming 19mm thick marien plywood (selected & approved make, bwr grade plywood) to be installed on the framing. Complete as per architectural detail drawing & site engineer's instruction. | sq.ft | 40 | 615 | 24600 | 119.7011 | 0 | 119.7011 | 73616.1531 | 0 | 73616.1531 | 49016.1531
31 | P&F of Rough outer sleeper wooden paneling at bar front wall with 15/18mm thick x 150mm wide rough outer sleeper wood to be fixed on the existing plywood paneling surface in different level with provision of indirect lighting, surface area to be finished with melamine polish. Rate including all necessary hardware fittings to install the rough wood, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive, etc.. Complete as per architectural detail drawing & site engineer's instruction. | sq.ft | 40 | 615 | 24600 | [6 empty] | -24600
32 | Providing & fixing brass Foot-rail made out of 38 mm.dia brass tube (14 gauge 304 grade hair line mat finished) framing, fixing the frame on floor with all necessary hardware fittings. Complete as per architectural detail drawing & site engineer' instruction.@ bar counter's front. | RFT | 40 | 643 | 25720 |  | 31.7563 | 31.7563 |  | 20419.288 | 20419.288 | -5300.712
33 | P&F of island counter of 600mm wide granite top working back counter, with 19mm thick marien plywood structure & 12mm plywood back (selected & approved make, bwr plywood), counter having 4 nos. of open able shutters (in 19mm thick plywood) on front side of the unit. Counter top to be finished with 19mm thick black galaxy granite with 38mm dual nose finished, counter front part, & all the visible part to be finished with 1mm thick wooden laminate, counter's internal part to be finished with 1mm thick light walnut laminate (selected make, basic cost INR. 1200.00/ sheet). Rate inclusive of all necessary hardware fittings - like hinges, draw telescopic channels, cup board lock, decorative antique bolt handle, wire managers, etc. (approved & branded make) & necessary cut out for services requirements. Counter having 50mm ht. 18 mm thick flamed granite skirting on front side on existing 150mm ht. kobah. Complete as per architectural detail drawing & site engineer's instruction. Size: 1760mm L x 600mm W x 1000mm H x1 nos. | RFT | 6 | 6726 | 40356 | 3.1625 | 5.2774 | 8.4399 | 21270.9212 | 35495.7117 | 56766.6329 | 16410.6329
BAR BACK
34 | P&F of bar back structure with MS framework made out of 50 x 50mm box section vertical members at 400 mm c/c & with horizontal members at 550 mm c/c, fixing the framing in proper line & level on existing wall/ floor/ mother slab. the MS to be finished with zink oxide and black powder coating. Rate including all necessary hardware fittings, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive, etc.. as required on site. Complete as per architectural detail drawing & site engineer's instruction. | RFT | 130 | 280 | 36400 | 83.3775 | 9.2642 | 92.6416 | 23345.6933 | 2593.9659 | 25939.6592 | -10460.3408
35 | P&F of crate wooden box paneling @ bar back wall having 25mm thick x 350mm wide x 350-450mm high crate wood (pine wood / approved wood) boxes to be fixed on both the MS framework with desired pattern as shown on the detail drawing, wooden surface to be finished clear PU paint. Rate including all necessary hardware fittings to install the panel, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. Pine wood Boxes Size: 350mm L x 350mm W x 500mm H as shown on elevation. | no. | 25 | 4560 | 114000 | 14 | 8 | 22 | 63840 | 36480 | 100320 | -13680
36 | P&F of 600mm wide 10MM THK toughned glass shelf with 10-15mm MS bidding all finished with black powder coating and shelf including provision for led lights. Rate including all necessary hardware fittings to install the partition, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. | sq.ft | 20 | 710 | 14200 |  | 18.7294 | 18.7294 |  | 13297.8456 | 13297.8456 | -902.1544
37 | P&F of 350mm wide Bar Bulkhead/ glass hanger having 25mm X 25MM brass metal in 2 layers having vertical and horizontal member @every 600mm c/c with 12mm thk toughthned glass shelf having provision for led profile light. brass metal to be brushed finish. the base including 8-10mm solid rods band in curve shape to hang the wine glass. Rate including all necessary hardware fittings to install the shelves, anchor fastner, ceiling support, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. Size: 2200mm L x 350mm W x 900mm H as shown on elevation. | RFT | 12 | 17150 | 205800 | 7.389 | 2.463 | 9.852 | 126721.35 | 42240.45 | 168961.8 | -36838.2
38 | P&F of Wooden rafter in hut shape with 19mm thick plywood boxing (selected & approved make, bwr grade plywood), boxing to be hanged from mother slab with necessary support from wall & slab to get hut shape as shown on detail drawing, after fixing the boxing in hut shape 15 /18 mm thick rough outer sleeper wood to be finished all three visible parts (except top side) the boxing (selected & approved sleeper wood), sleeper wood to be finished in linceed oil, including all necessary hardware fittings, required anchor fasteners to hang the rafter from the slab / wall, necessary scaffolding, etc. as required. Complete as per architectural detail drawing & site engineer's instruction. Size: 200mm H x 200mm D | RFT | 320 | 1425 | 456000 | 277.787 | 69.4467 | 347.2337 | 395846.4636 | 98961.6159 | 494808.0795 | 38808.0795
39 | P&F of "U" Shape Bench Seating, having 600mm width X 450MM seat height and 1200mm back ht. with 19mm thick plywood (selected & approved make, bwr grade) boxing for seating, boxing having storage provision, having 75mm to 175mm thk. slanted back partition of 1200mm ht with 19mm thick plywood framing & 12 mm thick plywood backing on the framing, openable seating with 50-75mm thick upholstery work (selected & approved density foam, father make) finished with selected & approved make fabrics (basic cost INR. 800 - 1000 /Mtr.), slanted back partition to be cusioned in chester feild pattern & all the visible parts of the bench seating to be finished with veneer having 150mm ht. 18 mm thick flamed granite skirting on front side. Rate including all necessary hardware fittings. Complete as per architectural detail drawing. | No | 2 | 102652 | 205304 | 1.8 | 0.2 | 2 | 184773.6 | 20530.4 | 205304 | 0
40 | P&F of Rough sleeper wooden paneling on main facade for signage with 12mm thick marine plywood (selected & approved make, bwr grade) backing on existing pop punning finished walls, after fixing of the plywood 15/18mm thick x 100mm wide rough sleeper wood to be fixed on the said surface and 18mm thick x 50mm wide btc wooden patti to bed fixed on all edges of the paneling as shown detail, total surface area to be finished with melamine polish. Rate including all necessary hardware fittings to install the panel, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive, etc.. Complete as per architectural detail drawing & site engineer's instruction. Size: 3000mm x 450mm height no. in hut shape, as per facade details. | sq.ft | 30 | 795 | 23850 | [6 empty] | -23850
41 | P&F of Wicket door of size 750mm x 1200mm @ Bar - a flush door . The outer surface of the door is with 15/18mm thick x 150mm wide sleeperwood to be finished with linceed oil.the top to have 75mm wide BTC wooden edge with round edging. The inner side of the door to be finished with 1mm thick laminate. Rate inclusive of all hardware fittings like- hinges, sliding channel, conceal door closer (Ozone make, 400mm ht. S.S. handle , door stopper, dead lock, tower bolt, all necessary hardware fittings, etc. (all the fittings should be branded / Ozone make and to be approved by architect / site engineer), both the sides having 150mm ht 14 gauge 304 grade SS (hairline matt finish) kick plate on bottom side of the door, etc. Complete as per architectural detail drawing & site engineer's instruction. Size: 750mm L x 1200mm H x 1 no. | Nos. | 1 | 23980 | 23980 |  | 1 | 1 |  | 23980 | 23980 | 0
42 | P&L of 6mm thick mdf sheet with transparent plastic paper to protect the flooring, after competition of all interior works the same to be removed from the floor with proper cleaning of the flooring & debris' to be removed from the compound. | sq.ft | 1800 | 52 | 93600 | 1664.2516 | 188.8791 | 1853.1308 | 86541.0853 | 9821.7151 | 96362.8005 | 2762.8005
43 | P&F of 450mm dia half cut wooden barrel finished with artistic paint & lacquer finish fixed on existing ms framework. Rate including all necessary hardware fittings to install the barrel, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. | Nos. | 12 | 7567 | 90804 |  | 0 | 0 |  | 0 | 0 | -90804
44 | P&F of crate wooden box having 25mm thick x 600mm wide x 250 mm high crate wood (pine wood / approved wood) boxes to be fixed on both the MS framework with desired pattern as shown on the detail drawing, wooden surface to be finished clear PU paint. Rate including all necessary hardware fittings to install the panel, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. Pine wood Boxes Size: 350mm L x 350mm W x 500mm H as shown on elevation. | no. | 20 | 3989 | 79780 | 6 | 11 | 17 | 23934 | 43879 | 67813 | -11967
45 | P & f of 900mm high MS decorative railing, with 50 mm x 50mm 14 swg gauge ms box post to be finished with 12mm thk plywood and veneer, top rail of 50mm X 50mm square pipe framing 14 swg gauge pipe having solid square rod 15mm X 15mm decorative design as shown on details drawing, with base plate fixing with necessary fastener. Complete railing in black powder coat finish. | RFT | 65 | 7357 | 478205 | 48.6032 | 4.302 | 52.9052 | 357573.7424 | 31650.1083 | 389223.8507 | -88981.1493
46 | P & f of MS framing for planters, with 25mm X 50mm box section framing (14 swg gauge) with 3 nos of horizontal and 12 nos of vertical frames as shown on details drawing, with base plate fixing with necessary fastener and to be finished in approve black powder coating. height upto 4000mm. | RFT | 350 | 220 | 77000 | 96.9765 | 221.2962 | 318.2728 | 21334.8344 | 48685.1733 | 70020.0077 | -6979.9923
47 | P & f of 1600mm high- 600mm height pine wood picket fance railing having 25mm thk pine wood plants size of 100mm wide finished in clear PU polish with color pegment. internal 25mm x 25mm MS framework to support the structure in curve shape. the metal to be finished with powder coating. the cost include all hardware fixture, required base plate, cutting rounding finishing in all respect as per drawing and instruction. | sq.ft | 550 | 806 | 443300 | 317.8609 | 0 | 317.8609 | 256195.9015 | 0 | 256195.9015 | -187104.0985
48 | P & f of pinewood board size of 600 x 900mm having 12mm thk pine wood plants size of 100mm wide finished in clear PU polish with color pegment. internal 25mm x 25mm MS framework to support the structure in curve shape. the metal to be finished with powder coating. the cost include all hardware fixture, required base plate, cutting rounding finishing in all respect as per drawing and instruction. | Nos. | 10 | 6720 | 67200 | [6 empty] | -67200
49 | Providing & fixing brass Foot-rail near planter box made out of 38 mm.dia brass tube (14 gauge 304 grade hair line mat finished) framing, fixing the frame on floor with all necessary hardware fittings. Complete as per architectural detail drawing & site engineer' instruction.@ bar counter's front. | RFT | 120 | 653 | 78360 |  | 81.4432 | 81.4432 |  | 53182.4096 | 53182.4096 | -25177.5904
50 | P&F of 25mm thk BTC wood signage with ingrave letters finished with melamine polish. Size - 2200 x 300mm high | Nos. | 1 | 11980 | 11980 | [6 empty] | -11980
51 | P&F of wooden paneling on column, with 50mm x 25mm aluminium pipe framing out of vertical members at 400 mm c/c & with horizontal members at 550 mm c/c, fixing the framing on the existing plaster finished column, after fixing farming 12mm thick plywood (selected & approved make, bwr grade plywood) to be installed on the framing and finished with apporved veneer and bamboo rope as per design. Complete as per architectural detail drawing & site engineer's instruction. | sq.ft | 200 | 609 | 121800 | 100.7403 | 0 | 100.7403 | 61350.8281 | 0 | 61350.8281 | -60449.1719
52 | Real scale jeep (vehicle) artwork installtion | job | 1 | 20000 | 20000 |  | 0.8 | 0.8 |  | 16000 | 16000 | -4000
53 | Old wooden barrel size of 600mm dia meter with proper polish | Nos. | 15 | 18450 | 276750 |  | 4.8 | 4.8 |  | 88560 | 88560 | -188190
54 | Artist work on wall_ slogans/ write up on walls. (Lumpsum amount 25000/- ) | Nos. | 10 | 3400 | 34000 | [6 empty] | -34000
55 | Artifact from antique store as per selection. (Lumpsum amount 2,00,000/- ) | job | 1 | 201450 | 201450 |  | 0.8 | 0.8 |  | 161160 | 161160 | -40290
56 | Canvas Photoframes and random size mirror as per brandstandard sizes in random frame design (Lumpsum amount 1,50,000/- ) | Nos. | 30 | 5150 | 154500 | [6 empty] | -154500
57 | P&F of Hostess desk barrel size of 1200mm height and 750-900mm dia finished with melamine polish. | Nos. | 1 | 37650 | 37650 |  | 0.8 | 0.8 |  | 30120 | 30120 | -7530
58 | P&F of hanging barrel structure with MS framework made out of 50 x 50mm box section vertical members at 400 mm c/c & with horizontal members at 550 mm c/c, fixing the framing in proper line & level on existing wall mother slab. the MS to be finished with zink oxide and black powder coating. Rate including all necessary hardware fittings, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive, etc.. as required on site. Complete as per architectural detail drawing & site engineer's instruction. | RFT | 350 | 325 | 113750 | 168.5349 | 4.0525 | 172.5873 | 54773.836 | 1317.0482 | 56090.8842 | -57659.1158
59 | Providing fixing double leaf toughened glass door with 600mm fix glass on top fixed on existing faacde with patch fitting. Rate to include cost of heavy duty floor spring (Everite / Hemco / Haldin / Hyper or equivalent of capacity 120 kg), wooden/ sleeperwood decorative handle of size 900mm, mortise concealed lock, all required hardware patch fitting complete as directed. (Toughned Glass Door : Size - 1800mm X 2400mm) | Nos. | 1 | 53855 | 53855 |  | 0 |  |  | 0 | 0 | -53855
60 | P&F of Dual leaf service trap door, with wooden framework out of vertical members at 400 mm c/c & with horizontal members at 550 mm c/c with both side 12mm thick bwr plywood (selected & approved make) backing both side of the framing,. Rate inclusive of all necessary supporting from existing slab, necessary scaffolding & hardware fittings, etc. Complete as per architectural detail drawing. Size: 1200mm X 2400mm. | Nos. | 2 | 21235 | 42470 | 2 | 0 | 2 | 42470 | 0 | 42470 | 0
61 | P&F of slate black board, with 1st grade BTC framing finished with melamine polish etc. Complete as per architectural detail drawing & site engineer's instruction. Size - 900 X 1200 mm | No | 2 | 10082 | 20164 | [6 empty] | -20164
62 | P&F of Main DB/ electrical panel unit of 600mm depth made out of 19mm thick plywood structure & with 12mm thick plywood (selected & approved make, bwr grade plywood) back, having 4 nos of semi wooden louvers open able shutter HT. 2200mm in wood, wooden surface to be finished with exterior grade melamine polish. Rate including all necessary hardware fittings to install the panel, and in rest of the side finished with 1mm thick light walnut laminate (selected make, basic cost INR. 800.00/ sheet), having provision of 75mm height cove light pelmet, all edges should be btc wooden patta with polish finished, including all necessary hardware fittings (approved & branded make) - like hinges, tower bolt, cup board lock, extended bottom part of the shutter to be used as a handle, etc. (approved & branded make) & necessary cut out for services requirements, etc. Complete as per architectural detail drawing & site engineer's instruction. Size: 3000mm L x 3000mm H x 1 no. | No | 1 | 99880 | 99880 | 1 | 0 | 1 | 99880 | 0 | 99880 | 0
Sub total for Interior Carpentry Work. Amt. Rs.
EXTRA ITEM - Part-1
1 | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, followed with 12mm thk. Bison board as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures. | Sft. | 218.8773 | 400 | 87550.9315 | 218.8773 | 0 | 218.8773 | 87550.9315 | 0 | 87550.9315 | 0
| GRAND TOTAL | [7 empty] | 3087559.5957 | 997667.4295 | 4085227.0252 | -905076.9063
19100

## MB Sheet
MB Sheet
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3 RA-4th
SR. NO. | ITEM DESCRIPTION | Unit | No. | Length | Width | Height | Total | Remarks
General Site Works
1 | Providing Pest Control & Anti-termite treatment by appointing a specialized agency as per the specifications mentioned by the Bureau of Indian Standard & Agencies specification (Whichever is higher ) for General Civil , Plumbing / Drainage & timber / Carpentry works , Gypsum related work including 5 Years guarantee under suitable undertaking on stamp paper etc complete as directed . ( Mode of Measurement to be on carpet area of floor & not the area of surface treated.) | sq.ft
2 | Site Barricading - Providing and fixing flex board out. Cost to include framework cost, opening for door, flex printing and installation. ( digital file provided by client ) Sizes as mentioned below | sq.ft
Waterproofing
3 | P&A Waterproofing on mother slabs, with single coats of chemical (Zypex or Equivalent chemical to be used) treatment on the mother slab, before doing the treatment mother slab needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team. (bar and flower bed entire carpet area considered) | sq.ft
| Planter-1 | sqm | 1 | 10.08 | 0.33 |  | 3.3264
| Planter-2 | sqm | 1 | 4.5 | 0.33 |  | 1.485
| Total Qty in Sqm | sqm |  |  |  |  | 4.8114
| Total Qty in Sqm | sft |  |  |  | 10.764 | 51.7899
| Previous Qty | sft |  |  |  |  | 51.7899
| This Bill Qty. | sft |  |  |  |  | 0
4 | P&A Waterproofing on mother slab & vertical wall up to 600mm height, with two coats of chemical (Zypex or Equivalent chemical to be used) treatment on wall surface, before doing the treatment wall surafce needs to clean properly up to the mark & dust free surface needs to achieve to apply the chemical (proof bond /BASF, Dr. Fixit / Equivalent make) & chemical needs to dry properly, including laying of 25mm protective layer of 1:4 , cement sand mortar on the mambaran sheet. After all there should be a water pond testing to be done for water tightness & rectifications of defects if any. Complete with 10 years performance guarantee with client's satisfaction. Entire process to be done under guideline & supervision of appointed engineering team. (bar counter and flower bed wall considered) | sq.ft
| Planter-1 | sqm | 1 | 20.08 |  | 0.43 | 8.6344
| Planter-2 | sqm | 1 | 9.45 |  | 0.43 | 4.0635
| Total Qty in Sqm | sqm |  |  |  |  | 12.6979
| Total Qty in Sqm | sft |  |  |  | 10.764 | 136.6802
| Previous Qty | sft |  |  |  |  | 136.6802
| This Bill Qty. | sft |  |  |  |  | 0
Construction of Walls
5 | P&C of 100mm thick full height exposed brick wall in CM 1:4 proportion, including scaffolding, ranking out the joints, cutting, providing & fixing of 12mm thick MS rod for the each one meter height of the wall, lintel work for the doors & windows opening, seven days water treatment to the walls, etc. complete as per site engineer's instruction. (All internal divider wall up to 4000mm ht.) | sq.ft
| Back sofa side wall | Sqm | 1 | 7.82 |  | 3.73 | 29.1686
| Bar counter area | Sqm | 1 | 10.02 |  | 3.71 | 37.1742
| Designer wall | Sqm | 1 | 1.75 |  | 2.4 | 4.2
| Above door opening to the lucknow street | Sqm | 1 | 1.38 |  | 0.88 | 1.2144
| Designer wall extended | Sqm | 1 | 0.75 |  | 2.4 | 1.8
| Total Qty in Sqm | Sqm |  |  |  |  | 73.5572
| Total Qty in Sqm | Sft |  |  |  | 10.764 | 791.7697
| Previous Qty | Sft |  |  |  |  | 791.7697
| This Bill Qty. | Sft |  |  |  |  | 0
6 | P&C of 100mm thick height brick wall in CM 1:4 proportion, including scaffolding, ranking out the joints, cutting, providing & fixing of 12mm thick MS rod for the each one meter height of the wall, lintel work for the doors & windows opening, seven days water treatment to the walls, etc. complete as per site engineer's instruction. (Bar counter's walls of 1200mm ht.)
7 | P&C of 100mm thick height brick wall in CM 1:4 proportion, including scaffolding, ranking out the joints, cutting, providing & fixing of 12mm thick MS rod for the each one meter height of the wall, lintel work for the doors & windows opening, seven days water treatment to the walls, etc. complete as per site engineer's instruction. (flowerbed walls of 450mm ht.)
| Planter-1 | sqm | 1 | 20.08 |  | 0.43 | 8.6344
| Planter-2 | sqm | 1 | 9.45 |  | 0.43 | 4.0635
| Total Qty in Sqm | sqm |  |  |  |  | 12.6979
| Total Qty in Sqm | sft |  |  |  | 10.764 | 136.6802
| Previous Qty | sft |  |  |  |  | 136.6802
| This Bill Qty. | sft |  |  |  |  | 0
| Plaster Works |  |  | -
8 | P&A of single coat backing plaster of 20 / 25 mm thick in CM 1:4 proportion to the walls & others surface including scaffolding, curing the joints, etc. The rates are inclusive of providing chicken mesh of 18mm gauge & 150mm width at junction of brick & RCC etc. at the walls, columns, beams etc., seven days water treatment as anti crack of plaster. Complete as per site engineer's instruction. | sq.ft
| Planter-1 | Sqm | 2 | 20.08 |  | 0.43 | 17.2688
| Planter-2 | Sqm | 2 | 9.45 |  | 0.43 | 8.127
| Design plaster sofa back wall | Sqm | 0.7 | 7.82 |  | 3.73 | 20.418
| Above door opening | Sqm | 0.7 | 1.4 |  | 3.73
| Above door opening to the lucknow street | Sqm | 0.7 | 1.38 |  | 0.88 | 0.85008
| Bar counter area | Sqm | 0.7 | 10 |  | 3.71 | 25.97
| Desiner Jeep Wall plaster | Sqm | 1 | 2.5 |  | 2.4 | 6
| Total Qty in Sqm | sqm |  |  |  |  | 78.6339
| Total Qty in Sqm | Sft |  |  |  | 10.764 | 846.4153
| Previous Qty | Sft |  |  |  |  | 781.8313
| This Bill Qty. | Sft |  |  |  |  | 64.584
| Kobah works |  |  | -
9 | P&C of 150mm height Kobah with 100mm thick modifoam in 1:4 cement sand proportion, modifoam to be laid on the waterproofing treated floor in proper leveling, after laying of the block, void area to be filled up with Siporex or equivalent light weight materials including making of 50mm thick PCC in 1:4 cement sand proportion & stone chips, laying the same in proper line & level over the siporex block to get smooth surface to lay the finishing material on the said surface. Complete as per instruction by the site engineer. It is considered for performance platform. (For bar flooring raised area) | sq.ft
| Bar counter area | Sqm | 1 | 3.05 |  | 3.59 | 10.9495
| Total Qty in Sqm | sqm |  |  |  |  | 10.9495
| Total Qty in Sqm | Sft |  |  |  | 10.764 | 117.8604
| Previous Qty | sft |  |  |  |  | 117.8604
| This Bill Qty. | Sft |  |  |  |  | 0
| Flooring,Dado and counter works |  |  | -
10 | P&L of 19mm thick Kotah Stone (selected & approved grey colour) flooring ( Size, 600mm x 600mm ) @ Kitchen, laying with 38mm thick cement sand mortar bed in 1:4 proportions, including finishing of joints in white cement with added color pigments, etc. Rate inclusive of polish finished (not mirror finished) of the stone surface up to the mark as per client's satisfaction, necessary cut out for services purpose, chamfer of edges, etc. Complete in proper line & level as per site engineer's instruction.( It is considered for bar area)
| Bar counter area | Sqm | 1 | 3.05 | 3.59 |  | 10.9495
| Total Qty in Sqm | Sqm |  |  |  |  | 10.9495
| Total Qty in Sqm | Sft |  |  |  | 10.764 | 117.8604
| Previous Qty | Sft |  |  |  |  | 117.8604
| This Bill Qty. | Sft |  |  |  |  | 0
11 | Fixing of Vitrified tile flooring of 1200mm X 600mm seating area's flooring, including laying of 38 / 45 mm thick cement sand mortar bed in 1:4 proportions below the tiles, finishing of joints in white cement with added color pigments. Rate should be included with sand, cement, spacer, grouting etc. all raw materials to lay the tiles up to the mark. Complete in proper line & level as per architectural drawing & site engineer's instruction..(Flooring pattern as per design). & Cleaning of the same as per intructions.tiles to be supplied by client. Basic cost - 120/ - | sq.ft
| area | Sqm | 1 | 7.73 | 13.59 |  | 105.0507
|  | Sqm | 1 | 4.26 | 2.91 |  | 12.3966
| Tile replace due to railing removing | Sqm | 4 | 1.2 | 0.6 |  | 2.88
| Total Qty in sqm | sqm |  |  |  |  | 120.3273
| Total Qty in sft | Sft |  |  |  | 10.764 | 1295.2031
| Previous Qty | Sft |  |  |  |  | 1155.4896
| This Bill Qty. | Sft |  |  |  |  | 139.7135
12 | Fixing of wooden finish Vitrified tile flooring of 1200mm X 300mm seating area's flooring, including laying of 38 / 45 mm thick cement sand mortar bed in 1:4 proportions below the tiles, finishing of joints in white cement with added color pigments. Rate should be included with sand, cement, spacer, grouting etc. all raw materials to lay the tiles up to the mark. Complete in proper line & level as per architectural drawing & site engineer's instruction..(Flooring pattern as per design). & Cleaning of the same as per intructions.tiles to be supplied by client. Basic cost - 150/ - | sq.ft
| wooden tiles arount bar counter | Sqm | 1 | 12.51 | 1.175 |  | 14.6993
|  |  |  | 18.165 | 1.6 |  | 29.064
| Total Qty in sqm | sqm |  |  |  |  | 43.7632
| Total Qty in sft | Sft |  |  |  | 10.764 | 471.0676
| Previous Qty | Sft |  |  |  |  | 471.0676
| This Bill Qty. | Sft |  |  |  |  | 0
13 | Fixing of pattern Vitrified tile flooring in various size lasar cut entrance area's flooring, including laying of 38 / 45 mm thick cement sand mortar bed in 1:4 proportions below the tiles, finishing of joints in white cement with added color pigments. Rate should be included with sand, cement, spacer, grouting etc. all raw materials to lay the tiles up to the mark. Complete in proper line & level as per architectural drawing & site engineer's instruction..(Flooring pattern as per design). & Cleaning of the same as per intructions.tiles to be supplied by client. Basic cost - 150/ - | sq.ft
| Entrance area | sqm | 1 | 18.3 | 0.6 |  | 10.98
| Total Qty in Sqm | sqm |  |  |  |  | 10.98
| Total Qty in Sft | Sft |  |  |  | 10.764 | 118.1887
| Previous Qty | Sft |  |  |  |  | 118.1887
| This Bill Qty. | Sft |  |  |  |  | 0
14 | P&F of 18 mm thick black leather finish granite skirting of 100mm height (selected & approved make. on existing wall's / column's surface with cement sand mortar bed in 1:4 proportions, finishing of joints in white cement with added color pigments, including cutting of random flamed granite slabs, finishing of top edges up to the mark, making cut out provision for all related services such as electrical switch board, plumbing fittings, etc as require. Complete laying in proper line & level as per architectural detail drawing & site engineer's instruction. Basic cost - 250/ - | RFT
| Planter -1 | Rmt | 1 | 20.08 |  |  | 20.08
| Planter-2 | Rmt | 1 | 9.45 |  |  | 9.45
| Bar counter skarting 150 mm front | Rmt | 1.5 | 3.85 |  |  | 5.775
| Side | Rmt | 1.5 | 3.15 |  |  | 4.725
| Side | Rmt | 1.5 | 3.15 |  |  | 4.725
| Total Qty in Rmt | Rmt |  |  |  |  | 44.755
| Total Qty in Rft | Rft |  |  |  | 3.284 | 146.9754
| Previous Qty | Rft |  |  |  |  | 146.9754
| This Bill Qty. | Rft |  |  |  |  | 0
15 | P&F of Semi vitrified tiles dado of 300mm x 600mm (Marbomax / Marbonite make, basic cost INR. 538.00/SM.) at bar's internal wall, fixing with cement sand mortar bed in 1:4 proportions / cement neru mortar bed in 1:1 proportions, including finishing of joints in white cement with added matching color pigments, etc, making cut out provisions for all related services such as electrical switch board, plumbing sanitary ware fittings, etc as required on site. Complete in proper line & level as per architectural detail drawing & site engineer's instruction. Tiles is considered up to 1200mm ht. Basic cost - 45/ - (COLOR DARK GREY) | sq.ft
| front wall | sqm | 1 | 3.59 |  | 1 | 3.59
| RHS wall | sqm | 1 | 3.05 |  | 1 | 3.05
| LHS wall | sqm | 1 | 2.55 |  | 1 | 2.55
| Total Qty in Sqm | sqm |  |  |  |  | 9.19
| Total Qty in Sft | Sft |  |  |  | 10.764 | 98.9212
| Previous Qty | Sft |  |  |  |  | 98.9212
| This Bill Qty. | Sft |  |  |  |  | 0
16 | Chasing in existing brick/siphorex/concrete wall, up to 200mm wide and 75mm deep, for installation of A.C. copper pipes/drain pipes as required and making good of chases with cement plaster/POP ready for application of paint. | RFT
| Bar counter area chassing brick wall for gyser and ro line horizontal | Rmt | 1 | 2.6 |  |  | 2.6
| Vertical on wall | Rmt | 1 | 3.73 |  |  | 3.73
| Wall chassing for electrical DB back side for cable tray concealed | Rmt | 1 | 2.73 |  |  | 2.73
| Total Qty in Rmt | Rmt |  |  |  |  | 9.06
| Total Qty in Rft | Rft |  |  |  | 3.284 | 29.753
| Previous Qty | Rft |  |  |  |  | 29.753
| This Bill Qty. | Rft |  |  |  |  | 0
17 | Making punctures in existing brick/siphorex/concrete wall block up to 600mm diameter, for passing A.C. copper pipes/drain pipes as required and making good the same with cement plaster/POP. | Nos
18 | P & Fixing of approved & selected granite cladding on one step's tread & riser from sitting area to the bar area with sand cement mortar / adhesive bed in 1:4 proportion on the existing plaster finished wall, having necessary supporting to hold the ledge on the wall, including complete edge polishing & joints in added color pigments, making edge polish. Complete in proper line & level as per architectural detail drawing of step's dado & tread-riser stone cladding | sq.ft
19 | 150mm wide Leather Finsh Granite threshold between lobby and restaurant flooring and between the service corridor and the bond room. sand cement mortar / adhesive bed in 1:4 proportion on the existing plaster finished wall, having necessary supporting to hold the ledge on the wall, including complete edge polishing & joints in added color pigments, making edge polish. Complete in proper line & level as per architectural detail drawing. | RFT
20 | P&F of Flat false ceiling in 12mm thick India Gypsum or equivalent Gypboard, with GI perimeter channels of size 0.55 mm.thick ( having one flange of 20 mm.& another flange of 30 mm. and a web of 270 mm. ), GI intermediate channels of size 45 mm ( 0.9mm thick to flanges of 15 mm each), GI cleat and steel expansion fasteners, ceiling section of 0.55 thickness having with the help of connecting clip, 12.5mm tapered edge Gypboard ( confirming to IS 2095-1996:part-1), 25mm drywall screws etc necessary hardware fittings as required, after fixing the Gypboard, the joints to be filled with jointing compound, joint paper, tape and two coats of drywall tape suitable for Gypboard ( as per recommended practices of BPB India Gypsum) to gain smooth surface of the ceiling, including all necessary provision making & cutting for light fixtures, AC grills, diffusers, speakers, etc.. Complete in proper line & level as per architectural detail drawing & Site Engineer's instruction. (All GI perimeter , channels - should be Gypsteel India make & Gypboard- India Gypsum or equivalent make). Complete as per architectural detail drawings & site engineer's instruction. | sq.ft
| Flat area | Sqm | 1 | 18.3 | 9.2 |  | 168.36
100%
| Total Qty in Sqm | Sqm |  |  |  |  | 168.36
| Total Qty in Sft | Sft |  |  |  | 10.764 | 1812.227
| Previous Qty | Sft |  |  |  |  | 1540.393
| This Bill Qty. | Sft |  |  |  |  | 271.8341
21 | Providing and applying of POP Punning on plastered walls with plaster of paris of average thickness of 15 to 30 mm thk of approved make to true line, level, plumb including leveling, sanding of surface fit to receive further finish. ( For Wall Only) | sq.ft
| Design plaster sofa back wall | Sqm | 0.7 | 7.82 |  | 3.73 | 20.418
| Above door opening to the lucknow street | Sqm | 0.7 | 1.38 |  | 0.88 | 0.85008
| Bar counter area | Sqm | 0.7 | 10.02 |  | 3.71 | 26.0219
| Glass fasade above area pop | Sqm | 0.7 | 18.7 |  | 0.85 | 15.895
| Airport coridor side pop | Sqm | 0.7 | 17.5 |  | 0.9 | 15.75
| Desiner Jeep Wall pop | Sqm | 1 | 2.5 |  | 2.4 | 6
| Total Qty in Sqm | Sqm |  |  |  |  | 84.935
| Total Qty in sft | Sft |  |  |  | 10.764 | 914.2408
| Previous Qty | Sft |  |  |  |  | 363.5929
| This Bill Qty. | Sft |  |  |  |  | 550.6479
22 | P&A of Acrylic Emulsion Paint, approved make & shade on POP Gypboard finished ceilings/ wall/ mother slab with sand papering & cleaning the surface, applying double boiled linseed acrylic/oil/cement primer & Lambi putty to surface 3 times, there after painting the surface in three finishing coats over base primer coat to achieve even finish. Complete up to the mark & site engineer's instruction. including all ceiling. | sq.ft
| Flat area | Sqm | 1 | 18.3 | 9.2 |  | 168.36
100%
| Total Qty in Sqm | Sqm |  |  |  |  | 168.36
| Total Qty in Sft | Sft |  |  |  | 10.764 | 1812.227
| Previous Qty | Sft |  |  |  |  | 1087.3362
| This Bill Qty. | Sft |  |  |  |  | 724.8908
23 | P&A of Luster Paint, approved make & shade on POP punning finished wall with sand papering & cleaning the surface, applying double boiled linseed acrylic/oil/cement primer & Lambi putty to surface 3 times, there after painting the surface in three finishing coats over base primer coat to achieve even finish. Complete up to the mark & site engineer's instruction. main wall | sq.ft
| Design plaster sofa back wall | Sqm | 0.7 | 7.82 |  | 3.73 | 20.418
| Above door opening to the lucknow street | Sqm | 0.7 | 1.38 |  | 0.88 | 0.85008
| Bar counter area | Sqm | 0.7 | 10.02 |  | 3.71 | 26.0219
| Glass fasade above area pop | Sqm | 0.7 | 18.7 |  | 0.85 | 11.1265
| Airport coridor side pop | Sqm | 0.7 | 17.5 |  | 0.9 | 11.025
100%
| Total Qty in Sqm | Sqm |  |  |  |  | 69.4415
| Total Qty in sft | Sft |  |  |  | 10.764 | 747.4687
| Previous Qty | Sft |  |  |  |  | 305.418
| This Bill Qty. | Sft |  |  |  |  | 442.0507
24 | P&A of texture metal paint on exposed duct, approved make & shade on decorative pop panel with sand papering & cleaning the surface, applying double boiled linseed acrylic/oil/cement primer, there after painting the surface in three finishing coats over base primer coat to achieve even finish. Complete up to the mark & site engineer's instruction. | sq.ft
| 850x300 mm duct | Sqm | 1 | 14.2 | 2.3 |  | 32.66
| 850x300 mm duct Glass screen side | Sqm | 1 | 13.6 | 2.3 |  | 31.28
| 550x200 mm duct | Sqm | 2 | 6 | 1.5 |  | 18
| 550x200 mm counter area | Sqm | 1 | 2.56 | 1.5 |  | 3.84
| Total Qty in Sqm | Sqm |  |  |  |  | 85.78
| Total Qty in sft | Sft |  |  |  | 10.764 | 923.3359
| Previous Qty | Sft
| This Bill Qty. | Sft |  |  |  |  | 923.3359
25 | P&A of Linseed oil/lacquer for exposed red brick wall including the number of quotes up to the mark as per site engineer's instructions. | sq.ft
| Design plaster sofa back wall | Sqm | 0.5 | 7.82 |  | 3.73 | 14.5843
| Above door opening to the lucknow street | Sqm | 0.5 | 1.38 |  | 0.88 | 0.6072
| Bar counter area wall | Sqm | 0.5 | 10.02 |  | 3.71 | 18.5871
| Design wall | Sqm | 2 | 2.54 |  | 2.4 | 12.192
| Planter -1 | Sqm | 1 | 20.08 |  | 0.43 | 8.6344
| Planter -2 | Sqm | 1 | 9.45 |  | 0.43 | 4.0635
| Glass fasade above area | Sqm | 0.5 | 18.7 |  | 0.85 | 7.9475
| Airport coridor side | Sqm | 0.5 | 17.5 |  | 0.9 | 7.875
| Column | Sqm | 2 | 2.77 |  | 0.43 | 2.3822
100%
| Total Qty in Sqm | Sqm |  |  |  |  | 76.8732
| Total Qty in sft | Sft |  |  |  | 10.764 | 827.4631
| Previous Qty | Sft |  |  |  |  | 378.9046
| This Bill Qty. | Sft |  |  |  |  | 448.5585
26 | Fire sprinkler paint_Providing & applying Three (03) coats of fire rated paint as per standard on exposed surface on metal including removing of old paint etc. complete with final coat no brush mark to be visible after painting colour shade as specified. | sq.ft
i) | 25 mm dia. (circumfrence of 25 mm =3.14x25=78.5 mm)
| Branch -1 above Bar counter | Sqm | 1 | 4 | 0.078 |  | 0.312
| Sprinklar branch bar area | Sqm | 2 | 0.895 | 0.078 |  | 0.13962
| Branch -2 above rafters | Sqm | 1 | 1.11 | 0.078 |  | 0.08658
| Sprinklar brances | Sqm | 1 | 2.685 | 0.078 |  | 0.20943
| Sprinklar brances | Sqm | 1 | 1.095 | 0.078 |  | 0.08541
|  | Sqm | 1 | 1.3 | 0.078 |  | 0.1014
|  | Sqm | 1 | 0.895 | 0.078 |  | 0.06981
| Above hut both side line | Sqm | 2 | 4.135 | 0.078 |  | 0.64506
| 3 rd branc above C- bench sofa | Sqm | 1 | 6 | 0.078 |  | 0.468
ii) | 40 mm dia. (circumfrence of 40 mm =3.14x25=125.6 mm)
| Branch -1 above Bar counter | Sqm | 1 | 2.02 | 0.126 |  | 0.25452
|  | Sqm | 1 | 0.79 | 0.126 |  | 0.09954
| Branch -2 above rafters | Sqm | 1 | 0.815 | 0.126 |  | 0.10269
| Above hut both side line | Sqm | 2 | 1.32 | 0.126 |  | 0.33264
|  | Sqm | 2 | 2.08 | 0.126 |  | 0.52416
| 3 rd branc above C- bench sofa | Sqm | 1 | 2.055 | 0.126 |  | 0.25893
iii) | 50 mm dia. (circumfrence of 40 mm =3.14x25=157 mm)
| Branch -2 above rafters | Sqm | 1 | 5.225 | 0.157 |  | 0.82032
| 3 rd branc above C- bench sofa | Sqm | 1 | 4.82 | 0.157 |  | 0.75674
iv) | 65 mm dia. (circumfrence of 40 mm =3.14x25=204 mm)
| Airport chilled line to main Header | Sqm | 1 | 5.5 | 0.204 |  | 1.122
| Down | Sqm | 1 | 0.6 | 0.204 |  | 0.1224
| Main Header run | Sqm | 1 | 5.25 | 0.204 |  | 1.071
| Total Qty in Sqm | Sqm |  |  |  |  | 7.5823
| Total Qty in Sqm | Sft |  |  |  | 10.764 | 81.6154
| Previous Qty | Sft |  |  |  |  | 81.6154
| This Bill Qty. | Sft |  |  |  |  | 0
27 | P&C of Service Station, with 19mm thick ashwood/ sheesham wood structure, unit having 4 nos. of drawers with necessary drawer compartment finished in felt, 1nos. of wooden shelves in side the unit, lower part having 3 nos. of open able shutters provision on one of the shutters (300mm L x 125mm H). unit finished with melanine polish. Rate inclusive of all necessary hardware fittings - like hinges, draw telescopic channels, cup board lock, decorative antique bolt handle, wire managers, locks etc. (approved & branded make) & necessary cut out for services requirements. Counter having 150mm ht. 18 mm thick flamed granite skirting on front side. Service desk back in paint finish as per refrence image with rough wood log borders in dark stain melamine polish as per reference image and the top front appron should have green paint with hand writtern text done by artist. Complete as per architectural detail drawing & site engineer's instruction. Size: 1000mm L x 600mm W x 1800mm H. | Nos
| Service station | Nos | 2 |  |  |  | 2 | 100%
| Total Qty | nos |  |  |  |  | 2
| Previous Qty | nos |  |  |  |  | 1.6
| This Bill Qty. | nos |  |  |  |  | 0.4
28 | P&C of Service Station, with 19mm thick ashwood/ sheesham wood structure, unit having 4 nos. of drawers with necessary drawer compartment finished in felt, 1nos. of wooden shelves in side the unit, lower part having 3 nos. of open able shutters provision on one of the shutters (300mm L x 125mm H). unit finished with melanine polish. Rate inclusive of all necessary hardware fittings - like hinges, draw telescopic channels, cup board lock, decorative antique bolt handle, wire managers, locks etc. (approved & branded make) & necessary cut out for services requirements. Counter having 150mm ht. 18 mm thick flamed granite skirting on front side. Service desk back in paint finish as per refrence image with rough wood log borders in dark stain melamine polish as per reference image and the top front appron should have green paint with hand writtern text done by artist. Complete as per architectural detail drawing & site engineer's instruction. Size: 1600mm L x 600mm W x 1800mm H. | Nos
| Service station | Nos | 1 |  |  |  | 1 | 100%
| Total Qty in Sqm | nos |  |  |  |  | 1
| Previous Qty | nos |  |  |  |  | 0.8
| This Bill Qty. | nos |  |  |  |  | 0.2
29 | P&F of 600mm wide Bar counter solid wooden top with 19mm thick double plywood (selected & approved make, bwr grade) backing, plywood to be fixed on the existing low height bar wall's top having pelmet provision as shown details. After fixing the plywood 12mm thick x 200 mm wide seasoned 1st quality btc wooden plank to be fixed on the top of the bar counter, having half round shape molding on both the edges, wooden top be finished with high gloss lamination polish ( stain free) as per approved sample up to the mark. Complete as per architectural detail drawing & site engineer's instruction. Size: 12000mm L x 600mm W x 50mm H
| Front side | Rmt | 1 | 4.3 |  |  | 4.3
| LHS | Rmt | 1 | 2.9 |  |  | 2.9
| RHS | Rmt | 1 | 2.51 |  |  | 2.51
| Total Qty in Sqm | Rmt |  |  |  |  | 9.71
| Total Qty in Sft | Rft |  |  |  | 3.284 | 31.8876
| Previous Qty | Rft |  |  |  |  | 31.8876
| This Bill Qty. | Rft |  |  |  |  | 0
30 | P&F of 18mm thk marien plywood paneling on bar counter front surface in levels with 30mm offset to give provision of led light, with 50mm x 25mm aluminium pipe framing out of vertical members at 400 mm c/c & with horizontal members at 550 mm c/c, fixing the framing on the existing plaster finished wall, after fixing farming 19mm thick marien plywood (selected & approved make, bwr grade plywood) to be installed on the framing. Complete as per architectural detail drawing & site engineer's instruction.
| Front side | Sqm | 1 | 3.83 |  | 1.15 | 4.4045
| LHS | Sqm | 1 | 3.16 |  | 1.15 | 3.634
| RHS | Sqm | 1 | 2.68 |  | 1.15 | 3.082
| Total Qty in Sqm | Sqm |  |  |  |  | 11.1205
| Total Qty in Sft | Sft |  |  |  | 10.764 | 119.7011
| Previous Qty | Sft |  |  |  |  | 119.7011
| This Bill Qty. | Sft |  |  |  |  | 0
31 | P&F of Rough outer sleeper wooden paneling at bar front wall with 15/18mm thick x 150mm wide rough outer sleeper wood to be fixed on the existing plywood paneling surface in different level with provision of indirect lighting, surface area to be finished with melamine polish. Rate including all necessary hardware fittings to install the rough wood, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive, etc.. Complete as per architectural detail drawing & site engineer's instruction.
32 | Providing & fixing brass Foot-rail made out of 38 mm.dia brass tube (14 gauge 304 grade hair line mat finished) framing, fixing the frame on floor with all necessary hardware fittings. Complete as per architectural detail drawing & site engineer' instruction.@ bar counter's front.
| Front side | Rmt | 1 | 3.83 |  |  | 3.83
| LHS | Rmt | 1 | 3.16 |  |  | 3.16
| RHS | Rmt | 1 | 2.68 |  |  | 2.68
| Total Qty in Sqm | Rmt |  |  |  |  | 9.67
| Total Qty in Sft | Rft |  |  |  | 3.284 | 31.7563
| Previous Qty | Rft
| This Bill Qty. | Sft |  |  |  |  | 31.7563
33 | P&F of island counter of 600mm wide granite top working back counter, with 19mm thick marien plywood structure & 12mm plywood back (selected & approved make, bwr plywood), counter having 4 nos. of open able shutters (in 19mm thick plywood) on front side of the unit. Counter top to be finished with 19mm thick black galaxy granite with 38mm dual nose finished, counter front part, & all the visible part to be finished with 1mm thick wooden laminate, counter's internal part to be finished with 1mm thick light walnut laminate (selected make, basic cost INR. 1200.00/ sheet). Rate inclusive of all necessary hardware fittings - like hinges, draw telescopic channels, cup board lock, decorative antique bolt handle, wire managers, etc. (approved & branded make) & necessary cut out for services requirements. Counter having 50mm ht. 18 mm thick flamed granite skirting on front side on existing 150mm ht. kobah. Complete as per architectural detail drawing & site engineer's instruction. Size: 1760mm L x 600mm W x 1000mm H x1 nos.
| Island counter | Rmt | 1 | 1.07 |  |  | 1.07
| Bar counter RHS | Rmt | 1 | 0.65 |  |  | 0.65
| Bar counter LHS | Rmt | 1 | 0.85 |  |  | 0.85
100%
| Total Qty in Sqm | Rmt |  |  |  |  | 2.57
| Total Qty in Sft | Rft |  |  |  | 3.284 | 8.4399
| Previous Qty | Rft |  |  |  |  | 3.1625
| This Bill Qty. | Rft |  |  |  |  | 5.2774
BAR BACK
34 | P&F of bar back structure with MS framework made out of 50 x 50mm box section vertical members at 400 mm c/c & with horizontal members at 550 mm c/c, fixing the framing in proper line & level on existing wall/ floor/ mother slab. the MS to be finished with zink oxide and black powder coating. Rate including all necessary hardware fittings, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive, etc.. as required on site. Complete as per architectural detail drawing & site engineer's instruction.
| Vertical member from ms true slab | Rmt | 4 | 2.85 |  |  | 11.4
| Vertical member from ms true slab | Rmt | 2 | 2.25 |  |  | 4.5
| LHS Horizontal membar | Rmt | 8 | 0.46 |  |  | 3.68
| RHS Horizontal membar | Rmt | 8 | 0.46 |  |  | 3.68
| Front and Back | Rmt | 8 | 0.45 |  |  | 3.6
| Top area support | Rmt | 3 | 0.45 |  |  | 1.35
100%
| Total Qty in Sqm | Rmt |  |  |  |  | 28.21
| Total Qty in Sft | Rft |  |  |  | 3.284 | 92.6416
| Previous Qty | Rft |  |  |  |  | 83.3775
| This Bill Qty. | Rft |  |  |  |  | 9.2642
35 | P&F of crate wooden box paneling @ bar back wall having 25mm thick x 350mm wide x 350-450mm high crate wood (pine wood / approved wood) boxes to be fixed on both the MS framework with desired pattern as shown on the detail drawing, wooden surface to be finished clear PU paint. Rate including all necessary hardware fittings to install the panel, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. Pine wood Boxes Size: 350mm L x 350mm W x 500mm H as shown on elevation.
| Crate box for ms frame bar area | nos | 22 |  |  |  | 22
100%
| Total Qty in Sqm | nos |  |  |  |  | 22
| Previous Qty | nos |  |  |  |  | 14
| This Bill Qty. | nos |  |  |  |  | 8
36 | P&F of 600mm wide 10MM THK toughned glass shelf with 10-15mm MS bidding all finished with black powder coating and shelf including provision for led lights. Rate including all necessary hardware fittings to install the partition, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction.
| bar hanger glass | Sqm | 4 | 1.45 | 0.3 |  | 1.74
| Total Qty in Sqm | Sqm |  |  |  |  | 1.74
| Total Qty in Sft | Sft |  |  |  | 10.764 | 18.7294
| Previous Qty | Sft
| This Bill Qty. | Sft |  |  |  |  | 18.7294
37 | P&F of 350mm wide Bar Bulkhead/ glass hanger having 25mm X 25MM brass metal in 2 layers having vertical and horizontal member @every 600mm c/c with 12mm thk toughthned glass shelf having provision for led profile light. brass metal to be brushed finish. the base including 8-10mm solid rods band in curve shape to hang the wine glass. Rate including all necessary hardware fittings to install the shelves, anchor fastner, ceiling support, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. Size: 2200mm L x 350mm W x 900mm H as shown on elevation.
| Counter Glass hangeer bulk head | Rmt | 1 | 3 |  |  | 3
100%
| Total Qty in Sqm | Rmt |  |  |  |  | 3
| Total Qty in Sft | Rft |  |  |  | 3.284 | 9.852
| Previous Qty | Rft |  |  |  |  | 7.389
| This Bill Qty. | Rft |  |  |  |  | 2.463
38 | P&F of Wooden rafter in hut shape with 19mm thick plywood boxing (selected & approved make, bwr grade plywood), boxing to be hanged from mother slab with necessary support from wall & slab to get hut shape as shown on detail drawing, after fixing the boxing in hut shape 15 /18 mm thick rough outer sleeper wood to be finished all three visible parts (except top side) the boxing (selected & approved sleeper wood), sleeper wood to be finished in linceed oil, including all necessary hardware fittings, required anchor fasteners to hang the rafter from the slab / wall, necessary scaffolding, etc. as required. Complete as per architectural detail drawing & site engineer's instruction. Size: 200mm H x 200mm D
| Outer section rafter | Rmt | 2 | 9.21 |  |  | 18.42
| Center section Rafter | Rmt | 2 | 8.87 |  |  | 17.74
| Horizontal rafter | Rmt | 5 | 2.79 |  |  | 13.95
| Horizontal rafter side 2 | Rmt | 5 | 2.71 |  |  | 13.55
| Tapper Horizontal Rafter | Rmt | 5 | 3.08 |  |  | 15.4
| Tapper Horizontal Rafter side 2 | Rmt | 5 | 2.99 |  |  | 14.95
| Inner small rafter | Rmt | 5 | 1.185 |  |  | 5.925
| Inner small rafter side 2 | Rmt | 5 | 1.16 |  |  | 5.8 | 100%
| Total Qty in Sqm | Rmt |  |  |  |  | 105.735
| Total Qty in Sft | Rft |  |  |  | 3.284 | 347.2337
| Previous Qty | Rft |  |  |  |  | 277.787
| This Bill Qty. | Rft |  |  |  |  | 69.4467
39 | P&F of "U" Shape Bench Seating, having 600mm width X 450MM seat height and 1200mm back ht. with 19mm thick plywood (selected & approved make, bwr grade) boxing for seating, boxing having storage provision, having 75mm to 175mm thk. slanted back partition of 1200mm ht with 19mm thick plywood framing & 12 mm thick plywood backing on the framing, openable seating with 50-75mm thick upholstery work (selected & approved density foam, father make) finished with selected & approved make fabrics (basic cost INR. 800 - 1000 /Mtr.), slanted back partition to be cusioned in chester feild pattern & all the visible parts of the bench seating to be finished with veneer having 150mm ht. 18 mm thick flamed granite skirting on front side. Rate including all necessary hardware fittings. Complete as per architectural detail drawing.
| U shape sofa | Nos | 2 |  |  |  | 2 | 100%
| Total Qty in nos | Nos |  |  |  |  | 2
| Previous Qty | nos |  |  |  |  | 1.6
| This Bill Qty. | nos |  |  |  |  | 0.4
40 | P&F of Rough sleeper wooden paneling on main facade for signage with 12mm thick marine plywood (selected & approved make, bwr grade) backing on existing pop punning finished walls, after fixing of the plywood 15/18mm thick x 100mm wide rough sleeper wood to be fixed on the said surface and 18mm thick x 50mm wide btc wooden patti to bed fixed on all edges of the paneling as shown detail, total surface area to be finished with melamine polish. Rate including all necessary hardware fittings to install the panel, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive, etc.. Complete as per architectural detail drawing & site engineer's instruction. Size: 3000mm x 450mm height no. in hut shape, as per facade details.
41 | P&F of Wicket door of size 750mm x 1200mm @ Bar - a flush door . The outer surface of the door is with 15/18mm thick x 150mm wide sleeperwood to be finished with linceed oil.the top to have 75mm wide BTC wooden edge with round edging. The inner side of the door to be finished with 1mm thick laminate. Rate inclusive of all hardware fittings like- hinges, sliding channel, conceal door closer (Ozone make, 400mm ht. S.S. handle , door stopper, dead lock, tower bolt, all necessary hardware fittings, etc. (all the fittings should be branded / Ozone make and to be approved by architect / site engineer), both the sides having 150mm ht 14 gauge 304 grade SS (hairline matt finish) kick plate on bottom side of the door, etc. Complete as per architectural detail drawing & site engineer's instruction. Size: 750mm L x 1200mm H x 1 no.
| Wicket Door | Nos | 1 |  |  |  | 1 | 100%
| Total Qty in nos | Nos |  |  |  |  | 1
| Previous Qty | nos |  |  |  |  | 0
| This Bill Qty. | nos |  |  |  |  | 1
42 | P&L of 6mm thick mdf sheet with transparent plastic paper to protect the flooring, after competition of all interior works the same to be removed from the floor with proper cleaning of the flooring & debris' to be removed from the compound.
| Bar counter area kota stone | Sqm | 1 | 3.05 | 3.59 |  | 10.9495
| area | Sqm | 1 | 7.73 | 13.59 |  | 105.0507
|  | Sqm | 1 | 4.26 | 2.91 |  | 12.3966
| wooden tiles arount bar counter | Sqm | 1 | 12.51 | 1.175 |  | 14.6993
|  |  |  | 18.165 | 1.6 |  | 29.064
| Total Qty in Sqm | Sqm |  |  |  |  | 172.1601
| Total Qty in Sft | Sft |  |  |  | 10.764 | 1853.1308
| Previous Qty | Sft |  |  |  |  | 1664.2516
| This Bill Qty. | Sft |  |  |  |  | 188.8791
43 | P&F of 450mm dia half cut wooden barrel finished with artistic paint & lacquer finish fixed on existing ms framework. Rate including all necessary hardware fittings to install the barrel, scaffolding, etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction.
| MS display wall planter box | nos | 12
| Total Qty in Sqm | nos |  |  |  |  | 0
| Previous Qty | Sft |  |  |  |  | 0
| This Bill Qty. | Sft |  |  |  |  | 0
44 | P&F of crate wooden box having 25mm thick x 600mm wide x 250 mm high crate wood (pine wood / approved wood) boxes to be fixed on both the MS framework with desired pattern as shown on the detail drawing, wooden surface to be finished clear PU paint. Rate including all necessary hardware fittings to install the panel, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive etc. as required on site. Complete as per architectural detail drawing & site engineer's instruction. Pine wood Boxes Size: 350mm L x 350mm W x 500mm H as shown on elevation.
| MS display wall planter box | nos | 6 |  |  |  | 6
| Ms railing planter box | nos | 11 |  |  |  | 11
| Total Qty in Sqm | nos |  |  |  |  | 17
| Previous Qty | nos |  |  |  |  | 6
| This Bill Qty. | nos |  |  |  |  | 11
45 | P & f of 900mm high MS decorative railing, with 50 mm x 50mm 14 swg gauge ms box post to be finished with 12mm thk plywood and veneer, top rail of 50mm X 50mm square pipe framing 14 swg gauge pipe having solid square rod 15mm X 15mm decorative design as shown on details drawing, with base plate fixing with necessary fastener. Complete railing in black powder coat finish.
| Ms railing | Rmt | 1 | 14.8 |  |  | 14.8
| Ms railing due to design change by akshay sir | Rmt | 1 | 1.31 |  |  | 1.31 | 100%
| Total Qty in Rmt | Rmt |  |  |  |  | 16.11
| Total Qty in Rft | Rft |  |  |  | 3.284 | 52.9052
| Previous Qty | Rft |  |  |  |  | 48.6032
| This Bill Qty. | Rft |  |  |  |  | 4.302
46 | P & f of MS framing for planters, with 25mm X 50mm box section framing (14 swg gauge) with 3 nos of horizontal and 12 nos of vertical frames as shown on details drawing, with base plate fixing with necessary fastener and to be finished in approve black powder coating. height upto 4000mm.
| Planter-1 | Rmt | 1 | 20.08 |  |  | 20.08
| Planter-2 | Rmt | 1 | 9.45 |  |  | 9.45
| Frame-1 Bar counter side Horizontal section | Rmt | 3 | 4.895 |  |  | 14.685
| Vertical member | Rmt | 6 | 2.73 |  |  | 16.38
| Frame-2 Horizontal section | Rmt | 3 | 4.525 |  |  | 13.575
| Vertical member | Rmt | 5 | 2.73 |  |  | 13.65
| Frame-3 Horizontal section | Rmt | 3 | 1.78 |  |  | 5.34
| Vertical member | Rmt | 3 | 2.73 |  |  | 8.19
| Frame-4 Horizontal section | Rmt | 3 | 4.075 |  |  | 12.225
| Vertical member | Rmt | 5 | 2.73 |  |  | 13.65 | 76.18%
| Total Qty in Sqm | Rmt |  |  |  |  | 96.9162
| Total Qty in Sft | Rft |  |  |  | 3.284 | 318.2728
| Previous Qty | Rft |  |  |  |  | 96.9765
| This Bill Qty. | Rft |  |  |  |  | 221.2962
47 | P & f of 1600mm high- 600mm height pine wood picket fance railing having 25mm thk pine wood plants size of 100mm wide finished in clear PU polish with color pegment. internal 25mm x 25mm MS framework to support the structure in curve shape. the metal to be finished with powder coating. the cost include all hardware fixture, required base plate, cutting rounding finishing in all respect as per drawing and instruction.
| Planter-1 | sqm | 1 | 20.08 |  | 1 | 20.08
| Planter-2 | sqm | 1 | 9.45 |  | 1 | 9.45
| Total Qty in Sqm | sqm |  |  |  |  | 29.53
| Total Qty in Sqm | sft |  |  |  | 10.764 | 317.8609
| Previous Qty | sft |  |  |  |  | 317.8609
| This Bill Qty. | sft |  |  |  |  | 0
48 | P & f of pinewood board size of 600 x 900mm having 12mm thk pine wood plants size of 100mm wide finished in clear PU polish with color pegment. internal 25mm x 25mm MS framework to support the structure in curve shape. the metal to be finished with powder coating. the cost include all hardware fixture, required base plate, cutting rounding finishing in all respect as per drawing and instruction.
49 | Providing & fixing brass Foot-rail near planter box made out of 38 mm.dia brass tube (14 gauge 304 grade hair line mat finished) framing, fixing the frame on floor with all necessary hardware fittings. Complete as per architectural detail drawing & site engineer' instruction.@ bar counter's front.
| Planter-1 | sqm | 1 | 21 |  | 1 | 21
| Planter-2 | sqm | 1 | 10 |  | 1 | 10 | 80%
| Total Qty in Sqm | sqm |  |  |  |  | 24.8
| Total Qty in Sqm | sft |  |  |  | 3.284 | 81.4432
| Previous Qty | sft
| This Bill Qty. | sft |  |  |  |  | 81.4432
50 | P&F of 25mm thk BTC wood signage with ingrave letters finished with melamine polish. Size - 2200 x 300mm high
51 | P&F of wooden paneling on column, with 50mm x 25mm aluminium pipe framing out of vertical members at 400 mm c/c & with horizontal members at 550 mm c/c, fixing the framing on the existing plaster finished column, after fixing farming 12mm thick plywood (selected & approved make, bwr grade plywood) to be installed on the framing and finished with apporved veneer and bamboo rope as per design. Complete as per architectural detail drawing & site engineer's instruction.
| near sofa ms column center | sqm | 2 | 0.2 |  | 2.45 | 0.98
|  | sqm | 2 | 0.23 |  | 2.45 | 1.127
| bar area side ms column center | sqm | 2 | 0.2 |  | 2.45 | 0.98
|  | sqm | 2 | 0.23 |  | 2.45 | 1.127
| Coridor side column near sofa front | sqm | 1 | 0.225 |  | 3.5 | 0.7875
| Sides | sqm | 2 | 0.27 |  | 3.5 | 1.89
| Coridor side column near bar front | sqm | 1 | 0.225 |  | 3.5 | 0.7875
| sides | sqm | 2 | 0.24 |  | 3.5 | 1.68 | 100%
| Total Qty in Sqm | sqm |  |  |  |  | 9.359
| Total Qty in Sft | sft |  |  |  | 10.764 | 100.7403
| Previous Qty | sft |  |  |  |  | 100.7403
| This Bill Qty. | sft |  |  |  |  | 0
52 | Real scale jeep (vehicle) artwork installtion
| jeep installation | nos | 1 |  |  |  | 1 | 80%
| Total Qty in Sqm | nos |  |  |  |  | 0.8
| Previous Qty | Sft |  |  |  |  | 0
| This Bill Qty. | Sft |  |  |  |  | 0.8
53 | Old wooden barrel size of 600mm dia meter with proper polish
| Old Barrel above sofa ms frame | nos | 6 |  |  |  | 6 | 80%
| Total Qty in Sqm | nos |  |  |  |  | 4.8
| Previous Qty | Sft |  |  |  |  | 0
| This Bill Qty. | Sft |  |  |  |  | 4.8
54 | Artist work on wall_ slogans/ write up on walls. (Lumpsum amount 25000/- )
55 | Artifact from antique store as per selection. (Lumpsum amount 2,00,000/- )
| Artifact | job | 1 |  |  |  | 1 | 80%
| Total Qty in Sqm | job |  |  |  |  | 0.8
| Previous Qty | job |  |  |  |  | 0
| This Bill Qty. | job |  |  |  |  | 0.8
56 | Canvas Photoframes and random size mirror as per brandstandard sizes in random frame design (Lumpsum amount 1,50,000/- )
57 | P&F of Hostess desk barrel size of 1200mm height and 750-900mm dia finished with melamine polish.
| Hostess desk barrel | nos | 1 |  |  |  | 1 | 80%
| Total Qty in Sqm | nos |  |  |  |  | 0.8
| Previous Qty | nos |  |  |  |  | 0
| This Bill Qty. | nos |  |  |  |  | 0.8
58 | P&F of hanging barrel structure with MS framework made out of 50 x 50mm box section vertical members at 400 mm c/c & with horizontal members at 550 mm c/c, fixing the framing in proper line & level on existing wall mother slab. the MS to be finished with zink oxide and black powder coating. Rate including all necessary hardware fittings, cut out for services requirements, required scaffolding, etc. as required on site, necessary adhesive, etc.. as required on site. Complete as per architectural detail drawing & site engineer's instruction.
| Horizontal bottam and top membar | Rmt | 4 | 5.02 |  |  | 20.08
| Horizontal under box section front | Rmt | 9 | 0.78 |  |  | 7.02
| Horizontal under box section Back | Rmt | 9 | 0.78 |  |  | 7.02
| Vertical membar front | Rmt | 5 | 1.12 |  |  | 5.6
| Vertical membar front | Rmt | 5 | 1.12 |  |  | 5.6
| Outer vertical | Rmt | 4 | 1.5 |  |  | 6
| vertical member above sofa | Rmt | 4 | 1 |  |  | 4 | 95%
| Total Qty in Rmt | Rmt |  |  |  |  | 52.554
| Total Qty in Rft | Rft |  |  |  | 3.284 | 172.5873
| Previous Qty | Rft |  |  |  |  | 168.5349
| This Bill Qty. | rft |  |  |  |  | 4.0525
59 | Providing fixing double leaf toughened glass door with 600mm fix glass on top fixed on existing faacde with patch fitting. Rate to include cost of heavy duty floor spring (Everite / Hemco / Haldin / Hyper or equivalent of capacity 120 kg), wooden/ sleeperwood decorative handle of size 900mm, mortise concealed lock, all required hardware patch fitting complete as directed. (Toughned Glass Door : Size - 1800mm X 2400mm)
60 | P&F of Dual leaf service trap door, with wooden framework out of vertical members at 400 mm c/c & with horizontal members at 550 mm c/c with both side 12mm thick bwr plywood (selected & approved make) backing both side of the framing,. Rate inclusive of all necessary supporting from existing slab, necessary scaffolding & hardware fittings, etc. Complete as per architectural detail drawing. Size: 1200mm X 2400mm.
| Trap door | nos | 2 |  |  |  | 2
| Total Qty in Sqm | nos |  |  |  |  | 2
| Previous Qty | nos |  |  |  |  | 0
| This Bill Qty. | nos |  |  |  |  | 2
61 | P&F of slate black board, with 1st grade BTC framing finished with melamine polish etc. Complete as per architectural detail drawing & site engineer's instruction. Size - 900 X 1200 mm
62 | P&F of Main DB/ electrical panel unit of 600mm depth made out of 19mm thick plywood structure & with 12mm thick plywood (selected & approved make, bwr grade plywood) back, having 4 nos of semi wooden louvers open able shutter HT. 2200mm in wood, wooden surface to be finished with exterior grade melamine polish. Rate including all necessary hardware fittings to install the panel, and in rest of the side finished with 1mm thick light walnut laminate (selected make, basic cost INR. 800.00/ sheet), having provision of 75mm height cove light pelmet, all edges should be btc wooden patta with polish finished, including all necessary hardware fittings (approved & branded make) - like hinges, tower bolt, cup board lock, extended bottom part of the shutter to be used as a handle, etc. (approved & branded make) & necessary cut out for services requirements, etc. Complete as per architectural detail drawing & site engineer's instruction. Size: 3000mm L x 3000mm H x 1 no.
| Outer vertical | Nos | 1 |  |  |  | 1 | 100%
| Total Qty in nos | Nos |  |  |  |  | 1
| Previous Qty. | Nos |  |  |  |  | 1
| This Bill Qty. | Nos |  |  |  |  | 0
Extra item
1 | Providing & fixing paneling made of 50x50mm MS framework @ 600mm c/c bothways fixed to the floor and soffit of slab/beam with MS cleats bolted as required, followed with 12mm thk. Bison board as base to receive tile cladding and different finishes over it as per design & details given in drawing/Architect instruction. Rate is inclusive of all necessary hardware & fixtures.
| Irish House | Sqm | 1 | 18.7 |  | 0.96 | 17.952
| Vertical column | Sqm | 2 | 0.43 |  | 2.77 | 2.3822
| Total Qty in Sqm | Sqm |  |  |  |  | 20.3342
| Total Qty in Sft | Sft |  |  |  | 10.764 | 218.8773
| Previous Qty | Sft |  |  |  |  | 218.8773
| This Bill Qty. | Sft |  |  |  |  | 0