## PI
VART
Infracon Pvt Ltd
229, Neha Ind. Est., Off Duttapada Road,
Opp. Oberoi Sky, Borivali (E), Mumbai - 400066
Contact No :- 022-40233596 / 28700110 Email : info@vartinfra.com
Proforma Invoice
To, | Simolina Kitchen Pvt. Ltd. |  |  | 2024-03-23
Ext-02 Ra-2nd
Kindly Attn.:- Mr. Irfaan ji
Sr. No. | Description | Unit | Previous | Up To Date | This Bill
1 | The Irish House Interior and finishing work RA-5th | Job | 343912.5991 | 904836.4086 | 560923.8095
| Basic Total |  | 343912.5991 | 904836.4086 | 560923.8095
| Add GST @ 18% |  | 61904.2678 | 162870.5536 | 100966.2857
| Grand Total |  | 405816.8669 | 1067706.9622 | 661890.0952
| This Bill Amount |  |  |  | 661890.0952
Work Completion Time Period
Material Delivery 1o days from the Date of PO with advance
Payment terms :
100% Advance with Work order
No Retention
For VART Infracon Pvt. Ltd.
Authorised Signatory

## Abstract
PRICE COMPARATIVE RA-2nd
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3 | [5 empty] | Qty. |  |  | Amount (RS) |  |  | Varation | Remarks
SR. NO. | ITEM DESCRIPTION | UOM | PO QTY. | UNIT RATE | PO Amount | Previous bill | This bill | Up To Date | Previous bill | This bill | Up To Date
EXTRA ITEM - Part-2
1 | Providing & fixing paneling made of 50x50mm MS framework @ 450mm c/c bothways fixed to the above ceiling and soffit of slab/beam with MS cleats bolted as required, followed with 2mm thk. MS Sheet as base to receive RO & Gysrer for resting and services purpose or as per engineer in-charge Rate is inclusive of all necessary hardware & fixtures. | Sft. | 23.2502 | 587 | 13647.8909 | 23.2502 | 0 | 23.2502 | 13647.8909 | 0 | 13647.8909 | 0
2 | Providing and fixing Kent Elite 50 LPH Ro system with 100 ltr or as project in-charge | nos | 1 | 44850 | 44850 |  | 1 | 1 |  | 44850 | 44850 | 0
3 | Providing and fixing 40 ltr. Water pressure tank for Ro system or as project in-charge | nos | 1 | 7500 | 7500 |  | 1 | 1 |  | 7500 | 7500 | 0
4 | Providing and applying 12x12mm cement base grout on brick tiles in wall with masking tape above height 3m rate include s.folding and cleaning or as approved make and speacetion make- Laticrete and roff | Sft. | 420 | 45 | 18900 | 372 | 0 | 372 | 16740 | 0 | 16740 | 2160
5 | Providing fixing double leaf toughened glass door with 600mm fix glass on top fixed on existing faacde with patch fitting. Rate to include cost of heavy duty floor spring (Everite / Hemco / Haldin / Hyper or equivalent of capacity 120 kg), Removing the existing old glass and Replacing the same with cut-outs with patch fitting and as per dicussion at site | nos | 1 | 116000 | 116000 | 1 | 0 | 1 | 116000 | 0 | 116000 | 0
6 | P&F of Plywood Boxing with 12mm thick plywood boxing (selected & approved make, bwr grade plywood), boxing to be Fixied from mother slab and Existing ms frame with necessary fittings shape as shown on detail drawing, after fixing the boxing 4 mm thick Decorative veneer finish, Veneer to be finished in Melamine polish or Complete as per architectural detail drawing & site engineer's instruction. Size: 250mm H x 75mm W | Rft. | 55 | 1400 | 77000 | 55 | 0 | 55 | 77000 | 0 | 77000 | 0
7 | Providing and making 25x25m ms tube Ledge table fixing with fastner and black duco paint complete as per drawing or project in-charge. | nos | 1 | 80000 | 80000 | 1 | 0 | 1 | 80000 | 0 | 80000 | 0
8 | Providing and fixing exesting wooden Hut upper side match with exesting sleeper wood panelling and same as finish process ect inclusive of all rewqorks required to complete the item . Or as per project in charge. | Rft | 406.6085 | 1150 | 467599.729 |  | 347 | 347 |  | 399050 | 399050 | 68549.729
9 | Providing and fixing pine wood planks fixeing on column size 100x25mm height upto level 3700 mm rate include melamine polish and all nessery fixing aarangement and s.folding etc or as per project- in- charge. | Rft | 52 | 779.3213 | 40524.7082 | 52 | 0 | 52 | 40524.7082 | 0 | 40524.7082 | 0
10 | Providing antique jeep as per drawing and architict detail. | nos | 1 | 109523.8095 | 109523.8095 |  | 1 | 1 |  | 109523.8095 | 109523.8095 | 0
| TOTAL |  |  |  | 975546.1376 |  |  |  | 343912.5991 | 560923.8095 | 904836.4086 | 70709.729
| GST 18% |  |  |  | 175598.3048 |  |  |  | 61904.2678 | 100966.2857 | 162870.5536 | 12727.7512
| Grand Total |  |  |  | 1151144.4424 |  |  |  | 405816.8669 | 661890.0952 | 1067706.9622 | 83437.4802

## MB Sheet
MB Sheet Extra Item -02
PROJECT: IRISH HOUSE, LUCKNOW AIRPORT - TERMINAL-T3 RA-2nd Correction Copy
SR. NO. | ITEM DESCRIPTION | Unit | No. | Length | Width | Height | Total | Remarks
EXTRA ITEM - Part-2
1 | Providing & fixing paneling made of 50x50mm MS framework @ 450mm c/c bothways fixed to the above ceiling and soffit of slab/beam with MS cleats bolted as required, followed with 2mm thk. MS Sheet as base to receive RO & Gysrer for resting and services purpose or as per engineer in-charge Rate is inclusive of all necessary hardware & fixtures. | Sft.
| Ro and Gyser base | Sqm | 1 | 1.2 | 1.8 |  | 2.16
| Total Qty in Sqm | Sqm |  |  |  |  | 2.16
| Total Qty in Sft | Sft |  |  |  | 10.764 | 23.2502
| Previous Qty | sft |  |  |  |  | 23.2502
| This Bill Qty | Sft |  |  |  |  | 0
2 | Providing and fixing Kent Elite 50 LPH Ro system with 100 ltr or as project in-charge | nos
| kent Elite Ro | nos | 1 |  |  |  | 1
| Total Qty in nos | Nos |  |  |  |  | 1
| Previous Qty | Nos
| This Bill Qty | Nos |  |  |  |  | 1
3 | Providing and fixing 40 ltr. Water pressure tank for Ro system or as project in-charge | nos
| kent Elite Ro | nos | 1 |  |  |  | 1
| Total Qty in nos | Nos |  |  |  |  | 1
| Previous Qty | Nos
| This Bill Qty | Nos |  |  |  |  | 1
4 | Providing and applying 12x12mm cement base grout on brick tiles in wall with masking tape above height 3m rate include s.folding and cleaning or as approved make and speacetion make- Laticrete and roff | Sft.
| Glass fasade above area | Sqm | 1 | 18.7 |  | 0.85 | 15.895
| Column Panelling | Sqm | 2 | 2.77 |  | 0.43 | 2.3822
| Airport coridor side panelling | Sqm | 1 | 17.5 |  | 0.9 | 15.75
| Glass side Boxing | Sqm | 1 | 0.2 |  | 2.9 | 0.58
| Total Qty in Sqm | Sqm |  |  |  |  | 34.6072
| Total Qty in Sft | Sft |  |  |  | 10.76 | 372
| Previous Qty | Sft |  |  |  |  | 372
| This Bill qty | Sft |  |  |  |  | 0
5 | Providing fixing double leaf toughened glass door with 600mm fix glass on top fixed on existing faacde with patch fitting. Rate to include cost of heavy duty floor spring (Everite / Hemco / Haldin / Hyper or equivalent of capacity 120 kg), Removing the existing old glass and Replacing the same with cut-outs with patch fitting and as per dicussion at site | nos
| Glass Door | Nos | 1 | 1 |  |  | 1
| Total Qty in Nos | Nos |  |  |  |  | 1
| Previous in nos | nos |  |  |  |  | 1
| This Bill qty | Nos |  |  |  |  | 0
6 | P&F of Plywood Boxing with 12mm thick plywood boxing (selected & approved make, bwr grade plywood), boxing to be Fixied from mother slab and Existing ms frame with necessary fittings shape as shown on detail drawing, after fixing the boxing 4 mm thick Decorative veneer finish, Veneer to be finished in Melamine polish or Complete as per architectural detail drawing & site engineer's instruction. Size: 250mm H x 75mm W | Rft.
| Wooden Box Align MS Framing Floor | Rmt | 1 | 16.66 |  |  | 16.66
| Total Qty in Sqm | Rmt |  |  |  |  | 16.66
| Total Qty in Sft | Rft |  |  |  | 3.28 | 55
| Previous Qty | Rft |  |  |  |  | 55
| This Bill qty | Rft |  |  |  |  | 0
7 | Providing and making 25x25m ms tube Ledge table fixing with fastner and black duco paint complete as per drawing or project in-charge. | nos
| Ledge Table | Nos | 1 | 1 |  |  | 1
| Total Qty in Nos | Nos |  |  |  |  | 1
| Previous in nos | nos |  |  |  |  | 1
| This Bill qty | Nos |  |  |  |  | 0
8 | Providing and fixing exesting wooden Hut upper side match with exesting sleeper wood panelling and same as finish process ect inclusive of all rewqorks required to complete the item . Or as per project in charge. | Rft
| Outer section rafter top | Rmt | 2 | 9.21 |  |  | 18.42
| Center section Rafter top | Rmt | 2 | 8.87 |  |  | 17.74
| Horizontal rafter top | Rmt | 5 | 2.79 |  |  | 13.95
| Horizontal rafter side 2 top | Rmt | 5 | 2.71 |  |  | 13.55
| Tapper Horizontal Rafter top | Rmt | 5 | 3.08 |  |  | 15.4
| Tapper Horizontal Rafter side 2 top | Rmt | 5 | 2.99 |  |  | 14.95
| Inner small rafter top | Rmt | 5 | 1.185 |  |  | 5.925
| Inner small rafter side 2 top | Rmt | 5 | 1.16 |  |  | 5.8
| Total Qty in Rmt | Rmt |  |  |  |  | 105.735
| Total Qty in Rft | Rft |  |  |  | 3.28 | 347
| Previous Qty | Rft
| This Bill qty | Rft |  |  |  |  | 347
9 | Providing and fixing pine wood planks fixeing on column size 100x25mm height upto level 3700 mm rate include melamine polish and all nessery fixing aarangement and s.folding etc or as per project- in- charge. | Rft
| Wooden planks | Rmt | 52 | 1 |  |  | 52
| Total Qty in Sqm | Rmt |  |  |  |  | 52
| Total Qty in Sft | Rft |  |  |  | 3.28 | 171
| Restricted Qty. | Rft |  |  |  |  | 52
| Previous Qty | Rft |  |  |  |  | 52
| This Bill qty | Rft |  |  |  |  | 0
10 | Providing antique jeep as per drawing and architict detail. | nos
| old jeep | nos | 1 |  |  |  | 1
| Total Qty in nos | Rmt |  |  |  |  | 1
| Previous Qty | Rft
| This Bill qty | Rft |  |  |  |  | 1