## PI
VART
Infracon Pvt Ltd
229, Neha Ind. Est., Off Duttapada Road,
Opp. Oberoi Sky, Borivali (E), Mumbai - 400066
Contact No :- 022-40233596 / 28700110 Email : info@vartinfra.com
Proforma Invoice
To, | Simolina Kitchen Pvt. Ltd. |  |  | 2024-05-30
Extra item Ra-1st
Kindly Attn.:- Mr. Irfaan ji
Sr. No. | Description | Unit | Previous | Up To Date | This Bill
1 | The Lucknow Seating Extra item -01 , RA-1st | Job |  | 167904.2022 | 167904.2022
| Basic Total |  | 0 | 167904.2022 | 167904.2022
| Add GST @ 18% |  | 0 | 30222.7564 | 30222.7564
| Grand Total |  | 0 | 198126.9586 | 198126.9586
| This Bill Amount |  |  |  | 198126.9586
Work Completion Time Period
Material Delivery 1o days from the Date of PO with advance
Payment terms :
100% Advance with Work order
No Retention
For VART Infracon Pvt. Ltd.
Authorised Signatory

## Abstract
PRICE COMPARATIVE RA-1st
PROJECT: THE LUCKNOW SEATING, LUCKNOW AIRPORT - TERMINAL-T3 | [5 empty] | Qty. |  |  | Amount (RS) |  |  | Qty varation | Remarks
SR. NO. | ITEM DESCRIPTION | UOM | QTY. | UNIT RATE | Amount | Previous bill | This bill | Up To Date | Previous bill | This bill | Up To Date
EXTRA ITEM-01
1 | Providing fixing testing and commissioning of braided UL Rated SS Flexible pipe With all necessery Fitting 1 Mtr. Length | Nos | 8 | 2150 | 17200 |  | 8 | 8 |  | 17200 | 17200 | 0
2 | Providing and Applying kerakoll chemical Super Flex OR LATICRETE S adhesive (as per manufacturer’s specification )or equivalent, inclusive of cleaning of site , and as per engineer in charge . | Sft. | 405 | 280 | 113400 |  | 359.4748 | 359.4748 |  | 100652.9477 | 100652.9477 | -45.5252
3 | Providing and fixing of hollow metal fire rated doors SIZE 2000 X 2400 as per IS 3614 part-1 part-2 for stability and integrity. Pressed Galvanized steel confirming to IS 277 with the following specification. Recommended fire door shall have doors tested at CBRI or ARAI for maximum rating of 2hrs. Test certificates should be available for vision lites panels as part of the fire door assembly. Door frame shall be double rebate profile of size 143 x 57 mm made out of 1.60mm (16 gauge) minimum thick galvanized steel sheet. Frames shall be Mitered and field assembled with self tabs. All provision should be mortised, drilled and tapped for receiving appropriate hardware. Rubber door silencers should be provided on the striking jamb. Frames should be provided with back plate bracket and anchor fasteners for installation on a finished plastered masonry wall opening. Once frame installed should be grouted with cement sand slurry necessary for fire doors on the clear masonry opening. Door leaf shall be 46mm thick fully flush double skin door with or without vision lite. Door leaf shall be manufactured from 1.2mm (18guage) minimum thick galvanised steel sheet. The internal construction of the door should be rigid reinforcement pads for receiving appropriate hardware. The infill material shall be resin bonded honeycomb core. All doors shall be factory prepped for receiving appropriate hardware and provided with necessary reinforcement for hinges, locks, and door closers. The edges should be interlocked with a bending radius of 1.4mm. For pair of doors astragals has to be provided on the meeting stile for both active and inactive leaf. Vision lite wherever applicable should be provided as per manufacturers recommendation with a beeding and screws from inside. All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. With Iron Pull Handle and Double lock. | Sft. | 1 | 75000 | 75000 |  | 0 | 0 |  | 0 | 0 | -1
4 | Providing fixing paneling made of 50x50mm MS framework @ 600mm c c bothways fixed to the floor and soffit of slab beam with MS cleats bolted as required, as base to receive tile cladding and different finishes over it as per design details given in drawing Architect instruction. Rate is inclusive of all necessary hardware fixtures. | Sft. | 200.24 | 250 | 50060 |  | 200.205 | 200.205 |  | 50051.2545 | 50051.2545 | -0.034982
| TOTAL |  |  |  | 255660 |  |  |  | 0 | 167904.2022 | 167904.2022
| GST 18% |  |  |  | 46018.8 |  |  |  |  | 30222.7564 | 30222.7564
| G.Total |  |  |  | 301678.8 |  |  |  | 0 | 198126.9586 | 198126.9586

## MB Sheet
MB SHEET Extra item -01, RA-01
Project -The Lucknow Seating D-21 Airport (Lucknow)
Sr No | Item Name | UOM | Boq Qty. | No. | Length | Width | Height | Total | Remarks
BOQ for Civil & Interior Work for LKN Dom Seating space D-21a
1 | Providing fixing testing and commissioning of braided UL Rated SS Flexible pipe With all necessery Fitting 1 Mtr. Length |  | 8
| Flexible pipe for sprinkler | nos |  | 8 |  |  |  | 8
| Total Qty in Nos | [6 empty] | 8
| Previous bill Qty | [6 empty] | 0
| This Bill Qty | [6 empty] | 8
2 | Providing and Applying kerakoll chemical Super Flex OR LATICRETE S adhesive (as per manufacturer’s specification )or equivalent, inclusive of cleaning of site , and as per engineer in charge . | Sqft | 405
| 75mm Ledge wall | Sqm |  | 1 | 7.99 |  | 1.2 | 9.588
| Seating Sides | Sqm |  | 2 | 0.6 |  | 0.45 | 0.54
| Fixed seating 2 facia | Sqm |  | 1 | 2.25 |  | 0.37 | 0.8325
| Fixed seating 2 sides | Sqm |  | 2 | 0.7 |  | 0.37 | 0.518
| Seating back | Sqm |  | 1 | 2.52 | 2.95 |  | 7.434
| Less seating facia | Sqm |  | -1 | 2.25 | 0.37 |  | -0.8325
| 75mm Ledge wall | Sqm |  | 1 | 7.98 |  | 1.18 | 9.4164
| Less trashbin | Sqm |  | -1 | 0.88 |  | 1.2 | -1.056
| Ledge Top Stone | Sqm |  | 1 | 8.065 | 0.125 |  | 1.0081
| Trasbin Top | Sqm |  | 1 | 0.91 | 0.45 |  | 0.4095
| High Table top | Sqm |  | 1 | 2.15 | 0.45 |  | 0.9675
| High Table RHS Mirror Wall | Sqm |  | 1 | 3.53 | 0.45 |  | 1.5885
| High Table top | Sqm |  | 1 | 2.15 | 0.45 |  | 0.9675
| Latak | Sqm |  | 1 | 2.15 | 0.075 |  | 0.16125
| High Table RHS Mirror Wall | Sqm |  | 1 | 3.53 | 0.45 |  | 1.5885
| Latak | Sqm |  | 1 | 3.53 | 0.075 |  | 0.26475
| Total Qty in Sqm | [6 empty] | 33.396
| Total Qty in Sqft | [5 empty] | 10.764 | 359.4748
Previous bill Qty
| This Bill Qty | [6 empty] | 359.4748
3 | Providing and fixing of hollow metal fire rated doors SIZE 2000 X 2400 as per IS 3614 part-1 part-2 for stability and integrity. Pressed Galvanized steel confirming to IS 277 with the following specification. Recommended fire door shall have doors tested at CBRI or ARAI for maximum rating of 2hrs. Test certificates should be available for vision lites panels as part of the fire door assembly. Door frame shall be double rebate profile of size 143 x 57 mm made out of 1.60mm (16 gauge) minimum thick galvanized steel sheet. Frames shall be Mitered and field assembled with self tabs. All provision should be mortised, drilled and tapped for receiving appropriate hardware. Rubber door silencers should be provided on the striking jamb. Frames should be provided with back plate bracket and anchor fasteners for installation on a finished plastered masonry wall opening. Once frame installed should be grouted with cement sand slurry necessary for fire doors on the clear masonry opening. Door leaf shall be 46mm thick fully flush double skin door with or without vision lite. Door leaf shall be manufactured from 1.2mm (18guage) minimum thick galvanised steel sheet. The internal construction of the door should be rigid reinforcement pads for receiving appropriate hardware. The infill material shall be resin bonded honeycomb core. All doors shall be factory prepped for receiving appropriate hardware and provided with necessary reinforcement for hinges, locks, and door closers. The edges should be interlocked with a bending radius of 1.4mm. For pair of doors astragals has to be provided on the meeting stile for both active and inactive leaf. Vision lite wherever applicable should be provided as per manufacturers recommendation with a beeding and screws from inside. All doors and frames shall be finished with polyurethane aliphatic grade paint of approved colour. With Iron Pull Handle and Double lock. | Nos | 1
| Fire Door | Nos |  | 1 |  |  |  | 0
| Total Qty | [6 empty] | 0
Previous bill Qty
| This Bill Qty | [6 empty] | 0
4 | BWP plyboard panelling Providing and fixing of BWP plyboard paneling with necessary wooden battens with complete hardware and fixing from wall and floor | Sqft | 200.24
| Mirror Wall | Sqm |  | 1 | 3.05 | 2.99 |  | 9.1195
| DB wall | Sqm |  | 1 | 1.6 | 2.9 |  | 4.64
| Less openable DB | Sqm |  | -1 | 1.6 | 0.6 |  | -0.96
| LHS wall | Sqm |  | 1 | 2 | 2.9 |  | 5.8
| Total Qty in Sqm | [6 empty] | 18.5995
| Total Qty in Sqft | [5 empty] | 10.764 | 200.205
Previous bill Qty
| This Bill Qty | [6 empty] | 200.205